## REDACTED
SHADED INFORMATION IS DESIGNATED AS CONFIDENTIAL PER WAC 480-07-160
REDACTED Version

## COVER PROJECTS=>
MAJOR GAS & ELECTRIC CONSTRUCTION PROJECTS
The following pages contain information that is confidential and proprietary in nature and is marked “Shaded information is designated as confidential per WAC 480-07-160.”

## Baker Grouting (R)
ANNUAL BUDGET OF EXPENDITURES TO THE WASHINGTON
UTILITIES AND TRANSPORTATION COMMISSION
Budget Report for the Year
Utility Name: Puget Sound Energy |  | Ended December 31, 2025
STATE OF WASHINGTON
INDIVIDUAL MAJOR PROJECT CONSTRUCTION BUDGET
($'s in 000's)
Name of Project: | Lower Baker Grouting Program
Description of Project: | Part of Lower Baker Dam Capital Improvements program to meet our Federal Energy Regulatory Commission (FERC) 2008 license requirement. This project addresses seepage through the dam foundation and abutments that has increased over time. Changes in cost estimates over time are a reflection of a greater understanding of the project complexity and challenges while moving through design phases from conceptual design in 2013 to construction contract execution in 2021. Design features not fully captured in the earlier estimates include the extensive diving/marine work, time intensive down-stage grouting approach, implementation of a supplement grouting program (bitumen) to assist in seepage mitigation, and water management system necessary to satisfy WA Department of Ecology requirements. Other factors that contribute to the changes in cost estimates include yearly adjustments due to inflation and industry impacts due to the previous pandemic.
Location of Project: | Skagit County, Washington
Anticipated In Service Date:
Original Anticipated In Service Date: |  | REDACTED
Date Project Started:
Reason why project will be justified: | Compliance with the FERC license agreement.
Previous Estimate of Total Project Expenditures as Amended
Present Estimate of Total Project Expenditures
Amount of Expenditures Made Prior to Budget Year |  | REDACTED
Amount of Expenditures To Be Made in Budget Year
Anticipated Expenditures After Budget Year
SHADED INFORMATION IS DESIGNATED AS CONFIDENTIAL PER WAC 480-07-160
REDACTED

## Beaver Creek (R)
ANNUAL BUDGET OF EXPENDITURES TO THE WASHINGTON
UTILITIES AND TRANSPORTATION COMMISSION
Budget Report for the Year
Utility Name: Puget Sound Energy |  | Ended December 31, 2025
STATE OF WASHINGTON
INDIVIDUAL MAJOR PROJECT CONSTRUCTION BUDGET
($'s in 000's)
Name of Project: | Beaver Creek Wind Project
Description of Project: | Beaver Creek is a utility-scale wind development project currently under construction with an expected nameplate capacity of 248 MW. The project is located in eastern Montana and will interconnect to a new 230 kV substation on NorthWestern Energy’s system. In addition to the NorthWestern Energy transmission wheel, PSE will repurpose existing transmission on the Colstrip Transmission System currently used for Colstrip Units 3 and 4 to bring the power back to PSE’s system.
Location of Project: | Stillwater, Montana
Anticipated In Service Date:
Original Anticipated In Service Date: |  | REDACTED
Date Project Started:
Reason why project will be justified: | Project is part of a lowest reasonable cost portfolio of resources that help meet CETA clean energy targets in 2025 and 2030. Beaver Creek is the only new-build clean energy resource alternative that can help meet PSE’s interim CETA target in 2025.
Previous Estimate of Total Project Expenditures as Amended
Present Estimate of Total Project Expenditures
Amount of Expenditures Made Prior to Budget Year |  | REDACTED
Amount of Expenditures To Be Made in Budget Year
Anticipated Expenditures After Budget Year
SHADED INFORMATION IS DESIGNATED AS CONFIDENTIAL PER WAC 480-07-160
REDACTED

## Appaloosa (R)
ANNUAL BUDGET OF EXPENDITURES TO THE WASHINGTON
UTILITIES AND TRANSPORTATION COMMISSION
Budget Report for the Year
Utility Name: Puget Sound Energy |  | Ended December 31, 2025
STATE OF WASHINGTON
INDIVIDUAL MAJOR PROJECT CONSTRUCTION BUDGET
($'s in 000's)
Name of Project: | Appaloosa Solar Project
Description of Project: | Appaloosa is a well-developed, utility-scale solar project with an expected nameplate capacity of 142 MW. Construction of the project is expected to begin in Q2 2025. The project is located in Garfield County, Washington, in and around the existing and future phases of PSE’s Lower Snake River (LSR) wind farm. Appaloosa will interconnect to the existing 230 kV Phalen Gulch substation and can utilize LSR’s existing interconnection and transmission rights to deliver the power to PSE’s system.
Location of Project: | Pomeroy, Washington
Anticipated In Service Date:
Original Anticipated In Service Date: |  | REDACTED
Date Project Started:
Reason why project will be justified: | Project is part of a lowest reasonable cost portfolio of resources that help meet CETA clean energy targets in 2030.
Previous Estimate of Total Project Expenditures as Amended
Present Estimate of Total Project Expenditures
Amount of Expenditures Made Prior to Budget Year |  | REDACTED
Amount of Expenditures To Be Made in Budget Year
Anticipated Expenditures After Budget Year
SHADED INFORMATION IS DESIGNATED AS CONFIDENTIAL PER WAC 480-07-160
REDACTED

## CEIP Project (R)
ANNUAL BUDGET OF EXPENDITURES TO THE WASHINGTON
UTILITIES AND TRANSPORTATION COMMISSION
Budget Report for the Year
Utility Name: Puget Sound Energy |  | Ended December 31, 2025
STATE OF WASHINGTON
INDIVIDUAL MAJOR PROJECTS CONSTRUCTION BUDGET
($'s in 000's)
Name of Project: | CEIP Project
Description of Project: | Utility-scale project that is being sought under PSE's Clean Energy Implementation Plan ("CEIP") is being explored under PSE's resource planning function. The previous estimate provided contained costs for more than one project. Certain projects have now moved to time periods beyond this report and will be incorporated in future year's filings once they come back into the reporting period.
Location of Project: | Washington state
Anticipated In Service Date:
Original Anticipated In Service Date: |  | REDACTED
Date Project Started:
Reason why projects will be justified: | In order to meet it's Clean Energy Transformation Act targets, PSE will need to rely on a mix of clean resources which will include owned clean generation assets as detailed in its CEIP.
Previous Estimate of Total Project Expenditures as Amended
Present Estimate of Total Project Expenditures
Amount of Expenditures Made Prior to Budget Year |  | REDACTED
Amount of Expenditures To Be Made in Budget Year
Anticipated Expenditures After Budget Year
SHADED INFORMATION IS DESIGNATED AS CONFIDENTIAL PER WAC 480-07-160
REDACTED