## Summary Table
Wildfire Work Plan Analysis
This analysis compares a handful of examples of actual and planned units of work reported in the 2022 wildfire plan and estimated units of work based on actual and budgeted total and incremental wildfire program component costs. Click (+) sign along top or [2] to show David James' total and incremental program costs in this workbook.
David James Rev.
| 2026-08-06 | [13 empty] | By: Aaron Tam, Public Counsel Unit Regulatory Analyst
All Values in $000's
| Changes to WF2021 Baseline | Capital |  |  | Capital Budget Forecast | [13 empty] | Units of Work | [10 empty] | Cost ($000s)/Unit Calculations/Cross-check
Unit Estimates provided as part of WA GRC PC-305 | System & Transmission | 2022 Expected CAPx | 2020 YE Actuals | 2021 YE Actuals | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 10-yr | comments and notes | Wildfire Mitigation Component | Cost ($000's)/Unit | Cost ($/Unit) | Source | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 10-yr | 2021 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029
Internal Labor to Develop Computer Algorith (1.5 FTE) | Fire-Weather Dashboard | 0 | 197.75 | 188.7 | [8 empty] | 386.45 | 2020-2021 Development of FW Dashboard Version 1.0 and 2.0
Removed from WFRES Plan 2021 | Conforming Rights-of-Way | 0 |  | 0.372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.372 | Removed from plan August 2021. See WFRES 2022 for explanation
Maintenance followup. Budget allocation | Transmission Inspection Pgm | 200 | 1.272 | 0.808 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 1602.08 | CapX follow-up on Tx aerial and ground patrols related to fire ignition
Transmission Steel Replacement $45k per structure | Transmssion Steel Conversion | 4000 | 73.5668 | 5454.6 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 37528.1668 | See 2022 WFRES Plan for updated decision matrix on where wood pole will be converted to steel. Will be based on fire history on a go-forward basis. Not WUI | Transmission Steel Replacement | 45 | 45000 | PC DR 305 | 1.6348 | 121.2133 | 88.8889 | 88.8889 | 88.8889 | 88.8889 | 88.8889 | 88.8889 | 88.8889 | 88.8889 | 833.9593 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45
| Transmission Total | 4200 | 272.5888 | 5644.48 | 4200 | 4200 | 4200 | 4200 | 4200 | 4200 | 4200 | 4200 | 39517.0688 |  | Transmission Steel Replacement | 25 | 25000 | 2022 Wildfire Plan, p. 10 | 2.9427 | 218.184 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 1501.1267 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25
[15 empty] | Transmission Steel Replacement | 15 | 15000 | 2022 Wildfire Plan, p. 10 | 4.9045 | 363.64 | 266.6667 | 266.6667 | 266.6667 | 266.6667 | 266.6667 | 266.6667 | 266.6667 | 266.6667 | 2501.8778 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
[5 empty] | Capital Budget Forecast | [9 empty] | Actual Transmission Steel Replacement | ~$0.2-6.09 | ~$200-6,090 | 2022 Wildfire Plan, p. 12 | Units of Work 2020: 368; Units of Work 2021: 896; Units of Work 2022: 852 | 0.19991 | 6.0877 | 4.6948
| Electric Distribution | 2022 Expected CAPx | 2020 YE Actuals | 2021 YE Actuals | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 10-yr |  | Distribution Auto DLM | 60 | 60000 | PC DR 305 | 0.50888 | 22.59 | 12.5 | 10.8333 | 10.8333 | 10.8333 | 10.8333 | 10.8333 | 10.8333 | 10.8333 | 88.3333 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60
| Fire Ignition Tracking System | 0 | 2.505 | -2.5 | 0 | [7 empty] | 0.005 | OMT work around is allowing tracking for fire-ignition events. Any new development of fire ignition tracking will be paired with the OMS replacement project. | Actual Distribution Auto DLM | ~$20.83-20.85 | $20,830-20,850 | 2022 Wildfire Plan, p. 21 | Units of Work 2021: 65; Units of Work 2022: 36 |  | 20.8523 | 20.8333
$60k per unit. Midline reclosers | Distribution Auto DLM | 750 | 30.533 | 1355.4 | 750 | 650 | 650 | 650 | 650 | 650 | 650 | 650 | 6685.933 | Replacing midline reclosers with DLM Automation devices. | Substation Auto DLM | 750 | 750000 | PC DR 305 | 0.00053333 | 0.68627 | 2 | 2 | 4 | 6 | 6 | 6 | 6 | 6 | 38 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750
$750k per substation. Add SCADA comm and equipment | Substation Auto DLM | 1500 | 0.4 | 514.7 | 1500 | 1500 | 3000 | 4500 | 4500 | 4500 | 4500 | 4500 | 29015.1 |  | Substation Auto DLM Goals | ~$300-900 | $300,000-900,000 | 2022 Wildfire Plan, p. 21 | 0.00053333 | 1 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 41.0005 | 750 | 514.7 | 300 | 300 | 600 | 900 | 900 | 900 | 900 | 900
$16k per mile. Advance 1,500 line miles into 2022-2029 | WPM Make-Ready for GH (XD007) | 3000 |  | 14.6 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 24014.6 |  | Transmission Wood Pole Wraps | 0.09 | 90 | PC DR 305 and 2022 Wildfire Plan, p. 10 | 1980.3533 | 4675.7778 | 6111.1111 | 6111.1111 | 6111.1111 | 6111.1111 | 6111.1111 | 6111.1111 | 6111.1111 | 6111.1111 | 48888.8889 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09
Placeholder | OE Sponsored GH (XD008) |  |  | 1.28 | [10 empty] | Actual Transmission Wood Pole Wraps | ~$0.14-0.34 | $140-340 | 2022 Wildfire Plan, p. 13 | Units of Work 2020: 1235; Units of Work 2021: 1938; Units of Work 2022: 1600 | 0.14432 | 0.21714 | 0.34375
$60k per mile. | WA Dist Grid Hardening (XD005) | 9000 | 1513.27 | 7133.8 | 9000 | 11500 | 12500 | 14700 | 14700 | 14700 | 14700 | 14700 | 115147.07
$60k per mile. | ID Dist Grid Hardening (XD006) | 6595 | 1601.649 | 4714.1 | 6595 | 6650 | 7650 | 7820 | 7820 | 8400 | 8400 | 8400 | 68050.749
| Distribution Total | 20845 | 3148.357 | 13731.38 | 20845 | 23300 | 26800 | 30670 | 30670 | 31250 | 31250 | 31250 | 242913.457
| T&D CapX Total | 25045 | 3420.9458 | 19375.86 | 25045 | 27500 | 31000 | 34870 | 34870 | 35450 | 35450 | 35450 | 282430.5258
|  |  | Total Grid Hardening: |  | PLAN
| Distribution |  | 2020 act | 2021 act | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | Totals
| Grid Hardening Budget |  | 3114.919 | 11847.9 | 15595 | 18150 | 20150 | 22520 | 22520 | 23100 | 23100 | 23100 | 183197.819
| Miles Projected at $60k/mi (forecast) |  | 66.5 | 146 | 259.9167 | 302.5 | 335.8333 | 375.3333 | 375.3333 | 385 | 385 | 385
| Cumulative Miles |  | 66.5 | 212.5 | 472.4167 | 774.9167 | 1110.75 | 1486.0833 | 1861.4167 | 2246.4167 | 2631.4167 | 3016.4167
|  | Operating |  |  | PLAN 2022: O&M Budget Forecast
| System & Transmission | 2022 Expected O&M | 2020 YE Actual | 2021 YE Actual | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 10-yr
Internal unloaded WF labor 33% (4 FTE) | WFRES Transmission Planning | 147 | 91.927 | 187.49 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 1455.417 | WFRES Team Labor based on 2021 HC
Subscription to Weather data service | Fire-Weather Dashboard | 150 |  | 0 | 150 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 675 | On going support of FW DB
$400 per mile. 1875 miles non-urban transmission | Digital Data Collection (Geo Digital) | 750 | 491.4217 | 450 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 6941.4217 | Based on $450mile (GeoDigital)- 2022 is full system
$90 per pole wrap | Transmission FR Pole Wraps | 550 | 178.2318 | 420.82 | 550 | 550 | 550 | 550 | 550 | 550 | 550 | 550 | 4999.0518 | Genic fire mesh $90/pole (assume H-frame $500/structure 500 structures/year - 8 structure/miles - 62.5 miles/year)
$2k per acre treated | Fuel Reduction Partner | 300 |  | 0 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 2400 | Estimated from WS. ~ $1k per acre
2021 only | Nox-PC Fire Damage (risk tree) |  |  | 513.13 | O&M Budget Forecast 10-yr: 513.13
$2000 per hour helicopter resource | Transmission Inspection Pgm | 150 | 137.372 | 172.047 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 1509.419 | Transmission Fire Inspection and O&M followup
| Transmission O&M | 2047 | 898.9525 | 1743.487 | 2047 | 1972 | 1972 | 1972 | 1972 | 1972 | 1972 | 1972 | 18493.4395
|  |  | Operating |  | O&M Budget Forecast 2022: O&M Budget Forecast
| Electric Distribution | 2022 Expected O&M | 2020 YE Actual | 2021 YE Actual | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 10-yr
Internal unloaded WF Labor 67% (4 FTE) | WFRES Distribution Planning | 294 | 232.53 | 269.06 | 294 | 294 | 294 | 294 | 294 | 294 | 294 | 294 | 2853.59 | WFRES Team Labor based on 2021 HC
$915 per tree removal | WA Dx Risk Tree | 5543.7 |  | 2110.68 | 3686.1 | 3231.5 | 3232 | 2688 | 2688 | 2688 | 2688 | 2688 | 25700.28
$915 per tree removal | ID Dx Risk Tree | 2856 | 1239.1134 | 3151.935 | 1898.9 | 1818 | 1818 | 1512 | 1512 | 1512 | 1512 | 1512 | 17485.9484 | Estimate from AM C H. 100% system minus heavy incorporated and no veg areas (17%). 11.02.21
$5k per household | Customer Choice RTRP | 350 |  | 0 | 350 | 500 | 750 | 750 | 750 | 500 | 300 | 200 | 4100 | Includes Public Outreach, Media messaging, and voucher remove/replace program
$70 per mile | Digital Data Collection (AiDASH) | 535 | 59.2817 | 327.211 | 535 | 535 | 535 | 535 | 535 | 535 | 535 | 535 | 4666.4927 | Based on AiDash Contract --- 70$/miles for 7650 miles OH System (535 base, 2021 reflects a negotiated price to establish baseline)
| Distribution O&M | 9578.7 | 1530.9251 | 5858.886 | 6764 | 6378.5 | 6629 | 5779 | 5779 | 5529 | 5329 | 5229 | 54806.3111 | Dx Grid Hardening Blended WA/ID Rate = $59.1k/mile
| T&D O&M | 11625.7 | 2429.8776 | 7602.373 | 8811 | 8350.5 | 8601 | 7751 | 7751 | 7501 | 7301 | 7201 | 73299.7506
Total Risk Tree
TOTAL
Note on D40: James, Dave: reallocated 150 to 2021-2029 due to COVID work restrictions
Note on F49: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Reflects 100% risk tree @ 950/mille X 5500 of treed miles
Note on W14: Tam, Aaron (ATG): Target
Note on W16: Tam, Aaron (ATG): Target
Note on W20: Tam, Aaron (ATG): Target