## 2024 Provisional Plant
Cascade Natural Gas Corp.
Docket UG-240008
2024 Provisional Plant Review
| Line No. | Project/Portfolio Review | Witness | Testimony Reference | Funding Project | Description | FERC Account No. | WA 2024 Authorized Cost | Closed to Plant (Month/Year) | WA Actual 2024 Cost | WA Actual Cost - Cumulative Rate Effective Period | $ Variance - Actual vs Settlement | % Variance - Actual vs Settlement | Signif. Cost Variance - $500k or 10% | Signif. Cost Overrun | Identified In 2023 IRP (Docket UG-220131) | Allowed Cost in 2024 Rate Base
Index |  | (A) | (B) | (C) | (D) | (E) | (F) | (G) | (H) | (I) | (J) | (K) | (L) | (M) | (N) | (O) | (P)
A | 1 | Project Review | Gilchrist | Exh-HG-1T-3-29-24 | FP-101480 | UG-Work Asset Management (2024) | 303 | 3980874.5233 | 2024/03 | 3643178.61 | 3643178.61 | -337695.9133 | -8.483% | - | - | - | 3643178.61
A | 2 | Project Review | Darras | Exh-PCD-1T-3-29-24 | FP-316046 | C/M RPL; 8" HP; YAKIMA; PH1 | 376.2 | 3037182.6014 |  | 0 | 0 | -3037182.6014 | -100% | Yes | - | - | 0
A | 3 | Project Review | Darras | Exh-PCD-1T-3-29-24 | FP-318186 | Sys Safety & Integrity Mains Rpl-WA | 376.3 | 3504094.9597 | 2024/11 | 6818341.85 | 6818341.85 | 3314246.8903 | 94.58% | Yes | Yes | - | 3504094.9597
A | 4 | Project Review | Darras | Exh-PCD-1T-3-29-24 | FP-318187 | Sys Safety & Integrity Srvcs Rpl-WA | 380.3 | 3511692.4775 | 2024/11 | 1483151.38 | 1483151.38 | -2028541.0975 | -57.77% | Yes | - | - | 1483151.38
A | 5 | Project Review | Darras | Exh-PCD-1T-3-29-24 | FP-319057 | RF-S. KENN TBS-CNGC | 378 | 1901518.06 |  | 0 | 0 | -1901518.06 | -100% | Yes | - | Appendix I, Page 9 | 0
A | 6 | Project Review | Darras | Exh-PCD-1T-3-29-24 | FP-319061 | RF-8" PE-KENN-2,500' | 376.3 | 2258569 |  | 0 | 0 | -2258569 | -100% | Yes | - | Appendix I, Page 9 | 0
A | 7 | Project Review | Darras | Exh-PCD-1T-3-29-24 | FP-319111 | MAOP MAIN RPL CNG WA | 376.3 | 3610320.72 |  | 0 | 0 | -3610320.72 | -100% | Yes | - | - | 0
A | 8 | Project Review | Darras | Exh-PCD-1T-3-29-24 | FP-320034 | RF; S. KENN GATE-WILLIAMS | 303 | 3016751.45 |  | 0 | 0 | -3016751.45 | -100% | Yes | - | Appendix I, Page 9 | 0
A | 9 | Project Review | Darras | Exh-PCD-1T-3-29-24 | FP-321116 | RP; 4" HP, WAPATO, 31,000' | 376.2 | 16645248.84 | 2024/12 | 17471256.21 | 17471256.21 | 826007.37 | 4.962% | Yes | Yes | Appendix I, Page 17 | 16645248.84
AA | 10 | (A): Total Project Review; (D): Total; (G): 41466252.632; (I): 29415928.05; (J): 29415928.05; (K): -12050324.582; (P): 25275673.7897
AB | 11
B | 12 | Portfolio Review | Gilchrist | Exh-HG-1T-3-29-24 | Capital Lease | Locus View Lease | 397.4 | 398580.42 | 2024/02 | 398580.42 | 398580.42 | 0 | 0% | - | - | - | 398580.42
B | 13 | Portfolio Review | Martuscelli | Exh-EPM-1T-3-29-24 | FP-101163 | Gas Work Equipment-CNGC | 396.2 | 2463904.4573 | 2024/12 | 1493405.45 | 1493405.45 | -970499.0073 | -39.39% | Yes | - | - | 1493405.45
B | 14 | Portfolio Review | Martuscelli | Exh-EPM-4-3-29-24 | FP-101164 | IT Network Equipment-CNG | 397.2 | 87401.4937 | 2024/12 | 60573.86 | 60573.86 | -26827.6337 | -30.69% | Yes | - | - | 60573.86
B | 15 | Portfolio Review | Martuscelli | Exh-EPM-1T-3-29-24 | FP-101190 | MAIN-GROWTH-WASHINGTON | 376 | -2677.37 | 2024/06 | -2677.37 | -2677.37 | 0 | 0% | - | - | - | -2677.37
B | 16 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-101194 | Dist Reg Station Growth Washington | 378 | 242320 | 2024/12 | 34230.49 | 34230.49 | -208089.51 | -85.87% | Yes | - | - | 34230.49
B | 17 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-101196 | Dist Reg Station Replace Washington | 378 | 498617.4188 | 2024/12 | 727679.97 | 727679.97 | 229062.5512 | 45.94% | Yes | Yes | - | 727679.97
B | 18 | Portfolio Review | Martuscelli | Exh-EPM-1T-3-29-24 | FP-101210 | Gas Meters-Total Company CNGC | 381 | 5937987.0246 | 2024/12 | 3564813.78 | 3564813.78 | -2373173.2446 | -39.97% | Yes | - | - | 3564813.78
B | 19 | Portfolio Review | Martuscelli | Exh-EPM-1T-3-29-24 | FP-101215 | Gas Vehicles-CNGC | 392.2 | 1060664.9308 | 2024/12 | 896387.9 | 896387.9 | -164277.0308 | -15.49% | Yes | - | - | 896387.9
B | 20 | Portfolio Review | Martuscelli | Exh-EPM-4-3-29-24 | FP-101259 | Gas Regulators-Total Company CNGC | 383 | 547264.6996 | 2024/12 | 592019.65 | 592019.65 | 44754.9504 | 8.178% | - | - | - | 592019.65
B | 21 | Portfolio Review | Tillis | Exh-DLT-13-3-29-24 | FP-200064 | UG-Customer Self Service Web/IVRCNG | 303 | 148544.6649 | 2024/12 | 121468.21 | 121468.21 | -27076.4549 | -18.23% | Yes | - | - | 121468.21
B | 22 | Portfolio Review | Martuscelli | Exh-EPM-4-3-29-24 | FP-200662 | Personal Computers&Peripherals CNGC | 391.3 | 113444.0048 | 2024/12 | 68901.78 | 68901.78 | -44542.2248 | -39.26% | Yes | - | - | 68901.78
B | 23 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-302369 | Gas Cathodic Protection - WA | 376.1 | 602782.14 | 2024/12 | 75004.26 | 75004.26 | -527777.88 | -87.56% | Yes | - | - | 75004.26
B | 24 | Portfolio Review | Darras | Exh-PCD-1T-3-29-24 | FP-316018 | C/M RPL; 2/4" HP; WHEELER; 7,500' | 376.2 | 2430742.775 | 2024/02 | 2933026 | 2933026 | 502283.225 | 20.66% | Yes | Yes | - | 2933026
B | 25 | Portfolio Review | Darras |  | FP-316031 | C/M RPL; 3" HP; S TOPPENISH; 6,161' | 376 | -24677.12 | 2024/02 | -24677.12 | -24677.12 | 0 | 0% | - | - | - | -24677.12
B | 26 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-316032 | C/M RPL; 2/3" HP; SUNNYSIDE; 8,612' | 376.2 | 427000 | 2024/01 | 434558.1 | 434558.1 | 7558.1 | 1.77% | - | - | - | 434558.1
B | 27 | Portfolio Review | Darras |  | FP-316044 | C/M RPL; 8" HP; BREMERTON; 4,510' | 376 | 3207.56 | 2024/01 | 3207.56 | 3207.56 | 0 | 0% | - | - | - | 3207.56
B | 28 | Portfolio Review | Darras | Exh-PCD-1T-3-29-24 | FP-316406 | RP; 8" HP ST; BREMRTN, 500' EXPOSD | 376 | 22281.93 | 2024/03 | 22345.96 | 22345.96 | 64.03 | 0.2874% | - | - | - | 22345.96
B | 29 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-316429 | RF; 8" HP; ABER; 12,500' BASICH BLV | 376.2 | 750000 | 2024/06 | 1089143.22 | 1089143.22 | 339143.22 | 45.22% | Yes | Yes | Appendix I, Page 33 | 1089143.22
B | 30 | Portfolio Review | Martuscelli | Exh-EPM-4-3-29-24 | FP-316445 | Toughbook Replacements-CNG | 391.3 | 139476.6668 | 2024/12 | 111863.98 | 111863.98 | -27612.6868 | -19.8% | Yes | - | - | 111863.98
B | 31 | Portfolio Review | Boese | Exh-HG-3-3-29-24 | FP-316451 | UG-PCAD Annual Enhancements-CNG | 303 | 109304.1271 |  | 0 | 0 | -109304.1271 | -100% | Yes | - | - | 0
B | 32 | Portfolio Review | Martuscelli | Exh-EPM-4-3-29-24 | FP-316832 | Office Structure & Eq-Kennewick GO | 391.5 | 97895.8512 | 2024/09 | 5778.75 | 5778.75 | -92117.1012 | -94.1% | Yes | - | - | 5778.75
B | 33 | Portfolio Review | Darras | Exh-PCD-1T-3-29-24 | FP-316980 | UPGRADE YAKIMA GATE STATION | 379 | 42890.19 | 2024/01 | 45153.6 | 45153.6 | 2263.41 | 5.277% | - | - | - | 45153.6
B | 34 | Portfolio Review | Darras | Exh-PCD-1T-3-29-24 | FP-317064 | RF; 6" PE; BELL; 6,700' Fraser St | 376 | 297108.61 | 2024/01 | 297108.61 | 297108.61 | 0 | 0% | - | - | - | 297108.61
B | 35 | Portfolio Review | Darras | Exh-PCD-1T-3-29-24 | FP-317065 | RP; 6" HP; BELL; 2500'; Meador Ave | 376 | 148928.12 | 2024/01 | 148928.12 | 148928.12 | 0 | 0% | - | - | Appendix I, Page 25 | 148928.12
B | 36 | Portfolio Review | Boese | Exh-HG-1T-3-29-24 | FP-317565 | Impl Work Asset Mgmt Hardware-CNG | 391.3 | 136058.75 |  | 0 | 0 | -136058.75 | -100% | Yes | - | - | 0
B | 37 | Portfolio Review | Darras |  | FP-317609 | GR; R-81 ABER; BASICH BLV | 378 | 26244.81 | 2024/01 | 26320.24 | 26320.24 | 75.43 | 0.2874% | - | - | - | 26320.24
B | 38 | Portfolio Review | Martuscelli | Exh-EPM-1T-3-29-24 | FP-317628 | MAIN-GROWTH-WALLA WALLA DISTRICT | 376.3 | 87598.68 | 2024/12 | 65680.24 | 65680.24 | -21918.44 | -25.02% | Yes | - | - | 65680.24
B | 39 | Portfolio Review | Martuscelli | Exh-EPM-1T-3-29-24 | FP-317629 | MAIN-REPLACE-WALLA WALLA DISTRICT | 376.3 | 260834.3778 | 2024/12 | 85626.07 | 85626.07 | -175208.3078 | -67.17% | Yes | - | - | 85626.07
B | 40 | Portfolio Review | Martuscelli | Exh-EPM-1T-3-29-24 | FP-317630 | SERV-GROWTH-WALLA WALLA DISTRICT | 380.3 | 432802.92 | 2024/12 | 233367.5 | 233367.5 | -199435.42 | -46.08% | Yes | - | - | 233367.5
B | 41 | Portfolio Review | Martuscelli | Exh-EPM-1T-3-29-24 | FP-317631 | SERV-REPLACE-WALLA WALLA DISTRICT | 380.3 | 230492.4405 | 2024/12 | 160333.56 | 160333.56 | -70158.8805 | -30.44% | Yes | - | - | 160333.56
B | 42 | Portfolio Review | Martuscelli | Exh-EPM-1T-3-29-24 | FP-317632 | MAIN-GROWTH-WENATCHEE DISTRICT | 376.3 | 14539.2 | 2024/12 | -13905.75 | -13905.75 | -28444.95 | -195.6% | Yes | - | - | -13905.75
B | 43 | Portfolio Review | Martuscelli | Exh-EPM-1T-3-29-24 | FP-317633 | MAIN-REPLACE-WENATCHEE DISTRICT | 376.3 | 19699.3514 | 2024/12 | 359.68 | 359.68 | -19339.6714 | -98.17% | Yes | - | - | 359.68
B | 44 | Portfolio Review | Martuscelli | Exh-EPM-1T-3-29-24 | FP-317634 | SERV-GROWTH-WENATCHEE DISTRICT | 380.3 | 54194.89 | 2024/12 | 69813.18 | 69813.18 | 15618.29 | 28.82% | Yes | Yes | - | 69813.18
B | 45 | Portfolio Review | Martuscelli | Exh-EPM-1T-3-29-24 | FP-317635 | SERV-REPLACE-WENATCHEE DISTRICT | 380.3 | 64673.6378 | 2024/12 | 6819.37 | 6819.37 | -57854.2678 | -89.46% | Yes | - | - | 6819.37
B | 46 | Portfolio Review | Martuscelli | Exh-EPM-1T-3-29-24 | FP-317636 | MAIN-GROWTH-YAKIMA DISTRICT | 376.3 | 102137.88 | 2024/12 | 140580.86 | 140580.86 | 38442.98 | 37.64% | Yes | Yes | - | 140580.86
B | 47 | Portfolio Review | Martuscelli | Exh-EPM-1T-3-29-24 | FP-317637 | MAIN-REPLACE-YAKIMA DISTRICT | 376.3 | 183118.1512 | 2024/12 | 26761.99 | 26761.99 | -156356.1612 | -85.39% | Yes | - | - | 26761.99
B | 48 | Portfolio Review | Martuscelli | Exh-EPM-1T-3-29-24 | FP-317638 | SERV-GROWTH-YAKIMA DISTRICT | 380.3 | 674851.56 | 2024/12 | 462772.16 | 462772.16 | -212079.4 | -31.43% | Yes | - | - | 462772.16
B | 49 | Portfolio Review | Martuscelli | Exh-EPM-1T-3-29-24 | FP-317639 | SERV-REPLACE-YAKIMA DISTRICT | 380.3 | 315682.8552 | 2024/12 | 11258.51 | 11258.51 | -304424.3452 | -96.43% | Yes | - | - | 11258.51
B | 50 | Portfolio Review | Martuscelli | Exh-EPM-1T-3-29-24 | FP-317640 | MAIN-GROWTH-ABERDEEN DISTRICT | 376.3 | 167040.84 | 2024/12 | 1587.5 | 1587.5 | -165453.34 | -99.05% | Yes | - | - | 1587.5
B | 51 | Portfolio Review | Martuscelli | Exh-EPM-1T-3-29-24 | FP-317641 | MAIN-REPLACE-ABERDEEN DISTRICT | 376.3 | 53179.9536 | 2024/12 | 29809.43 | 29809.43 | -23370.5236 | -43.95% | Yes | - | - | 29809.43
B | 52 | Portfolio Review | Martuscelli | Exh-EPM-1T-3-29-24 | FP-317642 | SERV-GROWTH-ABERDEEN DISTRICT | 380.3 | 266465.96 | 2024/12 | 210481.64 | 210481.64 | -55984.32 | -21.01% | Yes | - | - | 210481.64
B | 53 | Portfolio Review | Martuscelli | Exh-EPM-1T-3-29-24 | FP-317643 | SERV-REPLACE-ABERDEEN DISTRICT | 380.3 | 282029.4444 | 2024/12 | 15031.6 | 15031.6 | -266997.8444 | -94.67% | Yes | - | - | 15031.6
B | 54 | Portfolio Review | Martuscelli | Exh-EPM-1T-3-29-24 | FP-317644 | MAIN-GROWTH-BELLINGHAM DISTRICT | 376.3 | 808875.54 | 2024/12 | 129412.29 | 129412.29 | -679463.25 | -84% | Yes | - | - | 129412.29
B | 55 | Portfolio Review | Martuscelli | Exh-EPM-1T-3-29-24 | FP-317645 | MAIN-REPLACE-BELLINGHAM DISTRICT | 376.3 | 386986.5082 | 2024/12 | 250431.08 | 250431.08 | -136555.4282 | -35.29% | Yes | - | - | 250431.08
B | 56 | Portfolio Review | Martuscelli | Exh-EPM-1T-3-29-24 | FP-317646 | SERV-GROWTH-BELLINGHAM DISTRICT | 380.3 | 1278711.49 | 2024/12 | 813234.75 | 813234.75 | -465476.74 | -36.4% | Yes | - | - | 813234.75
B | 57 | Portfolio Review | Martuscelli | Exh-EPM-1T-3-29-24 | FP-317647 | SERV-REPLACE-BELLINGHAM DISTRICT | 380.3 | 338345.2871 | 2024/12 | 131757.91 | 131757.91 | -206587.3771 | -61.06% | Yes | - | - | 131757.91
B | 58 | Portfolio Review | Martuscelli | Exh-EPM-1T-3-29-24 | FP-317648 | MAIN-GROWTH-BREMERTON DISTRICT | 376.3 | 910308.31 | 2024/12 | 256081.35 | 256081.35 | -654226.96 | -71.87% | Yes | - | - | 256081.35
B | 59 | Portfolio Review | Martuscelli | Exh-EPM-1T-3-29-24 | FP-317649 | MAIN-REPLACE-BREMERTON DISTRICT | 376.3 | 209100.0978 | 2024/12 | -13895.34 | -13895.34 | -222995.4378 | -106.6% | Yes | - | - | -13895.34
B | 60 | Portfolio Review | Martuscelli | Exh-EPM-1T-3-29-24 | FP-317650 | SERV-GROWTH-BREMERTON DISTRICT | 380.3 | 1179967.52 | 2024/12 | 1660822.13 | 1660822.13 | 480854.61 | 40.75% | Yes | Yes | - | 1660822.13
B | 61 | Portfolio Review | Martuscelli | Exh-EPM-1T-3-29-24 | FP-317651 | SERV-REPLACE-BREMERTON DISTRICT | 380.3 | 127046.5833 | 2024/12 | 7239.87 | 7239.87 | -119806.7133 | -94.3% | Yes | - | - | 7239.87
B | 62 | Portfolio Review | Martuscelli | Exh-EPM-1T-3-29-24 | FP-317652 | MAIN-GROWTH-LONGVIEW DISTRICT | 376.3 | 6249.81 | 2024/12 | 97870.67 | 97870.67 | 91620.86 | 1466% | Yes | Yes | - | 97870.67
B | 63 | Portfolio Review | Martuscelli | Exh-EPM-1T-3-29-24 | FP-317653 | MAIN-REPLACE-LONGVIEW DISTRICT | 376.3 | 294068.292 | 2024/12 | 125805.92 | 125805.92 | -168262.372 | -57.22% | Yes | - | - | 125805.92
B | 64 | Portfolio Review | Martuscelli | Exh-EPM-1T-3-29-24 | FP-317654 | SERV-GROWTH-LONGVIEW DISTRICT | 380.3 | 344511.17 | 2024/12 | 377482.84 | 377482.84 | 32971.67 | 9.571% | - | - | - | 377482.84
B | 65 | Portfolio Review | Martuscelli | Exh-EPM-1T-3-29-24 | FP-317655 | SERV-REPLACE-LONGVIEW DISTRICT | 380.3 | 100146.05 | 2024/12 | 4333.09 | 4333.09 | -95812.96 | -95.67% | Yes | - | - | 4333.09
B | 66 | Portfolio Review | Martuscelli | Exh-EPM-1T-3-29-24 | FP-317656 | MAIN-GROWTH-MT VERNON DISTRICT | 376.3 | 502438.19 | 2024/12 | 76485.48 | 76485.48 | -425952.71 | -84.78% | Yes | - | - | 76485.48
B | 67 | Portfolio Review | Martuscelli | Exh-EPM-1T-3-29-24 | FP-317657 | MAIN-REPLACE-MT VERNON DISTRICT | 376.3 | 270192.0796 | 2024/12 | 143756.74 | 143756.74 | -126435.3396 | -46.79% | Yes | - | - | 143756.74
B | 68 | Portfolio Review | Martuscelli | Exh-EPM-1T-3-29-24 | FP-317658 | SERV-GROWTH-MT VERNON DISTRICT | 380.3 | 1103684.1 | 2024/12 | 917933.96 | 917933.96 | -185750.14 | -16.83% | Yes | - | - | 917933.96
B | 69 | Portfolio Review | Martuscelli | Exh-EPM-1T-3-29-24 | FP-317659 | SERV-REPLACE-MT VERNON DISTRICT | 380.3 | 231192.584 | 2024/12 | 61431.03 | 61431.03 | -169761.554 | -73.43% | Yes | - | - | 61431.03
B | 70 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-317744 | Tools & Minor Work Equip CNG WA | 394.1 | 163538.84 | 2024/07 | 40625.55 | 40625.55 | -122913.29 | -75.16% | Yes | - | - | 40625.55
B | 71 | Portfolio Review | Martuscelli | Exh-EPM-1T-3-29-24 | FP-317750 | MAIN-GROWTH-KENNEWICK DISTRICT | 376.3 | 1222711.99 | 2024/12 | 933263.28 | 933263.28 | -289448.71 | -23.67% | Yes | - | - | 933263.28
B | 72 | Portfolio Review | Martuscelli | Exh-EPM-1T-3-29-24 | FP-317751 | MAIN-REPLACE-KENNEWICK DISTRICT | 376.3 | 121240.8331 | 2024/12 | 50078.88 | 50078.88 | -71161.9531 | -58.69% | Yes | - | - | 50078.88
B | 73 | Portfolio Review | Martuscelli | Exh-EPM-1T-3-29-24 | FP-317752 | SERV-GROWTH-KENNEWICK DISTRICT | 380.3 | 1692514.27 | 2024/12 | 1434558.88 | 1434558.88 | -257955.39 | -15.24% | Yes | - | - | 1434558.88
B | 74 | Portfolio Review | Martuscelli | Exh-EPM-1T-3-29-24 | FP-317753 | SERV-REPLACE-KENNEWICK DISTRICT | 380.3 | 88759.2694 |  | 0 | 0 | -88759.2694 | -100% | Yes | - | - | 0
B | 75 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-318092 | HPSS Replacements CNG WA | 376.3 | 111603.3048 | 2024/02 | 41537.53 | 41537.53 | -70065.7748 | -62.78% | Yes | - | - | 41537.53
B | 76 | Portfolio Review | Darras | Exh-PCD-1T-3-29-24 | FP-318192 | Fixed Network Equipment-CNG | 397.2 | 1387227.5384 | 2024/12 | 269043.69 | 269043.69 | -1118183.8484 | -80.61% | Yes | - | - | 269043.69
B | 77 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-318197 | Gas SCADA Equipment-CNG | 397.2 | 52022.1813 | 2024/03 | 32650.5 | 32650.5 | -19371.6813 | -37.24% | Yes | - | - | 32650.5
B | 78 | Portfolio Review | Martuscelli | Exh-EPM-4-3-29-24 | FP-318211 | Communications Equipment CNG | 397.2 | 72377.089 | 2024/10 | 54793.87 | 54793.87 | -17583.219 | -24.29% | Yes | - | - | 54793.87
B | 79 | Portfolio Review | Darras |  | FP-318566 | RP-Brem-R-Werener&Twin View R-21 | 378 | 3845.46 | 2024/03 | 3856.51 | 3856.51 | 11.05 | 0.2874% | - | - | - | 3856.51
B | 80 | Portfolio Review | Darras | Exh-PCD-1T-3-29-24 | FP-318656 | RF-OAKH-4"PE-2.1MI | 376.3 | 1403134.75 | 2024/07 | 1099492.23 | 1099492.23 | -303642.52 | -21.64% | Yes | - | - | 1099492.23
B | 81 | Portfolio Review | Darras | Exh-PCD-1T-3-29-24 | FP-318740 | RF-Walla-8800ft 6"PE Cottonwood Rd | 376 | -63.6 | 2024/01 | -63.6 | -63.6 | 0 | 0% | - | - | - | -63.6
B | 82 | Portfolio Review | Darras | Exh-PCD-1T-3-29-24 | FP-318800 | Longview S. Gate Upgrade - CNG Side | 379 | -322.59 | 2024/02 | -322.59 | -322.59 | 0 | 0% | - | - | - | -322.59
B | 83 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-319027 | RP-Topp-TM-Canal Crossings | 367.1 | 533956.2182 |  | 0 | 0 | -533956.2182 | -100% | Yes | - | - | 0
B | 84 | Portfolio Review | Darras |  | FP-319029 | RP-MTVE-MTR-N TEXAS RD | 385 | 45815.19 | 2024/04 | 33632.09 | 33632.09 | -12183.1 | -26.59% | Yes | - | - | 33632.09
B | 85 | Portfolio Review | Darras | Exh-PCD-1T-3-29-24 | FP-319055 | RF; 12" & 6" HP; RICH; 3.3 mi | 376 | 175039.2 | 2024/01 | 175039.2 | 175039.2 | 0 | 0% | - | - | - | 175039.2
B | 86 | Portfolio Review | Darras | Exh-PCD-1T-3-29-24 | FP-319112 | MAOP SERV RPL CNG WA | 380.3 | 375340.572 | 2024/03 | 49044.42 | 49044.42 | -326296.152 | -86.93% | Yes | - | - | 49044.42
B | 87 | Portfolio Review | Darras |  | FP-319839 | Dischrge Coalescnt Filtr-BURL COMP | 377 | 27618.03 | 2024/01 | 27697.39 | 27697.39 | 79.36 | 0.2873% | - | - | - | 27697.39
B | 88 | Portfolio Review | Darras | Exh-PCD-1T-3-29-24 | FP-320004 | C/M RPL; 3" HP; PROSSER; 1,500' | 376.2 | 1069397.6492 |  | 0 | 0 | -1069397.6492 | -100% | Yes | - | - | 0
B | 89 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-320006 | C/M RPL; 3" HP; BURLINGTON; 410' | 376.2 | 930867.846 |  | 0 | 0 | -930867.846 | -100% | Yes | - | - | 0
B | 90 | Portfolio Review | Darras | Exh-PCD-1T-3-29-24 | FP-320007 | MAOP; 16" TM; MARCH POINT; 20' | 367 | 115.01 | 2024/02 | 114.79 | 114.79 | -0.22 | -0.1913% | - | - | - | 114.79
B | 91 | Portfolio Review | Darras | Exh-PCD-1T-3-29-24 | FP-320106 | GR-BurlingtonSouthFeed-6"PE-DP | 376.2 | 1829249.22 |  | 0 | 0 | -1829249.22 | -100% | Yes | - | Appendix I, Page 21 | 0
B | 92 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-320114 | R-21 Replacement - Castle Rock | 378 | 240690.4327 |  | 0 | 0 | -240690.4327 | -100% | Yes | - | - | 0
B | 93 | Portfolio Review | Darras |  | FP-320161 | RF-RICH R-133 | 378 | 13898.34 | 2024/01 | 13938.28 | 13938.28 | 39.94 | 0.2874% | - | - | - | 13938.28
B | 94 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-320223 | Indust Reg Stations-Growth-CNGC WA | 385 | 63609 |  | 0 | 0 | -63609 | -100% | Yes | - | - | 0
B | 95 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-320224 | Indust Reg Stations-Replace-CNGC WA | 385 | 60676.6251 | 2024/02 | 4212.48 | 4212.48 | -56464.1451 | -93.06% | Yes | - | - | 4212.48
B | 96 | Portfolio Review | Darras |  | FP-320486 | C/M; 12" HP; LONG; 1,220' WESTROCK | 376 | 61497.13 | 2024/02 | 61497.13 | 61497.13 | 0 | 0% | - | - | - | 61497.13
B | 97 | Portfolio Review | Gilchrist | Exh-HG-3-3-29-24 | FP-320934 | PUR Trng Props Bremerton WA Trl. | 394.1 | 16945.67 | 2024/12 | 19814.57 | 19814.57 | 2868.9 | 16.93% | Yes | Yes | - | 19814.57
B | 98 | Portfolio Review | Gilchrist | Exh-HG-3-3-29-24 | FP-320935 | PUR Trng Props Kennewick Wa Trlr | 394.1 | 14987.11 |  | 0 | 0 | -14987.11 | -100% | Yes | - | - | 0
B | 99 | Portfolio Review | Martuscelli | Exh-EPM-4-3-29-24 | FP-320999 | UG ThoughtSpot Betterment CNG | 303 | 44563.4363 | 2024/12 | 38077.89 | 38077.89 | -6485.5463 | -14.55% | Yes | - | - | 38077.89
B | 100 | Portfolio Review | Darras |  | FP-321243 | C/M RPL; 8" HP; WALLA WALLA; 4,595' | 376 | -48387.11 | 2024/01 | -49144.12 | -49144.12 | -757.01 | 1.564% | - | - | - | -49144.12
B | 101 | Portfolio Review | Nygard | Exh-TJN-3-3-29-24 | FP-321327 | UG - CC&B Upgrade&Betterments CNGC | 303 | 395808.6544 | 2024/12 | 294221.67 | 294221.67 | -101586.9844 | -25.67% | Yes | - | - | 294221.67
B | 102 | Portfolio Review | Darras | Exh-PCD-1T-3-29-24 | FP-321468 | C/M RPL; 6" HP TOPP-ZILLAH; 2,400' | 376.2 | 1111422.143 | 2024/01 | 1920683.51 | 1920683.51 | 809261.367 | 72.81% | Yes | Yes | - | 1920683.51
B | 103 | Portfolio Review | Link |  | FP-321557 | Gass SCADA cellular modems CNGC | 397 | 49077.56 | 2024/01 | 49345.22 | 49345.22 | 267.66 | 0.5454% | - | - | - | 49345.22
B | 104 | Portfolio Review | Nygard | Exh-TJN-3-3-29-24 | FP-321574 | UG-Powerplan Upgrade 2024 CNGC | 303 | 249076.76 | 2024/12 | 140350.87 | 140350.87 | -108725.89 | -43.65% | Yes | - | - | 140350.87
B | 105 | Portfolio Review | Darras |  | FP-321753 | RL-8" HP-4,500' PASCO-DARIGOLD | 376 | -277894.65 | 2024/01 | -277894.65 | -277894.65 | 0 | 0% | - | - | - | -277894.65
B | 106 | Portfolio Review | Martuscelli | Exh-EPM-4-3-29-24 | FP-321795 | RP; 3" ST; BELL; 2549 ALLEY PROJ | 376.1 | 166245.6348 | 2024/01 | 130702.5 | 130702.5 | -35543.1348 | -21.38% | Yes | - | - | 130702.5
B | 107 | Portfolio Review | Martuscelli |  | FP-321846 | RF; 2"PE; RICH; MEADOW HILLS | 376 | -15113.56 | 2024/08 | -15113.56 | -15113.56 | 0 | 0% | - | - | - | -15113.56
B | 108 | Portfolio Review | Martuscelli | Exh-EPM-4-3-29-24 | FP-321861 | RF; 6" PE; KENN; 2000' OLYMPIA | 376.3 | 31306.04 |  | 0 | 0 | -31306.04 | -100% | Yes | - | - | 0
B | 109 | Portfolio Review | Martuscelli | Exh-EPM-4-3-29-24 | FP-321983 | GR; 2" PE; VIEW; 6,000' | 376.3 | 20447.11 | 2024/08 | 92590.24 | 92590.24 | 72143.13 | 352.8% | Yes | Yes | - | 92590.24
B | 110 | Portfolio Review | Martuscelli |  | FP-322053 | GR; 4" PE; PASC; 1500 HYW12 | 376 | 133.69 | 2024/02 | 133.43 | 133.43 | -0.26 | -0.1945% | - | - | - | 133.43
B | 111 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-322143 | RL; 6" HP; MTVE; 100' | 376.2 | 340437.4092 |  | 0 | 0 | -340437.4092 | -100% | Yes | - | - | 0
B | 112 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-322144 | Instl Main Gibralter Rd Anacortes | 376.3 | 377277.1 |  | 0 | 0 | -377277.1 | -100% | Yes | - | - | 0
B | 113 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-322165 | MAOP; R-096 (R-001) YAKIMA | 378 | 103522.5603 |  | 0 | 0 | -103522.5603 | -100% | Yes | - | - | 0
B | 114 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-322173 | MAOP; R-097 YAKIMA | 378 | 200464.85 |  | 0 | 0 | -200464.85 | -100% | Yes | - | - | 0
B | 115 | Portfolio Review | Darras |  | FP-322205 | RP; 2" HP; FERN; 40' R-93 | 376 | 49.23 | 2024/04 | 49.14 | 49.14 | -0.09 | -0.1828% | - | - | - | 49.14
B | 116 | Portfolio Review | Martuscelli |  | FP-322219 | RP; 6" ST; MOSE; 200' | 376 | 612.91 | 2024/01 | 614.67 | 614.67 | 1.76 | 0.2872% | - | - | - | 614.67
B | 117 | Portfolio Review | Darras |  | FP-322305 | MAOP; R-59 OAKH; BLDG | 378 | 19701.02 | 2024/01 | 19757.63 | 19757.63 | 56.61 | 0.2873% | - | - | - | 19757.63
B | 118 | Portfolio Review | Martuscelli |  | FP-322385 | FRL; 2" PE; LONG; 2,000' 46TH AVE. | 376 | 11630.78 | 2024/06 | 11664.21 | 11664.21 | 33.43 | 0.2874% | - | - | - | 11664.21
B | 119 | Portfolio Review | Martuscelli | Exh-EPM-4-3-29-24 | FP-322468 | PURCHASE RMLD MT VERNON | 394.1 | 16755.97 |  | 0 | 0 | -16755.97 | -100% | Yes | - | - | 0
B | 120 | Portfolio Review | Martuscelli | Exh-EPM-4-3-29-24 | FP-322488 | PUR (2) STOP MACHINES MT VERNON | 394.1 | 3970.1 |  | 0 | 0 | -3970.1 | -100% | Yes | - | - | 0
B | 121 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-322504 | RP-4" HP MN-PASCO-160' | 376.2 | 212141.98 |  | 0 | 0 | -212141.98 | -100% | Yes | - | - | 0
B | 122 | Portfolio Review | Martuscelli | Exh-EPM-4-3-29-24 | FP-322580 | Purchase MBW Air Rammer Kelso | 394.1 | 10597.83 |  | 0 | 0 | -10597.83 | -100% | Yes | - | - | 0
B | 123 | Portfolio Review | Martuscelli | Exh-EPM-4-3-29-24 | FP-322598 | Install Generator -Bremerton Office | 390.1 | 126212.5 |  | 0 | 0 | -126212.5 | -100% | Yes | - | - | 0
B | 124 | Portfolio Review | Martuscelli |  | FP-322634 | Purchase Pavement Breaker Kelso | 394 | 76.24 | 2024/02 | 76.24 | 76.24 | 0 | 0% | - | - | - | 76.24
B | 125 | Portfolio Review | Martuscelli | Exh-EPM-4-3-29-24 | FP-322655 | Purch (2) RD8100 Locators Mt Vernon | 394.1 | 20141.35 | 2024/08 | 23377.5 | 23377.5 | 3236.15 | 16.07% | Yes | Yes | - | 23377.5
B | 126 | Portfolio Review | Darras | Exh-PCD-1T-3-29-24 | FP-322683 | GR-6" PE-ABER-5000' FRONT ST | 376 | 558.35 | 2024/04 | 559.96 | 559.96 | 1.61 | 0.2883% | - | - | - | 559.96
B | 127 | Portfolio Review | Darras | Exh-PCD-1T-3-29-24 | FP-322783 | RF; LAND FOR 6 MILE 20IN BURLINGTON | 374.1 | 119146.94 |  | 0 | 0 | -119146.94 | -100% | Yes | - | - | 0
B | 128 | Portfolio Review | Darras | Exh-PCD-1T-3-29-24 | FP-322784 | RF; R-197 PULVER RD, BURLING | 378 | 498151.91 |  | 0 | 0 | -498151.91 | -100% | Yes | - | - | 0
B | 129 | Portfolio Review | Gilchrist |  | FP-322912 | UG PUR AR/VR Trainng Dvlpmnt CNG GO | 303 | 4435.86 | 2024/02 | 4460.05 | 4460.05 | 24.19 | 0.5453% | - | - | - | 4460.05
B | 130 | Portfolio Review | Darras |  | FP-323040 | RP-8" STL-WALL-CLINTON 400' | 376 | -32090.57 | 2024/01 | -32090.57 | -32090.57 | 0 | 0% | - | - | - | -32090.57
B | 131 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-323166 | RP Bremerton R-023 | 378 | 67326.15 | 2024/06 | 568759.21 | 568759.21 | 501433.06 | 744.8% | Yes | Yes | - | 568759.21
B | 132 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-323236 | RPL MN - SHORTED CASING - WA | 376.1 | 344834.9645 | 2024/08 | 73404.22 | 73404.22 | -271430.7445 | -78.71% | Yes | - | - | 73404.22
B | 133 | Portfolio Review | Darras |  | FP-323429 | Fredonia CS camera upgrade | 377 | -581.06 | 2024/01 | -581.06 | -581.06 | 0 | 0% | - | - | - | -581.06
B | 134 | Portfolio Review | Darras | Exh-PCD-1T-3-29-24 | FP-323431 | GR L'view -2" HP MN, Divert INC RNG | 376.2 | 237521.69 |  | 0 | 0 | -237521.69 | -100% | Yes | - | - | 0
B | 135 | Portfolio Review | Darras | Exh-PCD-1T-3-29-24 | FP-323432 | INST RNG RS, DIVERT INC, Longview | 378 | 582324.92 |  | 0 | 0 | -582324.92 | -100% | Yes | - | - | 0
B | 136 | Portfolio Review | Darras | Exh-PCD-1T-3-29-24 | FP-323434 | INST RNG ODRIZR, DIVERT INC, L'VIEW | 378 | 1181773.33 |  | 0 | 0 | -1181773.33 | -100% | Yes | - | - | 0
B | 137 | Portfolio Review | Darras | Exh-PCD-1T-3-29-24 | FP-323435 | INST RNG MTR SET, DIVERT INC, LVIEW | 385 | 97718.88 |  | 0 | 0 | -97718.88 | -100% | Yes | - | - | 0
B | 138 | Portfolio Review | Darras |  | FP-323447 | RNG- Horn Rapids Pipeline 6"PE | 376 | 941.68 | 2024/01 | 944.38 | 944.38 | 2.7 | 0.2867% | - | - | - | 944.38
B | 139 | Portfolio Review | Darras |  | FP-323470 | RNG; Lamb Weston Richland 4" Steel | 376 | 14366.29 | 2024/01 | 14407.58 | 14407.58 | 41.29 | 0.2874% | - | - | - | 14407.58
B | 140 | Portfolio Review | Martuscelli | Exh-EPM-4-3-29-24 | FP-323530 | Instl PE Main McCormick N Pt Orchrd | 376.3 | 131189.38 | 2024/03 | 131189.38 | 131189.38 | 0 | 0% | - | - | - | 131189.38
B | 141 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-323595 | RF; 4" PE; 10,000'; Lynden | 376.3 | 343875.48 |  | 0 | 0 | -343875.48 | -100% | Yes | - | - | 0
B | 142 | Portfolio Review | Darras |  | FP-323596 | RF; 6" PE; 5,350'; Everson | 376 | 92851.07 | 2024/01 | 93117.59 | 93117.59 | 266.52 | 0.287% | - | - | - | 93117.59
B | 143 | Portfolio Review | Darras |  | FP-323627 | Fredonia CS Piston Rod Upgrade | 377 | 488.2 | 2024/01 | 488.2 | 488.2 | 0 | 0% | - | - | - | 488.2
B | 144 | Portfolio Review | Darras |  | FP-323628 | Fredonia CS LEL detector upgrade | 377 | -29.91 | 2024/01 | -29.91 | -29.91 | 0 | 0% | - | - | - | -29.91
B | 145 | Portfolio Review | Darras |  | FP-323630 | RP-BURBANK R-6 (R-142) MAIN | 376 | -3533.65 | 2024/01 | -3533.65 | -3533.65 | 0 | 0% | - | - | - | -3533.65
B | 146 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-323636 | RP-SHEL R-17 (R-84) MAIN | 376.2 | 63627.0473 | 2024/07 | 57515.36 | 57515.36 | -6111.6873 | -9.605% | - | - | - | 57515.36
B | 147 | Portfolio Review | Martuscelli |  | FP-323715 | FRL; 2" PE; EAST;400' | 376 | 18290.83 | 2024/07 | 18342.9 | 18342.9 | 52.07 | 0.2847% | - | - | - | 18342.9
B | 148 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-323730 | RP-SHEL R-17 (R-84) | 378 | 206332.3188 | 2024/07 | 536217.71 | 536217.71 | 329885.3912 | 159.9% | Yes | Yes | - | 536217.71
B | 149 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-323731 | Fredonia CS Scrubber Replacement | 377 | 147143.0528 | 2024/12 | 268514.58 | 268514.58 | 121371.5272 | 82.49% | Yes | Yes | - | 268514.58
B | 150 | Portfolio Review | Darras |  | FP-323746 | MAOP; R-100(R-52) SIDE; | 378 | 4778.33 | 2024/01 | 4792.06 | 4792.06 | 13.73 | 0.2873% | - | - | - | 4792.06
B | 151 | Portfolio Review | Darras |  | FP-323756 | RL-2" HP-900' Burbank | 376 | -173.41 | 2024/01 | -173.41 | -173.41 | 0 | 0% | - | - | - | -173.41
B | 152 | Portfolio Review | Martuscelli | Exh-EPM-4-3-29-24 | FP-323791 | Purchase Mueller Tools - Bellingham | 394.1 | 12729.9 | 2024/08 | 13586.08 | 13586.08 | 856.18 | 6.726% | - | - | - | 13586.08
B | 153 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-323795 | Fredonia CS Flame / PLC spare parts | 377 | 18881.81 | 2024/09 | 15791.24 | 15791.24 | -3090.57 | -16.37% | Yes | - | - | 15791.24
B | 154 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-323823 | RP; R-81 WHEE; RPL (R-53 & R-54) | 378 | 55851.3983 | 2024/02 | 108010.73 | 108010.73 | 52159.3317 | 93.39% | Yes | Yes | - | 108010.73
B | 155 | Portfolio Review | Link |  | FP-323826 | CC&B Enhancement for CNGC | 303 | 29259.34 | 2024/01 | 68497.43 | 68497.43 | 39238.09 | 134.1% | Yes | Yes | - | 68497.43
B | 156 | Portfolio Review | Martuscelli |  | FP-323833 | RP; 2" PE; LONG; 550' 1291 INDUSTRI | 376 | 30321.08 | 2024/06 | 96082.49 | 96082.49 | 65761.41 | 216.9% | Yes | Yes | - | 96082.49
B | 157 | Portfolio Review | Martuscelli |  | FP-323836 | RP; 2" ST; LONG; 75' 58 E. PORT WAY | 376 | 32934.75 | 2024/02 | 33029.4 | 33029.4 | 94.65 | 0.2874% | - | - | - | 33029.4
B | 158 | Portfolio Review | Martuscelli |  | FP-323837 | RP; 4" ST; LONG; 50' LAUREL RD & P | 376 | 62609.68 | 2024/06 | 62789.61 | 62789.61 | 179.93 | 0.2874% | - | - | - | 62789.61
B | 159 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-323909 | Yakima Enclose Canopy CS Fab | 390.1 | 37696.4005 | 2024/03 | 33907.5 | 33907.5 | -3788.9005 | -10.05% | Yes | - | - | 33907.5
B | 160 | Portfolio Review | Martuscelli | Exh-EPM-4-3-29-24 | FP-323917 | PURCHASE BEVELING MACHINE MT VERNON | 394.1 | 1592.8 |  | 0 | 0 | -1592.8 | -100% | Yes | - | - | 0
B | 161 | Portfolio Review | Martuscelli | Exh-EPM-4-3-29-24 | FP-323918 | Purchase Fresh Air Paks Mt Vernon | 394.1 | 10082.29 | 2024/08 | 10216.57 | 10216.57 | 134.28 | 1.332% | - | - | - | 10216.57
B | 162 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-323926 | Repl Mueller Equip CS WA | 394.1 | 102940.75 | 2025/02 | 4052 | 4052 | -98888.75 | -96.06% | Yes | - | - | 4052
B | 163 | Portfolio Review | Martuscelli | Exh-EPM-4-3-29-24 | FP-323951 | Purch Leak Survey Equip Kennewick | 394.1 | 32137.6 | 2024/06 | 38056.46 | 38056.46 | 5918.86 | 18.42% | Yes | Yes | - | 38056.46
B | 164 | Portfolio Review | Gilchrist | Exh-HG-3-3-29-24 | FP-323967 | UG-CNG PUR AR/VR Gas Emrgncy Rspns | 303 | 41466.0406 |  | 0 | 0 | -41466.0406 | -100% | Yes | - | - | 0
B | 165 | Portfolio Review | Gilchrist | Exh-HG-3-3-29-24 | FP-323968 | UG-CNG PUR AR/VR I-Leak Upg/Enhance | 303 | 7539.2801 |  | 0 | 0 | -7539.2801 | -100% | Yes | - | - | 0
B | 166 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-324005 | RP; 4" PE & 6" STL; ANAC; 1200' | 376.2 | 306877.8 |  | 0 | 0 | -306877.8 | -100% | Yes | - | - | 0
B | 167 | Portfolio Review | Martuscelli | Exh-EPM-4-3-29-24 | FP-324015 | PUR FORKLIFT SPREADER BAR MT VERNON | 394.1 | 3439.73 | 2024/08 | 4893.79 | 4893.79 | 1454.06 | 42.27% | Yes | Yes | - | 4893.79
B | 168 | Portfolio Review | Martuscelli | Exh-EPM-4-3-29-24 | FP-324018 | Purchase Steel Squeezer Elma | 394.1 | 7532.25 | 2024/07 | 8733.29 | 8733.29 | 1201.04 | 15.95% | Yes | Yes | - | 8733.29
B | 169 | Portfolio Review | Boese | Exh-HG-1T-3-29-24 | FP-324020 | UG-Locusview Software - CNGC | 303 | 810507.8561 | 2024/05 | 1147305.19 | 1147305.19 | 336797.3339 | 41.55% | Yes | Yes | - | 1147305.19
B | 170 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-324021 | FRL; R-195 (R-170) ANAC | 378 | 292793.2997 |  | 0 | 0 | -292793.2997 | -100% | Yes | - | - | 0
B | 171 | Portfolio Review | Boese | Exh-HG-1T-3-29-24 | FP-324035 | UG-IQ Geo Enhancements CNGC | 303 | 52501.4432 | 2024/12 | 4153.82 | 4153.82 | -48347.6232 | -92.09% | Yes | - | - | 4153.82
B | 172 | Portfolio Review | Gilchrist | Exh-HG-3-3-29-24 | FP-324053 | CONST Training Yard Elma D Off | 394.1 | 50215 |  | 0 | 0 | -50215 | -100% | Yes | - | - | 0
B | 173 | Portfolio Review | Darras | Exh-PCD-1T-3-29-24 | FP-324101 | C/M RPL; 8" TM; ANACORTES; 3,000' | 367.1 | 2632121.5674 | 2024/11 | 482378.59 | 482378.59 | -2149742.9774 | -81.67% | Yes | - | - | 482378.59
B | 174 | Portfolio Review | Martuscelli | Exh-EPM-4-3-29-24 | FP-324134 | PURCH SPREADER BAR BELLINGHAM | 394.1 | 4017.2 | 2024/06 | 4902.77 | 4902.77 | 885.57 | 22.04% | Yes | Yes | - | 4902.77
B | 175 | Portfolio Review | Martuscelli | Exh-EPM-4-3-29-24 | FP-324146 | Pur Shop Air Compressor Walla Walla | 394.1 | 2510.75 | 2024/02 | 2829.23 | 2829.23 | 318.48 | 12.68% | Yes | Yes | - | 2829.23
B | 176 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-324239 | Purch Electric Grease Gun Mt Vernon | 394.1 | 1506.45 | 2024/02 | 1410.08 | 1410.08 | -96.37 | -6.397% | - | - | - | 1410.08
B | 177 | Portfolio Review | Gilchrist | Exh-HG-3-3-29-24 | FP-324251 | Purch AED for Bellingham WA | 398 | 2008.6 |  | 0 | 0 | -2008.6 | -100% | Yes | - | - | 0
B | 178 | Portfolio Review | Gilchrist | Exh-HG-3-3-29-24 | FP-324253 | Purch PAPR's for Washington 2024 | 394.1 | 10043 |  | 0 | 0 | -10043 | -100% | Yes | - | - | 0
B | 179 | Portfolio Review | Martuscelli | Exh-EPM-4-3-29-24 | FP-324259 | Repl SAN & FC Switches CNGC GO | 397.3 | 75322.5 | 2024/09 | 67136.93 | 67136.93 | -8185.57 | -10.87% | Yes | - | - | 67136.93
B | 180 | Portfolio Review | Martuscelli | Exh-EPM-4-3-29-24 | FP-324263 | Replace Office Servers CNG | 391.3 | 45193.5 |  | 0 | 0 | -45193.5 | -100% | Yes | - | - | 0
B | 181 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-324273 | Purch Electric Grease Gun Longview | 394.1 | 1506.45 | 2024/02 | 1408.03 | 1408.03 | -98.42 | -6.533% | - | - | - | 1408.03
B | 182 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-324274 | Purch Electric Grease Gun Kennewick | 394.1 | 1506.45 | 2024/02 | 1401.33 | 1401.33 | -105.12 | -6.978% | - | - | - | 1401.33
B | 183 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-324276 | Replace Vacuum Pump Yak MS | 394.1 | 9800.4185 | 2024/07 | 12299.2 | 12299.2 | 2498.7815 | 25.5% | Yes | Yes | - | 12299.2
B | 184 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-324281 | Add HEPA Vacuum at the CNG meter sh | 394.1 | 3769.64 | 2024/02 | 1384.28 | 1384.28 | -2385.3601 | -63.28% | Yes | - | - | 1384.28
B | 185 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-324301 | Pur Completion Machine Mt Vern CS | 394.1 | 2638.748 |  | 0 | 0 | -2638.748 | -100% | Yes | - | - | 0
B | 186 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-324315 | Pur 12in Shell Cutter Mt Vernon CS | 394.1 | 10554.9921 | 2024/05 | 10987.63 | 10987.63 | 432.6379 | 4.099% | - | - | - | 10987.63
B | 187 | Portfolio Review | Martuscelli | Exh-EPM-4-3-29-24 | FP-324342 | RP; 2" ST; BELL; 360'; FLORA/UNITY | 376.1 | 72206.3381 | 2024/01 | 61746.19 | 61746.19 | -10460.1481 | -14.49% | Yes | - | - | 61746.19
B | 188 | Portfolio Review | Martuscelli | Exh-EPM-4-3-29-24 | FP-324375 | Rpl Main Nelson Rd/Ctr Vly Brmrtn | 376.3 | 193815.1095 | 2024/09 | 449652.87 | 449652.87 | 255837.7605 | 132% | Yes | Yes | - | 449652.87
B | 189 | Portfolio Review | Martuscelli | Exh-EPM-4-3-29-24 | FP-324409 | UG - Trellis Energy Software CNGC | 303 | 149733.9464 | 2024/12 | 117864.96 | 117864.96 | -31868.9864 | -21.28% | Yes | - | - | 117864.96
B | 190 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-324475 | Pur Elec Fume Extractor Mt Ver CS | 394.1 | 15078.5602 | 2024/08 | 7267.91 | 7267.91 | -7810.6502 | -51.8% | Yes | - | - | 7267.91
B | 191 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-324480 | Pur 2 Custom Pallets Mt Vernon CS | 394.1 | 8293.2081 | 2024/09 | 6111.35 | 6111.35 | -2181.8581 | -26.31% | Yes | - | - | 6111.35
B | 192 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-324495 | Fredonia CS Storage Shed | 377 | 18174 | 2024/06 | 17002.84 | 17002.84 | -1171.16 | -6.444% | - | - | - | 17002.84
B | 193 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-324502 | Fredonia CS Update facility Lights | 377 | 21808.8 | 2024/06 | 23856.99 | 23856.99 | 2048.19 | 9.392% | - | - | - | 23856.99
B | 194 | Portfolio Review | Martuscelli | Exh-EPM-4-3-29-24 | FP-324503 | Purchase Traffic Plates Walla Walla | 394.1 | 6527.95 | 2024/06 | 7059.39 | 7059.39 | 531.44 | 8.141% | - | - | - | 7059.39
B | 195 | Portfolio Review | Martuscelli | Exh-EPM-4-3-29-24 | FP-324524 | Purch Fork Lift Spreader Bar Kelso | 394.1 | 4017.2 | 2024/06 | 4862.29 | 4862.29 | 845.09 | 21.04% | Yes | Yes | - | 4862.29
B | 196 | Portfolio Review | Martuscelli | Exh-EPM-4-3-29-24 | FP-324527 | Purch Fork Lift Spreader Bar Elma | 394.1 | 4017.2 | 2024/06 | 4898.27 | 4898.27 | 881.07 | 21.93% | Yes | Yes | - | 4898.27
B | 197 | Portfolio Review | Martuscelli | Exh-EPM-4-3-29-24 | FP-324530 | Purchase Mueller Gate Valves Kelso | 394.1 | 4441.3 |  | 0 | 0 | -4441.3 | -100% | Yes | - | - | 0
B | 198 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-324556 | CNGC-Picarro Leak Survey Equipment | 394.1 | 904713.612 | 2024/09 | 990787.64 | 990787.64 | 86074.028 | 9.514% | - | - | - | 990787.64
B | 199 | Portfolio Review | Martuscelli | Exh-EPM-4-3-29-24 | FP-324559 | Purchase Shop Welder Bremerton | 394.1 | 7906.85 | 2024/03 | 9173.93 | 9173.93 | 1267.08 | 16.03% | Yes | Yes | - | 9173.93
B | 200 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-324581 | RF-OAKH-4"PE-1000' | 376.3 | 343625.52 |  | 0 | 0 | -343625.52 | -100% | Yes | - | - | 0
B | 201 | Portfolio Review | Darras | Exh-PCD-1T-3-29-24 | FP-324689 | RP-8" HP- ELMA 1100' WILD CAT CREEK | 376.2 | 1634772.2809 |  | 0 | 0 | -1634772.2809 | -100% | Yes | - | - | 0
B | 202 | Portfolio Review | Martuscelli | Exh-EPM-4-3-29-24 | FP-324690 | Purch Steel Road Plates Kelso | 394.1 | 5021.5 |  | 0 | 0 | -5021.5 | -100% | Yes | - | - | 0
B | 203 | Portfolio Review | Martuscelli | Exh-EPM-4-3-29-24 | FP-324695 | Purch Leak Survey Equip Kennewick | 394.1 | 42682.75 | 2024/08 | 36770.44 | 36770.44 | -5912.31 | -13.85% | Yes | - | - | 36770.44
B | 204 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-324704 | Fredonia CS Security Install | 377 | 30290 |  | 0 | 0 | -30290 | -100% | Yes | - | - | 0
B | 205 | Portfolio Review | Martuscelli | Exh-EPM-4-3-29-24 | FP-324761 | Crack Seal Parking Lot Walla Walla | 390.1 | 55236.5 | 2024/08 | 42524.26 | 42524.26 | -12712.24 | -23.01% | Yes | - | - | 42524.26
B | 206 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-324778 | CONST SVCS - TOOL SHED & REMODEL | 390.1 | 155213.8687 | 2024/12 | 37330.75 | 37330.75 | -117883.1187 | -75.95% | Yes | - | - | 37330.75
B | 207 | Portfolio Review | Martuscelli | Exh-EPM-4-3-29-24 | FP-324790 | Instl Shop Lighting Wentachee | 390.1 | 9540.85 | 2024/04 | 8395.51 | 8395.51 | -1145.34 | -12% | Yes | - | - | 8395.51
B | 208 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-324799 | FRL-MTV-HWY 9-6" HP-400FT | 376.2 | 512719.18 |  | 0 | 0 | -512719.18 | -100% | Yes | - | - | 0
B | 209 | Portfolio Review | Darras |  | FP-324801 | Fredonia CAT Crankshaft upgrade | 377 | -876.94 | 2024/02 | -876.94 | -876.94 | 0 | 0% | - | - | - | -876.94
B | 210 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-324804 | UPGRADE MODEL 5 PROVER - YAKIMA | 394.1 | 30129 | 2024/03 | 25267.04 | 25267.04 | -4861.96 | -16.14% | Yes | - | - | 25267.04
B | 211 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-324806 | MODEL 5 PROVER UPGRADE - BELLINGHAM | 394.1 | 30129 | 2024/03 | 25382.78 | 25382.78 | -4746.22 | -15.75% | Yes | - | - | 25382.78
B | 212 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-324820 | MAOP;4' ST;ARLI;5,610' | 376.2 | 76795.7418 | 2024/09 | 927624.82 | 927624.82 | 850829.0782 | 1108% | Yes | Yes | - | 927624.82
B | 213 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-324823 | Bellingham 1 TBS RTU Replacement | 379 | 4024.9238 | 2024/10 | 5142.51 | 5142.51 | 1117.5862 | 27.77% | Yes | Yes | - | 5142.51
B | 214 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-324824 | C/M;R-198(R-66) ARL | 378 | 53708.9961 | 2024/09 | 190439.75 | 190439.75 | 136730.7539 | 254.6% | Yes | Yes | - | 190439.75
B | 215 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-324827 | Sumas TBS RTU Replacement | 379 | 3930.4877 | 2024/10 | 5143.67 | 5143.67 | 1213.1823 | 30.87% | Yes | Yes | - | 5143.67
B | 216 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-324828 | Lynden TBS RTU Replacement | 379 | 4024.9238 | 2024/10 | 5135.61 | 5135.61 | 1110.6862 | 27.6% | Yes | Yes | - | 5135.61
B | 217 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-324829 | Hermiston TBS RTU Replacement | 379 | 4024.9238 |  | 0 | 0 | -4024.9238 | -100% | Yes | - | - | 0
B | 218 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-324830 | Stanwood TBS RTU replacment | 379 | 4024.9238 | 2024/08 | 5162.51 | 5162.51 | 1137.5862 | 28.26% | Yes | Yes | - | 5162.51
B | 219 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-324831 | Mt Vernon TBS RTU replacement | 379 | 4024.9238 | 2024/07 | 4686.53 | 4686.53 | 661.6062 | 16.44% | Yes | Yes | - | 4686.53
B | 220 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-324832 | Nyssa TBS RTU Replacement | 379 | 4024.9238 |  | 0 | 0 | -4024.9238 | -100% | Yes | - | - | 0
B | 221 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-324833 | Othello TBS RTU Replacement. | 379 | 4024.9238 | 2024/11 | 5344.41 | 5344.41 | 1319.4862 | 32.78% | Yes | Yes | - | 5344.41
B | 222 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-324834 | Redmond TBS RTU Replacement | 379 | 4024.9238 |  | 0 | 0 | -4024.9238 | -100% | Yes | - | - | 0
B | 223 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-324835 | Shelton TBS RTU replacement | 379 | 4024.9238 | 2024/07 | 5357.7 | 5357.7 | 1332.7762 | 33.11% | Yes | Yes | - | 5357.7
B | 224 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-324836 | South Bend TBS RTU Replacement | 379 | 4024.9238 |  | 0 | 0 | -4024.9238 | -100% | Yes | - | - | 0
B | 225 | Portfolio Review | Martuscelli | Exh-EPM-4-3-29-24 | FP-324847 | Instl Back Up Generator Walla Walla | 390.1 | 150645 | 2024/09 | 77660.7 | 77660.7 | -72984.3 | -48.45% | Yes | - | - | 77660.7
B | 226 | Portfolio Review | Martuscelli |  | FP-324853 | RF; 2" PE; LYND; 1290'; W FRONT | 376 | -3236.42 | 2024/01 | -3236.42 | -3236.42 | 0 | 0% | - | - | - | -3236.42
B | 227 | Portfolio Review | Darras |  | FP-324897 | C/M; R-200(R-60) OAKH; | 378 | 8935.9 | 2024/01 | 8961.58 | 8961.58 | 25.68 | 0.2874% | - | - | - | 8961.58
B | 228 | Portfolio Review | Darras | Exh-PCD-1T-3-29-24 | FP-324932 | RP; 6" HP; OAKH; 3000' | 376.1 | 1001332.7538 |  | 0 | 0 | -1001332.7538 | -100% | Yes | - | - | 0
B | 229 | Portfolio Review | Martuscelli | Exh-EPM-4-3-29-24 | FP-324946 | PUR CONTROL RADIOS AVTEC SYS - WA | 397.1 | 3741.15 | 2024/01 | 4598.59 | 4598.59 | 857.44 | 22.92% | Yes | Yes | - | 4598.59
B | 230 | Portfolio Review | Martuscelli |  | FP-324959 | PURCHASE 2 - ODORATOR's ELMA | 394 | -90.62 | 2024/01 | -90.62 | -90.62 | 0 | 0% | - | - | - | -90.62
B | 231 | Portfolio Review | Martuscelli | Exh-EPM-4-3-29-24 | FP-324982 | CNG UPS Replacements | 391.3 | 13227.2378 | 2024/11 | 13699.07 | 13699.07 | 471.8322 | 3.567% | - | - | - | 13699.07
B | 232 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-324988 | Inst Reinf main for R99, Yakima | 376.1 | 754871.91 | 2024/09 | 1134532.93 | 1134532.93 | 379661.02 | 50.29% | Yes | Yes | - | 1134532.93
B | 233 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-324995 | C/M; R-199(R-7) MTVE; | 378 | 98907.7256 | 2024/11 | 157517.77 | 157517.77 | 58610.0444 | 59.26% | Yes | Yes | - | 157517.77
B | 234 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-325037 | RP; 8" PE CLINTON; HDD 400' | 376.3 | 122656.28 |  | 0 | 0 | -122656.28 | -100% | Yes | - | - | 0
B | 235 | Portfolio Review | Martuscelli |  | FP-325044 | PURCHASE SENIT GOLD G2-MOSES LAKE | 394 | 26.98 | 2024/02 | 49.42 | 49.42 | 22.44 | 83.17% | Yes | Yes | - | 49.42
B | 236 | Portfolio Review | Martuscelli | Exh-EPM-4-3-29-24 | FP-325055 | REPLACE SHOP TUBE HEATER BREMERTON | 390.1 | 9404.2325 | 2024/01 | 7378.03 | 7378.03 | -2026.2025 | -21.55% | Yes | - | - | 7378.03
B | 237 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-325057 | Fredonia CS New Relief 1910K | 377 | 15145 | 2024/09 | 12542.03 | 12542.03 | -2602.97 | -17.19% | Yes | - | - | 12542.03
B | 238 | Portfolio Review | Martuscelli | Exh-EPM-4-3-29-24 | FP-325059 | Purchase Sensit Gold Kennewick | 394.1 | 3136.74 | 2024/07 | 3192.92 | 3192.92 | 56.18 | 1.791% | - | - | - | 3192.92
B | 239 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-325160 | RTU Replacement Kalama TBS | 379 | 4582.6119 | 2024/07 | 5249.28 | 5249.28 | 666.6681 | 14.55% | Yes | Yes | - | 5249.28
B | 240 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-325161 | Kelso RTU replacement | 379 | 4582.6119 | 2024/07 | 5571.95 | 5571.95 | 989.3381 | 21.59% | Yes | Yes | - | 5571.95
B | 241 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-325162 | Selah TBS RTU Replacement | 379 | 4591.8647 | 2024/10 | 4914.3 | 4914.3 | 322.4353 | 7.022% | - | - | - | 4914.3
B | 242 | Portfolio Review | Darras | Exh-PCD-5-3-29-24 | FP-325163 | R-38 Longview RTU Replacement | 379 | 4582.6119 | 2024/07 | 5165.15 | 5165.15 | 582.5381 | 12.71% | Yes | Yes | - | 5165.15
B | 243 | Portfolio Review | Martuscelli | Exh-EPM-4-3-29-24 | FP-325186 | PUR VIVAX METROTECH LOCATOR-YAKIMA | 394.1 | 3799.31 | 2024/01 | 3834.73 | 3834.73 | 35.42 | 0.9323% | - | - | - | 3834.73
B | 244 | Portfolio Review | Martuscelli | Exh-EPM-4-3-29-24 | FP-325187 | FRL;2'';VIEW'800' OIE HWY | 376.1 | 171343.3336 | 2024/03 | 721081.05 | 721081.05 | 549737.7164 | 320.8% | Yes | Yes | - | 721081.05
B | 245 | Portfolio Review | Martuscelli | Exh-EPM-4-3-29-24 | FP-325196 | RP; 6" ST; BELL; 2400'; NORTHWEST | 376.1 | 851809.5202 |  | 0 | 0 | -851809.5202 | -100% | Yes | - | - | 0
B | 246 | Portfolio Review | Martuscelli | Exh-EPM-4-3-29-24 | FP-325206 | FRL;2'' ST;WAPA;1,000' S.Naches A | 376.1 | 229130.5956 | 2024/05 | 823581.64 | 823581.64 | 594451.0444 | 259.4% | Yes | Yes | - | 823581.64
B | 247 | Portfolio Review | Martuscelli | Exh-EPM-4-3-29-24 | FP-325214 | PUR Sensit LZ-30s - Washington | 394.1 | 622666 | 2024/02 | 715303.47 | 715303.47 | 92637.47 | 14.88% | Yes | Yes | - | 715303.47
B | 248 | Portfolio Review | Martuscelli | Exh-EPM-4-3-29-24 | FP-325218 | PUR 1 Rivet Buster, Bellingham | 394.1 | 1584.38 | 2024/02 | 1596.67 | 1596.67 | 12.29 | 0.7757% | - | - | - | 1596.67
B | 249 | Portfolio Review | Martuscelli |  | FP-325250 | PUR - 2 HANDHELD RADIOS - BREMERTON | 397 | 3694.43 | 2024/04 | 3714.58 | 3714.58 | 20.15 | 0.5454% | - | - | - | 3714.58
B | 250 | Portfolio Review | Martuscelli |  | FP-325257 | PURCH (2) MET FIT TOOLS-WENATCHEE | 394 | 2488.48 | 2024/02 | 2502.06 | 2502.06 | 13.58 | 0.5457% | - | - | - | 2502.06
B | 251 | Portfolio Review | Martuscelli |  | FP-325273 | Replace Locator Longview | 394 | 6322.46 | 2024/03 | 6356.94 | 6356.94 | 34.48 | 0.5454% | - | - | - | 6356.94
B | 252 | Portfolio Review | Martuscelli |  | FP-325287 | Purchase Locator Walla Walla | 394 | 3372.34 | 2024/03 | 3390.73 | 3390.73 | 18.39 | 0.5453% | - | - | - | 3390.73
B | 253 | Portfolio Review | Martuscelli |  | FP-325289 | Purch Metrotech Locator Kennewick | 394 | 3363.01 | 2024/07 | 3381.35 | 3381.35 | 18.34 | 0.5453% | - | - | - | 3381.35
B | 254 | Portfolio Review | Martuscelli |  | FP-325300 | PURCH TWO METROTECH LOCATORS YAKIMA | 394 | 6697.85 | 2024/04 | 6734.38 | 6734.38 | 36.53 | 0.5454% | - | - | - | 6734.38
B | 255 | Portfolio Review | Martuscelli |  | FP-325304 | Replace 2LC Machine Bellingham | 394 | 4772.79 | 2024/04 | 4798.82 | 4798.82 | 26.03 | 0.5454% | - | - | - | 4798.82
B | 256 | Portfolio Review | Martuscelli |  | FP-325310 | GR; 2" PE; WOOD; 1,400' WOODLAND CR | 376 | 48404.23 | 2024/04 | 48599.92 | 48599.92 | 195.69 | 0.4043% | - | - | - | 48599.92
B | 257 | Portfolio Review | Martuscelli |  | FP-325313 | Repl Main NE 7th St Oak Harbor | 376 | 113272.93 | 2024/07 | 120573.04 | 120573.04 | 7300.11 | 6.445% | - | - | - | 120573.04
B | 258 | Portfolio Review | Martuscelli |  | FP-325341 | Purchase Saddle Machine Mt Vernon | 394 | 1642.67 | 2024/05 | 1651.63 | 1651.63 | 8.96 | 0.5455% | - | - | - | 1651.63
B | 259 | Portfolio Review | Martuscelli |  | FP-325356 | RL;6'' PE;TOPP;1000' 580 Fort Rd | 376 | 219022.49 | 2024/06 | 24716.92 | 24716.92 | -194305.57 | -88.71% | Yes | - | - | 24716.92
B | 260 | Portfolio Review | Martuscelli |  | FP-325358 | PURCH RD8000 YAKIMA | 394 | 5468.18 | 2024/04 | 5498 | 5498 | 29.82 | 0.5453% | - | - | - | 5498
B | 261 | Portfolio Review | Martuscelli |  | FP-325381 | Purch Heath Detecto Pak Bellingham | 394 | 13507.04 | 2024/04 | 13580.71 | 13580.71 | 73.67 | 0.5454% | - | - | - | 13580.71
B | 262 | Portfolio Review | Martuscelli |  | FP-325382 | PURCH NEW RMLD-MOSES LAKE | 394 | 18239.17 | 2024/05 | 18338.65 | 18338.65 | 99.48 | 0.5454% | - | - | - | 18338.65
B | 263 | Portfolio Review | Martuscelli |  | FP-325405 | Purch Sensit Gold G3 Longview | 394 | 3963.68 | 2024/05 | 3985.3 | 3985.3 | 21.62 | 0.5455% | - | - | - | 3985.3
B | 264 | Portfolio Review | Martuscelli |  | FP-325484 | Purchase RD8200 Bellingham | 394 | 12623.22 | 2024/06 | 12692.07 | 12692.07 | 68.85 | 0.5454% | - | - | - | 12692.07
B | 265 | Portfolio Review | Martuscelli |  | FP-325495 | Purchase Ice Machine Mt. Vernon | 398 | 7389.19 | 2024/08 | 7429.49 | 7429.49 | 40.3 | 0.5454% | - | - | - | 7429.49
B | 266 | Portfolio Review | Martuscelli |  | FP-326028 | Purchase RD7200 Bellingham | 394 | 5661.52 | 2024/08 | 5717.78 | 5717.78 | 56.26 | 0.9937% | - | - | - | 5717.78
BB | 267 | (A): Portfolio - Authorized Cost; (D): Total; (G): 60869895.301; (I): 37391135.04; (J): 37391135.04; (K): -23478760.261; (P): 37391135.04
BC | 268
C | 269 | Portfolio Review | Boese |  | FP-317012 | UG-PCAD Upgrade to v7-CNG | 303 | 0 | 2024/09 | -7141.58 | -7141.58 | -7141.58 |  | - | - | - | -7141.58
C | 270 | Portfolio Review | Darras |  | FP-323663 | MAOP INST 4"ST MN FOR LVIEW DWNRATE | 376.1 | 0 | 2024/09 | 431699.53 | 431699.53 | 431699.53 |  | - | - | - | 431699.53
C | 271 | Portfolio Review | Link |  | FP-323949 | UG-JAVA Technology Upgrade-CNG | 303 | 0 | 2024/12 | 25127.71 | 25127.71 | 25127.71 |  | - | - | - | 25127.71
C | 272 | Portfolio Review | Link |  | FP-323966 | UG-Dev&Implmnt ITDataWarehouse CNG | 303 | 0 | 2024/12 | 11019.4 | 11019.4 | 11019.4 |  | - | - | - | 11019.4
C | 273 | Portfolio Review | Martuscelli |  | FP-324633 | Inst Main Clear Creek Rd Silverdale | 376.3 | 0 | 2024/12 | 334210.26 | 334210.26 | 334210.26 |  | - | - | - | 334210.26
C | 274 | Portfolio Review | Darras |  | FP-325221 | Fredonia CS Relief UpgradeVib resit | 377 | 0 | 2024/12 | 18839.46 | 18839.46 | 18839.46 |  | - | - | - | 18839.46
C | 275 | Portfolio Review | Darras |  | FP-325227 | RF; 6in PE; Blaine; 3000' | 376.3 | 0 | 2024/12 | 6008.26 | 6008.26 | 6008.26 |  | - | - | - | 6008.26
C | 276 | Portfolio Review | Darras |  | FP-325239 | GR-MOSES LAKE-4" HP STL JR SIMPLOT | 376.2 | 0 | 2024/12 | 899521.29 | 899521.29 | 899521.29 |  | - | - | - | 899521.29
C | 277 | Portfolio Review | Darras |  | FP-325251 | MAOP; R-201(R-2) MTVE; | 378 | 0 | 2024/09 | 150628.3 | 150628.3 | 150628.3 |  | - | - | - | 150628.3
C | 278 | Portfolio Review | Martuscelli |  | FP-325339 | PUR - 1LC FUSION MACHINE -BREMERTON | 394.1 | 0 | 2024/09 | 2000.19 | 2000.19 | 2000.19 |  | - | - | - | 2000.19
C | 279 | Portfolio Review | Darras |  | FP-325377 | MAOP;R-7(R-1) COLL | 378 | 0 | 2024/09 | 154477.99 | 154477.99 | 154477.99 |  | - | - | - | 154477.99
C | 280 | Portfolio Review | Darras |  | FP-325432 | MAOP; RPL R-002;QUINCY | 378 | 0 | 2024/10 | 550700.07 | 550700.07 | 550700.07 |  | - | - | - | 550700.07
C | 281 | Portfolio Review | Darras |  | FP-325916 | Odorizer Tank UPG, B'ham R-184 | 379 | 0 | 2024/11 | 77687.1 | 77687.1 | 77687.1 |  | - | - | - | 77687.1
C | 282 | Portfolio Review | Darras |  | FP-325917 | INST ODRNT TANK, SEDRO W. Gate | 379 | 0 | 2024/11 | 161503.68 | 161503.68 | 161503.68 |  | - | - | - | 161503.68
C | 283 | Portfolio Review | Darras |  | FP-325970 | Fredonia New Catalysts | 368.1 | 0 | 2024/09 | 33830.5 | 33830.5 | 33830.5 |  | - | - | - | 33830.5
C | 284 | Portfolio Review | Darras |  | FP-325974 | Discharge Coalescent Filter 319839 | 368.1 | 0 | 2024/12 | 5382.39 | 5382.39 | 5382.39 |  | - | - | - | 5382.39
C | 285 | Portfolio Review | Martuscelli |  | FP-326011 | Instl HVAC/AC Unit Mt. Vernon | 390.1 | 0 | 2024/09 | 10648.64 | 10648.64 | 10648.64 |  | - | - | - | 10648.64
C | 286 | Portfolio Review | Martuscelli |  | FP-326083 | Purch (2) Welding Reels Mt. Vernon | 394.1 | 0 | 2024/09 | 3527.67 | 3527.67 | 3527.67 |  | - | - | - | 3527.67
C | 287 | Portfolio Review | Martuscelli |  | FP-326088 | Replace HVAC/AC Unit Shelton | 390.1 | 0 | 2024/12 | 12634.23 | 12634.23 | 12634.23 |  | - | - | - | 12634.23
C | 288 | Portfolio Review | Martuscelli |  | FP-326097 | REPL HVAC/AC UNIT ELMA OFFICE | 390.1 | 0 | 2024/10 | 5783.06 | 5783.06 | 5783.06 |  | - | - | - | 5783.06
C | 289 | Portfolio Review | Martuscelli |  | FP-326098 | Purch Land Mt Vrn Office Burlington | 389 | 0 | 2024/10 | 2328452.45 | 2328452.45 | 2328452.45 |  | - | - | - | 2328452.45
C | 290 | Portfolio Review | Boese |  | FP-326119 | UG - IRTH Solutions 2024-2025 CNG | 303 | 0 | 2024/12 | 59474.49 | 59474.49 | 59474.49 |  | - | - | - | 59474.49
C | 291 | Portfolio Review | Martuscelli |  | FP-326127 | REPLACE RMLD LONGVIEW | 394.1 | 0 | 2024/10 | 18297.08 | 18297.08 | 18297.08 |  | - | - | - | 18297.08
C | 292 | Portfolio Review | Martuscelli |  | FP-326130 | PURCH NEW LOCATOR TRANS-WENATCHEE | 394.1 | 0 | 2024/10 | 1289.73 | 1289.73 | 1289.73 |  | - | - | - | 1289.73
C | 293 | Portfolio Review | Martuscelli |  | FP-326137 | GR; 4" PE; KELS; 500' 1700 13TH AVE | 376.3 | 0 | 2024/12 | 17850.44 | 17850.44 | 17850.44 |  | - | - | - | 17850.44
C | 294 | Portfolio Review | Martuscelli |  | FP-326152 | Purchase 8" Clamp Kit Kennewick | 394.1 | 0 | 2024/12 | 4485.89 | 4485.89 | 4485.89 |  | - | - | - | 4485.89
CC | 295 | (A): Portfolio - New Projects; (D): Total; (G): 0; (I): 5317938.23; (J): 5317938.23; (K): 5317938.23; (P): 5317938.23
CC1 | 296 | (A): Total Portfolio Review; (G): 60869895.301; (I): 42709073.27; (J): 42709073.27; (K): -18160822.031; (P): 42709073.27
D | 297 | (A): Settlement Adjustment; (D): Total; (G): -4599290; (K): 4599290
E | 298 | (A): Total; (G): 97736857.933; (I): 72125001.32; (J): 72125001.32; (K): -25611856.613; (P): 67984747.0597

## Provisional Plant Additions-1
Cascade Natural Gas Corp.
Washington Jurisdiction
Twelve-Months ended December 31, 2023
UG-240008
JAD WP-1.27
PR-1 - Provisional Plant Additions Adjustments - Full Multiparty Settlement Stipulation in Docket UG-240008
Line No | Description | Amount
| A | B
1 | Rate Base Impact of 2024 Provisional Plant Additions |  |  |  | Description | Amount
2 | Provisional Plant Additions | 97736857.993 |  |  | PR-1 Net Operating Income Adjustment | -2575431.9033
3 | Less Estimated Retirements | -2834369 |  |  | PR-1 Rate Base Adjustment | 62684148.1338
4 | Provisional Net Plant Additions | 94902488.993
5 |  |  |  |  | Rate of Return - Settlement Proposal | 7.185%
6 | Estimated Increase to Accumulated Depreciation | -33840422.2858 |  |  | Conversion Factor | 0.7511
7 | Less Estimated Retirements | 2834369
8 | Less Estimated Removal Costs | -1530560.75 |  |  | PR-1 Revenue Requirement Effect | 9425210.58
9 | Net Estimated Increase to Accumulated Depreciation | -32536614.0358
10
11 | Estimated Increase to Accumulated Deferred Income Taxes | 318273.1766
12
13 | Net Operating Income Impact of 2024 Provisional Plant Additions
14 | Estimated New Customer Margin Revenue Offsets | 1571477.0432
15
16 | Estimated Revenue Taxes on New Customer Margin Revenue | 66819.2039
17
18 | Estimated Uncollectible Expense on New Customer Revenue | 10558.5297
19
20 | Estimated Depreciation Expense Increase | 3196917.6633
21 | Less Depreciation Impact of Estimated Retirements | -86731.69
22 | Net Estimated Depreciation Expense Increase | 3110185.9733
23
24 | Effective Property Tax Rate | 0.2311%
25 | Estimated Property Tax Increase | 219325.78
26
27 | Estimated O&M Offsets | -292500 | FERC 880 | -280000
28 |  |  | FERC 903 | -12500
29 | Tax Decrease | -324011.6132
30 | EDIT Amortization Increase | -54882.3818
31
32 | Settlement Adjustment | -103632.9646
33 | 2024 Revenue Offset - New Customer Revenue
34 | Forecast Customer Addtions from IRP | 2024-01-31 | 2024-02-29 | 2024-03-31 | 2024-04-30 | 2024-05-31 | 2024-06-30 | 2024-07-31 | 2024-08-31 | 2024-09-30 | 2024-10-31 | 2024-11-30 | 2024-12-31
35 | A | B | C | D | E | F | G | H | I | J | K | L | M
36 | Schedule 503 | 347 | 265 | 63 | -11 | -63 | -55 | 44 | 331 | 755 | 821 | 696 | 383
37 | Schedule 504 | 65 | 16 | -9 | -34 | -33 | -24 | -13 | 17 | 96 | 143 | 141 | 81
38 | Schedule 505 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1
39
40 | EOP Customer Additions from IRP:
41 | Schedule 503 | 3576 | 3576 | 3576 | 3576 | 3576 | 3576 | 3576 | 3576 | 3576 | 3576 | 3576 | 3576
42 | Schedule 504 | 446 | 446 | 446 | 446 | 446 | 446 | 446 | 446 | 446 | 446 | 446 | 446
43 | Schedule 505 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
44
45 | Usage per Customer:
46 | Schedule 503 | 108.0715 | 84.8139 | 72.4304 | 46.8151 | 29.6857 | 15.4457 | 15.9575 | 8.3754 | 18.2406 | 44.408 | 83.3341 | 107.6458
47 | Schedule 504 | 536.8672 | 426.7509 | 348.5313 | 223.8808 | 155.8946 | 99.4352 | 102.746 | 102.7475 | 144.3912 | 263.3844 | 390.3296 | 528.9664
48 | Schedule 505 Block 1 | 424.0605 | 395.4919 | 414.2202 | 382.0081 | 323.5653 | 207.2286 | 177.5031 | 169.8607 | 179.6209 | 222.6816 | 324.3225 | 388.7152
49 | Schedule 505 Block 2 | 1651.7036 | 1366.4435 | 1494.6101 | 1158.5519 | 916.0143 | 564.7776 | 454.3804 | 475.5676 | 496.084 | 643.9898 | 900.4341 | 1289.3899
50 | Schedule 505 Block 3 | 1649.8286 | 929.4456 | 1422.8889 | 776.5682 | 572.102 | 328.902 | 267.2495 | 349.2008 | 420.1742 | 1009.9694 | 782.1501 | 1064.5354
51
52 | Therms:
53 | Schedule 503 | 386463.8439 | 303294.4149 | 259011.237 | 167410.793 | 106156.2201 | 55233.7083 | 57064.1587 | 29950.3912 | 65228.443 | 158802.9926 | 298002.8388 | 384941.5378
54 | Schedule 504 | 239442.7696 | 190330.9228 | 155444.9771 | 99850.8311 | 69528.9793 | 44348.0779 | 45824.7362 | 45825.3857 | 64398.4609 | 117469.4276 | 174087.0151 | 235919.0366
55 | Schedule 505 Block 1 | 2968.4234 | 2768.4435 | 2899.5414 | 2674.057 | 2264.9571 | 1450.6 | 1242.5215 | 1189.0246 | 1257.3463 | 1558.7714 | 2270.2576 | 2721.0061
56 | Schedule 505 Block 2 | 11561.9254 | 9565.1048 | 10462.2707 | 8109.8635 | 6412.1 | 3953.4429 | 3180.6626 | 3328.9734 | 3472.5881 | 4507.9286 | 6303.0385 | 9025.7293
57 | Schedule 505 Block 3 | 11548.8004 | 6506.119 | 9960.2222 | 5435.9776 | 4004.7143 | 2302.3143 | 1870.7464 | 2444.4057 | 2941.2193 | 7069.7857 | 5475.0507 | 7451.7475
58
59 | Basic Service Charge and Margin Rates:
60 | Schedule 503 - Basic Service Charge | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
61 | Schedule 503 - Margin | 0.3572 | 0.3572 | 0.3572 | 0.3572 | 0.3572 | 0.3572 | 0.3572 | 0.3572 | 0.3572 | 0.3572 | 0.3572 | 0.3572
62 | Schedule 504 - Basic Service Charge | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
63 | Schedule 504 - Margin | 0.29528 | 0.29528 | 0.29528 | 0.29528 | 0.29528 | 0.29528 | 0.29528 | 0.29528 | 0.29528 | 0.29528 | 0.29528 | 0.29528
64 | Schedule 505 - Basic Service Charge | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60
65 | Schedule 505 Block 1 - Margin | 0.22844 | 0.22844 | 0.22844 | 0.22844 | 0.22844 | 0.22844 | 0.22844 | 0.22844 | 0.22844 | 0.22844 | 0.22844 | 0.22844
66 | Schedule 505 Block 2 - Margin | 0.18913 | 0.18913 | 0.18913 | 0.18913 | 0.18913 | 0.18913 | 0.18913 | 0.18913 | 0.18913 | 0.18913 | 0.18913 | 0.18913
67 | Schedule 505 Block 3 - Margin | 0.18319 | 0.18319 | 0.18319 | 0.18319 | 0.18319 | 0.18319 | 0.18319 | 0.18319 | 0.18319 | 0.18319 | 0.18319 | 0.18319
68
69 | Revenue at Current Rates:
70 | Schedule 503
71 | Basic Service Charge | 17880 | 17880 | 17880 | 17880 | 17880 | 17880 | 17880 | 17880 | 17880 | 17880 | 17880 | 17880
72 | Margin | 138044.885 | 108336.765 | 92518.8139 | 59799.1353 | 37919.0018 | 19729.4806 | 20383.3175 | 10698.2797 | 23299.5998 | 56724.429 | 106446.614 | 137501.1173
73 | Total Schedule 503 Revenue | 155924.885 | 126216.765 | 110398.8139 | 77679.1353 | 55799.0018 | 37609.4806 | 38263.3175 | 28578.2797 | 41179.5998 | 74604.429 | 124326.614 | 155381.1173
74
75 | Schedule 504
76 | Basic Service Charge | 5798 | 5798 | 5798 | 5798 | 5798 | 5798 | 5798 | 5798 | 5798 | 5798 | 5798 | 5798
77 | Margin | 70702.661 | 56200.9149 | 45899.7928 | 29483.9534 | 20530.517 | 13095.1004 | 13531.1281 | 13531.3199 | 19015.5775 | 34686.3726 | 51404.4138 | 69662.1731
78 | Total Schedule 504 Revenue | 76500.661 | 61998.9149 | 51697.7928 | 35281.9534 | 26328.517 | 18893.1004 | 19329.1281 | 19329.3199 | 24813.5775 | 40484.3726 | 57202.4138 | 75460.1731
79
80 | Schedule 505
81 | Basic Service Charge | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420
82 | Margin First 500 Therms | 678.1066 | 632.4232 | 662.3712 | 610.8616 | 517.4068 | 331.3751 | 283.8416 | 271.6208 | 287.2282 | 356.0857 | 518.6176 | 621.5866
83 | Margin Next 3,500 Therms | 2186.707 | 1809.0483 | 1978.7293 | 1533.8185 | 1212.7205 | 747.7146 | 601.5587 | 629.6087 | 656.7706 | 852.5845 | 1192.0937 | 1707.0362
84 | Margin > 4,000 Therms | 2115.6247 | 1191.8559 | 1824.6131 | 995.8167 | 733.6236 | 421.761 | 342.702 | 447.7907 | 538.802 | 1295.114 | 1002.9745 | 1365.0856
85 | Total Schedule 505 Revenue | 5400.4383 | 4053.3275 | 4885.7136 | 3560.4968 | 2883.7509 | 1920.8507 | 1648.1024 | 1769.0202 | 1902.8007 | 2923.7843 | 3133.6859 | 4113.7084
From Attachment A to Full Multiparty Settlement Stipulation in Docket UG-240008.

## Provisional Plant Additions-2
Cascade Natural Gas Corp.
Washington Jurisdiction
Twelve-Months ended December 31, 2023
UG-240008
JAD WP-1.27
PR-1 - Provisional Plant Additions Adjustments - Provisional Plant Review
Line No | Description | Amount
| A | B
1 | Rate Base Impact of 2024 Provisional Plant Additions |  |  |  | Description | Amount
2 | Provisional Plant Additions | 67984747.0597 |  |  | PR-1 Net Operating Income Adjustment | -1865089.6694
3 | Less Estimated Retirements | -1971558 |  |  | PR-1 Rate Base Adjustment | 33783863.6611
4 | Provisional Net Plant Additions | 66013189.0597
5 |  |  |  |  | Rate of Return - Settlement Proposal | 7.185%
6 | Estimated Increase to Accumulated Depreciation | -33424221.1132 |  |  | Conversion Factor | 0.7511
7 | Less Estimated Retirements | 1971558
8 | Less Estimated Removal Costs | -1530560.75 |  |  | PR-1 Revenue Requirement Effect | 5714888.6001
9 | Net Estimated Increase to Accumulated Depreciation | -32983223.8632 |  |  | Change to PR-1 from Settlement | -3710321.9799
10
11 | Estimated Increase to Accumulated Deferred Income Taxes | 753898.4645
12
13 | Net Operating Income Impact of 2024 Provisional Plant Additions
14 | Estimated New Customer Margin Revenue Offsets | 1571477.0432
15
16 | Estimated Revenue Taxes on New Customer Margin Revenue | 66819.2039
17
18 | Estimated Uncollectible Expense on New Customer Revenue | 10558.5297
19
20 | Estimated Depreciation Expense Increase | 2338113.2963
21 | Less Depreciation Impact of Estimated Retirements | -60329.67
22 | Net Estimated Depreciation Expense Increase | 2277783.6263
23
24 | Effective Property Tax Rate | 0.2311%
25 | Estimated Property Tax Increase | 152560.74
26
27 | Estimated O&M Offsets | -292500 | FERC 880 | -280000
28 |  |  | FERC 903 | -12500
29 | Tax Decrease | -135186.4619
30 | EDIT Amortization Increase | -54882.38
31
32 | Settlement Adjustment | -103632.9646
33 | 2024 Revenue Offset - New Customer Revenue
34 | Forecast Customer Addtions from IRP | 2024-01-31 | 2024-02-29 | 2024-03-31 | 2024-04-30 | 2024-05-31 | 2024-06-30 | 2024-07-31 | 2024-08-31 | 2024-09-30 | 2024-10-31 | 2024-11-30 | 2024-12-31
35 | A | B | C | D | E | F | G | H | I | J | K | L | M
36 | Schedule 503 | 347 | 265 | 63 | -11 | -63 | -55 | 44 | 331 | 755 | 821 | 696 | 383
37 | Schedule 504 | 65 | 16 | -9 | -34 | -33 | -24 | -13 | 17 | 96 | 143 | 141 | 81
38 | Schedule 505 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1
39
40 | EOP Customer Additions from IRP:
41 | Schedule 503 | 3576 | 3576 | 3576 | 3576 | 3576 | 3576 | 3576 | 3576 | 3576 | 3576 | 3576 | 3576
42 | Schedule 504 | 446 | 446 | 446 | 446 | 446 | 446 | 446 | 446 | 446 | 446 | 446 | 446
43 | Schedule 505 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
44
45 | Usage per Customer:
46 | Schedule 503 | 108.0715 | 84.8139 | 72.4304 | 46.8151 | 29.6857 | 15.4457 | 15.9575 | 8.3754 | 18.2406 | 44.408 | 83.3341 | 107.6458
47 | Schedule 504 | 536.8672 | 426.7509 | 348.5313 | 223.8808 | 155.8946 | 99.4352 | 102.746 | 102.7475 | 144.3912 | 263.3844 | 390.3296 | 528.9664
48 | Schedule 505 Block 1 | 424.0605 | 395.4919 | 414.2202 | 382.0081 | 323.5653 | 207.2286 | 177.5031 | 169.8607 | 179.6209 | 222.6816 | 324.3225 | 388.7152
49 | Schedule 505 Block 2 | 1651.7036 | 1366.4435 | 1494.6101 | 1158.5519 | 916.0143 | 564.7776 | 454.3804 | 475.5676 | 496.084 | 643.9898 | 900.4341 | 1289.3899
50 | Schedule 505 Block 3 | 1649.8286 | 929.4456 | 1422.8889 | 776.5682 | 572.102 | 328.902 | 267.2495 | 349.2008 | 420.1742 | 1009.9694 | 782.1501 | 1064.5354
51
52 | Therms:
53 | Schedule 503 | 386463.8439 | 303294.4149 | 259011.237 | 167410.793 | 106156.2201 | 55233.7083 | 57064.1587 | 29950.3912 | 65228.443 | 158802.9926 | 298002.8388 | 384941.5378
54 | Schedule 504 | 239442.7696 | 190330.9228 | 155444.9771 | 99850.8311 | 69528.9793 | 44348.0779 | 45824.7362 | 45825.3857 | 64398.4609 | 117469.4276 | 174087.0151 | 235919.0366
55 | Schedule 505 Block 1 | 2968.4234 | 2768.4435 | 2899.5414 | 2674.057 | 2264.9571 | 1450.6 | 1242.5215 | 1189.0246 | 1257.3463 | 1558.7714 | 2270.2576 | 2721.0061
56 | Schedule 505 Block 2 | 11561.9254 | 9565.1048 | 10462.2707 | 8109.8635 | 6412.1 | 3953.4429 | 3180.6626 | 3328.9734 | 3472.5881 | 4507.9286 | 6303.0385 | 9025.7293
57 | Schedule 505 Block 3 | 11548.8004 | 6506.119 | 9960.2222 | 5435.9776 | 4004.7143 | 2302.3143 | 1870.7464 | 2444.4057 | 2941.2193 | 7069.7857 | 5475.0507 | 7451.7475
58
59 | Basic Service Charge and Margin Rates:
60 | Schedule 503 - Basic Service Charge | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
61 | Schedule 503 - Margin | 0.3572 | 0.3572 | 0.3572 | 0.3572 | 0.3572 | 0.3572 | 0.3572 | 0.3572 | 0.3572 | 0.3572 | 0.3572 | 0.3572
62 | Schedule 504 - Basic Service Charge | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
63 | Schedule 504 - Margin | 0.29528 | 0.29528 | 0.29528 | 0.29528 | 0.29528 | 0.29528 | 0.29528 | 0.29528 | 0.29528 | 0.29528 | 0.29528 | 0.29528
64 | Schedule 505 - Basic Service Charge | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60
65 | Schedule 505 Block 1 - Margin | 0.22844 | 0.22844 | 0.22844 | 0.22844 | 0.22844 | 0.22844 | 0.22844 | 0.22844 | 0.22844 | 0.22844 | 0.22844 | 0.22844
66 | Schedule 505 Block 2 - Margin | 0.18913 | 0.18913 | 0.18913 | 0.18913 | 0.18913 | 0.18913 | 0.18913 | 0.18913 | 0.18913 | 0.18913 | 0.18913 | 0.18913
67 | Schedule 505 Block 3 - Margin | 0.18319 | 0.18319 | 0.18319 | 0.18319 | 0.18319 | 0.18319 | 0.18319 | 0.18319 | 0.18319 | 0.18319 | 0.18319 | 0.18319
68
69 | Revenue at Current Rates:
70 | Schedule 503
71 | Basic Service Charge | 17880 | 17880 | 17880 | 17880 | 17880 | 17880 | 17880 | 17880 | 17880 | 17880 | 17880 | 17880
72 | Margin | 138044.885 | 108336.765 | 92518.8139 | 59799.1353 | 37919.0018 | 19729.4806 | 20383.3175 | 10698.2797 | 23299.5998 | 56724.429 | 106446.614 | 137501.1173
73 | Total Schedule 503 Revenue | 155924.885 | 126216.765 | 110398.8139 | 77679.1353 | 55799.0018 | 37609.4806 | 38263.3175 | 28578.2797 | 41179.5998 | 74604.429 | 124326.614 | 155381.1173
74
75 | Schedule 504
76 | Basic Service Charge | 5798 | 5798 | 5798 | 5798 | 5798 | 5798 | 5798 | 5798 | 5798 | 5798 | 5798 | 5798
77 | Margin | 70702.661 | 56200.9149 | 45899.7928 | 29483.9534 | 20530.517 | 13095.1004 | 13531.1281 | 13531.3199 | 19015.5775 | 34686.3726 | 51404.4138 | 69662.1731
78 | Total Schedule 504 Revenue | 76500.661 | 61998.9149 | 51697.7928 | 35281.9534 | 26328.517 | 18893.1004 | 19329.1281 | 19329.3199 | 24813.5775 | 40484.3726 | 57202.4138 | 75460.1731
79
80 | Schedule 505
81 | Basic Service Charge | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420
82 | Margin First 500 Therms | 678.1066 | 632.4232 | 662.3712 | 610.8616 | 517.4068 | 331.3751 | 283.8416 | 271.6208 | 287.2282 | 356.0857 | 518.6176 | 621.5866
83 | Margin Next 3,500 Therms | 2186.707 | 1809.0483 | 1978.7293 | 1533.8185 | 1212.7205 | 747.7146 | 601.5587 | 629.6087 | 656.7706 | 852.5845 | 1192.0937 | 1707.0362
84 | Margin > 4,000 Therms | 2115.6247 | 1191.8559 | 1824.6131 | 995.8167 | 733.6236 | 421.761 | 342.702 | 447.7907 | 538.802 | 1295.114 | 1002.9745 | 1365.0856
85 | Total Schedule 505 Revenue | 5400.4383 | 4053.3275 | 4885.7136 | 3560.4968 | 2883.7509 | 1920.8507 | 1648.1024 | 1769.0202 | 1902.8007 | 2923.7843 | 3133.6859 | 4113.7084
Reflects updated 2024 provisional plant additions based on the Provisional Plant Review tab.