**Klamath Chronology**

**Date Event**

December 15, 2000 Notice of Intent to file an application filed with the Federal Energy Regulatory Commission and the First Stage Consultation Document released to public

January 23, 2001 Public meetings

August 7, 2001 Consultation meetings with stakeholders begin

August 8, 2001 Start of workgroup meetings

January 2002 PacifiCorp begins conducting additional studies

January-December 2003 PacifiCorp continues natural resource studies

January-December 2003 PacifiCorp continues stakeholder meetings (over 200 in all)

February 23, 2004 PacifiCorp submits final license application

April 16, 2004 FERC issues scoping document No. 1

August 16, 2004 FERC issues notice of application

February 17, 2005 FERC submits additional information requests to PacifiCorp

May 17, 2005 FERC issues scoping document No. 2

December 28, 2005 FERC issues Notice of Ready for Environmental Analysis

February 28, 2006 License expires - FERC issues annual license to operate

March 24, 2006 Federal agencies issue draft terms and conditions

March 26, 2006 PacifiCorp submits 401 applications to Oregon and California

March 27, 2006 PacifiCorp files alternative conditions

August 25, 2006 Trial-type hearing closes

September 25, 2006 FERC issues draft environmental impact statement

September 27, 2006 Decision issued in trial-type hearing

November 14, 2006 Public meetings on the draft environmental impact statement begin

January 24, 2007 Federal agencies issue modified terms and conditions

February 28, 2007 PacifiCorp resubmits 401 applications

March 21, 2007 FERC initiates Endangered Species Act consultation

September 17, 2007 PacifiCorp signs MOU for California Environmental Quality Act analysis

October 22, 2007 U.S. Fish and Wildlife service issues draft biological opinion

November 2, 2007 National Marine Fisheries Service issues draft biological opinion

November 16, 2007 FERC issues final environmental impact statement

December 3, 2007 U.S. Fish and Wildlife service issues final biological opinion

January 15, 2008 Klamath Basin Restoration Agreement (proposed) released

February 22, 2008 PacifiCorp withdraws and resubmits California and Oregon 401 applications

November 10, 2008 Interim Conservation Plan released

November 13, 2008 Agreement in Principle signed

June 2009 California Klamath River TMDL issued

August 27, 2009 PacifiCorp submits comments on the California Klamath River TMDL

September 10, 2009 PacifiCorp withdraws and resubmits California 401 application

September 30, 2009 Draft Klamath Hydroelectric Settlement Agreement released

December 23, 2009 Revised California TMDL issued

January 7, 2010 Klamath Basin Restoration Agreement Public Review Draft released

January 8, 2010 Klamath Hydroelectric Settlement Agreement Public Review Draft released

January 20, 2010 PacifiCorp withdraws and resubmits Oregon 401 application

February 18, 2010 Klamath Hydroelectric Settlement Agreement (“KHSA”) and Klamath Basin Restoration Agreement (“KBRA”) executed

March 17, 2010 KHSA parties petition ODEQ and SWRCB to hold in abeyance processing relicensing 401 applications

March 18, 2010 PacifiCorp files applications with the public utility commissions in California and Oregon to evaluate the Company’s decision to enter into the KHSA and begins collection of Oregon customer surcharges

June 7, 2010 Public scoping for Klamath Facilities Removal NEPA process begins

September 16, 2010 Oregon Public Utility Commission finds Company’s decision to enter into the KHSA benefits customers and affirms dam removal surcharges

September 16, 2010 PacifiCorp and CDFG submit HGMP to NMFS for approval

March 29, 2010 Oregon DEQ issues 401 certification abeyance

February 14, 2011 PacifiCorp submits coho salmon Habitat Conservation Plan to NMFS

May 5, 2011 California Public Utilities Commission finds Company’s decision to enter into the KHSA benefits customers and approves dam removal surcharges

May 18, 2010 SWRCB issues 401 certification abeyance resolution

August 25, 2011 PacifiCorp submits sucker Habitat Conservation Plan to USFWS

September 21, 2011 Department of Interior and California Department of Fish and Game issue Klamath Facilities Removal Draft EIS/R

November 10, 2011 Klamath settlement legislation introduced in U.S. Congress

January 3, 2012 PacifiCorp withdraws and resubmits Oregon 401 application

January 10, 2012 PacifiCorp begins collection of dam removal surcharges for California customers