## 2022 Dave
David James Rev.
2022-06-21
All Values in $000's
| Changes to WF2021 Baseline | Capital |  |  | Capital Budget Forecast
Unit Estimates provided as part of WA GRC PC-305 | System & Transmission | 2022 Expected CAPx | 2020 YE Actuals | 2021 YE Actuals | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 10-yr | comments and notes
Internal Labor to Develop Computer Algorith (1.5 FTE) | Fire-Weather Dashboard | 0 | 197.75 | 188.7 | Capital Budget Forecast 10-yr: 386.45 | 2020-2021 Development of FW Dashboard Version 1.0 and 2.0
Removed from WFRES Plan 2021 | Conforming Rights-of-Way | 0 |  | 0.372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.372 | Removed from plan August 2021. See WFRES 2022 for explanation
Maintenance followup. Budget allocation | Transmission Inspection Pgm | 200 | 1.272 | 0.808 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 1602.08 | CapX follow-up on Tx aerial and ground patrols related to fire ignition
Transmission Steel Replacement $45k per structure | Transmssion Steel Conversion | 4000 | 73.5668 | 5454.6 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 37528.1668 | See 2022 WFRES Plan for updated decision matrix on where wood pole will be converted to steel. Will be based on fire history on a go-forward basis. Not WUI
| Transmission Total | 4200 | 272.5888 | 5644.48 | 4200 | 4200 | 4200 | 4200 | 4200 | 4200 | 4200 | 4200 | 39517.0688
Capital Budget Forecast
| Electric Distribution | 2022 Expected CAPx | 2020 YE Actuals | 2021 YE Actuals | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 10-yr
| Fire Ignition Tracking System | 0 | 2.505 | -2.5 | Capital Budget Forecast 2022: 0; Capital Budget Forecast 10-yr: 0.005 | OMT work around is allowing tracking for fire-ignition events. Any new development of fire ignition tracking will be paired with the OMS replacement project.
$60k per unit. Midline reclosers | Distribution Auto DLM | 750 | 30.533 | 1355.4 | 750 | 650 | 650 | 650 | 650 | 650 | 650 | 650 | 6685.933 | Replacing midline reclosers with DLM Automation devices.
$750k per substation. Add SCADA comm and equipment | Substation Auto DLM | 1500 | 0.4 | 514.7 | 1500 | 1500 | 3000 | 4500 | 4500 | 4500 | 4500 | 4500 | 29015.1
$16k per mile. Advance 1,500 line miles into 2022-2029 | WPM Make-Ready for GH (XD007) | 3000 |  | 14.6 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 24014.6
Placeholder | OE Sponsored GH (XD008) |  |  | 1.28
$60k per mile. | WA Dist Grid Hardening (XD005) | 9000 | 1513.27 | 7133.8 | 9000 | 11500 | 12500 | 14700 | 14700 | 14700 | 14700 | 14700 | 115147.07
$60k per mile. | ID Dist Grid Hardening (XD006) | 6595 | 1601.649 | 4714.1 | 6595 | 6650 | 7650 | 7820 | 7820 | 8400 | 8400 | 8400 | 68050.749
| Distribution Total | 20845 | 3148.357 | 13731.38 | 20845 | 23300 | 26800 | 30670 | 30670 | 31250 | 31250 | 31250 | 242913.457
| T&D CapX Total | 25045 | 3420.9458 | 19375.86 | 25045 | 27500 | 31000 | 34870 | 34870 | 35450 | 35450 | 35450 | 282430.5258
|  |  | Total Grid Hardening: |  | Capital Budget Forecast 2022: PLAN
| Distribution |  | 2020 act | 2021 act | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | Totals
| Grid Hardening Budget |  | 3114.919 | 11847.9 | 15595 | 18150 | 20150 | 22520 | 22520 | 23100 | 23100 | 23100 | 183197.819
| Miles Projected at $60k/mi (forecast) |  | 66.5 | 146 | 259.9167 | 302.5 | 335.8333 | 375.3333 | 375.3333 | 385 | 385 | 385
| Cumulative Miles |  | 66.5 | 212.5 | 472.4167 | 774.9167 | 1110.75 | 1486.0833 | 1861.4167 | 2246.4167 | 2631.4167 | 3016.4167
|  | Operating |  |  | PLAN 2022: O&M Budget Forecast
| System & Transmission | 2022 Expected O&M | 2020 YE Actual | 2021 YE Actual | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 10-yr
Internal unloaded WF labor 33% (4 FTE) | WFRES Transmission Planning | 147 | 91.927 | 187.49 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 1455.417 | WFRES Team Labor based on 2021 HC
Subscription to Weather data service | Fire-Weather Dashboard | 150 |  | 0 | 150 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 675 | On going support of FW DB
$400 per mile. 1875 miles non-urban transmission | Digital Data Collection (Geo Digital) | 750 | 491.4217 | 450 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 6941.4217 | Based on $450mile (GeoDigital)- 2022 is full system
$90 per pole wrap | Transmission FR Pole Wraps | 550 | 178.2318 | 420.82 | 550 | 550 | 550 | 550 | 550 | 550 | 550 | 550 | 4999.0518 | Genic fire mesh $90/pole (assume H-frame $500/structure 500 structures/year - 8 structure/miles - 62.5 miles/year)
$2k per acre treated | Fuel Reduction Partner | 300 |  | 0 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 2400 | Estimated from WS. ~ $1k per acre
2021 only | Nox-PC Fire Damage (risk tree) |  |  | 513.13 | O&M Budget Forecast 10-yr: 513.13
$2000 per hour helicopter resource | Transmission Inspection Pgm | 150 | 137.372 | 172.047 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 1509.419 | Transmission Fire Inspection and O&M followup
| Transmission O&M | 2047 | 898.9525 | 1743.487 | 2047 | 1972 | 1972 | 1972 | 1972 | 1972 | 1972 | 1972 | 18493.4395
|  |  | Operating |  | O&M Budget Forecast 2022: O&M Budget Forecast
| Electric Distribution | 2022 Expected O&M | 2020 YE Actual | 2021 YE Actual | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 10-yr
Internal unloaded WF Labor 67% (4 FTE) | WFRES Distribution Planning | 294 | 232.53 | 269.06 | 294 | 294 | 294 | 294 | 294 | 294 | 294 | 294 | 2853.59 | WFRES Team Labor based on 2021 HC
$915 per tree removal | WA Dx Risk Tree | 5543.7 |  | 2110.68 | 3686.1 | 3231.5 | 3232 | 2688 | 2688 | 2688 | 2688 | 2688 | 25700.28
$915 per tree removal | ID Dx Risk Tree | 2856 | 1239.1134 | 3151.935 | 1898.9 | 1818 | 1818 | 1512 | 1512 | 1512 | 1512 | 1512 | 17485.9484 | Estimate from AM C H. 100% system minus heavy incorporated and no veg areas (17%). 11.02.21
$5k per household | Customer Choice RTRP | 350 |  | 0 | 350 | 500 | 750 | 750 | 750 | 500 | 300 | 200 | 4100 | Includes Public Outreach, Media messaging, and voucher remove/replace program
$70 per mile | Digital Data Collection (AiDASH) | 535 | 59.2817 | 327.211 | 535 | 535 | 535 | 535 | 535 | 535 | 535 | 535 | 4666.4927 | Based on AiDash Contract --- 70$/miles for 7650 miles OH System (535 base, 2021 reflects a negotiated price to establish baseline)
| Distribution O&M | 9578.7 | 1530.9251 | 5858.886 | 6764 | 6378.5 | 6629 | 5779 | 5779 | 5529 | 5329 | 5229 | 54806.3111 | Dx Grid Hardening Blended WA/ID Rate = $59.1k/mile
| T&D O&M | 11625.7 | 2429.8776 | 7602.373 | 8811 | 8350.5 | 8601 | 7751 | 7751 | 7501 | 7301 | 7201 | 73299.7506
Total Risk Tree
TOTAL
Note on D38: James, Dave: reallocated 150 to 2021-2029 due to COVID work restrictions
Note on F47: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Reflects 100% risk tree @ 950/mille X 5500 of treed miles