## APR
APPROPRIATION REQUEST for CAPITAL EXPENDITURES
PROJECT SUMMARY INFORMATION
TITLE: | JB U2 Turbine Upgrade HP/IP/LP
Plant/Hydro Facility: | Jim Bridger |  |  |  | APR: | 90000565
Unit: | U2 |  |  |  | Project/WBS: | SJIM/2008/C/131
Original Capital Plan: | N |  |  |  | DATE Submitted: | 2011-12-16
Investment Reason: | Asset Performance - Efficiency |  |  |  | FERC Loc/ProfitCtr: | 517002 | 1060 | 1
Overhaul Related: | Y |  |  |  | Responsible Person: | Tom Faucheux
Asbestos Related: | N |  |  |  | Retirement: | Y
TOTAL PROJECT PLAN by Calendar Year
COST ELEMENT | TOTAL | PRIOR | CY12 | CY13 | CY14 | CY15 | FUTURE |  | CY15 | CY16 | CY17 | CY18 | CY19 | CY20 | CY21
Materials | 1800000 | 0 | 0 | 1800000 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Labor | 390328 | 34826 | 155502 | 200000 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contracts | 36303764 | 15136093 | 11383766 | 9783905 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other | 183740.2637 | 54237 | 0 | 129503.2637 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Salv/Reimburs. (credit) | -20000 | 0 | 0 | -20000 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Removal Labor | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Removal Contract | 250000 | 0 | 0 | 250000 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Removal Asbestos | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Corporate Escalation | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contingency | 1400000 | 0 | 0 | 1400000 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Surcharge | 508225 | 508225 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
AFUDC | 3322056 | 1240150 | 1383605 | 698301 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total 100% (escalated) | 44138113.2637 | 16973531 | 12922873 | 14241709.2637 | 0 | 0 | 0
Other Owner's Share (escalated) | -13605351.0607 | -5244459.8089 | -3846422.282 | -4514468.9698 | 0 | 0 | 0 | 0.33333
Total PAC Share (escalated) | 30532762.203 | 11729071.1911 | 9076450.718 | 9727240.2939 | 0 | 0 | 0
Total PAC share esc wo AFUDC | 27210706.203 | 10488921.1911 | 7692845.718 | 9028939.2939 | 0 | 0 | 0
Total 100% (unescalated) APR Amt | 44138113.2637 | 16973531 | 12922873 | 14241709.2637 | 0 | 0 | 0
Total PAC Share (unescalated) | 30532762.203 | 11729071.1911 | 9076450.718 | 9727240.2939 | 0 | 0 | 0
PROJECT REVIEW and AUTHORIZATION |  |  |  | ECONOMIC DATA
DESCRIPTION | DATE | EMPLOYEE |  | DESCRIPTION |  |  | MEASURE
Technical Review | See APR Review List and Workflow |  |  |  |  | Internal Rate of Return: | 13.3%
Environmental Review | See APR Review List and Workflow |  |  |  |  | Payback Years: | 10
Accounting Review | See APR Review List and Workflow |  |  |  |  | Net Benefit to Capital Ratio:
Economic Review | See APR Review List and Workflow |  |  |  |  | Cash Flow NPV: | 40054
Controller Review | See APR Review List and Workflow |  |  |  |  | Present Value Revenue Requirement: | 43426
Pre Approver | See APR Review List and Workflow |  |  |  |  | LABOR | AMT
Pre Approver | See APR Review List and Workflow |  |  |  |  | SLC Eng
Pre Approver | See APR Review List and Workflow |  |  |  |  | Plant Eng
Pre Approver | See APR Review List and Workflow |  |  |  |  | Plant
Authorized & Approved | See APR Review List and Workflow |  |  |  |  | TOTAL | 0
PROPERTY RETIREMENT UNIT(S) |  |  |  |  | S |  | 30532762.203 | 100%
SYSTEM |  | SUBSYSTEM |  |  | ACCT | PRU | AMT | %
Main Turbine |  | High Pressure (HP) Turbine |  |  | 314 | TBHPT07 | 4579914.3305 | 15%
Main Turbine |  | Intermediate (IP) Turbine |  |  | 314 | TBIPT06 | 4579914.3305 | 15%
Main Turbine |  | Low Pressure (LP)Turbine |  |  | 314 | TBLPT06 | 21372933.5421 | 70%
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Escalation Rates |  |  | 0% | 1.5% | 3.327% | 5.29% |  |  | 7.291% | 9.329% | 11.52% | 13.75% | 15.91% | 18.11% | 20.35%
Note on A27: Capital Surcharge should match the SAP IM amount - manually enter on this row to the right.
Note on A28: AFUDC should match the SAP IM amount - manually enter on this row to the right.
Note on A31: PAC share should match the SAP IM amount - this is a calculated field where the JVA % is applied to total which does not include AFUDC.
Note on A34: PAC share should match the SAP IM amount - this is a calculated field where the JVA % is applied to total which does not include AFUDC.
Note on G9: The PROJECT is setup only after the APR is approved. This field can only be populated after approval.
Only input data in GREEN highlighted fields. All other fields will be populated from SAP IM.
PRU Catalog

## HYDRO Env Checklist
APR HYDRO ENVIRONMENTAL CHECKLIST
The purpose of this checklist is to identify applicable environmental regulatory requirements that may affect a project's budget, scope or schedule. This checklist does not constitute a comprehensive regulatory evaluation of all potential environmental impacts of a proposed project.
APR Face Sheet Information
APR: | 90000565 | Prepared by:
TITLE: | JB U2 Turbine Upgrade HP/IP/LP | Reviewed by:
Plant Facility: | Jim Bridger | Review Complete Date:
Calendar Year1: |  | Date Review is needed:
Provide a site map (footprint ) if available
Resource Areas | WILL THE PROPOSED ACTIVITY: | YES | NO | Project Action Description (To be filled out by Project Manager/Engineer) | REQUIREMENTS/COMMENTS (To be filled out by Regional Complaince Analyst) | PERMITTING
[6 empty] | Required Permits or Environmental Clearances/Lead | Duration to Acquire (wks)
Aquatic | 1a) Require work within the bank of a stream, floodplain, reservoir, wetland, mudflat or shoreline (zone of 200 feet landward from ordinary high water mark)? 1b) Result in material or equipment entering the water (e.g. sediment, fill material, turbine oil, sheet erosion, etc.)?
Aquatic | 2) Affect stream flow or water levels (during or after activity)?
Aquatic Invasive Species | 3) Will you be working in areas with known aquatic invasive species?
Spills | 4) Involve the addition or removal of oil containing equipment or bulk storage containers > or = to 55 gallons?
Spills | 5) Require use of heavy equipment, generators or machinery, or onsite fuel storage?
Cultural/Historic | 6) Require digging or soil disturbance (e.g. trenching, excavation, grading, clearing, etc.)? If yes, provide total surface area of disturbance, and excavation depth and quantity.
Cultural/Historic and | 7) Require construction, demolition or renovation of project structures or buildings? If yes, describe what building renovation or construction is involved (plumbing water line, septic install, electrical, flooring, acoustic tile, siding replacement, paint removal, etc.)
Land Management
Land Management | 8) Result in cumulative ground disturbance equal to or greater than 1 acre (includes temporary use and staging areas)?
Land Management | 9) Involve activities on non-PacifiCorp owned lands?
Wildlife Management | 10) Require vegetation removal? If yes, describe type, method and area of vegetation removal.
Wildlife Management | 11) Cause significant noise or activity over background levels? Provide construction time window, construction methods (e.g. drilling, blasting, etc.), maximum vertical height of structure or equipment, and construction noise levels.
FERC | 12) Change/modify project water retention or conveyance facilities in a way that may affect operations or dam safety (during or after activity)?
FERC | 13) Require construction/ground disturbance work within the FERC project boundary?
FERC | 14) Be non-routine project maintenance?
FERC | 15) Require construction of a cofferdam or dewatering of water conveyance facilities?
FERC | 16) Required blasting, excavation or drilling in the proximity of dams, water conveyance systems or project features?
Hazardous Materials | 17) Require the use or transportation of hazardous chemicals?
Waste Management | 18) Generate waste (e.g. wood waste, concrete, used oil, waste solvents, aerosol cans, paint chips, asbestos, fluorescent light tubes, batteries, mercoid switches, etc.)?
Public Safety | 19) Create public health or safety risks (e.g., unposted hazards, improper waste disposal, security risks, etc)?
Security | 20) Does project require a security system (cameras, card readers, motion detectors, etc)?
Security | 21) Is project site a critical asset (HCC, Swift 1, Lemolo 2, Copco 1)?
Security | 22) Are interconnections required with existing systems?
Recommended Permitting Lead (Consultant, SME, Compliance Analyst, etc.): |  |  |  |  | Anticipated Total Permitting Timeline (Weeks):
Instructions:
Project Manager / Engineer |  |  |  |  | Compliance Analysts
1. Project Manager/Engineer: Fill out the Environmental Checklist in the IM:APR Detail spreadsheet. Fill out checklist header, including a detailed project description and provide answers to all checklist questions. The Quick Reference Guide may be used as a reference. |  |  |  |  | 2. Compliance Analyst: complete an environmental review and list potential environmental issues and associated required actions and permits/environmental clearances on this form. Save the completed checklist to IM and approve/reject the APR as appropriate. If there are environmental impacts or permit requriements for a project, in addition to saving the checklist to IM, email the completed environmental checklist to the Project Manager/Engineer. Attach any supporting documentation to the e-mail as well.
3. Project Manager/Engineer: Monitor project scope and construction activities to assure that work does not take place that is outside the scope coverage of the environmental review. If scope changes occur, consult the compliance analyst shall and revise and re-submit the environmental checklist. |  |  |  |  | 1 Calendar year that the project will begin in.
Compliance Staff:
Hydro East/Utah/Idaho - Jim Burris
Hydro North- Briana Weatherly
Hydro South - Diane Barr | [6 empty] | Template Revised: 01/21/2010

## THERMAL Env Checklist
APR THERMAL ENVIRONMENTAL CHECKLIST
The purpose of this checklist is to identify applicable environmental regulatory requirements that may affect a project's budget, scope or schedule. This checklist does not constitute a comprehensive regulatory evaluation of all potential environmental impacts of a proposed project.
APR Face Sheet Information
ARP: 90000565 | APR Preparer:
Title: JB U2 Turbine Upgrade HP/IP/LP | Contact Name (Compliance Staff reviewer):
Plant: Jim Bridger | Review Complete Date:
Will the proposed activity: | YES | NO | Requirements/Comments
1) Will the project have the potential to increase generation or the amount of coal burned?
2) Will the project result in an operational change to the plant./unit?
3) Will the project involve a pollution control device (scrubber, EXP, baghouse, dust collector, etc.)?
4) Will the project involve the boiler and/or associated equipment (fans, mills, feeders, RW heaters, etc.)?
5) Will the project affect the plant site, including coal year, landfill, and ash pile?
6) Does the project have the potential to increase the emission rate in lb/hour of any pollutant (SO2, NOx, particulate matter, VOCs, CO?)
7) Does the project have the potential of increasing the tons/year of any pollutant?
8) Will this project disturb greater than one acre during construction?
9) Does this project have the potential to increase or change the characteristics of any water discharge from the plant? Is there potential of affecting any groundwater or surface waters?
10) Does this project have the potential to increase or change the characteristics of any waste generated by the plant?
11) Does this project have the potential to increase the amount of oil stored on site (either permanently or temporarily)? Will any additional oil storage containers >= to 55 gallons be brought on site?

## NERC CIP Checklist
APR NERC CIP CHECKLIST
The purpose of this checklist is to ensure that NERC-CIP standards are appropriately addressed as they relate to this project. This checklist does not constitute a comprehensive evaluation of all potential NERC-CIP implications this proposed project.
| APR: 90000565 | NERC-CIP Review Completed By:
| Title: JB U2 Turbine Upgrade HP/IP/LP | NERC-CIP Review Completion Date:
Plant: Jim Bridger
|  | YES | NO | Requirements/Comments
1 | Is the project being completed at an existing Critical Asset?
If you answered YES to question 1, you must answer questions 2, 3 & 4
2 | Will any portion of the system and/or equipment planned for installation be classified as a Critical Cyber Asset?
3 | Will any portion of the system and/or equipment planned for installation be linked, connected or associated with the Electronic Security Perimeter or an existing Critical Cyber Asset?
4 | Will any portion of the system and/or equipment planned for installation be linked, connected or associated with the Physical Security Perimeter?
If you answered YES to questions 2, 3 or 4, the CIP Representative must answer questions 5 & 6
5 | The CIP Representative has been notified that this project may have implications relating to NERC-CIP compliance.
6 | The CIP Representative has evaluated this project against all CIP standards, including all corporate policies and procedures, to ensure full compliance.

## AFUDC Estimate
USER INPUT in BLUE only
|  |  |  | CAPSchg %: | 4.7%
APR: 90000565 |  |  |  | Start Period: | 2008-01-08
TITLE: JB U2 Turbine Upgrade HP/IP/LP |  |  |  | End Period: | 2013-05-01
PLANT: Jim Bridger |  |  |  | AFUDC %: | 7.6%
PERIOD | DIRECT $ | CAP Scharge | TOTAL | AFUDC Est | TOTAL w/AFUDC
2008-01-08 | 0 | 0 | 0 | 0 | 0
2008-02-08 | 0 | 0 | 0 | 0 | 0
2008-03-10 | 0 | 0 | 0 | 0 | 0
2008-04-10 | 0 | 0 | 0 | 0 | 0
2008-05-11 | 0 | 0 | 0 | 0 | 0
2008-06-11 | 0 | 0 | 0 | 0 | 0
2008-07-12 | 0 | 0 | 0 | 0 | 0
2008-08-12 | 0 | 0 | 0 | 0 | 0
2008-09-12 | 0 | 0 | 0 | 0 | 0
2008-10-13 | 0 | 0 | 0 | 0 | 0
2008-11-13 | 0 | 0 | 0 | 0 | 0
2008-12-14 | 0 | 0 | 0 | 0 | 0
2009-01-14 | 0 | 0 | 0 | 0 | 0
2009-02-14 | 0 | 0 | 0 | 0 | 0
2009-03-17 | 0 | 0 | 0 | 0 | 0
2009-04-17 | 0 | 0 | 0 | 0 | 0
2009-05-18 | 0 | 0 | 0 | 0 | 0
2009-06-18 | 0 | 0 | 0 | 0 | 0
2009-07-19 | 0 | 0 | 0 | 0 | 0
2009-08-19 | 0 | 0 | 0 | 0 | 0
2009-09-19 | 0 | 0 | 0 | 0 | 0
2009-10-20 | 0 | 0 | 0 | 0 | 0
2009-11-20 | 0 | 0 | 0 | 0 | 0
2009-12-21 | 0 | 0 | 0 | 0 | 0
2010-01-21 | 0 | 0 | 0 | 0 | 0
2010-02-21 | 0 | 0 | 0 | 0 | 0
2010-03-24 | 0 | 0 | 0 | 0 | 0
2010-04-24 | 0 | 0 | 0 | 0 | 0
2010-05-25 | 0 | 0 | 0 | 0 | 0
2010-06-25 | 0 | 0 | 0 | 0 | 0
2010-07-26 | 0 | 0 | 0 | 0 | 0
2010-08-26 | 0 | 0 | 0 | 0 | 0
2010-09-26 | 0 | 0 | 0 | 0 | 0
2010-10-27 | 0 | 0 | 0 | 0 | 0
2010-11-27 | 0 | 0 | 0 | 0 | 0
2010-12-28 | 0 | 0 | 0 | 0 | 0
2011-01-28 | 0 | 0 | 0 | 0 | 0
2011-02-28 | 0 | 0 | 0 | 0 | 0
2011-03-31 | 0 | 0 | 0 | 0 | 0
2011-05-01 | 0 | 0 | 0 | 0 | 0
2011-06-01 | 0 | 0 | 0 | 0 | 0
2011-07-02 | 0 | 0 | 0 | 0 | 0
2011-08-02 | 0 | 0 | 0 | 0 | 0
2011-09-02 | 0 | 0 | 0 | 0 | 0
2011-10-03 | 0 | 0 | 0 | 0 | 0
2011-11-03 | 0 | 0 | 0 | 0 | 0
2011-12-04 | 0 | 0 | 0 | 0 | 0
2012-01-04 | 0 | 0 | 0 | 0 | 0
2012-02-04 | 0 | 0 | 0 | 0 | 0
2012-03-06 | 0 | 0 | 0 | 0 | 0
2012-04-06 | 0 | 0 | 0 | 0 | 0
2012-05-07 | 0 | 0 | 0 | 0 | 0
2012-06-07 | 0 | 0 | 0 | 0 | 0
2012-07-08 | 0 | 0 | 0 | 0 | 0
2012-08-08 | 0 | 0 | 0 | 0 | 0
2012-09-08 | 0 | 0 | 0 | 0 | 0
2012-10-09 | 0 | 0 | 0 | 0 | 0
2012-11-09 | 0 | 0 | 0 | 0 | 0
2012-12-10 | 0 | 0 | 0 | 0 | 0
2013-01-10 | 0 | 0 | 0 | 0 | 0
2013-02-10 | 0 | 0 | 0 | 0 | 0
2013-03-13 | 0 | 0 | 0 | 0 | 0
2013-04-13 | 0 | 0 | 0 | 0 | 0
2013-05-14 | 0 | 0 | 0 | 0 | 0
2013-06-14 | 0 | 0 | 0 | 0 | 0
2013-07-15 | 0 | 0 | 0 | 0 | 0
2013-08-15 | 0 | 0 | 0 | 0 | 0
2013-09-15 | 0 | 0 | 0 | 0 | 0
2013-10-16 | 0 | 0 | 0 | 0 | 0
2013-11-16 | 0 | 0 | 0 | 0 | 0
2013-12-17 | 0 | 0 | 0 | 0 | 0
TOTAL | 0 | 0 | 0 | 0 | 0
Formulas:
PERIOD = [PERIOD, row above]+31

## JO%
FERC Loc | PAC % | JO %
1 | 0% | 0%
300 | 84.69% | 15.31% | HUNTER PLANT COMMON FACILITIES
301 | 93.75% | 6.25% | HUNTER NO 1 STEAM ELECTRIC STATION
302 | 60.31% | 39.69% | HUNTER NO 2 STEAM ELECTRIC STATION
305 | 77.03% | 22.97% | HUNTER PLANT COMMON FACILTIES - UNITS 1
201003 | 47.5% | 52.5% | CENTRALIA UNIT 3 SKOOKUMCHUCK
517000 | 66.67% | 33.33% | JIM BRIDGER PLANT
517001 | 66.67% | 33.33% | JIM BRIDGER UNIT 1
517002 | 66.67% | 33.33% | JIM BRIDGER UNIT 2
517003 | 66.67% | 33.33% | JIM BRIDGER UNIT 3
517004 | 66.67% | 33.33% | JIM BRIDGER UNIT 4
517005 | 66.67% | 33.33% | JIM BRIDGER OUTSIDE RESOURCES - COMMON
517009 | 66.67% | 33.33% | JIM BRIDGER OUTSIDE RESOURCES - UNIT 4
519000 | 80% | 20% | WYODAK PLANT COMMON
519001 | 80% | 20% | WYODAK PLANT UNIT 1
519005 | 85.6% | 14.4% | WYODAK COAL FACILITIES
519006 | 57.6% | 42.4% | WYODAK BACK-UP COAL SYSTEM
576500 | 78.79% | 21.21% | FOOTE CREEK WIND PLANT

## PRU
CODE | SYSTEM | SUBSYSTEM | UNIT | STEAM ACCT | GAS ACCT | WIND ACCT | HYDRO ACCT | MEAS
25125 | Wind Generation | Step-up Transformer |  |  |  | 353
ABAUX** | Auxiliary Boiler | Auxiliary Boiler |  | 312 | 342
AC120 | AC Electrical System | 120 Volt Equipment |  | 315 | 345
ACATF | AC Electrical System | Auxiliary Transformer | ASBLY | 315 | 345 |  |  | Complete Assembly
ACATF01 | AC Electrical System | Auxiliary Transformer | ASBLY | 315 | 345 |  |  | Complete Assembly
ACATF01a | AC Electrical System | Auxiliary Transformer | ASBLY | 315 | 345 |  |  | Complete Assembly
ACATF01b | AC Electrical System | Auxiliary Transformer |  | 315 | 345
ACCHS | AC Electrical System | Coal Handling Substation | ASBLY | 315 |  |  |  | Complete Assembly
ACCHS01 | AC Electrical System | Coal Handling Substation | ASBLY | 315 |  |  |  | Complete Assembly
ACCHS02 | AC Electrical System | Coal Handling Substation |  | 315 |  |  |  | Complete Structure
ACCHS03 | AC Electrical System | Coal Handling Substation |  | 315
ACCRT | AC Electrical System | Critical AC | ASBLY | 315 | 345 |  |  | Complete Assembly
ACCRT01 | AC Electrical System | Critical AC |  | 315 | 345 |  |  | Each
ACCRT02 | AC Electrical System | Critical AC |  | 315 | 345
ACCSS | AC Electrical System | Carbon 44 Yard |  | 315
ACEME | AC Electrical System | Emergency Generator | ASBLY | 315 | 345 |  |  | Complete Assembly
ACEME01 | AC Electrical System | Emergency Generator | ASBLY | 315 | 345 |  |  | Complete Assembly
ACEME02 | AC Electrical System | Emergency Generator | ASBLY | 315 | 345 |  |  | Complete Assembly
ACEME03 | AC Electrical System | Emergency Generator |  | 315 | 345
ACEMF | AC Electrical System | Emergency Diesel Generator |  | 315 | 345
ACMCC | AC Electrical System | Motor Control Center |  | 315 | 345
ACMSC | AC Electrical System | Miscellaneous |  | 315 | 345
ACMSS | AC Electrical System | Mine Sub Batteries |  | 315
ACMTF | AC Electrical (SUBSTATIONS) | Main Transformer | ASBLY | 353 | 353 | 353 |  | Complete Assembly
ACMTF01 | AC Electrical (SUBSTATIONS) | Main Transformer | ASBLY | 353 | 353 | 353 |  | Complete Assembly
ACMTF01a | AC Electrical (SUBSTATIONS) | Main Transformer | ASBLY | 353 | 353 | 353 |  | Complete Assembly
ACMTF01b | AC Electrical (SUBSTATIONS) | Main Transformer |  | 353 | 353 | 353 |  | Complete Set
ACMTF01c | AC Electrical (SUBSTATIONS) | Main Transformer |  | 353 | 353 | 353 |  | Complete Set
ACMTF01d | AC Electrical (SUBSTATIONS) | Main Transformer | ASBLY | 353 | 353 | 353 |  | Complete Assembly
ACMTF01e | AC Electrical (SUBSTATIONS) | Main Transformer |  | 353 | 353 | 353
ACOSS | AC Electrical System | O'Conner Substation (Centralia) |  | 315
ACPLC | AC Electrical System | Plant Load Center |  | 315 | 345
ACPMC | AC Electrical System | Plant Motor Center |  | 315 | 345
ACSAT | AC Electrical System | Scrubber Auxiliary Transformer |  | 315
ACSMC | AC Electrical System | Scrubber Motor Control Center |  | 315
ACSSS | AC Electrical System | Plant Substations |  | 315 | 345
ACSST | AC Electrical System | Scrubber Start-Up Transformer |  | 315
ACSTF | AC Electrical System | Start-Up Transformer |  | 315 | 345
ACTSF | AC Electrical System | Transformers |  | 315 | 345
ACVIT | AC Electrical System | Vital AC |  | 315 | 345
AFBUS | Accessory Electrical Systems | Generator Buss, Cables, Conduit Runs |  |  |  |  | 334 | Complete Set
AFBUS01 | Accessory Electrical Systems | Generator Buss, Cables, Conduit Runs |  |  |  |  | 334 | Each
AFBUS02 | Accessory Electrical Systems | Generator Buss, Cables, Conduit Runs |  |  |  |  | 334 | Each
AFBUS03 | Accessory Electrical Systems | Generator Buss, Cables, Conduit Runs |  |  |  |  | 334 | Each
AFBUS04 | Accessory Electrical Systems | Generator Buss, Cables, Conduit Runs |  |  |  |  | 334 | Each
AFBUS05 | Accessory Electrical Systems | Generator Buss, Cables, Conduit Runs |  |  |  |  | 334
AFPCB | Accessory Electrical Systems | Generator Circuit Breaker |  |  |  |  | 334
AFTSF | Accessory Electrical Systems | Step-Up Transformer |  |  |  |  | 353
AHGLY | Air Heater | Glycol Air Heater | ASBLY | 312 |  |  |  | Complete Assembly
AHGLY01 | Air Heater | Glycol Air Heater |  | 312 |  |  |  | Each
AHGLY02 | Air Heater | Glycol Air Heater |  | 312 |  |  |  | Each
AHGLY03 | Air Heater | Glycol Air Heater | ASBLY | 312 |  |  |  | Complete Assembly
AHGLY04 | Air Heater | Glycol Air Heater |  | 312 |  |  |  | Each
AHGLY05 | Air Heater | Glycol Air Heater |  | 312
AHHOT | Air Heater | Hot Water Air Heater |  | 312 |  |  |  | Complete system
AHHOT01 | Air Heater | Hot Water Air Heater |  | 312 |  |  |  | Each
AHHOT02 | Air Heater | Hot Water Air Heater |  | 312
AHRGN | Air Heater | Air Heater, Regenerative | ASBLY | 312 |  |  |  | Complete Assembly
AHRGN01a | Air Heater | Air Heater, Regenerative |  | 312 |  |  |  | Complete Set
AHRGN01b | Air Heater | Air Heater, Regenerative |  | 312 |  |  |  | Complete Set
AHRGN01c | Air Heater | Air Heater, Regenerative |  | 312
AHRGN01d | Air Heater | Air Heater, Regenerative | ASBLY | 312 |  |  |  | Complete Assembly
AHRGN01e | Air Heater | Air Heater, Regenerative | ASBLY | 312 |  |  |  | Complete Assembly
AHRGN01f | Air Heater | Air Heater, Regenerative | ASBLY | 312 |  |  |  | Complete Assembly
AHRGN01g | Air Heater | Air Heater, Regenerative | ASBLY | 312 |  |  |  | Complete Assembly
AHRGN01h | Air Heater | Air Heater, Regenerative |  | 312 |  |  |  | Complete Set
AHRGN01i | Air Heater | Air Heater, Regenerative |  | 312 |  |  |  | Complete Set
AHRGN01j | Air Heater | Air Heater, Regenerative |  | 312 |  |  |  | Complete Set
AHRGN01k | Air Heater | Air Heater, Regenerative |  | 312 |  |  |  | Complete Set
AHRGN01l | Air Heater | Air Heater, Regenerative |  | 312 |  |  |  | Each
AHRGN01m | Air Heater | Air Heater, Regenerative | ASBLY | 312 |  |  |  | Complete Assembly
AHRGN01n | Air Heater | Air Heater, Regenerative |  | 312 |  |  |  | Complete Set
AHRGN01p | Air Heater | Air Heater, Regenerative | ASBLY | 312 |  |  |  | Complete Assembly
AHRGN02a | Air Heater | Air Heater, Regenerative | ASBLY | 312 |  |  |  | Complete Assembly
AHRGN02b | Air Heater | Air Heater, Regenerative | ASBLY | 312 |  |  |  | Complete Assembly
AHRGN02c | Air Heater | Air Heater, Regenerative | ASBLY | 312 |  |  |  | Complete Assembly
AHRGN02d | Air Heater | Air Heater, Regenerative |  | 312 |  |  |  | Complete Set
AHRGN02e | Air Heater | Air Heater, Regenerative |  | 312 |  |  |  | Complete Set
AHRGN02f | Air Heater | Air Heater, Regenerative | ASBLY | 312 |  |  |  | Complete Assembly
AHRGN02g | Air Heater | Air Heater, Regenerative |  | 312 |  |  |  | Complete Set
AHRGN02h | Air Heater | Air Heater, Regenerative |  | 312 |  |  |  | Complete Set
AHRGN02i | Air Heater | Air Heater, Regenerative | ASBLY | 312 |  |  |  | Complete Assembly
AHRGN02j | Air Heater | Air Heater, Regenerative |  | 312 |  |  |  | Complete Set
AHRGN02k | Air Heater | Air Heater, Regenerative |  | 312
AHSTM | Air Heater | Air Heater, Steam |  | 312 |  |  |  | Each Coil
AHSTM01 | Air Heater | Air Heater, Steam |  | 312
AIANN | Alarms and Information Handling | Annunciator |  | 312 | 342
AICPT | Alarms and Information Handling | Computer Services |  | 312 | 342
AIENV | Alarms and Information Handling | Environmental Computer |  | 312 | 342
AIHAG | Alarms and Information Handling | Hagan Control System |  | 312
AIHRC | Alarms and Information Handling | Heat Rate Computer |  | 312 | 342
AIMCC | Alarms and Information Handling | Main Control Computer |  | 312 | 342
ASAUS | Auxiliary Steam | Auxiliary Steam System |  | 312 | 342 |  |  | Each
ASAUS01 | Auxiliary Steam | Auxiliary Steam System |  | 312 | 342
ASBLR | Auxiliary Steam | Auxiliary Boiler |  | 312 | 342 |  |  | Each
ASBLR01 | Auxiliary Steam | Auxiliary Boiler |  | 312 | 342 |  |  | Each
ASBLR02 | Auxiliary Steam | Auxiliary Boiler |  | 312 | 342 |  |  | Each
ASBLR03 | Auxiliary Steam | Auxiliary Boiler |  | 312 | 342 |  |  | Each
ASBLR04 | Auxiliary Steam | Auxiliary Boiler |  | 312 | 342 |  |  | Each
ASBLR05 | Auxiliary Steam | Auxiliary Boiler |  | 312 | 342 |  |  | Each
ASBLR06 | Auxiliary Steam | Auxiliary Boiler |  | 312 | 342 |  |  | Each
ASBLR07 | Auxiliary Steam | Auxiliary Boiler |  | 312 | 342 |  |  | Complete Set
ASBLR08 | Auxiliary Steam | Auxiliary Boiler |  | 312 | 342
ASHPS | Auxiliary Steam | High Pressure Steam |  | 312
ASHPS01 | Auxiliary Steam | High Pressure Steam |  | 312
ASIPS | Auxiliary Steam | Intermediate Pressure Steam | ASBLY | 312 |  |  |  | Complete Assembly
ASIPS01 | Auxiliary Steam | Intermediate Pressure Steam |  | 312
ASLPS | Auxiliary Steam | Low Pressure Steam | ASBLY | 312 |  |  |  | Complete Assembly
ASLPS01 | Auxiliary Steam | Low Pressure Steam |  | 312
ASRDS | Auxiliary Steam | Reheat DeSuperheaters |  | 312
AZAOO | Air Cooled Condenser | Fans, common |  | 314 | 344
AZCDN | Air Cooled Condenser | Condenser |  | 314 | 344 |  |  | Each
AZCDN01 | Air Cooled Condenser | Condenser |  | 314 | 344 |  |  | Each Side
AZCDN01a | Air Cooled Condenser | Condenser |  | 314 | 344 |  |  | Each
AZCDN01b | Air Cooled Condenser | Condenser |  | 314 | 344 |  |  | Each
AZCDN01c | Air Cooled Condenser | Condenser |  | 314 | 344 |  |  | Each
AZCDN02 | Air Cooled Condenser | Condenser |  | 314 | 344 |  |  | Each
AZCDN02a | Air Cooled Condenser | Condenser |  | 314 | 344 |  |  | Each
AZCDN02b | Air Cooled Condenser | Condenser |  | 314 | 344 |  |  | Each
AZCDN02c | Air Cooled Condenser | Condenser |  | 314 | 344
AZEXD | Air Cooled Condenser | Exhaust Duct |  | 314 | 344 |  |  | Each
AZEXD01 | Air Cooled Condenser | Exhaust Duct |  | 314 | 344 |  |  | Each
AZEXD02 | Air Cooled Condenser | Exhaust Duct |  | 314 | 344
AZEXD03 | Air Cooled Condenser | Exhaust Duct |  | 314 | 344
AZVAC | Air Cooled Condenser | Vacuum Maintaining Equipment |  | 314 | 344 |  |  | Each
AZVAC01 | Air Cooled Condenser | Vacuum Maintaining Equipment |  | 314 | 344 |  |  | Each
AZVAC02 | Air Cooled Condenser | Vacuum Maintaining Equipment |  | 314 | 344
BAASP | Bottom Ash | Ash Pit Sump |  | 312
BAAWC | Bottom Ash | Ash Water Chemical |  | 312
BAAWS | Bottom Ash | Ash Water Storage |  | 312
BABAG | Bottom Ash | Bottom Ash Baghouse |  | 312
BABAH | Bottom Ash | Bottom Ash Hopper |  | 312 |  |  |  | Each
BABAH01 | Bottom Ash | Bottom Ash Hopper | ASBLY | 312 |  |  |  | Complete Assembly
BABAH01a | Bottom Ash | Bottom Ash Hopper | ASBLY | 312 |  |  |  | Complete Assembly
BABAH01b | Bottom Ash | Bottom Ash Hopper |  | 312 |  |  |  | Each
BABAH02 | Bottom Ash | Bottom Ash Hopper |  | 312 |  |  |  | Each
BABAH03 | Bottom Ash | Bottom Ash Hopper | ASBLY | 312 |  |  |  | Complete Assembly
BABAH04 | Bottom Ash | Bottom Ash Hopper | ASBLY | 312 |  |  |  | Complete Assembly
BABAH04a | Bottom Ash | Bottom Ash Hopper | ASBLY | 312 |  |  |  | Complete Assembly
BABAH04b | Bottom Ash | Bottom Ash Hopper | ASBLY | 312 |  |  |  | Complete Assembly
BABAH04c | Bottom Ash | Bottom Ash Hopper |  | 312 |  |  |  | Complete Set
BABAH04d | Bottom Ash | Bottom Ash Hopper |  | 312 |  |  |  | Complete Set
BABAH04e | Bottom Ash | Bottom Ash Hopper |  | 312 |  |  |  | Complete Set
BABAH04f | Bottom Ash | Bottom Ash Hopper |  | 312
BABAS | Bottom Ash | Bottom Ash Sump |  | 312
BABAT | Bottom Ash | Bottom Ash Transport |  | 312
BACRU | Bottom Ash | Bottom Ash Crusher | ASBLY | 312 |  |  |  | Complete Assembly
BACRU01 | Bottom Ash | Bottom Ash Crusher |  | 312
BACTL | Bottom Ash | Bottom Ash System Controls |  | 312
BADEW | Bottom Ash | Dewatering Bin |  | 312 |  |  |  | Each
BADEW01 | Bottom Ash | Dewatering Bin |  | 312 |  |  |  | Each
BADEW02 | Bottom Ash | Dewatering Bin | ASBLY | 312 |  |  |  | Complete Assembly
BADEW03 | Bottom Ash | Dewatering Bin | ASBLY | 312 |  |  |  | Complete Assembly
BADEW04 | Bottom Ash | Dewatering Bin |  | 312
BAECB | Bottom Ash | Economizer Ash |  | 312 |  |  |  | Each
BAECB01 | Bottom Ash | Economizer Ash |  | 312 |  |  |  | Each
BAECB02 | Bottom Ash | Economizer Ash |  | 312 |  |  |  | Each
BAECB03 | Bottom Ash | Economizer Ash |  | 312 |  |  |  | Each
BAECB04 | Bottom Ash | Economizer Ash |  | 312 |  |  |  | Each
BAECB05 | Bottom Ash | Economizer Ash |  | 312
BAEXH | Bottom Ash | Bottom Ash Exhauster |  | 312
BAHPA | Bottom Ash | High Pressure Ash | ASBLY | 312 |  |  |  | Complete Assembly
BAHPA01 | Bottom Ash | High Pressure Ash |  | 312 |  |  |  | Each
BAHPA01a | Bottom Ash | High Pressure Ash |  | 312 |  |  |  | Each
BAHPA01b | Bottom Ash | High Pressure Ash |  | 312
BALPA | Bottom Ash | Low Pressure Ash |  | 312 |  |  |  | Each
BALPA01 | Bottom Ash | Low Pressure Ash |  | 312 |  |  |  | Each
BALPA02 | Bottom Ash | Low Pressure Ash |  | 312
BAPDS | Bottom Ash | Pipe Drain System |  | 312
BAPYR | Bottom Ash | Pyrite Handling System |  | 312 |  |  |  | Each
BAPYR01 | Bottom Ash | Pyrite Handling System |  | 312
BASLR | Bottom Ash | Sludge Return System |  | 312
BASLW | Bottom Ash | Seal Water |  | 312
BASST | Bottom Ash | Settling and Surge Tanks |  | 312 |  |  |  | Each
BASST01 | Bottom Ash | Settling and Surge Tanks |  | 312 |  |  |  | Each
BASST02 | Bottom Ash | Settling and Surge Tanks |  | 312 |  |  |  | Each
BASST03 | Bottom Ash | Settling and Surge Tanks |  | 312
BAUNL | Bottom Ash | Bottom Ash Unloader | ASBLY | 312 |  |  |  | Complete Assembly
BAUNL01 | Bottom Ash | Bottom Ash Unloader | ASBLY | 312 |  |  |  | Complete Assembly
BAUNL02 | Bottom Ash | Bottom Ash Unloader | ASBLY | 312 |  |  |  | Complete Assembly
BAUNL03 | Bottom Ash | Bottom Ash Unloader | ASBLY | 312 |  |  |  | Complete Assembly
BAUNL04 | Bottom Ash | Bottom Ash Unloader | ASBLY | 312 |  |  |  | Complete Assembly
BAUNL05 | Bottom Ash | Bottom Ash Unloader |  | 312
BCCAM | Boiler Controls | Furnace Camera |  | 312
BCCCS | Boiler Controls | Boiler Trip Alarms |  | 312
BCCMB | Boiler Controls | Combustion Controls |  | 312
BCCTR | Boiler Controls | Boiler Controls |  | 312 |  |  |  | Complete System
BCCTR01 | Boiler Controls | Boiler Controls |  | 312
BCIAC | Boiler Controls | Boiler Instrumentation |  | 312
BCINS | Boiler Controls | Instrumentation |  | 312
BCOPA | Boiler Controls | Opacity |  | 312
BCTRP | Boiler Controls | Trip Circuits |  | 312
BDCHI | Boiler Draft | Chimney |  | 312 |  |  |  | Each
BDCHI01 | Boiler Draft | Chimney |  | 312
BDCHI02 | Boiler Draft | Chimney |  | 312
BDCHI03 | Boiler Draft | Chimney |  | 312
BDCHI04 | Boiler Draft | Chimney |  | 312 |  |  |  | Complete Module
BDCHI05 | Boiler Draft | Chimney |  | 312 |  |  |  | Complete System
BDCHI06 | Boiler Draft | Chimney |  | 312 |  |  |  | Each
BDCHI07 | Boiler Draft | Chimney |  | 312 |  |  |  | Each
BDCHI08 | Boiler Draft | Chimney |  | 312 |  |  |  | Each
BDCHI09 | Boiler Draft | Chimney |  | 312 |  |  |  | Each
BDCHI10 | Boiler Draft | Chimney |  | 312
BDFAN | Boiler Draft | Draft Fans |  | 312 |  |  |  | Each
BDFAN01 | Boiler Draft | Draft Fans |  | 312
BDFAN01a | Boiler Draft | Draft Fans |  | 312 |  |  |  | Each Side
BDFAN01b | Boiler Draft | Draft Fans |  | 312 |  |  |  | Each Side
BDFAN01c | Boiler Draft | Draft Fans |  | 312 |  |  |  | Each
BDFAN01d | Boiler Draft | Draft Fans |  | 312 |  |  |  | Each
BDFAN01e | Boiler Draft | Draft Fans |  | 312 |  |  |  | Each
BDFAN01f | Boiler Draft | Draft Fans |  | 312 |  |  |  | Each
BDFAN01g | Boiler Draft | Draft Fans |  | 312 |  |  |  | Each
BDFAN01h | Boiler Draft | Draft Fans |  | 312 |  |  |  | Complete Set of Two
BDFAN01i | Boiler Draft | Draft Fans |  | 312 |  |  |  | Each
BDFAN01j | Boiler Draft | Draft Fans |  | 312 |  |  |  | Each Side
BDFAN01k | Boiler Draft | Draft Fans |  | 312 |  |  |  | Each
BDFAN01l | Boiler Draft | Draft Fans |  | 312 |  |  |  | Each
BDFAN01m | Boiler Draft | Draft Fans |  | 312 |  |  |  | Each
BDFAN01n | Boiler Draft | Draft Fans |  | 312 |  |  |  | Each
BDFAN02 | Boiler Draft | Draft Fans |  | 312 |  |  |  | Each
BDFAN02a | Boiler Draft | Draft Fans |  | 312 |  |  |  | Each
BDFAN02b | Boiler Draft | Draft Fans |  | 312 |  |  |  | Each Side
BDFAN02c | Boiler Draft | Draft Fans |  | 312 |  |  |  | Each Side
BDFAN02d | Boiler Draft | Draft Fans |  | 312 |  |  |  | Each
BDFAN02e | Boiler Draft | Draft Fans |  | 312 |  |  |  | Each
BDFAN02f | Boiler Draft | Draft Fans |  | 312 |  |  |  | Each
BDFAN02g | Boiler Draft | Draft Fans |  | 312
BDFAN02h | Boiler Draft | Draft Fans |  | 312 |  |  |  | Each
BDFAN02i | Boiler Draft | Draft Fans |  | 312 |  |  |  | Complete Set of Two
BDFAN02j | Boiler Draft | Draft Fans |  | 312 |  |  |  | Each
BDFAN02k | Boiler Draft | Draft Fans |  | 312 |  |  |  | Each Side
BDFAN02l | Boiler Draft | Draft Fans |  | 312 |  |  |  | Each
BDFAN02m | Boiler Draft | Draft Fans |  | 312 |  |  |  | Each
BDFAN02n | Boiler Draft | Draft Fans |  | 312 |  |  |  | Each
BDFAN02p | Boiler Draft | Draft Fans |  | 312
BDFDF | Boiler Draft | Forced Draft Fans |  | 312 |  |  |  | Each
BDFDF01 | Boiler Draft | Forced Draft Fans |  | 312 |  |  |  | Each
BDFDF01a | Boiler Draft | Forced Draft Fans |  | 312 |  |  |  | Each
BDFDF01b | Boiler Draft | Forced Draft Fans |  | 312 |  |  |  | Each Side
BDFDF01c | Boiler Draft | Forced Draft Fans |  | 312 |  |  |  | Each Side
BDFDF01d | Boiler Draft | Forced Draft Fans |  | 312 |  |  |  | Each
BDFDF01e | Boiler Draft | Forced Draft Fans |  | 312 |  |  |  | Each
BDFDF01f | Boiler Draft | Forced Draft Fans |  | 312 |  |  |  | Each
BDFDF01g | Boiler Draft | Forced Draft Fans |  | 312 |  |  |  | Each
BDFDF01h | Boiler Draft | Forced Draft Fans |  | 312 |  |  |  | Each
BDFDF01i | Boiler Draft | Forced Draft Fans |  | 312 |  |  |  | Each
BDFDF01j | Boiler Draft | Forced Draft Fans |  | 312 |  |  |  | Each
BDFDF01k | Boiler Draft | Forced Draft Fans |  | 312 |  |  |  | Each Side
BDFDF01l | Boiler Draft | Forced Draft Fans |  | 312 |  |  |  | Each
BDFDF01m | Boiler Draft | Forced Draft Fans |  | 312 |  |  |  | Each
BDFDF01n | Boiler Draft | Forced Draft Fans |  | 312 |  |  |  | Each
BDFDF01p | Boiler Draft | Forced Draft Fans |  | 312 |  |  |  | Each
BDFDF01r | Boiler Draft | Forced Draft Fans |  | 312
BDFLG | Boiler Draft | Flue Gas |  | 312 |  |  |  | Complete System
BDFLG01 | Boiler Draft | Flue Gas |  | 312 |  |  |  | Each
BDFLG02 | Boiler Draft | Flue Gas | ASBLY | 312 |  |  |  | Complete Assembly
BDFLG03 | Boiler Draft | Flue Gas | ASBLY | 312 |  |  |  | Complete Assembly
BDFLG04 | Boiler Draft | Flue Gas |  | 312 |  |  |  | Each
BDFLG04a | Boiler Draft | Flue Gas |  | 312 |  |  |  | Complete Set of Nozzles
BDFLG05 | Boiler Draft | Flue Gas |  | 312
BDGRF | Boiler Draft | Gas Recirculation Fans |  | 312
BDGRF01 | Boiler Draft | Gas Recirculation Fans |  | 312 |  |  |  | Each
BDGRF01a | Boiler Draft | Gas Recirculation Fans |  | 312 |  |  |  | Each
BDGRF01b | Boiler Draft | Gas Recirculation Fans |  | 312 |  |  |  | Each Side
BDGRF01c | Boiler Draft | Gas Recirculation Fans |  | 312 |  |  |  | Each Side
BDGRF01d | Boiler Draft | Gas Recirculation Fans |  | 312 |  |  |  | Each
BDGRF01e | Boiler Draft | Gas Recirculation Fans |  | 312 |  |  |  | Each
BDGRF01f | Boiler Draft | Gas Recirculation Fans |  | 312 |  |  |  | Each
BDGRF01g | Boiler Draft | Gas Recirculation Fans |  | 312 |  |  |  | Each
BDGRF01h | Boiler Draft | Gas Recirculation Fans |  | 312 |  |  |  | Each
BDGRF01i | Boiler Draft | Gas Recirculation Fans |  | 312 |  |  |  | Complete Set
BDGRF01j | Boiler Draft | Gas Recirculation Fans |  | 312 |  |  |  | Complete Set of Two
BDGRF01k | Boiler Draft | Gas Recirculation Fans |  | 312 |  |  |  | Each
BDGRF01l | Boiler Draft | Gas Recirculation Fans |  | 312 |  |  |  | Each Side
BDGRF01m | Boiler Draft | Gas Recirculation Fans |  | 312 |  |  |  | Each
BDGRF01n | Boiler Draft | Gas Recirculation Fans |  | 312 |  |  |  | Each
BDGRF01p | Boiler Draft | Gas Recirculation Fans |  | 312 |  |  |  | Each
BDGRF01q | Boiler Draft | Gas Recirculation Fans |  | 312
BDIAC | Boiler Draft | Opacity Analyzer |  | 312
BDIDD | Boiler Draft | Induced Fan Fluid Drive |  | 312 |  |  |  | Each
BDIDD01 | Boiler Draft | Induced Fan Fluid Drive | ASBLY | 312 |  |  |  | Complete Assembly
BDIDD01a | Boiler Draft | Induced Fan Fluid Drive |  | 312
BDIDF | Boiler Draft | Induced Draft Fan |  | 312 |  |  |  | Each
BDIDF01 | Boiler Draft | Induced Draft Fan |  | 312 |  |  |  | Each
BDIDF01a | Boiler Draft | Induced Draft Fan |  | 312 |  |  |  | Each
BDIDF01b | Boiler Draft | Induced Draft Fan |  | 312 |  |  |  | Each Side
BDIDF01c | Boiler Draft | Induced Draft Fan |  | 312 |  |  |  | Each Side
BDIDF01d | Boiler Draft | Induced Draft Fan |  | 312 |  |  |  | Each
BDIDF01e | Boiler Draft | Induced Draft Fan |  | 312 |  |  |  | Each
BDIDF01f | Boiler Draft | Induced Draft Fan |  | 312 |  |  |  | Each
BDIDF01g | Boiler Draft | Induced Draft Fan |  | 312 |  |  |  | Each
BDIDF01h | Boiler Draft | Induced Draft Fan |  | 312 |  |  |  | Each
BDIDF01i | Boiler Draft | Induced Draft Fan |  | 312
BDIDF01j | Boiler Draft | Induced Draft Fan |  | 312 |  |  |  | Complete Set of Two
BDIDF01k | Boiler Draft | Induced Draft Fan |  | 312 |  |  |  | Each
BDIDF01l | Boiler Draft | Induced Draft Fan |  | 312 |  |  |  | Each Side
BDIDF01m | Boiler Draft | Induced Draft Fan |  | 312 |  |  |  | Each
BDIDF01n | Boiler Draft | Induced Draft Fan |  | 312 |  |  |  | Each
BDIDF01p | Boiler Draft | Induced Draft Fan |  | 312 |  |  |  | Each
BDIDF01q | Boiler Draft | Induced Draft Fan |  | 312 |  |  |  | Each
BDIDF01r | Boiler Draft | Induced Draft Fan |  | 312 |  |  |  | Each
BDIDF02 | Boiler Draft | Induced Draft Fan |  | 312 |  |  |  | Each
BDIDF02a | Boiler Draft | Induced Draft Fan |  | 312 |  |  |  | Each
BDIDF02b | Boiler Draft | Induced Draft Fan |  | 312 |  |  |  | Each
BDIDF02c | Boiler Draft | Induced Draft Fan |  | 312 |  |  |  | Each
BDIDF02d | Boiler Draft | Induced Draft Fan |  | 312 |  |  |  | Each
BDIDF02e | Boiler Draft | Induced Draft Fan |  | 312 |  |  |  | Complete Set
BDIDF02f | Boiler Draft | Induced Draft Fan |  | 312 |  |  |  | Complete Set
BDIDF02g | Boiler Draft | Induced Draft Fan |  | 312 |  |  |  | Complete Set
BDIDF02h | Boiler Draft | Induced Draft Fan |  | 312 |  |  |  | Each
BDIDF02i | Boiler Draft | Induced Draft Fan |  | 312 |  |  |  | Each
BDIDF02j | Boiler Draft | Induced Draft Fan |  | 312 |  |  |  | Each
BDIDF02k | Boiler Draft | Induced Draft Fan |  | 312
BDIDL | Boiler Draft | ID Fan Lube Oil |  | 312
BDIGA | Boiler Draft | Igniter Air |  | 312
BDIGN | Boiler Draft | Igniter Air (Duplicate) |  | 312
BDPAF** | Boiler Draft | Primary Air Fans |  | 312
BDPRI | Boiler Draft | Primary Air |  | 312
BDSCN | Boiler Draft | Scanner Air |  | 312
BDSEC | Boiler Draft | Secondary Air | ASBLY | 312 |  |  |  | Complete Assembly
BDSEC01 | Boiler Draft | Secondary Air |  | 312
BFAUX | Boiler Fireside | Auxiliary Air Systems |  | 312 |  |  |  | Complete Set by Level or Corner
BFAUX01 | Boiler Fireside | Auxiliary Air Systems |  | 312 |  |  |  | Complete Set by Corner
BFAUX02 | Boiler Fireside | Auxiliary Air Systems |  | 312 |  |  |  | Complete Set for Boiler
BFAUX03 | Boiler Fireside | Auxiliary Air Systems |  | 312
BFBFR | Boiler Fireside | Air Register Dampers |  | 312 |  |  |  | Complete Set by Burner Group
BFBFR01 | Boiler Fireside | Air Register Dampers |  | 312 |  |  |  | Complete Burner Group
BFBFR02 | Boiler Fireside | Air Register Dampers |  | 312
BFBLR | Boiler Fireside | Boiler |  | 312 | 342
BFCAM | Boiler Fireside | Camera |  | 312 |  |  |  | Each
BFCAM01 | Boiler Fireside | Camera |  | 312 |  |  |  | Each
BFCAM02 | Boiler Fireside | Camera |  | 312
BFFSS | Boiler Fireside | Fireside System |  | 312 |  |  |  | Complete Corner
BFFSS01 | Boiler Fireside | Fireside System |  | 312 |  |  |  | Complete Set by Level or Corner
BFFSS02 | Boiler Fireside | Fireside System |  | 312 |  |  |  | Complete Set by Level or Corner
BFFSS03 | Boiler Fireside | Fireside System |  | 312 |  |  |  | Complete Burner Group
BFFSS04 | Boiler Fireside | Fireside System |  | 312 |  |  |  | Complete Set by Burner Group
BFFSS04a | Boiler Fireside | Fireside System |  | 312 |  |  |  | Complete Set by Burner Group
BFFSS04b | Boiler Fireside | Fireside System |  | 312 |  |  |  | Complete Set by Burner Group
BFFSS04c | Boiler Fireside | Fireside System |  | 312
BFFUA | Boiler Fireside | Fuel Air System |  | 312 |  |  |  | Complete Set by Level or Corner
BFFUA01 | Boiler Fireside | Fuel Air System |  | 312 |  |  |  | Complete Set by Corner
BFFUA02 | Boiler Fireside | Fuel Air System |  | 312
BFFUA03 | Boiler Fireside | Fuel Air System |  | 312
BFFUR | Boiler Fireside | Furnace Assembly |  | 312
BFIGN | Boiler Fireside | Ignitors |  | 312 |  |  |  | Complete Set by Elevation
BFIGN01 | Boiler Fireside | Ignitors |  | 312 |  |  |  | Complete Set by Elevation
BFIGN02 | Boiler Fireside | Ignitors |  | 312 |  |  |  | Complete Set by Burner Group
BFIGN03 | Boiler Fireside | Ignitors |  | 312
BFSCA | Boiler Fireside | Flame Scanners |  | 312 |  |  |  | Complete Set by Elevation or Group
BFSCA01 | Boiler Fireside | Flame Scanners |  | 312
BFTLT | Boiler Fireside | Tilt System |  | 312
BFTLT01 | Boiler Fireside | Tilt System |  | 312
BFWBX | Boiler Fireside | Windbox Burner Front System |  | 312
BFWUG | Boiler Fireside | Warm Up Guns |  | 312 |  |  |  | Complete Set by Elevation or Group
BFWUG01 | Boiler Fireside | Warm Up Guns |  | 312
BGBCW | Bearing Cooling Water | Bearing Cooling Water | ASBLY | 312 | 342 |  |  | Complete Assembly
BGBCW01 | Bearing Cooling Water | Bearing Cooling Water |  | 312 | 342 |  |  | Each
BGBCW02 | Bearing Cooling Water | Bearing Cooling Water | ASBLY | 312 | 342 |  |  | Complete Assembly
BGBCW03 | Bearing Cooling Water | Bearing Cooling Water |  | 312 | 342
BHCTL | Baghouse | Controls |  | 312
BHEXT | Baghouse | External Structure |  | 312 |  |  |  | Complete Module
BHEXT01 | Baghouse | External Structure |  | 312
BHINT | Baghouse | Internal Structure |  | 312 |  |  |  | Complete Set by Compartment
BHINT01 | Baghouse | Internal Structure |  | 312 |  |  |  | Each
BHINT02 | Baghouse | Internal Structure |  | 312
BHREV | Baghouse | Reverse Air System |  | 312 |  |  |  | Each
BHREV01 | Baghouse | Reverse Air System |  | 312
BRINJ | Brine Gathering System | Brine Injection System | ASBLY | 312 |  |  |  | Complete Assembly
BRINJ01 | Brine Gathering System | Brine Injection System |  | 312 |  |  |  | Each
BRINJ01a | Brine Gathering System | Brine Injection System |  | 312 |  |  |  | Each
BRINJ01b | Brine Gathering System | Brine Injection System |  | 312 |  |  |  | Each
BRINJ01c | Brine Gathering System | Brine Injection System | ASBLY | 312 |  |  |  | Complete Assembly
BRINJ02 | Brine Gathering System | Brine Injection System |  | 312 |  |  |  | Each
BRINJ02a | Brine Gathering System | Brine Injection System |  | 312 |  |  |  | Complete Set
BRINJ02b | Brine Gathering System | Brine Injection System |  | 312 |  |  |  | Each
BRINJ02c | Brine Gathering System | Brine Injection System |  | 312
BRMSC | Brine Injection System | Brine System Miscellaneous |  | 312
BRPIP | Brine Gathering System | Brine System Piping |  | 312
BRSFS | Brine Gathering System | Seal Flush System |  | 312
BRSRG | Brine Gathering System | Brine Surge Tank System | ASBLY | 312 |  |  |  | Complete Assembly
BRSRG01 | Brine Gathering System | Brine Surge Tank System |  | 312
BRTRF | Brine Gathering System | Brine Transfer System | ASBLY | 312 |  |  |  | Complete Assembly
BRTRF01 | Brine Gathering System | Brine Transfer System |  | 312 |  |  |  | Each
BRTRF01a | Brine Gathering System | Brine Transfer System |  | 312 |  |  |  | Complete Set
BRTRF01b | Brine Gathering System | Brine Transfer System |  | 312
BRTRF01c | Brine Gathering System | Brine Transfer System |  | 312
BRVLV | Brine Gathering System | Brine System Valves |  | 312
BRWEL | Brine Gathering System | Wells |  | 312
BSBLS | Boiler Structural | Boiler Structural |  | 312 |  |  |  | Each Boiler
BSBLS01 | Boiler Structural | Boiler Structural |  | 312 |  |  |  | Each Boiler
BSBLS02 | Boiler Structural | Boiler Structural |  | 312
BSINS | Boiler Structural | Boiler Insulation |  | 312 |  |  |  | Each Boiler
BSINS01 | Boiler Structural | Boiler Insulation |  | 312 |  |  |  | Each Boiler
BSINS02 | Boiler Structural | Boiler Insulation |  | 312 |  |  |  | Each Boiler
BSINS03 | Boiler Structural | Boiler Insulation |  | 312
BUADM | Buildings | Administration Building |  | 311 | 341
BUCHB | Buildings | Coal Handling Building |  | 311
BUFGD | Buildings | Scrubber Building |  | 311
BUMNB | Buildings | Main Power Plant Building |  | 311 | 341
BUWHS | Buildings | Warehouse |  | 311 | 341
BWATB | Boiler Waterside | Atmospheric Blowdown |  | 312 |  |  |  | Each
BWATB01 | Boiler Waterside | Atmospheric Blowdown |  | 312 |  |  |  | Each
BWATB02 | Boiler Waterside | Atmospheric Blowdown |  | 312 |  |  |  | Each
BWATB03 | Boiler Waterside | Atmospheric Blowdown |  | 312
BWBCP | Boiler Waterside | Boiler Circulating Pump |  | 312 |  |  |  | Each
BWBCP01 | Boiler Waterside | Boiler Circulating Pump |  | 312
BWBLR | Boiler Waterside | Boiler |  | 312 |  |  |  | Each
BWBLR01 | Boiler Waterside | Boiler |  | 312 |  |  |  | Identifiable Grouping
BWBLR02 | Boiler Waterside | Boiler |  | 312 |  |  |  | Each
BWBLR03 | Boiler Waterside | Boiler |  | 312 |  |  |  | Each
BWBLR04 | Boiler Waterside | Boiler |  | 312 |  |  |  | Each
BWBLR05 | Boiler Waterside | Boiler |  | 312
BWBWS | Boiler Waterside | Boiler Circulating Water |  | 312
BWDRM | Boiler Waterside | Steam Drum |  | 312 |  |  |  | Each
BWDRM01 | Boiler Waterside | Steam Drum |  | 312 |  |  |  | Complete Set
BWDRM01a | Boiler Waterside | Steam Drum |  | 312 |  |  |  | Complete Set
BWDRM01b | Boiler Waterside | Steam Drum |  | 312 |  |  |  | Complete Set
BWDRM01c | Boiler Waterside | Steam Drum |  | 312 |  |  |  | Complete system
BWDRM01d | Boiler Waterside | Steam Drum |  | 312 |  |  |  | Each
BWDRM02 | Boiler Waterside | Steam Drum |  | 312 |  |  |  | Each
BWDRM03 | Boiler Waterside | Steam Drum |  | 312
BWECO | Boiler Waterside | Economizer |  | 312 |  |  |  | Each
BWECO01 | Boiler Waterside | Economizer |  | 312 |  |  |  | Each
BWECO02 | Boiler Waterside | Economizer |  | 312 |  |  |  | Identifiable Grouping
BWECO03 | Boiler Waterside | Economizer |  | 312
BWECO04 | Boiler Waterside | Economizer |  | 312
BWFAW | Boiler Waterside | Fill and Wash |  | 312
BWINJ | Boiler Waterside | Injection Water System |  | 312
BWREH | Boiler Waterside | Reheater |  | 312 |  |  |  | Each
BWREH01 | Boiler Waterside | Reheater |  | 312 |  |  |  | Each
BWREH02 | Boiler Waterside | Reheater |  | 312 |  |  |  | Identifiable Grouping
BWREH03 | Boiler Waterside | Reheater |  | 312 |  |  |  | Each
BWREH04 | Boiler Waterside | Reheater |  | 312 |  |  |  | Each
BWREH05 | Boiler Waterside | Reheater |  | 312
BWSEH | Boiler Waterside | Superheater |  | 312
BWSEH01 | Boiler Waterside | Superheater |  | 312 |  |  |  | Each
BWSEH02 | Boiler Waterside | Superheater |  | 312 |  |  |  | Identifiable Grouping
BWSEH03 | Boiler Waterside | Superheater |  | 312 |  |  |  | Each
BWSEH04 | Boiler Waterside | Superheater |  | 312 |  |  |  | Each
BWSEH05 | Boiler Waterside | Superheater |  | 312
CACAC | Compressed Air | Central Air Compressor |  | 316 | 346 |  |  | Each
CACAC01 | Compressed Air | Central Air Compressor |  | 316 | 346 |  |  | Each
CACAC01a | Compressed Air | Central Air Compressor |  | 316 | 346 |  |  | Each
CACAC01b | Compressed Air | Central Air Compressor |  | 316 | 346 |  |  | Each Stage
CACAC01c | Compressed Air | Central Air Compressor |  | 316 | 346 |  |  | Each
CACAC01d | Compressed Air | Central Air Compressor |  | 316 | 346 |  |  | Each
CACAC02 | Compressed Air | Central Air Compressor |  | 316 | 346
CACMP | Compressed Air | Compressor |  | 316 | 346
CACOL | Compressed Air | Coolant System |  | 316 | 346
CACWC | Compressed Air | Cooling Pump Coupling |  | 316 | 346
CACWP | Compressed Air | Cooling Pump Coupling |  | 316 | 346
CAFLY | Compressed Air | Service Air Control |  | 316 | 346 |  |  | Each
CAFLY01 | Compressed Air | Service Air Control |  | 316 | 346
CAINA | Compressed Air | Instruments/Controls |  | 316 | 346 |  |  | Each
CAINA01 | Compressed Air | Instruments/Controls |  | 316 | 346 |  |  | Complete Set
CAINA01a | Compressed Air | Instruments/Controls |  | 316 | 346 |  |  | Each
CAINA01b | Compressed Air | Instruments/Controls |  | 316 | 346
CAINA01c | Compressed Air | Instruments/Controls |  | 316 | 346 |  |  | Each
CAINA02 | Compressed Air | Instruments/Controls | ASBLY | 316 | 346 |  |  | Complete Assembly
CAINA03 | Compressed Air | Instruments/Controls |  | 316 | 346
CASER | Compressed Air | Service |  | 316 | 346 |  |  | Each
CASER01 | Compressed Air | Service | ASBLY | 316 | 346 |  |  | Complete Assembly
CASER02 | Compressed Air | Service |  | 316 | 346 |  |  | Each
CASER03 | Compressed Air | Service |  | 316 | 346
CASTB | Compressed Air | Soot Blowout |  | 316 |  |  |  | Each
CASTB01 | Compressed Air | Soot Blowout |  | 316 |  |  |  | Each
CASTB01a | Compressed Air | Soot Blowout |  | 316 |  |  |  | Each
CASTB01b | Compressed Air | Soot Blowout |  | 316 |  |  |  | Each Stage
CASTB01c | Compressed Air | Soot Blowout |  | 316 |  |  |  | Each
CASTB01d | Compressed Air | Soot Blowout |  | 316 |  |  |  | Each
CASTB02 | Compressed Air | Soot Blowout |  | 316 |  |  |  | Complete Set
CASTB02a | Compressed Air | Soot Blowout |  | 316 |  |  |  | Each Stage
CASTB02b | Compressed Air | Soot Blowout |  | 316
CASTB02c | Compressed Air | Soot Blowout |  | 316 |  |  |  | Each
CASTB02d | Compressed Air | Soot Blowout |  | 316 |  |  |  | Each
CASTB03 | Compressed Air | Soot Blowout |  | 316 |  |  |  | Each
CASTB04 | Compressed Air | Soot Blowout |  | 316
CASTU | Compressed Air | Start-up |  | 316 |  |  |  | Each
CASTU01 | Compressed Air | Start-up |  | 316
CCCCT | Component Cooling | Component Cooling Tower |  | 312 | 342 |  |  | Each
CCCCT01 | Component Cooling | Component Cooling Tower |  | 312 | 342 |  |  | Each
CCCCT01a | Component Cooling | Component Cooling Tower |  | 312 | 342 |  |  | Each
CCCCT01b | Component Cooling | Component Cooling Tower |  | 312 | 342 |  |  | Each
CCCCT01c | Component Cooling | Component Cooling Tower |  | 312 | 342
CCCOM | Component Cooling | Component Cooling System |  | 312 | 342
CDCON | Condensate | Condensate System |  | 312 | 342 |  |  | Each
CDCON01 | Condensate | Condensate System |  | 312 | 342 |  |  | Each
CDCON01a | Condensate | Condensate System |  | 312 | 342 |  |  | Complete Set
CDCON01b | Condensate | Condensate System |  | 312 | 342 |  |  | Each
CDCON01c | Condensate | Condensate System |  | 312 | 342 |  |  | Each
CDCON02 | Condensate | Condensate System |  | 312 | 342 |  |  | Each
CDCON03 | Condensate | Condensate System |  | 312 | 342 |  |  | Each
CDCON04 | Condensate | Condensate System |  | 312 | 342 |  |  | Each
CDCON05 | Condensate | Condensate System |  | 312 | 342 |  |  | Each
CDCON06 | Condensate | Condensate System |  | 312 | 342 |  |  | Each
CDCON07 | Condensate | Condensate System |  | 312 | 342 |  |  | Each
CDCON08 | Condensate | Condensate System |  | 312 | 342
CDDEA | Condensate | Deaerator |  | 312 | 342 |  |  | Each
CDDEA01 | Condensate | Deaerator |  | 312 | 342 |  |  | Complete Set
CDDEA01a | Condensate | Deaerator |  | 312 | 342
CDDEA02 | Condensate | Deaerator |  | 312 | 342
CDLHT | Condensate | Low Pressure Heaters |  | 312 | 342 |  |  | Each
CDLHT01 | Condensate | Low Pressure Heaters |  | 312 | 342 |  |  | Each
CDLHT01a | Condensate | Low Pressure Heaters |  | 312 | 342 |  |  | Each
CDLHT01b | Condensate | Low Pressure Heaters |  | 312 | 342
CDSTO | Condensate | Storage Tank |  | 312 | 342 |  |  | Each
CDSTO01 | Condensate | Storage Tank |  | 312 | 342
CDTRF | Condensate | Condensate Transfer System |  | 312 | 342
CDTRF01 | Condensate | Condensate Transfer System |  | 312 | 342
CECEM | Continuous Emission Monitor | Continuous Emission Monitors |  | 312 | 342 |  |  | Complete system
CECEM01 | Continuous Emission Monitor | Continuous Emission Monitors |  | 312 | 342 |  |  | Linear feet
CECEM02 | Continuous Emission Monitor | Continuous Emission Monitors |  | 312 | 342 |  |  | Complete system
CECEM03 | Continuous Emission Monitor | Continuous Emission Monitors |  | 312 | 342 |  |  | Complete system
CECEM04 | Continuous Emission Monitor | Continuous Emission Monitors |  | 312 | 342 |  |  | Complete system
CECEM05 | Continuous Emission Monitor | Continuous Emission Monitors |  | 312 | 342 |  |  | Complete System
CECEM06 | Continuous Emission Monitor | Continuous Emission Monitors |  | 312 | 342 |  |  | Complete system
CECEM07 | Continuous Emission Monitor | Continuous Emission Monitors | ASBLY | 312 | 342 |  |  | Complete Assembly
CECEM08 | Continuous Emission Monitor | Continuous Emission Monitors |  | 312 | 342
CFAMI | Boiler Chemical Feed | Amine |  | 312 | 342
CFAMM | Boiler Chemical Feed | Ammonia |  | 312 | 342
CFCAU | Boiler Chemical Feed | Caustic |  | 312 | 342
CFCCF | Boiler Chemical Feed | Chemical Condensate Feed System |  | 312 | 342
CFHYZ | Boiler Chemical Feed | Hydrazine |  | 312 | 342
CFINS | Boiler Chemical Feed | Instrumentation/Controls | ASBLY | 312 | 342 |  |  | Complete Assembly
CFINS01 | Boiler Chemical Feed | Instrumentation/Controls |  | 312 | 342
CFOXY | Boiler Chemical Feed | Oxygen Scavenger |  | 312 | 342
CFPHO | Boiler Chemical Feed | Phosphate |  | 312 | 342 |  |  | Each
CFPHO01 | Boiler Chemical Feed | Phosphate |  | 312 | 342
CHAPF | Coal Handling | Apron Feeders |  | 312 |  |  |  | Each
CHAPF01 | Coal Handling | Apron Feeders |  | 312
CHCAR | Coal Handling | Car Spotter |  | 312 |  |  |  | Each
CHCAR01 | Coal Handling | Car Spotter |  | 312 |  |  |  | Each
CHCAR01a | Coal Handling | Car Spotter |  | 312 |  |  |  | Each
CHCAR01b | Coal Handling | Car Spotter |  | 312
CHCHB | Coal Handling | Overland Monorail Hoist |  | 312
CHCLS | Coal Handling | Coal Loading System |  | 312 |  |  |  | Each
CHCLS01 | Coal Handling | Coal Loading System |  | 312 |  |  |  | Each
CHCLS02 | Coal Handling | Coal Loading System |  | 312
CHCLS03 | Coal Handling | Coal Loading System |  | 312 |  |  |  | Each
CHCLS04 | Coal Handling | Coal Loading System |  | 312 |  |  |  | Each
CHCLS05 | Coal Handling | Coal Loading System |  | 312 |  |  |  | Each
CHCLS06 | Coal Handling | Coal Loading System |  | 312 |  |  |  | Each
CHCLS07 | Coal Handling | Coal Loading System |  | 312 |  |  |  | Complete System
CHCLS08 | Coal Handling | Coal Loading System |  | 312
CHCNT | Coal Handling | Coal Controls |  | 312
CHCNV | Coal Handling | Conveyor |  | 312 |  |  |  | Each
CHCNV01 | Coal Handling | Conveyor |  | 312 |  |  |  | Each
CHCNV02 | Coal Handling | Conveyor |  | 312 |  |  |  | Each
CHCNV03 | Coal Handling | Conveyor |  | 312 |  |  |  | Complete Structure
CHCNV04 | Coal Handling | Conveyor | ASBLY | 312 |  |  |  | Complete Assembly
CHCNV05 | Coal Handling | Conveyor |  | 312 |  |  |  | Each
CHCNV06 | Coal Handling | Conveyor |  | 312
CHCRD | Coal Handling | Creep Drive System |  | 312
CHDSB | Coal Handling | Distribution Bin |  | 312 |  |  |  | Each
CHDSB01 | Coal Handling | Distribution Bin |  | 312
CHDUC | Coal Handling | Dust Collection |  | 312 |  |  |  | Each
CHDUC01 | Coal Handling | Dust Collection |  | 312 |  |  |  | Each
CHDUC02 | Coal Handling | Dust Collection |  | 312 |  |  |  | Complete Internals
CHDUC02a | Coal Handling | Dust Collection |  | 312 |  |  |  | Each
CHDUC03 | Coal Handling | Dust Collection |  | 312 |  |  |  | Each
CHDUC04 | Coal Handling | Dust Collection |  | 312
CHDUS | Coal Handling | Dust Suppression |  | 312
CHDUS01 | Coal Handling | Dust Suppression |  | 312
CHDVF | Coal Handling | Distribution Vibration |  | 312
CHFSP | Coal Handling | Feeder Sump Pump |  | 312
CHGAT | Coal Handling | Gates |  | 312 |  |  |  | Each
CHGAT01 | Coal Handling | Gates |  | 312
CHGOB | Coal Handling | Gobbler Assembly |  | 312 |  |  |  | Each
CHGOB01 | Coal Handling | Gobbler Assembly |  | 312
CHINS | Coal Handling | Inspection |  | 312
CHIVF | Coal Handling | Intermediate Vibrating |  | 312
CHMAG | Coal Handling | Magnetic Separator |  | 312 |  |  |  | Each
CHMAG01 | Coal Handling | Magnetic Separator |  | 312
CHMBC | Coal Handling | Mobile Conveyor |  | 312 |  |  |  | Each
CHMBC01 | Coal Handling | Mobile Conveyor |  | 312
CHMDT | Coal Handling | Metal Detector |  | 312 |  |  |  | Each
CHMDT01 | Coal Handling | Metal Detector |  | 312
CHMOB | Coal Handling | Mobile Equipment |  | 396 |  |  |  | Each
CHMOB01 | Coal Handling | Mobile Equipment |  | 396 |  |  |  | Each
CHMOB02 | Coal Handling | Mobile Equipment |  | 396 |  |  |  | Each
CHMOB03 | Coal Handling | Mobile Equipment |  | 396 |  |  |  | Complete Rebuild
CHMOB04 | Coal Handling | Mobile Equipment |  | 396 |  |  |  | Each
CHMOB05 | Coal Handling | Mobile Equipment |  | 396 |  |  |  | Each
CHMOB06 | Coal Handling | Mobile Equipment |  | 396 |  |  |  | Each
CHMOB07 | Coal Handling | Mobile Equipment |  | 396
CHNET | Coal Handling | Network 90 |  | 312
CHPCR | Coal Handling | Primary Crusher |  | 312 |  |  |  | Each
CHPCR01 | Coal Handling | Primary Crusher |  | 312 |  |  |  | Complete Set
CHPCR01a | Coal Handling | Primary Crusher |  | 312 |  |  |  | Each
CHPCR01b | Coal Handling | Primary Crusher |  | 312 |  |  |  | Each
CHPCR01c | Coal Handling | Primary Crusher |  | 312
CHRCF | Coal Handling | Reciprocating Feeders |  | 312 |  |  |  | Each
CHRCF01 | Coal Handling | Reciprocating Feeders |  | 312
CHRCS | Coal Handling | Coal Reclaim System |  | 312 |  |  |  | Each
CHRCS01 | Coal Handling | Coal Reclaim System |  | 312 |  |  |  | Each
CHRCS02 | Coal Handling | Coal Reclaim System |  | 312 |  |  |  | Complete Set
CHRCS03 | Coal Handling | Coal Reclaim System |  | 312 |  |  |  | Each
CHRCS04 | Coal Handling | Coal Reclaim System |  | 312 |  |  |  | Each
CHRCS05 | Coal Handling | Coal Reclaim System |  | 312 |  |  |  | Each
CHRCS06 | Coal Handling | Coal Reclaim System | ASBLY | 312 |  |  |  | Complete Assembly
CHRCS07 | Coal Handling | Coal Reclaim System |  | 312
CHRED | Coal Handling | Reddler/Tripper Equipment |  | 312 |  |  |  | Each
CHRED01 | Coal Handling | Reddler/Tripper Equipment |  | 312
CHRST | Coal Handling | Radial Stacker |  | 312 |  |  |  | Each
CHRST01 | Coal Handling | Radial Stacker |  | 312 |  |  |  | Each
CHRST01a | Coal Handling | Radial Stacker |  | 312 |  |  |  | Each
CHRST02 | Coal Handling | Radial Stacker |  | 312 |  |  |  | Each
CHRST03 | Coal Handling | Radial Stacker |  | 312
CHSCR | Coal Handling | Secondary Crusher Assembly |  | 312 |  |  |  | Each
CHSCR01 | Coal Handling | Secondary Crusher Assembly |  | 312 |  |  |  | Complete Set
CHSCR01a | Coal Handling | Secondary Crusher Assembly |  | 312 |  |  |  | Each
CHSCR01b | Coal Handling | Secondary Crusher Assembly |  | 312 |  |  |  | Each
CHSCR01c | Coal Handling | Secondary Crusher Assembly |  | 312 |  |  |  | Each
CHSCR01d | Coal Handling | Secondary Crusher Assembly |  | 312
CHSIL | Coal Handling | Silo Assembly |  | 312 |  |  |  | Each
CHSIL01 | Coal Handling | Silo Assembly | ASBLY | 312 |  |  |  | Complete Assembly
CHSIL02 | Coal Handling | Silo Assembly |  | 312
CHSMP | Coal Handling | Coal Sampling System |  | 312 |  |  |  | Complete System
CHSMP01 | Coal Handling | Coal Sampling System |  | 312 |  |  |  | Each
CHSMP01a | Coal Handling | Coal Sampling System |  | 312 |  |  |  | Each
CHSMP01b | Coal Handling | Coal Sampling System |  | 312
CHSRG | Coal Handling | Surge Bin |  | 312 |  |  |  | Each
CHSRG01 | Coal Handling | Surge Bin |  | 312
CHSTG | Coal Handling | Coal Storage |  | 312
CHSUM | Coal Handling | Coal Handling Sumps |  | 312
CHSVF | Coal Handling | Secondary Vibrating Feeder |  | 312
CHSVF01 | Coal Handling | Secondary Vibrating Feeder |  | 312
CHTPR | Coal Handling | Tripper |  | 312 |  |  |  | Each
CHTPR01 | Coal Handling | Tripper | ASBLY | 312 |  |  |  | Complete Assembly
CHTPR02 | Coal Handling | Tripper |  | 312
CIANN | Plant Control and Instrumentation | Annunciator |  | 315 | 345 |  | 334 | Each
CIANN01 | Plant Control and Instrumentation | Annunciator |  | 315 | 345 |  | 334
CIATS | Plant Control and Instrumentation | Auto Syncronizing Equipment |  | 315 | 345 |  | 334 | Each
CIATS01 | Plant Control and Instrumentation | Auto Syncronizing Equipment |  | 315 | 345 |  | 334
CICIE | Plant Control and Instrumentation | Control Instrumentation |  | 315 | 345 |  | 334
CICMP | Plant Control and Instrumentation | Computer Control Equipment |  | 315 | 345 |  | 334
CIMCO | Plant Control and Instrumentation | Other Instrumentation and Control |  | 315 | 345 |  | 334
CIRLY | Plant Control and Instrumentation | Relay Protection |  | 315 | 345 |  | 334 | Each
CIRLY01 | Plant Control and Instrumentation | Relay Protection |  | 315 | 345 |  | 334 | Each
CIRLY02 | Plant Control and Instrumentation | Relay Protection |  | 315 | 345 |  | 334 | Each
CIRLY03 | Plant Control and Instrumentation | Relay Protection |  | 315 | 345 |  | 334
CISCA | Plant Control and Instrumentation | Scada System |  | 315 | 345 |  | 334
CISCA01 | Plant Control and Instrumentation | Scada System |  | 315 | 345 |  | 334
CISCA02 | Plant Control and Instrumentation | Scada System |  | 315 | 345 |  | 334
CNCCW | Condenser & Auxiliaries | Condensate Circulating Water |  | 314 | 344 |  |  | Each
CNCCW01 | Condenser & Auxiliaries | Condensate Circulating Water |  | 314 | 344 |  |  | Each
CNCCW02 | Condenser & Auxiliaries | Condensate Circulating Water |  | 314 | 344
CNCDN | Condenser & Auxiliaries | Condenser |  | 314 | 344 |  |  | Each
CNCDN01 | Condenser & Auxiliaries | Condenser |  | 314 | 344 |  |  | Complete Set
CNCDN01a | Condenser & Auxiliaries | Condenser |  | 314 | 344 |  |  | Complete Set
CNCDN01b | Condenser & Auxiliaries | Condenser |  | 314 | 344 |  |  | Each
CNCDN02 | Condenser & Auxiliaries | Condenser |  | 314 | 344 |  |  | Each
CNCDN03 | Condenser & Auxiliaries | Condenser |  | 314 | 344
CNCNP | Condenser & Auxiliaries | Condensate Pumps |  | 314 | 344
CNHTW | Condenser & Auxiliaries | Hotwell or Condensate Receiver Tank |  | 314 | 344
CNPOL | Condenser & Auxiliaries | Condensate Polisher System |  | 314 | 344 |  |  | Each
CNPOL01 | Condenser & Auxiliaries | Condensate Polisher System |  | 314 | 344 |  |  | Each
CNPOL01a | Condenser & Auxiliaries | Condensate Polisher System |  | 314 | 344 |  |  | Each
CNPOL01b | Condenser & Auxiliaries | Condensate Polisher System |  | 314 | 344 |  |  | Each
CNPOL02 | Condenser & Auxiliaries | Condensate Polisher System |  | 314 | 344 |  |  | Cubic Feet
CNPOL03 | Condenser & Auxiliaries | Condensate Polisher System |  | 314 | 344
CNVAC | Condenser & Auxiliaries | Vacuum Maintenance System |  | 314 | 344 |  |  | Complete Set
CNVAC01 | Condenser & Auxiliaries | Vacuum Maintenance System |  | 314 | 344 |  |  | Each
CNVAC01a | Condenser & Auxiliaries | Vacuum Maintenance System |  | 314 | 344 |  |  | Each
CNVAC02 | Condenser & Auxiliaries | Vacuum Maintenance System |  | 314 | 344 |  |  | Each
CNVAC03 | Condenser & Auxiliaries | Vacuum Maintenance System |  | 314 | 344 |  |  | Each
CNVAC04 | Condenser & Auxiliaries | Vacuum Maintenance System |  | 314 | 344
CNVAC05 | Condenser & Auxiliaries | Vacuum Maintenance System |  | 314 | 344
COCAT | CO Oxidation System | CO Oxidation Catalyst |  |  | 343 |  |  | Complete Set
COCAT01 | CO Oxidation System | CO Oxidation Catalyst |  |  | 343
CPCDS | Cathodic Protection | Condenser |  | 315 | 345 |  |  | Complete System
CPCDS01 | Cathodic Protection | Condenser |  | 315 | 345
CPGRD | Cathodic Protection | Ground | ASBLY | 315 | 345 |  | 334 | Complete Assembly
CPGRD01 | Cathodic Protection | Ground | ASBLY | 315 | 345 |  | 334 | Complete Assembly
CPGRD02 | Cathodic Protection | Ground |  | 315 | 345 |  | 334
CPRIV | Cathodic Protection | River Cathodic Protection |  | 315
CTBDN | Cooling Tower | Blowdown |  | 314 | 344 |  |  | Each
CTBDN01 | Cooling Tower | Blowdown |  | 314 | 344
CTCBP | Cooling Tower | Booster Pumps |  | 314 | 344
CTCFP | Cooling Tower | Dry Pipe Air Compressor |  | 314 | 344
CTCHM | Cooling Tower | Chemicals |  | 314 | 344
CTCOT | Cooling Tower | Structures |  | 314 | 344 |  |  | >60% by Cell
CTCOT01 | Cooling Tower | Structures |  | 314 | 344 |  |  | Each
CTCOT02 | Cooling Tower | Structures |  | 314 | 344 |  |  | Complete Tower
CTCOT03 | Cooling Tower | Structures |  | 314 | 344 |  |  | Complete Tower
CTCOT04 | Cooling Tower | Structures |  | 314 | 344 |  |  | Complete Cell
CTCOT05 | Cooling Tower | Structures |  | 314 | 344 |  |  | Complete Cell
CTCOT06 | Cooling Tower | Structures |  | 314 | 344 |  |  | Complete Cell
CTCOT07 | Cooling Tower | Structures |  | 314 | 344 |  |  | Complete Tower
CTCOT08 | Cooling Tower | Structures |  | 314 | 344
CTCTC | Cooling Tower | Cooling Cells |  | 314 | 344 |  |  | Complete Cell
CTCTC01 | Cooling Tower | Cooling Cells |  | 314 | 344 |  |  | Each
CTCTC02 | Cooling Tower | Cooling Cells |  | 314 | 344
CTCTC03 | Cooling Tower | Cooling Cells |  | 314 | 344 |  |  | Each
CTCTC04 | Cooling Tower | Cooling Cells |  | 314 | 344 |  |  | Complete Cell
CTCTC05 | Cooling Tower | Cooling Cells |  | 314 | 344 |  |  | Complete Cell
CTCTC06 | Cooling Tower | Cooling Cells |  | 314 | 344 |  |  | Complete Cell
CTCTC07 | Cooling Tower | Cooling Cells |  | 314 | 344 |  |  | Complete Cell
CTCTC08 | Cooling Tower | Cooling Cells |  | 314 | 344 |  |  | Each
CTCTC09 | Cooling Tower | Cooling Cells |  | 314 | 344 |  |  | Complete Tower
CTCTC10 | Cooling Tower | Cooling Cells |  | 314 | 344
CTCTC11 | Cooling Tower | Cooling Cells |  | 314 | 344
CTCTI | Cooling Tower | Instrumentation |  | 314 | 344
CTIAC | Cooling Tower | Electrical |  | 314 | 344
GTIGV | Gas Turbine | Guide Vanes |  |  | 343 |  |  | Complete Set
GTIGV01 | Gas Turbine | Guide Vanes |  |  | 343 |  |  | Complete Set
GTIGV02 | Gas Turbine | Guide Vanes | ASBLY |  | 343 |  |  | Complete Assembly
GTIGV03 | Gas Turbine | Guide Vanes |  |  | 343
CWACD | Circulating Water | Acid |  | 314 | 344 |  |  | Each
CWACD01 | Circulating Water | Acid |  | 314 | 344 |  |  | Each
CWACD02 | Circulating Water | Acid | ASBLY | 314 | 344 |  |  | Complete Assembly
CWACD03 | Circulating Water | Acid |  | 314 | 344
CWCCF | Circulating Water | Chemical Feed |  | 314 | 344 |  |  | Each
CWCCF01 | Circulating Water | Chemical Feed |  | 314 | 344 |  |  | Each
CWCCF02 | Circulating Water | Chemical Feed |  | 314 | 344
CWCFS | Circulating Water | Chlorine System |  | 314 | 344 |  |  | Each
CWCFS01 | Circulating Water | Chlorine System |  | 314 | 344
CWCHL | Circulating Water | Chlorinator |  | 314 | 344 |  |  | Each
CWCHL01 | Circulating Water | Chlorinator |  | 314 | 344
CWCWB | Circulating Water | Circ Water Booster Pumps |  | 314 | 344 |  |  | Each
CWCWB01 | Circulating Water | Circ Water Booster Pumps |  | 314 | 344 |  |  | Complete Set
CWCWB01a | Circulating Water | Circ Water Booster Pumps |  | 314 | 344 |  |  | Each
CWCWB01b | Circulating Water | Circ Water Booster Pumps |  | 314 | 344 |  |  | Each
CWCWB02 | Circulating Water | Circ Water Booster Pumps |  | 314 | 344 |  |  | Complete Set
CWCWB02a | Circulating Water | Circ Water Booster Pumps |  | 314 | 344 |  |  | Each
CWCWB02b | Circulating Water | Circ Water Booster Pumps |  | 314 | 344
CWCWC | Circulating Water | Cool Water Circ Control |  | 314 | 344
CWCWH | Circulating Water | Circ Water Holding Basin |  | 314 | 344 |  |  | Each
CWCWH01 | Circulating Water | Circ Water Holding Basin |  | 314 | 344
CWCWI | Circulating Water | Circ Water Injection Pumps |  | 314 | 344
CWCWP | Circulating Water | Circulating Water Pumps |  | 314 | 344 |  |  | Each
CWCWP01 | Circulating Water | Circulating Water Pumps |  | 314 | 344 |  |  | Complete Set
CWCWP01a | Circulating Water | Circulating Water Pumps |  | 314 | 344 |  |  | Each
CWCWP01b | Circulating Water | Circulating Water Pumps |  | 314 | 344 |  |  | Each
CWCWP01c | Circulating Water | Circulating Water Pumps |  | 314 | 344 |  |  | Each
CWCWP01d | Circulating Water | Circulating Water Pumps |  | 314 | 344 |  |  | Each
CWCWP02 | Circulating Water | Circulating Water Pumps |  | 314 | 344
CWCWS | Circulating Water | Circulating Water Screens |  | 314 | 344 |  |  | Each
CWCWS01 | Circulating Water | Circulating Water Screens |  | 314 | 344 |  |  | Each
CWCWS02 | Circulating Water | Circulating Water Screens |  | 314 | 344
CWCWT | Circulating Water | Circulating Water |  | 314 | 344
CWCWT01 | Circulating Water | Circulating Water |  | 314 | 344 |  |  | Each
CWCWT02 | Circulating Water | Circulating Water |  | 314 | 344 |  |  | Each
CWCWT03 | Circulating Water | Circulating Water |  | 314 | 344 |  |  | Each
CWCWT04 | Circulating Water | Circulating Water |  | 314 | 344
CWRAW | Circulating Water | Raw Water Make-Up |  | 314 | 344
DC130 | DC Electrical System | DC 130 Volt |  | 315
DC140 | DC Electrical System | DC 140 Volt |  | 315
DC260 | DC Electrical System | DC 260 Volt |  | 315
DCBAT | DC Electrical System | Station Batteries |  | 315 | 345 |  |  | Complete Set of Cells
DCBAT01 | DC Electrical System | Station Batteries |  | 315 | 345 |  |  | Complete Set of Cells
DCBAT02 | DC Electrical System | Station Batteries |  | 315 | 345 |  |  | Each
DCBAT03 | DC Electrical System | Station Batteries |  | 315 | 345
DIACD | Demineralizer | Acid |  | 312 | 342 |  |  | Each
DIACD01 | Demineralizer | Acid |  | 312 | 342 |  |  | Each
DIACD02 | Demineralizer | Acid |  | 312 | 342 |  |  | Each
DIACD03 | Demineralizer | Acid |  | 312 | 342
DICAU | Demineralizer | Caustic |  | 312 | 342 |  |  | Each
DICAU01 | Demineralizer | Caustic |  | 312 | 342 |  |  | Each
DICAU02 | Demineralizer | Caustic |  | 312 | 342 |  |  | Each
DICAU03 | Demineralizer | Caustic |  | 312 | 342
DIDEM | Demineralizer | Demineralizer |  | 312 | 342 |  |  | Each
DIDEM01 | Demineralizer | Demineralizer |  | 312 | 342 |  |  | Each
DIDEM02 | Demineralizer | Demineralizer |  | 312 | 342 |  |  | Each
DIDEM03 | Demineralizer | Demineralizer |  | 312 | 342 |  |  | Each
DIDEM04 | Demineralizer | Demineralizer |  | 312 | 342 |  |  | Each
DIDEM05 | Demineralizer | Demineralizer |  | 312 | 342
DIDEM06 | Demineralizer | Demineralizer |  | 312 | 342 |  |  | Lot
DIDEM07 | Demineralizer | Demineralizer |  | 312 | 342
DINET | Demineralizer | Neutralization |  | 312 | 342 |  |  | Each
DINET01 | Demineralizer | Neutralization |  | 312 | 342 |  |  | Each
DINET02 | Demineralizer | Neutralization |  | 312 | 342
DIWSP | Demineralizer | Waste Sumps |  | 312 | 342
DRDAM | Dams and Rivers | Dam |  | 311 | 341 |  | 331
DRFIH | Dams and Rivers | Fish |  | 311 | 341 |  | 331
DRRIV | Dams and Rivers | River |  | 311 | 341 |  | 331
DRRPP | Dams and Rivers | River Pump Plant |  | 311 | 341 |  | 331
DTDFT | Turbine Discharge | Draft Tube |  |  |  |  | 333 | Each
DTDFT01 | Turbine Discharge | Draft Tube |  |  |  |  | 333
DWCIE | Dams and Reservoirs | Dam Control and Instrumentation |  |  |  |  | 332
DWCRT | Dams and Reservoirs | Dam Critical AC Electrical |  |  |  |  | 332
DWDAM | Dams and Reservoirs | Dam Structure |  |  |  |  | 332 | Complete for a Dam
DWDAM01 | Dams and Reservoirs | Dam Structure |  |  |  |  | 332 | Each
DWDAM02 | Dams and Reservoirs | Dam Structure |  |  |  |  | 332 | Each
DWDAM03 | Dams and Reservoirs | Dam Structure |  |  |  |  | 332 | Square Feet
DWDAM04 | Dams and Reservoirs | Dam Structure |  |  |  |  | 332 | Complete Set
DWDAM05 | Dams and Reservoirs | Dam Structure |  |  |  |  | 332 | Each
DWDAM06 | Dams and Reservoirs | Dam Structure |  |  |  |  | 332 | Each
DWDAM07 | Dams and Reservoirs | Dam Structure |  |  |  |  | 332 | Complete Set
DWDAM08 | Dams and Reservoirs | Dam Structure |  |  |  |  | 332
DWDCS | Dams and Reservoirs | Dam DC Electrical System |  |  |  |  | 332
DWFEN | Dams and Reservoirs | Dam Fence |  |  |  |  | 332
DWFSH | Dams and Reservoirs | Dam Fish Ladders, Screens, and Traps |  |  |  |  | 332 | Each
DWFSH01 | Dams and Reservoirs | Dam Fish Ladders, Screens, and Traps |  |  |  |  | 332 | Each
DWFSH02 | Dams and Reservoirs | Dam Fish Ladders, Screens, and Traps |  |  |  |  | 332 | Each
DWFSH03 | Dams and Reservoirs | Dam Fish Ladders, Screens, and Traps |  |  |  |  | 332 | Each
DWFSH04 | Dams and Reservoirs | Dam Fish Ladders, Screens, and Traps |  |  |  |  | 332 | Complete Set
DWFSH05 | Dams and Reservoirs | Dam Fish Ladders, Screens, and Traps |  |  |  |  | 332 | Each
DWFSH06 | Dams and Reservoirs | Dam Fish Ladders, Screens, and Traps |  |  |  |  | 332 | Each
DWFSH07 | Dams and Reservoirs | Dam Fish Ladders, Screens, and Traps |  |  |  |  | 332
DWRES | Dams and Reservoirs | Reservoirs |  |  |  |  | 332 | Each
DWRES01 | Dams and Reservoirs | Reservoirs |  |  |  |  | 332 | Each
DWRES02 | Dams and Reservoirs | Reservoirs |  |  |  |  | 332 | Complete Set
DWRES03 | Dams and Reservoirs | Reservoirs |  |  |  |  | 332
DWSST | Dams and Reservoirs | Dam Sation Service (Electrical System) |  |  |  |  | 332
DWSTR | Dams and Reservoirs | Dam Buildings |  |  |  |  | 332
EMATF | Other Accessory Electrical Equipment | Auxillary Transformer |  |  |  |  | 334
EMCRT | Other Accessory Electrical Equipment | Critical AC System |  |  |  |  | 334
EMDCS | Other Accessory Electrical Equipment | DC System |  |  |  |  | 334
EMFRL | Other Accessory Electrical Equipment | Fire Alarm Systems |  |  |  |  | 334
EMSST | Other Accessory Electrical Equipment | Station Service System |  |  |  |  | 334
EXDRN | Extraction Steam | Drain System |  | 312 | 342
EXEXT | Extraction Steam | Extraction System | ASBLY | 312 | 342 |  |  | Complete Assembly
EXEXT01 | Extraction Steam | Extraction System |  | 312 | 342 |  |  | Each
EXEXT02 | Extraction Steam | Extraction System |  | 312 | 342
EXTWP | Extraction Steam | TWIPS |  | 312 | 342
FAAHA | Fly Ash | Air Heater Ash System |  | 312 |  |  |  | Each
FAAHA01 | Fly Ash | Air Heater Ash System |  | 312
FABAG | Fly Ash | Baghouse |  | 312 |  |  |  | Complete system
FABAG01 | Fly Ash | Baghouse |  | 312 |  |  |  | Complete Internals
FABAG01a | Fly Ash | Baghouse |  | 312
FACTR | Fly Ash | Controls |  | 312 |  |  |  | Each
FACTR01 | Fly Ash | Controls |  | 312
FAECF | Fly Ash | Economizer |  | 312 |  |  |  | Each
FAECF01 | Fly Ash | Economizer |  | 312 |  |  |  | Complete Set per Side
FAECF02 | Fly Ash | Economizer |  | 312 |  |  |  | Complete Set per Side
FAECF03 | Fly Ash | Economizer |  | 312 |  |  |  | Each Side
FAECF04 | Fly Ash | Economizer | ASBLY | 312 |  |  |  | Complete Assembly
FAECF05 | Fly Ash | Economizer |  | 312
FAEXH | Fly Ash | Fly Ash Exhauster |  | 312
FAFAB | Fly Ash | Fly Ash Bin/Silo |  | 312 |  |  |  | Each
FAFAB01 | Fly Ash | Fly Ash Bin/Silo |  | 312 |  |  |  | Each
FAFAB02 | Fly Ash | Fly Ash Bin/Silo |  | 312 |  |  |  | Each
FAFAB03 | Fly Ash | Fly Ash Bin/Silo |  | 312
FAFLU | Fly Ash | Fluidizing Systems |  | 312 |  |  |  | Each
FAFLU01 | Fly Ash | Fluidizing Systems |  | 312 |  |  |  | Each
FAFLU02 | Fly Ash | Fluidizing Systems |  | 312
FAFTS | Fly Ash | Transport System |  | 312 |  |  |  | Each
FAFTS01 | Fly Ash | Transport System |  | 312 |  |  |  | Each
FAFTS02 | Fly Ash | Transport System |  | 312 |  |  |  | Each
FAFTS03 | Fly Ash | Transport System | ASBLY | 312 |  |  |  | Complete Assembly
FAFTS04 | Fly Ash | Transport System |  | 312
FAFUF | Fly Ash | Fly Ash Unloading Facility |  | 312 |  |  |  | Each
FAFUF01 | Fly Ash | Fly Ash Unloading Facility |  | 312 |  |  |  | Each
FAFUF02 | Fly Ash | Fly Ash Unloading Facility |  | 312 |  |  |  | Complete system
FAFUF03 | Fly Ash | Fly Ash Unloading Facility |  | 312 |  |  |  | Complete system
FAFUF04 | Fly Ash | Fly Ash Unloading Facility |  | 312 |  |  |  | Complete system
FAFUF05 | Fly Ash | Fly Ash Unloading Facility |  | 312 |  |  |  | Complete system
FAFUF06 | Fly Ash | Fly Ash Unloading Facility |  | 312 |  |  |  | Complete Station
FAFUF07 | Fly Ash | Fly Ash Unloading Facility |  | 312
FAMDC | Fly Ash | Mechanical Dust Collector | ASBLY | 312 |  |  |  | Complete Assembly
FAMDC01 | Fly Ash | Mechanical Dust Collector |  | 312 |  |  |  | Complete Set by Compartment
FAMDC02 | Fly Ash | Mechanical Dust Collector |  | 312 |  |  |  | Complete Set by Compartment
FAMDC03 | Fly Ash | Mechanical Dust Collector |  | 312 |  |  |  | Complete Set by Compartment
FAMDC04 | Fly Ash | Mechanical Dust Collector |  | 312 |  |  |  | Each
FAMDC05 | Fly Ash | Mechanical Dust Collector |  | 312 |  |  |  | Each
FAMDC06 | Fly Ash | Mechanical Dust Collector |  | 312
FAPRE | Fly Ash | Precipitator Hopper |  | 312 |  |  |  | Complete Set per Unit
FAPRE01 | Fly Ash | Precipitator Hopper |  | 312 |  |  |  | Complete Set per Unit
FAPRE02 | Fly Ash | Precipitator Hopper | ASBLY | 312 |  |  |  | Complete Assembly
FAPRE03 | Fly Ash | Precipitator Hopper |  | 312
FAUNL | Fly Ash | Fly Ash Unloader |  | 312 |  |  |  | Each
FAUNL01 | Fly Ash | Fly Ash Unloader |  | 312
FOFUS | Fuel Oil | Fuel Supply and Storage | ASBLY | 312 |  |  |  | Complete Assembly
FOFUS01 | Fuel Oil | Fuel Supply and Storage | ASBLY | 312 |  |  |  | Complete Assembly
FOFUS02 | Fuel Oil | Fuel Supply and Storage | ASBLY | 312 |  |  |  | Complete Assembly
FOFUS03 | Fuel Oil | Fuel Supply and Storage |  | 312
FOIGO | Fuel Oil | Igniter Oil |  | 312
FOWUO | Fuel Oil | Warm-up Oil |  | 312
FWBBP | Feedwater | Booster Pumps |  | 312 | 342 |  |  | Each
FWBBP01 | Feedwater | Booster Pumps |  | 312 | 342 |  |  | Each
FWBBP01a | Feedwater | Booster Pumps |  | 312 | 342 |  |  | Complete Set
FWBBP01b | Feedwater | Booster Pumps |  | 312 | 342 |  |  | Each
FWBBP01c | Feedwater | Booster Pumps |  | 312 | 342
FWBFP | Feedwater | Boiler Feed Pump |  | 312 | 342 |  |  | Each
FWBFP01 | Feedwater | Boiler Feed Pump |  | 312 | 342 |  |  | Each
FWBFP01a | Feedwater | Boiler Feed Pump |  | 312 | 342 |  |  | Each
FWBFP01b | Feedwater | Boiler Feed Pump |  | 312 | 342 |  |  | Complete Set
FWBFP01c | Feedwater | Boiler Feed Pump |  | 312 | 342 |  |  | Each
FWBFP01d | Feedwater | Boiler Feed Pump |  | 312 | 342 |  |  | Each
FWBFP02 | Feedwater | Boiler Feed Pump |  | 312 | 342 |  |  | Each
FWBFP02a | Feedwater | Boiler Feed Pump |  | 312 | 342 |  |  | Each
FWBFP02b | Feedwater | Boiler Feed Pump |  | 312 | 342
FWBTL | Feedwater | Boiler Feed Turbine Lube |  | 312 | 342 |  |  | Each
FWBTL01 | Feedwater | Boiler Feed Turbine Lube |  | 312 | 342
FWCLP | Feedwater | Hydraulic Coupling - Fluid Drive |  | 312 | 342 |  |  | Each
FWCLP01 | Feedwater | Hydraulic Coupling - Fluid Drive |  | 312 | 342 |  |  | Each
FWCLP01a | Feedwater | Hydraulic Coupling - Fluid Drive |  | 312 | 342
FWFWS | Feedwater | Feedwater System |  | 312 | 342 |  |  | Each
FWFWS01 | Feedwater | Feedwater System |  | 312 | 342 |  |  | Each
FWFWS02 | Feedwater | Feedwater System |  | 312 | 342
FWHTR | Feedwater | High Pressure Heaters |  | 312 |  |  |  | Each
FWHTR01 | Feedwater | High Pressure Heaters |  | 312 |  |  |  | Each
FWHTR01a | Feedwater | High Pressure Heaters |  | 312 |  |  |  | Each
FWHTR01b | Feedwater | High Pressure Heaters |  | 312
FWHTR02 | Feedwater | High Pressure Heaters |  | 312
FWIJW | Feedwater | Injection Water |  | 312 |  |  |  | Each
FWIJW01 | Feedwater | Injection Water |  | 312 |  |  |  | Each
FWIJW01a | Feedwater | Injection Water |  | 312
FWTUR | Feedwater | Boiler Feed Pump Turbine |  | 312 |  |  |  | Each
FWTUR01 | Feedwater | Boiler Feed Pump Turbine |  | 312 |  |  |  | Each
FWTUR01a | Feedwater | Boiler Feed Pump Turbine |  | 312 |  |  |  | Each Row
FWTUR01b | Feedwater | Boiler Feed Pump Turbine |  | 312 |  |  |  | Each
FWTUR01c | Feedwater | Boiler Feed Pump Turbine |  | 312 |  |  |  | Each Upper and Lower
FWTUR01d | Feedwater | Boiler Feed Pump Turbine |  | 312 |  |  |  | Each
FWTUR01e | Feedwater | Boiler Feed Pump Turbine |  | 312 |  |  |  | Each
FWTUR01f | Feedwater | Boiler Feed Pump Turbine |  | 312 |  |  |  | Each
FWTUR01g | Feedwater | Boiler Feed Pump Turbine |  | 312 |  |  |  | Each
FWTUR01h | Feedwater | Boiler Feed Pump Turbine |  | 312
FWTUR01i | Feedwater | Boiler Feed Pump Turbine |  | 312
FZFZP | Freeze Protection | Freeze Protection |  | 315 | 345 |  |  | Each
FZFZP01 | Freeze Protection | Freeze Protection |  | 315 | 345 |  |  | Section
FZFZP02 | Freeze Protection | Freeze Protection |  | 315 | 345
FZHET | Freeze Protection | Heat Trace |  | 315 | 345
GEBCW | Generator | Bearing Cooling Water System |  |  |  |  | 333 | Each
GEBCW01 | Generator | Bearing Cooling Water System |  |  |  |  | 333
GEBRG | Generator | Bearings |  |  |  |  | 333 | Each
GEBRG01 | Generator | Bearings |  |  |  |  | 333 | Each
GEBRG02 | Generator | Bearings |  |  |  |  | 333 | Each
GEBRG03 | Generator | Bearings |  |  |  |  | 333 | Each
GEBRG04 | Generator | Bearings |  |  |  |  | 333 | Complete Set
GEBRG05 | Generator | Bearings |  |  |  |  | 333 | Each
GEBRG06 | Generator | Bearings |  |  |  |  | 333
GEBRK | Generator | Braking System |  |  |  |  | 333 | Each
GEBRK01 | Generator | Braking System |  |  |  |  | 333 | Each
GEBRK02 | Generator | Braking System |  |  |  |  | 333
GEEXC | Generator | Exciter System |  |  |  |  | 333 | Each
GEEXC01 | Generator | Exciter System |  |  |  |  | 333 | Each
GEEXC02 | Generator | Exciter System |  |  |  |  | 333 | Each
GEEXC03 | Generator | Exciter System |  |  |  |  | 333 | Each
GEEXC04 | Generator | Exciter System |  |  |  |  | 333 | Each
GEEXC05 | Generator | Exciter System |  |  |  |  | 333 | Each
GEEXC06 | Generator | Exciter System |  |  |  |  | 333 | Complete Set
GEEXC07 | Generator | Exciter System |  |  |  |  | 333
GEGBL | Generator | Lube Oil System |  |  |  |  | 333 | Each
GEGBL01 | Generator | Lube Oil System |  |  |  |  | 333
GEGEN | Generator | Stator Assembly |  |  |  |  | 333 | Complete Set
GEGEN01 | Generator | Stator Assembly |  |  |  |  | 333 | Each
GEGEN02 | Generator | Stator Assembly |  |  |  |  | 333
GEIAC | Generator | Instruments (mounted on Generator) |  |  |  |  | 333
GEROT | Generator | Rotor Assembly | ASBLY |  |  |  | 333 | Complete Assembly
GEROT01 | Generator | Rotor Assembly |  |  |  |  | 333 | Complete Set
GEROT02 | Generator | Rotor Assembly |  |  |  |  | 333 | Each
GEROT03 | Generator | Rotor Assembly |  |  |  |  | 333 | Complete Set
GEROT04 | Generator | Rotor Assembly |  |  |  |  | 333 | Each
GESCE01 | Generator | Stator Cooling System |  |  |  |  | 333
GESCW | Generator | Stator Cooling System |  |  |  |  | 333 | Each
GM390 | General Mass Property | Structures and Improvements |  | 390 | 390 | 390 | 390 | Each Complete Unit
GM391 | General Mass Property | Office Furniture |  | 391 | 391 | 391 | 391 | Each Complete Unit
GM3912 | General Mass Property | Personal Computer Equipment |  | 391 | 391 | 391 | 391 | Each Complete Unit
GM3913 | General Mass Property | Office Equipment |  | 391 | 391 | 391 | 391 | Each Complete Unit
GM393 | General Mass Property | Warehouse/Stores Equipment |  | 393 | 393 | 393 | 393 | Each Complete Unit
GM394 | General Mass Property | Tools, Shop and Garage Equipment |  | 394 | 394 | 394 | 394 | Each Complete Unit
GM395 | General Mass Property | Laboratory and Test Equipment |  | 395 | 395 | 395 | 395 | Complete Unit
GM397 | General Mass Property | Communication Equipment |  | 397 | 397 | 397 | 397 | Each Complete Unit
GM3972 | General Mass Property | Mobile Radio Equipment |  | 397 | 397 | 397 | 397 | Each Complete Unit
GM398 | General Mass Property | Miscellaneous Equipment |  | 398 | 398 | 398 | 398
GNCDX | Generator | Cardox System |  | 314 | 344
GNCO2 | Generator | CO2 Purge |  | 314 | 344 |  |  | Complete System
GNCO201 | Generator | CO2 Purge |  | 314 | 344
GNEXC | Generator | Exciter |  | 314 | 344 |  |  | Each
GNEXC01 | Generator | Exciter |  | 314 | 344 |  |  | Each
GNEXC02 | Generator | Exciter |  | 314 | 344 |  |  | Each
GNEXC03 | Generator | Exciter |  | 314 | 344 |  |  | Complete Set
GNEXC04 | Generator | Exciter |  | 314 | 344 |  |  | Each
GNEXC05 | Generator | Exciter |  | 314 | 344 |  |  | Each
GNEXC06 | Generator | Exciter |  | 314 | 344 |  |  | Each
GNEXC07 | Generator | Exciter |  | 314 | 344 |  |  | Each Bundle
GNEXC08 | Generator | Exciter |  | 314 | 344 |  |  | Each
GNEXC09 | Generator | Exciter |  | 314 | 344 |  |  | Each
GNEXC10 | Generator | Exciter |  | 314 | 344 |  |  | Each Bar
GNEXC11 | Generator | Exciter |  | 314 | 344 |  |  | Each
GNEXC12 | Generator | Exciter |  | 314 | 344 |  |  | Each
GNEXC13 | Generator | Exciter |  | 314 | 344
GNGEN | Generator | Generator |  | 314 | 344 |  |  | Each
GNGEN01 | Generator | Generator |  | 314 | 344 |  |  | Each
GNGEN02 | Generator | Generator |  | 314 | 344 |  |  | Number of Laminations
GNGEN02a | Generator | Generator |  | 314 | 344 |  |  | Each by Slot Assembly
GNGEN02b | Generator | Generator |  | 314 | 344 |  |  | Complete Set
GNGEN02c | Generator | Generator |  | 314 | 344 |  |  | Complete Set
GNGEN02d | Generator | Generator |  | 314 | 344 |  |  | Complete Set
GNGEN02e | Generator | Generator |  | 314 | 344 |  |  | Each
GNGEN03 | Generator | Generator |  | 314 | 344 |  |  | Each
GNGEN03a | Generator | Generator |  | 314 | 344 |  |  | Each by Slot Assembly
GNGEN03b | Generator | Generator |  | 314 | 344 |  |  | Complete Set
GNGEN03c | Generator | Generator |  | 314 | 344 |  |  | Complete Set
GNGEN03d | Generator | Generator |  | 314 | 344 |  |  | Each
GNGEN04 | Generator | Generator |  | 314 | 344 |  |  | Each
GNGEN05 | Generator | Generator |  | 314 | 344 |  |  | Each
GNGEN06 | Generator | Generator |  | 314 | 344 |  |  | Each
GNGEN07 | Generator | Generator |  | 314 | 344 |  |  | Each End
GNGEN08 | Generator | Generator |  | 314 | 344 |  |  | Each End
GNGEN09 | Generator | Generator |  | 314 | 344 |  |  | Each
GNGEN10 | Generator | Generator |  | 314 | 344 |  |  | Complete Set
GNGEN11 | Generator | Generator |  | 314 | 344 |  |  | Each
GNGEN12 | Generator | Generator |  | 314 | 344 |  |  | Each
GNGEN13 | Generator | Generator |  | 314 | 344 |  |  | Complete Set
GNGEN14 | Generator | Generator |  | 314 | 344 |  |  | Each
GNGEN15 | Generator | Generator |  | 314 | 344 |  |  | Complete Set by End
GNGEN16 | Generator | Generator |  | 314 | 344 |  |  | Each
GNGEN17 | Generator | Generator |  | 314 | 344 |  |  | Each
GNGEN18 | Generator | Generator |  | 314 | 344
GNHYD | Generator | Hydrogen System |  | 314 | 344 |  |  | Each
GNHYD01 | Generator | Hydrogen System |  | 314 | 344 |  |  | Each
GNHYD02 | Generator | Hydrogen System |  | 314 | 344 |  |  | Each
GNHYD03 | Generator | Hydrogen System |  | 314 | 344 |  |  | Complete system
GNHYD04 | Generator | Hydrogen System |  | 314 | 344 |  |  | Each
GNHYD05 | Generator | Hydrogen System |  | 314 | 344
GNISO | Generator | Iso-phase |  | 314 | 344 |  |  | Each
GNISO01 | Generator | Iso-phase |  | 314 | 344 |  |  | Each by Phase
GNISO02 | Generator | Iso-phase |  | 314 | 344
GNLOS | Gas Turbine Generator | Generator Lube Oil System |  |  | 344 |  |  | Complete System
GNLOS01 | Gas Turbine Generator | Generator Lube Oil System |  |  | 344
GNSCW | Generator | Stator Cooling System |  | 314 | 344 |  |  | Each
GNSCW01 | Generator | Stator Cooling System |  | 314 | 344 |  |  | Each
GNSCW01a | Generator | Stator Cooling System |  | 314 | 344
GNSEO | Generator | Seal Oil System |  | 314 | 344 |  |  | Each
GNSEO01 | Generator | Seal Oil System |  | 314 | 344
GNTSF | Generator | Miscellaneous Transformer Equipment |  | 314 | 344
GRCRK | Grounds | Creek | ASBLY | 311 | 341 |  |  | Complete Assembly
GRCRK01 | Grounds | Creek |  | 311 | 341
GRFEN | Grounds | Fencing |  | 311 | 341
GRGEN | Grounds | Grounds |  | 311 | 341
GRGRD** | Grounds | Grounds (1st Duplicate) |  | 311
GRGRN** | Grounds | Grounds (2nd Duplicate) |  | 311
GRMTR | Grounds | Meteorological Tower |  | 316 | 346 |  |  | Each
GRMTR01 | Grounds | Meteorological Tower |  | 316 | 346
GRODL | Grounds | Outdoor Lighting |  | 311 | 341
GRPAR | Grounds | Parking |  | 311 | 341 |  |  | Lot
GRPAR01 | Grounds | Parking |  | 311 | 341 |  |  | Lot
GRPAR02 | Grounds | Parking |  | 311 | 341 |  |  | Lot
GRPAR03 | Grounds | Parking |  | 311 | 341
GRPRK | Grounds | Parking (Duplicate) |  | 311
GRROD | Grounds | Roads |  | 311 | 341
GRROD01 | Grounds | Roads |  | 311 | 341 |  |  | Lot
GRROD02 | Grounds | Roads |  | 311 | 341 |  |  | Lot
GRROD03 | Grounds | Roads |  | 311 | 341
GRRRD | Grounds | Railroads |  | 311 | 341 |  |  | Each 100 Feet
GRRRD01 | Grounds | Railroads |  | 311 | 341 |  |  | Each
GRRRD02 | Grounds | Railroads |  | 311 | 341 |  |  | Each
GRRRD03 | Grounds | Railroads |  | 311 | 341 |  |  | Each
GRRRD04 | Grounds | Railroads | ASBLY | 311 | 341 |  |  | Complete Assembly
GRRRD05 | Grounds | Railroads | ASBLY | 311 | 341 |  |  | Complete Assembly
GRRRD06 | Grounds | Railroads |  | 311 | 341
GRYRD | Grounds | Railroad Crossing |  | 311 | 341 |  |  | Each Crossing
GRYRD01 | Grounds | Railroad Crossing |  | 311 | 341
GTAIR | Gas Turbine | Inlet Air & Exhaust System |  |  | 343 |  |  | Complete System
GTAIR01 | Gas Turbine | Inlet Air & Exhaust System |  |  | 343 |  |  | Complete System
GTAIR02 | Gas Turbine | Inlet Air & Exhaust System |  |  | 343 |  |  | Complete System
GTAIR03 | Gas Turbine | Inlet Air & Exhaust System |  |  | 343
GTCAS | Gas Turbine | Control Air System |  |  | 343 |  |  | Complete System
GTCAS01 | Gas Turbine | Control Air System |  |  | 343
GTCLT | Gas Turbine | Clutch |  |  | 343 |  |  | Each
GTCLT01 | Gas Turbine | Clutch |  |  | 343
GTCMB | Gas Turbine | Combustors |  |  | 343 |  |  | Each
GTCMB01 | Gas Turbine | Combustors |  |  | 343 |  |  | Each
GTCMB02 | Gas Turbine | Combustors |  |  | 343 |  |  | Each
GTCMB03 | Gas Turbine | Combustors |  |  | 343 |  |  | Each
GTCMB04 | Gas Turbine | Combustors |  |  | 343 |  |  | Each
GTCMB05 | Gas Turbine | Combustors |  |  | 343 |  |  | Each
GTCMB06 | Gas Turbine | Combustors |  |  | 343 |  |  | Each
GTCMB07 | Gas Turbine | Combustors |  |  | 343 |  |  | Each
GTCMB08 | Gas Turbine | Combustors |  |  | 343 |  |  | Each
GTCMB09 | Gas Turbine | Combustors |  |  | 343 |  |  | Each
GTCMB10 | Gas Turbine | Combustors |  |  | 343
GTCMP | Gas Turbine | Compressor |  |  | 343 |  |  | Each
GTCMP01 | Gas Turbine | Compressor |  |  | 343 |  |  | Complete Set
GTCMP02 | Gas Turbine | Compressor |  |  | 343 |  |  | Complete Set
GTCMP03 | Gas Turbine | Compressor |  |  | 343 |  |  | Complete Set
GTCMP04 | Gas Turbine | Compressor |  |  | 343 |  |  | Complete Set
GTCMP05 | Gas Turbine | Compressor |  |  | 343
GTCTS | Gas Turbine | Control System |  |  | 343 |  |  | Complete System
GTCTS01 | Gas Turbine | Control System |  |  | 343
GTECL | Gas Turbine | Enclosure (HVAC, Electrical, Structural, Piping) |  |  | 343 |  |  | Each
GTECL01 | Gas Turbine | Enclosure (HVAC, Electrical, Structural, Piping) |  |  | 343
GTFGS | Gas Turbine | Fuel Gas System |  |  | 343 |  |  | Complete System
GTFGS01 | Gas Turbine | Fuel Gas System |  |  | 343
GTFPS | Gas Turbine | Fire Protection |  |  | 343 |  |  | Complete System
GTFPS01 | Gas Turbine | Fire Protection |  |  | 343
GTGBX | Gas Turbine | Accessory Drive and Transfer Gearbox |  |  | 343 |  |  | Complete System
GTGBX01 | Gas Turbine | Accessory Drive and Transfer Gearbox |  |  | 343
GTHCO | Gas Turbine | Hydraulic Control/Lift Oil System |  |  | 343 |  |  | Complete System
GTHCO01 | Gas Turbine | Hydraulic Control/Lift Oil System |  |  | 343
GTLUB | Gas Turbine | Lube Oil System |  |  | 343 |  |  | Complete System
GTLUB01 | Gas Turbine | Lube Oil System |  |  | 343 |  |  | Complete System
GTLUB02 | Gas Turbine | Lube Oil System |  |  | 343
GTNOX | Gas Turbine | NOx Water Injection System |  |  | 343 |  |  | Complete System
GTNOX01 | Gas Turbine | NOx Water Injection System |  |  | 343
GTPTN | Gas Turbine | Power Turbine |  |  | 343 |  |  | Complete Set
GTPTN01 | Gas Turbine | Power Turbine |  |  | 343 |  |  | Complete Set
GTPTN02 | Gas Turbine | Power Turbine |  |  | 343 |  |  | Complete Set
GTPTN03 | Gas Turbine | Power Turbine |  |  | 343 |  |  | Complete Set
GTPTN04 | Gas Turbine | Power Turbine |  |  | 343 |  |  | Each
GTPTN05 | Gas Turbine | Power Turbine |  |  | 343 |  |  | Each
GTPTN06 | Gas Turbine | Power Turbine |  |  | 343 |  |  | Complete Set
GTPTN07 | Gas Turbine | Power Turbine |  |  | 343 |  |  | Complete Set
GTPTN08 | Gas Turbine | Power Turbine |  |  | 343
GTSAS | Gas Turbine | Cooling & Sealing Air System |  |  | 343 |  |  | Complete System
GTSAS01 | Gas Turbine | Cooling & Sealing Air System |  |  | 343
GTSPK | Gas Turbine | Starting System Package |  |  | 343 |  |  | Complete System
GTSPK01 | Gas Turbine | Starting System Package |  |  | 343 |  |  | Complete System
GTSPK02 | Gas Turbine | Starting System Package |  |  | 343
GTSPR | Gas Turbine | Spray Intercooling (SPRINT) System/Skid |  |  | 343 |  |  | Complete System
GTSPR01 | Gas Turbine | Spray Intercooling (SPRINT) System/Skid |  |  | 343
GTTRG | Gas Turbine | Turning Gear |  |  | 343 |  |  | Complete System
GTTRG01 | Gas Turbine | Turning Gear |  |  | 343
GTWWS | Gas Turbine | Water Wash System |  |  | 343 |  |  | Complete System
GTWWS01 | Gas Turbine | Water Wash System |  |  | 343
GVAUX | Governor Control System | Auxillary Controls |  |  |  |  | 333
GVGOV | Governor Control System | Governor |  |  |  |  | 333 | Each
GVGOV01 | Governor Control System | Governor |  |  |  |  | 333 | Each
GVGOV02 | Governor Control System | Governor |  |  |  |  | 333 | Each
GVGOV03 | Governor Control System | Governor |  |  |  |  | 333 | Complete Set
GVGOV04 | Governor Control System | Governor |  |  |  |  | 333
GVHAT | Governor Control System | Hydraulic Actuator |  |  |  |  | 333 | Each
GVHAT01 | Governor Control System | Hydraulic Actuator |  |  |  |  | 333 | Complete Set
GVHAT02 | Governor Control System | Hydraulic Actuator |  |  |  |  | 333
GVPRS | Governor Control System | Oil Pressure System |  |  |  |  | 333 | Each
GVPRS01 | Governor Control System | Oil Pressure System |  |  |  |  | 333 | Each
GVPRS02 | Governor Control System | Oil Pressure System |  |  |  |  | 333
HGCRA | Intake Gates, Mechanisms, and Structures | Intake Crane |  |  |  |  | 332
HGHDG | Intake Gates, Mechanisms, and Structures | Intake Gate |  |  |  |  | 332 | Each
HGHDG01 | Intake Gates, Mechanisms, and Structures | Intake Gate |  |  |  |  | 332 | Each
HGHDG02 | Intake Gates, Mechanisms, and Structures | Intake Gate |  |  |  |  | 332 | Complete Set
HGHDG03 | Intake Gates, Mechanisms, and Structures | Intake Gate |  |  |  |  | 332 | Each
HGHDG04 | Intake Gates, Mechanisms, and Structures | Intake Gate |  |  |  |  | 332 | Each
HGHDG05 | Intake Gates, Mechanisms, and Structures | Intake Gate |  |  |  |  | 332
HGLOG | Intake Gates, Mechanisms, and Structures | Intake Stop Logs |  |  |  |  | 332
HGSTR | Intake Gates, Mechanisms, and Structures | Intake Structure |  |  |  |  | 332 | Each
HGSTR01 | Intake Gates, Mechanisms, and Structures | Intake Structure |  |  |  |  | 332 | Complete Set
HGSTR02 | Intake Gates, Mechanisms, and Structures | Intake Structure |  |  |  |  | 332 | Each Section
HGSTR03 | Intake Gates, Mechanisms, and Structures | Intake Structure |  |  |  |  | 332 | Each
HGSTR04 | Intake Gates, Mechanisms, and Structures | Intake Structure |  |  |  |  | 332 | Each
HGSTR05 | Intake Gates, Mechanisms, and Structures | Intake Structure |  |  |  |  | 332 | Each
HGSTR06 | Intake Gates, Mechanisms, and Structures | Intake Structure |  |  |  |  | 332 | Complete Set
HGSTR07 | Intake Gates, Mechanisms, and Structures | Intake Structure |  |  |  |  | 332 | Each
HGSTR08 | Intake Gates, Mechanisms, and Structures | Intake Structure |  |  |  |  | 332
HVCHW | Heating & Ventilating | Chilled Water System |  | 311 | 341 |  |  | Lot
IP303 | Miscellaneous Intangible Property | Intangible Property |  | 303 | 303
LOCND | Lube Oil | Lube Oil Conditioner | ASBLY | 316 | 346 |  |  | Complete Assembly
LOCND01 | Lube Oil | Lube Oil Conditioner | ASBLY | 316 | 346 |  |  | Complete Assembly
LOCND02 | Lube Oil | Lube Oil Conditioner |  | 316 | 346
LOLOS | Lube Oil | Lube Oil Storage |  | 316 | 346 |  |  | Complete system
LOLOS01 | Lube Oil | Lube Oil Storage |  | 316 | 346 |  |  | Each
LOLOS02 | Lube Oil | Lube Oil Storage |  | 316 | 346 |  |  | Complete system
LOLOS03 | Lube Oil | Lube Oil Storage |  | 316 | 346
LOLOT | Lube Oil | Lube Oil Transfer |  | 316 | 346
LOTLO | Lube Oil | Turbine Lube Oil | ASBLY | 314 | 344 |  |  | Complete Assembly
LOTLO01 | Lube Oil | Turbine Lube Oil |  | 314 | 344 |  |  | Each
LOTLO02 | Lube Oil | Turbine Lube Oil |  | 314 | 344 |  |  | Each
LOTLO03 | Lube Oil | Turbine Lube Oil |  | 314 | 344 |  |  | Each
LOTLO04 | Lube Oil | Turbine Lube Oil |  | 314 | 344 |  |  | Complete system
LOTLO06 | Lube Oil | Turbine Lube Oil |  | 314 | 344 |  |  | Complete Set
LOTLO07 | Lube Oil | Turbine Lube Oil |  | 314 | 344
LOWOL | Lube Oil | Waste Oil System |  | 314 | 344
MSDES | Main Steam | Superheat Desuperheater |  | 312 |  |  |  | Each
MSDES01 | Main Steam | Superheat Desuperheater |  | 312 |  |  |  | Each
MSDES02 | Main Steam | Superheat Desuperheater |  | 312
MSMNS | Main Steam | HP/IP/LP Steam |  | 312 | 342 |  |  | Each
MSMNS01 | Main Steam | HP/IP/LP Steam |  | 312 | 342 |  |  | Each
MSMNS02 | Main Steam | HP/IP/LP Steam |  | 312 | 342 |  |  | Each
MSMNS03 | Main Steam | HP/IP/LP Steam |  | 312 | 342 |  |  | Each
MSMNS04 | Main Steam | HP/IP/LP Steam |  | 312 | 342 |  |  | Each
MSMNS05 | Main Steam | HP/IP/LP Steam |  | 312 | 342 |  |  | Each
MSMNS06 | Main Steam | HP/IP/LP Steam |  | 312 | 342
NGCFF | Natural Gas Fuel Supply System | Gas Intake |  |  | 342 |  |  | Each
NGCFF01 | Natural Gas Fuel Supply System | Gas Intake |  |  | 342 |  |  | Each
NGCFF02 | Natural Gas Fuel Supply System | Gas Intake |  |  | 342 |  |  | Each
NGCFF03 | Natural Gas Fuel Supply System | Gas Intake |  |  | 342 |  |  | Each
NGCFF04 | Natural Gas Fuel Supply System | Gas Intake |  |  | 342
NGCLR | Natural Gas Fuel Supply System | Natural Gas Cooler |  |  | 342 |  |  | Each
NGCLR01 | Natural Gas Fuel Supply System | Natural Gas Cooler |  |  | 342
NGCOR | Natural Gas Fuel Supply System | Natural Gas Compressor |  |  | 342 |  |  | Each
NGCOR01 | Natural Gas Fuel Supply System | Natural Gas Compressor |  |  | 342
OHCAC | Miscellaneous Power Plant Equipment | Compressed Air System |  |  |  |  | 335 | Each
OHCAC01 | Miscellaneous Power Plant Equipment | Compressed Air System |  |  |  |  | 335 | Each
OHCAC02 | Miscellaneous Power Plant Equipment | Compressed Air System |  |  |  |  | 335 | Each
OHCAC03 | Miscellaneous Power Plant Equipment | Compressed Air System |  |  |  |  | 335
OHTCW | Miscellaneous Power Plant Equipment | Transformer Cooling Water System |  |  |  |  | 335
PCFDR | Pulverized Coal | Feeder | ASBLY | 312 |  |  |  | Complete Assembly
PCFDR01 | Pulverized Coal | Feeder | ASBLY | 312 |  |  |  | Complete Assembly
PCFDR02 | Pulverized Coal | Feeder |  | 312
PCLBO | Pulverized Coal | Lube Oil | ASBLY | 312 |  |  |  | Complete Assembly
PCLBO01 | Pulverized Coal | Lube Oil |  | 312
PCPAL | Pulverized Coal | PA Fan Lube Oil | ASBLY | 312 |  |  |  | Complete Assembly
PCPAL01 | Pulverized Coal | PA Fan Lube Oil |  | 312
PCPRF | Pulverized Coal | Primary Air Fan | ASBLY | 312 |  |  |  | Complete Assembly
PCPRF01 | Pulverized Coal | Primary Air Fan | ASBLY | 312 |  |  |  | Complete Assembly
PCPRF01a | Pulverized Coal | Primary Air Fan |  | 312 |  |  |  | Complete Set
PCPRF01b | Pulverized Coal | Primary Air Fan |  | 312
PCPRF01c | Pulverized Coal | Primary Air Fan |  | 312 |  |  |  | Each
PCPRF01d | Pulverized Coal | Primary Air Fan |  | 312 |  |  |  | Each
PCPRF01e | Pulverized Coal | Primary Air Fan |  | 312 |  |  |  | Each
PCPRF01f | Pulverized Coal | Primary Air Fan |  | 312
PCPUL | Pulverized Coal | Pulverizer | ASBLY | 312 |  |  |  | Complete Assembly
PCPUL01 | Pulverized Coal | Pulverizer | ASBLY | 312 |  |  |  | Complete Assembly
PCPUL01a | Pulverized Coal | Pulverizer |  | 312 |  |  |  | Each
PCPUL01b | Pulverized Coal | Pulverizer |  | 312 |  |  |  | Each
PCPUL01c | Pulverized Coal | Pulverizer | ASBLY | 312 |  |  |  | Complete Assembly
PCPUL01d | Pulverized Coal | Pulverizer |  | 312 |  |  |  | Complete Set
PCPUL01e | Pulverized Coal | Pulverizer |  | 312 |  |  |  | Each
PCPUL01f | Pulverized Coal | Pulverizer |  | 312 |  |  |  | Each
PCPUL01g | Pulverized Coal | Pulverizer |  | 312 |  |  |  | Each
PCPUL01h | Pulverized Coal | Pulverizer |  | 312 |  |  |  | Each
PCPUL01i | Pulverized Coal | Pulverizer | ASBLY | 312 |  |  |  | Complete Assembly
PCPUL01j | Pulverized Coal | Pulverizer |  | 312 |  |  |  | Each
PCPUL01k | Pulverized Coal | Pulverizer |  | 312 |  |  |  | Each
PCPUL01l | Pulverized Coal | Pulverizer | ASBLY | 312 |  |  |  | Complete Assembly
PCPUL01m | Pulverized Coal | Pulverizer | ASBLY | 312 |  |  |  | Complete Assembly
PCPUL01n | Pulverized Coal | Pulverizer | ASBLY | 312 |  |  |  | Complete Assembly
PCPUL01o | Pulverized Coal | Pulverizer | ASBLY | 312 |  |  |  | Complete Assembly
PCPUL01p | Pulverized Coal | Pulverizer |  | 312 |  |  |  | Each
PCPUL01q | Pulverized Coal | Pulverizer | ASBLY | 312 |  |  |  | Complete Assembly
PCPUL01r | Pulverized Coal | Pulverizer | ASBLY | 312 |  |  |  | Complete Assembly
PCPUL01s | Pulverized Coal | Pulverizer | ASBLY | 312 |  |  |  | Complete Assembly
PCPUL01t | Pulverized Coal | Pulverizer | ASBLY | 312 |  |  |  | Complete Assembly
PCPUL01u | Pulverized Coal | Pulverizer | ASBLY | 312 |  |  |  | Complete Assembly
PCPUL01v | Pulverized Coal | Pulverizer | ASBLY | 312 |  |  |  | Complete Assembly
PCPUL02 | Pulverized Coal | Pulverizer |  | 312 |  |  |  | Each
PCPUL02a | Pulverized Coal | Pulverizer | ASBLY | 312 |  |  |  | Complete Assembly
PCPUL02b | Pulverized Coal | Pulverizer | ASBLY | 312 |  |  |  | Complete Assembly
PCPUL02c | Pulverized Coal | Pulverizer | ASBLY | 312 |  |  |  | Complete Assembly
PCPUL02d | Pulverized Coal | Pulverizer | ASBLY | 312 |  |  |  | Complete Assembly
PCPUL02e | Pulverized Coal | Pulverizer | ASBLY | 312 |  |  |  | Complete Assembly
PCPUL02f | Pulverized Coal | Pulverizer | ASBLY | 312 |  |  |  | Complete Assembly
PCPUL02g | Pulverized Coal | Pulverizer | ASBLY | 312 |  |  |  | Complete Assembly
PCPUL02h | Pulverized Coal | Pulverizer | ASBLY | 312 |  |  |  | Complete Assembly
PCPUL02i | Pulverized Coal | Pulverizer | ASBLY | 312 |  |  |  | Complete Assembly
PCPUL02j | Pulverized Coal | Pulverizer | ASBLY | 312 |  |  |  | Complete Assembly
PCPUL03 | Pulverized Coal | Pulverizer |  | 312 |  |  |  | Complete Set
PCPUL03a | Pulverized Coal | Pulverizer |  | 312 |  |  |  | Each
PCPUL03b | Pulverized Coal | Pulverizer |  | 312 |  |  |  | Complete Set
PCPUL03c | Pulverized Coal | Pulverizer |  | 312 |  |  |  | Each
PCPUL03d | Pulverized Coal | Pulverizer |  | 312 |  |  |  | Complete Set
PCPUL03e | Pulverized Coal | Pulverizer |  | 312
PCPUL03f | Pulverized Coal | Pulverizer | ASBLY | 312 |  |  |  | Complete Assembly
PCPUL03g | Pulverized Coal | Pulverizer | ASBLY | 312 |  |  |  | Complete Assembly
PCPUL04 | Pulverized Coal | Pulverizer | ASBLY | 312 |  |  |  | Complete Assembly
PCPUL04a | Pulverized Coal | Pulverizer | ASBLY | 312 |  |  |  | Complete Assembly
PCPUL04b | Pulverized Coal | Pulverizer | ASBLY | 312 |  |  |  | Complete Assembly
PCPUL04c | Pulverized Coal | Pulverizer |  | 312 |  |  |  | Each
PCPUL04d | Pulverized Coal | Pulverizer |  | 312 |  |  |  | Each
PCPUL04e | Pulverized Coal | Pulverizer |  | 312 |  |  |  | Complete Set
PCPUL04f | Pulverized Coal | Pulverizer | ASBLY | 312 |  |  |  | Complete Assembly
PCPUL04g | Pulverized Coal | Pulverizer | ASBLY | 312 |  |  |  | Complete Assembly
PCPUL05 | Pulverized Coal | Pulverizer | ASBLY | 312 |  |  |  | Complete Assembly
PCPUL05a | Pulverized Coal | Pulverizer | ASBLY | 312 |  |  |  | Complete Assembly
PCPUL05b | Pulverized Coal | Pulverizer |  | 312 |  |  |  | Each
PCPUL05c | Pulverized Coal | Pulverizer |  | 312 |  |  |  | Each
PCPUL05d | Pulverized Coal | Pulverizer |  | 312 |  |  |  | Complete Set per Pulverizer
PCPUL05e | Pulverized Coal | Pulverizer | ASBLY | 312 |  |  |  | Complete Assembly
PCPUL05f | Pulverized Coal | Pulverizer | ASBLY | 312 |  |  |  | Complete Assembly
PCPUL05g | Pulverized Coal | Pulverizer | ASBLY | 312 |  |  |  | Complete Assembly
PCPUL05h | Pulverized Coal | Pulverizer | ASBLY | 312 |  |  |  | Complete Assembly
PCPUL06 | Pulverized Coal | Pulverizer |  | 312 |  |  |  | Complete system
PCPUL07 | Pulverized Coal | Pulverizer |  | 312
PCSAF | Pulverized Coal | Seal Air System |  | 312
PCTRF | Pulverized Coal | Transfer Pipes - Gates |  | 312
PCTRN | Pulverized Coal | Coal Piping |  | 312
PCTRP | Pulverized Coal | Coal Transport Piping |  | 312 |  |  |  | Complete Set
PCTRP01 | Pulverized Coal | Coal Transport Piping |  | 312
PEMOB | Plant Equipment | Mobile Equipment |  | 316 | 346 |  |  | Each Complete Unit
POWER | General Mass Property | Power Operated Equipment |  | 396 | 396 | 396 | 396
PRFPR | Boiler Draft | Precipitator |  | 312 |  |  |  | Each
PRFPR01 | Boiler Draft | Precipitator |  | 312 |  |  |  | Each Field Complete
PRFPR02 | Boiler Draft | Precipitator |  | 312 |  |  |  | Complete Set by Field
PRFPR03 | Boiler Draft | Precipitator |  | 312 |  |  |  | Each Field Complete
PRFPR04 | Boiler Draft | Precipitator |  | 312 |  |  |  | Complete Set by Field
PRFPR05 | Boiler Draft | Precipitator |  | 312 |  |  |  | Complete Set by Field
PRFPR06 | Boiler Draft | Precipitator |  | 312 |  |  |  | Complete Set by Field
PRFPR07 | Boiler Draft | Precipitator |  | 312 |  |  |  | Complete Set
PRFPR08 | Boiler Draft | Precipitator |  | 312 |  |  |  | Complete Set
PRFPR09 | Boiler Draft | Precipitator | ASBLY | 312 |  |  |  | Complete Assembly
PRFPR10 | Boiler Draft | Precipitator | ASBLY | 312 |  |  |  | Complete Assembly
PRFPR11 | Boiler Draft | Precipitator |  | 312
PRFRR | Boiler Draft | Precipitator Transformer Trips |  | 312
PRPFR | Boiler Draft | Precipitator Transformer Controller |  | 312 |  |  |  | Complete Set for Row or Chamber
PRPFR01 | Boiler Draft | Precipitator Transformer Controller |  | 312 |  |  |  | Complete System
PRPFR02 | Boiler Draft | Precipitator Transformer Controller |  | 312 |  |  |  | Complete System
PRPFR03 | Boiler Draft | Precipitator Transformer Controller |  | 312
PRSPR | Precipitator | Second Stage Precipitator-Centralia |  | 312 |  |  |  | Each
PRSPR01 | Precipitator | Second Stage Precipitator-Centralia |  | 312 |  |  |  | Each Field Complete
PRSPR02 | Precipitator | Second Stage Precipitator-Centralia |  | 312 |  |  |  | Complete Set by Field
PRSPR03 | Precipitator | Second Stage Precipitator-Centralia |  | 312 |  |  |  | Each Field Complete
PRSPR04 | Precipitator | Second Stage Precipitator-Centralia |  | 312 |  |  |  | Complete Set by Field
PRSPR05 | Precipitator | Second Stage Precipitator-Centralia |  | 312 |  |  |  | Complete Set by Field
PRSPR06 | Precipitator | Second Stage Precipitator-Centralia |  | 312 |  |  |  | Complete Set by Field
PRSPR07 | Precipitator | Second Stage Precipitator-Centralia |  | 312 |  |  |  | Complete Set
PRSPR08 | Precipitator | Second Stage Precipitator-Centralia |  | 312 |  |  |  | Complete Set
PRSPR09 | Precipitator | Second Stage Precipitator-Centralia |  | 312 |  |  |  | Each
PRSPR10 | Precipitator | Second Stage Precipitator-Centralia |  | 312
PRSPR11 | Precipitator | Second Stage Precipitator-Centralia |  | 312
PRSRP | Precipitator | Precipitator (Huntington) |  | 312 |  |  |  | Complete System
PRSRP01 | Precipitator | Precipitator (Huntington) |  | 312 |  |  |  | Each
PRSRP02 | Precipitator | Precipitator (Huntington) | ASBLY | 312 |  |  |  | Complete Assembly
PRSRP03 | Precipitator | Precipitator (Huntington) | ASBLY | 312 |  |  |  | Complete Assembly
PRSRP04 | Precipitator | Precipitator (Huntington) |  | 312 |  |  |  | Each
PRSRP04a | Precipitator | Precipitator (Huntington) |  | 312 |  |  |  | Complete Set
PRSRP05 | Precipitator | Precipitator (Huntington) |  | 312
PRTFR | Boiler Draft | Precipitator Transformer Rectifier |  | 312 |  |  |  | Each
PRTFR01 | Boiler Draft | Precipitator Transformer Rectifier |  | 312
PRVRC | Boiler Draft | Precipitator Vibrator/Rapper Control |  | 312 |  |  |  | Complete System
PRVRC01 | Boiler Draft | Precipitator Vibrator/Rapper Control |  | 312
PWCHL | Pretreatment Water | Chlorine |  | 311 | 341 |  |  | Each
PWCHL01 | Pretreatment Water | Chlorine |  | 311 | 341 |  |  | Each
PWCHL02 | Pretreatment Water | Chlorine |  | 311 | 341
PWCLR | Pretreatment Water | Clarifier |  | 311 | 341 |  |  | Each
PWCLR01 | Pretreatment Water | Clarifier |  | 311 | 341 |  |  | Each
PWCLR02 | Pretreatment Water | Clarifier |  | 311 | 341 |  |  | Each
PWCLR03 | Pretreatment Water | Clarifier |  | 311 | 341
PWCLW | Pretreatment Water | Clearwell |  | 311 | 341
PWCWS | Pretreatment Water | Clarifier Waste Sump |  | 311 | 341
PWFBK | Pretreatment Water | Filter Backwash |  | 311 | 341
PWFER | Pretreatment Water | Ferrisul |  | 311 | 341 |  |  | Each
PWFER01 | Pretreatment Water | Ferrisul |  | 311 | 341
PWFSW | Pretreatment Water | Filter Surface Wash |  | 311 | 341
PWFWT | Pretreatment Water | Filtered Water |  | 311 | 341 |  |  | Each
PWFWT01 | Pretreatment Water | Filtered Water |  | 311 | 341
PWGRA | Pretreatment Water | Gravity Filters |  | 311 | 341 |  |  | Each
PWGRA01 | Pretreatment Water | Gravity Filters |  | 311 | 341
PWGRA02 | Pretreatment Water | Gravity Filters |  | 311 | 341
PWLIM | Pretreatment Water | Lime |  | 311 |  |  |  | Each
PWLIM01 | Pretreatment Water | Lime |  | 311 |  |  |  | Each
PWLIM02 | Pretreatment Water | Lime |  | 311 |  |  |  | Each
PWLIM03 | Pretreatment Water | Lime |  | 311 |  |  |  | Each
PWLIM03a | Pretreatment Water | Lime |  | 311 |  |  |  | Each
PWLIM04 | Pretreatment Water | Lime |  | 311 |  |  |  | Each
PWLIM05 | Pretreatment Water | Lime |  | 311
PWPOL | Pretreatment Water | Polymer |  | 311 | 341 |  |  | Each
PWPOL01 | Pretreatment Water | Polymer |  | 311 | 341
PWPTR | Pretreatment Water | Pretreatment |  | 311 | 341 |  |  | Each
PWPTR01 | Pretreatment Water | Pretreatment |  | 311 | 341
PWRAW | Pretreatment Water | Raw Water |  | 311 | 341
PWSDA | Pretreatment Water | Soda Ash |  | 311 |  |  |  | Each
PWSDA01 | Pretreatment Water | Soda Ash |  | 311 |  |  |  | Each
PWSDA02 | Pretreatment Water | Soda Ash |  | 311
PWSUL | Pretreatment Water | Sulfite |  | 311 | 341 |  |  | Each
PWSUL01 | Pretreatment Water | Sulfite |  | 311 | 341
RCBTM | Recreation Facilities | Boat Launch Facilities |  |  |  |  | 331 | Each
RCBTM01 | Recreation Facilities | Boat Launch Facilities |  |  |  |  | 331 | Each
RCBTM02 | Recreation Facilities | Boat Launch Facilities |  |  |  |  | 331
RCREC | Recreation Facilities | Recreation Facilities |  |  |  |  | 331 | Each
RCREC01 | Recreation Facilities | Recreation Facilities |  |  |  |  | 331 | Each
RCREC02 | Recreation Facilities | Recreation Facilities |  |  |  |  | 331 | Each
RCREC03 | Recreation Facilities | Recreation Facilities |  |  |  |  | 331 | Each
RCREC04 | Recreation Facilities | Recreation Facilities |  |  |  |  | 331 | Each
RCREC05 | Recreation Facilities | Recreation Facilities |  |  |  |  | 331
RDASH | Residual Disposal | Ash Disposal |  | 311 |  |  |  | Complete Cell
RDASH01 | Residual Disposal | Ash Disposal |  | 311
RMBRD | Roads, Bridges, Trails | Bridge |  |  |  |  | 336 | Each
RMBRD01 | Roads, Bridges, Trails | Bridge |  |  |  |  | 336 | Each
RMBRD02 | Roads, Bridges, Trails | Bridge |  |  |  |  | 336 | Each
RMBRD03 | Roads, Bridges, Trails | Bridge |  |  |  |  | 336 | Each
RMBRD04 | Roads, Bridges, Trails | Bridge |  |  |  |  | 336
RMPAR | Roads, Bridges, Trails | Parking Lot |  |  |  |  | 336 | Square Feet
RMPAR01 | Roads, Bridges, Trails | Parking Lot |  |  |  |  | 336
RMRDS | Roads, Bridges, Trails | Roads and Trails |  |  |  |  | 336 | Complete Road
RMRDS01 | Roads, Bridges, Trails | Roads and Trails |  |  |  |  | 336 | Complete Trail
RMRDS02 | Roads, Bridges, Trails | Roads and Trails |  |  |  |  | 336
ROACD | Reverse Osmosis | Acid Feed Pump |  | 312 | 342 |  |  | Each
ROACD01 | Reverse Osmosis | Acid Feed Pump |  | 312 | 342
ROCTR | Reverse Osmosis | Control System |  | 312 | 342
ROFDP | Reverse Osmosis | Feed Pump |  | 312 | 342
ROFLT | Reverse Osmosis | Filter Skid |  | 312 | 342 |  |  | Each
ROFLT01 | Reverse Osmosis | Filter Skid |  | 312 | 342
ROHXP | Reverse Osmosis | Hexamethaphosphate Pump |  | 312 | 342 |  |  | Each
ROHXP01 | Reverse Osmosis | Hexamethaphosphate Pump |  | 312 | 342
ROINA | Reverse Osmosis | Instrument System |  | 312 | 342
ROMBN | Reverse Osmosis | Membrane Cleaning Skid |  | 312 | 342 |  |  | Each
ROMBN01 | Reverse Osmosis | Membrane Cleaning Skid |  | 312 | 342
RONAO | Reverse Osmosis | Hypochlorite Pump |  | 312 | 342
ROPMT | Reverse Osmosis | Permeate Storage Tank |  | 312 | 342 |  |  | Each
ROPMT01 | Reverse Osmosis | Permeate Storage Tank |  | 312 | 342
ROPO4 | Reverse Osmosis | Scale Inhibitor Pump |  | 312 | 342
ROROA | Reverse Osmosis | R.O. Acid Pumps |  | 312 | 342 |  |  | Each
ROROA01 | Reverse Osmosis | R.O. Acid Pumps |  | 312 | 342
ROROP | Reverse Osmosis | R.O. Pumps |  | 312 | 342
ROROS | Reverse Osmosis | RO System |  | 312 | 342 |  |  | Each
ROROS01 | Reverse Osmosis | RO System |  | 312 | 342
ROSO3 | Reverse Osmosis | Sodium Bisulfate Pump |  | 312 | 342 |  |  | Each
ROSO301 | Reverse Osmosis | Sodium Bisulfate Pump |  | 312 | 342
ROTRN | Reverse Osmosis | Train Assembly |  | 312 | 342
ROTWT | Reverse Osmosis | Treated Water System |  | 312 | 342 |  |  | Each
ROTWT01 | Reverse Osmosis | Treated Water System |  | 312 | 342
ROVSL | Reverse Osmosis | Vessels/Membranes |  | 312 | 342 |  |  | Complete Set
ROVSL01 | Reverse Osmosis | Vessels/Membranes |  | 312 | 342 |  |  | Complete Set
ROVSL02 | Reverse Osmosis | Vessels/Membranes |  | 312 | 342
RSCRH | Reheat Steam | Cold Reheat |  | 312 | 342 |  |  | Each
RSCRH01 | Reheat Steam | Cold Reheat |  | 312 | 342 |  |  | Each
RSCRH02 | Reheat Steam | Cold Reheat |  | 312 | 342
RSHRH | Reheat Steam | Hot Reheat |  | 312 | 342 |  |  | Each
RSHRH01 | Reheat Steam | Hot Reheat |  | 312 | 342 |  |  | Each
RSHRH02 | Reheat Steam | Hot Reheat |  | 312 | 342 |  |  | Each
RSHRH03 | Reheat Steam | Hot Reheat |  | 312 | 342
RSRDS | Reheat Steam | RH Desuperheater |  | 312 | 342 |  |  | Each
RSRDS01 | Reheat Steam | RH Desuperheater |  | 312 | 342 |  |  | Each
RSRDS02 | Reheat Steam | RH Desuperheater |  | 312 | 342
SBAHT | Soot Blowing | Air Heater |  | 312 |  |  |  | Each
SBAHT01 | Soot Blowing | Air Heater |  | 312
SBIKS** | Soot Blowing | IK Sootblowers |  | 312
SBIRA** | Soot Blowing | IR Sootblowers - Air |  | 312
SBIRS** | Soot Blowing | IR Sootblowers - Steam |  | 312
SBRET | Soot Blowing | Retractable Soot Blowers |  | 312 |  |  |  | Each
SBRET01 | Soot Blowing | Retractable Soot Blowers |  | 312
SBRTY | Soot Blowing | Rotary Soot Blowers |  | 312 |  |  |  | Each
SBRTY01 | Soot Blowing | Rotary Soot Blowers |  | 312
SBSBC | Soot Blowing | Soot Blower Controls |  | 312 |  |  |  | Each
SBSBC01 | Soot Blowing | Soot Blower Controls |  | 312
SBSSS | Soot Blowing | Soot Blower Steam Supply |  | 312
SBSTA | Soot Blowing | Soot Blower Air |  | 312
SBWAL | Soot Blowing | Water Wall Deslagger |  | 312 |  |  |  | Each
SBWAL01 | Soot Blowing | Water Wall Deslagger |  | 312
SBWLB** | Soot Blowing | Water Wall Deslagger (1st Duplicate) |  | 312
SBWTL | Soot Blowing | Water Lance Soot Blower |  | 312 |  |  |  | Each
SBWTL01 | Soot Blowing | Water Lance Soot Blower |  | 312
SCAFS | SCR NOx Removal System | Ammonia Forwarding System/Skid |  |  | 343 |  |  | Complete System
SCAFS01 | SCR NOx Removal System | Ammonia Forwarding System/skid |  |  | 343
SCAIG | SCR NOx Removal System | Injection Manifold and Grid |  |  | 343 |  |  | Complete System
SCAIG01 | SCR NOx Removal System | Injection Manifold and Grid |  |  | 343
SCAIS | SCR NOx Removal System | Ammonia Injection System/skid |  |  | 343 |  |  | Complete System
SCAIS01 | SCR NOx Removal System | Ammonia Injection System/Skid |  |  | 343
SCAST | SCR NOx Removal System | Ammonia Storage Tank |  |  | 343 |  |  | Complete System
SCAST01 | SCR NOx Removal System | Ammonia Storage Tank |  |  | 343
SCCAT | SCR NOx Removal System | NOx Catalyst |  |  | 343 |  |  | Complete System
SCCAT01 | SCR NOx Removal System | NOx Catalyst |  |  | 343
SCTAS | SCR NOx Removal System | Tempering Air System |  |  | 343 |  |  | Complete System
SCTAS01 | SCR NOx Removal System | Tempering Air System |  |  | 343
SGBPD | Heat Recovery Steam Generator | ByPass Damper |  |  | 342
SGBPS | Heat Recovery Steam Generator | ByPass Stack |  |  | 342 |  |  | Each
SGBPS01 | Heat Recovery Steam Generator | ByPass Stack |  |  | 342 |  |  | Each
SGBPS02 | Heat Recovery Steam Generator | ByPass Stack |  |  | 342 |  |  | Each
SGBPS03 | Heat Recovery Steam Generator | ByPass Stack |  |  | 342 |  |  | Each
SGBPS04 | Heat Recovery Steam Generator | ByPass Stack |  |  | 342
SGCNT | Heat Recovery Steam Generator | Controls |  |  | 342 |  |  | Each
SGCNT01 | Heat Recovery Steam Generator | Controls |  |  | 342 |  |  | Each
SGCNT02 | Heat Recovery Steam Generator | Controls |  |  | 342
SGDBR | Heat Recovery Steam Generator | Duct Burner |  |  | 342
SGGAT | Spillway Structure and Gates | Spillway Gates |  |  |  |  | 332 | Each
SGGAT01 | Spillway Structure and Gates | Spillway Gates |  |  |  |  | 332 | Each
SGGAT02 | Spillway Structure and Gates | Spillway Gates |  |  |  |  | 332 | Complete Set
SGGAT03 | Spillway Structure and Gates | Spillway Gates |  |  |  |  | 332 | Complete Set
SGGAT04 | Spillway Structure and Gates | Spillway Gates |  |  |  |  | 332 | Each
SGGAT05 | Spillway Structure and Gates | Spillway Gates |  |  |  |  | 332
SGHPS | Heat Recovery Steam Generator | High Pressure System |  |  | 342 |  |  | Each
SGHPS01 | Heat Recovery Steam Generator | High Pressure System |  |  | 342 |  |  | Each
SGHPS02 | Heat Recovery Steam Generator | High Pressure System |  |  | 342 |  |  | Each
SGHPS03 | Heat Recovery Steam Generator | High Pressure System |  |  | 342 |  |  | Identifiable Grouping
SGHPS04 | Heat Recovery Steam Generator | High Pressure System |  |  | 342
SGHPS05 | Heat Recovery Steam Generator | High Pressure System |  |  | 342 |  |  | Each
SGHPS06 | Heat Recovery Steam Generator | High Pressure System |  |  | 342 |  |  | Each
SGHPS07 | Heat Recovery Steam Generator | High Pressure System |  |  | 342 |  |  | Identifiable Grouping
SGHPS08 | Heat Recovery Steam Generator | High Pressure System |  |  | 342
SGHPS09 | Heat Recovery Steam Generator | High Pressure System |  |  | 342 |  |  | Each
SGHPS10 | Heat Recovery Steam Generator | High Pressure System |  |  | 342 |  |  | Each
SGHPS11 | Heat Recovery Steam Generator | High Pressure System |  |  | 342 |  |  | Identifiable Grouping
SGHPS12 | Heat Recovery Steam Generator | High Pressure System |  |  | 342 |  |  | Each
SGHPS13 | Heat Recovery Steam Generator | High Pressure System |  |  | 342 |  |  | Each
SGHPS14 | Heat Recovery Steam Generator | High Pressure System |  |  | 342 |  |  | Each
SGHPS15 | Heat Recovery Steam Generator | High Pressure System |  |  | 342 |  |  | Complete System
SGHPS16 | Heat Recovery Steam Generator | High Pressure System |  |  | 342 |  |  | Each
SGHPS17 | Heat Recovery Steam Generator | High Pressure System |  |  | 342
SGINS | Heat Recovery Steam Generator | Insulation |  |  | 342 |  |  | Each
SGINS01 | Heat Recovery Steam Generator | Insulation |  |  | 342 |  |  | Each
SGINS02 | Heat Recovery Steam Generator | Insulation |  |  | 342 |  |  | Each
SGINS03 | Heat Recovery Steam Generator | Insulation |  |  | 342
SGIPS | Heat Recovery Steam Generator | Intermediate Pressure System |  |  | 342 |  |  | Each
SGIPS01 | Heat Recovery Steam Generator | Intermediate Pressure System |  |  | 342 |  |  | Each
SGIPS02 | Heat Recovery Steam Generator | Intermediate Pressure System |  |  | 342 |  |  | Each
SGIPS03 | Heat Recovery Steam Generator | Intermediate Pressure System |  |  | 342 |  |  | Identifiable Grouping
SGIPS04 | Heat Recovery Steam Generator | Intermediate Pressure System |  |  | 342
SGIPS05 | Heat Recovery Steam Generator | Intermediate Pressure System |  |  | 342 |  |  | Each
SGIPS06 | Heat Recovery Steam Generator | Intermediate Pressure System |  |  | 342 |  |  | Each
SGIPS07 | Heat Recovery Steam Generator | Intermediate Pressure System |  |  | 342 |  |  | Identifiable Grouping
SGIPS08 | Heat Recovery Steam Generator | Intermediate Pressure System |  |  | 342
SGIPS09 | Heat Recovery Steam Generator | Intermediate Pressure System |  |  | 342 |  |  | Each
SGIPS10 | Heat Recovery Steam Generator | Intermediate Pressure System |  |  | 342 |  |  | Each
SGIPS11 | Heat Recovery Steam Generator | Intermediate Pressure System |  |  | 342 |  |  | Identifiable Grouping
SGIPS12 | Heat Recovery Steam Generator | Intermediate Pressure System |  |  | 342 |  |  | Each
SGIPS13 | Heat Recovery Steam Generator | Intermediate Pressure System |  |  | 342 |  |  | Each
SGIPS14 | Heat Recovery Steam Generator | Intermediate Pressure System |  |  | 342 |  |  | Each
SGIPS15 | Heat Recovery Steam Generator | Intermediate Pressure System |  |  | 342 |  |  | Complete System
SGIPS16 | Heat Recovery Steam Generator | Intermediate Pressure System |  |  | 342 |  |  | Each
SGIPS17 | Heat Recovery Steam Generator | Intermediate Pressure System |  |  | 342
SGLOG | Spillway Structure and Gates | Spillway Stop Log |  |  |  |  | 332 | Complete Set
SGLOG01 | Spillway Structure and Gates | Spillway Stop Log |  |  |  |  | 332
SGLPS | Heat Recovery Steam Generator | Low Pressure System |  |  | 342 |  |  | Each
SGLPS01 | Heat Recovery Steam Generator | Low Pressure System |  |  | 342 |  |  | Each
SGLPS02 | Heat Recovery Steam Generator | Low Pressure System |  |  | 342 |  |  | Each
SGLPS03 | Heat Recovery Steam Generator | Low Pressure System |  |  | 342 |  |  | Identifiable Grouping
SGLPS04 | Heat Recovery Steam Generator | Low Pressure System |  |  | 342
SGLPS05 | Heat Recovery Steam Generator | Low Pressure System |  |  | 342 |  |  | Each
SGLPS06 | Heat Recovery Steam Generator | Low Pressure System |  |  | 342 |  |  | Each
SGLPS07 | Heat Recovery Steam Generator | Low Pressure System |  |  | 342 |  |  | Identifiable Grouping
SGLPS08 | Heat Recovery Steam Generator | Low Pressure System |  |  | 342
SGLPS09 | Heat Recovery Steam Generator | Low Pressure System |  |  | 342 |  |  | Each
SGLPS10 | Heat Recovery Steam Generator | Low Pressure System |  |  | 342 |  |  | Each
SGLPS11 | Heat Recovery Steam Generator | Low Pressure System |  |  | 342 |  |  | Identifiable Grouping
SGLPS12 | Heat Recovery Steam Generator | Low Pressure System |  |  | 342 |  |  | Each
SGLPS13 | Heat Recovery Steam Generator | Low Pressure System |  |  | 342 |  |  | Each
SGLPS14 | Heat Recovery Steam Generator | Low Pressure System |  |  | 342 |  |  | Each
SGLPS15 | Heat Recovery Steam Generator | Low Pressure System |  |  | 342 |  |  | Complete System
SGLPS16 | Heat Recovery Steam Generator | Low Pressure System |  |  | 342 |  |  | Each
SGLPS17 | Heat Recovery Steam Generator | Low Pressure System |  |  | 342 |  |  | Each
SGLPS18 | Heat Recovery Steam Generator | Low Pressure System |  |  | 342 |  |  | Complete System
SGLPS19 | Heat Recovery Steam Generator | Low Pressure System |  |  | 342
SGRHT | Heat Recovery Steam Generator | Reheater |  |  | 342 |  |  | Each
SGRHT01 | Heat Recovery Steam Generator | Reheater |  |  | 342 |  |  | Each
SGRHT02 | Heat Recovery Steam Generator | Reheater |  |  | 342 |  |  | Identifiable Grouping
SGRHT03 | Heat Recovery Steam Generator | Reheater |  |  | 342 |  |  | Each
SGRHT04 | Heat Recovery Steam Generator | Reheater |  |  | 342 |  |  | Each
SGRHT05 | Heat Recovery Steam Generator | Reheater |  |  | 342 |  |  | Complete System
SGRHT06 | Heat Recovery Steam Generator | Reheater |  |  | 342 |  |  | Each
SGRHT07 | Heat Recovery Steam Generator | Reheater |  |  | 342
SGSTK | Heat Recovery Steam Generator | Stack |  |  | 342 |  |  | Each
SGSTK01 | Heat Recovery Steam Generator | Stack |  |  | 342 |  |  | Each
SGSTK02 | Heat Recovery Steam Generator | Stack |  |  | 342 |  |  | Each
SGSTK03 | Heat Recovery Steam Generator | Stack |  |  | 342 |  |  | Each
SGSTK04 | Heat Recovery Steam Generator | Stack |  |  | 342 |  |  | Each
SGSTK05 | Heat Recovery Steam Generator | Stack |  |  | 342 |  |  | Each
SGSTK06 | Heat Recovery Steam Generator | Stack |  |  | 342
SGSTL | Heat Recovery Steam Generator | Structural |  |  | 342 |  |  | Each
SGSTL01 | Heat Recovery Steam Generator | Structural |  |  | 342 |  |  | Each
SGSTL02 | Heat Recovery Steam Generator | Structural |  |  | 342
SGSTR | Spillway Structure and Gates | Spillway Structure |  |  |  |  | 332 | Each Section
SGSTR01 | Spillway Structure and Gates | Spillway Structure |  |  |  |  | 332 | Each
SGSTR02 | Spillway Structure and Gates | Spillway Structure |  |  |  |  | 332 | Each
SGSTR03 | Spillway Structure and Gates | Spillway Structure |  |  |  |  | 332 | Each
SGSTR04 | Spillway Structure and Gates | Spillway Structure |  |  |  |  | 332 | Each
SGSTR05 | Spillway Structure and Gates | Spillway Structure |  |  |  |  | 332
SMADM | Structures and Improvements | Administration or Office Buildings |  |  |  |  | 331
SMCOT | Structures and Improvements | Cottages (Employees Only) |  |  |  |  | 331
SMCRA | Structures and Improvements | Crane Assembly |  |  |  |  | 331
SMDOM | Structures and Improvements | Domestic Water and Sewer Systems |  |  |  |  | 331
SMFEN | Structures and Improvements | Fence |  |  |  |  | 331
SMFLS | Structures and Improvements | Fuel Storage System |  |  |  |  | 331 | Each
SMFLS01 | Structures and Improvements | Fuel Storage System |  |  |  |  | 331 | Each
SMFLS02 | Structures and Improvements | Fuel Storage System |  |  |  |  | 331
SMGRN | Structures and Improvements | Grounds and Landscaping |  |  |  |  | 331 | Each
SMGRN01 | Structures and Improvements | Grounds and Landscaping |  |  |  |  | 331 | Each
SMGRN02 | Structures and Improvements | Grounds and Landscaping |  |  |  |  | 331
SMPHS | Structures and Improvements | Power House Structure |  |  |  |  | 331
SMSHP | Structures and Improvements | Shop |  |  |  |  | 331
SMSTR | Structures and Improvements | Miscellaneous Structures |  |  |  |  | 331
SMWHS | Structures and Improvements | Warehouse |  |  |  |  | 331
SOABS | Scrubber | Absorber |  | 312 |  |  |  | Each
SOABS01 | Scrubber | Absorber |  | 312 |  |  |  | Each
SOABS01a | Scrubber | Absorber |  | 312 |  |  |  | Each
SOABS01b | Scrubber | Absorber |  | 312 |  |  |  | Each
SOABS01c | Scrubber | Absorber |  | 312 |  |  |  | Each
SOABS01d | Scrubber | Absorber |  | 312 |  |  |  | Each
SOABS01e | Scrubber | Absorber |  | 312 |  |  |  | Each
SOABS02 | Scrubber | Absorber |  | 312 |  |  |  | Each
SOABS03 | Scrubber | Absorber |  | 312 |  |  |  | Each
SOABS04 | Scrubber | Absorber |  | 312
SOABS05 | Scrubber | Absorber |  | 312 |  |  |  | Each
SOABS06 | Scrubber | Absorber | ASBLY | 312 |  |  |  | Complete Assembly
SOABS07 | Scrubber | Absorber |  | 312 |  |  |  | Each
SOABS08 | Scrubber | Absorber |  | 312
SOATM | Scrubber | Atomizer System |  | 312 |  |  |  | Each
SOATM01 | Scrubber | Atomizer System |  | 312
SOBLD | Scrubber | Building Lighting |  | 312
SOBMS | Scrubber | Ball Mill Slaker |  | 312 |  |  |  | Each
SOBMS01 | Scrubber | Ball Mill Slaker |  | 312
SOCAC | Scrubber | Central Air Compressor |  | 312 |  |  |  | Each
SOCAC01 | Scrubber | Central Air Compressor |  | 312
SOCFS | Scrubber | Chemical Feed |  | 312 |  |  |  | Each
SOCFS01 | Scrubber | Chemical Feed |  | 312 |  |  |  | Each
SOCFS02 | Scrubber | Chemical Feed |  | 312 |  |  |  | Each
SOCFS03 | Scrubber | Chemical Feed |  | 312
SOCTR | Scrubber | Controls |  | 312
SODAM | Scrubber | Dampers |  | 312 |  |  |  | Each
SODAM01 | Scrubber | Dampers |  | 312 |  |  |  | Each
SODAM02 | Scrubber | Dampers |  | 312
SODIL | Scrubber | Dilution System |  | 312 |  |  |  | Each
SODIL01 | Scrubber | Dilution System |  | 312
SOFED | Scrubber | Feed System |  | 312 |  |  |  | Each
SOFED01 | Scrubber | Feed System |  | 312 |  |  |  | Each
SOFED02 | Scrubber | Feed System |  | 312
SOFLG | Scrubber | Flue Gas |  | 312 |  |  |  | Each
SOFLG01 | Scrubber | Flue Gas |  | 312 |  |  |  | Each
SOFLG01a | Scrubber | Flue Gas |  | 312 |  |  |  | Each
SOFLG01b | Scrubber | Flue Gas |  | 312 |  |  |  | Each Side
SOFLG01c | Scrubber | Flue Gas |  | 312 |  |  |  | Each Side
SOFLG01d | Scrubber | Flue Gas |  | 312 |  |  |  | Each
SOFLG01e | Scrubber | Flue Gas |  | 312 |  |  |  | Each
SOFLG01f | Scrubber | Flue Gas |  | 312 |  |  |  | Each
SOFLG01g | Scrubber | Flue Gas |  | 312 |  |  |  | Each
SOFLG01h | Scrubber | Flue Gas |  | 312 |  |  |  | Each
SOFLG01i | Scrubber | Flue Gas |  | 312 |  |  |  | Complete Set of Two
SOFLG01j | Scrubber | Flue Gas |  | 312 |  |  |  | Each
SOFLG01k | Scrubber | Flue Gas |  | 312 |  |  |  | Each Side
SOFLG01l | Scrubber | Flue Gas |  | 312 |  |  |  | Each
SOFLG01m | Scrubber | Flue Gas |  | 312 |  |  |  | Each
SOFLG01n | Scrubber | Flue Gas |  | 312 |  |  |  | Each
SOFLG01p | Scrubber | Flue Gas |  | 312 |  |  |  | Each
SOFLG02 | Scrubber | Flue Gas |  | 312 |  |  |  | Each
SOFLG02a | Scrubber | Flue Gas |  | 312 |  |  |  | Each
SOFLG02b | Scrubber | Flue Gas |  | 312 |  |  |  | Each Side
SOFLG02c | Scrubber | Flue Gas |  | 312 |  |  |  | Each Side
SOFLG02d | Scrubber | Flue Gas |  | 312 |  |  |  | Each
SOFLG02e | Scrubber | Flue Gas |  | 312 |  |  |  | Each
SOFLG02f | Scrubber | Flue Gas |  | 312 |  |  |  | Each
SOFLG02g | Scrubber | Flue Gas |  | 312 |  |  |  | Each
SOFLG02h | Scrubber | Flue Gas |  | 312 |  |  |  | Each
SOFLG02i | Scrubber | Flue Gas |  | 312 |  |  |  | Complete Set of Two
SOFLG02j | Scrubber | Flue Gas |  | 312 |  |  |  | Each
SOFLG02k | Scrubber | Flue Gas |  | 312 |  |  |  | Each Side
SOFLG02l | Scrubber | Flue Gas |  | 312 |  |  |  | Each
SOFLG02m | Scrubber | Flue Gas |  | 312 |  |  |  | Each
SOFLG02n | Scrubber | Flue Gas |  | 312 |  |  |  | Each
SOFLG03 | Scrubber | Flue Gas |  | 312 |  |  |  | Each
SOFLG04 | Scrubber | Flue Gas |  | 312 |  |  |  | Each
SOFLG05 | Scrubber | Flue Gas |  | 312 |  |  |  | Each
SOFLG06 | Scrubber | Flue Gas |  | 312 |  |  |  | Each
SOFLG07 | Scrubber | Flue Gas |  | 312
SOINA | Scrubber | Instrument Air |  | 312 |  |  |  | Each
SOINA01 | Scrubber | Instrument Air |  | 312
SOLFS | Scrubber | Lime Feed System |  | 312 |  |  |  | Each
SOLFS01 | Scrubber | Lime Feed System |  | 312 |  |  |  | Each
SOLFS02 | Scrubber | Lime Feed System |  | 312 |  |  |  | Each
SOLFS03 | Scrubber | Lime Feed System |  | 312 |  |  |  | Each
SOLFS04 | Scrubber | Lime Feed System |  | 312 |  |  |  | Each
SOLFS05 | Scrubber | Lime Feed System | ASBLY | 312 |  |  |  | Complete Assembly
SOLFS06 | Scrubber | Lime Feed System |  | 312 |  |  |  | Complete system
SOLFS07 | Scrubber | Lime Feed System |  | 312
SOLNS | Scrubber | Lignosite Metering Pumps |  | 312
SOMIS | Scrubber | Mist Eliminators |  | 312 |  |  |  | Each
SOMIS01 | Scrubber | Mist Eliminators |  | 312 |  |  |  | Complete system
SOMIS02 | Scrubber | Mist Eliminators |  | 312 |  |  |  | Complete Set
SOMIS03 | Scrubber | Mist Eliminators |  | 312
SONET | Scrubber | Net 90 |  | 312
SOPND | Scrubber | Scrubber |  | 312
SOPOS | Scrubber | Pond System |  | 312
SOPOS01 | Scrubber | Pond System |  | 312
SOPOS02 | Scrubber | Pond System |  | 312
SORCY | Scrubber | Recycle System |  | 312
SOREC | Scrubber | Recycle |  | 312 |  |  |  | Each
SOREC01 | Scrubber | Recycle |  | 312
SOREC01a | Scrubber | Recycle |  | 312 |  |  |  | Each
SOREC01b | Scrubber | Recycle |  | 312 |  |  |  | Each
SOREC02 | Scrubber | Recycle |  | 312
SOREG | Scrubber | Reagent System |  | 312
SOSCB** | Scrubber | Scrubber |  | 312
SOSCB | Scrubber | Scrubber |  | 312
SOSER | Scrubber | Service Air |  | 312
SOSLK | Scrubber | Slaking Water |  | 312 |  |  |  | Each
SOSLK01 | Scrubber | Slaking Water |  | 312 |  |  |  | Each
SOSLK02 | Scrubber | Slaking Water |  | 312
SOSLK03 | Scrubber | Slaking Water |  | 312 |  |  |  | Each
SOSLK04 | Scrubber | Slaking Water |  | 312
SOSLS | Scrubber | Soda Liquor |  | 312 |  |  |  | Each
SOSLS01 | Scrubber | Soda Liquor |  | 312 |  |  |  | Each
SOSLS02 | Scrubber | Soda Liquor |  | 312
SOSPA | Scrubber | Spray Dry Absorber |  | 312 |  |  |  | Each
SOSPA01 | Scrubber | Spray Dry Absorber |  | 312 |  |  |  | Each
SOSPA02 | Scrubber | Spray Dry Absorber |  | 312 |  |  |  | Each
SOSPA03 | Scrubber | Spray Dry Absorber |  | 312 |  |  |  | Each
SOSPA04 | Scrubber | Spray Dry Absorber |  | 312
SOSPL | Scrubber | Spent Liquor |  | 312 |  |  |  | Each
SOSPL01 | Scrubber | Spent Liquor |  | 312 |  |  |  | Each
SOSPL02 | Scrubber | Spent Liquor |  | 312
SOSPL03 | Scrubber | Spent Liquor |  | 312
SOSTM | Scrubber | Hot Water System |  | 312 |  |  |  | Each
SOSTM01 | Scrubber | Hot Water System |  | 312
SOSUM | Scrubber | Sump Water |  | 312 |  |  |  | Each
SOSUM01 | Scrubber | Sump Water |  | 312
SOSUP | Scrubber | Sump Pumps |  | 312 |  |  |  | Each
SOSUP01 | Scrubber | Sump Pumps |  | 312
SOSWR | Scrubber | Seal Water |  | 312 |  |  |  | Each
SOSWR01 | Scrubber | Seal Water |  | 312
SOSWT | Scrubber | Service Water |  | 312 |  |  |  | Each
SOSWT01 | Scrubber | Service Water |  | 312 |  |  |  | Each
SOSWT02 | Scrubber | Service Water |  | 312
SOTHK | Scrubber | Thickener |  | 312 |  |  |  | Each
SOTHK01 | Scrubber | Thickener |  | 312 |  |  |  | Each
SOTHK02 | Scrubber | Thickener |  | 312 |  |  |  | Each
SOTHK03 | Scrubber | Thickener |  | 312 |  |  |  | Each
SOTHK04 | Scrubber | Thickener |  | 312 |  |  |  | Each
SOTHK05 | Scrubber | Thickener |  | 312 |  |  |  | Each
SOTHK06 | Scrubber | Thickener |  | 312 |  |  |  | Each
SOTHK07 | Scrubber | Thickener |  | 312
SOVES | Scrubber | Vessel System |  | 312 |  |  |  | Each
SOVES01 | Scrubber | Vessel System |  | 312 |  |  |  | Each
SOVES02 | Scrubber | Vessel System |  | 312 |  |  |  | Complete Set
SOVES03 | Scrubber | Vessel System |  | 312 |  |  |  | Each
SOVES04 | Scrubber | Vessel System |  | 312 |  |  |  | Each
SOVES05 | Scrubber | Vessel System | ASBLY | 312 |  |  |  | Complete Assembly
SOVES06 | Scrubber | Vessel System |  | 312
SOWTR | Scrubber | Water Treatment |  | 312 |  |  |  | Each
SOWTR01 | Scrubber | Water Treatment |  | 312 |  |  |  | Each
SOWTR02 | Scrubber | Water Treatment |  | 312 |  |  |  | Each
SOWTR03 | Scrubber | Water Treatment |  | 312 |  |  |  | Lot
SP | Capital Spare Parts | Capital Inventory
SRBCN | Stacker/Reclaimer | Boom Conveyor |  | 312 |  |  |  | Each
SRBCN01 | Stacker/Reclaimer | Boom Conveyor |  | 312
SRBML | Stacker/Reclaimer | Boom Lift |  | 312 |  |  |  | Each
SRBML01 | Stacker/Reclaimer | Boom Lift |  | 312
SRBWH | Stacker/Reclaimer | Bucket Wheel |  | 312 |  |  |  | Each
SRBWH01 | Stacker/Reclaimer | Bucket Wheel |  | 312 |  |  |  | Each
SRBWH02 | Stacker/Reclaimer | Bucket Wheel |  | 312
SRECN | Stacker/Reclaimer | Elevating Conveyor |  | 312 |  |  |  | Each
SRECN01 | Stacker/Reclaimer | Elevating Conveyor |  | 312
SRSTR | Stacker/Reclaimer | Stacker/Reclaimer |  | 312 |  |  |  | Each
SRSTR01 | Stacker/Reclaimer | Stacker/Reclaimer |  | 312 |  |  |  | Each
SRSTR02 | Stacker/Reclaimer | Stacker/Reclaimer |  | 312 |  |  |  | Each
SRSTR03 | Stacker/Reclaimer | Stacker/Reclaimer |  | 312
SRSWD | Stacker/Reclaimer | Swing Drive |  | 312 |  |  |  | Each
SRSWD01 | Stacker/Reclaimer | Swing Drive |  | 312
SRTRA | Stacker/Reclaimer | Travel Assembly |  | 312 |  |  |  | Each
SRTRA01 | Stacker/Reclaimer | Travel Assembly |  | 312 |  |  |  | Each
SW303 | Miscellaneous Intangible Plant | Software |  | 303 | 303
TBEHS | Main Turbine | E-H System |  | 314 |  |  |  | Each
TBEHS01 | Main Turbine | E-H System |  | 314
TBHPT | Main Turbine | High Pressure (HP) Turbine |  | 314 |  |  |  | Each
TBHPT01 | Main Turbine | High Pressure (HP) Turbine |  | 314 |  |  |  | Each
TBHPT01a | Main Turbine | High Pressure (HP) Turbine |  | 314 |  |  |  | Each Row
TBHPT01b | Main Turbine | High Pressure (HP) Turbine |  | 314 |  |  |  | Each Row
TBHPT01c | Main Turbine | High Pressure (HP) Turbine |  | 314 |  |  |  | Each Upper and Lower
TBHPT02 | Main Turbine | High Pressure (HP) Turbine |  | 314 |  |  |  | Each Upper and Lower
TBHPT03 | Main Turbine | High Pressure (HP) Turbine |  | 314 |  |  |  | Each Upper and Lower
TBHPT04 | Main Turbine | High Pressure (HP) Turbine |  | 314 |  |  |  | Each Row - Upper and Lower
TBHPT05 | Main Turbine | High Pressure (HP) Turbine |  | 314 |  |  |  | Each Upper and Lower
TBHPT06 | Main Turbine | High Pressure (HP) Turbine | ASBLY | 314 |  |  |  | Complete Assembly
TBHPT07 | Main Turbine | High Pressure (HP) Turbine |  | 314
TBIAC | Main Turbine | Instrumentation |  | 314
TBINS | Main Turbine | Instruments/Controls | ASBLY | 314 |  |  |  | Complete Assembly
TBINS01 | Main Turbine | Instruments/Controls | ASBLY | 314 |  |  |  | Complete Assembly
TBINS10 | Main Turbine | Instruments/Controls
TBINT | Main Turbine | Alarms |  | 314 |  |  |  | Each
TBINT01 | Main Turbine | Alarms |  | 314
TBIPT | Main Turbine | Intermediate (IP) Turbine |  | 314 |  |  |  | Each
TBIPT01 | Main Turbine | Intermediate Pressure (IP) Turbine |  | 314 |  |  |  | Each
TBIPT01a | Main Turbine | Intermediate Pressure (IP) Turbine |  | 314 |  |  |  | Each Row
TBIPT01b | Main Turbine | Intermediate Pressure (IP) Turbine |  | 314 |  |  |  | Each Row
TBIPT01c | Main Turbine | Intermediate Pressure (IP) Turbine |  | 314
TBIPT02 | Main Turbine | Intermediate Pressure (IP) Turbine |  | 314 |  |  |  | Each Upper and Lower
TBIPT03 | Main Turbine | Intermediate Pressure (IP) Turbine |  | 314 |  |  |  | Each Upper and Lower
TBIPT04 | Main Turbine | Intermediate Pressure (IP) Turbine | ASBLY | 314 |  |  |  | Complete Assembly
TBIPT05 | Main Turbine | Intermediate Pressure (IP) Turbine | ASBLY | 314 |  |  |  | Complete Assembly
TBIPT06 | Main Turbine | Intermediate Pressure (IP) Turbine |  | 314
TBLPT | Main Turbine | Low Pressure (LP)Turbine |  | 314 |  |  |  | Each by Shell
TBLPT01 | Main Turbine | Low Pressure (LP)Turbine |  | 314 |  |  |  | Each
TBLPT01a | Main Turbine | Low Pressure (LP)Turbine |  | 314 |  |  |  | Each
TBLPT01b | Main Turbine | Low Pressure (LP)Turbine |  | 314 |  |  |  | Each Row
TBLPT01c | Main Turbine | Low Pressure (LP)Turbine |  | 314 |  |  |  | Each Row
TBLPT01d | Main Turbine | Low Pressure (LP)Turbine |  | 314 |  |  |  | Each Upper and Lower
TBLPT02 | Main Turbine | Low Pressure (LP)Turbine |  | 314 |  |  |  | Each Upper and Lower
TBLPT03 | Main Turbine | Low Pressure (LP)Turbine |  | 314 |  |  |  | Each Upper and Lower
TBLPT04 | Main Turbine | Low Pressure (LP)Turbine |  | 314 |  |  |  | Each Upper and Lower
TBLPT05 | Main Turbine | Low Pressure (LP)Turbine | ASBLY | 314 |  |  |  | Complete Assembly
TBLPT06 | Main Turbine | Low Pressure (LP)Turbine |  | 314
TBLPT07 | Main Turbine | Low Pressure (LP)Turbine |  | 314
TBSES | Main Turbine | Seal Steam System |  | 314 |  |  |  | Each
TBSES01 | Main Turbine | Seal Steam System |  | 314 |  |  |  | Complete Set by Rotor Section
TBSES02 | Main Turbine | Seal Steam System |  | 314 |  |  |  | Complete Set by Rotor Section
TBSES03 | Main Turbine | Seal Steam System |  | 314 |  |  |  | Complete Set by Rotor Section
TBSES04 | Main Turbine | Seal Steam System |  | 314 |  |  |  | Each
TBSES05 | Main Turbine | Seal Steam System |  | 314 |  |  |  | Each
TBSES06 | Main Turbine | Seal Steam System |  | 314
TBTLO | Main Turbine | Turbine Lube Oil Sample |  | 314
TBTRB | Main Turbine | Turbine |  | 314 |  |  |  | Each Turbine Section
TBTRB01 | Main Turbine | Turbine |  | 314 |  |  |  | Each
TBTRB02 | Main Turbine | Turbine |  | 314
TBTRB03 | Main Turbine | Turbine |  | 314 |  |  |  | Complete Set
TBTRB04 | Main Turbine | Turbine |  | 314 |  |  |  | Complete Set
TBTRB05 | Main Turbine | Turbine |  | 314 |  |  |  | Each
TBTRB06 | Main Turbine | Turbine |  | 314 |  |  |  | Each
TBTRB07 | Main Turbine | Turbine |  | 314
TBVLV | Main Turbine | Valves - Steam, Throttle, etc |  | 314 |  |  |  | Each
TBVLV01 | Main Turbine | Valves - Steam, Throttle, etc |  | 314 |  |  |  | Each
TBVLV02 | Main Turbine | Valves - Steam, Throttle, etc |  | 314
TBVLV03 | Main Turbine | Valves - Steam, Throttle, etc |  | 314 |  |  |  | Each
TBVLV04 | Main Turbine | Valves - Steam, Throttle, etc |  | 314 |  |  |  | Each
TBVLV05 | Main Turbine | Valves - Steam, Throttle, etc |  | 314 |  |  |  | Each
TBVLV06 | Main Turbine | Valves - Steam, Throttle, etc |  | 314 |  |  |  | Each
TBVLV07 | Main Turbine | Valves - Steam, Throttle, etc |  | 314 |  |  |  | Each
TBVLV08 | Main Turbine | Valves - Steam, Throttle, etc |  | 314 |  |  |  | Complete Set
TBVLV09 | Main Turbine | Valves - Steam, Throttle, etc |  | 314
TETEL | Communications | Plant Communications |  | 316 | 346 |  |  | Complete System
TETEL01 | Communications | Plant Communications |  | 316 | 346 |  |  | Complete System
TETEL02 | Communications | Plant Communications |  | 316 | 346 |  |  | Each
TRANS | General Mass Property | Vehicles |  | 392 | 392 | 392 | 392
TUBCW | Turbine System | Bearing Cooling System |  |  |  |  | 333 | Each
TUBCW01 | Turbine System | Bearing Cooling System |  |  |  |  | 333
TUBRG | Turbine System | Bearings |  |  |  |  | 333 | Each
TUBRG01 | Turbine System | Bearings |  |  |  |  | 333 | Each
TUBRG02 | Turbine System | Bearings |  |  |  |  | 333 | Each
TUBRG03 | Turbine System | Bearings |  |  |  |  | 333 | Each
TUBRG04 | Turbine System | Bearings |  |  |  |  | 333 | Complete Set
TUBRG05 | Turbine System | Bearings |  |  |  |  | 333 | Each
TUBRG06 | Turbine System | Bearings |  |  |  |  | 333
TUNOZ | Turbine System | Needle Valve Assembly |  |  |  |  | 333 | Each
TUNOZ01 | Turbine System | Needle Valve Assembly |  |  |  |  | 333 | Each
TUNOZ02 | Turbine System | Needle Valve Assembly |  |  |  |  | 333
TURNR | Turbine System | Runner |  |  |  |  | 333 | Each
TURNR01 | Turbine System | Runner |  |  |  |  | 333 | Complete Set
TURNR02 | Turbine System | Runner |  |  |  |  | 333 | Each
TURNR03 | Turbine System | Runner |  |  |  |  | 333
TUTBL | Turbine System | Lube Oil System |  |  |  |  | 333 | Each
TUTBL01 | Turbine System | Lube Oil System |  |  |  |  | 333
TUTRB | Turbine System | Turbine |  |  |  |  | 333 | Each
TUTRB01 | Turbine System | Turbine |  |  |  |  | 333 | Each
TUTRB02 | Turbine System | Turbine |  |  |  |  | 333 | Each
TUTRB03 | Turbine System | Turbine |  |  |  |  | 333 | Each
TUTRB04 | Turbine System | Turbine |  |  |  |  | 333 | Each
TUTRB05 | Turbine System | Turbine |  |  |  |  | 333 | Complete Set
TUTRB06 | Turbine System | Turbine |  |  |  |  | 333
TUWKT | Turbine System | Wicket Gate Assembly |  |  |  |  | 333 | Each
TUWKT01 | Turbine System | Wicket Gate Assembly |  |  |  |  | 333 | Complete Set
TUWKT02 | Turbine System | Wicket Gate Assembly |  |  |  |  | 333 | Each
TUWKT03 | Turbine System | Wicket Gate Assembly |  |  |  |  | 333 | Each
TUWKT04 | Turbine System | Wicket Gate Assembly |  |  |  |  | 333 | Complete Set
TUWKT05 | Turbine System | Wicket Gate Assembly |  |  |  |  | 333
WCCAN | Waterways | Canals |  |  |  |  | 332 | Each
WCCAN01 | Waterways | Canals |  |  |  |  | 332 | Each
WCCAN02 | Waterways | Canals |  |  |  |  | 332 | Linear Feet
WCCAN03 | Waterways | Canals |  |  |  |  | 332 | Each
WCCAN04 | Waterways | Canals |  |  |  |  | 332 | Each
WCCAN05 | Waterways | Canals |  |  |  |  | 332 | Each
WCCAN06 | Waterways | Canals |  |  |  |  | 332 | Each
WCCAN07 | Waterways | Canals |  |  |  |  | 332 | Complete Set
WCCAN08 | Waterways | Canals |  |  |  |  | 332 | Each
WCCAN09 | Waterways | Canals |  |  |  |  | 332 | Each Structure
WCCAN10 | Waterways | Canals |  |  |  |  | 332 | Linear Feet
WCCAN11 | Waterways | Canals |  |  |  |  | 332 | Each
WCCAN12 | Waterways | Canals |  |  |  |  | 332
WCFEN | Waterways | Fence |  |  |  |  | 332
WCFLU | Waterways | Flumes |  |  |  |  | 332 | Linear Feet
WCFLU01 | Waterways | Flumes |  |  |  |  | 332 | Each
WCFLU02 | Waterways | Flumes |  |  |  |  | 332 | Complete Set
WCFLU03 | Waterways | Flumes |  |  |  |  | 332 | Each
WCFLU04 | Waterways | Flumes |  |  |  |  | 332 | Linear Feet
WCFLU05 | Waterways | Flumes |  |  |  |  | 332 | Each
WCFLU06 | Waterways | Flumes |  |  |  |  | 332
WCFSH | Waterways | Fish Ladders, Screens and Traps |  |  |  |  | 332 | Each
WCFSH01 | Waterways | Fish Ladders, Screens and Traps |  |  |  |  | 332 | Each
WCFSH02 | Waterways | Fish Ladders, Screens and Traps |  |  |  |  | 332 | Each
WCFSH03 | Waterways | Fish Ladders, Screens and Traps |  |  |  |  | 332 | Each
WCFSH04 | Waterways | Fish Ladders, Screens and Traps |  |  |  |  | 332 | Complete Set
WCFSH05 | Waterways | Fish Ladders, Screens and Traps |  |  |  |  | 332 | Each
WCFSH06 | Waterways | Fish Ladders, Screens and Traps |  |  |  |  | 332 | Each
WCFSH07 | Waterways | Fish Ladders, Screens and Traps |  |  |  |  | 332
WCLOG | Waterways | Stop Logs |  |  |  |  | 332 | Complete Set
WCLOG01 | Waterways | Stop Logs |  |  |  |  | 332
WCPEN | Waterways | Penstocks and Flowlines |  |  |  |  | 332 | Linear feet
WCPEN01 | Waterways | Penstocks and Flowlines |  |  |  |  | 332 | Each Structure
WCPEN02 | Waterways | Penstocks and Flowlines |  |  |  |  | 332 | Each Structure
WCPEN03 | Waterways | Penstocks and Flowlines |  |  |  |  | 332 | Each
WCPEN04 | Waterways | Penstocks and Flowlines |  |  |  |  | 332
WCRIV | Waterways | River |  |  |  |  | 332
WCSUG | Waterways | Surge Tanks |  |  |  |  | 332 | Each
WCSUG01 | Waterways | Surge Tanks |  |  |  |  | 332 | Each
WCSUG02 | Waterways | Surge Tanks |  |  |  |  | 332
WCTRC | Waterways | Tail Race |  |  |  |  | 332
WCTSV | Waterways | Turbine Isolation Valves (Penstock Valve or Turbine Stop Valve) |  |  |  |  | 332 | Each
WCTSV01 | Waterways | Turbine Isolation Valves (Penstock Valve or Turbine Stop Valve) |  |  |  |  | 332 | Each
WCTSV02 | Waterways | Turbine Isolation Valves (Penstock Valve or Turbine Stop Valve) |  |  |  |  | 332
WFFSH | Wildlife and Fish Facilities | Fish Facilities |  |  |  |  | 331 | Each
WFFSH01 | Wildlife and Fish Facilities | Fish Facilities |  |  |  |  | 331 | Each Structure
WFFSH02 | Wildlife and Fish Facilities | Fish Facilities |  |  |  |  | 331 | Each
WFFSH03 | Wildlife and Fish Facilities | Fish Facilities |  |  |  |  | 331 | Each
WFFSH04 | Wildlife and Fish Facilities | Fish Facilities |  |  |  |  | 331
WFWFD | Wildlife and Fish Facilities | Wildlife Facilities |  |  |  |  | 331 | Complete for an Area
WFWFD01 | Wildlife and Fish Facilities | Wildlife Facilities |  |  |  |  | 331 | Complete for an Area
WFWFD02 | Wildlife and Fish Facilities | Wildlife Facilities |  |  |  |  | 331
WGBBA | Wind Generation | Blade |  |  |  | 343 |  | Each
WGBBA01 | Wind Generation | Blade |  |  |  | 343 |  | Each
WGBBA02 | Wind Generation | Blade |  |  |  | 343 |  | Each
WGBBA03 | Wind Generation | Blade |  |  |  | 343 |  | Each
WGBBA04 | Wind Generation | Blade |  |  |  | 343
WGBGS | Wind Generation | Shaft, Blade Connecting |  |  |  | 343 |  | Each
WGBGS01 | Wind Generation | Shaft, Blade Connecting |  |  |  | 343
WGCSH | Wind Generation | Control System |  |  |  | 345 |  | Complete system
WGCSH01 | Wind Generation | Control System |  |  |  | 345 |  | Each
WGCSH02 | Wind Generation | Control System |  |  |  | 345 |  | Each
WGCSH03 | Wind Generation | Control System |  |  |  | 345
WGELE | Wind Generation | Electrical |  |  |  | 345 |  | Complete system
WGELE01 | Wind Generation | Electrical |  |  |  | 345 |  | Each
WGELE02 | Wind Generation | Electrical |  |  |  | 345
WGFND | Wind Generation | Structure |  |  |  | 343 |  | Each
WGFND01 | Wind Generation | Structure |  |  |  | 343
WGGBA | Wind Generation | Gearbox Assembly |  |  |  | 343 |  | Each
WGGBA01 | Wind Generation | Gearbox Assembly |  |  |  | 343
WGGEN | Wind Generation | Generator Assembly |  |  |  | 344 |  | Each
WGGEN01 | Wind Generation | Generator Assembly |  |  |  | 344
WGHPM | Wind Generation | Hydraulic Pump/Motor Assembly |  |  |  | 343 |  | Each
WGHPM01 | Wind Generation | Hydraulic Pump/Motor Assembly |  |  |  | 343
WGMTR | Wind Generation | Meteorological Tower |  |  |  | 346 |  | Each
WGMTR01 | Wind Generation | Meteorological Tower |  |  |  | 346
WGNFA | Wind Generation | Nacelle-Frame Assembly |  |  |  | 344 |  | Each
WGNFA01 | Wind Generation | Nacelle-Frame Assembly |  |  |  | 344 |  | Each
WGNFA02 | Wind Generation | Nacelle-Frame Assembly |  |  |  | 344
WGRHA | Wind Generation | Rotor Head Assembly |  |  |  | 343 |  | Each
WGRHA01 | Wind Generation | Rotor Head Assembly |  |  |  | 343
WGSRD | Wind Generation | Roads |  |  |  | 341 |  | Linear Feet
WGSRD01 | Wind Generation | Roads |  |  |  | 341 |  | Each
WGSRD02 | Wind Generation | Roads |  |  |  | 341 |  | Lot
WGSRD03 | Wind Generation | Roads |  |  |  | 341 |  | Lot
WGSRD04 | Wind Generation | Roads |  |  |  | 341 |  | Each
WGSRD05 | Wind Generation | Roads |  |  |  | 341 |  | Each
WGSRD06 | Wind Generation | Roads |  |  |  | 341 |  | Each
WGSRD07 | Wind Generation | Roads |  |  |  | 341
WGTLS | Wind Generation | Structural Tower - Lower Section |  |  |  | 343 |  | Each
WGTLS01 | Wind Generation | Structural Tower - Lower Section |  |  |  | 343
WGTMS | Wind Generation | Structural Tower - Mid Section |  |  |  | 343 |  | Each
WGTMS01 | Wind Generation | Structural Tower - Mid Section |  |  |  | 343
WGTUS | Wind Generation | Structural Tower - Upper Section |  |  |  | 343 |  | Each
WGTUS01 | Wind Generation | Structural Tower - Upper Section |  |  |  | 343
WGYGA | Wind Generation | Yaw Assembly |  |  |  | 343 |  | Each
WGYGA01 | Wind Generation | Yaw Assembly |  |  |  | 343 |  | Each
WGYGA02 | Wind Generation | Yaw Assembly |  |  |  | 343
WPCRN | Water Supply - Pump Plant | Chlorine |  | 311 | 341 |  |  | Each
WPCRN01 | Water Supply - Pump Plant | Chlorine |  | 311 | 341
WPDOM | Water Supply - Pump Plant | Domestic Water |  | 311 | 341
WPFLT | Water Supply - Pump Plant | Filter Plant |  | 311 | 341 |  |  | Each
WPFLT01 | Water Supply - Pump Plant | Filter Plant |  | 311 | 341
WPGRS | Water Supply - Pump Plant | Green River Station |  | 311 |  |  |  | Each
WPGRS01 | Water Supply - Pump Plant | Green River Station |  | 311
WPGST | Water Supply - Pump Plant | Gillette Station |  | 311 |  |  |  | Each
WPGST01 | Water Supply - Pump Plant | Gillette Station |  | 311
WPHDR | Water Supply - Pump Plant | Hydraulics |  | 311 | 341
WPPND | Water Supply - Pump Plant | Surge Pond |  | 311 | 341 |  |  | Each
WPPND01 | Water Supply - Pump Plant | Surge Pond |  | 311 | 341
WPPOW | Water Supply - Pump Plant | Potable Water |  | 311 | 341 |  |  | Each
WPPOW01 | Water Supply - Pump Plant | Potable Water |  | 311 | 341
WPRAW | Water Supply - Pump Plant | Raw Water |  | 311 | 341 |  |  | Each
WPRAW01 | Water Supply - Pump Plant | Raw Water |  | 311 | 341 |  |  | Each
WPRAW02 | Water Supply - Pump Plant | Raw Water | ASBLY | 311 | 341 |  |  | Complete Assembly
WPRAW03 | Water Supply - Pump Plant | Raw Water |  | 311 | 341
WPSWT | Water Supply - Pump Plant | Service Water |  | 311 | 341
WPTVS | Water Supply - Pump Plant | Traveling Screens |  | 311 | 341 |  |  | Each
WPTVS01 | Water Supply - Pump Plant | Traveling Screens |  | 311 | 341
WPWLL | Water Supply - Pump Plant | Deep Wells |  | 311 | 341 |  |  | Each
WPWLL01 | Water Supply - Pump Plant | Deep Wells |  | 311 | 341 |  |  | Lot
WRT310 | Water Rights | Water Rights |  | 310 |  |  |  | Lot
WRT340 | Water Rights | Water Rights |  |  | 340
WTACD | Water Treatment - Boiler Maint | Acid Storage |  | 312 | 342 |  |  | Each
WTACD01 | Water Treatment - Boiler Maint | Acid Storage |  | 312 | 342 |  |  | Each
WTACD02 | Water Treatment - Boiler Maint | Acid Storage |  | 312 | 342
WTAPA | Water Treatment - Boiler Maint | Ash Pond Acid Injection |  | 312 |  |  |  | Each
WTAPA01 | Water Treatment - Boiler Maint | Ash Pond Acid Injection |  | 312
WTBRN | Water Treatment - Boiler Maint | Brine System |  | 312
WTCTR | Water Treatment - Boiler Maint | Water Treatment Controls |  | 312 | 342
WTEVP | Water Treatment - Boiler Maint | Evaporator |  | 312 |  |  |  | Each
WTEVP01 | Water Treatment - Boiler Maint | Evaporator |  | 312 |  |  |  | Each
WTEVP02 | Water Treatment - Boiler Maint | Evaporator |  | 312
WTLAB | Water Treatment - Boiler Maint | Lab Equipment |  | 312 | 342
WTRCC | Water Treatment - Boiler Maint | Resources Conservation Corp |  | 312 | 342 |  |  | Complete Module
WTRCC01 | Water Treatment - Boiler Maint | Resources Conservation Corp |  | 312 | 342 |  |  | Each
WTRCC02 | Water Treatment - Boiler Maint | Resources Conservation Corp |  | 312 | 342 |  |  | Each
WTRCC03 | Water Treatment - Boiler Maint | Resources Conservation Corp |  | 312 | 342 |  |  | Each
WTRCC04 | Water Treatment - Boiler Maint | Resources Conservation Corp |  | 312 | 342 |  |  | Each
WTRCC05 | Water Treatment - Boiler Maint | Resources Conservation Corp |  | 312 | 342
WTWSF | Water Treatment - Boiler Maint | Water Softener |  | 312 | 342 |  |  | Each
WTWSF01 | Water Treatment - Boiler Maint | Water Softener |  | 312 | 342
WWADM | Waste Water | Administrative Building |  | 311 | 341
WWBDD | Waste Water | Building Drains |  | 311 | 341
WWBPP | Waste Water | Booster Pump |  | 311 | 341
WWCHM | Waste Water | Chemical Treatment |  | 311 | 341
WWCPR | Waste Water | Coal Pile Run-off |  | 311
WWEFF | Waste Water | Effluent Ponds - Evaporation Ponds |  | 311 | 341 |  |  | Each
WWEFF01 | Waste Water | Effluent Ponds - Evaporation Ponds |  | 311 | 341 |  |  | Each
WWEFF02 | Waste Water | Effluent Ponds - Evaporation Ponds |  | 311 | 341
WWIRR | Waste Water | Irrigation |  | 311 | 341 |  |  | Each
WWIRR01 | Waste Water | Irrigation |  | 311 | 341 |  |  | Each
WWIRR02 | Waste Water | Irrigation |  | 311 | 341 |  |  | Each
WWIRR03 | Waste Water | Irrigation |  | 311 | 341 |  |  | Each
WWIRR04 | Waste Water | Irrigation |  | 311 | 341
WWSFT | Waste Water | Sand Filter |  | 311
WWSTP | Waste Water | Sewage Treatment Plant |  | 311 | 341 |  |  | Complete system
WWSTP01 | Waste Water | Sewage Treatment Plant |  | 311 | 341 |  |  | Each
WWSTP02 | Waste Water | Sewage Treatment Plant |  | 311 | 341 |  |  | Each
WWSTP03 | Waste Water | Sewage Treatment Plant |  | 311 | 341 |  |  | Each
WWSTP04 | Waste Water | Sewage Treatment Plant |  | 311 | 341 |  |  | Each
WWSTP05 | Waste Water | Sewage Treatment Plant |  | 311 | 341
WWSUR | Waste Water | Surface Drainage |  | 311 | 341
WWWWM | Waste Water | Waste Water Management |  | 311 | 341 |  |  | Each
WWWWM01 | Waste Water | Waste Water Management |  | 311 | 341 |  |  | Each
WWWWM02 | Waste Water | Waste Water Management |  | 311 | 341 |  |  | Each
WWWWM03 | Waste Water | Waste Water Management |  | 311 | 341
WWYRD | Waste Water | Yard Drains |  | 311 | 341

## PC
Profit Ctr | Func | Location | State | Description
1001 | S | P000270 | WY | Naughton Plant (B/S) - Materials
1002 | S | P000271 | WY | Naughton Plant - Unit One
1003 | S | P000272 | WY | Naughton Plant - Unit Two
1004 | S | P000273 | WY | Naughton Plant - Unit Three
1009 | C | G000001 | OR | C&T Executive
1057 | S | P000467 | WY | Viva Naughton Plant
1058 | S | P517000 | WY | Jim Bridger Plant Common
1059 | S | P517001 | WY | Jim Bridger Plant - Unit One
1060 | S | P517002 | WY | Jim Bridger Plant - Unit Two
1061 | S | P517003 | WY | Jim Bridger Plant - Unit Three
1062 | S | P517004 | WY | Jim Bridger Plant - Unit Four
1063 | S | P000250 | UT | Carbon Plant- Common Core
1064 | S | P000251 | UT | Carbon Plant- Unit One
1065 | S | P000252 | UT | Carbon Plant- Unit Two
1066 | S | P000300 | UT | Hunter Plant Common Core
1067 | S | P000301 | UT | Hunter Plant Unit One
1068 | S | P000302 | UT | Hunter Plant Unit Two
1069 | S | P000303 | UT | Hunter Plant Unit Three
1070 | S | P000280 | UT | Huntington Plant Common Core
1071 | S | P000281 | UT | Huntington Plant Unit One
1072 | S | P000282 | UT | Huntington Plant Unit Two
1073 | S | P514000 | WY | Dave Johnston Plant Common Core
1074 | S | P514001 | WY | Dave Johnston Plant Unit One
1075 | S | P514002 | WY | Dave Johnston Plant Unit Two
1076 | S | P514003 | WY | Dave Johnston Plant Unit Three
1077 | S | P514004 | WY | Dave Johnston Plant Unit Four
1078 | S | P519000 | WY | Wyodak Plant Common Core
1079 | S | P519001 | WY | Wyodak Plant Unit One
1080 | S | P000260 | UT | Gadsby Gas Common
1081 | S | P000261 | UT | Gadsby Plant Unit #1
1082 | I | P201000 | WA | Centralia Plant Common Core
1083 | I | P201001 | WA | Centralia Plant Unit One
1084 | I | P201002 | WA | Centralia Plant Unit Two
1085 | H | P215000 | WA | Lewis Plant Common Core
1086 | H | P215000 | WA | Lewis Plant - Generation
1087 | H | P215000 | WA | Lewis Plant - Recreation
1088 | H | P215000 | WA | Lewis Plant - Lands
1089 | H | P133070 | OR | Rogue Plant Common Core
1090 | H | P133070 | OR | Rogue Generation Plant
1091 | H | P133070 | OR | Rogue Plant Recreation
1092 | H | P133070 | OR | Rogue Plant Lands
1093 | H | P019000 | OR | Umpqua Plant Common Core
1094 | H | P019000 | OR | Umpqua Generation Plant
1095 | H | P019000 | OR | Umpqua Plant Recreation
1096 | H | P019000 | OR | Umpqua Plant Lands
1097 | H | P651070 | CA | Klamath Plant Common Core
1098 | H | P651070 | CA | Klamath Generation Plant
1099 | H | P651070 | CA | Klamath Plant Recreation
1100 | H | P651070 | CA | Klamath Plant Lands
1101 | S | P000400 | CO | Craig Plant
1102 | S | P000410 | CO | Hayden Plant
1103 | S | P000240 | AZ | Cholla Plant
1104 | O | P129500 | OR | Hermiston Plant
1170 | H | P001034 | UT | East Hydro Plant Generation
1171 | H | P001034 | UT | East Hydro Plant Lands
1172 | H | P001034 | UT | East Hydro Plant Recreation
1173 | H | P136070 | OR | South Hydro Plant Common
1182 | S | P401000 | MT | Colstrip Plant
1183 | M | M517500 | WY | Bridger Coal Management & Administration
1184 | M | M202000 | WA | Centralia Coal Mangement & Admin
1185 | M | M515000 | WY | Glenrock Coal Management & Adminis.
1194 | H | P215000 | WA | Hydro North Small Plants
1196 | C | G000070 | OR | Net Power Cost
1197 | S | P000001 | UT | Generation Common
1198 | W | P576500 | WY | Foote Creek Plant
1199 | H | P215000 | WA | North Hydro Common
1202 | M | M000906 | UT | Interwest Mining
1203 | O | P220000 | WA | Camas Cogen
1204 | O | P000475 | UT | Little Mt. Thermal Plant
1205 | S | P000381 | UT | Blundell Thermal Plant Common
1208 | M | M000902 | UT | Deer Creek Mine
1209 | M | M000907 | UT | Preparation Plant Mine
1239 | M | M000904 | UT | Trail Mt. Mine
1240 | S | P000262 | UT | GADSBY PLNT UNIT #2
1241 | S | P000263 | UT | Gadsby Plant Unit #3
1264 | M | M009031 | UT | Energy West Mines Administration
1267 | M | M517500 | WY | Pacific Minerals Management & Administ
1268 | M | M000906 | UT | Fuel Resources
1269 | S | P000001 | UT | Generation Implementation
1270 | S | P000001 | UT | Generation Safety
1271 | S | P000001 | UT | Resource Development & Management
1272 | S | P514000 | WY | Dave Johnston & Wyodak Admin
1273 | S | G000300 | UT | Hunter & Huntington Administration
1300 | S | P517000 | WY | Jim Bridger Plant Common JVA
1301 | S | P517001 | WY | Jim Bridger Plant Unit 1 JVA
1302 | S | P517002 | WY | Jim Bridger Plant Unit 2 JVA
1303 | S | P517003 | WY | Jim Bridger Plant Unit 3 JVA
1304 | S | P517004 | WY | Jim Bridger Plant Unit 4 JVA
1305 | S | P000300 | UT | Hunter Plant Common Core JVA
1306 | S | P000301 | UT | Hunter Plant Unit 1 JVA
1307 | S | P000302 | UT | Hunter Plant Unit 2 JVA
1308 | S | P000303 | UT | Hunter Plant Unit 3 JVA
1309 | S | P519000 | WY | Wyodak Plant Common Core JVA
1310 | S | P519000 | WY | Wyodak Plant Unit 1 JVA
1311 | I | P201000 | WA | Centralia Plant Common JVA
1312 | I | P201001 | WA | Centralia Plant Unit 1 JVA
1313 | I | P201002 | WA | Centralia Plant Unit 2 JVA
1314 | H | P262000 | WA | Swift 2 Hydro JVA
1317 | S | P000300 | UT | Cattle Operation
1318 | S | P000001 | UT | Generation Project Management
1319 | H | P000001 | OR | Hydro Generation Support
1320 | S | G122092 | UT | Environmental Services
1330 | O | P000264 | UT | Gadsby Peaker Common
1331 | H | P000001 | OR | Hydro Compliance
1332 | C | P000001 | OR | C&T Mid-Office
1333 | M | M517000 | UT | Fuel Resources - Jim Bridger Coal
1334 | M | M517000 | UT | Fuel Resources Jim Bridger Coal - JVA
1335 | S | P000303 | UT | Hunter Plant Unit Four
1343 | M | M000906 | UT | Fuel Resources less Jim Bridger Coal
1358 | O | G000109 | UT | West Valley Common
1367 | O | G000328 | UT | West Valley Unit 1
1368 | O | G000328 | UT | West Valley Unit 2
1369 | O | G000328 | UT | West Valley Unit 3
1370 | O | G000328 | UT | West Valley Unit 4
1371 | O | G000328 | UT | West Valley Unit 5
1417 | C | G000001 | OR | State Regulatory Operations - System All
1419 | O | P000310 | UT | Currant Creek Common
1420 | O | P000311 | UT | Currant Creek #1
1421 | O | P000312 | UT | Currant Creek #2
1430 | S | P000001 | UT | Generation Corp Adj
1434 | O | P000225 | UT | Lake Side Power Plant
1443 | O | P000313 | UT | Currant Creek Steam Turbine 1
1444 | O | P000226 | UT | Lake Side Unit 1
1445 | O | P000227 | UT | Lake Side Unit 2
1446 | O | P000228 | UT | Lake Side Steam Turbine 1
1448 | O | G000314 | UT | Currant Creek Block 1 Common
1470 | O | G000225 | UT | Lake Side Block 1 Common
1516 | C | P000001 | OR | Energy Controller
1517 | C | P000001 | OR | C&T Planning
1518 | O | P000265 | UT | Gadsby Plant Unit #4
1519 | O | P000266 | UT | Gadsby Plant Unit #5
1520 | O | P000267 | UT | Gadsby Plant Unit #6
1680 | W | P000001 | UT | Wind Plants Administration
1681 | W | P505100 | UT | Glenrock Wind Common
1682 | W | P505110 | UT | Glenrock Wind Unit 1
1684 | W | P505130 | UT | Glenrock Wind Unit 3
1685 | W | P206110 | UT | Marengo Wind Unit 1
1686 | W | P206120 | UT | Marengo Wind Unit 2
1687 | W | P506100 | WY | Seven Mile Hill Wind Common
1688 | W | P506110 | WY | Seven Mile Hill Wind Unit 1
1689 | W | P505120 | ID | Rolling Hills Wind Plant
1690 | W | P505210 | ID | Rolling Hills Wind Unit 1
1691 | S | P000383 | UT | Blundell Unit 3
1692 | S | P000384 | UT | Blundell Thermal Plant Common Units 1&2
1693 | S | P519005 | UT | Wyodak Plant Coal Equipment
1694 | S | P000305 | UT | Hunter Plant Common Units 1 & 2 Only
1699 | S | P000001 | UT | VP Generation Support
1711 | S | P000385 | UT | Blundell Steam Field
1731 | S | G000001 | UT | PacifiCorp Energy Legal
1732 | W | G000001 | UT | Renewable Energy Development
1733 | S | G000001 | UT | Energy Executive
1735 | S | G000001 | UT | Asset Management
1736 | S | G000001 | UT | Generation Finance
1737 | C | G000001 | OR | C&T Front Office
1742 | C | G000001 | UT | C&T FAS 133 Accounts
1750 | S | G000001 | UT | Ops Support Vice President
1751 | S | G000001 | UT | Generation Engineering\Performance
1752 | S | G000001 | UT | Generation SAP Support
1754 | S | P000381 | UT | Blundell Unit 1
1755 | S | P000382 | UT | Blundell Unit 2
1756 | W | P129600 | UT | Leaning Juniper Wind Plant
1757 | M | M000906 | UT | Mining Controller
1758 | W | P206100 | WA | Marengo Wind Common
1759 | W | P205100 | WA | Goodnoe Hills Common Wind Plant
1760 | W | P205200 | WA | Goodnoe Hills Wind Plant Unit 1
1761 | W | P205300 | WA | Goodnoe Hills Wind Plant Unit 2
1763 | S | P000381 | UT | Steam Reserve Corp
1764 | S | P000296 | UT | Veyo REG Plant
1765 | O | P000292 | UT | REG Plant Common
1766 | O | P526103 | WY | Coyote Creek REG Plant
1767 | O | P000294 | UT | Elberta REG Plant
1768 | O | P000295 | UT | Fillmore REG Plant
1769 | O | P526101 | WY | Muddy Creek REG Plant
1770 | O | P526102 | WY | Painter REG Plant
1771 | O | P000293 | UT | Salt Lake REG Plant
1792 | W | P509100 | UT | Dunlap Wind Common
1793 | W | P509110 | UT | Dunlap Wind Plant Unit 1
1794 | W | P509120 | UT | Dunlap Wind Plant Unit 2
1795 | W | P510100 | UT | High Plains & McFadden Ridge Wind Common
1796 | W | P510110 | UT | High Plains Wind Plant
1797 | W | P510120 | UT | McFadden Ridge Wind Plant
1798 | W | P506120 | UT | Seven Hile Hill Wind Unit 2
1817 | C | P000001 | OR | PacifiCorp Energy Strategy
1819 | O | P203300 | UT | Chehalis Plant Common & Substation
1820 | O | P203301 | UT | Chehalis Combustion Turbine A
1821 | O | P203302 | UT | Chehalis Combustion Turbine B
1822 | O | P203303 | UT | Chehalis Steam Turbine
1823 | W | P507100 | WY | Wild Horse Wind Common
1824 | W | P507110 | WY | Wild Horse Wind Unit 1
1825 | W | P507120 | WY | Wild Horse Wind Unit 2
1826 | W | P508100 | WY | Twelve Mile Ranch Wind Common
1827 | W | P508110 | WY | Twelve Mile Ranch Wind Unit 1
1828 | W | P508120 | WY | Twelve Mile Ranch Wind Unit 2
1829 | C | P000001 | OR | Wyoming Ranch Management
1899 | M | M000001 | WY | PMI/BCC Eliminations
9001 | S | P000001 | UT | Generation B/S
Insert additional data above this line
Updated 12/08/2008
Tom Evans