## telco
Average Percent Complete
Overall Long Distance |  | Year 2000 Program Phase |  | 1999-03-31 | 1999-12-31
|  | Inventory |  | 88.89% | 89%
|  | Assessment |  | 88.89% | 89%
|  | Remediation/Testing |  | 62.13% | 62%
Industry Summary |  | Inventory | Assessment | Remediation/ Testing | Estimated Completion
| AT&T | 99.67% | 99.67% | 94.5% | 1998-12-31
| MCI | 67% | 67% | 34% | 1999-06-30
| Sprint | 100% | 100% | 57.89% | 1999-06-30
| Overall | 88.89% | 88.89% | 62.13% | 1999-06-30
| 1998-12-31 | 89% | 89% | 62%
Company Reports | Inventory | Assessment | Remediation/ Testing | Assessment of Probability of failure & risk | Preparation of contingency plan | Estimated Completion
AT&T | [5 empty] | 1999-06-30 | Non-Critical
Network Elements | 100% | 100% | 100% | Not reported | Not reported | 1998-12-31 | Critical
Support Systems | 100% | 100% | 100% | Not reported | Not reported | 1998-12-31 | Critical
Auxiliary Systems | 99% | 99% | 83.5% | Not reported | Not reported | 1998-12-31 | Critical
1999-06-30
Overall | 99.67% | 99.67% | 94.5% |  |  | 1998-12-31 | Critical
1998-12-31 | 100% | 100% | 100% |  |  | 1998-12-31 | Critical
MCI
Network Elements | 67% | 67% | 34% | Not reported | Not reported | 1999-03-31 | Critical
Support Systems | 67% | 67% | 34% | Not reported | Not reported | 1999-03-31 | Critical
Auxiliary Systems | 67% | 67% | 34% | Not reported | Not reported | 1999-03-31 | Critical
Overall | 67% | 67% | 34% |  |  | 1999-06-30
1998-12-31 | 67% | 67% | 34%
Sprint
Network Elements | 100% | 100% | 83% | N/A | N/A | 1999-06-30
Support Systems | 100% | 100% | 65.67% | N/A | N/A | 1999-06-30
Auxiliary Systems | 100% | 100% | 25% | N/A | N/A | 1999-06-30
Overall | 100% | 100% | 57.89% | N/A | N/A | 1999-06-30
1998-12-31 | 100% | 100% | 52% |  |  | 1999-06-30
N/A = Not Available
Average Percent Complete
Overall Local | Year 2000 Program Phase |  | 1999-03-31 | 1998-12-31
| Inventory |  | 100% | 100%
| Assessment |  | 95.24% | 99%
| Remediation/Testing |  | 65.79% | 70%
Weighted Company Summary
| Inventory | Assessment | Remediation/ Testing | Estimated Completion
US West | 100% | 100% | 86.78% | 1999-09-30 | Critical
GTE | 100% | 100% | 86.33% | 1999-06-30
Wahkiakum West | 100% | 66.67% | 65.56% | 1999-11-30
TDS Telecom | 100% | 100% | 74.44% | 1999-10-30
Toledo Telephone Co. | 100% | 100% | 17.44% | 1999-09-30
Sprint | 100% | 100% | 62.5% | 1999-06-30
CenturyTel | 100% | 100% | 67.5% | 1999-09-30
Overall | 100% | 95.24% | 65.79%
1999-12-31 | 100% | 99% | 70%
Overall Weighted completion | 100% | 99.47% | 84.23%
Large Company Weighted Summary
92 percent of lines | Inventory | Assessment | Remediation/ Testing | Estimated Completion
US West | 100% | 100% | 86.78% | 1999-09-30 | Critical
GTE | 100% | 100% | 86.33% | 1999-06-30
Overall | 100% | 100% | 86.56%
1998-12-31 | 100% | 100% | 82%
Weighted completion | 92% | 92% | 79.63%
Smaller Company Weighted Summary
8 percent of lines | Inventory | Assessment | Remediation/ Testing | Estimated Completion
Wahkiakum West | 100% | 66.67% | 65.56% | 1999-11-30
TDS Telecom | 100% | 100% | 74.44% | 1999-10-30
Toledo Telephone | 100% | 100% | 17.44% | 1999-09-30
Sprint | 100% | 100% | 62.5% | 1999-06-30
CenturyTel | 100% | 100% | 67.5% | 1999-09-30
Overall | 100% | 93.33% | 57.49% | 1999-11-30
1998-12-31 | 100% | 98% | 63%
Weighted completion | 8% | 7.467% | 4.599%
Company Reports
| Inventory | Assessment | Remediation/ Testing | Assessment of Probability of failure & risk | Preparation of contingency plan | Estimated Completion
US West
Network Elements | 100% | 100% | 96% | Not reported | Not reported | 1999-07-31
Support Systems | 100% | 100% | 94.33% | Not reported | Not reported | 1999-07-31
Auxiliary Systems | 100% | 100% | 70% | Not reported | Not reported | 1999-08-31
Overall | 100% | 100% | 86.78% |  |  | 1999-09-30
1998-12-31 | 100% | 100% | 66% |  |  | 1999-09-30
GTE
Network Elements | 100% | 100% | 95% | 95% | 5% | 1999-06-30 | Critical
Support Systems | 100% | 100% | 98% | N/A | N/A | 1999-06-30
Auxiliary Systems | 100% | 100% | 66% | N/A | N/A | 1999-06-30
Overall | 100% | 100% | 86.33% |  |  | 1999-06-30
1998-12-31 | 100% | 100% | 99% |  |  | 1999-06-30
Wahkiakum West
Network Elements | 100% | 65% | 65% | Not Reported | Not Reported | 1999-11-30
Support Systems | 100% | 65% | 65% | Not Reported | Not Reported | 1999-11-30
Auxiliary Systems | 100% | 70% | 66.67% | Not Reported | Not Reported | 1999-11-30
Overall | 100% | 66.67% | 65.56% |  |  | 1999-11-30
1998-12-31 | N/A | N/A | N/A |  |  | 1999-11-30
TDS Telecom
Network Elements | 100% | 100% | 66.67% | Not Reported | Not Reported | 1999-10-30
Support Systems | 100% | 100% | 86.67% | Not Reported | Not Reported | 1999-09-30
Auxiliary Systems | 100% | 100% | 70% | Not Reported | Not Reported | 1999-09-30
Overall | 100% | 100% | 74.44% |  |  | 1999-10-30
1998-12-31 | 91.67% | 80% | 66.67% |  |  | 1999-10-30
Toledo Telephone
Network Elements | 100% | 100% | 28% | 5% | 5% | 1999-09-30
Support Systems | 100% | 100% | 24.33% | 5% | 5% | 1999-09-30
Auxiliary Systems | 100% | 100% | 0% | 5% | 5% | 1999-09-30
Overall | 100% | 100% | 17.44% | 5% | 5% | 1999-09-30
1998-12-31 | N/A | N/A | N/A |  |  | 1999-09-30
Sprint
Network Elements | 100% | 100% | 96.67% | N/A | N/A | 1999-03-31
Support Systems | 100% | 100% | 100% | N/A | N/A
Auxiliary Systems | 100% | 100% | 25% | N/A | N/A | 1999-06-30
Overall | 100% | 100% | 62.5% | N/A | N/A | 1999-06-30
1998-12-31 | 100% | 100% | 81% |  |  | 1999-03-31
CenturyTel
Network Elements | 100% | 100% | 93.67% | Not Reported | Not Reported | 1999-09-30
Support Systems | 100% | 100% | 70.67% | Not Reported | Not Reported | 1999-09-30
Auxiliary Systems | 100% | 100% | 64.33% | Not Reported | Not Reported | 1999-09-30
Overall | 100% | 100% | 67.5% | Not Reported | Not Reported | 1999-09-30
1998-12-31 | 100% | 100% | 81% |  |  | 1999-09-30
Formulas:
Estimated Completion = +[Estimated Completion, row above]