## 500 kV Line (DO NOT USE)
| CPCN/Project Name: | 1. Aeolus-to-Bridger/Anticline Line
| REQUIRED PERMIT LIST | (140 mi, 500 kV transmission line; new Aeolus and Anticline substations; 5 mi, 345 kV transmission line; voltage control device at Latham substation)
2. TB Flats I and II Network Upgrades
(Shirley Basin substation modifications; new 16 mi Shirley Basin-Aeolus 230 kV line)
3. Cedar Springs Network Upgrades
(Windstar substation modifications; Freezeout substation modifications; rebuild 15 mi Aeolus-Freezeout-Standpipe 230 kV line; rebuild 16 mi Shirley Basin-Aeolus 230 kV line)
4. Ekola Flats Network Upgrades
(only requires modification of the new Aeolus substation already covered under number 1 above)
| Agency | Required Permit, Approval, or Consultation | Agency Action | Date Obtained
1 | Advisory Council on Historic Preservation | Section 106 Consultation, National Historic Preservation Act | Has the opportunity to comment if the Project may affect cultural resources that are either listed on or eligible for listing on the National Register of Historic Places (NRHP).
2 | U.S. Department of Defense, Army Corps of Engineers, Omaha District, Walla Walla District | Section 404, Clean Water Act Permit | Consider issuance of a Section 404 permit for the placement of dredge or fill material into all waters of the United States, including jurisdictional wetlands.
3 | U.S. Department of the Interior, Bureau of Land Management (BLM) | Antiquities and Cultural Resource Use Permit | Has the opportunity to issue permits for use in complying with Section 106 NHPA Act.
|  | Various Resource Management Plans | Item completed as part of the NEPA process and ROD issuance.
|  | Right-of-Way (ROW) Grant | ROW Granted received November 2013.
|  | Plan of Development (POD) | Consider approval of detailed POD.
|  | Notice to Proceed | Following issuance of a ROW grant and approval of a POD, consider issuance of a Notice to Proceed with Project development and mitigation activities.
4 | U.S. Department of Transportation, Federal Highway Administration | Encroachment Permit | Consider issuance of permit for transmission line crossing of federally funded highways (typically delegated to the state department of transportation).
5 | U.S. Environmental Protection Agency, Regions 8 and 10 | Section 402, CWA, National Pollutant Discharge Elimination System (NPDES) General Permit for Stormwater Discharges Associated with Construction Activity for Idaho | Review and issue NPDES permit for discharge of Stormwater in Idaho. In Wyoming, NPDES permitting is delegated to the Wyoming Department of Environmental Quality (see below).
|  | Section 404, Clean Water Act Permit | Review CWA, Section 404 applications for dredge-and-fill applications for the USACE with 404(c) veto power for permits issued by the USACE.
6 | All WY state agencies | Compliance with Executive Order (EO) 2011-5 | Requires that all agencies demonstrate that activity proposed for permitting be compliant with the requirements of the EO in sage- grouse core areas.
7 | WY Department of Environmental Quality (WDEQ) and the WY Industrial Siting Council | Industrial Siting Permit Wyoming Industrial Information and Siting Act under Chapters 1 and 2, Rules and Regulations of the Industrial Siting Council | Considers approval of construction and siting of projects with construction cost of $176 million or more or 160 kV or greater.
8 | WDEQ Air Quality Division | Construction permit | Consider measures to control fugitive dust emissions during construction.
9 | WDEQ Water Quality Division | Section 401, CWA, Water Quality Certification | Consider certification of a 404 permit issued by the USACE as consistent with state law and Section 401.
|  | Section 402, CWA, NPDES General Permit for Stormwater Discharges Associated with Construction Activity for Wyoming | Review and issue NPDES permit for discharge of stormwater.
10 | WY Game and Fish Department | Potential Project Impacts to Fish and Wildlife Species and Their Habitat | Coordinate with BLM, Forest Service, and USFWS on wildlife issues/impacts associated with the Project.
11 | WY State Historic Preservation Office | Section 106 Consultation, NHPA | Consult with the BLM, the Proponents, other land management agencies, and others regarding activities potentially affecting cultural resources.
12 | WY Office of State Lands and Investments | Easement Across State Lands | Consider issuance of a ROW across state lands.
13 | WY Public Service Commission | Certificate of Public Convenience and Necessity | Consider issuance of a certificate to allow construction of a public utility, including transmission lines.
14 | WY Department of Transportation | Encroachment Permit | Consider issuance of permit to cross or bore under state highways or be within a state highway ROW.
15 | Various (may also require federal and county approvals) | Explosives Permit | Consider issuance of a license to store and use explosives.
16 | Carbon County | Conditional Use Permit
17 | Sweetwater County | Conditional Use Permit

## Cedar Springs II
CPCN/Project Name: | Cedar Springs ("CS") I and II Projects
(Cedar Springs I is a nominal 200 MW portion of a nominal 400 MW wind facility and associated infrastructure)
(Cedar Springs II is a nominal 200 MW portion of a Nominal 400 MW wind facility and associated infrastructure)
Agency | Required Permit | Date Obtained
Federal Aviation Administration | Notice of Proposed Construction or Alteration | In FAA review; results expected in August 2019
Department of Commerce National Telecommunication Information Agency | Impacts to Telecommunication Systems and Radar | Will be completed by NextEra
U.S. Environmental Protection Agency (EPA) | Spill Prevention Controls and Countermeasure Plan (SPCC) | Will be completed by NextEra
Federal Communication Commission | Licensed Microwave Study | Will be completed by NextEra
WY Department of Environmental Quality | Wyoming Industrial Development Information and Siting Act /Industrial Siting Council Order | 2019-06-28
WY Department of Environmental Quality | Wyoming Pollutant Discharge Elimination System (WYPDES) ‐ Large Construction General Permit (WYR10‐000) ‐ Notice of Intent (NOI) and Storm Water Pollution and Prevention Plan (SWPPP) | Will be completed by NextEra; preparing SWPPP for submittal by August 2, 2019 - Westwood
WY Department of Environmental Quality | Permit to Construct Small Wastewater Facilities (Septic Tanks and Leach fields) | Will be completed by NextEra
WY Department of Environmental Quality | Section 401 Water Quality Certification | Will be completed by NextEra
WY Department of Environmental Quality | Temporary Increase in Turbidity | Will be completed by NextEra
WY State Engineers Office | Permit to appropriate groundwater (use, storage, wells, dewatering) or water stored in impoundments or reservoirs W.S. 41 3‐901 through 41‐3‐938, as amended (Form U.W. 5) | Will be completed by NextEra
WY Department of Transportation | Port of Entry | Will be completed by NextEra
WY Department of Transportation | Right‐of‐way encroachment | Will be completed by NextEra
WY Department of Transportation | Permit for Oversized / Overweight Loads | Will be completed by NextEra
WY Department of Transportation | Highway Access Permit | Will be completed by NextEra
WY Department of Transportation | Utility/Transmission Line Crossing | Will be completed by NextEra
WY State Historic Preservation Office | Section 106 of Natl Historic Preservation Act of 1966 as amended (16 U.S.C. 470 et seq) and Advisory Council Regulations on the Protection of Historic and Cultural Properties as amended (36 CFR 800) | Will be completed by NextEra
WY Game and Fish Department | WGFD Conservation Plan | Will be completed in August 2019
WY Department of Transportation | Road Use Permit | Road use agreement for transmission tie-line and substation construction will be completed in August 2019; road use agreement for wind park construction will be completed in September 2019
Converse County | Wind Energy Conversion System Use Permit (may be waived in lieu of ISA application and permit) | 2019-04-30
Converse County | Building permit(s) | Not required
Converse County | Road Use Permit | Will be completed in August 2019