## PC 109
Rocky Mountain Power
Washington GRC - PC 109
PacifiCorp Energy Submittal
Major Plant Addition Detail - Jan14 to Mar16
[11 empty] | 54-a. | 54-b. | 54-b. | 54-c. | 54-c.
Function | Plant | WBS | NEW WBS | Project | Factor | BU | In-Service | Total in filing | Forecasted PIS (1) | In-service | Actual In-Service Date | Actual PIS thru Aug-14 | % change | Add'l PIS | Why costs are not yet included | Est. In-service
HYDP | HYDRO | HLEW/2006/C/010/018 | HLEW/2006/C/010/018 | ILR 4.3 Merwin Upstream Collect & Trans | CAGW | PE | 2014-03-28 | 49333266.08 | 49467669 | Yes | Mar-14 | 48944628.07 | -0.7878% | 523040.93 | Final monitoring costs
STMP | JB | SJIM/2014/C/023 | SJIM/2014/C/023 | U1 Replace Cooling Tower 13/14 | JBG | PE | 2014-05-22 | 5889967 | 5526616 | Yes | May-14 | 5453020.66 | -7.418% | 73595.34 | Project close-out costs
HYDP | HYDRO | HLEW/2013/C/021 | HLEW/2013/C/021 | Swift Side Nets Replacement | CAGW | PE | 2014-03-31 | 3458441 | 2156065 | Yes | Mar-14 | 2156064.61 | -37.66% | 0.39
HYDP | HYDRO | HLEW/2014/C/002 | HLEW/2014/C/002 | Swift 11 Generator Rewind | CAGW | PE | 2014-09-15 | 3450962.31 | 3436880 | No | [5 empty] | Oct-14
TRNP | JB | SJIM/2012/C/071 | SJIM/2012/C/071 | U2 GSU Transformer Upgrade Replacement | JBG | PE | 2014-08-01 | 3359988.65 | 3263130 | No | [5 empty] | Sep-14
HYDP | HYDRO | HNUQ/2012/C/017 | HNUQ/2012/C/017 | Soda Springs Screen Upgrade | CAGW | PE | 2014-01-31 | 3030065.61 | 3100387 | Yes | Jan-14 | 3100387.49 | 2.321% | -0.49
HYDP | HYDRO | HLEW/2013/C/019 | HLEW/2013/C/019 | Yale Upper Rock Block Stabilization | CAGW | PE | 2014-10-31 | 2726219 | 6120506 | No | [5 empty] | Feb-15
HYDP | HYDRO | HLEW/2014/C/006 | HLEW/2014/C/006 | Swift Main Net Modifications | CAGW | PE | 2014-10-31 | 2655774 | 2602878 | No | [5 empty] | Oct-14
STMP | JB | SJIM/2014/C/001 | SJIM/2014/C/001 | U1 Pendant Plat Lower Replacement 14 | JBG | PE | 2014-05-31 | 2448968.17 | 2334290 | Yes | May-14 | 2334289.88 | -4.683% | 0.12
HYDP | HYDRO | HLEW/2012/C/010/004 | HLEW/2012/C/010/004 | ILR 6.2 Merwin Flow Controls | CAGW | PE | 2014-10-31 | 2296706 | 2525303 | No | [5 empty] | Oct-15
HYDP | HYDRO | HLEW/2008/C/010/001A | HLEW/2008/C/010/001A | ILR 8.7 Speelyai Hatchery Water Intake | CAGW | PE | 2014-10-17 | 2002024 | 2463112 | No | [5 empty] | Nov-15
HYDP | HYDRO | HLEW/2013/C/020 | HLEW/2013/C/020 | Swift 1 Spare Generator Windings | CAGW | PE | 2014-07-15 | 1632114.15 | 1614209 | Yes | Jun-14 | 1614208.77 | -1.097% | 0.23
STMP | JB | SJIM/2014/C/015 | SJIM/2014/C/015 | U1 Burners - Major 14 | JBG | PE | 2014-05-31 | 1438405 | 1327783 | Yes | May-14 | 1327783.27 | -7.691% | -0.27
HYDP | HYDRO | 10013945 | HNUQ/2014/C/008/002 | INU 10.6 Aquatic Connectivity 14 | CAGW | PE | 2014-11-24 | 1333292 | 946697 | No | [5 empty] | Nov-14
STMP | JB | SJIM/2010/C/024 | SJIM/2010/C/024 | New Sewage Treatment Plant or Lagoon | JBG | PE | 2014-05-31 | 1315211 | 1341288 | Yes | Jun-14 | 1309963.82 | -0.399% | 31324.18 | Project close-out costs
HYDP | HYDRO | HLEW/2013/C/014 | HLEW/2013/C/014 | Merwin 3 TIV Overhaul | CAGW | PE | 2014-09-02 | 1242975.41 | 1198444 | No | [5 empty] | Nov-14
HYDP | HYDRO | HLEW/2013/C/015 | HLEW/2013/C/015 | Merwin 1 TIV Overhaul | CAGW | PE | 2014-08-05 | 1241748.24 | 1190137 | No | [5 empty] | Oct-14
STMP | COLSTRIP |  | SCOL/2009/C/019 SCOL/2013/C/049 SCOL/2013/C/060 | Colstrip 4: Generator Repair CY13/CY14 | CAGW | PE | 2014-02-28 | 250000 | 1145617 | Yes | (2) | 1145617
Grand Total | [7 empty] | 89106127.62
(1) Based on Sep14 PIS forecast (EPIS Jan-14 to Dec-15)
(2) $3,146k in-service for this project (2013 - 2014). $2,000k booked for insurance payment received in Oct-13 and $600k in Jul-14. Credits booked to accumulated depreciation reserve.