## Sheet1
PacifiCorp
Washington General Rate Case - December 2013
|  | Major Plant Additions | [5 empty] | Submitted in mid July 2014 |  |  |  |  | Updated for end of August
[8 empty] | If completed |  |  |  |  | If completed
BU | Project Definition | Project Description | Function | Account | Factor | In-Service Date | Jan 14 - Dec 14 Plant Additions | PC-54a - Actual In-Service Date | PC-54b - Total dollars placed in-service | PC-54b - If more than 5% different, explain. | PC-54c - Additional amounts to be placed into service. | PC-54c - explanation | PC-54a - Actual In-Service Date | PC-54b - Total dollars placed in-service | PC-54b - If more than 5% different, explain. | PC-54c - Additional amounts to be placed into service. | PC-54c - explanation | PC-109d Updated ADIT at 3/31/2015
PP | TZAL/2013/C/002 | Alvey Series Cap Controls - Payment to BPA | TRNP | 355 | CAGW | 2014-02-28 | 1184713 | 2014-02-14 | 929407.5 | The initial payment amount was based on BPA's estimate of Pacific Power's costs prior to starting construction. Once construction was completed BPA notified us that total costs were less than estimated. |  |  | 2014-02-14 | 927300 | n/a | 0 | n/a | -19549
TMP | TZAL/2013/C/001 | Fry Sub Instl 115 kV Capacitor Bank TPL2 | TRNP | 355 | CAGW | 2014-12-19 | 6381000 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
PP | DZPO/2011/C/002 | Knott Sub Install 115-12.5 kV Transformer - Trans | TRNP | 355 | CAGW | 2014-10-01 | 3400000 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
PP | DZME/2009/C/005 | Line 3 Convert to 115kV - Phase 1and 2 | TRNP | 355 | CAGW | 2014-10-14 | 2835842.95 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
RMP | TCED/2009/C/001 | Middleton-Toquerville: 69 kV Line Rebuild 2.2 Miles | TRNP | 355 | CAGW | 2014-02-28 | 3737294.04 | 2014-02-14 | 2451004.83 | Favorable material of $200k, favorable labor (including contract labor) of $400k, favorable rights-of-way and permitting costs of $300k, and reduced overheads of $350k due to lower overall project costs and early project completion. | 500 | Final close-out activity | 2014-02-14 | 2451259.46 | No change | 0 | n/a | -49844
PP | TZKL/2012/C/002 | Purchase spare 230-69 kV 150 MVA Transformer (Klamath) | TRNP | 355 | CAGW | 2014-11-01 | 2000000 |  | 0 | n/a |  |  | n/a | n/a | n/a | n/a | n/a | n/a
Corp |  | Call Center ACD Replacement Project | GNLP | 397 | SO | 2014-03-31 | 4414551 | n/a | n/a | n/a | n/a | n/a | 2014-07-28 | 4515941 | n/a | 142000 | Project close out adjustments | -116697
PP | DORE/2011/C/002 | Replace 6GHz MW radios Starvout to Fort Rock phase 2 | GNLP | 397 | CAGW | 2014-12-31 | 1418280.81 | n/a | n/a | n/a | n/a | n/a | Note (1) | 825464.67 | This project is not complete; it is partially placed in service. The plant in-service through August was $825,465 | 440065 | The additional amount of $440,065 will be in-service September 2014. | n/a
PP | DZYA/2013/C/002 | Orchard and Wiiley Substation Capacity Relief (Clinton Feeder) | DSTP | 360 | WA | 2014-04-30 | 880000 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
PP | DZYA/2013/C/003 | Replace Spare 116-13.0kV 25 MVA w/ LTC - Yakima | DSTP | 360 | WA | 2014-10-01 | 655000 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
PP | DZYA/2012/C/002 | Selah Substation Capacity Relief (25 MVA at Pomona Heights) | DSTP | 360 | WA | 2014-12-31 | 4547967 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
TMP | TWAS/2010/C/001 | Union Gap - Add 230 - 115kV Capacity - TPL002 | DSTP | 360 | WA | 2014-08-01 | 8650000 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
(1): As of August 31, 2014, this project is partially placed in service.