## Slide 1: Smart Grid Investment Grant Update
September 23, 2011 Washington Utilities and Transportation Commission Update – Josh DiLuciano
Smart Circuit Project – Spokane, WA

## Slide 2: Overview
Substation Construction
9of 14 Substations Complete
Distribution Construction
Smart Switches & Capacitors being Installed
Reporting
Project Performance
Build Metrics
Impact Metrics
6 Stations 100% Complete with Overhead Construction
2
Notes: To date we have completed 24 miles of reconductor with 6.5 left. (Numbers are rough as I have not updated from completions last week.)
We have installed 219 devices with 159 left to install.
33 Vipers installed with 54 left to install
124 ScadaMates installed with 46 left to install
62 Switched banks installed with 59 left to install
4 stations are 100% complete with OH construction. North East, Lyons and Standard, Francis and Cedar, and Fort Wright.

## Slide 3: Distribution Construction
Chart: 
| Reconductor (miles) | Switches | Capacitors
Installed | 27 | 212 | 106
To Install | 2 | 45 | 15
3
Notes: 4 stations are 100% complete with OH construction. North East, Lyons and Standard, Francis and Cedar, and Fort Wright.
-initially planned on installing 59 vipers and scadamates on the rest, but decided to install 87 vipers and reduce scadamates because we learned they were less expensive to install and provided more functionality

## Slide 4
Project Performance
4
Cost Performance Index (CPI) 1.09
Schedule Performance Index (SPI): 0.94

## Slide 5: Smart Grid Update
September 23, 2011 Washington Utilities and Transportation Commission Update – Dan Johnson
Smart Grid Demonstration Project – Pullman, WA
5

## Slide 6: Smart Grid Demonstration Project Overview
Communications
Radio Network Complete
Port of Whitman Fiber Construction underway
Distribution Management System
Integration into Outage Management Tool
Substation Construction
Smart Switches & Capacitors installed
Smart Transformer Prototypes being tested
1.6Mile Reconductor Complete
Advanced Metering System
Meter Installation 100% Complete
Distribution Construction
Turner Substation construction on schedule
6

## Slide 7
Project Performance
7
Cost Performance Index (CPI) 1.14
Schedule Performance Index (SPI): 0.84

## Slide 8
Advanced Metering System
Energy Management Web Tools
Customer Pilot
The Customer Experience
8

## Slide 9
Advanced Metering System
  Scope Services provided the contract installation
  Albion/Pullman installation complete of 12,692 Electric and 5,264 Gas
  Communication reading meters is 99.5%
Smart Grid Demonstration –
Meter Installation
9

## Slide 10: Energy Management Web Tool
10

## Slide 11: Customer Experience Design
Chart: 
| Control Group | Treatment Group w/o My Account | Treatment Group w/My Account
Customer Experiment Hypothesis | 6500 | 1950 | 4550
 | Measure Change in Consumption | Measure Change in Satisfaction & Usefulness
24-48 Hour Delayed Data | X | X
Real Time Info |  | X
11

## Slide 12
The Customer Experience
Customer Pilot
    Improve energy consumption data
    Establish and test regional signals
    Understand customer experience, satisfaction, and program participation
    Target of 1,500 customers in Pullman
    Testing, Understanding, Learning
12

## Slide 13
Web Portal + Real Time Consumption using a Programmable Communicating Thermostat
Secure VPN
Encryption
13

## Slide 14: Customer Communications Update
September 23, 2011 Washington Utilities and Transportation Commission Update
Smart Grid Demonstration Project – Pullman, WA
Smart Circuit Project – Spokane, WA
14

## Slide 15: Communications Objectives
  Educate customers about the project and expected benefits
  Educate customers about activities that directly impact them such as replacing existing meters with new advanced meters
  Provide resources for customers to address their questions and concerns
  Educate and empower customers to more actively manage their energy usage with enhanced technology and tools
15

## Slide 16: Customer Advisory Group
Assembled customer advisory group
Currently consists of three Avista residential customers in Pullman
Group provides input and feedback on communication materials
16

## Slide 17: Community Meetings
Conducted a variety of community meetings and presentations which resulted in local news coverage, another channel to help educate and inform customers about the Demonstration Project
17

## Slide 18: Survey
Issued post-advanced meter installation survey to assess awareness of meter exchange communication and level of satisfaction with advanced meter installation process
18

## Slide 19: Post Meter Installation Survey Findings
282 total responses, resulting in a 6% response rate
Recall of communication prior to meter installation is high:
  Seventy-one percent (71%) of the customers surveyed recall receiving a
  letter in the mail prior to the installation
  11% recall reading a news article
  5% recall hearing a presentation from Avista
  14% recall “other” forms of communication: door hanger, neighbor, installer,
  internet, WSU, Avista employees (friends)
Nearly three-quarters of the customers are
‘very satisfied’ with the installation process
19

## Slide 20: Case Studies
Developed case studies about advanced meter installation for use on the web, events and community meetings
20

## Slide 21: Advanced Meter Web Portal
Finalizing Web Portal Communications Plan
    Tactics likely to include:
      Letter to customers in the treatment group with an overview of the new portal features and benefits as well as instructions on how to access
      Online tutorial for how to access and use new energy usage portal
      Web portal FAQ
    Conducting baseline survey mid-October to measure awareness and attitudes toward current online energy saving tools
21

## Slide 22: Cyber Security Overview
22
September 23, 2011 Washington Utilities and Transportation Commission Update – Clay Storey
Smart Grid Demonstration Project – Pullman, WA
Smart Circuit Project – Spokane, WA

## Slide 23: Security Update - Goals
Goals
  Identify risk from new investments and capabilities
  Measure risk for impact and probability
  Manage risk to the organization and its customers
  Apply best practice controls per industry baselines
What Success Looks Like
  The NIST Security Lifecycle is operational
  Documented risk response and controls implementation
  Senior leadership understands and accepts the residual risk profile
23

## Slide 24
Physical Security
Cyber Security
Security Update - Strategy
Transmission and Distribution
Facilities
Enterprise Security
Generation and Production
Enterprise Technology
Smart Grid
24

## Slide 25: Security Update - Pullman
Categorize
Systems
Select
Controls
Implement
Controls
Assess
Controls
Authorize
Systems
Continuous Monitoring
25

## Slide 26: Security Update - Spokane
Categorize
Systems
Select
Controls
Implement
Controls
Assess
Controls
Authorize
Systems
Continuous Monitoring
26

## Slide 27: Questions………..
27