## PSE 50 Worst Circuit Projects
PSE TOP 50 WORST CIRCUITS PROJECTS
Circuit | 5 Year Rank | Projects | Comments
BRS-24 | 1 | 2005 - CRP; reviewing a tree wire project for circuit | Standards approval of 34 kV tree wire pending. This 34 kV circuit is remote and has no feeder ties.
CLA-13 | 2 | No future projects planned at this time | The circuit serves 7 customers at the top of Grass Mountain and the sub is fed from a radial 55 kV transmission tap
LON-22 | 3 | 1.2007 - CRP in Clearwood 2.2006 - Tree wire project on Bald Hill Rd 3.2007 -Split circuit 22 into two circuits 4.2009 -11 UG feeder replacement in Clearwood 5.2008-09 Reconductor 153rd Ave SE
LON-26 | 4 | 2007 - Lindsay Rd Reconductor w/tree wire; 80% of load was shifted to RAI-13
CHI-12 | 5 | Three major expenditure options proposed in the future to remediate reliability problems on this circuit. 1.) Install a new third feeder into the Seabeck-Holly area 2.) Build a new substation and transmission into the Seabeck-Holly area 3.) Underground a good portion of the Chico 34kV system | 1.) Currently budgeted for study and possible ROW acquisition beginning in fiscal year 2008, and this project alone is expected to save in the neighborhood of 2.5-5 SAIDI minutes
SIL-13 | 6 | Outages include car-pole, and tree outages and cable problems out to Coyle Road. Looking at a potential tree wire of feeder or underground proposal for 2009
GWR-16 | 7 | No future projects planned at this time | The substation is fed from a radial 55 kV transmission tap. the generator at Crystal Mountain provides some power to customers when the circuit and/or substation are out
HYA-13 | 8 | 2008 Project to replace aged and weathered equipment on HYA-13. Thousands of feet of UG feeder and 1/0 cable installed in the late 1960s and early 1970s will be replaced. Also, construct some 3ph 1/0 ties so padmounted switches can be taken out of service w/o loss of service to customers. | HYA-13 is located along Snoqualmie Pass an area that is typically exposed to high winds and heavy snowfall which prolongs outage response time and restoration.
ORT-22 | 9 | Reviewing the following options; (1) Orting Substation 4th breaker, dbl ckt (2) Sunrise - Orting distribution tie, and (3) New Thrift Substation
DUV-15 | 10 | 1. 2008 - DUV-15 2ACSR TW Odell Rd
2. Past projects - CRP at Lake Marcell & 112949 297the Pl SE
LON-23 | 11 | 2008 - Add second circuit to split into two circuits. | Part of 2008 County PI project.
DIS-13 | 12 | 2008 - Tree wire project between the existing recloser 1606 and solid blade switch 13-363. Overhead fault indicators and a fused bypass at switch 1641 (or 1611).
FAL-15 | 13 | 2006 - Project to relocate recloser to protect Lk Alice customers from faults on the line South of the Raging River bridge. Worked w/ Vegetation Mgmt to move circuit from 6 yr to 4 yr trim cycle. Trimmed in 2007 | Additional capacity and reliability improvements are planned for the transmission line. Reconductoring of line, improved access roads and vegetation management planned for 2008-09.
GRI-13 | 14 | 2008 - Reconductor 1 mile tree wire on Southshore Rd and convert 1 mile OH to UG on Summit Lk Rd.
PGA-13 | 15 | 2008 - Kingston substation | Kingston substation will take a lot of customers off this circuit and additional swtches will aid sectionalizing capability.
BLU-17 | 16 | 2007 -Shifted 50% of load to BLU-16 and added a recloser to BLU-16.
FLD-12 | 17 | Many previous projects include TW and recloser installations; FLD-12 to BRO-16 feeder tie (future)
HAM-13 | 18 | 2008 - UG conversion on South Skagit Hwy (2008). HAM-13 to NLM-13 feeder tie (future)
SKY-25 | 19 | 1. 2008 - Replace fuses with solid blades to aid fuse coordination.
2. 2009 - Investigate TW or UG project for Old Cascade Hwy
DUV-12 | 20 | 1. 2007 - 2607E040 DUV-12 Add 3rd phase Lake Margaret
2. 2007 - 2607E040 DUV-12 320 AV NE #2 ACSR TW
3. 2007 - 2607E040 DUV-12 FDR TW Mt View Rd
VAS-13 | 21 | No improvements proposed at this time due to undergrounding cost to solve tree problems. | Will continue to review.
HAM-15 | 22 | 2005, 2006 and 2008 - Pole replacement projectsPole replacements. BRS-13 to HAM-15 feeder tie (future) | Reliability has significantly improved per 2006 rank due to pole replacements.
SLA-16 | 23 | 2010 - LAB-26 to SLA-16 feeder tie | Poor SAIDI due to car-pole accident history.
CUM-13 | 24 | 2006/2007 - Tacoma Headworks rebuild feeder
LGY-15 | 25 | Tree wire (2007 carryover - construction not funded for 2008). Useless Bay Substation (2010)
SHA-13 | 26 | Installation recloser being reviewed | Very short feeder in the worst wooded area in Pierce Co.
NOP-23 | 27 | 2006 NOP23 Rebuild 10604894, rebuild project should help No future project planned at this time.
SIL-16 | 28 | 2007 - Tree wire installed Seabeck Highway | Will continue to review outages looking for improvement projects
SWI-17 | 29 | 1.2006-07 CRP in Sunwood Lakes. 2.Future Replace 350 fdr with 750 fdr
SKY-23 | 30 | Numbers inflated by Maloney Ridge outages | Need customer agreement/funding to replace cables
QUI-26 | 31 | Proposed 6 additional switches to isolate sections of feeder by servicemen to reduce outage impacts.
WIN-15 | 32 | 2007 - OH-UG conversion
THO-13 | 33 | None | Normally this circuit is quite reliable. Unfortunately, the 12/14/06 major storm outage was included in the SAIDI data for this circuit and not designated as a major storm which would have excluded this outage from the SAIDI results. This circuit would then have dropped off the top 50 list.
IRO-15 | 34 | Future - Install loop on West Valley Road
ELD-25 | 35 | 2005-06 1.5 miles treewire installed on Cooper Pt Rd & several side laterals.
CHR-22 | 36 | 2008 - Kingston substation | Kingston Substation will allow this circuit's cross country problem area to be isloated.
PGA-12 | 37 | Projects being reviewed include potential reclosers and switches; eventually need a 4th circuit out of Poulsbo and an additional feeder tie from Poulsbo heading north toward Port Gamble
WLK-13 | 38 | Future - Buckley substation rebuild | Will increase backup capacity available, reduce response and restoration time, and increase backup capacity available in the area, reduce response and restoration times
COT-13 | 39 | 1.2007 - COT-13 UG OLD WOODINVILLE-DUVAL
2. 2008 - COT-13 UG Mink Rd
3. Future - COT-13 NE 145 St FDR TW
4. Future - CRP: 244TH AVE NE & NE 196TH ST
LLS-17 | 40 | 2006 - CRP; 2007 - Tree Wire completed for entire feeder, new distribution switches installed and transmission pole replacement; | Reliability has significantly improved per 2006 rank.
MIL-22 | 41 | The relocation for two reclosers to better isloate problems is being evaluated. | This circuit was realligned with the Kingston Substation new circuits project. The relocation for two reclosers to better isloate problems is being evaluated.
KEN-13 | 42 | Single phase tree wire has been installed. Reviewing additional tree wire installation
FRA-12 | 43 | Circuit reconfigured in the past; Future reclosers will be installed
SOO-25 | 44 | 2001 TW Kent-Black Diamond Rd & -1001195 SE 272 ST AND 152 AVE SE 1998 TW 101000018 168 Ave SE
NUG-26 | 45 | NUG-26 to KEN-12 feeder tie (2011) | Pole relocation has reduced car-pole accidents.
BON-16 | 46 | BON-16 TO RHO-13 feeder tie (2007) | This feeder tie will redistribute the load and decrease restoration times
HOB-15 | 47 | Four Corners substation (2009) | Load will be split up between Hobart and Four Corner and will help reduce outage duration
DIS-12 | 48 | No cost effective distribution solution found. Problems in the transmission and substation caused the highest customer outage numbers. | No customer complaint identified during the study in 2006. System is continuing being monitored and maintenance continues.
CLE-11 | 49 | None | Circuit is a long 34kV circuit in Kittitas County. Normally circuit is quite reliable. Unfortunately, the 12/15/06 major storm outage was included in the SAIDI data for this circuit and not designated as a major storm which would have excluded this outage from the SAIDI results. This circuit would then have dropped off the top 50 list.
NOR-24 | 50 | 1. 2006 -NOR-24 Replace BO Switch
3. 2005 -NOR-24 REPLACE 13 BO poles
3. 2004 - NOR-24 PRP 4 poles
4. 2003 - NOR-24 Downtown Kirkland CRP
SCH-15 | 51
VAS-12 | 52
PMA-16 | 53
HKX-16 | 54
SOM-15 | 55
CUM-15 | 56
BLU-13 | 57
BON-13 | 58
SNQ-17 | 59
HYA-15 | 60
BRS-13 | 61
TOL-15 | 62
YEL-27 | 63
MIR-13 | 64
SHD-18 | 65
BLA-13 | 66
CHR-25 | 67
PEA-15 | 68
OSC-22 | 69
LLT-16 | 70
OSC-23 | 71
PMA-12 | 72
FLD-15 | 73
SIL-15 | 74
NLM-15 | 75
GWR-13 | 76
BRO-16 | 77
SCH-12 | 78
COT-17 | 79
PTL-16 | 80
KAP-15 | 81
AIR-23 | 82
BIG-12 | 83
COT-16 | 84
SEQ-13 | 85
COT-15 | 86
LMC-25 | 87
LGY-16 | 88
HAP-16 | 89
MIR-17 | 90
SOO-23 | 91
GLA-12 | 92
ING-13 | 93
PET-13 | 94
BDI-12 | 95
MUR-16 | 96
NUG-25 | 97
NBE-16 | 98
PTL-13 | 99
ORT-23 | 100
MED-33 | 101
SME-12 | 102
CRE-12 | 103
IRO-13 | 104
KNT-37 | 105
SEQ-22 | 106
SHD-17 | 107
MIL-17 | 108
YEL-25 | 109
ETN-13 | 110
HAN-16 | 111
BIG-15 | 112
RPT-22 | 113
WLS-16 | 114
BTR-22 | 115
LLS-15 | 116
RED-14 | 117
AVO-17 | 118
MWD-15 | 119
MWD-16 | 120
CPV-13 | 121
FRG-15 | 122
MCW-14 | 123
GBK-13 | 124
HOU-23 | 125
FRA-15 | 126
WOB-25 | 127
KNM-23 | 128
EGT-25 | 129
ROC-16 | 130
MED-36 | 131
FLD-13 | 132
MIL-16 | 133
FRG-26 | 134
SNQ-15 | 135
QUI-25 | 136
SCH-13 | 137
SUM-15 | 138
SKE-26 | 139
SBE-25 | 140
KLA-15 | 141
THO-04 | 142
SKE-22 | 143
PAT-15 | 144
WOB-23 | 145
KNM-27 | 146
MIR-16 | 147
KEN-12 | 148
PLG-13 | 149
MCA-13 | 150
BHL-13 | 151
GRI-15 | 152
KCR-17 | 153
HKX-13 | 154
LGY-12 | 155
BLU-16 | 156
CRE-15 | 157
ROC-26 | 158
DUV-13 | 159
HOL-15 | 160
KWH-23 | 161
KNT-23 | 162
LAC-17 | 163
BLA-12 | 164
COL-26 | 165
BDI-13 | 166
BRO-15 | 167
VAS-23 | 168
CPV-15 | 169
BRI-17 | 170
LAB-25 | 171
LAB-26 | 172
LWS-15 | 173
SPI-17 | 174
ING-15 | 175
ROC-25 | 176
NLM-12 | 177
BCH-15 | 178
HOB-16 | 179
WIN-13 | 180
VWY-15 | 181
ALG-12 | 182
PHA-13 | 183
LAT-17 | 184
SOU-23 | 185
BRW-13 | 186
POU-15 | 187
PIN-26 | 188
BUC-16 | 189
LAT-14 | 190
VWY-13 | 191
ORI-15 | 192
DGR-15 | 193
HWD-25 | 194
MAN-12 | 195
GAR-13 | 196
WAY-13 | 197
LYN-13 | 198
ING-16 | 199
ENU-17 | 200
WAU-26 | 201
BCH-16 | 202
WAY-15 | 203
SLA-15 | 204
BRI-15 | 205
WIN-12 | 206
MAN-16 | 207
BTR-25 | 208
KWH-25 | 209
FAL-13 | 210
CLE-13 | 211
BOW-26 | 212
CAP-13 | 213
WLK-15 | 214
LOC-23 | 215
SWA-12 | 216
SIN-25 | 217
ELD-23 | 218
GRI-16 | 219
LMD-15 | 220
MWD-13 | 221
HLC-23 | 222
MOT-15 | 223
MER-15 | 224
EGT-28 | 225
FNW-16 | 226
LAC-16 | 227
FNW-17 | 228
ALG-15 | 229
BRW-16 | 230
MTH-15 | 231
PET-16 | 232
CLY-23 | 233
FRA-13 | 234
WIS-14 | 235
CWD-24 | 236
LUH-14 | 237
TAN-13 | 238
HWD-22 | 239
HAS-15 | 240
RJN-13 | 241
HWD-26 | 242
SKE-23 | 243
LAB-23 | 244
ROS-21 | 245
THO-25 | 246
NBO-26 | 247
RHO-17 | 248
SAH-17 | 249
RDO-12 | 250
PRI-21 | 251
FRA-16 | 252
PMA-13 | 253
YEL-26 | 254
STA-13 | 255
CEN-14 | 256
PRE-26 | 257
CAM-17 | 258
AIR-22 | 259
SNQ-13 | 260
FLC-15 | 261
CRE-16 | 262
NHL-17 | 263
EVE-23 | 264
MAP-13 | 265
LWS-14 | 266
SNQ-16 | 267
PMA-15 | 268
MIL-23 | 269
ETN-15 | 270
MCA-15 | 271
AIR-26 | 272
INT-17 | 273
NOB-24 | 274
LWS-12 | 275
MIR-15 | 276
LUH-17 | 277
MCW-15 | 278
HEM-13 | 279
HAN-13 | 280
HIG-15 | 281
LLT-17 | 282
BTR-21 | 283
YEL-23 | 284
FNW-13 | 285
BAR-13 | 286
ELD-27 | 287
FRG-25 | 288
MLK-13 | 289
WOO-27 | 290
SOO-27 | 291
BDI-16 | 292
RDO-16 | 293
DGR-16 | 294
MUR-15 | 295
LOL-23 | 296
NRU-25 | 297
PIP-25 | 298
JHO-16 | 299
BRW-15 | 300
NBE-15 | 301
TOL-17 | 302
HEM-15 | 303
RDO-13 | 304
LYN-24 | 305
MVW-17 | 306
SWA-13 | 307
WAB-13 | 308
CPV-12 | 309
KNM-26 | 310
EAR-16 | 311
CLY-25 | 312
ROS-17 | 313
SBE-22 | 314
PLG-17 | 315
PTR-16 | 316
TRA-22 | 317
LTA-18 | 318
BDI-15 | 319
SPA-16 | 320
LMC-23 | 321
TIL-23 | 322
PTR-14 | 323
BUC-25 | 324
SPI-15 | 325
LLT-13 | 326
CLV-16 | 327
SHD-16 | 328
SOM-17 | 329
NBE-13 | 330
KEA-14 | 331
WOO-23 | 332
KAP-16 | 333
CLY-27 | 334
SIN-22 | 335
PIP-23 | 336
VIS-22 | 337
WAU-25 | 338
WOL-23 | 339
SHE-26 | 340
BRE-36 | 341
EAR-15 | 342
SEQ-17 | 343
LMC-27 | 344
WIS-16 | 345
BEL-16 | 346
GRA-26 | 347
ROC-17 | 348
HAN-15 | 349
WOO-26 | 350
CUS-16 | 351
SWI-15 | 352
POU-16 | 353
LYN-17 | 354
SOM-13 | 355
CEK-14 | 356
PAN-14 | 357
SME-15 | 358
SAH-15 | 359
SAH-13 | 360
TAN-16 | 361
NNO-13 | 362
BTN-36 | 363
IRO-17 | 364
SBE-26 | 365
FWY-12 | 366
HOB-17 | 367
ROE-13 | 368
FWD-16 | 369
MVW-15 | 370
WIS-12 | 371
WOL-25 | 372
SBE-23 | 373
OVE-15 | 374
CEK-15 | 375
ROL-16 | 376
SUM-12 | 377
NLM-13 | 378
WIN-16 | 379
RPT-23 | 380
MAN-13 | 381
KAP-13 | 382
LYN-14 | 383
LEA-17 | 384
PAN-13 | 385
NNO-12 | 386
LEA-13 | 387
PRE-13 | 388
FWD-15 | 389
ROL-15 | 390
PAT-13 | 391
LYN-23 | 392
LHL-25 | 393
HAZ-13 | 394
WAY-12 | 395
HKX-12 | 396
LOL-25 | 397
ORC-15 | 398
BRI-14 | 399
NRU-23 | 400
INT-15 | 401
HAS-12 | 402
VAS-22 | 403
WOD-13 | 404
EGT-16 | 405
DGR-13 | 406
KLA-17 | 407
CEN-15 | 408
FWY-13 | 409
DEC-15 | 410
RED-24 | 411
VIT-23 | 412
MED-35 | 413
THU-16 | 414
LYN-26 | 415
PIN-27 | 416
SHA-15 | 417
LOL-22 | 418
STA-26 | 419
HOU-25 | 420
HEM-16 | 421
KWH-26 | 422
KIT-22 | 423
SKI-16 | 424
TOT-25 | 425
SHE-16 | 426
MUR-13 | 427
PIP-26 | 428
MVW-13 | 429
SIL-17 | 430
HAP-13 | 431
ELL-12 | 432
PCR-13 | 433
SIN-24 | 434
GRA-16 | 435
NOB-23 | 436
BEL-15 | 437
ORC-16 | 438
JUA-13 | 439
HWD-23 | 440
NRU-27 | 441
MOT-14 | 442
NBO-22 | 443
HLC-24 | 444
EAR-13 | 445
FRU-25 | 446
VIS-26 | 447
OVE-12 | 448
MHT-15 | 449
RED-12 | 450
PIP-22 | 451
WCA-15 | 452
MCW-17 | 453
CUS-13 | 454
GRA-25 | 455
BUC-26 | 456
OVE-13 | 457
MAP-15 | 458
RHO-13 | 459
PET-12 | 460
ORI-13 | 461
GOO-16 | 462
MST-25 | 463
BEL-26 | 464
CAM-23 | 465
NOR-25 | 466
CHA-15 | 467
BRS-15 | 468
WAB-12 | 469
EGT-11 | 470
MAN-15 | 471
PRI-23 | 472
NOR-23 | 473
HOU-27 | 474
RHO-15 | 475
RHO-16 | 476
LWS-16 | 477
BAK-26 | 478
CHI-15 | 479
RED-15 | 480
WOB-26 | 481
HIG-13 | 482
SHE-15 | 483
ELL-13 | 484
FRU-26 | 485
BRE-35 | 486
IRO-16 | 487
EVA-27 | 488
PLG-16 | 489
VIS-23 | 490
WCA-16 | 491
EVA-23 | 492
BUC-15 | 493
RJN-35 | 494
HAR-17 | 495
HAS-13 | 496
PAT-17 | 497
CAM-24 | 498
EGT-15 | 499
PAN-12 | 500
MST-27 | 501
SNQ-18 | 502
BRE-37 | 503
WLS-13 | 504
CLR-15 | 505
RED-13 | 506
ROS-13 | 507
SMR-26 | 508
RPT-15 | 509
RDO-15 | 510
RIV-13 | 511
SAH-16 | 512
SOO-26 | 513
CLV-15 | 514
LEA-16 | 515
ZEN-26 | 516
CHI-13 | 517
HOL-13 | 518
MOT-16 | 519
PHA-16 | 520
VIC-15 | 521
FAC-13 | 522
HAR-16 | 523
MCK-12 | 524
MLK-12 | 525
ROS-15 | 526
NOB-11 | 527
ELL-14 | 528
VAL-22 | 529
CUS-15 | 530
LLS-13 | 531
HAZ-16 | 532
ROL-13 | 533
RIT-16 | 534
HAN-12 | 535
PIN-23 | 536
EGT-27 | 537
AIR-25 | 538
RIT-19 | 539
PEA-17 | 540
BHL-16 | 541
LAT-16 | 542
SWE-23 | 543
BIG-13 | 544
VIC-14 | 545
LAB-27 | 546
GRV-15 | 547
SWE-25 | 548
DES-12 | 549
HAZ-15 | 550
NHL-16 | 551
MER-16 | 552
PHA-17 | 553
MCK-16 | 554
LMD-12 | 555
LOL-21 | 556
PLG-15 | 557
CAS-16 | 558
BTN-35 | 559
JHO-12 | 560
PRE-27 | 561
AVO-24 | 562
HEM-17 | 563
AVO-15 | 564
EDG-13 | 565
SOM-16 | 566
ORT-25 | 567
VIC-16 | 568
HAR-18 | 569
BCH-12 | 570
GRA-15 | 571
BOW-25 | 572
VIK-25 | 573
WAY-16 | 574
HOU-26 | 575
RED-23 | 576
RIV-12 | 577
KCR-16 | 578
CHA-13 | 579
GRA-17 | 580
GRV-16 | 581
NOP-22 | 582
GAR-15 | 583
TOT-23 | 584
GRV-12 | 585
LON-25 | 586
SWA-16 | 587
RED-22 | 588
CAM-25 | 589
ASB-17 | 590
EPO-13 | 591
BEL-17 | 592
MER-12 | 593
LAT-13 | 594
MED-37 | 595
SKI-13 | 596
SOU-26 | 597
EDG-16 | 598
MST-23 | 599
HAP-15 | 600
CWD-25 | 601
KEA-15 | 602
GBK-15 | 603
TOT-22 | 604
VWY-12 | 605
COL-25 | 606
ROE-17 | 607
RJN-11 | 608
MCK-15 | 609
STA-15 | 610
ZEN-23 | 611
STA-17 | 612
DUT-14 | 613
GOO-13 | 614
GAR-16 | 615
EAR-17 | 616
STW-13 | 617
FAC-16 | 618
LTA-17 | 619
MCW-16 | 620
ELL-15 | 621
BRE-33 | 622
ANA-15 | 623
SEQ-16 | 624
GOO-15 | 625
MHT-13 | 626
CLY-26 | 627
ROC-15 | 628
EPO-12 | 629
EPO-15 | 630
WIS-13 | 631
KIT-25 | 632
EDG-15 | 633
NRU-26 | 634
BEL-25 | 635
TRA-23 | 636
FNW-15 | 637
KCR-15 | 638
PGA-15 | 639
LOC-26 | 640
WLS-12 | 641
HAZ-12 | 642
KNT-36 | 643
SHA-17 | 644
BLS-23 | 645
CED-13 | 646
CED-17 | 647
FWD-17 | 648
SMR-24 | 649
FWD-13 | 650
GOO-17 | 651
OLD-26 | 652
CRE-13 | 653
HLC-25 | 654
EGT-12 | 655
MVW-16 | 656
BOW-27 | 657
STA-16 | 658
MLK-15 | 659
RPT-16 | 660
BLS-22 | 661
PAN-15 | 662
PIK-21 | 663
VIC-17 | 664
CAP-15 | 665
BHL-12 | 666
BAK-25 | 667
BON-15 | 668
GRV-13 | 669
OBY-17 | 670
ELD-26 | 671
SHE-17 | 672
MKI-17 | 673
ZEN-25 | 674
AVO-13 | 675
BIG-16 | 676
PCR-14 | 677
CHR-23 | 678
SEQ-15 | 679
ROS-22 | 680
LHL-23 | 681
VIS-25 | 682
DGR-17 | 683
NOR-26 | 684
TOL-16 | 685
CHI-16 | 686
SWE-27 | 687
ORC-13 | 688
FWY-15 | 689
NNO-15 | 690
EDG-12 | 691
LOC-25 | 692
SNN-21 | 693
ORI-17 | 694
RPT-26 | 695
KNT-35 | 696
MER-13 | 697
CAR-16 | 698
BHL-15 | 699
AVO-16 | 700
INT-16 | 701
OSC-26 | 702
CEK-16 | 703
SHD-15 | 704
BON-17 | 705
PCR-12 | 706
RPT-17 | 707
BEL-23 | 708
CAM-26 | 709
PIN-25 | 710
DEC-16 | 711
FRG-16 | 712
JUA-15 | 713
CHA-16 | 714
ROE-15 | 715
FLC-14 | 716
STA-23 | 717
WOD-15 | 718
MCA-16 | 719
LAC-15 | 720
SKI-12 | 721
SLA-17 | 722
CWD-22 | 723
BTR-24 | 724
OSC-25 | 725
SPI-16 | 726
DES-15 | 727
MTV-15 | 728
PLU-13 | 729
NHL-15 | 730
NOB-21 | 731
TAN-15 | 732
HIG-16 | 733
LTA-16 | 734
MKI-14 | 735
PIN-17 | 736
SWI-13 | 737
FRU-22 | 738
KWH-22 | 739
POU-13 | 740
ENU-18 | 741
HAR-22 | 742
KNT-26 | 743
LLT-15 | 744
ASB-15 | 745
THU-15 | 746
HAW-11 | 747
NBO-25 | 748
CHA-12 | 749
PIK-22 | 750
MOT-17 | 751
STW-16 | 752
RIV-16 | 753
GAR-12 | 754
KLA-18 | 755
ELL-16 | 756
CEK-17 | 757
KNT-27 | 758
SWI-16 | 759
MLK-16 | 760
JUA-14 | 761
FAB-17 | 762
FCH-16 | 763
HAW-12 | 764
MHT-16 | 765
ZEN-24 | 766
SME-13 | 767
PIK-23 | 768
BAR-17 | 769
SWA-15 | 770
MAP-16 | 771
LHL-22 | 772
TRA-25 | 773
FAB-15 | 774
MTH-16 | 775
NLM-16 | 776
LMD-16 | 777
ENU-16 | 778
CED-15 | 779
LAC-13 | 780
HAR-15 | 781
MTV-16 | 782
ORC-17 | 783
TRA-26 | 784
SLA-13 | 785
DEC-13 | 786
WIS-15 | 787
JUA-12 | 788
OBY-16 | 789
MTH-17 | 790
ASB-16 | 791
BAK-22 | 792
FRN-13 | 793
PAN-16 | 794
PET-15 | 795
FCH-24 | 796
LEA-15 | 797
BAK-23 | 798
TOT-24 | 799
WCA-17 | 800
ROC-13 | 801
BEL-13 | 802
FAB-13 | 803
MKI-15 | 804
LWS-13 | 805
PIK-25 | 806
BRE-13 | 807
CLE-14 | 808
PAT-16 | 809
SHE-25 | 810
UHL-23 | 811
MST-26 | 812
WAU-22 | 813
PEA-16 | 814
ENU-15 | 815
DEC-17 | 816
LOC-27 | 817
EVA-26 | 818
DES-16 | 819
KNM-25 | 820
MIR-26 | 821
NOR-27 | 822
MAP-17 | 823
PLY-13 | 824
STA-25 | 825
ROL-17 | 826
LUH-15 | 827
UHL-25 | 828
NOP-25 | 829
MTV-17 | 830
SMR-23 | 831
CWD-23 | 832
LHL-26 | 833
WOB-27 | 834
FWY-11 | 835
JUA-16 | 836
PHA-15 | 837
MHT-17 | 838
TIL-25 | 839
BAR-15 | 840
EVE-17 | 841
OLD-23 | 842
EVE-15 | 843
LMC-26 | 844
ZEN-17 | 845
SPA-17 | 846
MTH-13 | 847
SEH-12 | 848
CAR-15 | 849
CLR-16 | 850
WLS-15 | 851
HAR-25 | 852
RJN-25 | 853
WOO-25 | 854
WOL-26 | 855
PLY-16 | 856
BTR-23 | 857
DES-13 | 858
KEA-13 | 859
CED-16 | 860
EPO-16 | 861
FAC-12 | 862
PRI-22 | 863
PLY-15 | 864
STW-15 | 865
PEA-14 | 866
COL-23 | 867
NOP-26 | 868
NNO-16 | 869
INT-23 | 870
NHL-13 | 871
LMD-13 | 872
RIV-15 | 873
NBE-12 | 874
SEH-13 | 875
HOL-12 | 876
KNT-33 | 877
UHL-21 | 878
HIG-17 | 879
ANA-16 | 880
PIK-24 | 881
DUT-16 | 882
BAR-16 | 883
PLU-24 | 884
RED-25 | 885
SAM-11 | 886
BCH-13 | 887
GAG-13 | 888
CAR-12 | 889
TIL-22 | 890
VIK-23 | 891
ORI-16 | 892
OPC-39 | 893
UHL-22 | 894
VIT-18 | 895
BLS-25 | 896
VAL-21 | 897
OLD-25 | 898
PRE-12 | 899
ANA-13 | 900
RJN-14 | 901
EGT-26 | 902
SEH-16 | 903
KNT-25 | 904
NOB-22 | 905
INT-13 | 906
SAM-14 | 907
SUN-14 | 908
ASB-13 | 909
SST-17 | 910
FLC-16 | 911
CAR-13 | 912
WAU-23 | 913
RAI-11 | 914
STW-12 | 915
SAM-12 | 916
QRY-13 | 917
KLA-16 | 918
WOL-22 | 919
SEH-15 | 920
PLA-23 | 921
SUN-12 | 922
ANA-17 | 923
VAL-12 | 924
LYN-16 | 925
PLA-21 | 926
SUM-13 | 927
PLA-22 | 928
BTN-38 | 929
MKI-16 | 930
EVE-22 | 931
PLU-25 | 932
NRU-14 | 933
OLD-22 | 934
HLC-26 | 935
LYO-15 | 936
EVE-26 | 937
RJN-26 | 938
SMR-25 | 939
SST-16 | 940
JHO-13 | 941
GAG-11 | 942
HAR-26 | 943
SPI-23 | 944
SUN-13 | 945
PAD-15 | 946
LYO-12 | 947
NOB-12 | 948
PLA-24 | 949
FAB-16 | 950
FRU-23 | 951
SUN-11 | 952
RIT-17 | 953
RJN-15 | 954
RAI-14 | 955