## Grid Mod Circuit Summary
GRID MODERNIZATION PLAN 2023-2025 - BY CIRCUIT
Rev. 12/29/2021
Disclaimer: The work plan outined below in each Program, is subject to change, due to scheduling, priority or budget shifts, which can and will occur on a regular basis.
X = project, F = future project, P = possible project, C = contingency project
[5 empty] | Grid Modernization - CEIP | [5 empty] | Grid Modernization - Core
Main Circuit | Planning County/Region | Substation | HIC | VP | VPP | Hosting Capacity | DERMS | DER Circuit Enablement | Resiliency Enhancement | Substation SCADA - Accelerated | Voltage Reduction | AMI | ADMS - D-SCADA, OMS | Demonstrations and pilots | Vegetation management (dist only) | Wildfire mitigation (dist only) | Pole Inspection (dist only) | Submarine Cable Mitigation | Substation Reliability | Substation SCADA | Cable Remediation | WPC | Targeted Reliability | Targeted Capacity | Underground Conversions | Copper Conductor Replacement | Reclosers | FuseSavers | DA | TA
AIR-22 | Thurston | AIR | X |  | X | X | [5 empty] | X | X |  | 2025 | X | 2025 |  | 2025
AIR-23 | Thurston | AIR |  |  | X | X | [5 empty] | X | X |  |  | X |  |  | 2025 | [8 empty] | 2023
AIR-25 | Thurston | AIR |  |  | X | X | [5 empty] | X | X |  |  | X |  |  | 2025
AIR-26 | Thurston | AIR | X |  | X | X | [5 empty] | X | X |  | 2025 | X |  |  | 2025
ALG-12 | Skagit | ALG | X |  | X | X | [5 empty] | X | X |  | 2024 |  | 2024 |  | 2023 |  | X | 2023
ALG-13 | Skagit | ALG |  |  | X | X | [5 empty] | X | X | [5 empty] | 2023
ALG-15 | Skagit | ALG | X |  | X | X |  | P |  |  |  | X | X | [5 empty] | 2023 |  |  | 2024
ALP-11 | South King | ALP | X | X | X | X | [5 empty] | X | X | [6 empty] | F
ALP-21 | South King | ALP | X | X | X | X | [5 empty] | X | X | [6 empty] | F
ANA-13 | Skagit | ANA |  |  | X | X | [5 empty] | X | X |  | 2025
ANA-15 | Skagit | ANA | X |  | X | X | [5 empty] | X | X |  | 2025 |  | 2025 |  |  |  | X
ANA-16 | Skagit | ANA | X |  | X | X | [5 empty] | X | X |  | 2025
ANA-17 | Skagit | ANA |  |  | X | X | [5 empty] | X | X |  | 2025
ARD-11 | North King | ARD |  |  | X | X | [5 empty] | X | X
ARD-12 | North King | ARD |  |  | X | X | [5 empty] | X | X
ARD-13 | North King | ARD |  |  | X | X | [5 empty] | X | X
ARD-14 | North King | ARD |  |  | X | X | [5 empty] | X | X
ARD-15 | North King | ARD |  |  | X | X | [5 empty] | X | X |  | 2025 |  | 2024
ARD-16 | North King | ARD |  |  | X | X | [5 empty] | X | X
ARD-41 | North King | ARD |  |  | X | X | [5 empty] | X | X
ARD-42 | North King | ARD |  |  | X | X | [5 empty] | X | X
ARD-43 | North King | ARD |  |  | X | X | [5 empty] | X | X
ARD-44 | North King | ARD |  |  | X | X | [5 empty] | X | X
ARD-45 | North King | ARD |  |  | X | X | [5 empty] | X | X
ARD-46 | North King | ARD |  |  | X | X | [5 empty] | X | X
ASB-13 | South King | ASB | X | X | X | X |  |  |  | P |  | X | X |  | 2025 |  |  |  |  | 2025
ASB-15 | South King | ASB | X | X | X | X |  |  |  | P |  | X | X |  | 2025 |  |  |  |  | 2025
ASB-16 | South King | ASB | X | X | X | X |  |  |  | P |  | X | X | [6 empty] | 2025
ASB-17 | South King | ASB | X | X | X | X |  |  |  | P |  | X | X |  | 2025 |  |  |  |  | 2025
AVO-13 | North King | AVO |  |  | X | X | [5 empty] | X | X |  | 2025 |  | 2025 | [5 empty] | 2024
AVO-15 | North King | AVO |  |  | X | X | [5 empty] | X | X | [7 empty] | X | [7 empty] | 2023
AVO-16 | North King | AVO |  |  | X | X | [5 empty] | X | X
AVO-17 | North King | AVO |  |  | X | X | [5 empty] | X | X
AVO-24 | North King | AVO |  |  | X | X | [5 empty] | X | X | [15 empty] | 2023
BAK-22 | Whatcom | BAK | X | X | X | X |  |  |  | P |  | X | X |  | 2023 |  |  |  |  | 2025 | X
BAK-23 | Whatcom | BAK |  |  | X | X | [5 empty] | X | X |  | 2023 |  |  |  |  | 2025
BAK-25 | Whatcom | BAK |  |  | X | X |  | P |  |  |  | X | X |  |  |  | 2023 |  |  | 2025
BAR-13 | Thurston | BAR |  |  | X | X | [5 empty] | X | X |  | 2023 | X | 2025 |  | 2024 | 2024
BAR-15 | Thurston | BAR |  |  | X | X | [5 empty] | X | X |  | 2023 | X |  |  | 2024 | 2024
BAR-16 | Thurston | BAR | X |  | X | X |  |  |  | P |  | X | X |  | 2024 | X |  |  | 2024 | 2024
BAR-17 | Thurston | BAR |  |  | X | X | [5 empty] | X | X |  | 2023 | X |  |  | 2024 | 2024 | X
BAS-11 | South King | BAS | X | X | X | X | [5 empty] | X | X
BAS-12 | South King | BAS | X | X | X | X | [5 empty] | X | X |  | 2024
BAS-13 | South King | BAS | X | X | X | X | [5 empty] | X | X |  | 2023 | [9 empty] | 2023
BAS-14 | South King | BAS | X | X | X | X | [5 empty] | X | X
BAS-15 | South King | BAS | X | X | X | X | [5 empty] | X | X
BCH-12 | Whatcom | BCH |  |  | X | X | [5 empty] | X | X |  | 2025 | [5 empty] | X | [8 empty] | 2024
BCH-13 | Whatcom | BCH | X |  | X | X | [5 empty] | X | X | [16 empty] | 2024
BCH-15 | Whatcom | BCH | X |  | X | X | [5 empty] | X | X | [8 empty] | 2023 | [5 empty] | 2023 |  | 2024
BCH-16 | Whatcom | BCH | X | X | X | X | [5 empty] | X | X |  | 2025 | [7 empty] | 2024 |  |  |  | 2023 |  |  | 2024
BDI-12 | South King | BDI | X |  | X | X | [5 empty] | X | X |  | 2025 |  |  |  | 2025
BDI-13 | South King | BDI | X |  | X | X | [5 empty] | X | X | [5 empty] | 2025 |  |  |  |  | 2023
BDI-15 | South King | BDI | X |  | X | X | [5 empty] | X | X |  | 2025 |  | 2025 |  | 2025 | [8 empty] | 2023
BDI-16 | South King | BDI | X |  | X | X | [5 empty] | X | X |  | 2025 |  |  |  | 2025
BEL-13 | South King | BEL | X | X | X | X |  |  |  | P |  | X | X | [5 empty] | 2024 | 2023 | [8 empty] | 2023 | 2024
BEL-15 | South King | BEL | X | X | X | X |  |  |  | P |  | X | X |  | 2023 |  |  |  | 2024 | 2023 | [9 empty] | 2024
BEL-16 | South King | BEL | X | X | X | X |  |  |  | P |  | X | X |  | 2023 |  | 2024 |  | 2024 | 2023 | [9 empty] | 2024
BEL-17 | South King | BEL | X | X | X | X |  |  |  | P |  | X | X | [5 empty] | 2024 | 2023 | [9 empty] | 2024
BEL-22 | South King | BEL |  |  | X | X | [5 empty] | X | X | [5 empty] | 2024 | 2023 | [9 empty] | 2024
BEL-23 | South King | BEL | X | X | X | X |  |  |  | P |  | X | X | [5 empty] | 2024 | 2023 | [9 empty] | 2024
BEL-25 | South King | BEL | X | X | X | X |  |  |  | P |  | X | X | [5 empty] | 2024 | 2023 | [9 empty] | 2024
BEL-26 | South King | BEL | X | X | X | X |  |  |  | P |  | X | X | [5 empty] | 2024 | 2023 | [9 empty] | 2024
BHL-12 | Kitsap | BHL |  |  | X | X |  |  |  |  | C | X | X | [6 empty] | 2024
BHL-13 | Kitsap | BHL |  |  | X | X |  |  |  |  | C | X | X |  | 2025 |  |  |  |  | 2024 | [7 empty] | 2023
BHL-15 | Kitsap | BHL |  |  | X | X |  |  |  |  | C | X | X |  | 2025 |  |  |  |  | 2024
BHL-16 | Kitsap | BHL |  |  | X | X |  |  |  |  | C | X | X |  | 2025 |  |  |  |  | 2024
BHS-11 | Whatcom | BHS |  |  | X | X |  | P |  |  |  | X | X |  | 2024 |  | 2023
BHS-12 | Whatcom | BHS |  |  | X | X | [5 empty] | X | X |  | 2025 |  | 2023
BHS-13 | Whatcom | BHS |  |  | X | X | [5 empty] | X | X |  | 2023 |  | 2025 |  |  |  | X | [6 empty] | 2023
BHS-14 | Whatcom | BHS |  |  | X | X |  | P |  |  |  | X | X |  | 2024 |  | 2025
BHS-15 | Whatcom | BHS |  |  | X | X | [5 empty] | X | X
BIG-12 | Skagit | BIG |  |  | X | X | [5 empty] | X | X |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  |  | 2023
BIG-13 | Skagit | BIG |  | X | X | X | [5 empty] | X | X |  | 2023 |  |  |  | 2024
BIG-15 | Skagit | BIG |  | X | X | X | [5 empty] | X | X |  | 2024 |  |  |  | 2024 |  | X
BIG-16 | Skagit | BIG |  | X | X | X | [5 empty] | X | X |  | 2024 |  | 2025 |  | 2024
BKB-11 | Skagit | BKB |  |  | X | X | [5 empty] | X | X
BKB-12 | Skagit | BKB | X | X | X | X | [5 empty] | X | X |  |  |  | 2024
BKB-13 | Skagit | BKB |  | X | X | X | [5 empty] | X | X |  | 2023
BKB-14 | Skagit | BKB |  | X | X | X | [5 empty] | X | X |  | 2025
BKB-15 | Skagit | BKB |  | X | X | X | [5 empty] | X | X |  | 2023
BLA-12 | Whatcom | BLA |  |  | X | X | [5 empty] | X | X |  | 2024 |  |  |  | 2023 | 2023 | X | [6 empty] | 2023 | 2023 | 2024
BLA-13 | Whatcom | BLA |  |  | X | X | [5 empty] | X | X |  | 2025 |  |  |  | 2023 | 2023 | [6 empty] | 2023 |  |  | 2024
BLA-15 | Whatcom | BLA |  |  | X | X | [5 empty] | X | X | [5 empty] | 2023 | 2023 | [9 empty] | 2024
BLA-16 | Whatcom | BLA |  |  | X | X | [5 empty] | X | X | [5 empty] | 2023 | 2023 | [9 empty] | 2024
BLA-17 | Whatcom | BLA |  |  | X | X | [5 empty] | X | X | [5 empty] | 2023 | 2023 | [9 empty] | 2024
BLS-22 | Whatcom | BLS | X | X | X | X | [5 empty] | X | X |  | 2024 |  |  |  |  | F
BLS-23 | Whatcom | BLS | X | X | X | X | [5 empty] | X | X |  |  |  | 2025 |  |  | F | X
BLS-25 | Whatcom | BLS | X | X | X | X | [5 empty] | X | X | [6 empty] | F | [7 empty] | 2023
BLS-26 | Whatcom | BLS | X | X | X | X | [5 empty] | X | X | [6 empty] | F
BLU-13 | Thurston | BLU |  |  | X | X | [5 empty] | X | X | X | 2023 | X | 2023 | [5 empty] | 2023 | 2023 |  |  | 2023
BLU-16 | Thurston | BLU | X |  | X | X | [5 empty] | X | X | X |  | 2023 | [5 empty] | 2023
BLU-17 | Thurston | BLU | X |  | X | X |  | P |  |  |  | X | X | X | 2024 | X |  |  |  |  | X
BON-13 | Pierce | BON |  |  | X | X | [5 empty] | X | X |  | 2023 |  |  |  |  | 2024
BON-15 | Pierce | BON |  |  | X | X | [5 empty] | X | X |  | 2024 |  | 2025 |  |  | 2024
BON-16 | Pierce | BON |  |  | X | X | [5 empty] | X | X |  | 2024 |  | 2024 |  |  | 2024
BON-17 | Pierce | BON | X |  | X | X |  |  |  | P |  | X | X |  | 2024 |  | 2023 |  |  | 2024
BOW-15 | South King | BOW | X | X | X | X | [5 empty] | X | X
BOW-16 | South King | BOW | X | X | X | X | [5 empty] | X | X
BOW-23 | South King | BOW | X | X | X | X | [5 empty] | X | X |  | 2025
BOW-25 | South King | BOW | X | X | X | X | [5 empty] | X | X |  | 2025
BOW-26 | South King | BOW | X | X | X | X | [5 empty] | X | X |  | 2024 | [5 empty] | X
BOW-27 | South King | BOW | X | X | X | X | [5 empty] | X | X |  | 2024
BRE-11 | Kitsap | BRE | X |  | X | X | [5 empty] | X | X |  | 2025
BRE-13 | Kitsap | BRE |  |  | X | X | [5 empty] | X | X
BRE-14 | Kitsap | BRE | X |  | X | X | [5 empty] | X | X |  | 2025
BRE-21 | Kitsap | BRE | X |  | X | X | [5 empty] | X | X |  | 2025
BRE-22 | Kitsap | BRE | X | X | X | X | [5 empty] | X | X |  | 2025 | [5 empty] | X
BRE-24 | Kitsap | BRE | X |  | X | X | [5 empty] | X | X |  | 2025
BRI-14 | Whatcom | BRI |  |  | X | X | [5 empty] | X | X |  | 2025 |  |  |  | 2024 |  |  |  | 2023 | [6 empty] | 2023
BRI-15 | Whatcom | BRI |  | X | X | X | [5 empty] | X | X | [5 empty] | 2024 | [8 empty] | 2023 |  | 2023
BRI-16 | Whatcom | BRI |  |  | X | X | [5 empty] | X | X | [5 empty] | 2024 | [10 empty] | 2023
BRI-17 | Whatcom | BRI |  |  | X | X | [5 empty] | X | X |  | 2025 |  |  |  | 2024 |  | X | [5 empty] | 2023 |  |  | 2023
BRO-15 | Island | BRO |  |  | X | X | [5 empty] | X | X | [7 empty] | X
BRO-16 | Island | BRO |  |  | X | X | [5 empty] | X | X | [15 empty] | C
BRS-13 | Skagit | BRS | X |  | X | X | [5 empty] | X | X |  | 2025
BRS-15 | Skagit | BRS | X |  | X | X | [5 empty] | X | X |  | 2025
BRS-16 | Skagit | BRS | X |  | X | X | [5 empty] | X | X
BRS-24 | Skagit | BRS | X |  | X | X | [5 empty] | X | X |  |  | X | [10 empty] | 2023
BRS-25 | Skagit | BRS |  |  | X | X | [5 empty] | X | X
BRW-13 | Skagit | BRW | X |  | X | X | [5 empty] | X | X
BRW-15 | Skagit | BRW | X |  | X | X |  | P |  |  |  | X | X
BRW-16 | Skagit | BRW |  |  | X | X | [5 empty] | X | X | [7 empty] | X
BRW-17 | Skagit | BRW |  |  | X | X | [5 empty] | X | X
BTN-35 | Skagit | BTN |  | X | X | X | [5 empty] | X | X |  | 2023 |  | 2024 |  |  |  | X
BTN-36 | Skagit | BTN | X | X | X | X | [5 empty] | X | X |  | 2023 | [5 empty] | X
BTN-37 | Skagit | BTN |  | X | X | X | [5 empty] | X | X |  | 2024
BTN-38 | Skagit | BTN | X | X | X | X | [5 empty] | X | X |  | 2023 |  | 2025
BTR-11 | North King | BTR |  |  | X | X | [5 empty] | X | X
BTR-12 | North King | BTR |  |  | X | X | [5 empty] | X | X
BTR-13 | North King | BTR |  |  | X | X | [5 empty] | X | X
BTR-14 | North King | BTR |  |  | X | X | [5 empty] | X | X
BTR-15 | North King | BTR |  |  | X | X | [5 empty] | X | X
BTR-21 | North King | BTR |  |  | X | X | [5 empty] | X | X |  |  |  | 2024
BTR-22 | North King | BTR |  |  | X | X | [5 empty] | X | X | [9 empty] | 2023
BTR-23 | North King | BTR |  |  | X | X | [5 empty] | X | X
BTR-24 | North King | BTR |  |  | X | X | [5 empty] | X | X
BTR-25 | North King | BTR |  |  | X | X | [5 empty] | X | X
BUC-15 | Pierce | BUC |  | X | X | X | [5 empty] | X | X |  | 2025 |  |  |  |  | F | [7 empty] | 2023
BUC-16 | Pierce | BUC | X | X | X | X | [5 empty] | X | X | [6 empty] | F |  |  | 2024
BUC-25 | Pierce | BUC | X | X | X | X | [5 empty] | X | X | [6 empty] | F
BUC-26 | Pierce | BUC | X | X | X | X | [5 empty] | X | X |  | 2024 |  |  |  |  | F
CAM-17 | South King | CAM | X | X | X | X |  |  |  | P |  | X | X |  | 2024 |  |  |  |  | 2025 | X
CAM-23 | South King | CAM | X | X | X | X |  |  |  | P |  | X | X |  | 2023 |  | 2023 |  |  | 2025 | X
CAM-24 | South King | CAM | X | X | X | X |  |  |  | P |  | X | X |  | 2023 |  |  |  |  | 2025
CAM-25 | South King | CAM | X | X | X | X |  |  |  | P |  | X | X |  | 2023 |  |  |  |  | 2025 | [7 empty] | 2023
CAM-26 | South King | CAM | X | X | X | X |  |  |  | P |  | X | X |  | 2023 |  |  |  |  | 2025
CAP-13 | Thurston | CAP |  |  | X | X | [5 empty] | X | X |  | 2025 | X |  |  |  | F | X |  |  |  | 2023
CAP-15 | Thurston | CAP |  |  | X | X | [5 empty] | X | X |  | 2025 |  |  |  |  | F
CAP-16 | Thurston | CAP |  |  | X | X | [5 empty] | X | X | [6 empty] | F
CAP-18 | Thurston | CAP |  |  | X | X |  | P |  |  |  | X | X | [6 empty] | F
CAP-25 | Thurston | CAP |  |  | X | X | [5 empty] | X | X | [6 empty] | F
CAP-26 | Thurston | CAP |  |  | X | X | [5 empty] | X | X | [6 empty] | F
CAP-27 | Thurston | CAP |  |  | X | X | [5 empty] | X | X | [6 empty] | F
CAR-12 | Whatcom | CAR |  | X | X | X | [5 empty] | X | X |  | 2024 |  |  |  | 2024
CAR-13 | Whatcom | CAR |  | X | X | X | [5 empty] | X | X |  | 2024 |  |  |  | 2024
CAR-15 | Whatcom | CAR |  | X | X | X | [5 empty] | X | X |  | 2025 |  |  |  | 2024
CAR-16 | Whatcom | CAR |  | X | X | X |  | P |  |  |  | X | X |  | 2024 |  |  |  | 2024 |  | X
CAS-14 | Kittitas | CAS |  |  | X | X |  | P |  |  |  | X | X |  |  | X
CAS-15 | Kittitas | CAS |  |  | X | X |  | P |  |  |  | X | X |  |  | 2023 | [6 empty] | 2024
CAS-16 | Kittitas | CAS |  |  | X | X |  | P |  |  |  | X | X |  | 2025 | 2023 | 2025
CED-13 | Pierce | CED | X |  | X | X | [5 empty] | X | X |  | 2024 |  |  |  |  | F
CED-15 | Pierce | CED | X |  | X | X | [5 empty] | X | X |  | 2024 |  |  |  |  | F | X
CED-16 | Pierce | CED | X |  | X | X | [5 empty] | X | X |  | 2025 |  |  |  |  | F
CED-17 | Pierce | CED | X |  | X | X | [5 empty] | X | X |  | 2025 |  | 2023 |  |  | F | [6 empty] | 2023
CEK-14 | Kitsap | CEK |  |  | X | X | [5 empty] | X | X | [5 empty] | 2025 | 2024 |  | 2024 | [7 empty] | 2025
CEK-15 | Kitsap | CEK |  |  | X | X | [5 empty] | X | X | [5 empty] | 2025 | 2024 | [9 empty] | 2025
CEK-16 | Kitsap | CEK |  |  | X | X | [5 empty] | X | X |  |  |  | 2025 |  | 2025 | 2024 | [9 empty] | 2025
CEK-17 | Kitsap | CEK |  |  | X | X | [5 empty] | X | X | [5 empty] | 2025 | 2024 | [9 empty] | 2025
CEN-11 | Cent King | CEN |  |  | X | X | [5 empty] | X | X
CEN-12 | Cent King | CEN |  |  | X | X | [5 empty] | X | X
CEN-13 | Cent King | CEN |  |  | X | X | [5 empty] | X | X
CEN-14 | Cent King | CEN |  |  | X | X | [5 empty] | X | X
CEN-15 | Cent King | CEN |  |  | X | X | [5 empty] | X | X
CEN-1N | Cent King | CEN |  |  | X | X | [5 empty] | X | X
CEN-21 | Cent King | CEN |  |  | X | X | [5 empty] | X | X
CEN-22 | Cent King | CEN |  |  | X | X | [5 empty] | X | X
CEN-23 | Cent King | CEN |  |  | X | X | [5 empty] | X | X
CEN-24 | Cent King | CEN |  |  | X | X | [5 empty] | X | X
CEN-25 | Cent King | CEN |  |  | X | X | [5 empty] | X | X |  |  |  | 2024 |  |  |  | X
CEN-2N | Cent King | CEN |  |  | X | X | [5 empty] | X | X
CHA-12 | Thurston | CHA |  |  | X | X |  |  |  |  | 2023 | X | X |  | 2023 | X |  |  |  | 2025
CHA-13 | Thurston | CHA |  |  | X | X |  |  |  |  | 2023 | X | X |  |  | X |  |  |  | 2025 | [7 empty] | 2023
CHA-15 | Thurston | CHA |  |  | X | X |  |  |  |  | 2023 | X | X |  |  | X |  |  |  | 2025
CHA-16 | Thurston | CHA |  |  | X | X |  |  |  |  | 2023 | X | X |  | 2023 | X |  |  |  | 2025
CHI-12 | Kitsap | CHI |  |  | X | X | [5 empty] | X | X |  | 2024 |  |  |  | 2023 | [10 empty] | 2025
CHI-13 | Kitsap | CHI |  |  | X | X | [5 empty] | X | X |  | 2025 |  |  |  | 2023 | [10 empty] | 2025
CHI-15 | Kitsap | CHI |  |  | X | X | [5 empty] | X | X |  |  |  | 2025 |  | 2023 |  | X | [8 empty] | 2025
CHI-16 | Kitsap | CHI |  |  | X | X | [5 empty] | X | X |  | 2025 |  |  |  | 2023 | [10 empty] | 2025
CHR-22 | Kitsap | CHR | X |  | X | X |  |  |  | P |  | X | X |  |  |  | 2024 |  |  |  |  | 2024 | [6 empty] | C
CHR-23 | Kitsap | CHR | X |  | X | X |  |  |  | P |  | X | X |  | 2025 |  | 2023
CHR-25 | Kitsap | CHR | X |  | X | X |  |  |  | P |  | X | X
CLE-11 | Kittitas | CLE |  |  | X | X |  | P |  |  |  | X | X |  | 2024 | 2023 |  |  |  | 2024 | [6 empty] | 2023 |  | C
CLE-12 | Kittitas | CLE |  |  | X | X |  | P |  |  |  | X | X |  | 2025 | 2023 |  |  |  | 2024 | [6 empty] | 2023 |  | C
CLE-13 | Kittitas | CLE |  |  | X | X |  | P |  |  |  | X | X |  |  | 2023 |  |  |  | 2024 | [6 empty] | 2023 |  | C
CLE-14 | Kittitas | CLE |  |  | X | X |  | P |  |  |  | X | X |  |  | X |  |  |  | 2024
CLR-13 | Kittitas | CLR |  |  | X | X |  | P |  |  |  | X | X
CLR-15 | Kittitas | CLR |  | X | X | X |  | P |  |  |  | X | X |  |  | X |  |  |  |  | X
CLR-16 | Kittitas | CLR |  |  | X | X |  | P |  |  |  | X | X |  |  | X | 2024
CLV-12 | Island | CLV |  |  | X | X | [5 empty] | X | X | [5 empty] | 2025 | F
CLV-13 | Island | CLV |  |  | X | X | [5 empty] | X | X | [5 empty] | 2025 | F
CLV-15 | Island | CLV |  | X | X | X | [5 empty] | X | X |  | 2025 |  |  |  | 2025 | F
CLV-16 | Island | CLV |  | X | X | X | [5 empty] | X | X | [5 empty] | 2025 | F | [6 empty] | 2023 | 2023
CLY-22 | Cent King | CLY |  |  | X | X | [5 empty] | X | X | [6 empty] | 2025
CLY-23 | Cent King | CLY |  |  | X | X | [5 empty] | X | X |  | 2024 |  | 2025 |  |  | 2025
CLY-25 | Cent King | CLY |  |  | X | X | [5 empty] | X | X | [6 empty] | 2025
CLY-26 | Cent King | CLY |  |  | X | X | [5 empty] | X | X |  | 2023 |  | 2025 |  |  | 2025
CLY-27 | Cent King | CLY |  |  | X | X | [5 empty] | X | X |  |  |  | 2024 |  |  | 2025
CLY-2N | Cent King | CLY |  |  | X | X | [5 empty] | X | X | [6 empty] | 2025
COL-22 | Cent King | COL |  |  | X | X | [5 empty] | X | X | [6 empty] | F
COL-23 | Cent King | COL |  |  | X | X | [5 empty] | X | X | [6 empty] | F
COL-24 | Cent King | COL |  |  | X | X | [5 empty] | X | X |  | 2025 |  |  |  |  | F
COL-25 | Cent King | COL |  | X | X | X | [5 empty] | X | X | [6 empty] | F
COL-26 | Cent King | COL |  | X | X | X | [5 empty] | X | X |  |  |  | 2024 |  |  | F | X
COT-13 | North King | COT |  |  | X | X | [5 empty] | X | X | [7 empty] | X | 2024 |  |  |  |  | 2023
COT-15 | North King | COT |  |  | X | X | [5 empty] | X | X
COT-16 | North King | COT |  |  | X | X | [5 empty] | X | X |  | 2025 |  | 2023
COT-17 | North King | COT |  |  | X | X | [5 empty] | X | X |  | 2025
CPV-12 | Island | CPV |  |  | X | X | [5 empty] | X | X |  | 2025
CPV-13 | Island | CPV |  |  | X | X | [5 empty] | X | X |  | 2024
CPV-15 | Island | CPV |  |  | X | X | [5 empty] | X | X |  | 2023 |  | 2023 | [10 empty] | 2023
CRE-12 | Island | CRE |  |  | X | X | [5 empty] | X | X | [5 empty] | 2024 |  | X
CRE-13 | Island | CRE |  | X | X | X | [5 empty] | X | X |  | 2025 |  | 2025 |  | 2024
CRE-15 | Island | CRE |  |  | X | X | [5 empty] | X | X |  |  |  | 2024 |  | 2024
CRE-16 | Island | CRE |  |  | X | X | [5 empty] | X | X |  | 2025 |  | 2023 |  | 2024 |  | X | [5 empty] | 2023
CTR-21 | South King | CTR | X |  | X | X | [5 empty] | X | X
CTR-22 | South King | CTR | X |  | X | X | [5 empty] | X | X |  | 2024 | [5 empty] | X
CTR-23 | South King | CTR | X |  | X | X | [5 empty] | X | X
CTR-24 | South King | CTR | X |  | X | X | [5 empty] | X | X |  | 2025
CTR-25 | South King | CTR | X |  | X | X | [5 empty] | X | X |  | 2025
CUM-13 | South King | CUM |  |  | X | X | [5 empty] | X | X |  |  |  | 2024 |  |  |  | X
CUM-14 | South King | CUM |  |  | X | X | [5 empty] | X | X
CUM-15 | South King | CUM |  |  | X | X | [5 empty] | X | X |  |  | X | 2025 | [5 empty] | 2023 | 2023 |  |  | 2023
CUS-13 | Whatcom | CUS |  |  | X | X | [5 empty] | X | X |  | 2025 |  | 2025 |  |  | F | [9 empty] | 2024
CUS-14 | Whatcom | CUS |  |  | X | X | [5 empty] | X | X | [6 empty] | F | [9 empty] | 2024
CUS-15 | Whatcom | CUS |  | X | X | X | [5 empty] | X | X | [6 empty] | F | X | [8 empty] | 2024
CUS-16 | Whatcom | CUS |  |  | X | X | [5 empty] | X | X | [6 empty] | F | X | [8 empty] | 2024
CWD-22 | North King | CWD |  |  | X | X | [5 empty] | X | X |  | 2025 |  |  |  |  | F | [7 empty] | 2023
CWD-23 | North King | CWD |  |  | X | X | [5 empty] | X | X |  | 2025 |  |  |  |  | F
CWD-24 | North King | CWD |  |  | X | X | [5 empty] | X | X |  | 2025 |  |  |  |  | F | [7 empty] | 2023
CWD-25 | North King | CWD |  |  | X | X | [5 empty] | X | X | [6 empty] | F
DEC-13 | Thurston | DEC |  |  | X | X | [5 empty] | X | X |  | 2025 | X |  |  | 2024 | 2024
DEC-15 | Thurston | DEC |  |  | X | X | [5 empty] | X | X |  | 2024 |  |  |  | 2024 | 2024
DEC-16 | Thurston | DEC |  |  | X | X | [5 empty] | X | X | [5 empty] | 2024 | 2024 | X
DEC-17 | Thurston | DEC |  |  | X | X | [5 empty] | X | X |  | 2024 | X |  |  | 2024 | 2024
DES-12 | South King | DES | X | X | X | X | [5 empty] | X | X |  | 2023 |  | 2025 |  |  | F
DES-13 | South King | DES | X | X | X | X | [5 empty] | X | X |  |  |  | 2025 |  |  | F
DES-15 | South King | DES | X | X | X | X | [5 empty] | X | X | [6 empty] | F | [6 empty] | 2023
DES-16 | South King | DES | X |  | X | X | [5 empty] | X | X |  |  |  | 2023 |  |  | F
DGR-13 | Pierce | DGR |  |  | X | X |  |  |  |  | 2023 | X | X |  | 2025
DGR-15 | Pierce | DGR | X |  | X | X |  |  |  |  | 2023 | X | X
DGR-16 | Pierce | DGR | X | X | X | X |  |  |  |  | 2023 | X | X |  |  |  | 2025
DGR-17 | Pierce | DGR | X | X | X | X |  |  |  |  | 2023 | X | X
DUT-14 | Pierce | DUT |  |  | X | X | [5 empty] | X | X |  | 2025 |  | 2024 |  |  | F
DUT-15 | Pierce | DUT |  |  | X | X | [5 empty] | X | X | [6 empty] | F
DUT-16 | Pierce | DUT |  |  | X | X | [5 empty] | X | X |  | 2024 |  |  |  |  | F | [6 empty] | 2023
DUT-17 | Pierce | DUT |  |  | X | X | [5 empty] | X | X | [6 empty] | F
DUV-12 | North King | DUV |  |  | X | X | [5 empty] | X | X | [7 empty] | X |  |  |  |  | 2023
DUV-13 | North King | DUV |  |  | X | X | [5 empty] | X | X |  | 2025 |  | 2024 | [10 empty] | 2023
DUV-15 | North King | DUV |  |  | X | X | [5 empty] | X | X |  | 2025 | [6 empty] | 2023
DUV-16 | North King | DUV |  |  | X | X | [5 empty] | X | X
EAR-13 | South King | EAR | X | X | X | X |  |  | 2023 |  |  | X | X |  | 2025 |  |  |  |  | F
EAR-15 | South King | EAR | X | X | X | X |  |  | 2023 |  |  | X | X |  | 2025 |  |  |  |  | F
EAR-16 | South King | EAR | X | X | X | X |  |  | 2023 |  |  | X | X | [6 empty] | F
EAR-17 | South King | EAR | X | X | X | X |  |  | 2023 |  |  | X | X |  | 2025 |  | 2025 |  |  | F
EDG-12 | Pierce | EDG | X |  | X | X |  |  |  |  | C | X | X |  | 2025 |  |  |  |  | F
EDG-13 | Pierce | EDG | X |  | X | X |  |  |  |  | C | X | X |  | 2025 |  | 2025 |  |  | F
EDG-15 | Pierce | EDG | X |  | X | X |  |  |  |  | C | X | X | [6 empty] | F | [7 empty] | 2023
EDG-16 | Pierce | EDG | X | X | X | X |  |  |  |  | C | X | X |  | 2025 |  |  |  |  | F
EGT-11 | Cent King | EGT |  |  | X | X | [5 empty] | X | X |  | 2024 | [5 empty] | X
EGT-12 | Cent King | EGT |  |  | X | X | [5 empty] | X | X |  | 2023
EGT-13 | Cent King | EGT |  |  | X | X | [5 empty] | X | X
EGT-15 | Cent King | EGT |  |  | X | X | [5 empty] | X | X |  | 2025 | [13 empty] | C
EGT-16 | Cent King | EGT |  |  | X | X | [5 empty] | X | X |  | 2025 |  | 2025
EGT-25 | Cent King | EGT |  |  | X | X | [5 empty] | X | X |  |  |  | 2023
EGT-26 | Cent King | EGT |  |  | X | X | [5 empty] | X | X
EGT-27 | Cent King | EGT |  |  | X | X | [5 empty] | X | X |  |  |  | 2024 | [10 empty] | 2023
EGT-28 | Cent King | EGT |  |  | X | X | [5 empty] | X | X | [7 empty] | X | [6 empty] | 2023
ELD-23 | Thurston | ELD |  |  | X | X | [5 empty] | X | X |  |  | X | 2023 |  | 2023 | 2023 | [9 empty] | 2025
ELD-25 | Thurston | ELD |  |  | X | X | [5 empty] | X | X |  |  | 2023 |  |  | 2023 | 2023 |  | 2024 | [7 empty] | 2025
ELD-26 | Thurston | ELD |  |  | X | X | [5 empty] | X | X |  |  | X |  |  | 2023 | 2023 | [9 empty] | 2025
ELD-27 | Thurston | ELD |  |  | X | X | [5 empty] | X | X |  |  | X |  |  | 2023 | 2023 | [8 empty] | 2023 | 2025
ELL-12 | South King | ELL | X | X | X | X |  |  |  | P |  | X | X |  | 2025 |  | 2025 |  | 2025 | 2024
ELL-13 | South King | ELL | X | X | X | X |  |  |  | P |  | X | X |  | 2025 |  | 2024 |  | 2025 | 2024 | [7 empty] | 2023
ELL-14 | South King | ELL | X | X | X | X |  |  |  | P |  | X | X |  | 2025 |  | 2023 |  | 2025 | 2024
ELL-15 | South King | ELL | X | X | X | X |  |  |  | P |  | X | X |  | 2025 |  |  |  | 2025 | 2024
ELL-16 | South King | ELL | X | X | X | X |  |  |  | P |  | X | X |  | 2025 |  |  |  | 2025 | 2024 | [7 empty] | 2023
ENU-15 | South King | ENU |  |  | X | X | [5 empty] | X | X |  | 2023 |  |  |  | 2024
ENU-16 | South King | ENU |  |  | X | X | [5 empty] | X | X | [5 empty] | 2024 | [8 empty] | 2023
ENU-17 | South King | ENU |  |  | X | X | [5 empty] | X | X |  | 2023 |  | 2025 |  | 2024 | [8 empty] | 2023
ENU-18 | South King | ENU | X | X | X | X | [5 empty] | X | X |  | 2023 |  |  |  | 2024
EPO-12 | Kitsap | EPO |  |  | X | X | [5 empty] | X | X |  | 2025 |  | 2025 |  | 2023 | 2023 |  |  | 2023
EPO-13 | Kitsap | EPO |  |  | X | X | [5 empty] | X | X |  | 2025 |  | 2024 |  | 2023 | 2023 | [6 empty] | 2023 |  | 2023
EPO-15 | Kitsap | EPO |  |  | X | X | [5 empty] | X | X |  | 2025 |  | 2025 |  | 2023 | 2023
EPO-16 | Kitsap | EPO |  |  | X | X | [5 empty] | X | X |  | 2025 |  |  |  | 2023 | 2023 |  |  | 2023 |  |  |  | 2023
ETN-13 | Kittitas | ETN |  |  | X | X |  | P |  |  |  | X | X |  |  | 2023 |  |  | 2025 | F | X
ETN-15 | Kittitas | ETN |  |  | X | X |  | P |  |  |  | X | X |  |  | 2023 |  |  | 2025 | F | [8 empty] | C
EVA-17 | South King | EVA | X | X | X | X | [5 empty] | X | X | [5 empty] | 2024 | F
EVA-23 | South King | EVA | X | X | X | X | [5 empty] | X | X |  |  |  | 2024 |  | 2024 | F
EVA-25 | South King | EVA | X | X | X | X | [5 empty] | X | X | [5 empty] | 2024 | F
EVA-26 | South King | EVA | X | X | X | X | [5 empty] | X | X | [5 empty] | 2024 | F
EVA-27 | South King | EVA | X | X | X | X | [5 empty] | X | X | [5 empty] | 2024 | F
EVE-13 | North King | EVE |  |  | X | X | [5 empty] | X | X
EVE-15 | North King | EVE |  |  | X | X | [5 empty] | X | X
EVE-16 | North King | EVE |  |  | X | X | [5 empty] | X | X
EVE-17 | North King | EVE |  |  | X | X | [5 empty] | X | X
EVE-22 | North King | EVE |  |  | X | X | [5 empty] | X | X
EVE-23 | North King | EVE |  |  | X | X | [5 empty] | X | X | [7 empty] | X
EVE-25 | North King | EVE |  |  | X | X | [5 empty] | X | X
EVE-26 | North King | EVE |  |  | X | X | [5 empty] | X | X
FAB-13 | Island | FAB |  | X | X | X |  |  |  | P |  | X | X | [6 empty] | 2025
FAB-15 | Island | FAB |  | X | X | X |  |  |  | P |  | X | X |  | 2024 |  |  |  |  | 2025
FAB-16 | Island | FAB |  | X | X | X |  |  |  | P |  | X | X |  | 2025 |  |  |  |  | 2025
FAB-17 | Island | FAB |  | X | X | X |  |  |  | P |  | X | X |  | 2024 |  |  |  |  | 2025
FAC-11 | Cent King | FAC |  |  | X | X | [5 empty] | X | X | [6 empty] | F
FAC-12 | Cent King | FAC |  |  | X | X | [5 empty] | X | X | [6 empty] | F | X
FAC-13 | Cent King | FAC |  |  | X | X | [5 empty] | X | X |  |  |  | 2023 |  |  | F
FAC-14 | Cent King | FAC |  |  | X | X | [5 empty] | X | X | [6 empty] | F
FAC-15 | Cent King | FAC |  |  | X | X | [5 empty] | X | X |  | 2025 |  |  |  |  | F
FAC-21 | Cent King | FAC |  |  | X | X | [5 empty] | X | X | [6 empty] | F
FAC-23 | Cent King | FAC |  |  | X | X | [5 empty] | X | X |  |  |  | 2025 |  |  | F
FAC-24 | Cent King | FAC |  |  | X | X | [5 empty] | X | X | [6 empty] | F
FAC-25 | Cent King | FAC |  |  | X | X | [5 empty] | X | X | [6 empty] | F
FAL-13 | East King | FAL |  |  | X | X |  |  | 2023 |  |  | X | X |  | 2023 | [12 empty] | 2023
FAL-15 | East King | FAL |  |  | X | X |  |  | 2023 |  |  | X | X | [7 empty] | X |  |  |  |  | 2023
FAL-16 | East King | FAL |  |  | X | X |  |  | 2023 |  |  | X | X |  |  |  | 2025 |  |  |  | X | [6 empty] | 2023
FCH-16 | Pierce | FCH |  | X | X | X |  |  | 2023 |  |  | X | X |  | 2025 |  |  |  |  | F
FCH-17 | Pierce | FCH |  | X | X | X |  |  | 2023 |  |  | X | X | [6 empty] | F
FCH-23 | Pierce | FCH |  | X | X | X |  |  | 2023 |  |  | X | X | [6 empty] | F
FCH-24 | Pierce | FCH |  | X | X | X |  |  | 2023 |  |  | X | X |  | 2025 |  |  |  |  | F
FCH-26 | Pierce | FCH |  | X | X | X |  |  | 2023 |  |  | X | X | [6 empty] | F
FCR-11 | South King | FCR |  |  | X | X | [5 empty] | X | X |  | 2025
FCR-12 | South King | FCR | X |  | X | X | [5 empty] | X | X |  | 2024 | [12 empty] | 2023
FCR-13 | South King | FCR |  |  | X | X | [5 empty] | X | X |  | 2023
FCR-14 | South King | FCR |  |  | X | X | [5 empty] | X | X |  | 2025
FLC-14 | South King | FLC | X | X | X | X | [5 empty] | X | X |  | 2024 |  |  |  |  | F
FLC-15 | South King | FLC | X | X | X | X | [5 empty] | X | X | [6 empty] | F
FLC-16 | South King | FLC | X | X | X | X | [5 empty] | X | X |  | 2024 |  |  |  |  | F
FLC-17 | South King | FLC | X | X | X | X | [5 empty] | X | X |  | 2024 |  |  |  |  | F
FLD-12 | Island | FLD |  |  | X | X | [5 empty] | X | X | [8 empty] | 2024 | [6 empty] | C
FLD-13 | Island | FLD |  |  | X | X | [5 empty] | X | X | [14 empty] | 2023
FLD-15 | Island | FLD |  |  | X | X | [5 empty] | X | X | [7 empty] | X | 2024
FNW-13 | Kitsap | FNW |  |  | X | X | [5 empty] | X | X |  | 2025 |  | 2024 |  |  |  | X |  | 2024
FNW-15 | Kitsap | FNW |  |  | X | X | [5 empty] | X | X |  |  |  | 2024 |  |  |  | X
FNW-16 | Kitsap | FNW |  |  | X | X | [5 empty] | X | X |  |  |  | 2023
FNW-17 | Kitsap | FNW |  |  | X | X | [5 empty] | X | X |  | 2025 | [5 empty] | X
FRA-12 | Kitsap | FRA |  |  | X | X | [5 empty] | X | X |  |  |  | 2023 |  |  |  | X | [6 empty] | 2023
FRA-13 | Kitsap | FRA |  |  | X | X | [5 empty] | X | X |  | 2023 | [12 empty] | 2023
FRA-15 | Kitsap | FRA |  |  | X | X | [5 empty] | X | X
FRA-16 | Kitsap | FRA |  |  | X | X | [5 empty] | X | X
FRG-22 | Thurston | FRG |  |  | X | X | [5 empty] | X | X |  | 2024 | X | 2025 | [10 empty] | 2023
FRG-23 | Thurston | FRG |  |  | X | X | [5 empty] | X | X |  |  | X | 2024 | [11 empty] | 2023
FRG-24 | Thurston | FRG |  |  | X | X | [5 empty] | X | X |  |  | X | [11 empty] | 2023
FRG-25 | Thurston | FRG |  |  | X | X | [5 empty] | X | X |  | 2024 | 2023 | 2023
FRU-22 | Pierce | FRU |  | X | X | X | [5 empty] | X | X |  | 2024
FRU-23 | Pierce | FRU |  |  | X | X | [5 empty] | X | X
FRU-25 | Pierce | FRU |  |  | X | X | [5 empty] | X | X |  | 2025 |  | 2023 | [11 empty] | 2023
FRU-26 | Pierce | FRU |  | X | X | X | [5 empty] | X | X |  | 2025 | [11 empty] | 2023
FWD-13 | South King | FWD | X |  | X | X | [5 empty] | X | X |  | 2025 |  | 2023
FWD-15 | South King | FWD |  |  | X | X | [5 empty] | X | X
FWD-16 | South King | FWD | X |  | X | X | [5 empty] | X | X |  | 2024 | [5 empty] | X
FWD-17 | South King | FWD | X |  | X | X | [5 empty] | X | X |  | 2024 | [10 empty] | 2023
FWY-11 | South King | FWY | X | X | X | X | [5 empty] | X | X |  | 2023 |  | 2023 |  |  | F | [7 empty] | 2023
FWY-12 | South King | FWY | X | X | X | X | [5 empty] | X | X | [6 empty] | F
FWY-13 | South King | FWY | X | X | X | X | [5 empty] | X | X |  | 2023 |  | 2025 |  |  | F
FWY-15 | South King | FWY | X | X | X | X | [5 empty] | X | X |  | 2024 |  |  |  |  | F
GAG-11 | Skagit | GAG |  | X | X | X | [5 empty] | X | X |  | 2025
GAG-12 | Skagit | GAG |  | X | X | X | [5 empty] | X | X |  | 2025
GAG-13 | Skagit | GAG |  | X | X | X | [5 empty] | X | X |  | 2025
GAG-14 | Skagit | GAG |  | X | X | X | [5 empty] | X | X |  | 2024
GAG-15 | Skagit | GAG |  |  | X | X | [5 empty] | X | X
GAR-12 | Pierce | GAR | X |  | X | X | [5 empty] | X | X
GAR-13 | Pierce | GAR | X |  | X | X | [5 empty] | X | X | [14 empty] | 2023
GAR-15 | Pierce | GAR | X |  | X | X | [5 empty] | X | X |  | 2023 |  | 2024
GAR-16 | Pierce | GAR |  |  | X | X | [5 empty] | X | X
GBK-12 | Island | GBK |  |  | X | X | [5 empty] | X | X
GBK-13 | Island | GBK |  |  | X | X | [5 empty] | X | X |  | 2023 | [5 empty] | X | 2024
GBK-15 | Island | GBK |  |  | X | X |  | P |  |  |  | X | X |  | 2023 |  | 2024
GLA-12 | Whatcom | GLA | X | X | X | X | [5 empty] | X | X | [7 empty] | X | [8 empty] | 2023
GLA-13 | Whatcom | GLA |  |  | X | X | [5 empty] | X | X | [16 empty] | 2023
GLC-11 | South King | GLC | X | X | X | X | [5 empty] | X | X |  | 2024
GLC-12 | South King | GLC | X | X | X | X | [5 empty] | X | X |  | 2024
GLC-13 | South King | GLC | X | X | X | X | [5 empty] | X | X |  | 2025
GLC-14 | South King | GLC | X | X | X | X | [5 empty] | X | X
GLC-15 | South King | GLC | X | X | X | X | [5 empty] | X | X |  | 2024
GOO-13 | East King | GOO |  |  | X | X | [5 empty] | X | X |  | 2025 |  |  |  |  | 2024
GOO-15 | East King | GOO |  |  | X | X | [5 empty] | X | X | [6 empty] | 2024
GOO-16 | East King | GOO |  |  | X | X | [5 empty] | X | X | [6 empty] | 2024
GOO-17 | East King | GOO |  |  | X | X | [5 empty] | X | X | [6 empty] | 2024
GOO-21 | East King | GOO |  |  | X | X | [5 empty] | X | X |  | 2025 |  |  |  |  | 2024
GRA-14 | South King | GRA | X |  | X | X |  |  |  | P |  | X | X | [6 empty] | 2024
GRA-15 | South King | GRA | X |  | X | X |  |  |  | P |  | X | X |  |  |  | 2025 |  |  | 2024
GRA-16 | South King | GRA | X |  | X | X |  |  |  | P |  | X | X |  |  |  | 2023 |  |  | 2024
GRA-17 | South King | GRA | X |  | X | X |  |  |  | P |  | X | X | [6 empty] | 2024
GRA-25 | South King | GRA | X | X | X | X |  |  |  | P |  | X | X | [6 empty] | 2024 | X
GRA-26 | South King | GRA | X | X | X | X |  |  |  | P |  | X | X | [6 empty] | 2024
GRI-13 | Thurston | GRI |  |  | X | X | [5 empty] | X | X |  |  | 2023 |  |  |  |  | X | 2024 |  |  |  |  | 2023 |  |  | 2025
GRI-15 | Thurston | GRI |  |  | X | X | [5 empty] | X | X |  |  | X | 2025 |  |  |  | X | [8 empty] | 2025
GRI-16 | Thurston | GRI |  |  | X | X | [5 empty] | X | X |  |  | 2023 |  |  |  |  | X | [8 empty] | 2025
GRV-12 | Pierce | GRV |  | X | X | X |  |  |  | P |  | X | X |  | 2025 |  | 2024 |  |  | 2023
GRV-13 | Pierce | GRV |  |  | X | X | [5 empty] | X | X |  | 2024 |  |  |  |  | 2023
GRV-15 | Pierce | GRV | X | X | X | X |  |  |  | P |  | X | X |  | 2025 |  |  |  |  | 2023
GRV-16 | Pierce | GRV |  |  | X | X | [5 empty] | X | X |  | 2024 |  | 2024 |  |  | 2023
GWR-13 | South King | GWR |  |  | X | X | [5 empty] | X | X |  | 2025 | X
GWR-16 | South King | GWR |  |  | X | X | [5 empty] | X | X |  | 2025 | X
HAM-13 | Skagit | HAM |  |  | X | X | [5 empty] | X | X |  | 2025 |  |  |  | 2023 | 2023
HAM-15 | Skagit | HAM | X |  | X | X |  |  |  | P |  | X | X |  | 2025 |  |  |  | 2023 | 2023 |  | 2023
HAN-12 | Whatcom | HAN |  |  | X | X | [5 empty] | X | X |  | 2025 |  | 2025 | [10 empty] | 2023
HAN-13 | Whatcom | HAN |  |  | X | X | [5 empty] | X | X | [7 empty] | X
HAN-15 | Whatcom | HAN |  |  | X | X | [5 empty] | X | X |  | 2025 | [5 empty] | X
HAN-16 | Whatcom | HAN | X |  | X | X | [5 empty] | X | X |  |  |  | 2023 |  |  |  | X
HAP-12 | Whatcom | HAP |  |  | X | X | [5 empty] | X | X | [6 empty] | 2024 | [9 empty] | 2024
HAP-13 | Whatcom | HAP |  | X | X | X |  |  |  | P |  | X | X | [6 empty] | 2024 | X | [8 empty] | 2024
HAP-15 | Whatcom | HAP |  | X | X | X |  |  |  | P |  | X | X | [6 empty] | 2024 | [9 empty] | 2024
HAP-16 | Whatcom | HAP |  | X | X | X |  |  |  | P |  | X | X | [6 empty] | 2024 |  | 2023 | [7 empty] | 2024
HAR-15 | South King | HAR | X | X | X | X | [5 empty] | X | X |  |  |  | 2025 |  |  | F
HAR-16 | South King | HAR | X | X | X | X | [5 empty] | X | X | [6 empty] | F
HAR-17 | South King | HAR | X | X | X | X | [5 empty] | X | X |  | 2025 |  |  |  |  | F
HAR-18 | South King | HAR | X | X | X | X | [5 empty] | X | X | [6 empty] | F
HAR-22 | South King | HAR | X | X | X | X | [5 empty] | X | X |  |  |  | 2024 |  |  | F
HAR-23 | South King | HAR | X | X | X | X | [5 empty] | X | X |  | 2025 |  |  |  |  | F
HAR-24 | South King | HAR | X | X | X | X | [5 empty] | X | X | [6 empty] | F
HAR-25 | South King | HAR | X | X | X | X | [5 empty] | X | X | [6 empty] | F
HAR-26 | South King | HAR | X | X | X | X | [5 empty] | X | X | [6 empty] | F
HAW-11 | Thurston | HAW |  | X | X | X | [5 empty] | X | X |  | 2023 | X |  |  |  |  | X |  | 2025 |  |  |  |  | 2023
HAW-12 | Thurston | HAW | X | X | X | X | [5 empty] | X | X |  |  | X | [12 empty] | 2023
HAW-13 new | Thurston | HAW |  |  | X | X | [5 empty] | X | X
HAW-14 | Thurston | HAW |  |  | X | X | [5 empty] | X | X |  |  | X
HAZ-12 | Cent King | HAZ |  |  | X | X | [5 empty] | X | X |  | 2024
HAZ-13 | Cent King | HAZ |  |  | X | X | [5 empty] | X | X |  | 2023 | [13 empty] | C
HAZ-15 | Cent King | HAZ |  |  | X | X | [5 empty] | X | X |  | 2023 |  | 2024 | [10 empty] | 2023
HAZ-16 | Cent King | HAZ |  |  | X | X | [5 empty] | X | X |  | 2023 | [12 empty] | 2023
HEM-13 | Pierce | HEM |  | X | X | X |  |  | 2023 |  | C | X | X |  | 2024 |  | 2025 | [11 empty] | 2023
HEM-15 | Pierce | HEM |  |  | X | X |  |  | 2023 |  | C | X | X |  | 2023 | [12 empty] | 2023
HEM-16 | Pierce | HEM |  |  | X | X |  |  | 2023 |  | C | X | X |  | 2023
HEM-17 | Pierce | HEM |  |  | X | X |  |  | 2023 |  | C | X | X |  | 2025 | [7 empty] | 2023
HIG-13 | Cent King | HIG | X | X | X | X | [5 empty] | X | X |  | 2025 |  | 2023 |  |  | F
HIG-15 | Cent King | HIG | X | X | X | X | [5 empty] | X | X |  | 2025 |  |  |  |  | F
HIG-16 | Cent King | HIG | X | X | X | X | [5 empty] | X | X |  | 2025 |  | 2023 |  |  | F
HIG-17 | Cent King | HIG | X | X | X | X | [5 empty] | X | X |  | 2025 |  | 2023 |  |  | F
HKX-12 | Skagit | HKX |  |  | X | X | [5 empty] | X | X
HKX-13 | Skagit | HKX |  |  | X | X | [5 empty] | X | X |  | 2025 |  | 2025
HKX-15 | Skagit | HKX |  |  | X | X | [5 empty] | X | X
HKX-16 | Skagit | HKX |  |  | X | X | [5 empty] | X | X | [7 empty] | X | 2024
HLC-23 | Island | HLC |  | X | X | X |  |  |  | P |  | X | X |  |  |  | 2025 |  |  | 2025 | [6 empty] | 2023
HLC-24 | Island | HLC |  | X | X | X |  |  |  | P |  | X | X |  | 2024 |  |  |  |  | 2025
HLC-25 | Island | HLC |  | X | X | X |  |  |  | P |  | X | X |  | 2024 |  |  |  |  | 2025
HLC-26 | Island | HLC |  | X | X | X |  |  |  | P |  | X | X |  | 2025 |  |  |  |  | 2025
HOB-15 | South King | HOB |  |  | X | X | [5 empty] | X | X
HOB-16 | South King | HOB |  |  | X | X | [5 empty] | X | X |  | 2023 | [5 empty] | X | 2025
HOB-17 | South King | HOB |  |  | X | X | [5 empty] | X | X |  | 2025 |  | 2024 |  |  |  | X |  | 2025 |  |  |  |  | 2023
HOL-12 | Pierce | HOL |  |  | X | X | [5 empty] | X | X |  | 2023 |  |  |  |  | F
HOL-13 | Pierce | HOL |  |  | X | X | [5 empty] | X | X |  | 2024 |  |  |  |  | F | X
HOL-15 | Pierce | HOL |  |  | X | X | [5 empty] | X | X |  | 2023 |  | 2024 |  |  | F |  |  | 2023
HOU-23 | North King | HOU |  |  | X | X | [5 empty] | X | X | [6 empty] | 2025
HOU-25 | North King | HOU |  |  | X | X | [5 empty] | X | X | [6 empty] | 2025 | [8 empty] | 2023
HOU-26 | North King | HOU |  |  | X | X | [5 empty] | X | X | [6 empty] | 2025
HOU-27 | North King | HOU |  |  | X | X | [5 empty] | X | X |  | 2025 |  |  |  |  | 2025
HWD-22 | North King | HWD |  |  | X | X | [5 empty] | X | X | [5 empty] | 2023 | [9 empty] | 2023 | 2025
HWD-23 | North King | HWD |  |  | X | X | [5 empty] | X | X | [5 empty] | 2023 | [10 empty] | 2025
HWD-25 | North King | HWD |  |  | X | X | [5 empty] | X | X |  | 2025 |  | 2023 |  | 2023 | [10 empty] | 2025
HWD-26 | North King | HWD |  |  | X | X | [5 empty] | X | X |  |  |  | 2023 |  | 2023 | [10 empty] | 2025
HYA-13 | Kittitas | HYA |  |  | X | X |  | P |  |  |  | X | X |  | 2025 |  |  |  |  | 2023 | [6 empty] | 2023
HYA-15 | Kittitas | HYA |  |  | X | X |  | P |  |  |  | X | X |  | 2025 |  |  |  |  | 2023
ING-13 | North King | ING |  |  | X | X |  |  | 2023 |  |  | X | X | [7 empty] | X
ING-15 | North King | ING |  |  | X | X |  | P | 2023 |  |  | X | X |  | 2024
ING-16 | North King | ING |  |  | X | X |  |  | 2023 |  |  | X | X |  |  |  | 2025 | [11 empty] | 2023
ING-17 | North King | ING |  |  | X | X |  |  | 2023 |  |  | X | X |  | 2025 | [13 empty] | 2023
JHO-12 | Thurston | JHO |  |  | X | X | [5 empty] | X | X |  | 2023 | X |  |  |  | F | [9 empty] | 2023
JHO-13 | Thurston | JHO |  |  | X | X | [5 empty] | X | X |  | 2024 |  |  |  |  | F | [9 empty] | 2023
JHO-15 | Thurston | JHO |  |  | X | X | [5 empty] | X | X |  | 2025 | X |  |  |  | F | [9 empty] | 2023
JHO-16 | Thurston | JHO |  |  | X | X | [5 empty] | X | X |  | 2024 |  |  |  |  | F | [9 empty] | 2023
JUA-11 | North King | JUA |  |  | X | X | [5 empty] | X | X |  | 2025
JUA-12 | North King | JUA |  |  | X | X | [5 empty] | X | X |  | 2025
JUA-13 | North King | JUA |  |  | X | X | [5 empty] | X | X |  | 2025
JUA-14 | North King | JUA |  |  | X | X | [5 empty] | X | X |  | 2025
JUA-15 | North King | JUA |  |  | X | X | [5 empty] | X | X |  | 2025
JUA-21 | North King | JUA |  |  | X | X | [5 empty] | X | X
JUA-22 | North King | JUA |  |  | X | X | [5 empty] | X | X
JUA-23 | North King | JUA |  |  | X | X | [5 empty] | X | X
JUA-24 | North King | JUA |  |  | X | X | [5 empty] | X | X
JUA-25 | North King | JUA |  |  | X | X | [5 empty] | X | X |  |  |  | 2023
KAP-13 | Pierce | KAP |  |  | X | X | [5 empty] | X | X | [5 empty] | 2025
KAP-15 | Pierce | KAP |  |  | X | X | [5 empty] | X | X | [5 empty] | 2025 | [7 empty] | 2023
KAP-16 | Pierce | KAP |  |  | X | X |  | P |  |  |  | X | X | [5 empty] | 2025 |  | X | [5 empty] | 2023
KCR-13 | South King | KCR | X | X | X | X |  |  |  | P |  | X | X | [6 empty] | 2025 | [9 empty] | 2024
KCR-15 | South King | KCR | X | X | X | X |  |  |  | P |  | X | X |  | 2025 |  |  |  |  | 2025 | [9 empty] | 2024
KCR-16 | South King | KCR | X | X | X | X |  |  |  | P |  | X | X |  | 2024 |  |  |  |  | 2025 |  |  |  | 2023 |  | 2023 |  | 2023 |  | 2024
KCR-17 | South King | KCR | X | X | X | X |  |  |  | P |  | X | X |  | 2025 |  | 2024 |  |  | 2025 | [9 empty] | 2024
KEN-12 | Whatcom | KEN | X | X | X | X | [5 empty] | X | X | [5 empty] | 2023 |  | X | 2023 | [7 empty] | 2023
KEN-13 | Whatcom | KEN | X | X | X | X | [5 empty] | X | X |  | 2025 |  |  |  | 2023 |  | X | [8 empty] | 2023
KIN-21 | Kitsap | KIN | X |  | X | X | [5 empty] | X | X | [7 empty] | X |  |  | 2023
KIN-22 | Kitsap | KIN | X |  | X | X | [5 empty] | X | X |  | 2025
KIN-23 | Kitsap | KIN | X |  | X | X | [5 empty] | X | X |  | 2025
KIN-24 | Kitsap | KIN | X |  | X | X | [5 empty] | X | X |  | 2025
KIN-25 | Kitsap | KIN |  |  | X | X | [5 empty] | X | X
KIT-22 | Kittitas | KIT |  | X | X | X |  | P |  |  |  | X | X |  | 2023 | X | 2024 |  |  | F | X
KIT-25 | Kittitas | KIT |  | X | X | X |  | P |  |  |  | X | X |  | 2025 | 2023 |  |  |  | F | X
KIT-26 | Kittitas | KIT |  |  | X | X |  | P |  |  |  | X | X |  | 2025 | 2023 | 2023 |  |  | F | X |  | 2023
KLA-15 | East King | KLA |  |  | X | X | [5 empty] | X | X |  | 2024 |  |  |  |  | 2025 | [8 empty] | C
KLA-16 | East King | KLA |  |  | X | X | [5 empty] | X | X | [6 empty] | 2025
KLA-17 | East King | KLA |  |  | X | X | [5 empty] | X | X |  | 2024 |  |  |  |  | 2025 | X
KLA-18 | East King | KLA |  |  | X | X | [5 empty] | X | X |  | 2024 |  |  |  |  | 2025
KNM-23 | North King | KNM |  |  | X | X | [5 empty] | X | X | [7 empty] | X | [6 empty] | 2023
KNM-25 | North King | KNM |  |  | X | X | [5 empty] | X | X |  | 2025 |  | 2023
KNM-26 | North King | KNM |  |  | X | X | [5 empty] | X | X | [7 empty] | X | [6 empty] | 2023
KNM-27 | North King | KNM |  |  | X | X | [5 empty] | X | X |  | 2023
KNO-11 | Pierce | KNO |  |  | X | X | [5 empty] | X | X
KNO-12 | Pierce | KNO |  |  | X | X | [5 empty] | X | X
KNO-13 | Pierce | KNO |  |  | X | X | [5 empty] | X | X | [7 empty] | X
KNO-14 | Pierce | KNO |  |  | X | X | [5 empty] | X | X
KNT-23 | South King | KNT | X |  | X | X |  |  | 2023 | P |  | X | X |  | 2025 |  | 2024 |  | 2023 | 2023
KNT-25 | South King | KNT | X | X | X | X |  |  | 2023 | P |  | X | X |  | 2025 |  |  |  | 2023 | 2023
KNT-26 | South King | KNT | X | X | X | X |  |  | 2023 | P |  | X | X |  | 2025 |  | 2025 |  | 2023 | 2023
KNT-27 | South King | KNT | X |  | X | X |  |  | 2023 | P |  | X | X |  | 2025 |  |  |  | 2023 | 2023
KNT-33 | South King | KNT | X | X | X | X |  |  | 2023 | P |  | X | X |  | 2025 |  |  |  | 2023 | 2023
KNT-35 | South King | KNT | X | X | X | X |  |  | 2023 | P |  | X | X |  | 2025 |  |  |  | 2023 | 2023
KNT-36 | South King | KNT | X | X | X | X |  |  | 2023 | P |  | X | X |  |  |  | 2025 |  | 2023 | 2023
KNT-37 | South King | KNT | X | X | X | X |  |  | 2023 | P |  | X | X |  | 2025 |  |  |  | 2023 | 2023 |  |  | 2024
KWH-22 | North King | KWH |  |  | X | X | [5 empty] | X | X |  |  |  | 2025 | [10 empty] | 2023
KWH-23 | North King | KWH |  |  | X | X | [5 empty] | X | X |  |  |  | 2023 | [10 empty] | 2023
KWH-24 | North King | KWH |  |  | X | X | [5 empty] | X | X
KWH-25 | North King | KWH |  |  | X | X | [5 empty] | X | X |  |  |  | 2024
KWH-26 | North King | KWH |  |  | X | X | [5 empty] | X | X |  | 2024
LAB-23 | Whatcom | LAB | X | X | X | X | [5 empty] | X | X |  | 2024 | [11 empty] | 2023
LAB-25 | Whatcom | LAB | X | X | X | X | [5 empty] | X | X |  | 2024 |  | 2025
LAB-26 | Whatcom | LAB | X | X | X | X | [5 empty] | X | X |  |  |  | 2024 | [5 empty] | 2024
LAB-27 | Whatcom | LAB | X | X | X | X | [5 empty] | X | X |  | 2024 |  | 2023
LAC-13 | Thurston | LAC |  |  | X | X | [5 empty] | X | X |  | 2024 | X | 2025 |  |  | 2025 | [7 empty] | 2023 |  | 2023
LAC-15 | Thurston | LAC |  |  | X | X | [5 empty] | X | X |  | 2025 |  |  |  |  | 2025 | [9 empty] | 2023
LAC-16 | Thurston | LAC |  |  | X | X | [5 empty] | X | X |  | 2025 |  |  |  |  | 2025 | [9 empty] | 2023
LAC-17 | Thurston | LAC |  |  | X | X | [5 empty] | X | X |  |  | X |  |  |  | 2025 | X | [8 empty] | 2023
LAT-13 | South King | LAT | X | X | X | X | [5 empty] | X | X |  | 2025
LAT-14 | South King | LAT | X | X | X | X | [5 empty] | X | X |  |  |  | 2023 |  |  |  | X |  |  | 2023 |  | 2023 | 2023 |  | 2023
LAT-15 | South King | LAT | X | X | X | X | [5 empty] | X | X |  | 2024 | [5 empty] | X
LAT-16 | South King | LAT | X | X | X | X | [5 empty] | X | X |  | 2025 |  | 2024
LAT-17 | South King | LAT | X | X | X | X | [5 empty] | X | X |  | 2025 | [8 empty] | 2023 |  | 2023 |  |  | 2023
LAU-11 | Whatcom | LAU | X | X | X | X | [5 empty] | X | X |  | 2025
LAU-12 | Whatcom | LAU | X | X | X | X | [5 empty] | X | X |  | 2025
LAU-13 | Whatcom | LAU | X | X | X | X |  | P |  |  |  | X | X |  | 2025
LAU-14 | Whatcom | LAU | X | X | X | X | [5 empty] | X | X |  | 2025
LAU-15 | Whatcom | LAU |  |  | X | X | [5 empty] | X | X
LEA-13 | South King | LEA | X | X | X | X |  |  | 2023 |  |  | X | X |  | 2025 | [5 empty] | X | [7 empty] | C
LEA-15 | South King | LEA | X | X | X | X |  |  | 2023 |  |  | X | X |  |  |  | 2023 | [5 empty] | 2023 |  |  |  | 2023 |  | C
LEA-16 | South King | LEA | X | X | X | X |  |  | 2023 |  |  | X | X |  | 2025 | [12 empty] | 2023
LEA-17 | South King | LEA | X | X | X | X |  |  | 2023 |  |  | X | X |  | 2025
LGY-12 | Island | LGY |  |  | X | X | [5 empty] | X | X |  | 2024 |  |  |  | 2025 |  | X | 2024
LGY-13 | Island | LGY |  |  | X | X | [5 empty] | X | X | [5 empty] | 2025
LGY-15 | Island | LGY |  |  | X | X | [5 empty] | X | X | [5 empty] | 2025
LGY-16 | Island | LGY |  |  | X | X | [5 empty] | X | X |  | 2024 |  |  |  | 2025 |  | X
LHL-22 | Cent King | LHL |  | X | X | X | [5 empty] | X | X |  | 2023
LHL-23 | Cent King | LHL |  |  | X | X | [5 empty] | X | X |  | 2023 |  | 2024
LHL-25 | Cent King | LHL |  |  | X | X | [5 empty] | X | X |  | 2023
LHL-26 | Cent King | LHL |  |  | X | X | [5 empty] | X | X |  | 2024
LLS-13 | Whatcom | LLS |  |  | X | X | [5 empty] | X | X | [5 empty] | 2023 | 2023
LLS-15 | Whatcom | LLS |  |  | X | X | [5 empty] | X | X | [5 empty] | 2023 | 2023 | X
LLS-16 | Whatcom | LLS |  |  | X | X | [5 empty] | X | X | [5 empty] | 2023 | 2023
LLS-17 | Whatcom | LLS |  |  | X | X | [5 empty] | X | X | [5 empty] | 2023 | 2023
LLT-13 | North King | LLT |  |  | X | X | [5 empty] | X | X | [5 empty] | 2023
LLT-15 | North King | LLT |  |  | X | X | [5 empty] | X | X | [5 empty] | 2023
LLT-16 | North King | LLT |  |  | X | X | [5 empty] | X | X | [5 empty] | 2023 |  | X
LLT-17 | North King | LLT |  |  | X | X | [5 empty] | X | X |  |  |  | 2025 |  | 2023 |  | X
LMC-23 | Cent King | LMC |  |  | X | X | [5 empty] | X | X |  | 2025 |  |  |  | 2024 | 2023 |  |  | 2023
LMC-25 | Cent King | LMC |  |  | X | X | [5 empty] | X | X |  | 2024 |  | 2025 |  | 2024 | 2023 | [8 empty] | 2023
LMC-26 | Cent King | LMC |  |  | X | X | [5 empty] | X | X | [5 empty] | 2024 | 2023
LMC-27 | Cent King | LMC |  |  | X | X | [5 empty] | X | X |  | 2025 |  | 2023 |  | 2024 | 2023 |  |  | 2025
LMD-12 | South King | LMD | X | X | X | X |  |  |  | P |  | X | X | [6 empty] | 2025
LMD-13 | South King | LMD | X | X | X | X |  |  |  | P |  | X | X |  |  |  | 2024 |  |  | 2025
LMD-15 | South King | LMD | X | X | X | X |  |  |  | P |  | X | X | [6 empty] | 2025 | X
LMD-16 | South King | LMD | X |  | X | X |  |  |  | P |  | X | X | [6 empty] | 2025 | X
LOC-20 | Cent King | LOC |  |  | X | X | [5 empty] | X | X
LOC-22 | Cent King | LOC |  |  | X | X | [5 empty] | X | X | [10 empty] | 2024
LOC-23 | Cent King | LOC |  |  | X | X | [5 empty] | X | X |  |  |  | 2023
LOC-24 | Cent King | LOC |  |  | X | X | [5 empty] | X | X
LOC-25 | Cent King | LOC |  |  | X | X | [5 empty] | X | X |  | 2025
LOC-26 | Cent King | LOC |  |  | X | X | [5 empty] | X | X |  | 2025
LOC-2N | Cent King | LOC |  |  | X | X | [5 empty] | X | X
LOC-30 | Cent King | LOC |  |  | X | X | [5 empty] | X | X
LOC-32 | Cent King | LOC |  |  | X | X | [5 empty] | X | X
LOC-33 | Cent King | LOC |  |  | X | X | [5 empty] | X | X |  |  |  | 2025
LOC-34 | Cent King | LOC |  |  | X | X | [5 empty] | X | X
LOC-35 | Cent King | LOC |  |  | X | X | [5 empty] | X | X
LOC-36 | Cent King | LOC |  |  | X | X | [5 empty] | X | X
LOC-3N | Cent King | LOC |  |  | X | X | [5 empty] | X | X
LOL-21 | Kitsap | LOL |  |  | X | X | [5 empty] | X | X |  | 2023 |  |  |  | 2025 |  | X
LOL-22 | Kitsap | LOL |  |  | X | X | [5 empty] | X | X |  | 2023 |  | 2025 |  | 2025
LOL-23 | Kitsap | LOL |  |  | X | X | [5 empty] | X | X |  | 2025 |  | 2023 |  | 2025
LOL-25 | Kitsap | LOL |  |  | X | X | [5 empty] | X | X |  | 2023 |  |  |  | 2025 |  |  |  | 2025 |  |  |  |  | 2023 | 2023
LON-17 | Thurston | LON |  |  | X | X | [5 empty] | X | X |  | 2023 |  |  |  | 2025 |  |  | 2024 | [5 empty] | 2023
LON-22 | Thurston | LON |  |  | X | X | [5 empty] | X | X |  | 2025 |  |  |  | 2025 | [7 empty] | 2023
LON-23 | Thurston | LON |  | X | X | X | [5 empty] | X | X | [5 empty] | 2025
LON-25 | Thurston | LON |  | X | X | X | [5 empty] | X | X | [5 empty] | 2025
LON-26 | Thurston | LON |  | X | X | X | [5 empty] | X | X |  | 2024 |  |  |  | 2025
LTA-16 | Pierce | LTA | X |  | X | X | [5 empty] | X | X |  | 2024
LTA-17 | Pierce | LTA | X |  | X | X | [5 empty] | X | X |  | 2025 | [6 empty] | 2024
LTA-18 | Pierce | LTA | X | X | X | X | [5 empty] | X | X |  | 2023 | [12 empty] | 2023
LUH-14 | Thurston | LUH |  |  | X | X |  | P |  |  |  | X | X |  | 2023 |  |  |  |  | 2025 | [7 empty] | 2023
LUH-15 | Thurston | LUH |  |  | X | X | [5 empty] | X | X |  | 2024 |  |  |  |  | 2025 | [8 empty] | 2023
LUH-17 | Thurston | LUH |  |  | X | X | [5 empty] | X | X |  | 2024 |  | 2025 |  |  | 2025 | [6 empty] | 2023
LWS-12 | South King | LWS | X |  | X | X | [5 empty] | X | X |  |  |  | 2023 | [9 empty] | 2023 | 2023
LWS-13 | South King | LWS | X |  | X | X | [5 empty] | X | X |  |  |  | 2024
LWS-14 | South King | LWS | X |  | X | X | [5 empty] | X | X
LWS-15 | South King | LWS | X |  | X | X | [5 empty] | X | X
LWS-16 | South King | LWS | X |  | X | X | [5 empty] | X | X | [7 empty] | X | [6 empty] | 2023 | 2023
LYN-13 | Whatcom | LYN | X |  | X | X | [5 empty] | X | X |  | 2024 |  |  |  |  | F
LYN-14 | Whatcom | LYN | X |  | X | X | [5 empty] | X | X |  | 2023 |  | 2023 |  |  | F |  |  | 2024
LYN-16 | Whatcom | LYN | X |  | X | X | [5 empty] | X | X |  | 2024 |  |  |  |  | F
LYN-17 | Whatcom | LYN | X |  | X | X | [5 empty] | X | X |  | 2023 |  | 2023 |  |  | F
LYN-23 | Whatcom | LYN | X |  | X | X |  | P |  |  |  | X | X |  | 2024 |  |  |  |  | F |  |  |  | 2023
LYN-24 | Whatcom | LYN | X |  | X | X |  | P |  |  |  | X | X |  | 2025 |  | 2024 |  |  | F | X
LYN-26 | Whatcom | LYN | X |  | X | X | [5 empty] | X | X |  | 2024 |  |  |  |  | F |  |  |  | 2024
LYN-27 | Whatcom | LYN |  |  | X | X | [5 empty] | X | X | [6 empty] | F
LYO-11 | South King | LYO |  |  | X | X | [5 empty] | X | X
LYO-12 | South King | LYO |  |  | X | X | [5 empty] | X | X |  | 2025 | [5 empty] | X
LYO-15 | South King | LYO | X |  | X | X | [5 empty] | X | X |  | 2025 | [5 empty] | X | [6 empty] | 2023 | 2023
MAN-12 | Kitsap | MAN |  |  | X | X | [5 empty] | X | X |  | 2025 | [5 empty] | X | [6 empty] | 2023
MAN-13 | Kitsap | MAN |  |  | X | X | [5 empty] | X | X | [15 empty] | 2023
MAN-15 | Kitsap | MAN |  |  | X | X | [5 empty] | X | X |  | 2025 |  | 2023
MAN-16 | Kitsap | MAN |  |  | X | X | [5 empty] | X | X | [14 empty] | 2023
MAP-13 | Cent King | MAP |  |  | X | X | [5 empty] | X | X | [5 empty] | 2024
MAP-15 | Cent King | MAP |  |  | X | X | [5 empty] | X | X | [5 empty] | 2024 |  | X | [6 empty] | 2023
MAP-16 | Cent King | MAP | X | X | X | X | [5 empty] | X | X |  |  |  | 2024 |  | 2024
MAP-17 | Cent King | MAP |  |  | X | X | [5 empty] | X | X | [5 empty] | 2024
MAX-11 | Island | MAX |  |  | X | X | [5 empty] | X | X
MAX-12 | Island | MAX |  |  | X | X | [5 empty] | X | X | [7 empty] | X
MAX-13 | Island | MAX |  |  | X | X | [5 empty] | X | X
MAX-14 | Island | MAX |  |  | X | X | [5 empty] | X | X
MAX-15 | Island | MAX |  |  | X | X | [5 empty] | X | X
MCA-13 | Thurston | MCA | X |  | X | X | [5 empty] | X | X |  | 2023 | X | 2023 |  |  | F | [7 empty] | 2023
MCA-15 | Thurston | MCA | X |  | X | X | [5 empty] | X | X |  | 2024 | X | 2023 |  |  | F
MCA-16 | Thurston | MCA | X | X | X | X | [5 empty] | X | X |  | 2023 | X | 2023 |  |  | F
MCK-12 | Whatcom | MCK |  | X | X | X | [5 empty] | X | X |  | 2025 | [14 empty] | 2024
MCK-13 | Whatcom | MCK |  |  | X | X | [5 empty] | X | X | [16 empty] | 2024
MCK-15 | Whatcom | MCK |  | X | X | X |  | P |  |  |  | X | X |  | 2024 | [12 empty] | 2023 |  | 2024
MCK-16 | Whatcom | MCK |  | X | X | X | [5 empty] | X | X |  | 2024 | [14 empty] | 2024
MCW-14 | Kitsap | MCW |  |  | X | X | [5 empty] | X | X |  | 2024 |  | 2025 |  | 2025 | 2025 | X
MCW-15 | Kitsap | MCW |  |  | X | X | [5 empty] | X | X |  | 2023 |  | 2025 |  | 2025 | 2025
MCW-16 | Kitsap | MCW | X | X | X | X |  |  |  | P |  | X | X |  | 2024 |  |  |  | 2025 | 2025 | [7 empty] | 2023
MCW-17 | Kitsap | MCW |  |  | X | X | [5 empty] | X | X |  | 2023 |  |  |  | 2025 | 2025 | X
MED-33 | Cent King | MED |  |  | X | X | [5 empty] | X | X |  | 2025 |  | 2025 |  |  | F
MED-35 | Cent King | MED |  |  | X | X | [5 empty] | X | X |  | 2025 |  |  |  |  | F
MED-36 | Cent King | MED |  |  | X | X | [5 empty] | X | X |  | 2025 |  | 2024 |  |  | F
MED-37 | Cent King | MED |  |  | X | X | [5 empty] | X | X |  | 2025 |  |  |  |  | F
MER-12 | Cent King | MER |  |  | X | X | [5 empty] | X | X
MER-13 | Cent King | MER |  |  | X | X | [5 empty] | X | X |  | 2025
MER-15 | Cent King | MER |  |  | X | X | [5 empty] | X | X | [7 empty] | X | [6 empty] | 2023
MER-16 | Cent King | MER |  |  | X | X | [5 empty] | X | X
MHT-13 | South King | MHT | X |  | X | X | [5 empty] | X | X |  | 2023 |  | 2023 |  |  | F | X
MHT-15 | South King | MHT | X |  | X | X | [5 empty] | X | X |  | 2023 |  |  |  |  | F
MHT-16 | South King | MHT | X | X | X | X | [5 empty] | X | X |  | 2024 |  |  |  |  | F
MHT-17 | South King | MHT | X | X | X | X | [5 empty] | X | X |  | 2024 |  |  |  |  | F
MHT-23 | South King | MHT | X | X | X | X | [5 empty] | X | X | [6 empty] | F
MIL-16 | Kitsap | MIL | X |  | X | X | [5 empty] | X | X |  | 2024 | [13 empty] | C
MIL-17 | Kitsap | MIL | X |  | X | X | [5 empty] | X | X |  | 2023
MIL-22 | Kitsap | MIL | X |  | X | X | [5 empty] | X | X
MIL-23 | Kitsap | MIL | X |  | X | X | [5 empty] | X | X | [8 empty] | 2023 | [5 empty] | 2023
MIR-13 | East King | MIR |  |  | X | X | [5 empty] | X | X |  | 2024 |  | 2023 |  | 2023
MIR-15 | East King | MIR |  |  | X | X | [5 empty] | X | X | [5 empty] | 2023 | [5 empty] | 2023
MIR-16 | East King | MIR |  |  | X | X | [5 empty] | X | X | [5 empty] | 2023
MIR-17 | East King | MIR |  |  | X | X | [5 empty] | X | X |  | 2025 |  |  |  | 2023 | [9 empty] | 2023
MIR-23 | East King | MIR |  |  | X | X | [5 empty] | X | X | [5 empty] | 2023
MIR-24 | East King | MIR |  |  | X | X | [5 empty] | X | X | [5 empty] | 2023
MIR-25 | East King | MIR |  |  | X | X | [5 empty] | X | X | [5 empty] | 2023
MIR-26 | East King | MIR |  |  | X | X |  | P |  |  |  | X | X |  | 2025 |  |  |  | 2023
MKI-14 | Thurston | MKI |  |  | X | X | [5 empty] | X | X |  | 2023 | X |  |  |  | 2025 | [9 empty] | 2023
MKI-15 | Thurston | MKI |  |  | X | X | [5 empty] | X | X |  | 2024 | X |  |  |  | 2025 | [9 empty] | 2023
MKI-16 | Thurston | MKI |  |  | X | X | [5 empty] | X | X |  | 2023 | X |  |  |  | 2025 | [9 empty] | 2023
MKI-17 | Thurston | MKI |  |  | X | X | [5 empty] | X | X |  | 2025 | X |  |  |  | 2025 | [9 empty] | 2023
MLK-12 | Cent King | MLK |  |  | X | X | [5 empty] | X | X |  | 2024
MLK-13 | Cent King | MLK |  | X | X | X | [5 empty] | X | X |  | 2023 |  | 2024
MLK-15 | Cent King | MLK |  |  | X | X | [5 empty] | X | X |  | 2023 |  | 2025
MLK-16 | Cent King | MLK |  |  | X | X | [5 empty] | X | X |  |  |  | 2024 |  |  |  | X
MOT-14 | Thurston | MOT |  |  | X | X | [5 empty] | X | X |  |  | X |  |  | 2025 | 2025 | [8 empty] | 2023 | 2025
MOT-15 | Thurston | MOT |  |  | X | X | [5 empty] | X | X |  | 2024 | X |  |  | 2025 | 2025 | [9 empty] | 2025
MOT-16 | Thurston | MOT |  |  | X | X | [5 empty] | X | X |  | 2024 | X |  |  | 2025 | 2025 | [9 empty] | 2025
MOT-17 | Thurston | MOT |  |  | X | X | [5 empty] | X | X |  | 2024 | X |  |  | 2025 | 2025 | [9 empty] | 2025
MSI-21 | East King | MSI |  |  | X | X | [5 empty] | X | X
MSI-22 | East King | MSI |  |  | X | X | [5 empty] | X | X
MSI-23 | East King | MSI |  |  | X | X | [5 empty] | X | X
MSI-24 | East King | MSI |  |  | X | X | [5 empty] | X | X |  |  |  | 2025 | [10 empty] | 2023
MSI-25 | East King | MSI | X |  | X | X | [5 empty] | X | X
MST-23 | South King | MST | X | X | X | X | [5 empty] | X | X |  | 2025 |  | 2025 | [11 empty] | C
MST-25 | South King | MST | X | X | X | X | [5 empty] | X | X |  | 2024
MST-26 | South King | MST | X | X | X | X | [5 empty] | X | X |  | 2024 | [13 empty] | C
MST-27 | South King | MST | X | X | X | X | [5 empty] | X | X |  | 2025 |  | 2024
MTH-13 | South King | MTH | X |  | X | X | [5 empty] | X | X |  | 2025 |  |  |  |  | F
MTH-15 | South King | MTH | X | X | X | X | [5 empty] | X | X |  | 2024 |  |  |  |  | F
MTH-16 | South King | MTH | X | X | X | X | [5 empty] | X | X |  | 2025 |  |  |  |  | F
MTH-17 | South King | MTH | X | X | X | X | [5 empty] | X | X |  | 2025 |  | 2025 |  |  | F
MTH-21 | South King | MTH | X | X | X | X | [5 empty] | X | X |  | 2024 |  |  |  |  | F
MTV-13 | Skagit | MTV |  | X | X | X | [5 empty] | X | X |  | 2023 |  | 2025
MTV-15 | Skagit | MTV |  | X | X | X | [5 empty] | X | X |  | 2025
MTV-16 | Skagit | MTV |  | X | X | X | [5 empty] | X | X |  | 2024 |  | 2025
MTV-17 | Skagit | MTV |  | X | X | X | [5 empty] | X | X |  | 2024
MUR-13 | Kitsap | MUR |  |  | X | X | [5 empty] | X | X |  | 2023 |  |  |  | 2024 | 2023
MUR-15 | Kitsap | MUR |  |  | X | X | [5 empty] | X | X |  | 2024 |  |  |  | 2024 | 2023
MUR-16 | Kitsap | MUR |  |  | X | X | [5 empty] | X | X |  | 2025 |  |  |  | 2024 | 2023 | X
MUR-17 | Kitsap | MUR |  |  | X | X | [5 empty] | X | X |  | 2023 |  |  |  | 2024 | 2023
MVW-13 | South King | MVW | X | X | X | X |  |  |  | P |  | X | X |  | 2023 | [5 empty] | X | [8 empty] | 2024
MVW-15 | South King | MVW | X | X | X | X |  |  |  | P |  | X | X |  | 2023 | [12 empty] | 2023 |  | 2024
MVW-16 | South King | MVW | X | X | X | X |  |  |  | P |  | X | X |  | 2023 | [13 empty] | 2023 | 2024
MVW-17 | South King | MVW | X | X | X | X |  |  |  | P |  | X | X |  | 2023 | [5 empty] | X | [8 empty] | 2024
MWD-13 | Cent King | MWD |  |  | X | X | [5 empty] | X | X | [6 empty] | F
MWD-15 | Cent King | MWD |  |  | X | X | [5 empty] | X | X | [6 empty] | F
MWD-16 | Cent King | MWD |  |  | X | X | [5 empty] | X | X | [6 empty] | F
NBE-12 | East King | NBE |  |  | X | X |  |  | 2023 |  |  | X | X |  | 2023 |  | 2024
NBE-13 | East King | NBE | X |  | X | X |  |  | 2023 | P |  | X | X |  | 2025 | [11 empty] | 2023
NBE-15 | East King | NBE |  |  | X | X |  |  | 2023 |  |  | X | X |  | 2025 | [12 empty] | 2023
NBE-16 | East King | NBE |  |  | X | X |  |  | 2023 |  |  | X | X | [14 empty] | 2023
NBO-22 | North King | NBO |  |  | X | X | [5 empty] | X | X |  | 2025 |  | 2024 |  | 2025 | F
NBO-23 | North King | NBO |  |  | X | X | [5 empty] | X | X |  | 2025 |  |  |  | 2025 | F
NBO-25 | North King | NBO |  |  | X | X | [5 empty] | X | X |  | 2025 |  |  |  | 2025 | F
NBO-26 | North King | NBO |  |  | X | X | [5 empty] | X | X |  | 2023 |  | 2024 |  | 2025 | F |  |  | 2024 |  |  |  |  | 2023
NHL-13 | North King | NHL |  |  | X | X |  |  |  |  | 2023 | X | X |  |  |  | 2024 |  |  | 2023 | [9 empty] | 2025
NHL-15 | North King | NHL |  |  | X | X |  |  |  |  | 2023 | X | X |  | 2025 |  |  |  |  | 2023 | X |  | 2024 | [6 empty] | 2025
NHL-16 | North King | NHL |  |  | X | X |  |  |  |  | 2023 | X | X |  |  |  | 2025 |  |  | 2023 | [9 empty] | 2025
NHL-17 | North King | NHL |  |  | X | X |  |  |  |  | 2023 | X | X |  |  |  | 2025 |  |  | 2023 | [9 empty] | 2025
NLM-12 | Skagit | NLM | X | X | X | X | [5 empty] | X | X |  |  |  | 2024
NLM-13 | Skagit | NLM | X | X | X | X | [5 empty] | X | X |  |  |  | 2023
NLM-14 | Skagit | NLM |  |  | X | X | [5 empty] | X | X
NLM-15 | Skagit | NLM | X |  | X | X | [5 empty] | X | X
NLM-16 | Skagit | NLM | X |  | X | X | [5 empty] | X | X |  | 2023
NNO-12 | South King | NNO | X |  | X | X | [5 empty] | X | X |  | 2025 | [10 empty] | 2023
NNO-13 | South King | NNO | X | X | X | X | [5 empty] | X | X |  | 2025
NNO-15 | South King | NNO | X |  | X | X | [5 empty] | X | X |  | 2025
NNO-16 | South King | NNO | X | X | X | X | [5 empty] | X | X |  | 2025
NOB-11 | Cent King | NOB |  |  | X | X |  |  | 2023 |  |  | X | X
NOB-12 | Cent King | NOB |  |  | X | X |  |  | 2023 |  |  | X | X |  |  |  | 2024 | [11 empty] | 2023
NOB-13 | Cent King | NOB |  |  | X | X |  |  | 2023 |  |  | X | X
NOB-14 | Cent King | NOB |  |  | X | X |  |  | 2023 |  |  | X | X
NOB-1N | Cent King | NOB |  |  | X | X |  |  | 2023 |  |  | X | X
NOB-21 | Cent King | NOB |  |  | X | X |  |  | 2023 |  |  | X | X
NOB-22 | Cent King | NOB |  |  | X | X |  |  | 2023 |  |  | X | X
NOB-23 | Cent King | NOB |  |  | X | X |  |  | 2023 |  |  | X | X |  | 2025
NOB-24 | Cent King | NOB |  |  | X | X |  |  | 2023 |  |  | X | X |  | 2024 | [12 empty] | 2023 | 2023
NOB-2N | Cent King | NOB |  |  | X | X |  |  | 2023 |  |  | X | X
NOP-22 | South King | NOP | X | X | X | X | [5 empty] | X | X |  | 2024 |  |  |  |  | F
NOP-23 | South King | NOP | X | X | X | X | [5 empty] | X | X |  | 2025 |  |  |  |  | F | X
NOP-25 | South King | NOP | X | X | X | X | [5 empty] | X | X |  | 2025 |  |  |  |  | F
NOP-26 | South King | NOP | X | X | X | X | [5 empty] | X | X |  | 2023 |  |  |  |  | F
NOR-23 | North King | NOR |  |  | X | X | [5 empty] | X | X |  | 2023 |  |  |  | 2025 | 2024
NOR-24 | North King | NOR |  |  | X | X | [5 empty] | X | X |  | 2025 |  |  |  | 2025 | 2024 |  |  | 2025
NOR-25 | North King | NOR |  |  | X | X | [5 empty] | X | X |  | 2024 |  |  |  | 2025 | 2024
NOR-26 | North King | NOR |  |  | X | X | [5 empty] | X | X |  | 2025 |  |  |  | 2025 | 2024 | [5 empty] | 2023
NOR-27 | North King | NOR |  |  | X | X | [5 empty] | X | X |  | 2025 |  |  |  | 2025 | 2024
NRU-14 | Cent King | NRU |  |  | X | X | [5 empty] | X | X | [6 empty] | 2024
NRU-23 | Cent King | NRU |  |  | X | X | [5 empty] | X | X | [6 empty] | 2024 | [6 empty] | 2023
NRU-25 | Cent King | NRU |  |  | X | X | [5 empty] | X | X |  |  |  | 2023 |  |  | 2024 | [8 empty] | 2023
NRU-26 | Cent King | NRU |  |  | X | X | [5 empty] | X | X | [6 empty] | 2024 | [8 empty] | 2023
NRU-27 | Cent King | NRU |  |  | X | X | [5 empty] | X | X |  |  |  | 2024 |  |  | 2024
NUG-25 | Whatcom | NUG | X | X | X | X | [5 empty] | X | X |  | 2025 |  | 2025 | [5 empty] | 2023 | [6 empty] | 2023
NUG-26 | Whatcom | NUG | X | X | X | X |  | P |  |  |  | X | X |  | 2024 | [5 empty] | X | 2023 | [7 empty] | 2023
OBY-13 | Thurston | OBY |  |  | X | X | [5 empty] | X | X | [5 empty] | 2024 | 2023
OBY-15 | Thurston | OBY |  |  | X | X | [5 empty] | X | X | [5 empty] | 2024 | 2023
OBY-16 | Thurston | OBY |  |  | X | X | [5 empty] | X | X |  |  | X | 2025 |  | 2024 | 2023 | X
OBY-17 | Thurston | OBY |  |  | X | X | [5 empty] | X | X |  | 2025 | X |  |  | 2024 | 2023
OLD-22 | Whatcom | OLD |  |  | X | X | [5 empty] | X | X | [6 empty] | F
OLD-23 | Whatcom | OLD |  |  | X | X | [5 empty] | X | X |  | 2025 |  |  |  |  | F
OLD-25 | Whatcom | OLD | X |  | X | X |  | P |  |  |  | X | X |  | 2023 |  |  |  |  | F
OLD-26 | Whatcom | OLD |  |  | X | X | [5 empty] | X | X |  | 2025 |  |  |  |  | F
ORC-13 | South King | ORC | X | X | X | X | [5 empty] | X | X |  | 2025 | [5 empty] | X | 2025
ORC-15 | South King | ORC | X | X | X | X | [5 empty] | X | X |  | 2025
ORC-16 | South King | ORC | X | X | X | X | [5 empty] | X | X |  | 2025 | [5 empty] | X
ORC-17 | South King | ORC | X | X | X | X | [5 empty] | X | X |  | 2025 | [12 empty] | 2023
ORI-13 | South King | ORI | X | X | X | X | [5 empty] | X | X | [6 empty] | F
ORI-15 | South King | ORI | X | X | X | X | [5 empty] | X | X |  | 2025 |  |  |  |  | F
ORI-16 | South King | ORI | X | X | X | X | [5 empty] | X | X | [6 empty] | F
ORI-17 | South King | ORI | X | X | X | X | [5 empty] | X | X |  | 2024 |  |  |  |  | F
ORT-22 | Pierce | ORT |  |  | X | X |  |  |  |  | 2023 | X | X
ORT-23 | Pierce | ORT | X |  | X | X |  |  |  |  | 2023 | X | X |  | 2023
ORT-25 | Pierce | ORT |  |  | X | X |  |  |  |  | 2023 | X | X |  |  |  | 2025
ORT-26 | Pierce | ORT |  |  | X | X |  |  |  |  | 2023 | X | X
OSC-22 | South King | OSC | X | X | X | X | [5 empty] | X | X |  |  |  | 2023 |  | 2023
OSC-23 | South King | OSC | X | X | X | X | [5 empty] | X | X | [5 empty] | 2023
OSC-25 | South King | OSC | X | X | X | X | [5 empty] | X | X |  | 2023 |  | 2023 |  | 2023
OSC-26 | South King | OSC | X | X | X | X | [5 empty] | X | X |  | 2023 |  |  |  | 2023
OVE-12 | Cent King | OVE |  |  | X | X | [5 empty] | X | X |  |  |  | 2023
OVE-13 | Cent King | OVE |  |  | X | X | [5 empty] | X | X |  | 2025 |  | 2025
OVE-15 | Cent King | OVE |  |  | X | X | [5 empty] | X | X |  | 2025 |  | 2023 | [5 empty] | 2023 |  |  |  | 2023
PAD-15 | Skagit | PAD | X |  | X | X | [5 empty] | X | X | [6 empty] | F
PAD-16 | Skagit | PAD | X |  | X | X | [5 empty] | X | X | [6 empty] | F
PAN-12 | South King | PAN | X |  | X | X |  |  |  | P |  | X | X |  | 2025 |  | 2023 |  |  | 2025 | X
PAN-13 | South King | PAN | X |  | X | X |  |  |  | P |  | X | X |  | 2024 |  | 2025 |  |  | 2025 | X
PAN-14 | South King | PAN | X |  | X | X |  |  |  | P |  | X | X |  | 2024 |  |  |  |  | 2025
PAN-15 | South King | PAN | X | X | X | X |  |  |  | P |  | X | X |  | 2024 |  | 2023 |  |  | 2025 | X | [6 empty] | 2023
PAN-16 | South King | PAN | X |  | X | X |  |  |  | P |  | X | X |  | 2024 |  |  |  |  | 2025
PAT-13 | Thurston | PAT |  |  | X | X |  |  |  |  | 2023 | X | X |  | 2023 | X |  |  | 2023
PAT-15 | Thurston | PAT | X |  | X | X |  |  |  |  | 2023 | X | X |  |  | X |  |  | 2023
PAT-16 | Thurston | PAT |  |  | X | X |  |  |  |  | 2023 | X | X |  | 2025 | X |  |  | 2023 |  | X
PAT-17 | Thurston | PAT |  |  | X | X |  |  |  |  | 2023 | X | X |  | 2023 | X | 2023 |  | 2023 |  | X | [6 empty] | 2023
PCR-12 | Cent King | PCR | X |  | X | X | [5 empty] | X | X | [6 empty] | F
PCR-13 | Cent King | PCR | X | X | X | X | [5 empty] | X | X |  |  |  | 2025 |  |  | F
PCR-14 | Cent King | PCR | X | X | X | X | [5 empty] | X | X | [6 empty] | F
PCR-15 | Cent King | PCR |  |  | X | X | [5 empty] | X | X | [6 empty] | F
PCR-22 | Cent King | PCR |  |  | X | X | [5 empty] | X | X |  | 2025 |  |  |  |  | F
PCR-23 | Cent King | PCR |  |  | X | X | [5 empty] | X | X | [6 empty] | F
PCR-24 | Cent King | PCR | X |  | X | X | [5 empty] | X | X |  | 2025 |  |  |  |  | F
PCR-25 | Cent King | PCR |  |  | X | X | [5 empty] | X | X | [6 empty] | F
PEA-14 | South King | PEA | X | X | X | X |  |  | 2023 |  |  | X | X |  | 2025 |  |  |  |  | F
PEA-15 | South King | PEA | X | X | X | X |  |  | 2023 |  |  | X | X |  | 2023 |  |  |  |  | F |  |  | 2023 |  |  |  |  | 2023
PEA-16 | South King | PEA | X | X | X | X |  |  | 2023 |  |  | X | X |  | 2024 |  |  |  |  | F
PEA-17 | South King | PEA | X | X | X | X |  |  | 2023 |  |  | X | X |  | 2023 |  |  |  |  | F | [5 empty] | 2023 |  | 2023
PET-12 | Skagit | PET | X |  | X | X |  |  |  | P |  | X | X |  | 2023 |  |  |  | 2023 | 2023 | X | [7 empty] | 2023
PET-13 | Skagit | PET | X |  | X | X |  |  |  | P |  | X | X |  | 2024 |  |  |  | 2023 | 2023 | X |  | 2024
PET-15 | Skagit | PET | X |  | X | X |  |  |  | P |  | X | X |  | 2023 |  | 2024 |  | 2023 | 2023 | X
PET-16 | Skagit | PET | X |  | X | X |  | P |  | P |  | X | X |  | 2024 |  | 2023 |  | 2023 | 2023 |  |  | 2025
PGA-12 | Kitsap | PGA |  |  | X | X | [5 empty] | X | X | [5 empty] | 2023 | [7 empty] | 2023 | 2023 | 2023
PGA-13 | Kitsap | PGA | X |  | X | X | [5 empty] | X | X |  | 2023 |  |  |  | 2023 |  | X | 2024 | [5 empty] | 2023
PGA-15 | Kitsap | PGA |  |  | X | X | [5 empty] | X | X | [5 empty] | 2023
PGA-16 | Kitsap | PGA |  |  | X | X | [5 empty] | X | X |  |  |  | 2024 |  | 2023 |  | X
PHA-13 | Cent King | PHA |  | X | X | X | [5 empty] | X | X |  | 2024 |  |  |  |  | F
PHA-15 | Cent King | PHA |  |  | X | X | [5 empty] | X | X | [6 empty] | F
PHA-16 | Cent King | PHA |  | X | X | X | [5 empty] | X | X | [6 empty] | F | [7 empty] | 2023
PHA-17 | Cent King | PHA |  | X | X | X | [5 empty] | X | X | [6 empty] | F
PIK-21 | East King | PIK |  |  | X | X | [5 empty] | X | X |  | 2023 | [6 empty] | 2024
PIK-22 | East King | PIK |  |  | X | X | [5 empty] | X | X |  | 2025
PIK-23 | East King | PIK |  |  | X | X | [5 empty] | X | X
PIK-24 | East King | PIK |  |  | X | X | [5 empty] | X | X |  | 2024
PIK-25 | East King | PIK |  |  | X | X | [5 empty] | X | X |  | 2025
PIN-17 | East King | PIN |  |  | X | X | [5 empty] | X | X |  | 2025 |  |  |  |  | 2025
PIN-23 | East King | PIN |  |  | X | X | [5 empty] | X | X |  | 2023 |  |  |  |  | 2025
PIN-25 | East King | PIN |  |  | X | X | [5 empty] | X | X |  |  |  | 2023 |  |  | 2025
PIN-26 | East King | PIN |  |  | X | X | [5 empty] | X | X |  | 2025 |  |  |  |  | 2025
PIN-27 | East King | PIN |  |  | X | X | [5 empty] | X | X | [6 empty] | 2025
PIP-22 | South King | PIP | X |  | X | X | [5 empty] | X | X |  | 2025 | [12 empty] | 2023
PIP-23 | South King | PIP | X |  | X | X | [5 empty] | X | X |  | 2024
PIP-25 | South King | PIP | X |  | X | X | [5 empty] | X | X |  | 2025 |  | 2025 |  |  |  | X
PIP-26 | South King | PIP | X |  | X | X | [5 empty] | X | X |  | 2025
PLA-21 | North King | PLA |  |  | X | X | [5 empty] | X | X |  | 2025 | [11 empty] | 2023 |  | C
PLA-22 | North King | PLA |  |  | X | X | [5 empty] | X | X |  | 2025
PLA-23 | North King | PLA |  |  | X | X | [5 empty] | X | X |  | 2025 |  | 2023
PLA-24 | North King | PLA |  |  | X | X | [5 empty] | X | X |  | 2025 |  | 2025
PLG-13 | Thurston | PLG |  |  | X | X | [5 empty] | X | X |  |  | X | 2024 |  | 2023 | 2023 | [6 empty] | 2023
PLG-15 | Thurston | PLG |  |  | X | X | [5 empty] | X | X |  |  | X |  |  | 2023 | 2023
PLG-16 | Thurston | PLG |  |  | X | X | [5 empty] | X | X |  |  | X |  |  | 2023 | 2023 | X
PLG-17 | Thurston | PLG |  | X | X | X |  |  |  | P |  | X | X |  |  | X | 2025 |  | 2023 | 2023 |  |  | 2023
PLU-21 | Thurston | PLU |  |  | X | X | [5 empty] | X | X |  | 2024
PLU-22 | Thurston | PLU |  |  | X | X | [5 empty] | X | X
PLU-24 | Thurston | PLU |  |  | X | X | [5 empty] | X | X | [15 empty] | 2023
PLU-25 | Thurston | PLU |  |  | X | X | [5 empty] | X | X
PLY-12 | Whatcom | PLY |  |  | X | X | [5 empty] | X | X |  | 2024
PLY-13 | Whatcom | PLY | X |  | X | X | [5 empty] | X | X |  | 2023 |  | 2025
PLY-15 | Whatcom | PLY |  |  | X | X | [5 empty] | X | X |  | 2023
PLY-16 | Whatcom | PLY |  | X | X | X | [5 empty] | X | X |  | 2023
PMA-12 | Kitsap | PMA | X |  | X | X | [5 empty] | X | X |  | 2024
PMA-13 | Kitsap | PMA |  |  | X | X | [5 empty] | X | X |  | 2023 | [5 empty] | X
PMA-15 | Kitsap | PMA |  |  | X | X | [5 empty] | X | X |  |  |  | 2024 |  |  |  | X |  |  |  |  | 2023
PMA-16 | Kitsap | PMA |  |  | X | X | [5 empty] | X | X |  | 2023 |  | 2025 |  |  |  | X
POU-13 | Kitsap | POU |  |  | X | X | [5 empty] | X | X |  |  |  | 2023 |  | 2024 | [7 empty] | 2023 | 2023
POU-15 | Kitsap | POU |  |  | X | X | [5 empty] | X | X |  |  |  | 2024 |  | 2024 | [9 empty] | 2023
POU-16 | Kitsap | POU |  |  | X | X | [5 empty] | X | X | [5 empty] | 2024
PRE-11 | Cent King | PRE | X | X | X | X | [5 empty] | X | X | [14 empty] | 2023
PRE-12 | Cent King | PRE | X | X | X | X | [5 empty] | X | X |  | 2025 |  | 2024
PRE-13 | Cent King | PRE |  | X | X | X | [5 empty] | X | X |  | 2023
PRE-14 | Cent King | PRE | X | X | X | X | [5 empty] | X | X
PRE-15 | Cent King | PRE |  |  | X | X | [5 empty] | X | X
PRI-13 | Thurston | PRI | X |  | X | X | [5 empty] | X | X |  |  | 2023
PRI-15 | Thurston | PRI |  |  | X | X | [5 empty] | X | X
PRI-22 | Thurston | PRI | X |  | X | X | [5 empty] | X | X |  | 2024 | X
PRI-23 | Thurston | PRI | X |  | X | X | [5 empty] | X | X |  |  | X | 2024 |  |  |  | X |  | 2023
PRI-24 | Thurston | PRI | X |  | X | X | [5 empty] | X | X |  |  | X
PTR-14 | Whatcom | PTR |  |  | X | X | [5 empty] | X | X |  | 2025 | [5 empty] | X | [5 empty] | 2023
PTR-16 | Whatcom | PTR |  |  | X | X | [5 empty] | X | X |  | 2025 | [5 empty] | X
RAI-11 | Thurston | RAI |  |  | X | X | [5 empty] | X | X |  | 2024 | X | 2024
RAI-12 | Thurston | RAI |  | X | X | X | [5 empty] | X | X |  |  | X | 2024 | [10 empty] | 2023
RAI-13 | Thurston | RAI |  |  | X | X | [5 empty] | X | X |  | 2025 | [12 empty] | 2023
RAI-14 | Thurston | RAI |  |  | X | X | [5 empty] | X | X |  | 2025 | X | 2025
RDO-12 | South King | RDO | X | X | X | X | [5 empty] | X | X | [7 empty] | X
RDO-13 | South King | RDO | X | X | X | X | [5 empty] | X | X
RDO-15 | South King | RDO | X | X | X | X | [5 empty] | X | X |  | 2025
RDO-16 | South King | RDO | X | X | X | X | [5 empty] | X | X |  |  |  | 2025
RED-12 | North King | RED |  |  | X | X | [5 empty] | X | X | [6 empty] | 2023
RED-13 | North King | RED |  |  | X | X | [5 empty] | X | X |  | 2025 |  |  |  |  | 2023
RED-14 | North King | RED |  |  | X | X | [5 empty] | X | X |  | 2024 |  |  |  |  | 2023
RED-15 | North King | RED |  |  | X | X | [5 empty] | X | X | [6 empty] | 2023
RED-22 | North King | RED |  |  | X | X | [5 empty] | X | X |  | 2025 |  |  |  |  | 2023
RED-23 | North King | RED |  |  | X | X | [5 empty] | X | X | [6 empty] | 2023 | [8 empty] | 2023
RED-24 | North King | RED |  |  | X | X | [5 empty] | X | X |  | 2025 |  |  |  |  | 2023
RED-25 | North King | RED |  |  | X | X | [5 empty] | X | X | [6 empty] | 2023
RHO-13 | Pierce | RHO |  |  | X | X | [5 empty] | X | X | [5 empty] | 2023 | 2023 | [7 empty] | 2023
RHO-15 | Pierce | RHO |  | X | X | X |  |  |  | P |  | X | X | [5 empty] | 2023 | 2023
RHO-16 | Pierce | RHO |  |  | X | X | [5 empty] | X | X |  | 2024 |  |  |  | 2023 | 2023
RHO-17 | Pierce | RHO |  |  | X | X | [5 empty] | X | X |  | 2025 |  |  |  | 2023 | 2023
RIT-16 | Skagit | RIT |  | X | X | X | [5 empty] | X | X |  | 2023
RIT-17 | Skagit | RIT |  | X | X | X | [5 empty] | X | X | [14 empty] | 2023
RIT-18 | Skagit | RIT | X | X | X | X | [5 empty] | X | X |  |  |  | 2023
RIT-19 | Skagit | RIT |  | X | X | X | [5 empty] | X | X |  | 2024
RIV-12 | Skagit | RIV |  | X | X | X | [5 empty] | X | X |  | 2024 |  |  |  | 2025
RIV-13 | Skagit | RIV |  | X | X | X | [5 empty] | X | X |  | 2023 |  | 2025 |  | 2025
RIV-15 | Skagit | RIV | X | X | X | X | [5 empty] | X | X |  | 2024 |  |  |  | 2025 | [9 empty] | 2023
RIV-16 | Skagit | RIV |  | X | X | X | [5 empty] | X | X |  | 2024 |  | 2024 |  | 2025
RJN-11 | South King | RJN | X | X | X | X |  |  |  | P |  | X | X | [6 empty] | 2024
RJN-12 | South King | RJN | X | X | X | X |  |  |  | P |  | X | X | [6 empty] | 2024
RJN-13 | South King | RJN | X | X | X | X |  |  |  | P |  | X | X |  | 2025 |  |  |  |  | 2024 | X
RJN-14 | South King | RJN | X | X | X | X |  |  |  | P |  | X | X | [6 empty] | 2024
RJN-15 | South King | RJN | X | X | X | X |  |  |  | P |  | X | X | [6 empty] | 2024
RJN-23 | South King | RJN |  |  | X | X | [5 empty] | X | X |  | 2024 |  |  |  |  | 2024
RJN-25 | South King | RJN | X | X | X | X |  |  |  | P |  | X | X | [6 empty] | 2024
RJN-26 | South King | RJN | X | X | X | X |  |  |  | P |  | X | X | [6 empty] | 2024
RJN-27 | South King | RJN | X | X | X | X |  |  |  | P |  | X | X | [6 empty] | 2024
RJN-33 | South King | RJN |  |  | X | X | [5 empty] | X | X | [6 empty] | 2024
RJN-35 | South King | RJN | X | X | X | X |  |  |  | P |  | X | X | [6 empty] | 2024
RJN-36 | South King | RJN | X | X | X | X |  |  |  | P |  | X | X | [6 empty] | 2024
ROC-15 | Thurston | ROC | X | X | X | X | [5 empty] | X | X |  |  |  | 2024 |  | 2025
ROC-16 | Thurston | ROC | X | X | X | X | [5 empty] | X | X |  |  | X | 2023 |  | 2025 |  | X
ROC-17 | Thurston | ROC | X | X | X | X | [5 empty] | X | X | [5 empty] | 2025 | [6 empty] | 2023 | 2023
ROC-25 | Thurston | ROC | X | X | X | X | [5 empty] | X | X |  | 2023 |  |  |  | 2025
ROC-26 | Thurston | ROC | X | X | X | X | [5 empty] | X | X |  | 2023 |  |  |  | 2025 | [7 empty] | 2023
ROC-27 | Thurston | ROC | X | X | X | X | [5 empty] | X | X | [5 empty] | 2025
ROE-13 | Whatcom | ROE | X | X | X | X | [5 empty] | X | X |  | 2024 |  |  |  |  | F | [6 empty] | 2023
ROE-15 | Whatcom | ROE |  |  | X | X | [5 empty] | X | X | [6 empty] | F
ROE-16 | Whatcom | ROE | X |  | X | X | [5 empty] | X | X | [6 empty] | F
ROE-17 | Whatcom | ROE | X | X | X | X | [5 empty] | X | X |  | 2023 |  |  |  |  | F
ROL-13 | South King | ROL | X | X | X | X | [5 empty] | X | X |  |  |  | 2024 |  |  | F
ROL-15 | South King | ROL | X | X | X | X | [5 empty] | X | X | [6 empty] | F
ROL-16 | South King | ROL | X | X | X | X | [5 empty] | X | X |  |  |  | 2024 |  |  | F | [7 empty] | 2023
ROL-17 | South King | ROL | X | X | X | X | [5 empty] | X | X | [6 empty] | F
ROS-13 | North King | ROS |  |  | X | X | [5 empty] | X | X |  | 2024 |  |  |  | 2025 | 2024
ROS-15 | North King | ROS |  |  | X | X | [5 empty] | X | X |  |  |  | 2025 |  | 2025 | 2024
ROS-16 | North King | ROS |  |  | X | X | [5 empty] | X | X | [5 empty] | 2025 | 2024
ROS-17 | North King | ROS |  |  | X | X | [5 empty] | X | X |  | 2024 |  |  |  | 2025 | 2024
ROS-21 | North King | ROS |  |  | X | X | [5 empty] | X | X | [5 empty] | 2025 | 2024
ROS-22 | North King | ROS |  |  | X | X | [5 empty] | X | X |  | 2025 |  |  |  | 2025 | 2024
RPT-15 | Kitsap | RPT | X |  | X | X |  |  |  | P | 2023 | X | X |  | 2023 |  | 2025 |  |  | 2025
RPT-16 | Kitsap | RPT | X |  | X | X |  |  |  | P | 2023 | X | X |  | 2025 |  |  |  |  | 2025 | X
RPT-17 | Kitsap | RPT | X |  | X | X |  |  |  | P | 2023 | X | X |  | 2025 |  | 2025 |  |  | 2025 | X |  |  | 2023 |  |  |  | 2023
RPT-22 | Kitsap | RPT | X |  | X | X |  |  |  | P | 2023 | X | X |  | 2025 |  |  |  |  | 2025
RPT-23 | Kitsap | RPT | X |  | X | X |  |  |  | P | 2023 | X | X |  | 2025 |  |  |  |  | 2025
RPT-26 | Kitsap | RPT | X |  | X | X |  |  |  | P | 2023 | X | X |  | 2025 |  |  |  |  | 2025
SAH-13 | North King | SAH |  |  | X | X | [5 empty] | X | X |  | 2025 |  | 2023 |  | 2024 |  | X
SAH-15 | North King | SAH |  |  | X | X | [5 empty] | X | X |  | 2025 |  | 2025 |  | 2024
SAH-16 | North King | SAH |  |  | X | X | [5 empty] | X | X |  | 2025 |  | 2023 |  | 2024
SAH-17 | North King | SAH |  |  | X | X | [5 empty] | X | X |  |  |  | 2025 |  | 2024 | [9 empty] | C
SAM-10 | North King | SAM |  |  | X | X | [5 empty] | X | X | [5 empty] | 2024
SAM-11 | North King | SAM |  |  | X | X | [5 empty] | X | X | [5 empty] | 2024
SAM-12 | North King | SAM |  |  | X | X | [5 empty] | X | X | [5 empty] | 2024 | [9 empty] | 2023
SAM-13 | North King | SAM |  |  | X | X | [5 empty] | X | X |  | 2025 |  |  |  | 2024
SAM-14 | North King | SAM |  |  | X | X | [5 empty] | X | X | [5 empty] | 2024
SBE-22 | Cent King | SBE |  |  | X | X | [5 empty] | X | X |  | 2025 |  |  |  |  | F | [6 empty] | 2023
SBE-23 | Cent King | SBE |  |  | X | X | [5 empty] | X | X |  | 2025 |  |  |  |  | F
SBE-25 | Cent King | SBE |  |  | X | X | [5 empty] | X | X |  | 2025 |  |  |  |  | F
SBE-26 | Cent King | SBE |  |  | X | X | [5 empty] | X | X | [6 empty] | F
SCE-14 | North King | SCE |  |  | X | X | [5 empty] | X | X
SCE-15 | North King | SCE |  |  | X | X | [5 empty] | X | X
SCH-12 | Whatcom | SCH | X |  | X | X |  |  |  | P |  | X | X |  | 2025 |  |  |  |  | 2024
SCH-13 | Whatcom | SCH | X |  | X | X |  |  |  | P |  | X | X |  | 2024 |  |  |  |  | 2024 |  |  | 2023
SCH-15 | Whatcom | SCH | X | X | X | X |  |  |  | P |  | X | X |  | 2024 |  | 2024 |  |  | 2024
SCH-16 | Whatcom | SCH | X | X | X | X |  |  |  | P |  | X | X |  |  |  | 2023 |  |  | 2024
SEH-11 | Whatcom | SEH |  |  | X | X | [5 empty] | X | X |  | 2024 | [14 empty] | 2024
SEH-12 | Whatcom | SEH |  |  | X | X | [5 empty] | X | X |  | 2024 | [14 empty] | 2024
SEH-13 | Whatcom | SEH |  |  | X | X | [5 empty] | X | X | [16 empty] | 2024
SEH-14 | Whatcom | SEH |  |  | X | X | [5 empty] | X | X | [16 empty] | 2024
SEH-15 | Whatcom | SEH |  |  | X | X | [5 empty] | X | X | [16 empty] | 2024
SEM-11 | Whatcom | SEM |  |  | X | X | [5 empty] | X | X |  | 2024 | [14 empty] | 2024
SEM-12 | Whatcom | SEM |  |  | X | X | [5 empty] | X | X | [16 empty] | 2024
SEM-13 | Whatcom | SEM |  |  | X | X | [5 empty] | X | X | [16 empty] | 2024
SEM-14 | Whatcom | SEM |  |  | X | X | [5 empty] | X | X | [7 empty] | X | [8 empty] | 2024
SEM-15 | Whatcom | SEM |  |  | X | X | [5 empty] | X | X | [9 empty] | 2025 | [5 empty] | 2023 | 2024
SEQ-13 | South King | SEQ | X | X | X | X | [5 empty] | X | X |  | 2024 | [5 empty] | X
SEQ-15 | South King | SEQ | X | X | X | X | [5 empty] | X | X |  |  |  | 2024
SEQ-16 | South King | SEQ | X | X | X | X | [5 empty] | X | X |  | 2025
SEQ-17 | South King | SEQ | X | X | X | X | [5 empty] | X | X |  |  |  | 2023
SEQ-22 | South King | SEQ | X | X | X | X | [5 empty] | X | X
SHA-13 | Pierce | SHA |  | X | X | X | [5 empty] | X | X |  | 2023 | [5 empty] | X | [5 empty] | 2023
SHA-15 | Pierce | SHA |  | X | X | X | [5 empty] | X | X |  | 2025 |  | 2023 |  |  |  | X | [6 empty] | 2023
SHA-16 | Pierce | SHA |  | X | X | X | [5 empty] | X | X |  | 2025
SHA-17 | Pierce | SHA |  | X | X | X | [5 empty] | X | X
SHD-15 | South King | SHD | X | X | X | X | [5 empty] | X | X |  | 2025 |  |  |  |  | F
SHD-16 | South King | SHD | X | X | X | X | [5 empty] | X | X |  | 2024 |  |  |  |  | F
SHD-17 | South King | SHD | X | X | X | X | [5 empty] | X | X |  | 2025 |  |  |  |  | F | X
SHD-18 | South King | SHD | X | X | X | X | [5 empty] | X | X | [6 empty] | F |  | 2023 |  |  |  |  | 2023
SHE-15 | Kitsap | SHE |  |  | X | X |  |  |  |  | 2023 | X | X |  | 2025 |  | 2024
SHE-16 | Kitsap | SHE | X | X | X | X |  |  |  |  | 2023 | X | X |  | 2025
SHE-17 | Kitsap | SHE | X | X | X | X |  |  |  |  | 2023 | X | X | [7 empty] | X |  |  |  |  | 2023
SHE-25 | Kitsap | SHE | X |  | X | X |  |  |  |  | 2023 | X | X |  | 2025
SHE-26 | Kitsap | SHE |  |  | X | X |  |  |  |  | 2023 | X | X |  |  |  | 2025
SIL-13 | Kitsap | SIL |  |  | X | X | [5 empty] | X | X |  |  |  | 2023 | [12 empty] | 2025
SIL-15 | Kitsap | SIL |  |  | X | X | [5 empty] | X | X | [7 empty] | X | [8 empty] | 2025
SIL-16 | Kitsap | SIL |  |  | X | X | [5 empty] | X | X | [13 empty] | 2023 |  | C | 2025
SIL-17 | Kitsap | SIL |  |  | X | X | [5 empty] | X | X |  | 2025 | [14 empty] | 2025
SIN-22 | Kitsap | SIN |  |  | X | X | [5 empty] | X | X |  | 2025
SIN-23 | Kitsap | SIN |  |  | X | X | [5 empty] | X | X |  |  |  | 2024
SIN-24 | Kitsap | SIN |  |  | X | X | [5 empty] | X | X |  | 2023 |  | 2024
SIN-25 | Kitsap | SIN |  |  | X | X | [5 empty] | X | X | [7 empty] | X
SKE-22 | Kitsap | SKE |  |  | X | X | [5 empty] | X | X |  |  |  | 2023
SKE-23 | Kitsap | SKE |  |  | X | X |  | P |  |  |  | X | X
SKE-26 | Kitsap | SKE | X |  | X | X |  |  |  | P |  | X | X |  | 2025 |  | 2024 |  |  |  | X | [6 empty] | 2023
SKI-12 | North King | SKI |  |  | X | X | [5 empty] | X | X |  | 2025 |  |  |  |  | 2025
SKI-13 | North King | SKI |  |  | X | X | [5 empty] | X | X |  | 2025 |  |  |  |  | 2025
SKI-16 | North King | SKI |  |  | X | X | [5 empty] | X | X |  | 2025 |  |  |  |  | 2025
SKY-23 | North King | SKY |  |  | X | X | [5 empty] | X | X |  | 2025 | X | [5 empty] | 2025 | [5 empty] | 2023
SKY-25 | North King | SKY |  |  | X | X | [5 empty] | X | X |  | 2025 | X | [5 empty] | 2024
SLA-13 | Whatcom | SLA | X | X | X | X | [5 empty] | X | X
SLA-15 | Whatcom | SLA | X | X | X | X | [5 empty] | X | X |  | 2024 |  | 2024 | [10 empty] | 2023
SLA-16 | Whatcom | SLA | X | X | X | X |  | P |  |  |  | X | X | [7 empty] | X | [6 empty] | 2023
SLA-17 | Whatcom | SLA | X | X | X | X | [5 empty] | X | X | [13 empty] | 2023
SME-12 | Cent King | SME |  |  | X | X | [5 empty] | X | X | [6 empty] | F
SME-13 | Cent King | SME |  |  | X | X | [5 empty] | X | X | [6 empty] | F
SME-15 | Cent King | SME |  |  | X | X | [5 empty] | X | X | [6 empty] | F | [6 empty] | 2023
SMR-23 | Pierce | SMR |  |  | X | X | [5 empty] | X | X | [6 empty] | F
SMR-24 | Pierce | SMR |  |  | X | X | [5 empty] | X | X |  | 2025 |  |  |  |  | F | [6 empty] | 2023
SMR-25 | Pierce | SMR |  |  | X | X | [5 empty] | X | X | [6 empty] | F
SMR-26 | Pierce | SMR | X |  | X | X | [5 empty] | X | X |  | 2025 |  | 2025 |  |  | F | [6 empty] | 2023
SNN-21 | Skagit | SNN | X | X | X | X | [5 empty] | X | X
SNN-22 | Skagit | SNN | X | X | X | X | [5 empty] | X | X |  | 2025
SNQ-13 | East King | SNQ |  |  | X | X | [5 empty] | X | X | [13 empty] | 2023
SNQ-15 | East King | SNQ | X |  | X | X | [5 empty] | X | X
SNQ-16 | East King | SNQ | X |  | X | X | [5 empty] | X | X |  | 2025
SNQ-17 | East King | SNQ |  |  | X | X | [5 empty] | X | X |  | 2025
SNQ-18 | East King | SNQ |  |  | X | X | [5 empty] | X | X
SOM-13 | Cent King | SOM |  |  | X | X | [5 empty] | X | X
SOM-15 | Cent King | SOM |  |  | X | X | [5 empty] | X | X |  | 2025
SOM-16 | Cent King | SOM |  |  | X | X | [5 empty] | X | X |  | 2024 | [5 empty] | X | [7 empty] | C
SOM-17 | Cent King | SOM |  |  | X | X | [5 empty] | X | X |  | 2023 | [13 empty] | C
SOO-23 | South King | SOO | X |  | X | X | [5 empty] | X | X |  | 2024 |  | 2024
SOO-25 | South King | SOO | X |  | X | X | [5 empty] | X | X |  | 2024 | [5 empty] | X | [6 empty] | 2023
SOO-26 | South King | SOO | X |  | X | X | [5 empty] | X | X |  | 2024
SOO-27 | South King | SOO | X | X | X | X | [5 empty] | X | X |  | 2024 | [5 empty] | X
SOU-22 | South King | SOU | X | X | X | X | [5 empty] | X | X | [6 empty] | F
SOU-23 | South King | SOU | X | X | X | X | [5 empty] | X | X |  |  |  | 2024 |  |  | F | X
SOU-24 | South King | SOU | X | X | X | X | [5 empty] | X | X | [6 empty] | F
SOU-25 | South King | SOU | X | X | X | X | [5 empty] | X | X | [6 empty] | F
SOU-26 | South King | SOU | X | X | X | X | [5 empty] | X | X |  | 2025 |  |  |  |  | F
SPA-16 | Pierce | SPA | X | X | X | X |  |  | 2023 | P |  | X | X |  | 2023 |  |  |  | 2024 | 2024
SPA-17 | Pierce | SPA | X | X | X | X |  |  | 2023 | P |  | X | X |  | 2024 |  |  |  | 2024 | 2024
SPG-11 | Thurston | SPG |  |  | X | X | [5 empty] | X | X |  | 2023 | X
SPG-13 | Thurston | SPG |  |  | X | X | [5 empty] | X | X |  |  | 2023 |  |  |  |  | X
SPG-14 | Thurston | SPG |  |  | X | X | [5 empty] | X | X |  |  | X | 2024
SPI-14 | North King | SPI |  |  | X | X | [5 empty] | X | X | [6 empty] | F
SPI-15 | North King | SPI |  |  | X | X | [5 empty] | X | X | [6 empty] | F
SPI-16 | North King | SPI |  |  | X | X | [5 empty] | X | X | [6 empty] | F
SPI-17 | North King | SPI |  |  | X | X | [5 empty] | X | X | [6 empty] | F
SPI-23 | North King | SPI |  |  | X | X | [5 empty] | X | X | [6 empty] | F
SST-11 | Whatcom | SST |  |  | X | X | [5 empty] | X | X
SST-12 | Whatcom | SST |  |  | X | X | [5 empty] | X | X |  | 2023
SST-13 | Whatcom | SST |  |  | X | X | [5 empty] | X | X
SST-14 | Whatcom | SST |  |  | X | X | [5 empty] | X | X |  | 2023
SST-15 | Whatcom | SST |  |  | X | X | [5 empty] | X | X
SST-16 | Whatcom | SST |  |  | X | X | [5 empty] | X | X
SST-17 | Whatcom | SST |  |  | X | X | [5 empty] | X | X
STA-13 | South King | STA | X | X | X | X | [5 empty] | X | X |  | 2024
STA-15 | South King | STA | X | X | X | X | [5 empty] | X | X |  | 2025
STA-16 | South King | STA | X | X | X | X | [5 empty] | X | X |  | 2024 | [7 empty] | 2023
STA-17 | South King | STA | X | X | X | X | [5 empty] | X | X |  | 2025 | [13 empty] | 2023
STA-22 | South King | STA |  |  | X | X | [5 empty] | X | X
STA-23 | South King | STA | X | X | X | X | [5 empty] | X | X |  | 2024 |  | 2024 | [10 empty] | 2023
STA-25 | South King | STA | X | X | X | X | [5 empty] | X | X |  | 2025
STA-26 | South King | STA | X | X | X | X | [5 empty] | X | X |  | 2024 | [13 empty] | 2023
STR-11 | North King | STR |  |  | X | X | [5 empty] | X | X
STR-12 | North King | STR |  |  | X | X | [5 empty] | X | X
STR-13 | North King | STR |  |  | X | X | [5 empty] | X | X
STR-14 | North King | STR |  |  | X | X | [5 empty] | X | X
STR-31 | North King | STR |  |  | X | X | [5 empty] | X | X
STR-32 | North King | STR |  |  | X | X | [5 empty] | X | X
STR-33 | North King | STR |  |  | X | X | [5 empty] | X | X
STR-34 | North King | STR |  |  | X | X | [5 empty] | X | X
STW-12 | Pierce | STW | X |  | X | X |  |  |  |  | 2023 | X | X |  | 2025 |  |  |  |  | F
STW-13 | Pierce | STW | X |  | X | X |  |  |  |  | 2023 | X | X |  | 2023 |  | 2024 |  |  | F
STW-15 | Pierce | STW | X |  | X | X |  |  |  |  | 2023 | X | X |  | 2024 |  |  |  |  | F
STW-16 | Pierce | STW | X |  | X | X |  |  |  |  | 2023 | X | X |  | 2024 |  |  |  |  | F | [6 empty] | 2023
SUM-21 | Skagit | SUM | X |  | X | X | [5 empty] | X | X |  | 2025 | [5 empty] | X | 2023
SUM-22 | Skagit | SUM | X |  | X | X | [5 empty] | X | X |  | 2024
SUM-23 | Skagit | SUM | X |  | X | X | [5 empty] | X | X |  | 2025
SUM-24 | Skagit | SUM |  |  | X | X | [5 empty] | X | X
SUM-25 | Skagit | SUM |  |  | X | X | [5 empty] | X | X
SUN-11 | Pierce | SUN | X |  | X | X | [5 empty] | X | X
SUN-12 | Pierce | SUN | X |  | X | X | [5 empty] | X | X
SUN-13 | Pierce | SUN |  |  | X | X | [5 empty] | X | X
SUN-14 | Pierce | SUN |  |  | X | X | [5 empty] | X | X
SWA-12 | Island | SWA |  |  | X | X | [5 empty] | X | X |  | 2025 |  | 2025 |  | 2023
SWA-13 | Island | SWA |  |  | X | X | [5 empty] | X | X |  | 2024 |  |  |  | 2023
SWA-15 | Island | SWA |  | X | X | X | [5 empty] | X | X |  | 2025 |  |  |  | 2023
SWA-16 | Island | SWA |  |  | X | X | [5 empty] | X | X |  | 2025 |  |  |  | 2023 |  | X
SWD-11 | Kitsap | SWD |  |  | X | X |  |  | 2023 |  |  | X | X |  | 2025 |  | 2025
SWD-12 | Kitsap | SWD | X |  | X | X |  |  | 2023 |  |  | X | X |  |  |  | 2025 | [11 empty] | C
SWD-13 | Kitsap | SWD | X |  | X | X |  |  | 2023 |  |  | X | X |  | 2025 |  | 2024 | [11 empty] | C
SWD-14 | Kitsap | SWD | X |  | X | X |  |  | 2023 |  |  | X | X |  | 2025
SWE-13 | South King | SWE | X | X | X | X | [5 empty] | X | X |  | 2025 |  | 2024
SWE-15 | South King | SWE | X | X | X | X | [5 empty] | X | X
SWE-23 | South King | SWE | X | X | X | X | [5 empty] | X | X |  | 2025 |  | 2024
SWE-25 | South King | SWE | X | X | X | X | [5 empty] | X | X |  | 2025
SWE-26 | South King | SWE |  |  | X | X | [5 empty] | X | X |  | 2025
SWE-27 | South King | SWE | X | X | X | X | [5 empty] | X | X |  | 2024 |  | 2025 | [10 empty] | 2023
SWI-13 | Thurston | SWI |  |  | X | X |  |  | 2023 |  |  | X | X |  | 2025 | X | 2025 |  |  |  | X
SWI-15 | Thurston | SWI |  |  | X | X |  |  | 2023 |  |  | X | X |  | 2025 | X |  |  |  |  | X | [5 empty] | 2023 | 2023
SWI-16 | Thurston | SWI |  |  | X | X |  |  | 2023 |  |  | X | X |  | 2023 | X | 2023
SWI-17 | Thurston | SWI |  |  | X | X |  |  | 2023 |  |  | X | X |  | 2025 | X
SWI-21 | Thurston | SWI |  |  | X | X |  |  | 2023 |  |  | X | X |  |  | X
TAN-13 | Thurston | TAN |  | X | X | X |  |  |  |  | 2023 | X | X |  | 2025 | X |  |  |  |  | X | [8 empty] | 2023
TAN-15 | Thurston | TAN |  | X | X | X |  |  |  |  | 2023 | X | X |  | 2025 | X | [12 empty] | 2023 | 2023
TAN-16 | Thurston | TAN |  | X | X | X |  |  |  |  | 2023 | X | X |  | 2023 | X | 2024 |  |  |  | X | [8 empty] | 2023
THO-04 | Kittitas | THO |  |  | X | X |  | P |  |  |  | X | X |  | 2025 | 2023
THO-13 | Kittitas | THO |  |  | X | X |  | P |  |  |  | X | X |  | 2025
THO-25 | Kittitas | THO |  |  | X | X |  | P |  |  |  | X | X |  | 2024 | X
THU-13 | Thurston | THU |  |  | X | X |  |  | 2023 |  |  | X | X | [6 empty] | F
THU-15 | Thurston | THU |  |  | X | X |  |  | 2023 |  |  | X | X | [6 empty] | F
THU-16 | Thurston | THU |  |  | X | X |  |  | 2023 |  |  | X | X | [6 empty] | F
THU-22 | Thurston | THU |  |  | X | X |  |  | 2023 |  |  | X | X | [6 empty] | F
THU-26 | Thurston | THU |  |  | X | X |  |  | 2023 |  |  | X | X | [6 empty] | F
TIL-22 | Pierce | TIL |  | X | X | X |  |  |  | P |  | X | X |  | 2025 |  |  |  | 2025 | 2025
TIL-23 | Pierce | TIL |  | X | X | X |  |  |  | P |  | X | X |  | 2024 |  |  |  | 2025 | 2025
TIL-25 | Pierce | TIL |  | X | X | X |  |  |  | P |  | X | X | [5 empty] | 2025 | 2025 | X
TOL-15 | North King | TOL |  |  | X | X |  |  | 2023 |  |  | X | X | [6 empty] | 2025 | [7 empty] | 2023
TOL-16 | North King | TOL |  |  | X | X |  |  | 2023 |  |  | X | X |  | 2025 |  |  |  |  | 2025 | X
TOL-17 | North King | TOL |  |  | X | X |  |  | 2023 |  |  | X | X | [6 empty] | 2025
TOT-22 | North King | TOT |  |  | X | X | [5 empty] | X | X |  | 2025
TOT-23 | North King | TOT |  |  | X | X | [5 empty] | X | X |  | 2025 |  | 2025 | [10 empty] | 2023
TOT-24 | North King | TOT |  |  | X | X | [5 empty] | X | X
TOT-25 | North King | TOT |  |  | X | X | [5 empty] | X | X
TOT-26 | North King | TOT |  |  | X | X | [5 empty] | X | X
TRA-22 | Kitsap | TRA |  |  | X | X | [5 empty] | X | X | [5 empty] | 2024 | 2024
TRA-23 | Kitsap | TRA | X | X | X | X |  |  |  | P |  | X | X | [5 empty] | 2024 | 2024 | X
TRA-25 | Kitsap | TRA |  |  | X | X | [5 empty] | X | X | [5 empty] | 2024 | 2024
TRA-26 | Kitsap | TRA |  |  | X | X | [5 empty] | X | X | [5 empty] | 2024 | 2024 | X | [6 empty] | 2023
UHL-21 | North King | UHL |  |  | X | X |  | P |  |  |  | X | X |  | 2025
UHL-22 | North King | UHL |  |  | X | X | [5 empty] | X | X |  | 2025
UHL-23 | North King | UHL |  |  | X | X | [5 empty] | X | X |  | 2025 |  | 2024
UHL-24 | North King | UHL |  |  | X | X | [5 empty] | X | X
UHL-25 | North King | UHL |  |  | X | X | [5 empty] | X | X |  | 2025 |  | 2025 |  |  |  | X | [6 empty] | 2023
VAS-12 | Kitsap | VAS |  |  | X | X |  | P |  |  | 2023 | X | X |  | 2023 | [5 empty] | X | 2024
VAS-13 | Kitsap | VAS |  |  | X | X |  | P |  |  | 2023 | X | X |  | 2023 | [5 empty] | X
VAS-22 | Kitsap | VAS |  |  | X | X |  |  |  |  | 2023 | X | X |  | 2025 | [6 empty] | 2024
VAS-23 | Kitsap | VAS |  |  | X | X |  | P |  |  | 2023 | X | X |  | 2023 | [5 empty] | X | 2025
VIC-14 | South King | VIC | X | X | X | X | [5 empty] | X | X | [6 empty] | F
VIC-15 | South King | VIC | X | X | X | X | [5 empty] | X | X |  | 2024 |  |  |  |  | F
VIC-16 | South King | VIC | X | X | X | X | [5 empty] | X | X |  |  |  | 2024 |  |  | F | X
VIC-17 | South King | VIC | X | X | X | X |  | P |  |  |  | X | X | [6 empty] | F
VIC-18 | South King | VIC | X | X | X | X | [5 empty] | X | X | [6 empty] | F
VIK-13 | Whatcom | VIK |  |  | X | X | [5 empty] | X | X | [16 empty] | 2024
VIK-15 | Whatcom | VIK |  |  | X | X | [5 empty] | X | X | [16 empty] | 2024
VIK-16 | Whatcom | VIK |  |  | X | X | [5 empty] | X | X | [16 empty] | 2024
VIK-23 | Whatcom | VIK |  | X | X | X |  |  |  | P |  | X | X | [16 empty] | 2024
VIK-25 | Whatcom | VIK |  | X | X | X |  |  |  | P |  | X | X |  | 2025 |  | 2024 | [12 empty] | 2024
VIS-22 | Whatcom | VIS | X | X | X | X |  |  |  | P |  | X | X | [5 empty] | 2025 | 2024 | X
VIS-23 | Whatcom | VIS | X | X | X | X |  |  |  | P |  | X | X | [5 empty] | 2025 | 2024
VIS-25 | Whatcom | VIS | X | X | X | X |  |  |  | P |  | X | X |  | 2024 |  | 2025 |  | 2025 | 2024 | [7 empty] | 2023
VIS-26 | Whatcom | VIS |  | X | X | X |  |  |  | P |  | X | X | [5 empty] | 2025 | 2024 | [6 empty] | 2023
VIT-15 | North King | VIT |  |  | X | X | [5 empty] | X | X | [6 empty] | F
VIT-16 | North King | VIT |  |  | X | X | [5 empty] | X | X |  | 2025 |  |  |  |  | F
VIT-17 | North King | VIT |  |  | X | X | [5 empty] | X | X | [6 empty] | F
VIT-18 | North King | VIT |  |  | X | X | [5 empty] | X | X | [6 empty] | F
VIT-22 | North King | VIT |  |  | X | X | [5 empty] | X | X | [6 empty] | F
VIT-23 | North King | VIT |  |  | X | X | [5 empty] | X | X | [6 empty] | F
VIT-24 | North King | VIT |  |  | X | X | [5 empty] | X | X | [6 empty] | F
VIT-25 | North King | VIT |  |  | X | X | [5 empty] | X | X | [6 empty] | F
VWY-12 | Whatcom | VWY | X |  | X | X | [5 empty] | X | X |  |  |  | 2024 |  |  |  | X | [8 empty] | 2023
VWY-13 | Whatcom | VWY | X | X | X | X | [5 empty] | X | X | [7 empty] | X | [8 empty] | 2023
VWY-15 | Whatcom | VWY | X |  | X | X | [5 empty] | X | X | [7 empty] | X | [8 empty] | 2023
WAB-12 | South King | WAB | X | X | X | X |  | P |  | P |  | X | X |  | 2025 |  |  |  |  | 2024
WAB-13 | South King | WAB | X | X | X | X |  |  |  | P |  | X | X |  | 2025 |  |  |  |  | 2024
WAU-22 | South King | WAU | X |  | X | X | [5 empty] | X | X |  | 2025 |  | 2024 |  |  | F
WAU-23 | South King | WAU | X | X | X | X | [5 empty] | X | X | [6 empty] | F
WAU-25 | South King | WAU | X |  | X | X | [5 empty] | X | X |  | 2025 |  |  |  |  | F
WAU-26 | South King | WAU | X |  | X | X | [5 empty] | X | X | [6 empty] | F
WAY-12 | North King | WAY |  |  | X | X |  |  | 2023 |  |  | X | X |  | 2025 |  | 2025 | [12 empty] | 2025
WAY-13 | North King | WAY |  |  | X | X |  |  | 2023 |  |  | X | X |  |  |  | 2024 | [12 empty] | 2025
WAY-15 | North King | WAY |  |  | X | X |  |  | 2023 |  |  | X | X |  | 2025 | [5 empty] | X | [7 empty] | 2023 | 2025
WAY-16 | North King | WAY |  |  | X | X |  |  | 2023 |  |  | X | X |  | 2023 |  | 2023 |  |  |  | X | [7 empty] | 2023 | 2025
WCA-14 | South King | WCA | X | X | X | X |  |  |  | P |  | X | X |  | 2025 |  |  |  |  | 2025
WCA-15 | South King | WCA | X | X | X | X |  |  |  | P |  | X | X |  | 2025 |  | 2024 |  |  | 2025
WCA-16 | South King | WCA | X | X | X | X |  |  |  | P |  | X | X |  | 2025 |  |  |  |  | 2025
WCA-17 | South King | WCA | X | X | X | X |  |  |  | P |  | X | X |  | 2025 |  | 2024 |  |  | 2025 | X
WCA-18 | South King | WCA | X | X | X | X |  |  |  | P |  | X | X | [6 empty] | 2025
WIN-12 | Kitsap | WIN |  |  | X | X | [5 empty] | X | X |  |  |  | 2023
WIN-13 | Kitsap | WIN |  |  | X | X | [5 empty] | X | X | [7 empty] | X | 2024 | [6 empty] | 2023
WIN-15 | Kitsap | WIN |  |  | X | X | [5 empty] | X | X | [7 empty] | X | [7 empty] | 2023
WIN-16 | Kitsap | WIN |  |  | X | X | [5 empty] | X | X | [15 empty] | 2023
WIS-12 | East King | WIS |  |  | X | X | [5 empty] | X | X |  | 2023 |  | 2025 | [5 empty] | 2025
WIS-13 | East King | WIS |  |  | X | X | [5 empty] | X | X |  | 2025 | [7 empty] | 2024
WIS-14 | East King | WIS |  |  | X | X | [5 empty] | X | X |  | 2023 | [5 empty] | X | [6 empty] | 2023
WIS-15 | East King | WIS |  |  | X | X | [5 empty] | X | X |  | 2023 | [12 empty] | 2023
WIS-16 | East King | WIS |  |  | X | X | [5 empty] | X | X | X | 2025 |  | 2023
WLK-13 | Pierce | WLK | X |  | X | X | [5 empty] | X | X
WLK-15 | Pierce | WLK | X |  | X | X | [5 empty] | X | X |  |  | X | 2023 |  |  |  | X | [5 empty] | 2023
WLS-12 | Skagit | WLS | X |  | X | X | [5 empty] | X | X |  | 2025 |  |  |  | 2024
WLS-13 | Skagit | WLS | X |  | X | X |  | P |  |  |  | X | X |  | 2025 |  |  |  | 2024 |  | X
WLS-15 | Skagit | WLS | X |  | X | X | [5 empty] | X | X |  |  |  | 2023 |  | 2024 |  | X
WLS-16 | Skagit | WLS | X |  | X | X |  | P |  |  |  | X | X | [5 empty] | 2024 |  | X |  |  | 2024 |  |  | 2023
WOB-23 | Whatcom | WOB | X |  | X | X | [5 empty] | X | X |  | 2024 | [5 empty] | X
WOB-25 | Whatcom | WOB |  |  | X | X | [5 empty] | X | X |  | 2025 |  | 2024
WOB-26 | Whatcom | WOB |  | X | X | X | [5 empty] | X | X |  | 2024 | [9 empty] | 2023
WOB-27 | Whatcom | WOB |  |  | X | X | [5 empty] | X | X |  | 2024 | [5 empty] | X
WOD-13 | Kittitas | WOD |  | X | X | X |  | P |  |  |  | X | X |  | 2024 | X | 2025 |  |  | F | [6 empty] | 2023
WOD-15 | Kittitas | WOD |  |  | X | X |  | P |  |  |  | X | X |  | 2025 | 2023 |  |  |  | F | [5 empty] | 2023
WOL-22 | Thurston | WOL |  |  | X | X | [5 empty] | X | X |  |  | X
WOL-23 | Thurston | WOL |  |  | X | X | [5 empty] | X | X |  |  | X
WOL-25 | Thurston | WOL |  |  | X | X | [5 empty] | X | X |  |  | X
WOL-26 | Thurston | WOL |  |  | X | X | [5 empty] | X | X
WOO-23 | Pierce | WOO | X |  | X | X | [5 empty] | X | X |  | 2024 |  | 2023
WOO-25 | Pierce | WOO |  | X | X | X | [5 empty] | X | X |  | 2024
WOO-26 | Pierce | WOO | X |  | X | X | [5 empty] | X | X |  | 2024 |  | 2025 |  |  |  | X | [6 empty] | 2023
WOO-27 | Pierce | WOO |  |  | X | X | [5 empty] | X | X |  | 2024 |  | 2024
YEL-23 | Thurston | YEL |  | X | X | X |  |  |  |  | 2023 | X | X | [13 empty] | 2023
YEL-25 | Thurston | YEL | X | X | X | X |  |  |  |  | 2023 | X | X | [7 empty] | X
YEL-26 | Thurston | YEL |  | X | X | X |  |  |  |  | 2023 | X | X |  | 2024
YEL-27 | Thurston | YEL |  | X | X | X |  |  |  |  | 2023 | X | X | [8 empty] | 2024
ZEN-17 | South King | ZEN | X | X | X | X | [5 empty] | X | X | [6 empty] | F
ZEN-23 | South King | ZEN | X | X | X | X | [5 empty] | X | X |  |  |  | 2024 |  |  | F
ZEN-24 | South King | ZEN | X | X | X | X | [5 empty] | X | X | [6 empty] | F
ZEN-25 | South King | ZEN | X | X | X | X | [5 empty] | X | X |  |  |  | 2025 |  |  | F
ZEN-26 | South King | ZEN | X | X | X | X | [5 empty] | X | X | [6 empty] | F
REVISED VERSION 4/14/2022
REVISED TEXT IN RED