## Go Live Date 2.2.15
Project Compass Communication Timeline
DRAFT
Updated 12-9-14
Peggy Blowers, Debbie Simock
|  | 2nd Q 2014 | [13 empty] | 3rd Q 2014 | [12 empty] | 4th Q 2014 | [12 empty] | 1st Q 2015
|  | April |  |  |  |  | May |  |  |  | June |  |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  |  | Media | Total | Original | Budget | April
|  | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 2 | 9 | 16 | 23 | 30 | 30 | 30 | 30 | 30 | 6 | 13 | 20 | 27 | 30
GO LIVE
Color Key - gray is development and review timeline; colors indicate the time period communications wil be occurring. | bar: July 7 to August 4; August 18 to September 1; September 15 to September 22; October 20 to February 2; February 16 to Budget 30
[43 empty] | Announce & Inform |  |  | Instruct & Re-enforce
CONNECTIONS NEWSLETTER | bar: September 8 to September 29; January 5 to January 26; Total 30 to Budget 30
C&I COMMUNICATION BILL INSERT OR DIRECT MAIL | bar: January 5 to February 2; Total 30 to Budget 30
PR/NEWS STORIES (Tentative)
Information Guide Release | bar: January 12; Total 30 to Budget 30
Change is here: New bill and account number; Benefits of new CC&B. | bar: February 9; Total 30 to Budget 30
Post-launch issues management (if necessary) | bar: February 16 to March 30; Total 30 to Budget 30
DIRECT MAIL-RESIDENTIAL& | bar: January 12; Total 30 to Budget 30
C&I w SPECIAL ENVELOPE | bar: January 12; Total 30 to Budget 30
BILL INSERTS | bar: February 2 to March 23; Total 30 to Budget 30
Feb. insert production timeline | bar: Total 30 to Budget 30
Mar. insert production timeline | bar: Total 30 to Budget 30
CHANGE MESSAGE PRINTED ON | bar: February 9 to March 30; Total 30 to Budget 30
SPECIAL BILL MAILING ENVELOPE | bar: Total 30 to Budget 30
BILL MESSAGE CENTER | bar: Total 30 to Budget 30
Targeted message for residential and C&I | bar: February 2 to April 27
Targeted Cusomter Segment Communications
Area/Street Lights | bar: January 5 to January 26
APS - Postcard | bar: January 5 to January 26
Landlords | bar: January 5 to January 26
Prior Ob (TBD)
3rd Party Notification (TBD)
Collection Agencies
Wind Power | bar: January 19 to March 16
SOCIAL MEDIA | bar: January 12 to March 23; Total 30 to Budget 30
EBLAST (May be Direct Mail) | bar: Total 30 to Budget 30
Anchor Communication piece (specific to e-bill customers) | bar: January 12; Total 30 to Budget 30
QUESTLINE | bar: January 12; Total 30 to Budget 30
C&I BUSINESS ONE-SHEET | bar: Total 30 to Budget 30
WEBPAGE and VIDEO
Reminder of blackout | bar: January 26 to February 2
Web content goes live: How to read your bill; Direct mail piece; FAQ; video | bar: February 9 to April 27
EVP/IVR
On-hold message: Change is coming | bar: January 12 to January 26; Total 30 to Budget 30
On-hold message: Information about the conversion taking place over the weekend and the website being down | bar: January 26 to February 2; Total 30 to Budget 30
On-hold message: Information about new bill and new account number reminders | bar: February 2 to March 2; Total 30 to Budget 30
GO-LIVE EMPLOYEE COMMUNICATIONS | bar: February 2
eView | bar: January 19
Interim message to employees | bar: January 26
Executive Steering Committee Announcement | bar: January 26
Project Team Announcement | bar: January 26
Leadership Announcement | bar: January 26
All employee announcement | bar: January 26
eView Extra | bar: January 26
Weclome to Maximo | bar: January 26
Welcome to CC&B | bar: January 26
AVAnet Home Page Announcement | bar: January 26
Web update | bar: January 26
Any needed talking points to CSR's | bar: January 26
POST GO-LIVE EMPLOYEE COMMUNICATIONS | bar: February 9 to April 30
eView | bar: February 2
TBD

## Go Live Date 10.6.14
Project Compass Customer Communications Timeline
DRAFT
Updated 5 -29-2014
|  | 2nd Q 2014 | [13 empty] | 3rd Q 2014 | [12 empty] | 4th Q 2014 | [12 empty] | 4th Q 2014
|  | April |  |  |  |  | May |  |  |  | June |  |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  |  | October |  |  |  | November |  |  |  |  | December |  |  |  | Media | Total | Original | Budget
|  | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | Cost | Spent | Budget | Remaining
LIVE
Color Key - gray is development and review timeline; colors indicate the time period communications wil be occurring. | bar: July 7 to August 4; August 18 to September 1; September 15 to September 22; October 6; October 20 to December 22
[7 empty] | Context Setting | [18 empty] | Announce & Inform |  |  | Instruct & Re-enforce
CONNECTIONS NEWSLETTER | bar: May 5 to May 26
C&I COMMUNICATION BILL INSERT OR DIRECT MAIL | bar: September 8 to October 6
PR/NEWS STORIES
Information Guide Release | bar: September 15
Change is here: New bill and account number; Benefits of new CC&B. | bar: October 13
Post-launch issues management (if necessary) | bar: October 20 to December 1
DIRECT MAIL-RESIDENTIAL& | bar: September 15
C&I w SPECIAL ENVELOPE | bar: September 15
BILL INSERTS | bar: October 6 to November 24
Oct. insert production timeline
Nov. insert production timeline
CHANGE MESSAGE PRINTED ON | bar: October 13 to December 1
SPECIAL BILL MAILING ENVELOPE
BILL MESSAGE CENTER
Targeted message for residential and C&I | bar: October 6 to December 29
BLOG AND SOCIAL MEDIA | bar: September 15 to November 24
EBLAST
Anchor Communication piece (specific to e-bill customers) | bar: September 15
QUESTLINE | bar: September 15
C&I BUSINESS ONE-SHEET
WEBPAGE and VIDEO
Reminder of blackout | bar: September 29 to October 6
Web content goes live: How to read your bill; Direct mail piece; FAQ; video | bar: October 13 to December 29
EVP
On-hold message: Change is coming | bar: September 15 to September 29
On-hold message: Information about the conversion taking place over the weekend and the website being down | bar: September 29 to October 6
On-hold message: Information about new bill and new account number reminders | bar: October 6 to November 3