## Summary
EIM estimated non-labor for Oct 2021-Sept 2022
Utilicast | 438250
CAISO pmts | 150000
588250
P/T Ratio | 386127.3 | WA Share
| 65.64% | WA
| 34.36% | ID

## CAISO
Activity
Project Delivery Dates supporting
March 2, 2022 Go-Live
Detailed Project Management Plan | March 2019-December 2019
The Parties will develop and initiate a final project management plan that describes specific project tasks each Party must perform, including delivery dates, project team members, meeting requirements, and a process for approving changes to support completion of the Project. This phase will include a detailed IT system review to assist Avista in development of a detailed metering plan, bid-to-bill system and coordination with Avista EMS. Work will be initiated on the Avista staff training program using the foundational and detailed system computer-based training module, as well as on the resource data templates needed during Milestone 2.
· Milestone 1 – This milestone is completed when the Agreement has been made effective in accordance with Section 1 of the Agreement. | 2020-04-01
Full Network Model Expansion | 2020-11-01
Full Network Model expansion for Avista and EMS/SCADA including: proof of concept of export/import of EMS data, complete model into the CAISO test environment, complete validation for all SCADA points from Avista, testing of the new market model and validation of the Outage and State Estimator applications.
· Milestone 2 – This milestone is completed upon modeling Avista into the CAISO Full Network Model through the EMS which will be deployed into a non-production test environment using the CAISO's network and resource modeling process. | 2021-06-30
System Implementation and Connectivity Testing | 2021-08-01
System requirements and software design, the execution of necessary software vendor contracts, development of Market network model including Avista, allow Avista to connect to a non-production test system.
· Milestone 3 | 2021-07-15
CAISO to promote market network model including Avista area to non-production system, and allow Avista to connect and exchange data in advance of Market Simulation.
Construction, Testing and Training in Preparation for Market Simulation - This task includes IT infrastructure upgrades, security testing, training, Day-in-life simulation and functional testing. | 2021-07-15
· Milestone 4a | Mid-July 2021
Start of Joint Integration Testing with CAISO, Interface testing with minimum data requirements and functional integration testing. CAISO will make the test environment available for Avista connectivity testing prior to the delivery date assuming Avista has provided all prerequisite data and non-production system availability does not conflict with CAISO production system Spring Release schedule.
· Milestone 4b – Begin ‘Day in the Life’ scenario testing | 2021-09-01
· Milestone 4c – Begin Structured Market simulation | 2021-10-01 | 50000
(Milestone 4 payment due at this point)
Activate Parallel Operations | 2021-12-01
During December 2021, the CAISO will activate a parallel operation environment to practice production grade systems integration as well as market processes and operating procedures in anticipation of the impending Avista activation as an EIM Entity and to confirm compliance with the EIM readiness criteria set forth in the CAISO tariff.
· Milestone 5 – Start of parallel operations | 2021-12-01 | 50000
System Deployment and Go Live | 2022-03-02
Implementing the Project and going live will include resource registration, operating procedures and updates, execution of service agreements, completion of the Avista tariff process, applicable board approvals, the filing and acceptance of service agreements and tariff changes with FERC, and completion and filing of a readiness criteria certification in accordance with the CAISO tariff.
· Milestone 6 – This milestone is complete upon the first production Avista EIM trade date. | 2022-03-02 | 50000
150000

## Utilicast
Estimated Utilicast commitments as of 9/22/2020 per Kelly
| 2021 (Full Yr) | 2022 (Mar end)
Utilicast | 481000 | 318000
*Note: 2021 payment timing is unknown, following assumes equal pay every month of year
120250 | ($481k adjusted for Oct-Dec 2021)
318000
438250