## REDACTED
Redacted Version
Redacted Version

## TOC
Smart Grid Business Case Model
Contents
I | Overview
Summary
Sensativity Analysis
Project and Resource Planning
Risk Assessment
MATRIX: Smart Grid Applications and Owners
II | Data Totals
III | Scenario Analysis
Scenario 0: Status Quo
Scenario 1: Gradual AMI
Scenario 2: Hybrid-New Vendor
Scenario 3: Hybrid-L+G
Scenario 4: Full Deployment
IV | Charts
Annual AMI Deployment by Scenario
L+G Annual Supported Meters by Scenario
Annual Net Benefits by Scenario
Cumulative Annual Net Benefits by Scenario
L+G Total Managed Service Contract Cost by Scenario
Total Termination Fees by Scenario
NPV of Network Expenditures by Scenario
Total AMI Deployment Costs by Scenario
NPV and Net TCO of Scenarios
Retern on Investment (ROI) Analysis
Internal Rate of Return (IRR) Analysis
Total Cost of Ownership (TCO) of Scenarios
Capital vs O&M Costs
Cost Breakdowns by Scenario
Network Breakdown by Scenario
Total Nomainal Cost Breakdown by Scenario
Sensativity Analysis
Additional Charts for Presentations
V | Data Sources
Silver Spring NOC Costs Summary
Silver Spring NOC Costs Proforma
Gas First Response Meter Exchange Costs
Meter Cost Study Installatio Cost Data
Meter Cost Study Meter Costs
PSE 2011 Corporate Customer Forecast
Contract Termination Fees Calculations
JC's TCO Model Inputs
VI | Glossary
DRAFT

## Summary
Smart Grid Investment Model
This file contains financials model of several smart-grid technology deployment scenarios. The purpose of this model is to provide an overview of the costs and benefits of different technology strategies.
|  |  | Tab Color Guide | Proformas | Data | Charts | Assumptions | Business Case Analysis
| # | Option | Description | L+G Contract Action | Network Architecture | AMR Coverage | AMI Coverage | AMI % of customers by 2024 | AMI Deployment Timeframe | Pros | Cons | Issues
| 0 | Status Quo | Continue to leverage the existing L+G contract for meter reading services. In April 2016, PSE will assume ownership, operation and maintenance of all network equipment. | Status Quo | Existing AMR Network maintained | 100% | Filler solution-small pilot | 0% | N/A | The L+G contract terms, costs and relationship are well known. The majority of existing processes can be transitioned to PSE as appropriate or be subcontracted to a third party as needed. | L+G is not able to fulfill all of PSE's service requirements. PSE is provided with mediocre network performance, a high manual read rate and inadequate load profile and demand services. O&M costs are high. There are few to no options for distribution automation, no potential for remote disconnect programs, few options for new customer service options. | In 2016, ownership of the existing L+G network will be transferred to PSE. PSE will need to maintain the existing L+G network infrastructure.
| 1 | Gradual AMI | Add a second two-way network and passively add AMI as AMR meters are retired and as new customers add service. | Ramp down | L+G AMR AND a New Vendor's Network by 2014 | Reduce by attrition. | Advanced read meters + attrition and growth | XXXXXX | 10+years | PSE can keep the L+G contract for the majority of its customers but can utilize a new, optimized two-way network for AMI and other smart grid applications. PSE can leverage its existing base of AMR meters and can add AMI where needed. Two networks allow PSE to continuously pursue the most cost effective meter/module technology. Two networks provide potential redundancy for key DA devices. | PSE will have to pay for the cost of the two way network and data hosting. PSE will have to manage L+G and another network vendor. PSE will still need to manage the network ownership transition in 2016. | In 2016, ownership of the existing L+G network will be transferred to PSE. PSE will need to maintain the existing L+G network infrastructure.
| 2 | Hybrid-New Vendor | Replace the existing L+G network infrastructure with a new two-way system and utilize a minimal starting deployment of AMI to further enable mesh communications. | Termination in 2016. | 2-WAY hybrid network ONLY by 2016 | Reduce by attrition. | Advanced read meters + attrition and growth |  | 10+years | The large reduction in meter read fees reduces O&M. The hybrid network can potentially read L+G meters AND meters/modules from another vendor. O&M costs are greatly reduced. | PSE must develop the intellectual property to process AMR reads, AMI will not be available for all customers, PSE will pay significant termination fees. Which is a large O&M hit in one year. | Developing the intellectual property required to read AMR meters is risky and has many unknowns.
| 3 | Hybrid-L+G | Replace any AMR network equipment with new Hybrid-L+G equipment. Extend the metering contract with L+G and upgrade the terms of the contract. | Renegotiation | 2-Way L+G network ONLY by 2014. | Reduce by attrition. | Advanced read meters + attrition and growth | XXXXXX | 10+years | Hybrid-L+G is already partially deployed. In 2012, PSE will conduct a small pilot of AMI meters using this technology. | PSE will be fully committed to a relationship with L+G for all smart grid communications. PSE will have to deploy ONLY L+G or compatible modules, which limits PSE's ability to purchase other technologies or negotiate on costs. | A wholesale network upgrade will require complete re-negotiation of the existing L+G contract.
| 1 | Hybrid AMI | In April 2016, PSE will assume ownership, operation and maintenance of all network equipment. Utilizing the L+G 2-way technology, PSE will build out an AMI network from 2016-2018. Initial deployments of AMI will be based on business needs, followed by replacement for attrition and growth going forward. | Renegotiation | L+G AMR Network is upgraded to 100% two way from 2016-2017. | AMR meters are phased out over 10 years. | AMI meters are deployed over 10 years. | #VALUE! | 10 years | Allows PSE to move to L+G's next generation of meter reading technology gradually. Organizational and contractual risks will be lower due to the continued relationship with an existing vendor. | PSE will be fully committed to a relationship with L+G for all smart grid communications. PSE will have to deploy ONLY L+G or compatible modules, which limits PSE's ability to purchase other technologies or negotiate on costs. | L+G's AMI solution still has many shortcomings and gas AMI solutions are likely to continue to be a pain point.
| 2 | Two Networks Two Vendors | This scenario deploys 2 AMI networks: 1) L+G's Gridstream over all electric service territories and 2) A second vendor's technology over the gas service territories. Both will be built out over 2016-2017. Deployments of AMI meters will be the same as in the "Hybrid AMI" scenario. | Starting in 2016, PSE will start to exercise meter minimum off-ramp. New contract required for each vendor. | Two-vendors, L+G mesh technology in the electric areas and another vendor in the gas areas. | AMR meters are phased out over 10 years. | AMI meters are deployed over 10 years. | #VALUE! | 10 years | PSE can move towards next generation metering and billing technologies, enhancing customer service. Having two different vendors provides PSE with more options to address gas operational challenges and establishes more contractual leverage, which may lead to better pricing for meter radios and possibly meters. | Two contracts may be more difficult to manage. PSE will need to manage two separate networks and additional field device. PSE will have to develop stores, engineering and meter operations processes/practices and there will be additional maintenance and overhead expenses. | PSE will need to issue an RFP and research the product quality of an alternate vendor.
| 3 | Full Deployment | This scenario installs a new two-way network with a new vendor and converts all meters to AMI over three years. | Complete termination by 2018. PSE must pay meter reduction fees and a termination fee. | New two-way network. Installed over 2 years (2016-2017) | AMR meters are phased out from 2016 to 2018. | Meters are 100% deployed from 2016-2018. | #VALUE! | 3 years | An optimal AMI network can be deployed and maintained at a significantly lower cost. A full deployment would enable the largest reduction in O&M expenditures. | PSE must pay large contract termination fees to L+G which would result in a significant near-term hit to O&M. Replacing all AMR meters is expensive, requires significant workforce planning and would result in capital write-offs. | A significant ramp-up in resources would be required to move forward this rapidly.
| a | Meter Minimum | Reduce the number of existing AMR meters to the L+G contract meter floor and replace those meters with AMI. | Reduce to and maintain AMR at the L+G contract meter minimum | AMR AND 2-Way by 2016 | Reduce to and maintain AMR at the L+G contract meter minimum | Following meter minimums. | XXXXXX | 10+years | Reduction in L+G meter read fees. No new negotiation or payment of any contract penalty. | PSE will have to manage L+G and another network vendor. | In 2016, ownership of the existing L+G network will be transferred to PSE. PSE will need to maintain the existing L+G network infrastructure.
| b | Meter Floor | Reduce the number of existing AMR meters to the absolute minimum (meter floor) allowed under the L+G contract and replace those meters with AMI. | Reduce to and maintain AMR at the L+G contract meter floor. | AMR AND 2-Way by 2015 | Reduce to and maintain AMR at the L+G contract meter floor. | Following the meter floor. | XXXXXX | 10+years | Reduction in L+G meter read fees. No new negotiation. | PSE must pay meter reduction fees when the number of AMR meters deployed drops below the meter minimum. PSE will have to manage L+G and another network vendor. | In 2016, ownership of the existing L+G network will be transferred to PSE. PSE will need to maintain the existing L+G network infrastructure.
| 4 | L+G Proposal | PSE will continue to utilize L+G as its meter reading service provider as is done today. L+G will build out an AMI network from 2014-2016. PSE will do initial deployments of electric AMI based on business needs and then continue to replacement for attrition and growth going forward. L+G will replace all gas endpoints by 2020. | Renegotiation | L+G AMR Network is upgraded to 100% two way from 2016-2017. | AMR meters are phased out over 10 years. | AMI meters are deployed over 10 years. | #VALUE! | 10 years | Allows PSE to move to the next generation of meter reading technology gradually. Organizational and contractual risks will be lower due to the continued relationship with an existing vendor. The managed service contract allows PSE to avoid some large capital expenditures to upgrade its network as well as avoid the operational and financial risks of taking services which are currently performed by L+G, in house. | Cost for this option exceed alternatives and increase O&M requirements. PSE will be fully committed to a relationship with L+G for all smart grid communications. PSE will have to deploy ONLY L+G or compatible modules, which limits PSE's ability to purchase other technologies or negotiate on costs. | L+G's AMI solution still has many shortcomings and gas AMI solutions are likely to continue to be a pain point.
DRAFT

## Sensitivity (hidden)
Sensitivity Analysis
Note: This Data is hard coded and out of Date.
| 150% of Baseline Costs | Electric Meter Exchange Labor ($) | Meter & Module Hardware ($) | Post 2016 Read Fees ($) | Termination Fees ($) | AMI Network Devices (#) | AMI Network Equipment Cost ($) | Network Installation Costs (AMI and AMR) ($) | AMR Network Maintenance Visits ($) | Manual Read Rate (%) | Baseline | Check
| #VALUE! | -117.2266 | -167.5683 | -57.01 | -116.2381 | -148.0211 | -118.76 | -116.696 | -130.0327 | -116.3019 | -116.2381 | #VALUE! | -111.906
| #VALUE! | 10.2701 | -33.4649 | 225.18 | 6.9333 | -23.1438 | 4.91 | 7.9851 | 11.782 | 11.5126 | 11.5606 | #VALUE! | 7.5986
| Meter Minimum | -135.9341 | -222.6348 | -30.31 | -135.4288 | -157.8031 | -139.07 | -135.8867 | -138.2324 | -135.5489 | -135.4288 | #REF! | -135.4288
| Meter Floor | -126.4224 | -229.1905 | 23.49 | -137.0149 | -148.438 | -129.71 | -126.5216 | -128.8673 | -126.2803 | -126.0638 | #REF! | -126.0638
| Full Deployment | -149.0971 | -291.6923 | 71.15 | -164.6353 | -170.2913 | -151.56 | -148.375 | -138.9314 | -148.2187 | -147.9171 | 184.4321 | -147.9171
| 50% of Baseline Costs | Electric Meter Exchange Labor ($) | Meter & Module Hardware ($) | Post 2016 Read Fees ($) | Termination Fees ($) | AMI Network Devices (#) | AMI Network Equipment Cost ($) | Network Installation Costs (AMI and AMR) ($) | AMR Network Maintenance Visits ($) | Manual Read Rate (%) | Baseline
| #VALUE! | -115.2496 | -64.9079 | -143.9 | -116.2381 | -84.4551 | -113.72 | -115.7777 | -102.4487 | -116.1743 | -116.2381
| #VALUE! | 12.8511 | 56.5862 | -99.83 | 16.188 | 46.2651 | 18.21 | 15.1388 | 11.3341 | 11.6087 | 11.5606
| Meter Minimum | -134.9235 | -48.2229 | -185.78 | -135.4288 | -113.0546 | -131.79 | -134.9684 | -132.6304 | -135.3087 | -135.4288
| Meter Floor | -125.7051 | -22.9371 | -204.95 | -115.1127 | -103.6895 | -122.42 | -125.6033 | -123.2653 | -125.8472 | -126.0638
| Full Deployment | -146.737 | -4.1419 | -264.76 | -131.1989 | -125.5428 | -144.27 | -147.4566 | -156.9079 | -147.6155 | -147.9171
| 150% of Baseline Costs | Electric Meter Exchange Labor ($) | Meter & Module Hardware ($) | Post 2016 Read Fees ($) | Termination Fees ($) | AMI Network Devices (#) | AMI Network Equipment Cost ($) | Network Installation Costs (AMI and AMR) ($) | AMR Network Maintenance Visits ($) | Manual Read Rate (%) | Baseline | Check
| #VALUE! | -0.8504% | -44.16% | 50.95% | 0% | -27.34% | -2.17% | -0.3939% | -11.87% | -0.05491% | -116.2381 | #VALUE!
| #VALUE! | -11.16% | -389.5% | 1848% | -40.03% | -300.2% | -57.53% | -30.93% | 1.915% | -0.4154% | 11.5606 | #VALUE!
| Meter Minimum | -0.3731% | -64.39% | 77.62% | 0% | -16.52% | -2.689% | -0.3381% | -2.07% | -0.08867% | -135.4288 | #REF!
| Meter Floor | -0.2845% | -81.81% | 118.6% | -8.687% | -17.75% | -2.892% | -0.3632% | -2.224% | -0.1718% | -126.0638 | #REF!
| Full Deployment | -0.7978% | -97.2% | 148.1% | -11.3% | -15.13% | -2.463% | -0.3096% | 6.075% | -0.2039% | -147.9171 | 1328.0664
| 50% of Baseline Costs | Electric Meter Exchange Labor ($) | Meter & Module Hardware ($) | Post 2016 Read Fees ($) | Termination Fees ($) | AMI Network Devices (#) | AMI Network Equipment Cost ($) | Network Installation Costs (AMI and AMR) ($) | AMR Network Maintenance Visits ($) | Manual Read Rate (%) | Baseline
| #VALUE! | 0.8504% | 44.16% | -23.8% | 0% | 27.34% | 2.166% | 0.3961% | 11.86% | 0.05491% | -116.2381
| #VALUE! | 11.16% | 389.5% | -963.5% | 40.03% | 300.2% | 57.52% | 30.95% | -1.96% | 0.4154% | 11.5606
| Meter Minimum | 0.3731% | 64.39% | -37.18% | 0% | 16.52% | 2.687% | 0.34% | 2.066% | 0.08867% | -135.4288
| Meter Floor | 0.2845% | 81.81% | -62.58% | 8.687% | 17.75% | 2.89% | 0.3653% | 2.22% | 0.1718% | -126.0638
| Full Deployment | 0.7978% | 97.2% | -78.99% | 11.3% | 15.13% | 2.466% | 0.3113% | -6.078% | 0.2039% | -147.9171

## PCP (hidden)
PCP for AMI Meters + Head-end Set-up
Cost | Calculations | 2015-2017 Nominal Spend | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023
Meter Engineering (1 FTE) | $150/year in $2012 | #VALUE! |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Meter Hardware | [(5% of customer meters X meter cost)-(attrition rate X customer meters X cost of amr meter (and module post 2016) ] X (stores overhead)] | #VALUE! |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Meter Installation | (5% - attrition rate) x # customer meters X cost of a meter exchange | #VALUE! |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Deployment Project Management (I FTE) | $150/year in $2012 | #VALUE! | 2015: #VALUE!; 2016: #VALUE!; 2017: #VALUE!
Head End & MDMS Configuration and Development L+G (SS set up estimate) | $330,000 in 2012 | #VALUE! | 2015: #VALUE!
Head End & MDMS Configuration and Development PSE (1.5 FTEs) | $330,000 in 2012 | #VALUE! |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | #VALUE! | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Assumptions
[5 empty] | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05

## 5-Year Budget (R)
Row # |  | Director/Officer | Contact | Work Group | CAPEX vs O&M |  | (denomination) | Description | Calculation/Source Description | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | Total
Project Management
1 |  | Joe Beer | Laura Feinstein/Veronica Dreher | Smart Meter Technology | O&M | Labor | ($Millions) | One contract Project Manager | I FTE for one year split between 2015-2016 | 0 | 0 | 0.33772 | 0.34447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Module Maintenance and Growth
3 |  | Harry Shapiro/Durga Doraisamy | Harry Shapiro/Durga Doraisamy | Gas Ops/Capital Budgeting | CAPEX | Materials | ($Millions) | PSE Gas Module Purchases for Maintenance | [(PSE Gas Module Exchange rate) X (# Gas customers) X (weighted average gas module cost)]+[(L+G Gas Module Exchange rate) X (# Gas customers) X (weighted average gas module cost)] | 0 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
4 |  | Harry Shapiro/Durga Doraisamy | Harry Shapiro/Durga Doraisamy | Gas Ops/Capital Budgeting | CAPEX | Labor | ($Millions) | New PSE Gas Module Exchanges | (L+G Gas Module Exchange rate) X (# Gas customers) X ( gas module exchange cost) | 0 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
5 |  | Ed Schild/ Durga Doraisamy | Mike Herndon | Electric Operations | CAPEX | Materials | ($Millions) | PSE Electric Module Purchases for Maintenance | (Annual Electric Meter Attition Rate) X (# of meters in service) X (cost of electric modules) | 0 | 0 | 0 | 0.26425 | 0.36785 | 0.38366 | 0.47773 | 0.56963 | 0.65563 | 0.74296 | 0.84239 | 0.95406 | 1.0557 | 1.0982 | 1.0548 | 0.95243 | 0.85138 | 0.71221 | 0.55813 | 0.4852 | 0.53077 | 0.93461 | 0.72643 | 0.55688 | 0.46254 | 0.45186 | 0.53925 | 0.088501 | 7.4121
6 |  | Ed Schild/ Durga Doraisamy | Mike Herndon | Electric Operations | CAPEX | Revenue | ($Millions) | Electric MARP & MDMS Reimbursements | Forecaast done by Jennifer Cummings and Theresa Burch | -0.20907 | -0.19268 | -0.18556 | -0.045656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.63296
7 |  | Rex Pietzyk | Theresa Burch | Meter Data | O&M | Labor | ($Millions) | FTE to Manage Module Maintenance Flags/Inventory/ Testing (Annual $) | Estimated costs of one FTE | 0 | 0 | 0 | 0.1182 | 0.16075 | 0.16397 | 0.16725 | 0.17059 | 0.17401 | 0.17749 | 0.18104 | 0.18466 | 0.18835 | 0.19212 | 0.19596 | 0.19988 | 0.20388 | 0.20795 | 0.21211 | 0.21635 | 0.22068 | 0.22509 | 0.2296 | 0.23419 | 0.23887 | 0.24365 | 0.24852 | 0.25349 | 1.8784
8 |  | Joe Beer | Laura Feinstein | Standards | O&M | Labor | ($Millions) | Electric Meter Commodities and Standards Engineering | 1 FTE | 0.1326 | 0.13525 | 0.13796 | 0.14072 | 0.14353 | 0.1464 | 0.14933 | 0.15232 | 0.15536 | 0.15847 | 0.16164 | 0.16487 | 0.16817 | 0.17153 | 0.17496 | 0.17846 | 0.18203 | 0.18567 | 0.18939 | 0.19317 | 0.19704 | 0.20098 | 0.205 | 0.2091 | 0.21328 | 0.21754 | 0.21754 | 0.2219 | 2.1181
9 |  | Joe Beer | Laura Feinstein | Standards | O&M | Labor | ($Millions) | Gas Module Specification | 1/5 of an FTE | 0.02652 | 0.02705 | 0.027591 | 0.028143 | 0.028706 | 0.02928 | 0.029866 | 0.030463 | 0.031072 | 0.031694 | 0.032328 | 0.032974 | 0.033634 | 0.034306 | 0.034993 | 0.035692 | 0.036406 | 0.037134 | 0.037877 | 0.038635 | 0.039407 | 0.040195 | 0.040999 | 0.041819 | 0.042656 | 0.043509 | 0.043509 | 0.044379 | 0.42363
10 |  | Harry Shapiro/Durga Doraisamy | Vincent Fong/Purchasing | Plant Accounting TBD | CAPEX | Materials | ($Millions) | Gas Modules (on New Meters) | (# Growth in Gas customers) X (weighted average gas module cost) | 0 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
11 |  | Ed Schild/ Durga Doraisamy | Vincent Fong/Purchasing | Plant Accounting TBD | CAPEX | Materials | ($Millions) | Electric Modules on New Meters | (# Growth in electric customers) X (weighted average electric module cost) | 0 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
14 |  |  |  |  | CAPEX |  | ($Millions) | Total Growth and Maintenance Module Costs |  | -0.049949 | -0.030377 | -0.020009 | 5.9728 | 8.349 | 8.6857 | 8.9057 | 9.2118 | 9.6399 | 10.0956 | 10.5818 | 11.083 | 11.5869 | 12.0489 | 12.4367 | 12.7697 | 13.1316 | 13.457 | 13.7786 | 14.1919 | 14.7376 | 15.1207 | 15.4368 | 15.8116 | 16.2825 | 16.6127 | 17.2945 | 17.4663 | 106.0608
15 | Pole Attachments
16 |  | Wayne Gould | Tim Gasser | Contract Management | O&M | Labor | ($Millions) | 3rd Party Pole Attachment Leases Estimate |  | 0 | 0 | 0 | 0.38544 | 0.39485 | 0.40448 | 0.41435 | 0.42446 | 0.43482 | 0.44543 | 0.4563 | 0.46743 | 0.47884 | 0.49052 | 0.50249 | 0.51475 | 0.52731 | 0.54018 | 0.55336 | 0.56686 | 0.58069 | 0.59486 | 0.60937 | 0.62424 | 0.63947 | 0.65508 | 0.67106 | 0.68743 | 4.7969
17 |  | Wayne Gould | Tim Gasser | Contract Management | O&M | Labor | ($Millions) | 1/2 FTE to Manage Pole Attachments |  | 0 | 0 | 0 | 0.07488 | 0.076378 | 0.077905 | 0.079463 | 0.081053 | 0.082674 | 0.084327 | 0.086014 | 0.087734 | 0.089489 | 0.091278 | 0.093104 | 0.094966 | 0.096865 | 0.098803 | 0.10078 | 0.10279 | 0.10485 | 0.10695 | 0.10909 | 0.11127 | 0.11349 | 0.11576 | 0.11808 | 0.12044 | 0.91119
18 |  | Durga Doraisamy | ??? | Revenue Forecasting | Revenue | Revenue | ($Millions) | Unmetered energy (currently billed to L+G) |  | -0.13473 | -0.13756 | -0.14045 | -0.03585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.44859
19 |  | Wayne Gould | Tim Gasser | Contract Management | O&M | Revenue | ($Millions) | Unmetered energy (PSE needs to pay to other utilities) |  | 0 | 0 | 0 | 0.02715 | 0.036924 | 0.037663 | 0.038416 | 0.039184 | 0.039968 | 0.040767 | 0.041583 | 0.042414 | 0.043263 | 0.044128 | 0.04501 | 0.045911 | 0.046829 | 0.047766 | 0.048721 | 0.049695 | 0.050689 | 0.051703 | 0.052737 | 0.053792 | 0.054868 | 0.055965 | 0.055965 | 0.057084 | 0.43146
20 |  |  |  |  | O&M |  | ($Millions) | Total Pole Attachment Costs |  | -0.13473 | -0.13756 | -0.14045 | 0.45163 | 0.50815 | 0.52005 | 0.53223 | 0.5447 | 0.55746 | 0.57052 | 0.58389 | 0.59758 | 0.61159 | 0.62593 | 0.6406 | 0.65563 | 0.671 | 0.68674 | 0.70286 | 0.71935 | 0.73623 | 0.75351 | 0.7712 | 0.7893 | 0.80783 | 0.8268 | 0.8451 | 0.86496 | 5.691
21 | Network Maintenance
22 |  | Margaret Hopkins | Charlie Seese | Telecom | CAPEX | Materials | ($Millions) | AMR Network growth (CM & MCC) |  | 0 | 0 | 0 | 0.35226 | 0.5124 | 0.53624 | 0.56119 | 0.5873 | 0.61462 | 0.64321 | 0.67314 | 0.70446 | 0.73723 | 0.77153 | 0.80743 | 0.84499 | 0.88431 | 0.92545 | 0.96851 | 1.0136 | 1.0607 | 1.1101 | 1.1617 | 1.2158 | 1.2723 | 1.3315 | 1.3935 | 1.4583 | 6.6936
23 |  | Margaret Hopkins | Charlie Seese | Telecom | CAPEX | Labor | ($Millions) | AMR Network growth (CM&MCC Labor) |  | 0 | 0 | 0 | 0.14061 | 0.19602 | 0.20493 | 0.21426 | 0.22401 | 0.2342 | 0.24486 | 0.256 | 0.26765 | 0.27982 | 0.29256 | 0.30587 | 0.31978 | 0.33433 | 0.34955 | 0.36545 | 0.38208 | 0.39946 | 0.41764 | 0.43664 | 0.45651 | 0.47728 | 0.49899 | 0.5217 | 0.54544 | 2.5549
24 |  | Margaret Hopkins | Charlie Seese | Telecom | O&M | Materials | ($Millions) | Back-up Batteries
25 |  | Margaret Hopkins | Charlie Seese | Telecom | O&M | Materials | ($Millions) | AMR Network maintenance (CM &MCC) |  | 0 | 0 | 0 | 0.19304 | 0.28079 | 0.29386 | 0.30753 | 0.32184 | 0.33681 | 0.35248 | 0.36888 | 0.38604 | 0.404 | 0.4228 | 0.44247 | 0.46305 | 0.4846 | 0.50714 | 0.53074 | 0.55543 | 0.58127 | 0.60831 | 0.63662 | 0.66623 | 0.69723 | 0.72967 | 0.76362 | 0.79915 | 3.6681
26 |  | Margaret Hopkins | Charlie Seese | Telecom | O&M | Labor | ($Millions) | AMR Network maintenance (CM& MCC Labor) |  | 0 | 0 | 0 | 0.75367 | 1.0614 | 1.1207 | 1.1828 | 1.2481 | 1.3165 | 1.3883 | 1.4636 | 1.5426 | 1.6254 | 1.7122 | 1.8032 | 1.8987 | 1.9987 | 2.1036 | 2.2135 | 2.3287 | 2.4495 | 2.576 | 2.7086 | 2.8475 | 2.9931 | 3.1456 | 3.3053 | 3.4727 | 14.4153
27 |  | Margaret Hopkins | Charlie Seese | Telecom | O&M | Labor | ($Millions) | Network Construction Management (1/2 FTE) |  | 0 | 0 | 0 | 0.059101 | 0.080377 | 0.081985 | 0.083624 | 0.085297 | 0.087003 | 0.088743 | 0.090518 | 0.092328 | 0.094175 | 0.096058 | 0.097979 | 0.099939 | 0.10194 | 0.10398 | 0.10606 | 0.10818 | 0.11034 | 0.11255 | 0.1148 | 0.11709 | 0.11944 | 0.12182 | 0.12426 | 0.12675 | 0.93921
28 |  | Margaret Hopkins | Charlie Seese | Telecom | O&M | Labor | ($Millions) | Network Maintenance Management |  | 0 | 0 | 0 | 0.1182 | 0.16075 | 0.16397 | 0.16725 | 0.17059 | 0.17401 | 0.17749 | 0.18104 | 0.18466 | 0.18835 | 0.19212 | 0.19596 | 0.19988 | 0.20388 | 0.20795 | 0.21211 | 0.21635 | 0.22068 | 0.22509 | 0.2296 | 0.23419 | 0.23887 | 0.24365 | 0.24852 | 0.25349 | 1.8784
30 | [6 empty] | ($Millions) | Total Network Maintenance |  | 0 | 0 | 0 | 1.6169 | 2.2917 | 2.4016 | 2.5167 | 2.6371 | 2.7632 | 2.8951 | 3.0332 | 3.1777 | 3.329 | 3.4873 | 3.6529 | 3.8263 | 4.0078 | 4.1977 | 4.3964 | 4.6043 | 4.8219 | 5.0497 | 5.2879 | 5.5373 | 5.7982 | 6.0712 | 6.3569 | 6.6558 | 30.1495
31 | Communications Backhaul
32 |  | Margaret Hopkins | Charlie Seese | Telecom | O&M | Fee | ($Millions) | FCC License Renewal Costs |  | 0 | 0 | 0 | 0.00014127 | 0.00019231 | 0.00019635 | 0.00020048 | 0.00020469 | 0.00020898 | 0.00021337 | 0.00021785 | 0.00022243 | 0.0002271 | 0.00023187 | 0.00023674 | 0.00024171 | 0.00024679 | 0.00025197 | 0.00025726 | 0.00026266 | 0.00026818 | 0.00027381 | 0.00027956 | 0.00028543 | 0.00029142 | 0.00029142 | 0.00029754 | 0.00030379 | 0.0022567
33 |  | Margaret Hopkins | Charlie Seese | Telecom | O&M | Fee | ($Millions) | FCC Transfer Cost |  | 0 | 0 | 0 | 0.033687 | 0.033285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1e-06 | 2e-06 | 3e-06 | 4e-06 | 5e-06 | 6e-06 | 7e-06 | 8e-06 | 9e-06 | 1e-05 | 1.1e-05 | 1.2e-05 | 1.3e-05 | 1.4e-05 | 0.066972
34 |  | Margaret Hopkins | Charlie Seese | Telecom | O&M | Fee | ($Millions) | Backhaul (Data Costs) |  | 0 | 0 | 0 | 0.17604 | 0.23965 | 0.24469 | 0.24982 | 0.25507 | 0.26043 | 0.2659 | 0.27148 | 0.27718 | 0.283 | 0.28894 | 0.29501 | 0.30121 | 0.30753 | 0.31399 | 0.32058 | 0.32732 | 0.33419 | 0.34121 | 0.34837 | 0.35569 | 0.36316 | 0.36316 | 0.37079 | 0.37857 | 2.8122
35 |  | Margaret Hopkins | Charlie Seese | Telecom | O&M | Labor | ($Millions) | Backhaul (PSE Maintenance) |  | 0 | 0 | 0 | 0.1182 | 0.16075 | 0.16397 | 0.16725 | 0.17059 | 0.17401 | 0.17749 | 0.18104 | 0.18466 | 0.18835 | 0.19212 | 0.19596 | 0.19988 | 0.20388 | 0.20795 | 0.21211 | 0.21635 | 0.22068 | 0.22509 | 0.2296 | 0.23419 | 0.23887 | 0.24365 | 0.24852 | 0.25349 | 1.8784
36 | [7 empty] | Total Backhaul |  | 0 | 0 | 0 | 0.32807 | 0.43388 | 0.40885 | 0.41727 | 0.42587 | 0.43464 | 0.44359 | 0.45273 | 0.46206 | 0.47158 | 0.48129 | 0.49121 | 0.50133 | 0.51166 | 0.5222 | 0.53296 | 0.54394 | 0.55515 | 0.56659 | 0.57826 | 0.59017 | 0.60233 | 0.60711 | 0.61962 | 0.63238 | 4.7598
37 | Customer Service and Other Overhead
38
39 |  |  |  | Does this change? |  |  | ($Millions) | Meter Shop Annual Expenses |  | 380004.823 | 387604.9194 | 395357.0178 | 403264.1582 | 411329.4413 | 419556.0302 | 427947.1508 | 436506.0938 | 445236.2156 | 454140.94 | 463223.7588 | 472488.2339 | 481937.9986 | 491576.7586 | 501408.2938 | 511436.4596 | 521665.1888 | 532098.4926 | 542740.4625 | 553595.2717 | 564667.1771 | 575960.5207 | 587479.7311 | 599229.3257 | 611213.9122 | 623438.1905 | 635906.9543 | 648625.0934
40 |  |  |  | Does this change? |  |  | ($Millions) | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
41 |  |  |  | Does this change? |  |  | ($Millions) | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
42 |  |  |  | Does this change? |  |  | ($Millions) | Customer Service Expenses |  | 703849.2334 | 717926.218 | 732284.7424 | 746930.4372 | 761869.046 | 777106.4269 | 792648.5554 | 808501.5265 | 824671.5571 | 841164.9882 | 857988.288 | 875148.0537 | 892651.0148 | 910504.0351 | 928714.1158 | 947288.3981 | 966234.1661 | 985558.8494 | 1005270.0264 | 1025375.4269 | 1045882.9355 | 1066800.5942 | 1088136.6061 | 1109899.3382 | 1132097.325 | 1154739.2714 | 1177834.0569 | 1201390.738
43 |  |  |  | Does this change? |  |  | ($Millions) | DataRaker (Cost is per meter per month) |  | 737991.1426 | 752750.9654 | 767805.9847 | 783162.1044 | 798825.3465 | 814801.8534 | 831097.8905 | 847719.8483 | 864674.2453 | 881967.7302 | 899607.0848 | 917599.2265 | 935951.211 | 954670.2352 | 973763.6399 | 993238.9127 | 1013103.691 | 1033365.7648 | 1054033.0801 | 1075113.7417 | 1096616.0165 | 1118548.3369 | 1140919.3036 | 1163737.6897 | 1187012.4435 | 1210752.6923 | 1234967.7462 | 1259667.1011
44 | [6 empty] | ($Millions) | DataRaker Reimbursement |  | -252104.5138 | -257146.604 | -262289.5361 | -267535.3268 | -272886.0334 | -278343.754 | -283910.6291 | -289588.8417 | -295380.6185 | -301288.2309 | -307313.9955 | -313460.2754 | -319729.4809 | -326124.0706 | -332646.552 | -339299.483 | -346085.4727 | -353007.1821 | -360067.3258 | -367268.6723 | -374614.0457 | -382106.3267 | -389748.4532 | -397543.4222 | -405494.2907 | -413604.1765 | -421876.26 | -430313.7852
45 |  |  |  | Does this change? |  |  | ($Millions) | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
46 |  |  |  | Does this change? |  |  | ($Millions) | Downtime and Outage Expenses |  | 6133.02 | 6134.04 | 6135.06 | 6136.08 | 6137.1 | 6138.12 | 6139.14 | 6140.16 | 6141.18 | 6142.2 | 6143.22 | 6144.24 | 6145.26 | 6146.28 | 6147.3 | 6148.32 | 6149.34 | 6150.36 | 6151.38 | 6152.4 | 6153.42 | 6154.44 | 6155.46 | 6156.48 | 6157.5 | 6158.52 | 6159.54 | 6160.56
47 |  |  |  | Does this change? |  |  | ($Millions) | 4 FTE Analysts/Engineers |  | 569685.2429 | 581078.9477 | 592700.5267 | 604554.5372 | 616645.628 | 628978.5405 | 641558.1113 | 654389.2736 | 667477.059 | 680826.6002 | 694443.1322 | 708331.9949 | 722498.6348 | 736948.6075 | 751687.5796 | 766721.3312 | 782055.7578 | 797696.873 | 813650.8104 | 829923.8267 | 846522.3032 | 863452.7492 | 880721.8042 | 898336.2403 | 916302.9651 | 934629.0244 | 953321.6049 | 972388.037
48 |  |  |  | Does this change? |  |  | ($Millions) | 2 FTE Corporate Managers |  | 569685.2429 | 581078.9477 | 592700.5267 | 604554.5372 | 616645.628 | 628978.5405 | 641558.1113 | 654389.2736 | 667477.059 | 680826.6002 | 694443.1322 | 708331.9949 | 722498.6348 | 736948.6075 | 751687.5796 | 766721.3312 | 782055.7578 | 797696.873 | 813650.8104 | 829923.8267 | 846522.3032 | 863452.7492 | 880721.8042 | 898336.2403 | 916302.9651 | 934629.0244 | 953321.6049 | 972388.037
49 |  |  |  | Does this change? |  |  | ($Millions) | Technology training - Field (8hr day 2x/year - 12 people) Field O&M |  | 9145.8504 | 9146.8704 | 9147.8904 | 9148.9104 | 9149.9304 | 9150.9504 | 9151.9704 | 9152.9904 | 9154.0104 | 9155.0304 | 9156.0504 | 9157.0704 | 9158.0904 | 9159.1104 | 9160.1304 | 9161.1504 | 9162.1704 | 9163.1904 | 9164.2104 | 9165.2304 | 9166.2504 | 9167.2704 | 9168.2904 | 9169.3104 | 9170.3304 | 9171.3504 | 9172.3704 | 9173.3904
50 |  |  |  | Does this change? |  |  | ($Millions) | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
51 |  |  |  | Does this change? |  |  | ($Millions) | EA Annual Maintenance Fee |  | 280776.02 | 280777.04 | 280778.06 | 280779.08 | 280780.1 | 280781.12 | 280782.14 | 280783.16 | 280784.18 | 280785.2 | 280786.22 | 280787.24 | 280788.26 | 280789.28 | 280790.3 | 280791.32 | 280792.34 | 280793.36 | 280794.38 | 280795.4 | 280796.42 | 280797.44 | 280798.46 | 280799.48 | 280800.5 | 280801.52 | 280802.54 | 280803.56
52 |  |  |  | Does this change? |  |  | ($Millions) | Server Hardware and Software Maintenance Analyst |  | 159733.02 | 159734.04 | 159735.06 | 159736.08 | 159737.1 | 159738.12 | 159739.14 | 159740.16 | 159741.18 | 159742.2 | 159743.22 | 159744.24 | 159745.26 | 159746.28 | 159747.3 | 159748.32 | 159749.34 | 159750.36 | 159751.38 | 159752.4 | 159753.42 | 159754.44 | 159755.46 | 159756.48 | 159757.5 | 159758.52 | 159759.54 | 159760.56
53
54 | [7 empty] | Total |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
55 | Gas Battery Program
56 |  |  | Harry Shapiro | Gas Ops |  |  | ($Millions) | Cost of Battery Pruchases |  | 0 | 0 | 0 | 746458.8528 | 912553.2789 | 453470.8301 | 464535.5184 | 475870.185 | 179466.8585 | 183845.8498 | 188331.6886 | 192926.9818 | 197634.4001 | 202456.6795 | 207396.6225 | 212457.1001 | 217641.0533 | 222951.495 | 228391.5115 | 233964.2644 | 239672.9924 | 245521.0134 | 251511.7262 | 257648.6123 | 263935.2384 | 270375.2582 | 276972.4145 | 283730.5415
57 |  |  | Harry Shapiro | Gas Ops |  |  | ($Millions) | Cost of Battery Disposals |  | 5511.1235 | 8607.6025 | 32207.3747 | 32993.2347 | 33798.2696 | 16795.2159 | 17205.0192 | 17624.8217 | 6646.9207 | 6809.1055 | 6975.2477 | 7145.4438 | 7319.7926 | 7498.3955 | 7681.3564 | 7868.7815 | 8060.7798 | 8257.4628 | 8458.9449 | 8665.3431 | 8876.7775 | 9093.3709 | 9315.2491 | 9542.5412 | 9775.3792 | 10013.8985 | 10258.2376 | 10508.5386
58 |  |  | Harry Shapiro | Gas Ops |  |  | ($Millions) | Cost of Installations (Labor including overhead) |  | 278642.4022 | 435200.3812 | 814202.4329 | 834068.9723 | 854420.2552 | 424583.0587 | 434942.8853 | 445555.4917 | 336068.3098 | 344268.3766 | 352668.525 | 361273.637 | 370088.7137 | 379118.8784 | 388369.379 | 397845.5918 | 407553.0243 | 417497.3181 | 427684.2526 | 438119.7484 | 448809.8703 | 459760.8311 | 470978.9954 | 482470.8829 | 494243.1724 | 506302.7058 | 518656.4918 | 531311.7102
59 |  |  | Harry Shapiro | Gas Ops |  |  | ($Millions) | Honeywell Alternative |  | 0 | 0 | 171874.576 | 179947.8213 | 190548.0531 | 186620.2848 | 189598.8294 | 192622.9149 | 197962.6532 | 202792.9419 | 207741.0897 | 212809.9723 | 218002.5356 | 223321.7975 | 228770.8494 | 234352.8581 | 240071.0678 | 245928.8019 | 251929.4647 | 258076.5436 | 264373.6113 | 270824.3274 | 277432.441 | 284201.7925 | 291136.3163 | 298240.0424 | 305517.0994 | 312971.7166
60 |  |  | Harry Shapiro | Gas Ops |  |  | ($Millions) | Total Cost of Battery Program |  | 0.28415 | 0.44381 | 1.0183 | 1.7935 | 1.9913 | 1.0815 | 1.1063 | 1.1317 | 0.72014 | 0.73772 | 0.75572 | 0.77416 | 0.79305 | 0.8124 | 0.83222 | 0.85252 | 0.87333 | 0.89464 | 0.91646 | 0.93883 | 0.96173 | 0.9852 | 1.0092 | 1.0339 | 1.0591 | 1.0849 | 1.1114 | 1.1385
61
62 | Totals | [9 empty] | Year | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
[8 empty] | NPV (10 Years) ($2014) | [29 empty] | 25 Year Total Nominal (2015-2039)
63 | [6 empty] | New PSE AMR Costs | 73.9838 |  | -0.18468 | 0.024742 | 0.36282 | 8.7138 | 11.5828 | 12.0163 | 12.3719 | 12.8195 | 13.3952 | 14.0048 | 14.6516 | 15.3203 | 15.9991 | 16.6434 | 17.2215 | 17.7529 | 18.322 | 18.8636 | 19.4108 | 20.0595 | 20.8509 | 21.4904 | 22.0742 | 22.7284 | 23.4909 | 24.1179 | 25.1161 | 25.6194 | 419.3806
64 | [6 empty] | O&M | 18.294 |  | 0.024389 | 0.024742 | 0.36282 | 2.5352 | 2.8583 | 2.929 | 3.0372 | 3.1498 | 3.2669 | 3.3888 | 3.5157 | 3.6477 | 3.7852 | 3.9284 | 4.0774 | 4.2325 | 4.3941 | 4.5624 | 4.7376 | 4.9201 | 5.1103 | 5.3083 | 5.5146 | 5.7296 | 5.9536 | 6.1793 | 6.416 | 6.6692 | 103.5409
65 | [6 empty] | CAPEX | 55.6898 |  | -0.20907 | 0 | 0 | 6.1786 | 8.7245 | 9.0873 | 9.3347 | 9.6697 | 10.1283 | 10.616 | 11.1359 | 11.6726 | 12.2138 | 12.715 | 13.1441 | 13.5204 | 13.9279 | 14.3012 | 14.6732 | 15.1394 | 15.7407 | 16.1821 | 16.5596 | 16.9988 | 17.5373 | 17.9385 | 18.7001 | 18.9502 | 315.8397
[7 empty] | Ownership Contingency 50% | 36.9919 |  |  | 0.012371 | 0.18141 | 4.3569 | 5.7914 | 6.0081 | 6.1859 | 6.4098 | 6.6976 | 7.0024 | 7.3258 | 7.6602 | 7.9995 | 8.3217 | 8.6107 | 8.8765 | 9.161 | 9.4318 | 9.7054 | 10.0297 | 10.4255 | 10.7452 | 11.0371 | 11.3642 | 11.7455 | 12.0589 | 12.5581 | 12.8097 | 209.6903
67 | [6 empty] | New PSE AMR Costs with 50% Contingency | 110.9757 |  |  | 0.037114 | 0.54423 | 13.0707 | 17.3742 | 18.0244 | 18.5578 | 19.2293 | 20.0928 | 21.0072 | 21.9774 | 22.9805 | 23.9986 | 24.9651 | 25.8322 | 26.6294 | 27.4831 | 28.2954 | 29.1161 | 30.0892 | 31.2764 | 32.2357 | 33.1113 | 34.0926 | 35.2364 | 36.1768 | 37.6742 | 38.4291 | 629.0709
[7 empty] | New PSE AMR Costs+ 50% Contingency+AMR Contract | 205.601 |  |  | 31.0657 | 32.9096 | 31.0607 | 31.3606 | 32.0108 | 33.1559 | 34.5359 | 36.1507 | 37.8611 | 39.6668 | 41.5468 | 43.4852 | 45.4176 | 47.2986 | 49.1599 | 51.1304 | 53.115 | 55.166 | 57.4304 | 59.9729 | 62.3547 | 64.7233 | 67.2716 | 70.0601 | 72.7268 | 76.036 | 78.6926 | 1225.6074
68 | [6 empty] | Incremental Cost of Hypothetical Contract Extension | 132.4818 |  | -1.8071 | 0 | 0 | 14.0089 | 19.7968 | 21.3374 | 22.2705 | 23.3515 | 24.4976 | 25.712 | 26.9865 | 28.3243 | 29.7283 | 31.202 | 32.7487 | 34.372 | 36.0759 | 37.8642 | 39.7412 | 41.7111 | 43.7788 | 45.9489 | 48.2267 | 50.6173 | 53.1264 | 55.7599 | 58.524 | 61.4251 | 845.7109
69 | [6 empty] | PSE Savings over Status Quo Contract Extension | 95.4899 |  | 0 | 0 | 0 | 9.6519 | 14.0054 | 15.3292 | 16.0846 | 16.9418 | 17.8 | 18.7096 | 19.6607 | 20.6641 | 21.7288 | 22.8803 | 24.1379 | 25.4956 | 26.9149 | 28.4324 | 30.0358 | 31.6814 | 33.3533 | 35.2037 | 37.1896 | 39.2531 | 41.381 | 43.701 | 45.9659 | 48.6153 | 636.202
70 | [6 empty] | O&M: L+G Contract Costs | 94.6253 |  | 30.16 | 31.0286 | 32.3653 | 17.9899 | 13.9864 | 13.9864 | 14.5981 | 15.3067 | 16.0579 | 16.8539 | 17.6894 | 18.5662 | 19.4866 | 20.4525 | 21.4664 | 22.5305 | 23.6473 | 24.8196 | 26.0499 | 27.3412 | 28.6965 | 30.119 | 31.612 | 33.1791 | 34.8238 | 36.55 | 38.3618 | 40.2634 | 596.5365
[7 empty] | Estimate of extension of AMR Managed Service (requires re-negotiation) | 233.8851 |  |  | 31.0286 | 32.3653 | 33.7597 | 35.2141 | 36.7311 | 38.3135 | 39.9641 | 41.6857 | 43.4816 | 45.3548 | 47.3087 | 49.3468 | 51.4727 | 53.6902 | 56.0032 | 58.4158 | 60.9324 | 63.5574 | 66.2955 | 69.1516 | 72.1307 | 75.2381 | 78.4794 | 81.8604 | 85.387 | 89.0655 | 92.9025 | 1405.2053
[7 empty] | Estimated Savings | 28.2841 |  |  | -0.037114 | -0.54423 | 2.699 | 3.8535 | 4.7203 | 5.1576 | 5.4282 | 5.5351 | 5.6205 | 5.688 | 5.762 | 5.8616 | 6.0551 | 6.3916 | 6.8433 | 7.2854 | 7.8175 | 8.3914 | 8.8651 | 9.1787 | 9.776 | 10.5148 | 11.2078 | 11.8002 | 12.6602 | 13.0295 | 14.2099 | 179.598
[11 empty] | 5 Year | 1: 10 Year
[7 empty] | Total Contract Extension Costs |  |  |  | 183.9824 | 1: 411.1601
[7 empty] | Total Status Quo Costs |  |  |  | 162.1239 | 1: 360.8344
[7 empty] | 5 Year NPV (2016-2020) |  |  |  | 14.7668
[7 empty] | 10 Year NPV (2016-225) |  |  |  | 28.2841
[7 empty] | 25 Year NPV (2015-2039) |  |  |  | 61.6169
[9 empty] | 5-Year Totals | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026
[8 empty] | Telecom CAPEX | 1201292.6062 | 0 | 0 | 0 | 0.49288 | 0.70841 | 0.74117 | 0.77545 | 0.8113 | 0.84882 | 0.88807 | 0.92914 | 0.9721 | 1.0171 | 1.0641
[8 empty] | Telecom O&M | 3469267.2751 | 0 | 0 | 0 | 1.4521 | 2.0172 | 2.0693 | 2.1585 | 2.2517 | 2.349 | 2.4506 | 2.5568 | 2.6677 | 2.7835 | 2.9045
[8 empty] | Director | 2013-2017 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026
[8 empty] | Joe Beer | 1.5103 | 0.15912 | 0.1623 | 0.50327 | 0.51333 | 0.17224 | 0.17568 | 0.17919 | 0.18278 | 0.18643 | 0.19016 | 0.19397 | 0.19785 | 0.2018 | 0.20584
[8 empty] | Rex Pietzyk | 0.27896 | 0 | 0 | 0 | 0.1182 | 0.16075 | 0.16397 | 0.16725 | 0.17059 | 0.17401 | 0.17749 | 0.18104 | 0.18466 | 0.18835 | 0.19212
[8 empty] | Harry Shapiro | 10.8847 | 0 | 0 | 0 | 4.5225 | 6.3622 | 6.6494 | 6.7409 | 6.9201 | 7.2264 | 7.5581 | 7.9077 | 8.2591 | 8.6225 | 9.0023
[8 empty] | Lars Bergmann | 2.2298 | -0.20907 | -0.19268 | -0.18556 | 1.1632 | 1.6538 | 1.6967 | 1.8183 | 1.9383 | 2.0531 | 2.1698 | 2.2992 | 2.4414 | 2.5743 | 2.6487
[8 empty] | Wayne Gould | 0.99563 | 0 | 0 | 0 | 0.48747 | 0.50815 | 0.52005 | 0.53223 | 0.5447 | 0.55746 | 0.57052 | 0.58389 | 0.59758 | 0.61159 | 0.62593
[8 empty] | Margaret Hopkins | 4.6706 | 0 | 0 | 0 | 1.945 | 2.7256 | 2.8105 | 2.934 | 3.063 | 3.1978 | 3.3387 | 3.4859 | 3.6398 | 3.8005 | 3.9686
[8 empty] | Durga Doraisamy | -0.44859 | -0.13473 | -0.13756 | -0.14045 | -0.03585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Agnes Barard (L+G Contract Costs) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Rex Pietzyk (L+G Contract Costs) |  | 29.618 | 30.6433 | 31.8636 | 17.8312 | 13.9443 | 13.9864 | 14.5981 | 15.3067 | 16.0579 | 16.8539 | 17.6894 | 18.5662 | 19.4866 | 20.4525
[8 empty] | Total |  | -0.18468 | -0.16794 | 0.17726 | 8.7138 | 11.5828 | 12.0163 | 12.3719 | 12.8195 | 13.3952 | 14.0048 | 14.6516 | 15.3203 | 15.9991 | 16.6434
[8 empty] | Validate |  | 0 | 0.19268 | 0.18556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Project (hidden)
Scenario Project Plans
Plan
Execute
Event
Budget | Preparing and constructing a financial total cost of ownership model and creating a 5 year budget plan.
Staffing | Determining resource needs, reporting requirements, creating job descriptions and setting up requisitions.
Contract Transfers
PSE and Other Utility Pole Attachments | L&G has pole attachment agreements which needs to be transferred to PSE.
Network Radio License Transfer | L&G has radio licences for operating its network, which need to be transferred to PSE when PSE owns and operates network equipment.
Process Changes for L+G
Network and Module Purchasing | PSE will need to establish purchasing agreements, procedures, and inventory of network equipment.
Inventory | PSE must establish processes or contracts for commodity acceptance, inventory, module quality control and module refurbishment.
Meter/Module Field Maintenance | PSE must establish a module and battery maitenance and upgrade process.
Network Maintenance | PSE must establish processes or contracts for maintaining network equipment.
Data Center | PSE must decide if and when it will take over operation and maintenance of the Data or Network Operations Center (NOC)
Status Quo
| 2011 |  |  |  | 2012 |  |  |  | 2013 |  |  |  | 2014 |  |  |  | 2015 |  |  |  | 2016 |  |  |  | 2017
| Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Budget
Staffing | bar: 2015 Q3 to 2017 Q4
External Contract Changes for L+G
PSE and Other Utility Pole Attachments | bar: 2014 Q4 to 2017 Q4
Network Radio License Transfer | bar: 2015 Q4 to 2016 Q4
Network and Module Purchasing | bar: 2015 Q4 to 2017 Q4
Process Changes for L+G
Inventory/Meter Shop | bar: 2015 Q4 to 2017 Q4
Meter/Module Field Maintenance | bar: 2014 Q4 to 2017 Q4
Network Maintenance | bar: 2014 Q4 to 2017 Q4
Data Center | bar: 2014 Q4 to 2017 Q4
Gradual AMI
| 2011 |  |  |  | 2012 |  |  |  | 2013 |  |  |  | 2014 |  |  |  | 2015 |  |  |  | 2016 |  |  |  | 2017
| Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Budget | bar: 2012 Q1 to 2017 Q4
Staffing | bar: 2012 Q1 to 2017 Q4
New AMI Contract Agreements
PSE and Other Utility Pole Attachments | bar: 2013 Q1 to 2017 Q4
Network Radio Licence Procurement | bar: 2013 Q1 to 2017 Q4
Network and Module Purchasing | bar: 2013 Q1 to 2017 Q4
External Contract Changes for L+G
PSE and Other Utility Pole Attachments | bar: 2014 Q4 to 2017 Q4
Network Radio License Transfer | bar: 2015 Q4 to 2016 Q4
Network and Module Purchasing | bar: 2015 Q4 to 2017 Q4
New AMI Process Changes
Inventory/Meter Shop | bar: 2015 Q4 to 2017 Q4
Meter/Module Field Maintenance | bar: 2014 Q4 to 2017 Q4
Network Maintenance | bar: 2014 Q4 to 2017 Q4
Data Center | bar: 2014 Q4 to 2017 Q4
Process Changes for L+G
Inventory/Meter Shop | bar: 2015 Q4 to 2017 Q4
Meter/Module Field Maintenance | bar: 2014 Q4 to 2017 Q4
Network Maintenance | bar: 2014 Q4 to 2017 Q4
Data Center | bar: 2014 Q4 to 2017 Q4

## RiskMatrix (hidden)
Risk Matrix
| Total O&M Expenditures | Reliability & Grid Operations | Regulatory and Public Relations | Customer Service | Technology-Security | Interoperability | Overall NPV | Total
Status Quo | 1 | 1 | 1 | 1 | 2 | 1 | 5
Gradual AMI | 2 | 3 | 2 | 2 | 3 | 3 | 4 | 19
Hybrid-New Vendor | 5 | 2 | 5 | 3 | 1 | 2 | 6 | 24
Meter Minimum | 3 | 4 | 3 | 4 | 2 | 3 | 3 | 22
Meter Floor | 4 | 5 | 4 | 5 | 2 | 3 | 2 | 25
Full Deployment | 6 | 6 | 6 | 6 | 6 | 3 | 1 | 34
Categoy | Description | [5 empty] | 1 =Worst | 6=Best
Total O&M Expenditures | Total O&M Expenditure 2012-2026
Reliability & Grid Operations | Reliability of data transmission and the ability to coordination, monitor and control grid equipment.
Regulatory and Public Relations | Potential challenges managing the perception of technology
Customer Service | Providing customers with information and service options.
Technology-Security | Management of technological challenges such as complexity and security.
Interoperability | Conformance with standards, protocols and upgrades.
Overall NPV | Estimated NPV of the option.
Note on I4: vdrehe:

## MATRIX (hidden)
|  |  | Level of Involvement | [8 empty] | Strategy | [5 empty] | Business Case |  |  |  | PSE IT System Enablers | [11 empty] | Level of benefit impact by NIST Smart Grid Domain
Smart Grid Projects | PSE Lead (Team Rep) | Team | Metering | Telecom | Energy Control Systems | IT Applications | T&D | Operations | Energy Efficiency | Customer Care | Resource Acq & Emer Tech | 2022 Vision | SG-CMM Area | SG-CMM Vision Level 2022 | Waypoints 2012-2014 | Waypoints 2015-2022 | Vision 2023 and beyond | Costs | Benefits | Total Assignable Net Benefits ($) | Net Benefit Certainty | OMS | EMS | DMS | GIS | CIS | MDMS / MEMS | Data Historian | AMI | Informational Metering | Operations WAN | FAN | Other IT System | Customers | Markets | Service Providers | Operations | Bulk Generation | Transmission | Distribution | Notes
IT Enablers
Field Area Network | Laura Feinstein | John McClaine, Theresa Burch, Charlie Seese, Veronica Dreher | A | R | I | R | C | I | I | I | I | Reliable and secure two-way wired and wireless meter communications and control network throughout the PSE electric and gas service territory. | Grid Operations (GO) | 4-Optimizing | 2014-First phase roll out of two-way network to customer meters. | Full scale deployment. | Maintaining FAN | 2016 -At implementation $35 million (for network and NOC) + $10 million (L&G termination fees)+O&M = Total $40+ million | 2016-Enablement of other smart grid applications + meter read reduction benefits =$1 million/year | ($70 million) | 1-Rough Guess | [5 empty] | x |  | x |  | ? | x |  | 1-Negligable | 1-Negligable | 3-Significant | 4-Transformative | 2-Marginal | 4-Transformative | 4-Transformative
Advanced Metering Infrastructure (AMI) (customer meters) | Laura Feinstein | Laura Feinstein, Theresa Burch, Susan Beardsley, Rachel Montoya, John McClaine | A | R | I | R | C | C | C | R | C | 90% + electric customer AMI enablement, advanced meter reads, diagnostics, electric meter accuracy testing, connect/disconnect capability, kVAR testing, advanced net-metering, theft detection, kV reads (for CVR), integration to HAN, dynamic rate capable. | Grid Operations (GO) | 4-Optimizing | 2012 First pilots with select customers. | Targeted roll-outs (<200K) to customers enrolled in AMI enabled programs. Replacement for attrition of one-way meters. | Replacement for attrition. | $275 million | Improved billing cycles-->less late payments $2 million year | $10 million | 1-Rough Guess | [12 empty] | 4-Transformative | 1-Negligable | 4-Transformative | 4-Transformative | 2-Marginal | 4-Transformative | 4-Transformative
Informational Meters (generation and T&D meters) | Laura Feinstein | Laura Feinstein, Theresa Burch, Brent Carper, Rachel Montoya, John McClaine, Generation, Substations Ops stakeholders TBD | A | R | R | I | C | C | I | I | I | All transmission, generation and substation informational metering upgraded to current standards with DNP or comparable comm technology. | Grid Operations (GO) | 4-Optimizing | Replacing 50-70% of Quantum Meters, JEM Meters and watt-var transducers with current informational metering technology identified in MID and standard | Replacing 100% of Quantum Meters, JEM Meters and watt-var transducers with current informational metering technology identified in MID and standard | Using the meters to perform PQ analysis, simplified testing | Per meter replacement cost: JEM or Quantum to SEL=$6600 (Qty 16 @ generators; up to 58 @ Substations); JEM or transducer to SATEC=$4400 (Qty 200) Includes 2011 labor costs and cost of equipt. | At generators, reduced outages for testing meters (because test switch will be installed when meter is installed). PQ analysis possible; supports AGC at generation sites; easier field support because there will be a smaller number of variations of meter types in the field. | ? | 2-Good Estimate | x | x | x |  | ? |  |  |  |  | x |  | OSISOFT PI | 2-Marginal | 2-Marginal | 1-Negligable | 3-Significant | 3-Significant | 3-Significant | 3-Significant
Substation IP (WAN) | Charlie Seese | Dave Caldwell, Ron Tornquist | R | A | I | C | C | I | I | I | I | IP SCADA to nearly all T&D Substations |  | 3-Integrating | July 2013 IP SCADA on 130 critical subs |  |  | $50k/sub 400 (130 critical subs, 3 currently enabled) Fiber $20K-60K/mile | [12 empty] | x
Substation Fiber (WAN) | Charlie Seese | Ron Tornquist | I | A | I | I | C | I | I | I | I | ≈100% Fiber | Technology (TECH)
Energy Management System (EMS) | George Hendrickson (Urmi Kavi) | Mike Tongue, Loic Roger, Tammy Burkhardt, Tom Discipio, Paul Michels | R | R | A | I | C | R | I | I | I | OMS-DMS-EMS-MDMS integration | Grid Operations (GO) | 4-Optimizing | EMS (Alstom)upgrade Release 1 complete by December 2011, Release 2 by Q2 2012 with reliability toolbox and by Q4 2012 situational awareness (E-Tera Vision), Wind Following and Economic Dispatch. EMP Upgrade in 2014 | [12 empty] | x |  | x | x | x
Customer Information System (CIS) | Bob Bisschoff | Theresa Burch, Jon Pielmeier, Randy Dieterle | C | I | I | A | I | I | I | C | I |  |  | 4-Optimizing | Full implementation by 2013
Geographic Information System (GIS) | Mark Maass | John McClaine, Roli Cortez, Dee Williamson, Turushia Thomas, Bruce Bjorklund, Dave Trimble | I | I | I | A | C | C | I | I | I |  | Technology (TECH) | 4-Optimizing | New System by 2012 | [17 empty] | SAP
Outage Management System (OMS) | John McClaine | John McClaine, Roger Fletcher, Krista Malmgren, Dee Williamson, Turushia Thomas, Bruce Bjorklund, Dave Trimble | R | C | A | R | C | R | I | I | I | OMS-DMS-EMS-MDMS integration | Grid Operations (GO) | 4-Optimizing | Integration with MDMS, Integrated with AMI on net-metered customers | Distribution isolation/restoration | [7 empty] | x | x | x | x |  | x |  | x | x
Data Historian | Urmi Kavi | John McClaine, Theresa Burch, George Hendrickson, Rashmi Nagarkar | [9 empty] | Full integration and connectivity of data historians. Integration of meter and operations data? |  |  | Integration of corporate PI data with other systems data.
Distribution Management System (DMS) | John McClaine | John McClaine, Roger Fletcher, Krista Malmgren, Dee Williamson, Turushia Thomas, Bruce Bjorklund, Dave Trimble, Rashmi Nagarkar | R | R | A | R | C | R | I | I | I | OMS-DMS-EMS-MDMS integration, asset optimization, transformer monitoring, short circuit localization, fault detection, isolation restoration, feeder switching, load tap changers and capacitor bank controls | Grid Operations (GO) | 4-Optimizing | Enablement of FDIR, VVO | OMS-DMS integration | [5 empty] | x |  |  | x | x | x |  | x | x | x | x
Programs and Processes
Distribution Automation (DA) and Control | Dee Williamson | Hugh Nguyen, Don Yuen, Rashmi Nagarkar | R | C |  |  | A | R | I | I | I | Automated reclosers, complete DA for Bellevue CBD and Whidby Island, fault indicators on 100% lines, feeder restoration automation on select circuits, additional feeders, asset management, vehicle-transformer coordination. |  | 4-Optimizing | Automate select reclousers by 2012. Continue to monitor and learn from the DA systems serving Microsoft Evaluate and develop pilots in one to two select areas where reliability is an issue. Enable "smart grid ready" substation equipment. | [6 empty] | x | ? | x | x |  |  |  |  | ? | x | x
Transmission Automation | Kebede Jimma | Gary Shumate; Charlie Seese, David Parker, Zach Sanford | C | R | R |  | A | R | I | I | C | Selective deployment syncrophasers and Phaser Measurement Units |  |  | Identify automatic transmission schemes projects and upgrade aging/older SCADA systems in transmission substations. Evaluate optimal location for syncrophasers.
Power Quality Measurement and Monitoring | Chris McVicker | John Campion, Karen Pavletich, (someone from Technical Field Services), Hugh Nguyen | R | C | C | C | A | R | I | R | I | Load analysis | Grid Operations (GO) | 3-Integrating | Evaluate better power quality meters | [14 empty] | x
Distribution Islanding | Jeanne Harshbarger | [10 empty] | Ability to Island portions of the PSE system which have generation resources. | [17 empty] | x | bar: R
Conservation Voltage Reduction (CVR) | Hugh Nguyen & Don Yuen | Jennifer Tada, Laura Feinstein, Bruce Bjorklund, Veronica Dreher | R | I | R | I | A | R | C | C | I | Automated CVR on selected circuits | Grid Operations (GO) | 5-Pioneering | 12012-2013-12 Substations with LDC | 70 substations and some selected pilots with end-of-line voltage voltage control and feed-back technologies; integration with other DM systems. | 170 substations - combination of LDC and EOL voltage control automation technologies; full integration with other DM systems. | $2.1million for the first 12 substations | 5.5 BC ratio | $11.6 million | 2-Good Estimate | x | ? | x | ? |  | x |  | x | x | x | x
Customer Information Feedback-Interface | Michael Wehling-R/ Lori Moen-C&I | Laura Feinstein, Theresa Burch, Susan Beardsley | C | I |  | A | C |  | R | A | I | Real time energy information feedback integration with building control systems and Home Area Networks (HAN) |  | 2-Enabling |  |  |  | Itron costs 100k/year and $120/month for reads | [7 empty] | x | [6 empty] | Itron Energy Interval Services
Targeted Customer Programs | [11 empty] | Use customer data to provide targeted energy efficiency and customer programs.
Demand Response (DR) | Rich Hazzard | Shannon McCormick, Syd France, Bob Stolarski, Michael Wehling | R | I |  |  | R |  | A | R | C | Automated demand response with supporting equipment, rates and load shifting capabilities. |  | 2-Enabling
Dynamic Pricing
Electric Vehicles Program (EV) | Will Einstein | Ben Farrow | R | I |  |  | I |  | I | R | A | Vehicle recognition, PSE charging stations |  | 3-Integrating
Distributed Generation | Jake Wade | Will Einstein | R | I |  |  | C |  | C | R | A | Dispatchable customer generation on select circuits |  | 3-Integrating
Prepay Billing | Sue Beardsley | Rachel Montoya | R | I |  |  | C |  | I | A | I
Theft Detection | Susan Beardsley | Rachel Montoya | R | I |  |  | C |  | I | A | I | ? |  | 4-Optimizing
Energy Storage Integration |  |  | C | I |  |  | R |  | I | I | A
Remote Disconnect Reconnect | Susan Beardsley | Rachel Montoya | A | I |  | R | I |  |  | R | I
Mobile Workforce | Charlie Seese | Susan Beardsley | C | A |  |  | I |  | I | R | I
Generation Information Support System | Ron Tornquist | Casey Harman, Thedora Lybarger | [9 empty] | Enhancement of the Baker Information Support System, Historian Servers, AGC in all plants
Renewable Energy Integration | Irena Netik
Home Area Networks and Smart Appliances | [13 empty] | 2-Enabling
[12 empty] | Pioneering |  | 1
|  | Responsible | 12 | 6 | 3 | 5 | 2 | 8 | 1 | 7 | 0 | Optimizing |  | 10
|  | Accountable | 4 | 3 | 3 | 3 | 4 | 0 | 1 | 3 | 3 | Integrating |  | 4
|  | Consulted | 5 | 3 | 1 | 2 | 13 | 3 | 3 | 2 | 3 | Enabling |  | 3
|  | Informed | 2 | 11 | 6 | 4 | 4 | 4 | 17 | 11 | 17 | Initiating |  | 0
[12 empty] | Default |  | 1
Note on B2: vdrehe: The PSE Lead is the person accountable for managing existing SG projects in this area. The team rep (if not the PSE Lead) is the person (in brackets) responsible for reporting in this template.
Note on C2: vdrehe: Team members leading SG project.
Note on D1: vdrehe: Levels are R = Responsible A = Accountable (can only be one) C =Consulted I = Informed For framework details see: http://en.wikipedia.org/wiki/Responsibility_assignment_matrix
Note on D2: vdrehe: Meter Technology and Data Integrity, and Smart Meter Technology
Note on G2: vdrehe: This includes only Web Applications, Data Applications Services and SAP
Note on H2: lfeins: System Planning
Note on I2: vdrehe: Load Office, Substation Engineering
Note on K2: lfeins: Billing and Meter Network Services (field crews)
Note on L2: vdrehe: Resource Acquisition and Emerging Technologies
Note on M2: vdrehe: "Vision" is defined as the current understanding of the "best" technology state PSE could achieve by 2022. In other words, this is the ideal cost effective solution given our current hypothesis about what is achievable with this technology by 2022.
Note on M5: vdrehe: Still evaluating AMI for Gas
Note on N2: vdrehe: Areas Include: -Strategy Management and Regulatory (SMR) - Organization and Structure (OS) - Grid Operations (GO) - Work and Asset - Management (WAM) - Technology (TECH) -Customer (CUST), Value Chain Integration (VCI) -Societal and Environmental (SE) See the Carnegie Mellon Smart Grid Maturity Model Matrix Version 1.1 (located on page 59). Link: http://repository.cmu.edu/cgi/viewcontent.cgi?article=1204&context=sei&sei-redir=1#search="smart+grid+maturity+model+matrix+version+1.1"
Note on O2: vdrehe: See the Carnegie Mellon Smart Grid Maturity Model Matrix Version 1.1 (located on page 59). Link: http://repository.cmu.edu/cgi/viewcontent.cgi?article=1204&context=sei&sei-redir=1#search="smart+grid+maturity+model+matrix+version+1.1"
Note on S1: vdrehe: Please include both immediate and any mid to long term projects that can be quantified (even a rough estimate is useful).
Note on S2: vdrehe: .This is the incremental cost associated with adding a technology/program. (Capital Costs + O&M over the investment lifetime). This should be the NPV (in nominal dollars discounted at 8.2%) in the year of implementation. Please specify year and program(s).
Note on T2: vdrehe: This is the incremental benefit associated with adding a technology/program. (Reduced O&M + reduced CAPEX benefits+deferred investments+etc.). This should be the NPV (in nominal dollars discounted at 8.2%) in the year of implementation. Please specify year and program(s)
Note on V2: vdrehe: The level of business case development.
Note on V6: lfeins: Good estimate on the costs.
Note on W1: vdrehe: Predecessor Technologies
Note on AF2: Joe Beer: Operations Wide Area Network (WAN): Hi-capacity, highly reliable, IP capable network between Data Centers, Control Center, BUCC, Generation Sites and Substations. Includes multiple forms of physical network transport (Fiber, microwave, leased line, radio, etc)
Note on AG2: Joe Beer: Field Area Network (FAN): Hi-capacity, highly reliable, IP capable network that connects PSE and Customer field devices and meters to the WAN. Includes all forms of physical network transport, wired and wireless.
Note on AI1: vdrehe: Indicate the level of impact the project/technology has on each NIST "Domain." (the levels are PSE chosen). The highest level of impact is "4-Transformative" to lowest "1-Negligible." See the "Info" tab and the NIST document: http://www.nist.gov/smartgrid/nistandsmartgrid.cfm
Note on AI2: vdrehe: The end users of electricity. May also generate, store, and manage the use of energy. Traditionally, three customer types are discussed, each with its own domain: home, commercial/building, and industrial.
Note on AJ2: vdrehe: The operators and participants in electricity markets.
Note on AK2: vdrehe: The organizations providing services to electrical customers and utilities.
Note on AL2: vdrehe: The managers of the movement of electricity.
Note on AM2: lfeins: The generators of electricity in bulk quantities. May also store energy for later distribution.
Note on AN2: lfeins: The carriers of bulk electricity over long distances. May also store and generate electricity.
Note on AO2: lfeins: The distributors of electricity to and from customers. May also store and generate electricity.
DRAFT
DRAFT

## Totls (R)
Scenario Totals and Analysis
|  |  | -1 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
| (millions $) | NPV (Scenario compared with Status Quo) | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | Nominal Net Benefits (Scenario compared with Status Quo)
Annual Net Benefits (Metering Only)
| Meter Minimum | #REF! | -1 2013: -6.7103; 0 2014: #REF!; 1 2015: #REF!; 2 2016: #REF!; 3 2017: #REF!; 4 2018: #REF!; 5 2019: #REF!; 6 2020: #REF!; 7 2021: #REF!; 8 2022: #REF!; 9 2023: #REF!; 10 2024: #REF!; 11 2025: #REF!; 12 2026: #REF! | #REF!
| Meter Floor | #REF! | -1 2013: #REF!; 0 2014: #REF!; 1 2015: #REF!; 2 2016: #REF!; 3 2017: #REF!; 4 2018: #REF!; 5 2019: #REF!; 6 2020: #REF!; 7 2021: #REF!; 8 2022: #REF!; 9 2023: #REF!; 10 2024: #REF!; 11 2025: #REF!; 12 2026: #REF! | #REF!
| Hybrid AMI | -1.4661 | 0.0019191 | 0.0017992 | -1.2666 | -35.6302 | -39.2143 | -21.4868 | -18.688 | -16.6049 | -15.0848 | -13.3293 | -11.6833 | -1.6312 | 7.2945 | 27.7467 | 28.9221 | 30.0031 | 31.1495 | 32.2667 | 33.4184 | 34.875 | 36.7413 | 39.4238 | 40.6785 | 42.1307 | 43.8867 | 45.6345 | 48.0851 | 49.1398 | 299.5521
| L+G Proposal | -253.2686 | 0.0019191 | 3.2758 | 2.9896 | -23.9859 | -28.2436 | -34.0951 | -33.1515 | -33.1596 | -33.8693 | -34.4764 | -35.3247 | -36.1723 | -33.124 | -15.1353 | -16.2165 | -17.5224 | -18.872 | -20.3974 | -22.0307 | -23.5091 | -24.7319 | -25.8717 | -28.0095 | -30.1226 | -32.1135 | -34.3033 | -35.9918 | -39.2856 | -631.4486
| Two Vendors Two Networks | -4.3368 | 0.0019191 | 0.0017992 | -2.5349 | -35.9127 | -40.9346 | -20.445 | -17.7139 | -15.5977 | -13.9903 | -12.1189 | -10.3351 | -0.82212 | 7.5813 | 26.4192 | 27.5882 | 28.6577 | 29.7988 | 30.9044 | 32.0424 | 33.483 | 35.3327 | 37.9281 | 39.1872 | 40.6455 | 42.409 | 44.1686 | 46.6308 | 47.6987 | 241.5758
| Full Deployment | -77.8584 | 0.0019191 | 0.0017992 | -3.6122 | -96.3572 | -107.8934 | -129.209 | 15.8104 | 17.0227 | 17.8346 | 19.1303 | 20.5101 | 21.9841 | 23.4877 | 24.8858 | 26.0405 | 27.1008 | 28.2283 | 29.3265 | 30.4597 | 31.8983 | 33.7472 | 36.4169 | 37.6604 | 39.1035 | 40.8522 | 42.5873 | 45.035 | 46.089 | 184.4321
| (millions $) | NPV (Scenario compared with Status Quo) | 0 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | Nominal Net Benefits (Scenario compared with Status Quo)
Annual Net Benefits
| Hybrid AMI | 57.0685 | 0.0019191 | 0.0017992 | -2.2166 | -37.1316 | -38.3028 | -19.4654 | -15.7852 | -12.7265 | -10.1829 | -7.3595 | -4.6143 | 6.4564 | 16.1969 | 37.1749 | 38.7196 | 40.1211 | 41.7369 | 43.2996 | 44.9327 | 46.882 | 49.5434 | 53.3802 | 54.7509 | 56.3124 | 58.17 | 60.0111 | 62.5455 | 63.6736 | 485.5266
| Two Vendors Two Networks | 54.1978 | 0.0019191 | 0.0017992 | -3.4849 | -37.4141 | -40.0231 | -18.4237 | -14.8111 | -11.7193 | -9.0884 | -6.1491 | -3.2661 | 7.2655 | 16.4837 | 35.8474 | 37.3856 | 38.7757 | 40.3862 | 41.9372 | 43.5567 | 45.49 | 48.1347 | 51.8845 | 53.2596 | 54.8272 | 56.6924 | 58.5452 | 61.0912 | 62.2324 | 427.5504
| Full Deployment | -13.0998 | 0.0019191 | 0.0017992 | -4.5622 | -98.038 | -106.3555 | -125.7624 | 21.1325 | 22.9004 | 24.3389 | 26.3224 | 28.4338 | 30.5677 | 32.5577 | 34.314 | 35.838 | 37.2188 | 38.8157 | 40.3594 | 41.974 | 43.9053 | 46.5492 | 50.3733 | 51.7329 | 53.2852 | 55.1356 | 56.9639 | 59.4953 | 60.6228 | 381.0405
| Cumulative Net Benefits | NPV | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | Total (Nominal $)
| Meter Minimum |  | 2013: #REF!; 2014: #REF!; 2015: #REF!; 2016: #REF!; 2017: #REF!; 2018: #REF!; 2019: #REF!; 2020: #REF!; 2021: #REF!; 2022: #REF!; 2023: #REF!; 2024: #REF!; 2025: #REF!; 2026: #REF! | #REF!
| Meter Floor |  | 2013: #REF!; 2014: #REF!; 2015: #REF!; 2016: #REF!; 2017: #REF!; 2018: #REF!; 2019: #REF!; 2020: #REF!; 2021: #REF!; 2022: #REF!; 2023: #REF!; 2024: #REF!; 2025: #REF!; 2026: 0 | #REF!
| Hybrid AMI | 74.4522 | 0.0020682 | 0.0037377 | -1.9048 | -31.5702 | -59.965 | -73.3548 | -83.4302 | -90.9676 | -96.5638 | -100.3167 | -102.5001 | -99.6653 | -93.0666 | -79.0133 | -65.4315 | -52.3726 | -39.7673 | -27.6329 | -15.9486 | -4.6364 | 6.456 | 17.5458 | 28.1004 | 38.1732 | 47.8282 | 57.0706 | 66.0088 | 74.4522 | 74.4522
| Two Networks | 71.1825 | 0.0020682 | 0.0037377 | -2.9968 | -32.8878 | -62.5579 | -75.2311 | -84.6848 | -91.6257 | -96.6203 | -99.756 | -101.3014 | -98.1115 | -91.3959 | -77.8445 | -64.7305 | -52.1096 | -39.9122 | -28.1596 | -16.8332 | -5.8568 | 4.9202 | 15.6993 | 25.9663 | 35.7735 | 45.1832 | 54.1998 | 62.9302 | 71.1825 | 71.1825
| Full Deployment | 3.4434 | 0.0020682 | 0.0037377 | -3.9243 | -82.2493 | -161.0933 | -247.6023 | -234.1138 | -220.5507 | -207.175 | -193.7521 | -180.298 | -166.877 | -153.6128 | -140.641 | -128.07 | -115.9558 | -104.2327 | -92.9222 | -82.0073 | -71.4134 | -60.9913 | -50.5262 | -40.5535 | -31.0221 | -21.8708 | -13.0977 | -4.5954 | 3.4434 | 3.4434
| TCO by Option (Metering Only) | NPV (Scenario compared with Status Quo) | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | Total (Nominal $)
| Status Quo | 613.0458 | 25.4697 | 42.973 | 48.7802 | 45.4328 | 45.8781 | 45.9148 | 46.6068 | 48.0646 | 49.7521 | 52.0512 | 54.5012 | 56.9911 | 59.5339 | 62.0223 | 64.3455 | 66.527 | 68.8974 | 71.1729 | 73.4841 | 76.096 | 79.1401 | 81.6602 | 84.4403 | 87.476 | 90.8756 | 94.3222 | 98.543 | 101.4365 | 1603.7293
| Meter Minimum | #REF! | 32.1801 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
| Meter Floor | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
| Hybrid AMI | 614.5118 | 25.4678 | 42.9712 | 50.0468 | 81.063 | 85.0925 | 67.4016 | 65.2948 | 64.6694 | 64.8369 | 65.3805 | 66.1846 | 58.6223 | 52.2394 | 34.2755 | 35.4234 | 36.5239 | 37.7479 | 38.9062 | 40.0657 | 41.221 | 42.3988 | 42.2364 | 43.7618 | 45.3453 | 46.989 | 48.6877 | 50.4578 | 52.2966 | 1254.8255
| Two Vendors Two Networks | 617.3825 | 25.4678 | 42.9712 | 51.3151 | 81.3455 | 86.8128 | 66.3599 | 64.3207 | 63.6623 | 63.7424 | 64.1701 | 64.8363 | 57.8132 | 51.9526 | 35.6031 | 36.7573 | 37.8693 | 39.0986 | 40.2685 | 41.4417 | 42.613 | 43.8074 | 43.7321 | 45.2531 | 46.8305 | 48.4666 | 50.1536 | 51.9121 | 53.7377 | 1268.8229
| Full Deployment | 690.9042 | 25.4678 | 42.9712 | 52.3924 | 141.79 | 153.7715 | 175.1239 | 30.7963 | 31.0419 | 31.9175 | 32.921 | 33.9911 | 35.007 | 36.0462 | 37.1364 | 38.305 | 39.4261 | 40.6691 | 41.8463 | 43.0244 | 44.1978 | 45.3929 | 45.2433 | 46.7798 | 48.3725 | 50.0234 | 51.7349 | 53.508 | 55.3474 | 1328.0664
| L+G Contract Costs By Option | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
| Status Quo | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
| Meter Minimum | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
| Meter Floor | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
|  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
| Hybrid AMI | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
| Two Vendors Two Networks | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
| Full Deployment | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
| Termination Fees by Option | NPV (Scenario compared with Status Quo) | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | Total (Nominal $)
| Meter Minimum | 0 | 2013: 0; 2014: 0; 2015: 0; 2016: 0; 2017: 0; 2018: 0; 2019: 0; 2020: 0; 2021: 0; 2022: 0; 2023: 0; 2024: 0; 2025: 0; 2026: 0 | 0
| Meter Floor | 16.8153 | 2013: 0; 2014: 10.2017; 2015: 11.6884; 2016: 0; 2017: 0; 2018: 0; 2019: 0; 2020: 0; 2021: 0; 2022: 0; 2023: 0; 2024: 0; 2025: 0; 2026: 0 | 21.8901
| Hybrid AMI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Two Vendors Two Networks | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Full Deployment | 15.8819 | 0 | 0 | 0 | 1.3523 | 3.5643 | 17.6763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.593
| Spend on AMR Meters | NPV (Scenario compared with Status Quo) | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | Total (Nominal $)
| Status Quo | 307.2978 | -4.8175 | 9.7606 | 14.1456 | 22.615 | 26.1714 | 26.0747 | 25.982 | 26.5518 | 27.3019 | 28.6118 | 30.0259 | 31.4307 | 32.8371 | 34.135 | 35.2114 | 36.0868 | 37.0889 | 37.931 | 38.7405 | 39.7792 | 41.1749 | 41.9679 | 42.9383 | 44.0778 | 45.4905 | 46.8269 | 48.8661 | 49.4723 | 771.3134
| Meter Minimum | #REF! | -8.1008 | 4.8512 | 7.4178 | 9.7828 | 11.1092 | 11.6764 | 11.1612 | 11.1261 | 11.5239 | 12.006 | 12.5252 | 12.9945 | 13.4689 | 13.9699 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Meter Floor | #REF! | -8.1008 | 4.8512 | 7.4178 | 9.7828 | 11.1092 | 11.6764 | 11.1612 | 11.1261 | 11.5239 | 12.006 | 12.5252 | 12.9945 | 13.4689 | 13.9699 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Hybrid AMI | 28.6538 | -4.8175 | 9.7606 | 14.1456 | 9.2842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.373
| Full Deployment | 28.6538 | -4.8175 | 9.7606 | 14.1456 | 9.2842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.373
| Spend on new AMI Meter/Module Hardware | NPV (Scenario compared with Status Quo) | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | Total (Nominal $)
| Status Quo | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| #REF! | 119.7395 | 0 | 26.342 | 14.4144 | 15.3388 | 15.7963 | 16.0119 | 15.7798 | 15.8986 | 16.3143 | 16.7872 | 17.2899 | 17.6496 | 18.0167 | 18.3915 | 224.0311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| #REF! | 174.3602 | 0 | 79.8494 | 88.0138 | 8.02 | 8.3321 | 8.3863 | 7.9659 | 7.9111 | 8.1647 | 8.4747 | 8.812 | 9.1177 | 9.4298 | 9.7607 | 262.2382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Hybrid AMI | 395.4346 | 0 | 0 | 0 | 42.5611 | 55.5979 | 52.7291 | 51.4774 | 51.6901 | 52.7325 | 54.2028 | 55.9985 | 49.2966 | 43.4558 | 25.6049 | 26.5403 | 27.4234 | 28.4232 | 29.3521 | 30.2765 | 31.1908 | 32.1213 | 31.7014 | 32.9617 | 34.2723 | 35.6351 | 37.0521 | 38.5256 | 40.0579 | 875.2449
| Full Deployment | 445.2977 | 0 | 0 | 0 | 96.6885 | 120.8241 | 147.144 | 20.3131 | 20.4193 | 21.1522 | 22.0095 | 22.9301 | 23.7928 | 24.6753 | 25.6049 | 26.5403 | 27.4234 | 28.4232 | 29.3521 | 30.2765 | 31.1908 | 32.1213 | 31.7014 | 32.9617 | 34.2723 | 35.6351 | 37.0521 | 38.5256 | 40.0579 | 885.4518
| Network Spend | NPV (Scenario compared with Status Quo) | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | Total (Nominal $)
| Status Quo | 29.5145 | 0 | 0 | 0 | 1.6169 | 2.2917 | 2.4016 | 2.5167 | 2.6371 | 2.7632 | 2.8951 | 3.0332 | 3.1777 | 3.329 | 3.4873 | 3.6529 | 3.8263 | 4.0078 | 4.1977 | 4.3964 | 4.6043 | 4.8219 | 5.0497 | 5.2879 | 5.5373 | 5.7982 | 6.0712 | 6.3569 | 6.6558 | 81.3299
| Meter Minimum | #REF! | 5.6171 | 5.8015 | 2.6458 | 100.4963 | 125.0558 | 151.4753 | 24.746 | 24.956 | 25.795 | 26.7607 | 27.792 | 28.7679 | 29.7659 | 30.8137 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Meter Floor | #REF! | 5.6171 | 5.8015 | 2.6458 | 100.4963 | 125.0558 | 151.4753 | 24.746 | 24.956 | 25.795 | 26.7607 | 27.792 | 28.7679 | 29.7659 | 30.8137 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Hybrid AMI | 29.4991 | 0 | 0 | 0 | 8.7814 | 13.9457 | 1.3533 | 1.3834 | 1.4142 | 1.4458 | 1.4781 | 1.5112 | 1.5451 | 1.5798 | 1.6153 | 1.6517 | 1.689 | 1.7272 | 1.7663 | 1.8064 | 1.8474 | 1.8894 | 1.9325 | 1.9766 | 2.0219 | 2.0683 | 2.1159 | 2.1647 | 2.2147 | 56.4301
| Full Deployment | 33.0547 | 0 | 0 | 0 | 13.2319 | 13.9457 | 1.3533 | 1.3834 | 1.4142 | 1.4458 | 1.4781 | 1.5112 | 1.5451 | 1.5798 | 1.6153 | 1.6517 | 1.689 | 1.7272 | 1.7663 | 1.8064 | 1.8474 | 1.8894 | 1.9325 | 1.9766 | 2.0219 | 2.0683 | 2.1159 | 2.1647 | 2.2147 | 60.8806
Net Margin
| #REF! | #REF! | 2013: -20.85%; 2014: #REF!; 2015: #REF!; 2016: #REF!; 2017: #REF!; 2018: #REF!; 2019: #REF!; 2020: #REF!; 2021: #REF!; 2022: #REF!; 2023: #REF!; 2024: #REF!; 2025: #REF!; 2026: #REF! | #REF!
| #REF! | #REF! | 2013: #REF!; 2014: #REF!; 2015: #REF!; 2016: #REF!; 2017: #REF!; 2018: #REF!; 2019: #REF!; 2020: #REF!; 2021: #REF!; 2022: #REF!; 2023: #REF!; 2024: #REF!; 2025: #REF!; 2026: #REF! | #REF!
| Full Deployment | -11.27% | 0.007535% | 0.004187% | -6.894% | -67.96% | -70.16% | -73.78% | 51.34% | 54.84% | 55.88% | 58.11% | 60.34% | 62.8% | 65.16% | 67.01% | 67.98% | 68.74% | 69.41% | 70.08% | 70.8% | 72.17% | 74.34% | 80.49% | 80.51% | 80.84% | 81.67% | 82.32% | 84.16% | 83.27% | 13.89%
| Hybrid AMI | -0.2386% | 0.007535% | 0.004187% | -2.531% | -43.95% | -46.08% | -31.88% | -28.62% | -25.68% | -23.27% | -20.39% | -17.65% | -2.783% | 13.96% | 80.95% | 81.65% | 82.15% | 82.52% | 82.93% | 83.41% | 84.6% | 86.66% | 93.34% | 92.95% | 92.91% | 93.4% | 93.73% | 95.3% | 93.96% | 23.87%
| IRR and ROI | IRR (Solver Calculated) | 2013: ROI (CAPEX Investment to Net Benefits); 2014: IRR Excel Calculated (with Solver Guess)
| #REF! | 571051% | 2013: #REF!; 2014: NA
| #REF! | -12.22% | 2013: #REF!; 2014: #VALUE!
Hybrid-L+G
Full Deployment
| PSE O&M | NPV (Scenario compared with Status Quo) | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | Total (Nominal $)
| Status Quo | 110.4318 | 4.1697 | 4.5336 | 5.2442 | 8.7399 | 9.8974 | 9.1866 | 9.5109 | 9.8388 | 9.7755 | 10.1531 | 10.5524 | 10.9735 | 11.3981 | 11.7855 | 12.1137 | 12.4056 | 12.7127 | 13.002 | 13.2932 | 13.6668 | 14.1539 | 14.9374 | 15.2255 | 15.5632 | 15.9815 | 16.5238 | 17.1319 | 17.3055 | 278.8147
| Meter Minimum | #REF! | 0.94297 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Meter Floor | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Hybrid AMI | 90.5962 | 4.1678 | 4.5318 | 5.2425 | 6.2262 | 5.7703 | 6.2622 | 6.7947 | 7.3414 | 7.9055 | 8.4895 | 9.0958 | 9.5585 | 9.9461 | 10.2218 | 10.5059 | 10.7984 | 11.0999 | 11.4102 | 11.7294 | 12.0576 | 12.3951 | 12.7361 | 13.088 | 13.451 | 13.8256 | 14.2046 | 14.6024 | 15.0141 | 234.6515
| Full Deployment | 129.5713 | 4.1678 | 4.5318 | 8.1468 | 10.9185 | 11.5463 | 11.5102 | 11.7478 | 11.9461 | 12.15 | 12.3599 | 12.5761 | 12.7986 | 13.0274 | 13.2628 | 13.5738 | 13.8925 | 14.2195 | 14.5546 | 14.8981 | 15.2499 | 15.6104 | 15.9732 | 16.3453 | 16.7272 | 17.1191 | 17.5212 | 17.9329 | 18.3565 | 318.8538
| CAPEX | NPV (Scenario compared with Status Quo) | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | Total (Nominal $)
| Status Quo | 265.1467 | -6.9147 | 7.4107 | 11.1706 | 18.703 | 21.9943 | 22.7418 | 22.4978 | 22.9191 | 23.9187 | 25.0442 | 26.2594 | 27.4513 | 28.6493 | 29.7843 | 30.7654 | 31.5909 | 32.5374 | 33.3513 | 34.141 | 35.0881 | 36.2897 | 36.6038 | 37.6027 | 38.7337 | 40.0704 | 41.2484 | 43.0493 | 43.8675 | 668.4044
| Meter Minimum | #REF! | 3.0224 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Meter Floor | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Hybrid AMI | 429.2488 | -6.9147 | 7.4107 | 12.439 | 59.528 | 69.5578 | 53 | 51.572 | 51.6158 | 52.4875 | 53.7822 | 55.3958 | 48.3652 | 42.2933 | 24.0537 | 24.9174 | 25.7255 | 26.648 | 27.496 | 28.3363 | 29.1634 | 30.0037 | 29.5003 | 30.6739 | 31.8943 | 33.1633 | 34.483 | 35.8554 | 37.2825 | 892.1083
| Full Deployment | 475.0624 | -6.9147 | 7.4107 | 11.8802 | 117.1213 | 133.5005 | 145.9374 | 19.0485 | 19.0958 | 19.7675 | 20.561 | 21.415 | 22.2085 | 23.0189 | 23.8736 | 24.7312 | 25.5336 | 26.4496 | 27.2917 | 28.1263 | 28.9478 | 29.7825 | 29.2702 | 30.4345 | 31.6453 | 32.9043 | 34.2136 | 35.5751 | 36.991 | 893.0413
| L&G O&M | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | 0
| Status Quo | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
| Meter Minimum | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
| Meter Floor | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
| Hybrid AMI | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
| Full Deployment | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Corporate Model Inputs
Without Applications
Total O&M
| Status Quo | 347.8991 | 32.3844 | 35.5622 | 37.6096 | 26.7298 | 23.8838 | 23.173 | 24.109 | 25.1454 | 25.8334 | 27.007 | 28.2418 | 29.5398 | 30.8846 | 32.238 | 33.5801 | 34.9361 | 36.3601 | 37.8215 | 39.3431 | 41.0079 | 42.8504 | 45.0564 | 46.8375 | 48.7423 | 50.8053 | 53.0738 | 55.4937 | 57.569
| Hybrid AMI | 185.263 | 32.3825 | 35.5604 | 37.6078 | 21.5351 | 15.5347 | 14.4017 | 13.7228 | 13.0536 | 12.3494 | 11.5984 | 10.7887 | 10.2571 | 9.9461 | 10.2218 | 10.5059 | 10.7984 | 11.0999 | 11.4102 | 11.7294 | 12.0576 | 12.3951 | 12.7361 | 13.088 | 13.451 | 13.8256 | 14.2046 | 14.6024 | 15.0141
| Full Deployment | 215.8418 | 32.3825 | 35.5604 | 40.5122 | 24.6687 | 20.271 | 29.1865 | 11.7478 | 11.9461 | 12.15 | 12.3599 | 12.5761 | 12.7986 | 13.0274 | 13.2628 | 13.5738 | 13.8925 | 14.2195 | 14.5546 | 14.8981 | 15.2499 | 15.6104 | 15.9732 | 16.3453 | 16.7272 | 17.1191 | 17.5212 | 17.9329 | 18.3565
Meter Capital
| Status Quo | 252.5599 | -6.9147 | 7.4107 | 11.1706 | 18.0171 | 21.0051 | 21.7068 | 21.4148 | 21.786 | 22.7331 | 23.8037 | 24.9614 | 26.0932 | 27.2282 | 28.2974 | 29.2096 | 29.9631 | 30.8341 | 31.5692 | 32.2763 | 33.137 | 34.2482 | 34.4678 | 35.3677 | 36.3952 | 37.6235 | 38.6882 | 40.3705 | 41.0646
| Hybrid AMI | 403.0409 | -6.9147 | 7.4107 | 11.1706 | 49.7482 | 54.9583 | 51.926 | 50.5031 | 50.5357 | 51.3885 | 52.6588 | 54.2435 | 47.411 | 41.4726 | 23.5382 | 24.387 | 25.1805 | 26.0871 | 26.9196 | 27.7443 | 28.5557 | 29.3798 | 28.8567 | 30.0098 | 31.2091 | 32.4563 | 33.7533 | 35.1022 | 36.5049
| Full Deployment | 452.8968 | -6.9147 | 7.4107 | 11.8802 | 104.4984 | 120.6115 | 145.6637 | 18.7678 | 18.808 | 19.4723 | 20.2583 | 21.1045 | 21.8899 | 22.692 | 23.5382 | 24.387 | 25.1805 | 26.0871 | 26.9196 | 27.7443 | 28.5557 | 29.3798 | 28.8567 | 30.0098 | 31.2091 | 32.4563 | 33.7533 | 35.1022 | 36.5049
Network Capital
| Status Quo | 12.5868 | 0 | 0 | 0 | 0.68592 | 0.98921 | 1.035 | 1.083 | 1.1331 | 1.1856 | 1.2405 | 1.298 | 1.3581 | 1.4211 | 1.4869 | 1.5558 | 1.6278 | 1.7032 | 1.7821 | 1.8647 | 1.9511 | 2.0415 | 2.136 | 2.235 | 2.3385 | 2.4468 | 2.5602 | 2.6788 | 2.8029
| Hybrid AMI | 26.208 | 0 | 0 | 1.2683 | 9.7798 | 14.5995 | 1.074 | 1.0689 | 1.0801 | 1.099 | 1.1234 | 1.1523 | 0.95424 | 0.82074 | 0.51549 | 0.5304 | 0.54503 | 0.56087 | 0.57633 | 0.59196 | 0.60772 | 0.62388 | 0.64361 | 0.66403 | 0.68518 | 0.70708 | 0.72976 | 0.75324 | 0.77757
| Full Deployment | 22.1656 | 0 | 0 | 0 | 12.6229 | 12.889 | 0.27373 | 0.28068 | 0.28783 | 0.29519 | 0.30276 | 0.31056 | 0.31859 | 0.32686 | 0.33538 | 0.34415 | 0.35318 | 0.36249 | 0.37209 | 0.38197 | 0.39216 | 0.40267 | 0.4135 | 0.42467 | 0.43619 | 0.44808 | 0.46034 | 0.47299 | 0.48604
With AMI Applications
Total O&M
| Status Quo | 766.147 | 68.1127 | 71.9308 | 74.4135 | 63.9672 | 61.523 | 61.1831 | 62.5303 | 63.7989 | 64.775 | 66.0186 | 67.1665 | 68.64 | 70.5907 | 71.9263 | 73.2219 | 74.7237 | 75.7527 | 76.9167 | 78.0138 | 79.2188 | 80.9832 | 83.3385 | 86.0499 | 88.9073 | 91.9457 | 95.213 | 98.6554 | 101.7774 | 1825.649
| Hybrid AMI | 536.0832 | 68.1108 | 71.929 | 74.4118 | 58.7201 | 51.6948 | 49.8086 | 48.4463 | 46.912 | 45.4494 | 43.6771 | 41.6572 | 40.2578 | 39.7126 | 39.4188 | 39.2606 | 39.3511 | 38.7603 | 38.299 | 37.683 | 37.0286 | 36.8834 | 37.0618 | 38.2279 | 39.4343 | 40.6828 | 41.9673 | 43.3037 | 44.6888 | 1142.8792
| Full Deployment | 560.4379 | 68.1108 | 71.929 | 77.3161 | 62.0332 | 55.8047 | 63.1682 | 44.0521 | 43.8052 | 43.6476 | 43.2163 | 42.5899 | 42.3033 | 42.6262 | 42.4598 | 42.3284 | 42.4452 | 41.8798 | 41.4435 | 40.8516 | 40.221 | 40.0987 | 40.2989 | 41.4853 | 42.7106 | 43.9762 | 45.2839 | 46.6342 | 48.0311 | 1200.8016
Meter Capital
| Status Quo | 252.5599 | -6.9147 | 7.4107 | 11.1706 | 18.0171 | 21.0051 | 21.7068 | 21.4148 | 21.786 | 22.7331 | 23.8037 | 24.9614 | 26.0932 | 27.2282 | 28.2974 | 29.2096 | 29.9631 | 30.8341 | 31.5692 | 32.2763 | 33.137 | 34.2482 | 34.4678 | 35.3677 | 36.3952 | 37.6235 | 38.6882 | 40.3705 | 41.0646 | 633.8053
| Hybrid AMI | 403.0409 | -6.9147 | 7.4107 | 11.1706 | 49.7482 | 54.9583 | 51.926 | 50.5031 | 50.5357 | 51.3885 | 52.6588 | 54.2435 | 47.411 | 41.4726 | 23.5382 | 24.387 | 25.1805 | 26.0871 | 26.9196 | 27.7443 | 28.5557 | 29.3798 | 28.8567 | 30.0098 | 31.2091 | 32.4563 | 33.7533 | 35.1022 | 36.5049 | 850.8365
| Full Deployment | 452.8968 | -6.9147 | 7.4107 | 11.8802 | 104.4984 | 120.6115 | 145.6637 | 18.7678 | 18.808 | 19.4723 | 20.2583 | 21.1045 | 21.8899 | 22.692 | 23.5382 | 24.387 | 25.1805 | 26.0871 | 26.9196 | 27.7443 | 28.5557 | 29.3798 | 28.8567 | 30.0098 | 31.2091 | 32.4563 | 33.7533 | 35.1022 | 36.5049 | 860.4666
Network Capital
| Status Quo | 20.8172 | 0.25707 | 0.52699 | 0.54017 | 1.2396 | 1.5567 | 1.6167 | 1.878 | 2.0499 | 2.1253 | 2.2037 | 2.2852 | 2.37 | 2.4582 | 2.55 | 2.6455 | 2.7448 | 2.8481 | 2.9556 | 3.0675 | 3.184 | 2.8839 | 2.136 | 2.235 | 2.3385 | 2.4468 | 2.5602 | 2.6788 | 2.8029 | 53.1433
| Hybrid AMI | 43.3315 | 0.25707 | 0.52699 | 2.7585 | 11.8871 | 15.7345 | 2.2374 | 2.6589 | 2.9136 | 2.9783 | 3.0496 | 3.1268 | 2.978 | 2.8951 | 2.6417 | 2.7098 | 2.7789 | 2.8506 | 2.9233 | 2.9976 | 3.0735 | 2.3088 | 0.64361 | 0.66403 | 0.68518 | 0.70708 | 0.72976 | 0.75324 | 0.77757 | 78.4273
| Full Deployment | 39.2891 | 0.25707 | 0.52699 | 1.4902 | 14.7302 | 14.0241 | 1.4371 | 1.8707 | 2.1213 | 2.1745 | 2.229 | 2.285 | 2.3424 | 2.4012 | 2.4616 | 2.5235 | 2.5871 | 2.6522 | 2.7191 | 2.7876 | 2.858 | 2.0876 | 0.4135 | 0.42467 | 0.43619 | 0.44808 | 0.46034 | 0.47299 | 0.48604 | 70.2889
Total Capital
| Status Quo | 273.3771 | -6.6576 | 7.9377 | 11.7108 | 19.2566 | 22.5618 | 23.3235 | 23.2928 | 23.8359 | 24.8583 | 26.0074 | 27.2467 | 28.4632 | 29.6865 | 30.8474 | 31.8551 | 32.7078 | 33.6822 | 34.5248 | 35.3438 | 36.321 | 37.1321 | 36.6038 | 37.6027 | 38.7337 | 40.0704 | 41.2484 | 43.0493 | 43.8675 | 686.9486
| Hybrid AMI | 446.3723 | -6.6576 | 7.9377 | 13.9291 | 61.6353 | 70.6928 | 54.1634 | 53.162 | 53.4493 | 54.3668 | 55.7084 | 57.3702 | 50.389 | 44.3677 | 26.18 | 27.0968 | 27.9594 | 28.9377 | 29.843 | 30.742 | 31.6292 | 31.6886 | 29.5003 | 30.6739 | 31.8943 | 33.1633 | 34.483 | 35.8554 | 37.2825 | 929.2638
| Full Deployment | 492.1859 | -6.6576 | 7.9377 | 13.3704 | 119.2286 | 134.6355 | 147.1008 | 20.6385 | 20.9293 | 21.6468 | 22.4873 | 23.3894 | 24.2322 | 25.0932 | 25.9998 | 26.9106 | 27.7675 | 28.7394 | 29.6387 | 30.532 | 31.4136 | 31.4674 | 29.2702 | 30.4345 | 31.6453 | 32.9043 | 34.2136 | 35.5751 | 36.991 | 930.7555
Total O&M + Lost Revenue
| Status Quo | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Hybrid AMI | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Full Deployment | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Lost Revenue
| Status Quo | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Hybrid AMI | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Full Deployment | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Selected Totals
| AMR Metering | NPV (Scenario compared with Status Quo) | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
AMR Meter Capital Spend
| Status Quo CAPEX | 252.5599 | -6.9147 | 7.4107 | 11.1706 | 18.0171 | 21.0051 | 21.7068 | 21.4148 | 21.786 | 22.7331 | 23.8037 | 24.9614 | 26.0932 | 27.2282 | 28.2974 | 29.2096 | 29.9631 | 30.8341 | 31.5692 | 32.2763 | 33.137 | 34.2482 | 34.4678 | 35.3677 | 36.3952 | 37.6235 | 38.6882 | 40.3705 | 41.0646
| Hybrid AMI CAPEX | 22.5512 | -6.9147 | 7.4107 | 11.1706 | 7.5813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Full Deployment CAPEX | 22.5512 | -6.9147 | 7.4107 | 11.1706 | 7.5813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AMR Meter O&M Spend
| Status Quo O&M | 43.6293 | 1.813 | 1.9061 | 1.9567 | 2.8045 | 3.175 | 3.2864 | 3.4609 | 3.6341 | 3.8487 | 4.0704 | 4.3087 | 4.5633 | 4.8158 | 5.0253 | 5.1695 | 5.2712 | 5.3815 | 5.4672 | 5.5478 | 5.7034 | 5.9649 | 6.5149 | 6.5613 | 6.6487 | 6.8079 | 7.0537 | 7.3842 | 7.2691
| Hybrid AMI O&M | 4.0975 | 1.813 | 1.9061 | 1.9567 | 0.80623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Full Deployment O&M | 4.0975 | 1.813 | 1.9061 | 1.9567 | 0.80623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AMI Metering
AMI Meter Capital Spend
| Status Quo CAPEX | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Hybrid AMI CAPEX | 380.4896 | 0 | 0 | 0 | 42.1669 | 54.9583 | 51.926 | 50.5031 | 50.5357 | 51.3885 | 52.6588 | 54.2435 | 47.411 | 41.4726 | 23.5382 | 24.387 | 25.1805 | 26.0871 | 26.9196 | 27.7443 | 28.5557 | 29.3798 | 28.8567 | 30.0098 | 31.2091 | 32.4563 | 33.7533 | 35.1022 | 36.5049
| Full Deployment CAPEX | 428.6075 | 0 | 0 | 0 | 96.1927 | 119.8718 | 145.6637 | 18.7678 | 18.808 | 19.4723 | 20.2583 | 21.1045 | 21.8899 | 22.692 | 23.5382 | 24.387 | 25.1805 | 26.0871 | 26.9196 | 27.7443 | 28.5557 | 29.3798 | 28.8567 | 30.0098 | 31.2091 | 32.4563 | 33.7533 | 35.1022 | 36.5049
AMI Meter O&M Spend
| Status Quo O&M | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Hybrid AMI O&M | 14.945 | 0 | 0 | 0 | 0.39416 | 0.63966 | 0.80315 | 0.97433 | 1.1543 | 1.344 | 1.544 | 1.7551 | 1.8856 | 1.9833 | 2.0667 | 2.1533 | 2.243 | 2.3361 | 2.4324 | 2.5321 | 2.6351 | 2.7415 | 2.8447 | 2.9519 | 3.0632 | 3.1788 | 3.2988 | 3.4235 | 3.5529
| Full Deployment O&M | 16.6902 | 0 | 0 | 0 | 0.4958 | 0.95229 | 1.4804 | 1.5453 | 1.6113 | 1.6799 | 1.7513 | 1.8257 | 1.903 | 1.9833 | 2.0667 | 2.1533 | 2.243 | 2.3361 | 2.4324 | 2.5321 | 2.6351 | 2.7415 | 2.8447 | 2.9519 | 3.0632 | 3.1788 | 3.2988 | 3.4235 | 3.5529
Network Expenditures
Network Capital Spend
| Status Quo CAPEX | 12.5868 | 0 | 0 | 0 | 0.68592 | 0.98921 | 1.035 | 1.083 | 1.1331 | 1.1856 | 1.2405 | 1.298 | 1.3581 | 1.4211 | 1.4869 | 1.5558 | 1.6278 | 1.7032 | 1.7821 | 1.8647 | 1.9511 | 2.0415 | 2.136 | 2.235 | 2.3385 | 2.4468 | 2.5602 | 2.6788 | 2.8029
| Hybrid AMI CAPEX | 18.61 | 0 | 0 | 0 | 8.1724 | 12.889 | 0.27373 | 0.28068 | 0.28783 | 0.29519 | 0.30276 | 0.31056 | 0.31859 | 0.32686 | 0.33538 | 0.34415 | 0.35318 | 0.36249 | 0.37209 | 0.38197 | 0.39216 | 0.40267 | 0.4135 | 0.42467 | 0.43619 | 0.44808 | 0.46034 | 0.47299 | 0.48604
| Full Deployment CAPEX | 22.1656 | 0 | 0 | 0 | 12.6229 | 12.889 | 0.27373 | 0.28068 | 0.28783 | 0.29519 | 0.30276 | 0.31056 | 0.31859 | 0.32686 | 0.33538 | 0.34415 | 0.35318 | 0.36249 | 0.37209 | 0.38197 | 0.39216 | 0.40267 | 0.4135 | 0.42467 | 0.43619 | 0.44808 | 0.46034 | 0.47299 | 0.48604
Network O&M Spend
| Status Quo O&M | 16.9277 | 0 | 0 | 0 | 0.93097 | 1.3025 | 1.3666 | 1.4337 | 1.504 | 1.5775 | 1.6546 | 1.7352 | 1.8196 | 1.9079 | 2.0004 | 2.0972 | 2.1985 | 2.3045 | 2.4155 | 2.5317 | 2.6533 | 2.7805 | 2.9136 | 3.053 | 3.1988 | 3.3514 | 3.511 | 3.6781 | 3.8529
| Hybrid AMI O&M | 10.8891 | 0 | 0 | 0 | 0.60903 | 1.0567 | 1.0795 | 1.1028 | 1.1264 | 1.1506 | 1.1753 | 1.2006 | 1.2265 | 1.2529 | 1.2799 | 1.3076 | 1.3358 | 1.3647 | 1.3942 | 1.4244 | 1.4552 | 1.4868 | 1.519 | 1.552 | 1.5857 | 1.6202 | 1.6556 | 1.6917 | 1.7287
| Full Deployment O&M | 10.8891 | 0 | 0 | 0 | 0.60903 | 1.0567 | 1.0795 | 1.1028 | 1.1264 | 1.1506 | 1.1753 | 1.2006 | 1.2265 | 1.2529 | 1.2799 | 1.3076 | 1.3358 | 1.3647 | 1.3942 | 1.4244 | 1.4552 | 1.4868 | 1.519 | 1.552 | 1.5857 | 1.6202 | 1.6556 | 1.6917 | 1.7287
NOC Head End Costs
Head End CAPEX
| Status Quo CAPEX | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Hybrid AMI CAPEX | 7.598 | 0 | 0 | 1.2683 | 1.6074 | 1.7104 | 0.8003 | 0.7882 | 0.7923 | 0.80379 | 0.8206 | 0.84177 | 0.63565 | 0.49388 | 0.18012 | 0.18625 | 0.19185 | 0.19838 | 0.20424 | 0.20999 | 0.21556 | 0.22121 | 0.2301 | 0.23936 | 0.24899 | 0.259 | 0.26942 | 0.28026 | 0.29153
| Full Deployment CAPEX | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Head End O&M
| Status Quo O&M | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Hybrid AMI O&M | 12.3606 | 0 | 0 | 0 | 0.17659 | 0.37445 | 0.54237 | 0.7114 | 0.8848 | 1.0641 | 1.2506 | 1.4452 | 1.6027 | 1.7351 | 1.8076 | 1.8828 | 1.9607 | 2.0416 | 2.1253 | 2.2119 | 2.3015 | 2.3941 | 2.4903 | 2.5905 | 2.6947 | 2.8031 | 2.9159 | 3.0331 | 3.1551
| Full Deployment O&M | 54.0056 | 0 | 0 | 3.6139 | 5.6739 | 6.714 | 4.9833 | 5.0608 | 5.0959 | 5.1321 | 5.1694 | 5.2077 | 5.2473 | 5.288 | 5.3299 | 5.4418 | 5.5561 | 5.6728 | 5.7919 | 5.9136 | 6.0377 | 6.1645 | 6.294 | 6.4262 | 6.5611 | 6.6989 | 6.8396 | 6.9832 | 7.1298
Telecom and Other Costs
Telecome & Other CAPEX
| Status Quo O&M | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Hybrid AMI O&M | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Full Deployment O&M | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Telecome & Other O&M
| Status Quo O&M | 38.7662 | 2.0725 | 2.1837 | 2.2692 | 3.211 | 3.4286 | 3.4521 | 3.51 | 3.569 | 3.6291 | 3.6904 | 3.7528 | 3.8165 | 3.8813 | 3.9474 | 4.0148 | 4.0834 | 4.1534 | 4.2246 | 4.2973 | 4.3713 | 4.4468 | 4.5236 | 4.602 | 4.6818 | 4.7632 | 4.8741 | 4.9581 | 5.0449
| Hybrid AMI O&M | 46.2989 | 2.0706 | 2.1819 | 2.2675 | 3.3435 | 3.6995 | 3.8372 | 4.0062 | 4.1758 | 4.3467 | 4.5196 | 4.6949 | 4.8437 | 4.9748 | 5.0676 | 5.1623 | 5.2589 | 5.3575 | 5.4582 | 5.561 | 5.6658 | 5.7728 | 5.8821 | 5.9936 | 6.1074 | 6.2235 | 6.3344 | 6.4541 | 6.5774
| Full Deployment O&M | 43.6219 | 2.0706 | 2.1819 | 2.2675 | 3.1613 | 3.563 | 3.9669 | 4.0389 | 4.1124 | 4.1874 | 4.264 | 4.3421 | 4.4219 | 4.5032 | 4.5863 | 4.6711 | 4.7576 | 4.8459 | 4.936 | 5.028 | 5.1219 | 5.2177 | 5.3155 | 5.4153 | 5.5172 | 5.6212 | 5.7273 | 5.8345 | 5.945
Comparison of Costs
Status Quo vs Hybrid AMI
| Year | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | Total
| L+G Managed Service Contract | -142.8004 | 0 | 0 | 0 | -2.6811 | -4.222 | -5.847 | -7.67 | -9.5945 | -11.6139 | -13.7451 | -15.9965 | -17.8676 | -19.4866 | -20.4525 | -21.4664 | -22.5305 | -23.6473 | -24.8196 | -26.0499 | -27.3412 | -28.6965 | -30.119 | -31.612 | -33.1791 | -34.8238 | -36.55 | -38.3618 | -40.2634 | -433.462
CAPEX | AMR Electric Meter Hardware (Growth) | -27.2826 | 0 | 0 | 0 | -1.2411 | -2.842 | -2.73 | -2.5749 | -2.5463 | -2.6173 | -2.7051 | -2.8021 | -2.8904 | -2.9817 | -3.0791 | -3.1772 | -3.2672 | -3.3715 | -3.4675 | -3.5621 | -3.6541 | -3.7483 | -4.7117 | -4.9012 | -5.0984 | -5.3034 | -5.4033 | -5.6206 | -5.8467 | -73.2726
CAPEX | AMR Electric Meter Hardware (Maintenance) | -11.3109 | 0 | 0 | 0 | -0.32944 | -0.71865 | -0.74829 | -0.93005 | -1.108 | -1.2751 | -1.4448 | -1.6381 | -1.8551 | -2.0525 | -2.135 | -2.0504 | -1.8511 | -1.6546 | -1.3839 | -1.0844 | -0.9425 | -1.0308 | -1.8211 | -1.4154 | -1.0851 | -0.90124 | -0.88045 | -1.0507 | -0.17244 | -29.4554
CAPEX | AMR Electric Meter Exchange (Growth) | -11.8445 | 0 | 0 | 0 | -0.6218 | -1.2365 | -1.1866 | -1.1181 | -1.1046 | -1.1343 | -1.1712 | -1.212 | -1.249 | -1.2872 | -1.3279 | -1.3689 | -1.4063 | -1.4497 | -1.4895 | -1.5287 | -1.5666 | -1.6055 | -2.0161 | -2.0952 | -2.1773 | -2.2627 | -2.3514 | -2.4436 | -2.5394 | -31.6158
O&M | AMR Electric Meter Exchange (Maintenance) | -4.9011 | 0 | 0 | 0 | -0.16505 | -0.31268 | -0.32525 | -0.40386 | -0.48067 | -0.5526 | -0.62555 | -0.70854 | -0.8016 | -0.88603 | -0.92074 | -0.8834 | -0.79676 | -0.71146 | -0.5945 | -0.46536 | -0.40409 | -0.44153 | -0.77923 | -0.60507 | -0.46339 | -0.38451 | -0.38315 | -0.4568 | -0.074895 | -12.7119
CAPEX | AMR Gas Meter Hardware (Growth) | -72.6713 | 0 | 0 | 0 | -3.0182 | -7.0462 | -7.4087 | -7.0843 | -7.0646 | -7.3198 | -7.6287 | -7.9615 | -8.2627 | -8.5674 | -8.8893 | -9.2082 | -9.4979 | -9.8383 | -10.1378 | -10.4299 | -10.7126 | -10.9967 | -9.4869 | -9.8685 | -10.2654 | -10.6783 | -11.0438 | -11.488 | -11.9501 | -191.3716
CAPEX | AMR Gas Meter Hardware (Maintenance) | -20.4526 | 0 | 0 | 0 | -0.86583 | -1.6105 | -1.6947 | -1.7785 | -1.8639 | -1.9528 | -2.0457 | -2.1428 | -2.2439 | -2.3493 | -2.4591 | -2.5734 | -2.692 | -2.8154 | -2.9435 | -3.0762 | -3.2137 | -3.3559 | -3.4909 | -3.6313 | -3.7774 | -3.9293 | -4.0638 | -4.2273 | -4.3973 | -56.5062
CAPEX | AMR Gas Meter Exchange (Growth) | -41.6794 | 0 | 0 | 0 | -1.8732 | -4.0629 | -4.2677 | -4.0769 | -4.0615 | -4.2041 | -4.3773 | -4.5637 | -4.7318 | -4.9015 | -5.0806 | -5.2578 | -5.4179 | -5.6065 | -5.7715 | -5.9321 | -6.0869 | -6.2421 | -5.3799 | -5.5908 | -5.81 | -6.0377 | -6.2744 | -6.5204 | -6.776 | -109.3344
O&M | AMR Gas Meter Exchange (Maintenance) | -11.7226 | 0 | 0 | 0 | -0.53737 | -0.92864 | -0.97624 | -1.0235 | -1.0716 | -1.1216 | -1.1738 | -1.2283 | -1.285 | -1.3441 | -1.4055 | -1.4694 | -1.5356 | -1.6044 | -1.6758 | -1.7496 | -1.826 | -1.905 | -1.9796 | -2.0573 | -2.1379 | -2.2217 | -2.3088 | -2.3993 | -2.4934 | -32.2578
CAPEX | AMR Gas Modules for Maintenance | -44.7673 | 0 | 0 | 0 | -2.4862 | -3.4883 | -3.6707 | -3.8521 | -4.0371 | -4.2297 | -4.4308 | -4.6412 | -4.8603 | -5.0886 | -5.3264 | -5.5738 | -5.8308 | -6.0981 | -6.3755 | -6.663 | -6.9607 | -7.2688 | -7.5612 | -7.8654 | -8.1817 | -8.5108 | -8.671 | -9.0198 | -9.3826 | -123.0012
O&M | AMR Gas Module Exchanges | -14.4338 | 0 | 0 | 0 | -0.86514 | -1.2329 | -1.2532 | -1.2711 | -1.2881 | -1.3482 | -1.411 | -1.4765 | -1.5447 | -1.6157 | -1.6895 | -1.7663 | -1.8459 | -1.9286 | -2.0144 | -2.1032 | -2.195 | -2.2899 | -2.3797 | -2.473 | -2.5699 | -2.6707 | -2.7754 | -2.8842 | -2.9973 | -39.2327
O&M | AMR Gas Module Visits | -6.8174 | 0 | 0 | 0 | -0.31252 | -0.54006 | -0.56774 | -0.59522 | -0.62319 | -0.65227 | -0.68263 | -0.71433 | -0.74733 | -0.78166 | -0.81739 | -0.85453 | -0.89304 | -0.93307 | -0.97456 | -1.0175 | -1.0619 | -1.1079 | -1.1513 | -1.1964 | -1.2433 | -1.2921 | -1.3427 | -1.3954 | -1.4501 | -18.76
O&M | Battery Costs | -9.1037 | 0 | 0 | 0 | -0.89673 | -1.9913 | -1.0815 | -1.1063 | -1.1317 | -0.72014 | -0.73772 | -0.75572 | -0.77416 | -0.79305 | -0.8124 | -0.83222 | -0.85252 | -0.87333 | -0.89464 | -0.91646 | -0.93883 | -0.96173 | -0.9852 | -1.0092 | -1.0339 | -1.0591 | -1.0849 | -1.1114 | -1.1385 | -21.1578
O&M | FTE to Manage Inventory/Testing | -1.6569 | 0 | 0 | 0 | -0.1182 | -0.16075 | -0.16397 | -0.16725 | -0.17059 | -0.17401 | -0.17749 | -0.18104 | -0.18466 | -0.18835 | -0.19212 | -0.19596 | -0.19988 | -0.20388 | -0.20795 | -0.21211 | -0.21635 | -0.22068 | -0.22509 | -0.2296 | -0.23419 | -0.23887 | -0.24365 | -0.24852 | -0.25349 | -4.263
| Total | -278.6441 | 0 | 0 | 0 | -13.3308 | -26.1714 | -26.0747 | -25.982 | -26.5518 | -27.3019 | -28.6118 | -30.0259 | -31.4307 | -32.8371 | -34.135 | -35.2114 | -36.0868 | -37.0889 | -37.931 | -38.7405 | -39.7792 | -41.1749 | -41.9679 | -42.9383 | -44.0778 | -45.4905 | -46.8269 | -48.8661 | -49.4723 | -742.9404
CAPEX | AMI Electric Meter Hardware (Growth) | 145.8937 | 0 | 0 | 0 | 17.2822 | 22.222 | 24.8501 | 23.4797 | 22.91 | 22.6798 | 22.6809 | 22.863 | 23.169 | 20.0758 | 4.1148 | 4.2458 | 4.3661 | 4.5055 | 4.6338 | 4.7602 | 4.8831 | 5.0091 | 6.2965 | 6.5498 | 6.8132 | 7.0873 | 7.3723 | 7.6689 | 7.9773 | 285.4775
CAPEX | AMI Electric Meter Hardware (Maintenance) | 5.6665 | 0 | 0 | 0 | 0.058759 | 0.13555 | 0.22288 | 0.3074 | 0.39175 | 0.47708 | 0.56422 | 0.6538 | 0.7463 | 0.83023 | 0.86166 | 0.89419 | 0.92781 | 0.96262 | 0.99859 | 1.0357 | 1.0741 | 1.1137 | 1.1585 | 1.2051 | 1.2535 | 1.304 | 1.3564 | 1.411 | 1.4677 | 17.1774
CAPEX | AMI Electric Meter Exchange (Growth) | 32.2648 | 0 | 0 | 0 | 3.3875 | 4.8961 | 5.6497 | 5.1033 | 4.8163 | 4.6367 | 4.5289 | 4.4759 | 4.4593 | 3.9743 | 1.3279 | 1.3689 | 1.4063 | 1.4497 | 1.4895 | 1.5287 | 1.5666 | 1.6055 | 2.0161 | 2.0952 | 2.1773 | 2.2627 | 2.3514 | 2.4436 | 2.5394 | 66.2226
O&M | AMI Electric Meter Exchange (Maintenance) | 1.8259 | 0 | 0 | 0 | 0.019149 | 0.044131 | 0.072495 | 0.099885 | 0.12717 | 0.15472 | 0.1828 | 0.21161 | 0.24132 | 0.26819 | 0.27807 | 0.28829 | 0.29884 | 0.30974 | 0.321 | 0.33262 | 0.3446 | 0.35695 | 0.37094 | 0.38548 | 0.4006 | 0.4163 | 0.43262 | 0.44958 | 0.46721 | 5.5249
CAPEX | AMI Gas Meter/Module Hardware (Growth) | 75.5298 | 0 | 0 | 0 | 3.3643 | 7.3042 | 7.6799 | 7.3436 | 7.3231 | 7.5877 | 7.9079 | 8.2529 | 8.5651 | 8.881 | 9.2146 | 9.5453 | 9.8455 | 10.1984 | 10.5088 | 10.8117 | 11.1047 | 11.3992 | 9.8341 | 10.2297 | 10.6412 | 11.0692 | 11.5144 | 11.9775 | 12.4593 | 198.6121
CAPEX | AMI Gas Meter/Module Hardware (Maintenance) | 18.2722 | 0 | 0 | 0 | 0.34375 | 0.68811 | 0.89776 | 1.1215 | 1.3597 | 1.6132 | 1.8826 | 2.169 | 2.3261 | 2.4353 | 2.5491 | 2.6676 | 2.7905 | 2.9185 | 3.0512 | 3.1888 | 3.3313 | 3.4788 | 3.6187 | 3.7643 | 3.9157 | 4.0732 | 4.237 | 4.4074 | 4.5847 | 54.1846
CAPEX | AMI Gas Meter Exchange (Growth) | 41.6794 | 0 | 0 | 0 | 1.8732 | 4.0629 | 4.2677 | 4.0769 | 4.0615 | 4.2041 | 4.3773 | 4.5637 | 4.7318 | 4.9015 | 5.0806 | 5.2578 | 5.4179 | 5.6065 | 5.7715 | 5.9321 | 6.0869 | 6.2421 | 5.3799 | 5.5908 | 5.81 | 6.0377 | 6.2744 | 6.5204 | 6.776 | 109.3344
O&M | AMI Gas Meter Exchange (Maintenance) | 10.0632 | 0 | 0 | 0 | 0.1914 | 0.38276 | 0.49889 | 0.62259 | 0.7541 | 0.89381 | 1.0421 | 1.1994 | 1.285 | 1.3441 | 1.4055 | 1.4694 | 1.5356 | 1.6044 | 1.6758 | 1.7496 | 1.826 | 1.905 | 1.9796 | 2.0573 | 2.1379 | 2.2217 | 2.3088 | 2.3993 | 2.4934 | 29.7819
CAPEX | New AMI Gas Modules (Deployments) | 47.0768 | 0 | 0 | 0 | 13.3903 | 12.9177 | 6.4244 | 6.9606 | 7.4088 | 7.7881 | 8.171 | 8.5681 | 2.3956 | 0 | 0 | 0 | 0 | 0 | -1.3328e-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74.0245
CAPEX | New AMI Gas Module Exchanges (Deployments) | 11.3149 | 0 | 0 | 0 | 2.4145 | 2.6267 | 1.7964 | 1.9389 | 2.0567 | 2.1554 | 2.2583 | 2.3657 | 0.6624 | 0.0022727 | 0 | 0 | 0 | 0 | -1.8622e-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.2773
O&M | AMI Gas Module Visits | 0.58524 | 0 | 0 | 0 | 0.011131 | 0.02226 | 0.029014 | 0.036207 | 0.043856 | 0.05198 | 0.060605 | 0.069754 | 0.074733 | 0.078166 | 0.081739 | 0.085453 | 0.089304 | 0.093307 | 0.097456 | 0.10175 | 0.10619 | 0.11079 | 0.11513 | 0.11964 | 0.12433 | 0.12921 | 0.13427 | 0.13954 | 0.14501 | 1.732
CAPEX | AMI Gas Modules (Maintenance) | 2.7916 | 0 | 0 | 0 | 0.052517 | 0.10513 | 0.13716 | 0.17133 | 0.20773 | 0.24645 | 0.28763 | 0.33137 | 0.35537 | 0.37206 | 0.38945 | 0.40754 | 0.42633 | 0.44588 | 0.46616 | 0.48718 | 0.50895 | 0.53148 | 0.55286 | 0.57509 | 0.59822 | 0.62229 | 0.64732 | 0.67335 | 0.70044 | 8.2782
O&M | AMI Gas Modude Exchanges (Maintenance) | 0.78227 | 0 | 0 | 0 | 0.014878 | 0.029754 | 0.038781 | 0.048397 | 0.05862 | 0.06948 | 0.081008 | 0.093238 | 0.099893 | 0.10448 | 0.10926 | 0.11422 | 0.11937 | 0.12472 | 0.13027 | 0.13601 | 0.14194 | 0.14808 | 0.15389 | 0.15992 | 0.16619 | 0.17271 | 0.17948 | 0.18651 | 0.19383 | 2.3151
O&M | FTE to Manage Inventory/Testing | 1.6884 | 0 | 0 | 0 | 0.1576 | 0.16075 | 0.16397 | 0.16725 | 0.17059 | 0.17401 | 0.17749 | 0.18104 | 0.18466 | 0.18835 | 0.19212 | 0.19596 | 0.19988 | 0.20388 | 0.20795 | 0.21211 | 0.21635 | 0.22068 | 0.22509 | 0.2296 | 0.23419 | 0.23887 | 0.24365 | 0.24852 | 0.25349 | 4.3024
0 | Total | 395.4346 | 0 | 0 | 0 | 42.5611 | 55.5979 | 52.7291 | 51.4774 | 51.6901 | 52.7325 | 54.2028 | 55.9985 | 49.2966 | 43.4558 | 25.6049 | 26.5403 | 27.4234 | 28.4232 | 29.3521 | 30.2765 | 31.1908 | 32.1213 | 31.7014 | 32.9617 | 34.2723 | 35.6351 | 37.0521 | 38.5256 | 40.0579 | 875.2449
| Total Gas | -13.5527 | 0 | 0 | 0 | 10.8007 | 7.2386 | 0.84939 | 1.532 | 2.1326 | 3.0616 | 3.5809 | 4.1292 | -3.954 | -7.3224 | -7.6498 | -7.9884 | -8.341 | -8.7061 | -9.0864 | -9.4808 | -9.8896 | -10.3126 | -10.7805 | -11.1952 | -11.6261 | -12.0738 | -12.2693 | -12.7417 | -13.2326 | -95.0816
| Gas Capital | 17.094 | 0 | 0 | 0 | 13.1951 | 11.4967 | 4.1614 | 4.821 | 5.3906 | 5.8886 | 6.4023 | 6.9417 | -1.0624 | -4.3146 | -4.5215 | -4.735 | -4.9583 | -5.1891 | -5.4305 | -5.6815 | -5.942 | -6.212 | -6.5333 | -6.7961 | -7.0695 | -7.3538 | -7.38 | -7.6768 | -7.9856 | -17.5024
| Gas O&M | -30.6467 | 0 | 0 | 0 | -2.3944 | -4.2581 | -3.312 | -3.2889 | -3.258 | -2.827 | -2.8214 | -2.8124 | -2.8916 | -3.0077 | -3.1283 | -3.2534 | -3.3828 | -3.517 | -3.6559 | -3.7994 | -3.9476 | -4.1006 | -4.2472 | -4.3991 | -4.5566 | -4.7199 | -4.8893 | -5.0649 | -5.247 | -77.5792

## Managed Service (R)
0.1-Managed Service
| ($Millions) |  | NPV | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
| Year |  |  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
COSTS
|  | Contract Costs | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
|  | Incrimental Costs | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
|  | Total Status Quo Metering Costs | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
|  | O&M Status Quo | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
|  | CAPEX Status Quo | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
|  | O&M Managed Service | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
|  | Total Status Quo Meter+Other Costs) | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
|  | Total Managed Service Costs | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX

## Status Quo (R)
0-Status Quo
| ($Millions) |  |  | NPV | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
| Year |  |  |  | -1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
| COSTS | CAPEX VS O&M
|  |  | Year of Deployment |  | -1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
| L+G Managed Service Contract | O&M | L+G Managed Service Contract | XXXXXX | 28.2147 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
|  | CAPEX | AMR Electric Meter Hardware (Growth) | 29.9595 | -1.5776 | 0.6574 | 1.2489 | 2.4822 | 2.842 | 2.73 | 2.5749 | 2.5463 | 2.6173 | 2.7051 | 2.8021 | 2.8904 | 2.9817 | 3.0791 | 3.1772 | 3.2672 | 3.3715 | 3.4675 | 3.5621 | 3.6541 | 3.7483 | 4.7117 | 4.9012 | 5.0984 | 5.3034 | 5.4033 | 5.6206 | 5.8467 | 74.8424
|  | CAPEX | AMR Electric Meter Hardware (Maintenance) | 12.0774 | 0.2256 | 0.30188 | 0.31488 | 0.59896 | 0.71865 | 0.74829 | 0.93005 | 1.108 | 1.2751 | 1.4448 | 1.6381 | 1.8551 | 2.0525 | 2.135 | 2.0504 | 1.8511 | 1.6546 | 1.3839 | 1.0844 | 0.9425 | 1.0308 | 1.8211 | 1.4154 | 1.0851 | 0.90124 | 0.88045 | 1.0507 | 0.17244 | 30.5673
|  | CAPEX | AMR Electric Meter Exchange (Growth) | 13.8817 | -1.4443 | 0.60126 | 1.1411 | 1.2436 | 1.2365 | 1.1866 | 1.1181 | 1.1046 | 1.1343 | 1.1712 | 1.212 | 1.249 | 1.2872 | 1.3279 | 1.3689 | 1.4063 | 1.4497 | 1.4895 | 1.5287 | 1.5666 | 1.6055 | 2.0161 | 2.0952 | 2.1773 | 2.2627 | 2.3514 | 2.4436 | 2.5394 | 32.5357
|  | O&M | AMR Electric Meter Exchange (Maintenance) | 5.5129 | 0.20653 | 0.2761 | 0.2877 | 0.30008 | 0.31268 | 0.32525 | 0.40386 | 0.48067 | 0.5526 | 0.62555 | 0.70854 | 0.8016 | 0.88603 | 0.92074 | 0.8834 | 0.79676 | 0.71146 | 0.5945 | 0.46536 | 0.40409 | 0.44153 | 0.77923 | 0.60507 | 0.46339 | 0.38451 | 0.38315 | 0.4568 | 0.074895 | 13.6172
|  | CAPEX | AMR Gas Meter Hardware (Growth) | 81.1219 | -2.8151 | 2.6901 | 4.1151 | 6.0364 | 7.0462 | 7.4087 | 7.0843 | 7.0646 | 7.3198 | 7.6287 | 7.9615 | 8.2627 | 8.5674 | 8.8893 | 9.2082 | 9.4979 | 9.8383 | 10.1378 | 10.4299 | 10.7126 | 10.9967 | 9.4869 | 9.8685 | 10.2654 | 10.6783 | 11.0438 | 11.488 | 11.9501 | 198.3799
|  | CAPEX | AMR Gas Meter Hardware (Maintenance) | 22.7272 | 0.96052 | 0.99899 | 1.0479 | 1.4233 | 1.6105 | 1.6947 | 1.7785 | 1.8639 | 1.9528 | 2.0457 | 2.1428 | 2.2439 | 2.3493 | 2.4591 | 2.5734 | 2.692 | 2.8154 | 2.9435 | 3.0762 | 3.2137 | 3.3559 | 3.4909 | 3.6313 | 3.7774 | 3.9293 | 4.0638 | 4.2273 | 4.3973 | 60.0711
|  | CAPEX | AMR Gas Meter Exchange (Growth) | 48.0249 | -2.2638 | 2.1611 | 3.3027 | 3.7464 | 4.0629 | 4.2677 | 4.0769 | 4.0615 | 4.2041 | 4.3773 | 4.5637 | 4.7318 | 4.9015 | 5.0806 | 5.2578 | 5.4179 | 5.6065 | 5.7715 | 5.9321 | 6.0869 | 6.2421 | 5.3799 | 5.5908 | 5.81 | 6.0377 | 6.2744 | 6.5204 | 6.776 | 114.4076
|  | O&M | AMR Gas Meter Exchange (Maintenance) | 13.4678 | 0.7724 | 0.80254 | 0.84105 | 0.88335 | 0.92864 | 0.97624 | 1.0235 | 1.0716 | 1.1216 | 1.1738 | 1.2283 | 1.285 | 1.3441 | 1.4055 | 1.4694 | 1.5356 | 1.6044 | 1.6758 | 1.7496 | 1.826 | 1.905 | 1.9796 | 2.0573 | 2.1379 | 2.2217 | 2.3088 | 2.3993 | 2.4934 | 35.0198
|  | O&M | Credit Disconnects/Reconnects | 0 | [28 empty] | 0
|  | O&M | Battery Costs | 11.1086 | 0.28415 | 0.44381 | 1.0183 | 1.7935 | 1.9913 | 1.0815 | 1.1063 | 1.1317 | 0.72014 | 0.73772 | 0.75572 | 0.77416 | 0.79305 | 0.8124 | 0.83222 | 0.85252 | 0.87333 | 0.89464 | 0.91646 | 0.93883 | 0.96173 | 0.9852 | 1.0092 | 1.0339 | 1.0591 | 1.0849 | 1.1114 | 1.1385 | 23.8008
|  | CAPEX | Gas Modules for Maintenance | 44.7673 | 0 | 0 | 0 | 2.4862 | 3.4883 | 3.6707 | 3.8521 | 4.0371 | 4.2297 | 4.4308 | 4.6412 | 4.8603 | 5.0886 | 5.3264 | 5.5738 | 5.8308 | 6.0981 | 6.3755 | 6.663 | 6.9607 | 7.2688 | 7.5612 | 7.8654 | 8.1817 | 8.5108 | 8.671 | 9.0198 | 9.3826 | 123.0012
|  | O&M | Gas Module Exchanges | 15.0975 | 0.31807 | 0.31553 | 0.31574 | 0.98916 | 1.2329 | 1.2532 | 1.2711 | 1.2881 | 1.3482 | 1.411 | 1.4765 | 1.5447 | 1.6157 | 1.6895 | 1.7663 | 1.8459 | 1.9286 | 2.0144 | 2.1032 | 2.195 | 2.2899 | 2.3797 | 2.473 | 2.5699 | 2.6707 | 2.7754 | 2.8842 | 2.9973 | 40.306
|  | O&M | Gas Module Visits | 7.8942 | 0.51603 | 0.51191 | 0.51224 | 0.51372 | 0.54006 | 0.56774 | 0.59522 | 0.62319 | 0.65227 | 0.68263 | 0.71433 | 0.74733 | 0.78166 | 0.81739 | 0.85453 | 0.89304 | 0.93307 | 0.97456 | 1.0175 | 1.0619 | 1.1079 | 1.1513 | 1.1964 | 1.2433 | 1.2921 | 1.3427 | 1.3954 | 1.4501 | 20.5013
|  | O&M | FTE to Manage Inventory/Testing | 1.6569 | 0 | 0 | 0 | 0.1182 | 0.16075 | 0.16397 | 0.16725 | 0.17059 | 0.17401 | 0.17749 | 0.18104 | 0.18466 | 0.18835 | 0.19212 | 0.19596 | 0.19988 | 0.20388 | 0.20795 | 0.21211 | 0.21635 | 0.22068 | 0.22509 | 0.2296 | 0.23419 | 0.23887 | 0.24365 | 0.24852 | 0.25349 | 4.263
| AMR Meter Costs |  |  | 307.2978 | -4.8175 | 9.7606 | 14.1456 | 22.615 | 26.1714 | 26.0747 | 25.982 | 26.5518 | 27.3019 | 28.6118 | 30.0259 | 31.4307 | 32.8371 | 34.135 | 35.2114 | 36.0868 | 37.0889 | 37.931 | 38.7405 | 39.7792 | 41.1749 | 41.9679 | 42.9383 | 44.0778 | 45.4905 | 46.8269 | 48.8661 | 49.4723 | 771.3134
|  | CAPEX | AMR Network growth (CM & MCC) | 6.5287 | 0 | 0 | 0 | 0.35226 | 0.5124 | 0.53624 | 0.56119 | 0.5873 | 0.61462 | 0.64321 | 0.67314 | 0.70446 | 0.73723 | 0.77153 | 0.80743 | 0.84499 | 0.88431 | 0.92545 | 0.96851 | 1.0136 | 1.0607 | 1.1101 | 1.1617 | 1.2158 | 1.2723 | 1.3315 | 1.3935 | 1.4583 | 17.9584
|  | CAPEX | AMR Network growth (CM&MCC Labor) | 2.4805 | 0 | 0 | 0 | 0.14061 | 0.19602 | 0.20493 | 0.21426 | 0.22401 | 0.2342 | 0.24486 | 0.256 | 0.26765 | 0.27982 | 0.29256 | 0.30587 | 0.31978 | 0.33433 | 0.34955 | 0.36545 | 0.38208 | 0.39946 | 0.41764 | 0.43664 | 0.45651 | 0.47728 | 0.49899 | 0.5217 | 0.54544 | 6.7995
|  | CAPEX | AMR Network maintenance (CM &MCC) | 3.5777 | 0 | 0 | 0 | 0.19304 | 0.28079 | 0.29386 | 0.30753 | 0.32184 | 0.33681 | 0.35248 | 0.36888 | 0.38604 | 0.404 | 0.4228 | 0.44247 | 0.46305 | 0.4846 | 0.50714 | 0.53074 | 0.55543 | 0.58127 | 0.60831 | 0.63662 | 0.66623 | 0.69723 | 0.72967 | 0.76362 | 0.79915 | 9.8411
|  | O&M | AMR Network maintenance (CM& MCC Labor) | 14.4423 | 0 | 0 | 0 | 0.75367 | 1.0614 | 1.1207 | 1.1828 | 1.2481 | 1.3165 | 1.3883 | 1.4636 | 1.5426 | 1.6254 | 1.7122 | 1.8032 | 1.8987 | 1.9987 | 2.1036 | 2.2135 | 2.3287 | 2.4495 | 2.576 | 2.7086 | 2.8475 | 2.9931 | 3.1456 | 3.3053 | 3.4727 | 40.3363
|  | O&M | Network Overhead and management | 2.4854 | 0 | 0 | 0 | 0.1773 | 0.24113 | 0.24595 | 0.25087 | 0.25589 | 0.26101 | 0.26623 | 0.27155 | 0.27698 | 0.28252 | 0.28817 | 0.29394 | 0.29982 | 0.30581 | 0.31193 | 0.31817 | 0.32453 | 0.33102 | 0.33764 | 0.34439 | 0.35128 | 0.35831 | 0.36547 | 0.37278 | 0.38024 | 6.3945
|  | O&M | Manual Meter Reading | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Network Costs |  |  | 29.5145 | 0 | 0 | 0 | 1.6169 | 2.2917 | 2.4016 | 2.5167 | 2.6371 | 2.7632 | 2.8951 | 3.0332 | 3.1777 | 3.329 | 3.4873 | 3.6529 | 3.8263 | 4.0078 | 4.1977 | 4.3964 | 4.6043 | 4.8219 | 5.0497 | 5.2879 | 5.5373 | 5.7982 | 6.0712 | 6.3569 | 6.6558 | 81.3299
|  | O&M | Backhaul Costs (Licences and Data) | 4.1985 | 0 | 0 | 0 | 0.32807 | 0.43388 | 0.40885 | 0.41727 | 0.42587 | 0.43464 | 0.44359 | 0.45273 | 0.46206 | 0.47158 | 0.48129 | 0.49121 | 0.50133 | 0.51166 | 0.5222 | 0.53296 | 0.54394 | 0.55515 | 0.56659 | 0.57826 | 0.59017 | 0.60233 | 0.60711 | 0.61962 | 0.63238 | 10.7556
|  | O&M | Poll Attachment Costs | 5.1929 | -0.13473 | -0.13756 | -0.14045 | 0.45163 | 0.50815 | 0.52005 | 0.53223 | 0.5447 | 0.55746 | 0.57052 | 0.58389 | 0.59758 | 0.61159 | 0.62593 | 0.6406 | 0.65563 | 0.671 | 0.68674 | 0.70286 | 0.71935 | 0.73623 | 0.75351 | 0.7712 | 0.7893 | 0.80783 | 0.8268 | 0.8451 | 0.86496 | 13.6253
|  | O&M | Customer Service and Other Overhead | 40.753 | 3.1649 | 3.2191 | 3.2744 | 3.3307 | 3.3882 | 3.4469 | 3.5067 | 3.5677 | 3.63 | 3.6935 | 3.7582 | 3.8243 | 3.8916 | 3.9604 | 4.0305 | 4.102 | 4.1749 | 4.2493 | 4.3251 | 4.4025 | 4.4815 | 4.562 | 4.6441 | 4.7279 | 4.8133 | 4.9005 | 4.9894 | 5.08 | 98.1696
|  | O&M | Field Work Reimbursements | -11.3783 | -0.95763 | -0.8978 | -0.86471 | -0.89945 | -0.90169 | -0.92369 | -0.94623 | -0.96932 | -0.99297 | -1.0172 | -1.042 | -1.0674 | -1.0935 | -1.1202 | -1.1475 | -1.1755 | -1.2042 | -1.2336 | -1.2637 | -1.2945 | -1.3261 | -1.3584 | -1.3916 | -1.4255 | -1.4603 | -1.4603 | -1.496 | -1.5325 | -27.9746
| Telecom and Other Costs |  |  | 38.7662 | 2.0725 | 2.1837 | 2.2692 | 3.211 | 3.4286 | 3.4521 | 3.51 | 3.569 | 3.6291 | 3.6904 | 3.7528 | 3.8165 | 3.8813 | 3.9474 | 4.0148 | 4.0834 | 4.1534 | 4.2246 | 4.2973 | 4.3713 | 4.4468 | 4.5236 | 4.602 | 4.6818 | 4.7632 | 4.8741 | 4.9581 | 5.0449 | 94.5758
|  |  | Total | 613.0458 | 25.4697 | 42.973 | 48.7802 | 45.4328 | 45.8781 | 45.9148 | 46.6068 | 48.0646 | 49.7521 | 52.0512 | 54.5012 | 56.9911 | 59.5339 | 62.0223 | 64.3455 | 66.527 | 68.8974 | 71.1729 | 73.4841 | 76.096 | 79.1401 | 81.6602 | 84.4403 | 87.476 | 90.8756 | 94.3222 | 98.543 | 101.4365 | 1528.0871
|  |  | Costs (real) | 613.0458 | 27.4487 | 39.8747 | 41.9998 | 36.2974 | 34.0106 | 31.5838 | 29.7483 | 28.4669 | 27.3419 | 26.543 | 25.7886 | 25.0225 | 24.2544 | 23.4463 | 22.5708 | 21.6536 | 20.8083 | 19.9458 | 19.1087 | 18.3613 | 17.719 | 16.965 | 16.2778 | 15.6472 | 15.0834 | 14.5267 | 14.0825 | 13.4509 | 625.9678
| O&M Costs |  | O&M Costs | 110.4318 | 4.1697 | 4.5336 | 5.2442 | 8.7399 | 9.8974 | 9.1866 | 9.5109 | 9.8388 | 9.7755 | 10.1531 | 10.5524 | 10.9735 | 11.3981 | 11.7855 | 12.1137 | 12.4056 | 12.7127 | 13.002 | 13.2932 | 13.6668 | 14.1539 | 14.9374 | 15.2255 | 15.5632 | 15.9815 | 16.5238 | 17.1319 | 17.3055 | 278.8147
| CAPEX |  | CAPEX | 265.1467 | -6.9147 | 7.4107 | 11.1706 | 18.703 | 21.9943 | 22.7418 | 22.4978 | 22.9191 | 23.9187 | 25.0442 | 26.2594 | 27.4513 | 28.6493 | 29.7843 | 30.7654 | 31.5909 | 32.5374 | 33.3513 | 34.141 | 35.0881 | 36.2897 | 36.6038 | 37.6027 | 38.7337 | 40.0704 | 41.2484 | 43.0493 | 43.8675 | 668.4044
| L&G O&M |  | L&G O&M | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
BENEFITS
Network
|  |  | Total | -613.0458 | -25.4697 | -42.973 | -48.7802 | -45.4328 | -45.8781 | -45.9148 | -46.6068 | -48.0646 | -49.7521 | -52.0512 | -54.5012 | -56.9911 | -59.5339 | -62.0223 | -64.3455 | -66.527 | -68.8974 | -71.1729 | -73.4841 | -76.096 | -79.1401 | -81.6602 | -84.4403 | -87.476 | -90.8756 | -94.3222 | -98.543 | -101.4365 | -1528.0871
0
| Net Benefits |  | Net Benefits | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Net Benefits (real) |  | Net Benefits (real) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Cumulative Net Benefits |  | Cumulative Net Benefits |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CORP MODEL INPUTS (AMI & Metering Only)
| Total O&M |  |  | 347.8991 | 32.3844 | 35.5622 | 37.6096 | 26.7298 | 23.8838 | 23.173 | 24.109 | 25.1454 | 25.8334 | 27.007 | 28.2418 | 29.5398 | 30.8846 | 32.238 | 33.5801 | 34.9361 | 36.3601 | 37.8215 | 39.3431 | 41.0079 | 42.8504 | 45.0564 | 46.8375 | 48.7423 | 50.8053 | 53.0738 | 55.4937 | 57.569 | 859.6827
| Meter Capital |  |  | 252.5599 | -6.9147 | 7.4107 | 11.1706 | 18.0171 | 21.0051 | 21.7068 | 21.4148 | 21.786 | 22.7331 | 23.8037 | 24.9614 | 26.0932 | 27.2282 | 28.2974 | 29.2096 | 29.9631 | 30.8341 | 31.5692 | 32.2763 | 33.137 | 34.2482 | 34.4678 | 35.3677 | 36.3952 | 37.6235 | 38.6882 | 40.3705 | 41.0646 | 633.8053
| Network |  |  | 12.5868 | 0 | 0 | 0 | 0.68592 | 0.98921 | 1.035 | 1.083 | 1.1331 | 1.1856 | 1.2405 | 1.298 | 1.3581 | 1.4211 | 1.4869 | 1.5558 | 1.6278 | 1.7032 | 1.7821 | 1.8647 | 1.9511 | 2.0415 | 2.136 | 2.235 | 2.3385 | 2.4468 | 2.5602 | 2.6788 | 2.8029 | 34.5991
AMI Applications
Disconnect/Reconnect
|  | CAPEX | CIS Remote Disconnect and Prepay Enablement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | O&M | Management Costs (Annual) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Revenue | Credit Write offs from Electric Only Service Areas (Revenue) | 149.9801 | 11.2392 | 11.4753 | 11.7162 | 11.9623 | 12.2135 | 12.47 | 12.7318 | 12.9992 | 13.2722 | 13.5509 | 13.8355 | 14.126 | 14.4227 | 14.7255 | 15.0348 | 15.3505 | 15.6729 | 16.002 | 16.338 | 16.6811 | 17.0314 | 17.3891 | 17.7543 | 18.1271 | 18.5078 | 18.8964 | 19.2933 | 19.6984 | 364.6293
|  | Revenue | UEU Electric Write Offs (Revenue)$ | 43.9736 | 3.2953 | 3.3645 | 3.4352 | 3.5073 | 3.581 | 3.6562 | 3.7329 | 3.8113 | 3.8914 | 3.9731 | 4.0565 | 4.1417 | 4.2287 | 4.3175 | 4.4081 | 4.5007 | 4.5952 | 4.6917 | 4.7903 | 4.8909 | 4.9936 | 5.0984 | 5.2055 | 5.3148 | 5.4264 | 5.5404 | 5.6567 | 5.7755 | 106.908
|  | O&M | UEU Labor & Overhead (O&M) | 3.5606 | 0.26682 | 0.27243 | 0.27815 | 0.28399 | 0.28995 | 0.29604 | 0.30226 | 0.30861 | 0.31509 | 0.3217 | 0.32846 | 0.33536 | 0.3424 | 0.34959 | 0.35693 | 0.36443 | 0.37208 | 0.37989 | 0.38787 | 0.39602 | 0.40433 | 0.41282 | 0.42149 | 0.43035 | 0.43938 | 0.44861 | 0.45803 | 0.46765 | 8.6564
| Disconnect/Reconnect Total |  | Total | 197.5143 | 14.8014 | 15.1122 | 15.4295 | 15.7536 | 16.0844 | 16.4222 | 16.767 | 17.1191 | 17.4786 | 17.8457 | 18.2204 | 18.6031 | 18.9937 | 19.3926 | 19.7999 | 20.2156 | 20.6402 | 21.0736 | 21.5162 | 21.968 | 22.4293 | 22.9004 | 23.3813 | 23.8723 | 24.3736 | 24.8854 | 25.408 | 25.9416 | 480.1938
CVR
|  | CAPEX | Upgrade Costs | 8.2304 | 0.25707 | 0.52699 | 0.54017 | 0.55367 | 0.56751 | 0.5817 | 0.79499 | 0.91673 | 0.93964 | 0.96314 | 0.98721 | 1.0119 | 1.0372 | 1.0631 | 1.0897 | 1.1169 | 1.1449 | 1.1735 | 1.2028 | 1.2329 | 0.84248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.5442
|  | O&M | Management Costs | 18.7605 | 0.195 | 0.29213 | 0.39398 | 0.50075 | 0.61262 | 0.72976 | 0.88717 | 1.0698 | 1.261 | 1.4612 | 1.6705 | 1.8894 | 2.1182 | 2.3573 | 2.6069 | 2.8676 | 3.1397 | 3.4236 | 3.7198 | 4.0286 | 4.2768 | 4.3837 | 4.4933 | 4.6056 | 4.7208 | 4.8388 | 4.9598 | 5.0838 | 57.7053
| CVR LDC Costs |  | Total | 26.9909 | 0.45207 | 0.81912 | 0.93415 | 1.0544 | 1.1801 | 1.3115 | 1.6822 | 1.9865 | 2.2007 | 2.4243 | 2.6577 | 2.9013 | 3.1554 | 3.4204 | 3.6966 | 3.9846 | 4.2846 | 4.5971 | 4.9226 | 5.2615 | 5.1193 | 4.3837 | 4.4933 | 4.6056 | 4.7208 | 4.8388 | 4.9598 | 5.0838 | 76.2496
|  | O&M | Annual Peak Savings EOL ($) | -27.3896 | 0 | -0.082922 | -0.25498 | -0.4356 | -0.62508 | -0.82377 | -1.032 | -1.3142 | -1.6428 | -1.987 | -2.3473 | -2.7244 | -3.119 | -3.5315 | -3.9627 | -4.4133 | -4.8839 | -5.3753 | -5.8882 | -6.4234 | -6.9817 | -7.428 | -7.6137 | -7.804 | -7.9991 | -8.1991 | -8.404 | -8.6141 | -88.6937
|  | O&M | Annual Energy Savings EOL($) | -47.2915 | 0 | -0.12012 | -0.37645 | -0.64706 | -0.96183 | -1.3203 | -1.6861 | -2.1996 | -2.6373 | -3.3043 | -4.14 | -4.7248 | -4.8911 | -5.6929 | -6.5355 | -7.1981 | -8.4136 | -9.5442 | -10.8143 | -12.1325 | -13.008 | -13.6501 | -13.7982 | -13.9463 | -14.0944 | -14.2424 | -14.3905 | -14.5386 | -155.8367
| CVR LDC Benefits |  | Total | -74.6811 | 0 | -0.20304 | -0.63144 | -1.0827 | -1.5869 | -2.144 | -2.7181 | -3.5138 | -4.2801 | -5.2913 | -6.4873 | -7.4492 | -8.01 | -9.2244 | -10.4982 | -11.6113 | -13.2975 | -14.9195 | -16.7025 | -18.5559 | -19.9896 | -21.078 | -21.4118 | -21.7502 | -22.0934 | -22.4415 | -22.7946 | -23.1528 | -244.5304
Outage
|  | O&M | Automated analysis of system status including outage device prediction | 61.3399 | 4.5967 | 4.6932 | 4.7918 | 4.8924 | 4.9952 | 5.1001 | 5.2072 | 5.3165 | 5.4281 | 5.5421 | 5.6585 | 5.7774 | 5.8987 | 6.0226 | 6.149 | 6.2782 | 6.41 | 6.5446 | 6.682 | 6.8224 | 6.9656 | 7.1119 | 7.2613 | 7.4137 | 7.5694 | 7.7284 | 7.8907 | 8.0564 | 149.1286
|  | O&M | Electric First Response (EFR) Investigations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | O&M | Storm Response Costs | 162.3946 | 12.1696 | 12.4251 | 12.686 | 12.9524 | 13.2245 | 13.5022 | 13.7857 | 14.0752 | 14.3708 | 14.6726 | 14.9807 | 15.2953 | 15.6165 | 15.9444 | 16.2793 | 16.6211 | 16.9702 | 17.3266 | 17.6904 | 18.0619 | 18.4412 | 18.8285 | 19.2239 | 19.6276 | 20.0398 | 20.4606 | 20.8903 | 21.329 | 394.8114
|  | O&M | Non-storm response Costs | 44.1302 | 3.307 | 3.3765 | 3.4474 | 3.5198 | 3.5937 | 3.6692 | 3.7462 | 3.8249 | 3.9052 | 3.9872 | 4.071 | 4.1564 | 4.2437 | 4.3328 | 4.4238 | 4.5167 | 4.6116 | 4.7084 | 4.8073 | 4.9083 | 5.0113 | 5.1166 | 5.224 | 5.3337 | 5.4457 | 5.5601 | 5.6769 | 5.7961 | 107.2886
|  | O&M | SAIDI Fines | 8.7895 | 0.65867 | 0.6725 | 0.68663 | 0.70105 | 0.71577 | 0.7308 | 0.74615 | 0.76181 | 0.77781 | 0.79415 | 0.81082 | 0.82785 | 0.84524 | 0.86299 | 0.88111 | 0.89961 | 0.9185 | 0.93779 | 0.95749 | 0.97759 | 0.99812 | 1.0191 | 1.0405 | 1.0623 | 1.0846 | 1.1074 | 1.1307 | 1.1544 | 21.369
| Outage Total |  | Total | 276.6542 | 20.732 | 21.1673 | 21.6118 | 22.0657 | 22.5291 | 23.0022 | 23.4852 | 23.9784 | 24.482 | 24.9961 | 25.521 | 26.0569 | 26.6041 | 27.1628 | 27.7332 | 28.3156 | 28.9103 | 29.5174 | 30.1373 | 30.7701 | 31.4163 | 32.0761 | 32.7496 | 33.4374 | 34.1396 | 34.8565 | 35.5885 | 36.3359 | 672.5976
| Total AMR Application Costs |  | Total | 426.4782 | 35.9854 | 36.8956 | 37.3441 | 37.791 | 38.2067 | 38.5918 | 39.2163 | 39.5702 | 39.8812 | 39.9748 | 39.9119 | 40.1121 | 40.7433 | 40.7514 | 40.7315 | 40.9045 | 40.5375 | 40.2687 | 39.8735 | 39.4438 | 38.9753 | 38.2821 | 39.2124 | 40.165 | 41.1405 | 42.1392 | 43.1617 | 44.2084 | 984.5105
| Status Quo Costs |  |  | 1039.524 | 61.4551 | 79.8686 | 86.1243 | 83.2238 | 84.0848 | 84.5066 | 85.8231 | 87.6348 | 89.6333 | 92.026 | 94.4131 | 97.1032 | 100.2772 | 102.7737 | 105.077 | 107.4315 | 109.4349 | 111.4416 | 113.3576 | 115.5398 | 118.1154 | 119.9423 | 123.6527 | 127.641 | 132.0161 | 136.4614 | 141.7046 | 145.6449 | 2512.5976
CORP MODEL INPUTS (AMI Metering AND Applications)
| Total O&M |  | Total O&M | 766.147 | 68.1127 | 71.9308 | 74.4135 | 63.9672 | 61.523 | 61.1831 | 62.5303 | 63.7989 | 64.775 | 66.0186 | 67.1665 | 68.64 | 70.5907 | 71.9263 | 73.2219 | 74.7237 | 75.7527 | 76.9167 | 78.0138 | 79.2188 | 80.9832 | 83.3385 | 86.0499 | 88.9073 | 91.9457 | 95.213 | 98.6554 | 101.7774 | 1825.649
| Meter Capital |  | Meter Capital | 252.5599 | -6.9147 | 7.4107 | 11.1706 | 18.0171 | 21.0051 | 21.7068 | 21.4148 | 21.786 | 22.7331 | 23.8037 | 24.9614 | 26.0932 | 27.2282 | 28.2974 | 29.2096 | 29.9631 | 30.8341 | 31.5692 | 32.2763 | 33.137 | 34.2482 | 34.4678 | 35.3677 | 36.3952 | 37.6235 | 38.6882 | 40.3705 | 41.0646 | 633.8053
| Network/Substation Capital |  | Network | 20.8172 | 0.25707 | 0.52699 | 0.54017 | 1.2396 | 1.5567 | 1.6167 | 1.878 | 2.0499 | 2.1253 | 2.2037 | 2.2852 | 2.37 | 2.4582 | 2.55 | 2.6455 | 2.7448 | 2.8481 | 2.9556 | 3.0675 | 3.184 | 2.8839 | 2.136 | 2.235 | 2.3385 | 2.4468 | 2.5602 | 2.6788 | 2.8029 | 53.1433
1039.524
Note on B34: vdrehe: Gas module maintenance is only on AMI module population because any AMR module requiring maintenance will be replaced with and AMI module.
Note on B51: vdrehe: "Investment Costs" include up front costs such as termination fees, network deployment, IP and MDM development costs as well as meter hardware costs (if any in the given scenario).
Note on C18: vdrehe: Includes meters and meter exchange costs. All meter/exchanges for AMR will be conversions to AMI.
Note on C20: vdrehe: Network Hardware will continue to grow at the AMI network growth rate despite a larger initial deployment because an increasing AMI mesh will limit the need for new network hardware.
Note on C22: vdrehe: This equation = (%Cellmaster unscheduled visits*#of Cellmasters*cost of unscheduled visits)+(scheduled Cellmaster preventive visits*CM preventive maintenance cost***)+(total % of MCCs visited per year*#MCCs) ***Assumed to be 1/2 of the unscheduled maintenance cost.
Note on C23: vdrehe: Capital replacement starts in 2014 but is only at 50% because it will be the first year that equipment will be deployed. And only 1/2 of deployment has been accomplished.
Note on C25: vdrehe: This is the expected cost of the additional visits PSE will pay for on top of the included visits for preventive and unscheduled maintenance included in the contract.
Note on C34: vdrehe: The cost of maintaining the new population of AMI modules on gas meters.
Note on C36: vdrehe: The existing contract structure strongly incentivises L&G to minimize its manual meter reading costs.
Note on C38: vdrehe: From JC's TCO model.
Note on C39: vdrehe: From JC's TCO Model
Note on C42: Puget Sound Energy: Includes from JC's TCO Model: Battery Costs for replacement and non-program years, battery disposal, average battery CPU replacement, labor costs, honeywell, seal costs, 3rd party pole attachment leases and energy use, EA annual Maintenance fee, server hardware and software maintenance.
Note on C44: Puget Sound Energy: From JC's TCO model and include: Infrastructure leaded office space reimbursements. Manual Meter reading expenses-lead expense, other meter reading expenses (scheduling), Downtime, outage and failures expenses (500/month), ZCON Field Service Reimbursements, meter shop expenses, field expenses, gas operations and gas meter exchange, customer service expenses, Dataraker (net cost) consulting costs, IT training, Auditing, IT related time, corporate management time.
Note on C53: vdrehe: This is the cost of the contract based on asset values.

## #1 (hidden)
1-Gradual AMI
| ($Millions) |  | NPV | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026
Year
COSTS
|  | Year of Deployment |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| L+G Contract | L+G Contract | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| L+G Termination Fees | L+G Termination Fees | [16 empty] | 0
|  | AMR Electric Meter Hardware (Growth) | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
|  | AMR Electric Meter Exchange (Growth) | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
|  | AMR Gas Meter Hardware (Growth) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | AMR Gas Meter Exchange (Growth) | #VALUE! | #VALUE! | -2.2638 | 2.1611 | 3.3027 | 3.7464 | 4.0629 | 4.2677 | 4.0769 | 4.0615 | 4.2041 | 4.3773 | 4.5637 | 4.7318 | 4.9015 | 5.0806 | #VALUE!
| AMR Meter Costs |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| AMI Meter/Module Hardware and Deployment | AMI Meter/Module Hardware and Deployment | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | AMI Network growth (capital) | #VALUE! | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | AMI Network growth (installation) | #VALUE! | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | AMI Network maintenance (O&M) | #VALUE! | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | AMI Network maintenance (capital) | #VALUE! | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | AMR Network maintenance (capital) | #VALUE! | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | AMR Network maintenance (O&M) | #VALUE! | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | AMI Network Hardware (Initial capital) | #VALUE! | 0 | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
|  | AMI Network Deployment (initial installation) | #VALUE! | 0 | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
| Network Costs |  | #VALUE! | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| SaaS/NOC/Deployment Services | SaaS/NOC/Deployment Services | #VALUE! | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | Gas Modules for Maintenance | #VALUE! | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | Gas Module Exchanges | #VALUE! | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| #VALUE! |  | #VALUE! | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Manual Meter Reading | Manual Meter Reading | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | Phone Circuits | #VALUE! | 0 | 0 | #VALUE! | #VALUE! | 0.32807 | 0.43388 | 0.40885 | 0.41727 | 0.42587 | 0.43464 | 0.44359 | 0.45273 | 0.46206 | 0.47158 | 0.48129 | #VALUE!
|  | Variable Network Costs (telcom,etc) | #VALUE! | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Telecom Costs |  | #VALUE! | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | Battery Costs | #VALUE! | #VALUE! | 0.28415 | 0.44381 | 1.0183 | 1.7935 | 1.9913 | 1.0815 | 1.1063 | 1.1317 | 0.72014 | 0.73772 | 0.75572 | 0.77416 | 0.79305 | 0.8124 | #VALUE!
|  | Poll Attachment Costs | #VALUE! | #VALUE! | -0.13473 | -0.13756 | -0.14045 | 0.45163 | 0.50815 | 0.52005 | 0.53223 | 0.5447 | 0.55746 | 0.57052 | 0.58389 | 0.59758 | 0.61159 | 0.62593 | #VALUE!
|  | Customer Service and Other Overhead | #VALUE! | #VALUE! | 3.1649 | 3.2191 | 3.2744 | 3.3307 | 3.3882 | 3.4469 | 3.5067 | 3.5677 | 3.63 | 3.6935 | 3.7582 | 3.8243 | 3.8916 | 3.9604 | #VALUE!
| Other Ops Costs |  | #VALUE! | #VALUE! | 3.3143 | 3.5253 | 4.1522 | 5.5758 | 5.8877 | 5.0484 | 5.1452 | 5.2441 | 4.9076 | 5.0017 | 5.0978 | 5.196 | 5.2963 | 5.3987 | #VALUE!
|  | Total | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | Costs (real) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| AMI Investment | AMI Investment | #VALUE! | [15 empty] | #VALUE!
| Investment Costs | Investment Costs | #VALUE! | 0 | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| O&M Costs | O&M Costs | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| CAPEX | CAPEX | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| L&G O&M | L&G O&M | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
BENEFITS
O&M
|  | Contract Costs and Network Maintenance | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Net Benefits | Net Benefits | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Net Benefits (real) | Net Benefits (real) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Cumulative Net Benefits | Cumulative Net Benefits |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Note on B49: vdrehe: "Investment Costs" include up front costs such as termination fees, network deployment, IP and MDM development costs as well as meter hardware costs (if any in the given scenario).
Note on C11: vdrehe: Includes meters and meter exchange costs.
Note on C19: vdrehe: Network Hardware will continue to grow at the AMI network growth rate despite a larger initial deployment because an increasing AMI mesh will limit the need for new network hardware.
Note on C21: vdrehe: This equation = (%Cellmaster unscheduled visits*#of Cellmasters*cost of unscheduled visits)+(scheduled Cellmaster preventive visits*CM preventive maintenance cost***)+(total % of MCCs visited per year*#MCCs) ***Assumed to be 1/2 of the unscheduled maintenance cost.
Note on C22: vdrehe: Capital replacement starts in 2014 but is only at 50% because it will be the first year that equipment will be deployed. And only 1/2 of deployment has been accomplished.
Note on C32: vdrehe: The cost of maintaining new AMI modules on gas meters.
Note on C34: vdrehe: The existing contract structure strongly incentivises L&G to minimize its manual meter reading costs.
Note on C36: vdrehe: From JC's TCO model.
Note on C37: vdrehe: From JC's TCO Model
Note on C40: Puget Sound Energy: Includes from JC's TCO Model: Battery Costs for replacement and non-program years, battery disposal, average battery CPU replacement, labor costs, honeywell, seal costs, 3rd party pole attachment leases and energy use, EA annual Maintenance fee, server hardware and software maintenance.
Note on C42: Puget Sound Energy: From JC's TCO model and include: Infrastructure leaded office space reimbursements. Manual Meter reading expenses-lead expense, other meter reading expenses (scheduling), Downtime, outage and failures expenses (500/month), ZCON Field Service Reimbursements, meter shop expenses, field expenses, gas operations and gas meter exchange, customer service expenses, Dataraker (net cost) consulting costs, IT training, Auditing, IT related time, corporate management time.
Note on C51: vdrehe: This is the cost of the contract based on asset values.

## #2 (hidden)
2-Hybrid-New Vendor
| ($Millions) |  | NPV | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026
Year
COSTS
|  | Year of Deployment |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| L+G Contract | L+G Contract | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| L+G Termination Fees | L+G Termination Fees | #VALUE! | 5: #VALUE! | #VALUE!
| AMI Meter/Module Hardware and Deployment | AMI Meter/Module Hardware and Deployment | #VALUE! | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | AMR Electric Meter Hardware (Growth) | #VALUE! | #VALUE! | -1.5776 | 0.6574 | 1.2489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
|  | AMR Electric Meter Exchange (Growth) | #VALUE! | #VALUE! | -1.4443 | 0.60126 | 1.1411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
|  | AMR Gas Meter Hardware (Growth) | #VALUE! | #VALUE! | -2.8151 | 2.6901 | 4.1151 | 6.0364 | 7.0462 | 7.4087 | 7.0843 | 7.0646 | 7.3198 | 7.6287 | 7.9615 | 8.2627 | 8.5674 | 8.8893 | #VALUE!
|  | AMR Gas Meter Exchange (Growth) | #VALUE! | #VALUE! | -2.2638 | 2.1611 | 3.3027 | 3.7464 | 4.0629 | 4.2677 | 4.0769 | 4.0615 | 4.2041 | 4.3773 | 4.5637 | 4.7318 | 4.9015 | 5.0806 | #VALUE!
| AMR Meter Costs |  | #VALUE! | #VALUE! | -8.1008 | 6.1099 | 9.8078 | 9.7828 | 11.1092 | 11.6764 | 11.1612 | 11.1261 | 11.5239 | 12.006 | 12.5252 | 12.9945 | 13.4689 | 13.9699 | #VALUE!
|  | AMI Network growth (capital) | #VALUE! | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | AMI Network growth (installation) | #VALUE! | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | AMI Network maintenance (O&M) | #VALUE! | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | AMI Network maintenance (capital) | #VALUE! | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | AMI Network Hardware (Initial capital) | #VALUE! | 0 | 0 | 0 | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
|  | AMI Network Deployment (initial installation) | #VALUE! | 0 | 0 | 0 | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
| Network Costs |  | #VALUE! | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| SaaS/NOC/Deployment Services | SaaS/NOC/Deployment Services | #VALUE! | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| MDMS and Intellectual Property Development | MDMS and Intellectual Property Development | #VALUE! | 0 | 0 | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
|  | Gas Modules for Maintenance | #VALUE! | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | Gas Module Exchanges | #VALUE! | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| #VALUE! |  | #VALUE! | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Manual Meter Reading | Manual Meter Reading | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | Phone Circuits | #VALUE! | 0 | 0 | 0 | 0 | 0.32807 | 0.43388 | 0.40885 | 0.41727 | 0.42587 | 0.43464 | 0.44359 | 0.45273 | 0.46206 | 0.47158 | 0.48129 | 4.7598
|  | Variable Network Costs (telcom,etc) | #VALUE! | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Telecom Costs |  | #VALUE! | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | Battery Costs | #VALUE! | #VALUE! | 0.28415 | 0.44381 | 1.0183 | 1.7935 | 1.9913 | 1.0815 | 1.1063 | 1.1317 | 0.72014 | 0.73772 | 0.75572 | 0.77416 | 0.79305 | 0.8124 | #VALUE!
|  | Poll Attachment Costs | #VALUE! | #VALUE! | -0.13473 | -0.13756 | -0.14045 | 0.45163 | 0.50815 | 0.52005 | 0.53223 | 0.5447 | 0.55746 | 0.57052 | 0.58389 | 0.59758 | 0.61159 | 0.62593
|  | Customer Service and Other Overhead | #VALUE! | #VALUE! | 3.1649 | 3.2191 | 3.2744 | 3.3307 | 3.3882 | 3.4469 | 3.5067 | 3.5677 | 3.63 | 3.6935 | 3.7582 | 3.8243 | 3.8916 | 3.9604 | #VALUE!
| Other Ops Costs |  | #VALUE! | #VALUE! | 3.3143 | 3.5253 | 4.1522 | 5.5758 | 5.8877 | 5.0484 | 5.1452 | 5.2441 | 4.9076 | 5.0017 | 5.0978 | 5.196 | 5.2963 | 5.3987 | #VALUE!
|  | Total | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | Costs (real) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| AMI Investment | AMI Investment | #VALUE! | [15 empty] | 0
| Investment Costs | Investment Costs | #VALUE! | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
| O&M Costs | O&M Costs | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| CAPEX | CAPEX | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| L&G O&M |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
BENEFITS
O&M
|  | Contract Costs and Network Maintenance | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | Total | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | Net Benefits | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | Net Benefits (real) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | Cumulative Net Benefits |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Note on C8: vdrehe: Default is the value of the contract based on a per read fee.
Note on C10: vdrehe: Includes module price after q1 2016.
Note on C16: vdrehe:All network costs are based on the "gradual" scenario
Note on C20: vdrehe: Network Hardware will continue to grow at the AMI network growth rate despite a larger initial deployment because an increasing AMI mesh will limit the need for new network hardware.
Note on C22: vdrehe: This equation = (%Cellmaster unscheduled visits*#of Cellmasters*cost of unscheduled visits)+(scheduled Cellmaster preventive visits*CM preventive maintenance cost***)+(total % of MCCs visited per year*#MCCs) ***Assumed to be 1/2 of the unscheduled maintenance cost.
Note on C23: vdrehe: Capital replacement starts in 2014 but is only at 50% because it will be the first year that equipment will be deployed. And only 1/2 of deployment has been accomplished.
Note on C25: vdrehe: This is the expected cost of the additional visits PSE will pay for on top of the included visits for preventive and unscheduled maintenance included in the contract.
Note on C32: vdrehe: The existing contract structure strongly incentivises L&G to minimize its manual meter reading costs.
Note on C34: vdrehe: From JC's TCO model.
Note on C35: vdrehe: From JC's TCO Model
Note on C38: Puget Sound Energy: Includes from JC's TCO Model: Battery Costs for replacement and non-program years, battery disposal, average battery CPU replacement, labor costs, honeywell, seal costs, 3rd party pole attachment leases and energy use, EA annual Maintenance fee, server hardware and software maintenance.
Note on C40: Puget Sound Energy: From JC's TCO model and include: Infrastructure leaded office space reimbursements. Manual Meter reading expenses-lead expense, other meter reading expenses (scheduling), Downtime, outage and failures expenses (500/month), ZCON Field Service Reimbursements, meter shop expenses, field expenses, gas operations and gas meter exchange, customer service expenses, Dataraker (net cost) consulting costs, IT training, Auditing, IT related time, corporate management time.
Note on C46: vdrehe: This is the cost of the contract based on asset values.

## #3 (hidden)
3-Hybrid-L+G
| ($Millions) |  | NPV | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026
Year
COSTS
|  | Year of Deployment |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| L+G Managed Service Contract | L+G Managed Service Contract | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | AMR Electric Meter Hardware | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
|  | AMR Electric Meter Exchange | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
|  | AMR Gas Meter Hardware | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | AMR Gas Meter Exchange | #VALUE! | #VALUE! | -2.2638 | 2.1611 | 3.3027 | 3.7464 | 4.0629 | 4.2677 | 4.0769 | 4.0615 | 4.2041 | 4.3773 | 4.5637 | 4.7318 | 4.9015 | 5.0806 | #VALUE!
| AMR Meter Costs |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| AMI Meter/Module Hardware and Deployment | AMI Meter/Module Hardware and Deployment | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | AMI Network Hardware (Initial capital) | #VALUE! | 0 | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
|  | AMI Network Deployment (initial installation) | #VALUE! | 0 | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
|  | AMI Network growth (capital) | #VALUE! | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | AMI Network growth (installation) | #VALUE! | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | AMI Network maintenance (O&M) | #VALUE! | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | AMI Network maintenance (capital) | #VALUE! | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | AMR Network maintenance (capital) | #VALUE! | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | AMR Network maintenance (O&M) | #VALUE! | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Network Costs |  | #VALUE! | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | Gas Modules for Maintenance | #VALUE! | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | Gas Module Exchange | #VALUE! | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Gas Module Maintenance |  | #VALUE! | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Manual Meter Reading | Manual Meter Reading | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
|  | Phone Circuits | #VALUE! | #VALUE! | 0 | 0 | 0 | 0.32807 | 0.43388 | 0.40885 | 0.41727 | 0.42587 | 0.43464 | 0.44359 | 0.45273 | 0.46206 | 0.47158 | 0.48129 | #VALUE!
|  | Variable Network Costs (telcom,etc) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Telecom Costs |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | Battery Costs | #VALUE! | #VALUE! | 0.28415 | 0.44381 | 1.0183 | 1.7935 | 1.9913 | 1.0815 | 1.1063 | 1.1317 | 0.72014 | 0.73772 | 0.75572 | 0.77416 | 0.79305 | 0.8124 | #VALUE!
|  | Poll Attachment Costs | #VALUE! | #VALUE! | -0.13473 | -0.13756 | -0.14045 | 0.45163 | 0.50815 | 0.52005 | 0.53223 | 0.5447 | 0.55746 | 0.57052 | 0.58389 | 0.59758 | 0.61159 | 0.62593 | #VALUE!
|  | Customer Service and Other Overhead | #VALUE! | #VALUE! | 3.1649 | 3.2191 | 3.2744 | 3.3307 | 3.3882 | 3.4469 | 3.5067 | 3.5677 | 3.63 | 3.6935 | 3.7582 | 3.8243 | 3.8916 | 3.9604 | #VALUE!
| Other Ops Costs |  | #VALUE! | #VALUE! | 3.3143 | 3.5253 | 4.1522 | 5.5758 | 5.8877 | 5.0484 | 5.1452 | 5.2441 | 4.9076 | 5.0017 | 5.0978 | 5.196 | 5.2963 | 5.3987 | #VALUE!
|  | Total | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | Costs (real) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| O&M Costs | O&M Costs | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| CAPEX | CAPEX | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| L&G O&M |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
BENEFITS
Network
O&M
|  | Contract Costs and Network Maintenance | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | Total | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
0
| Net Benefits | Net Benefits | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Net Benefits (real) | Net Benefits (real) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Cumulative Net Benefits | Cumulative Net Benefits |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Note on B51: vdrehe: "Investment Costs" include up front costs such as termination fees, network deployment, IP and MDM development costs as well as meter hardware costs (if any in the given scenario).
Note on C11: vdrehe: Includes meters and meter exchange costs.
Note on C19: vdrehe: Network Hardware will continue to grow at the AMI network growth rate despite a larger initial deployment because an increasing AMI mesh will limit the need for new network hardware.
Note on C21: vdrehe: This equation = (%Cellmaster unscheduled visits*#of Cellmasters*cost of unscheduled visits)+(scheduled Cellmaster preventive visits*CM preventive maintenance cost***)+(total % of MCCs visited per year*#MCCs) ***Assumed to be 1/2 of the unscheduled maintenance cost.
Note on C22: vdrehe: Capital replacement starts in 2014 but is only at 50% because it will be the first year that equipment will be deployed. And only 1/2 of deployment has been accomplished.
Note on C23: vdrehe: AMR equipment quantities are fixed assuming that the AMR network will not grow given that AMI is being deployed.
Note on C24: vdrehe: This is the expected cost of the additional visits PSE will pay for on top of the included visits for preventive and unscheduled maintenance included in the contract.
Note on C37: vdrehe: The existing contract structure strongly incentivises L&G to minimize its manual meter reading costs.
Note on C39: vdrehe: From JC's TCO model.
Note on C40: vdrehe: Since PSE will own its own AMI network in this scenario, we are assuming that PSE would have its own network costs as in scenario 1.
Note on C43: Puget Sound Energy: Includes from JC's TCO Model: Battery Costs for replacement and non-program years, battery disposal, average battery CPU replacement, labor costs, honeywell, seal costs, 3rd party pole attachment leases and energy use, EA annual Maintenance fee, server hardware and software maintenance.
Note on C44: Puget Sound Energy: From JC's TCO model and include: Infrastructure leaded office space reimbursements. Manual Meter reading expenses-lead expense, other meter reading expenses (scheduling), Downtime, outage and failures expenses (500/month), ZCON Field Service Reimbursements, meter shop expenses, field expenses, gas operations and gas meter exchange, customer service expenses, Dataraker (net cost) consulting costs, IT training, Auditing, IT related time, corporate management time.
Note on C53: vdrehe: This is the cost of the contract based on asset values.

## MeterMinimums (hidden)
5-Meter Minimums
| ($Millions) |  | NPV | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026
Year
COSTS
|  | Year of Deployment |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| L+G Contract | L+G Contract | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| L+G Termination Fees | L+G Termination Fees | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| AMI Meter/Module Hardware and Deployment | AMI Meter/Module Hardware and Deployment | #VALUE! | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
0
|  | AMR Electric Meter Hardware (Growth) | #VALUE! | #VALUE! | -1.5776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
|  | AMR Electric Meter Exchange (Growth) | #VALUE! | #VALUE! | -1.4443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
|  | AMR Gas Meter Hardware (Growth) | #VALUE! | #VALUE! | -2.8151 | 2.6901 | 4.1151 | 6.0364 | 7.0462 | 7.4087 | 7.0843 | 7.0646 | 7.3198 | 7.6287 | 7.9615 | 8.2627 | 8.5674 | 8.8893 | #VALUE!
|  | AMR Gas Meter Exchange (Growth) | #VALUE! | #VALUE! | -2.2638 | 2.1611 | 3.3027 | 3.7464 | 4.0629 | 4.2677 | 4.0769 | 4.0615 | 4.2041 | 4.3773 | 4.5637 | 4.7318 | 4.9015 | 5.0806 | #VALUE!
| AMR Meter Costs |  | #VALUE! | #VALUE! | -8.1008 | 4.8512 | 7.4178 | 9.7828 | 11.1092 | 11.6764 | 11.1612 | 11.1261 | 11.5239 | 12.006 | 12.5252 | 12.9945 | 13.4689 | 13.9699 | #VALUE!
|  | AMI Network growth (capital) | #VALUE! | #VALUE! | 0 | 0 | 0 | 0.1576 | 0.16075 | 0.16397 | 0.16725 | 0.17059 | 0.17401 | 0.17749 | 0.18104 | 0.18466 | 0.18835 | 0.19212 | #VALUE!
|  | AMI Network growth (installation) | #VALUE! | #VALUE! | 0 | 0 | 0 | 96.6885 | 120.8241 | 147.144 | 20.3131 | 20.4193 | 21.1522 | 22.0095 | 22.9301 | 23.7928 | 24.6753 | 25.6049 | #VALUE!
|  | AMI Network maintenance (O&M) | #VALUE! | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | AMI Network maintenance (capital) | #VALUE! | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | AMR Network maintenance (capital) | #VALUE! | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | AMR Network maintenance (O&M) | #VALUE! | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | AMI Network Hardware (Initial capital deployoment) | #VALUE! | 0 | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
|  | AMI Network Deployment (initial installation) | #VALUE! | 0 | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
| Network Costs |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| SaaS/NOC/Deployment Services | SaaS/NOC/Deployment Services | #VALUE! | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| MDMS and Intellectual Property Development | MDMS and Intellectual Property Development | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
|  | Gas Modules for Maintenance | #VALUE! | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | Gas Module Exchanges | #VALUE! | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| #VALUE! |  | #VALUE! | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Manual Meter Reading | Manual Meter Reading | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | Phone Circuits | #VALUE! | #VALUE! | 0 | 0 | 0 | 0.32807 | 0.43388 | 0.40885 | 0.41727 | 0.42587 | 0.43464 | 0.44359 | 0.45273 | 0.46206 | 0.47158 | 0.48129 | #VALUE!
|  | Variable Network Costs (telcom,etc) | #VALUE! | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Telecom Costs |  | #VALUE! | #VALUE! | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | Battery, Consulting and Poll Attachment Costs | #VALUE! | #VALUE! | 0.28415 | 0.44381 | 1.0183 | 1.7935 | 1.9913 | 1.0815 | 1.1063 | 1.1317 | 0.72014 | 0.73772 | 0.75572 | 0.77416 | 0.79305 | 0.8124 | #VALUE!
|  | Operations Expenses | #VALUE! | #VALUE! | 3.1649 | 3.2191 | 3.2744 | 3.3307 | 3.3882 | 3.4469 | 3.5067 | 3.5677 | 3.63 | 3.6935 | 3.7582 | 3.8243 | 3.8916 | 3.9604 | #VALUE!
| Other Ops Costs |  | #VALUE! | #VALUE! | 3.4491 | 3.6629 | 4.2926 | 5.1242 | 5.3796 | 4.5284 | 4.613 | 4.6994 | 4.3501 | 4.4312 | 4.5139 | 4.5984 | 4.6847 | 4.7728 | #VALUE!
|  | Total | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | Costs (real) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| AMI Investment | AMI Investment | #VALUE! | [15 empty] | #VALUE!
| Investment Costs | Investment Costs | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| O&M Costs | O&M Costs | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| CAPEX | CAPEX | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| L&G O&M |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
BENEFITS
Network
|  | Contract Costs and Network Maintenance | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | Total | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Net Benefits | Net Benefits | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Net Benefits (real) | Net Benefits (real) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Cumulative Net Benefits | Cumulative Net Benefits |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Indicates a contracted service
Note on B52: vdrehe: "Investment Costs" include up front costs such as termination fees, network deployment, IP and MDM development costs as well as meter hardware costs (if any in the given scenario).
Note on C12: vdrehe: Includes meters and meter exchange costs.
Note on C21: vdrehe: Network Hardware will continue to grow at the AMI network growth rate despite a larger initial deployment because an increasing AMI mesh will limit the need for new network hardware.
Note on C23: vdrehe: This equation = (%Cellmaster unscheduled visits*#of Cellmasters*cost of unscheduled visits)+(scheduled Cellmaster preventive visits*CM preventive maintenance cost***)+(total % of MCCs visited per year*#MCCs) ***Assumed to be 1/2 of the unscheduled maintenance cost.
Note on C24: vdrehe: Capital replacement starts in 2014 but is only at 50% because it will be the first year that equipment will be deployed. And only 1/2 of deployment has been accomplished.
Note on C26: vdrehe: This is the expected cost of the additional visits PSE will pay for on top of the included visits for preventive and unscheduled maintenance included in the contract.
Note on C38: vdrehe: The existing contract structure strongly incentivises L&G to minimize its manual meter reading costs.
Note on C40: vdrehe: From JC's TCO model.
Note on C41: vdrehe: Since PSE will own its own AMI network in this scenario, we are assuming that PSE would have its own network costs as in scenario 1.
Note on C44: Puget Sound Energy: Includes from JC's TCO Model: Battery Costs for replacement and non-program years, battery disposal, average battery CPU replacement, labor costs, honeywell, seal costs, 3rd party pole attachment leases and energy use, EA annual Maintenance fee, server hardware and software maintenance.
Note on C45: Puget Sound Energy: From JC's TCO model and include: Infrastructure leaded office space reimbursements. Manual Meter reading expenses-lead expense, other meter reading expenses (scheduling), Downtime, outage and failures expenses (500/month), ZCON Field Service Reimbursements, meter shop expenses, field expenses, gas operations and gas meter exchange, customer service expenses, Dataraker (net cost) consulting costs, IT training, Auditing, IT related time, corporate management time.
Note on C54: vdrehe: This is the cost of the contract based on asset values.

## #6 (hidden)
6-Meter Floor
| ($Millions) |  | NPV | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026
Year
COSTS
|  | Year of Deployment |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | TCO
| L+G Contract | L+G Contract | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| L+G Termination Fees | L+G Termination Fees | #VALUE! | 0 | 0 | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
| AMI Meter/Module Hardware and Deployment | AMI Meter/Module Hardware and Deployment | #VALUE! | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | AMR Electric Meter Hardware (Growth) | #VALUE! | #VALUE! | -1.5776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
|  | AMR Electric Meter Exchange (Growth) | #VALUE! | #VALUE! | -1.4443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
|  | AMR Gas Meter Hardware (Growth) | #VALUE! | #VALUE! | -2.8151 | 2.6901 | 4.1151 | 6.0364 | 7.0462 | 7.4087 | 7.0843 | 7.0646 | 7.3198 | 7.6287 | 7.9615 | 8.2627 | 8.5674 | 8.8893 | #VALUE!
|  | AMR Gas Meter Exchange (Growth) | #VALUE! | #VALUE! | -2.2638 | 2.1611 | 3.3027 | 3.7464 | 4.0629 | 4.2677 | 4.0769 | 4.0615 | 4.2041 | 4.3773 | 4.5637 | 4.7318 | 4.9015 | 5.0806 | #VALUE!
| AMR Meter Costs |  | #VALUE! | #VALUE! | -8.1008 | 4.8512 | 7.4178 | 9.7828 | 11.1092 | 11.6764 | 11.1612 | 11.1261 | 11.5239 | 12.006 | 12.5252 | 12.9945 | 13.4689 | 13.9699 | #VALUE!
|  | AMI Network growth (capital) | #VALUE! | #VALUE! | 0 | 0 | 0 | 0.1576 | 0.16075 | 0.16397 | 0.16725 | 0.17059 | 0.17401 | 0.17749 | 0.18104 | 0.18466 | 0.18835 | 0.19212 | #VALUE!
|  | AMI Network growth (installation) | #VALUE! | #VALUE! | 0 | 0 | 0 | 96.6885 | 120.8241 | 147.144 | 20.3131 | 20.4193 | 21.1522 | 22.0095 | 22.9301 | 23.7928 | 24.6753 | 25.6049 | #VALUE!
|  | AMI Network maintenance (O&M) | #VALUE! | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | AMI Network maintenance (capital) | #VALUE! | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | AMR Network maintenance (capital) | #VALUE! | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | AMR Network maintenance (O&M) | #VALUE! | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | AMI Network Hardware (Initial capital) | #VALUE! | 0 | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
|  | AMI Network Deployment (initial installation) | #VALUE! | 0 | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
| Network Costs |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| SaaS/NOC/Deployment Services | SaaS/NOC/Deployment Services | #VALUE! | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| MDMS and Intellectual Property Development | MDMS and Intellectual Property Development | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
|  | Gas Modules for Maintenance | #VALUE! | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | Gas Module Exchanges | #VALUE! | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| #VALUE! |  | #VALUE! | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Manual Meter Reading | Manual Meter Reading | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | Phone Circuits | #VALUE! | #VALUE! | 0 | 0 | 0 | 0.32807 | 0.43388 | 0.40885 | 0.41727 | 0.42587 | 0.43464 | 0.44359 | 0.45273 | 0.46206 | 0.47158 | 0.48129 | #VALUE!
|  | Variable Network Costs (telcom,etc) | #VALUE! | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Telecom Costs |  | #VALUE! | #VALUE! | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | Battery, Consulting and Poll Attachment Costs | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | Operations Expenses | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Other Ops Costs |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | Total | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | Costs (real) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| AMI Investment | AMI Investment | #VALUE! | [15 empty] | #VALUE!
| Investment Costs | Investment Costs | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
| O&M Costs | O&M Costs | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| CAPEX | CAPEX | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| L&G O&M |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
BENEFITS
Network
|  | Contract Costs and Network Maintenance | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | Total | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Net Benefits | Net Benefits | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Net Benefits (real) | Net Benefits (real) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Cumulative Net Benefits | Cumulative Net Benefits |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Indicates a contracted service
Note on D11: vdrehe: Includes module price after q1 2016. There continues to be some ARM growth and maintenance because AMI deployments are being done geographically.
Note on D13: vdrehe: AMR meters that are returned can be redeployed in areas where AMI does not exist.
Note on D14: vdrehe: There is still growth in AMR meters in non-AMI areas. The zeros in early years are the result of 0% projected customer growth.
Note on D21: vdrehe: These are the AMR gas module exchanges that will continue to occur where there is not yet AMI network availability.
Note on D22: vdrehe:vdrehe: These are the AMR gas module visits that will continue to occur where there is not yet AMI network availability.
Note on D23: Puget Sound Energy: Includes from JC's TCO Model: Battery Costs for replacement and non-program years, battery disposal, average battery CPU replacement, labor costs, honeywell, seal costs, 3rd party pole attachment leases and energy use, EA annual Maintenance fee, server hardware and software maintenance.
Note on D26: vdrehe: Includes module price. There continues to be some ARM growth and maintenance until 2016, because AMI deployments are being done geographically and according to network availability.
Note on D27: vdrehe: This is the maintenance on the AMI population.
Note on D28: vdrehe: Different costs for installation are being used. The AMR rate is used for "business case" deployments and a lower rate is used for "fill-ins" that are done less expensively.
Note on D29: vdrehe: This is the maintenance being done on the AMI population. Only one standard rate applies.
Note on D30: vdrehe: This is the installation of new AMI meter/module combination for new customers. This is the portion of new AMI gas installations that will also include a meter exchange. This cost is for the hardware component.
Note on D31: vdrehe: This is the installation of AMI meter/modules AMI meters that have failed (hardware component).
Note on D32: vdrehe: This is the installation of new AMI meter/module combination for new customers. This is the portion of new AMI gas installations that will also include a meter exchange. This cost is for the labor component.
Note on D33: vdrehe: vdrehe: This is the installation of AMI meter/modules AMI meters that have failed (labor component).
Note on D34: vdrehe: This is the new gas modules that will be added for growth and attrition of AMR modules. It is assumed that anything that is not part of PSE's normal growth of new customers will be a AMR to AMI module exchange.
Note on D44: vdrehe: This is the network equipment failure rate. This assumes that there only CAPEX equipment required for "failures."
Note on D46: vdrehe:
Note on D53: vdrehe: Cost of installing equipment/software for PSE owned meter read solution.
Note on D60: vdrehe: From JC's TCO model.
Note on D62: Puget Sound Energy: From JC's TCO model and include: Infrastructure leaded office space reimbursements. Manual Meter reading expenses-lead expense, other meter reading expenses (scheduling), Downtime, outage and failures expenses (500/month), ZCON Field Service Reimbursements, meter shop expenses, field expenses, gas operations and gas meter exchange, customer service expenses, Dataraker (net cost) consulting costs, IT training, Auditing, IT related time, corporate management time.

## Hybrid AMI (R)
1-Hybrid AMI
| ($Millions) |  |  |  | NPV | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
| Year |  |  |  |  | -1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
| COSTS | CAPEX VS O&M
|  |  | Year of Deployment |  |  | -1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
| L+G Managed Service Contract | O&M | L+G Managed Service Contract | This is based on the (read fees) X (annual AMR supported meters). It does not include AMI meters. | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
|  | CAPEX | AMR Electric Meter Hardware (Growth) | Continues in non-AMI areas until 2016 | 2.6769 | -1.5776 | 0.6574 | 1.2489 | 1.2411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5698
|  | CAPEX | AMR Electric Meter Hardware (Maintenance) | Continues in non-AMI areas until 2016 | 0.76656 | 0.2256 | 0.30188 | 0.31488 | 0.26953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1119
|  | CAPEX | AMR Electric Meter Hardware (Redeployed) | Continues in non-AMI areas until 2016 | 0 | [28 empty] | 0
|  | CAPEX | AMR Electric Meter Exchange (Growth) | Continues in non-AMI areas until 2016 | 2.0372 | -1.4443 | 0.60126 | 1.1411 | 0.6218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.91989
|  | O&M | AMR Electric Meter Exchange (Maintenance) | Continues in non-AMI areas until 2016 | 0.61179 | 0.20653 | 0.2761 | 0.2877 | 0.13504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.90537
|  | CAPEX | AMR Gas Meter Hardware (Growth) | Continues in non-AMI areas until 2016 | 8.4506 | -2.8151 | 2.6901 | 4.1151 | 3.0182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.0083
|  | CAPEX | AMR Gas Meter Hardware (Maintenance) | Continues in non-AMI areas until 2016 | 2.2746 | 0.96052 | 0.99899 | 1.0479 | 0.55745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5649
|  | CAPEX | AMR Gas Meter Exchange (Growth) | Continues in non-AMI areas until 2016 | 6.3455 | -2.2638 | 2.1611 | 3.3027 | 1.8732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.0732
|  | O&M | AMR Gas Meter Exchange (Maintenance) | Continues in non-AMI areas until 2016 | 1.7452 | 0.7724 | 0.80254 | 0.84105 | 0.34597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.762
|  | CAPEX | AMR Gas Modules for Maintenance | No modules ever purchased by PSE. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | O&M | AMR Gas Module Exchanges | Only through 2015. | 0.66371 | 0.31807 | 0.31553 | 0.31574 | 0.12402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0734
|  | O&M | AMR Gas Module Visits | Only through 2015. | 1.0768 | 0.51603 | 0.51191 | 0.51224 | 0.20121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7414
|  | O&M | Battery Costs |  | 2.005 | 0.28415 | 0.44381 | 1.0183 | 0.89673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.643
| AMR Meter/ Module Costs |  | Total |  | 28.6538 | -4.8175 | 9.7606 | 14.1456 | 9.2842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.373
|  | CAPEX | AMI Electric Meter Hardware (Growth) | Begins in 2013, inclds all growth 2016 on. | 145.8937 | 0 | 0 | 0 | 17.2822 | 22.222 | 24.8501 | 23.4797 | 22.91 | 22.6798 | 22.6809 | 22.863 | 23.169 | 20.0758 | 4.1148 | 4.2458 | 4.3661 | 4.5055 | 4.6338 | 4.7602 | 4.8831 | 5.0091 | 6.2965 | 6.5498 | 6.8132 | 7.0873 | 7.3723 | 7.6689 | 7.9773 | 285.4775
|  | CAPEX | AMI Electric Meter Hardware (Maintenance) | Begins in 2013, inclds all maintenance 2016 on. | 5.6665 | 0 | 0 | 0 | 0.058759 | 0.13555 | 0.22288 | 0.3074 | 0.39175 | 0.47708 | 0.56422 | 0.6538 | 0.7463 | 0.83023 | 0.86166 | 0.89419 | 0.92781 | 0.96262 | 0.99859 | 1.0357 | 1.0741 | 1.1137 | 1.1585 | 1.2051 | 1.2535 | 1.304 | 1.3564 | 1.411 | 1.4677 | 17.1774
|  | CAPEX | AMI Electric Meter Exchange (Growth) | Begins in 2013, inclds all growth 2016 on. | 32.2648 | 0 | 0 | 0 | 3.3875 | 4.8961 | 5.6497 | 5.1033 | 4.8163 | 4.6367 | 4.5289 | 4.4759 | 4.4593 | 3.9743 | 1.3279 | 1.3689 | 1.4063 | 1.4497 | 1.4895 | 1.5287 | 1.5666 | 1.6055 | 2.0161 | 2.0952 | 2.1773 | 2.2627 | 2.3514 | 2.4436 | 2.5394 | 66.2226
|  | O&M | AMI Electric Meter Exchange (Maintenance) | Begins in 2013, inclds all maintenance 2016 on. | 1.8259 | 0 | 0 | 0 | 0.019149 | 0.044131 | 0.072495 | 0.099885 | 0.12717 | 0.15472 | 0.1828 | 0.21161 | 0.24132 | 0.26819 | 0.27807 | 0.28829 | 0.29884 | 0.30974 | 0.321 | 0.33262 | 0.3446 | 0.35695 | 0.37094 | 0.38548 | 0.4006 | 0.4163 | 0.43262 | 0.44958 | 0.46721 | 5.5249
|  | CAPEX | AMI Gas Meter/Module Hardware (Growth) | Begins in 2013 | 75.5298 | 0 | 0 | 0 | 3.3643 | 7.3042 | 7.6799 | 7.3436 | 7.3231 | 7.5877 | 7.9079 | 8.2529 | 8.5651 | 8.881 | 9.2146 | 9.5453 | 9.8455 | 10.1984 | 10.5088 | 10.8117 | 11.1047 | 11.3992 | 9.8341 | 10.2297 | 10.6412 | 11.0692 | 11.5144 | 11.9775 | 12.4593 | 198.6121
|  | CAPEX | AMI Gas Meter/Module Hardware (Maintenance) | Begins in 2013 | 18.2722 | 0 | 0 | 0 | 0.34375 | 0.68811 | 0.89776 | 1.1215 | 1.3597 | 1.6132 | 1.8826 | 2.169 | 2.3261 | 2.4353 | 2.5491 | 2.6676 | 2.7905 | 2.9185 | 3.0512 | 3.1888 | 3.3313 | 3.4788 | 3.6187 | 3.7643 | 3.9157 | 4.0732 | 4.237 | 4.4074 | 4.5847 | 54.1846
|  | CAPEX | AMI Gas Meter Exchange (Growth) | Begins in 2013 | 41.6794 | 0 | 0 | 0 | 1.8732 | 4.0629 | 4.2677 | 4.0769 | 4.0615 | 4.2041 | 4.3773 | 4.5637 | 4.7318 | 4.9015 | 5.0806 | 5.2578 | 5.4179 | 5.6065 | 5.7715 | 5.9321 | 6.0869 | 6.2421 | 5.3799 | 5.5908 | 5.81 | 6.0377 | 6.2744 | 6.5204 | 6.776 | 109.3344
|  | O&M | AMI Gas Meter Exchange (Maintenance) | Begins in 2013 | 10.0632 | 0 | 0 | 0 | 0.1914 | 0.38276 | 0.49889 | 0.62259 | 0.7541 | 0.89381 | 1.0421 | 1.1994 | 1.285 | 1.3441 | 1.4055 | 1.4694 | 1.5356 | 1.6044 | 1.6758 | 1.7496 | 1.826 | 1.905 | 1.9796 | 2.0573 | 2.1379 | 2.2217 | 2.3088 | 2.3993 | 2.4934 | 29.7819
|  | CAPEX | New AMI Gas Modules (Deployments) |  | 47.0768 | 0 | 0 | 0 | 13.3903 | 12.9177 | 6.4244 | 6.9606 | 7.4088 | 7.7881 | 8.171 | 8.5681 | 2.3956 | 0 | 0 | 0 | 0 | 0 | -1.3328e-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74.0245
|  | CAPEX | New AMI Gas Module Exchanges (Deployments) |  | 11.3149 | 0 | 0 | 0 | 2.4145 | 2.6267 | 1.7964 | 1.9389 | 2.0567 | 2.1554 | 2.2583 | 2.3657 | 0.6624 | 0.0022727 | 0 | 0 | 0 | 0 | -1.8622e-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.2773
|  | O&M | AMI Gas Module Visits |  | 0.58524 | 0 | 0 | 0 | 0.011131 | 0.02226 | 0.029014 | 0.036207 | 0.043856 | 0.05198 | 0.060605 | 0.069754 | 0.074733 | 0.078166 | 0.081739 | 0.085453 | 0.089304 | 0.093307 | 0.097456 | 0.10175 | 0.10619 | 0.11079 | 0.11513 | 0.11964 | 0.12433 | 0.12921 | 0.13427 | 0.13954 | 0.14501 | 1.732
|  | CAPEX | AMI Gas Modules (Maintenance) |  | 2.7916 | 0 | 0 | 0 | 0.052517 | 0.10513 | 0.13716 | 0.17133 | 0.20773 | 0.24645 | 0.28763 | 0.33137 | 0.35537 | 0.37206 | 0.38945 | 0.40754 | 0.42633 | 0.44588 | 0.46616 | 0.48718 | 0.50895 | 0.53148 | 0.55286 | 0.57509 | 0.59822 | 0.62229 | 0.64732 | 0.67335 | 0.70044 | 8.2782
|  | O&M | AMI Gas Modude Exchanges (Maintenance) |  | 0.78227 | 0 | 0 | 0 | 0.014878 | 0.029754 | 0.038781 | 0.048397 | 0.05862 | 0.06948 | 0.081008 | 0.093238 | 0.099893 | 0.10448 | 0.10926 | 0.11422 | 0.11937 | 0.12472 | 0.13027 | 0.13601 | 0.14194 | 0.14808 | 0.15389 | 0.15992 | 0.16619 | 0.17271 | 0.17948 | 0.18651 | 0.19383 | 2.3151
|  | O&M | FTE to Manage Inventory/Testing |  | 1.6884 | 0 | 0 | 0 | 0.1576 | 0.16075 | 0.16397 | 0.16725 | 0.17059 | 0.17401 | 0.17749 | 0.18104 | 0.18466 | 0.18835 | 0.19212 | 0.19596 | 0.19988 | 0.20388 | 0.20795 | 0.21211 | 0.21635 | 0.22068 | 0.22509 | 0.2296 | 0.23419 | 0.23887 | 0.24365 | 0.24852 | 0.25349 | 4.3024
| AMI Meter/ Module Costs |  | Total |  | 395.4346 | 0 | 0 | 0 | 42.5611 | 55.5979 | 52.7291 | 51.4774 | 51.6901 | 52.7325 | 54.2028 | 55.9985 | 49.2966 | 43.4558 | 25.6049 | 26.5403 | 27.4234 | 28.4232 | 29.3521 | 30.2765 | 31.1908 | 32.1213 | 31.7014 | 32.9617 | 34.2723 | 35.6351 | 37.0521 | 38.5256 | 40.0579 | 875.2449
|  | CAPEX | AMI Network Installation (Hardware) |  | 12.1626 | 0 | 0 | 0 | 6.1378 | 9.7918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.9296
|  | CAPEX | AMI Network Installation (Labor) |  | 3.5156 | 0 | 0 | 0 | 1.7741 | 2.8303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.6044
|  | CAPEX | AMI Network maintenance (Hardware) |  | 2.9319 | 0 | 0 | 0 | 0.26041 | 0.26697 | 0.27373 | 0.28068 | 0.28783 | 0.29519 | 0.30276 | 0.31056 | 0.31859 | 0.32686 | 0.33538 | 0.34415 | 0.35318 | 0.36249 | 0.37209 | 0.38197 | 0.39216 | 0.40267 | 0.4135 | 0.42467 | 0.43619 | 0.44808 | 0.46034 | 0.47299 | 0.48604 | 7.5901
|  | O&M | AMI Network maintenance (Labor) |  | 7.5535 | 0 | 0 | 0 | 0.36619 | 0.74704 | 0.76198 | 0.77722 | 0.79276 | 0.80862 | 0.82479 | 0.84128 | 0.85811 | 0.87527 | 0.89278 | 0.91063 | 0.92885 | 0.94742 | 0.96637 | 0.9857 | 1.0054 | 1.0255 | 1.046 | 1.067 | 1.0883 | 1.1101 | 1.1323 | 1.1549 | 1.178 | 19.6273
|  | O&M | Manual Meter Reading |  | 0.85023 | 0 | 0 | 0 | 0.065529 | 0.068535 | 0.07161 | 0.074661 | 0.077761 | 0.080972 | 0.08431 | 0.087781 | 0.091382 | 0.095117 | 0.098992 | 0.10301 | 0.10717 | 0.11148 | 0.11594 | 0.12054 | 0.1253 | 0.13021 | 0.13532 | 0.14062 | 0.14614 | 0.15187 | 0.15782 | 0.16401 | 0.17044 | 2.2842
|  | O&M | Network Overhead and management |  | 2.4854 | 0 | 0 | 0 | 0.1773 | 0.24113 | 0.24595 | 0.25087 | 0.25589 | 0.26101 | 0.26623 | 0.27155 | 0.27698 | 0.28252 | 0.28817 | 0.29394 | 0.29982 | 0.30581 | 0.31193 | 0.31817 | 0.32453 | 0.33102 | 0.33764 | 0.34439 | 0.35128 | 0.35831 | 0.36547 | 0.37278 | 0.38024 | 6.3945
|  |  | Cost of Implimentation of Disconnect/Reconnect Program |  | 0 | [28 empty] | 0
|  |  | Cost of Maintaining Disconnect/Reconnect Program |  | 0 | [28 empty] | 0
| Network Costs |  | Total |  | 29.4991 | 0 | 0 | 0 | 8.7814 | 13.9457 | 1.3533 | 1.3834 | 1.4142 | 1.4458 | 1.4781 | 1.5112 | 1.5451 | 1.5798 | 1.6153 | 1.6517 | 1.689 | 1.7272 | 1.7663 | 1.8064 | 1.8474 | 1.8894 | 1.9325 | 1.9766 | 2.0219 | 2.0683 | 2.1159 | 2.1647 | 2.2147 | 56.4301
|  | CAPEX | Software Licence Fee |  | 5.3788 | 0 | 0 | 0 | 0.88293 | 0.97078 | 0.8003 | 0.7882 | 0.7923 | 0.80379 | 0.8206 | 0.84177 | 0.63565 | 0.49388 | 0.18012 | 0.18625 | 0.19185 | 0.19838 | 0.20424 | 0.20999 | 0.21556 | 0.22121 | 0.2301 | 0.23936 | 0.24899 | 0.259 | 0.26942 | 0.28026 | 0.29153 | 10.4152
|  | CAPEX | Set-up and Installation of Command Center |  | 0.041238 | 0 | 0 | 0.047895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAPEX | ECC Security Head End Appliances (Per Set) - Requires 1-set each for production, Disaster Recovery, testing (one time cost) |  | 0.43987 | 0 | 0 | 0.51088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | O&M | Software Maintenance Fee (per endpoint/year) |  | 12.3606 | 0 | 0 | 0 | 0.17659 | 0.37445 | 0.54237 | 0.7114 | 0.8848 | 1.0641 | 1.2506 | 1.4452 | 1.6027 | 1.7351 | 1.8076 | 1.8828 | 1.9607 | 2.0416 | 2.1253 | 2.2119 | 2.3015 | 2.3941 | 2.4903 | 2.5905 | 2.6947 | 2.8031 | 2.9159 | 3.0331 | 3.1551
|  | CAPEX | Deployment Project Management |  | 1.738 | 0 | 0 | 0.70955 | 0.72446 | 0.73967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1737
| NOC Head End Costs |  | Total |  | 19.9586 | 0 | 0 | 1.2683 | 1.784 | 2.0849 | 1.3427 | 1.4996 | 1.6771 | 1.8679 | 2.0712 | 2.287 | 2.2384 | 2.229 | 1.9877 | 2.0691 | 2.1526 | 2.24 | 2.3295 | 2.4219 | 2.517 | 2.6153 | 2.7205 | 2.8299 | 2.9437 | 3.0621 | 3.1853 | 3.3134 | 3.4467 | 50.2393
0
|  |  | Testing/Security |  | 0
|  | O&M | Backhaul Costs (Licences and Data) |  | 4.1985 | 0 | 0 | 0 | 0.32807 | 0.43388 | 0.40885 | 0.41727 | 0.42587 | 0.43464 | 0.44359 | 0.45273 | 0.46206 | 0.47158 | 0.48129 | 0.49121 | 0.50133 | 0.51166 | 0.5222 | 0.53296 | 0.54394 | 0.55515 | 0.56659 | 0.57826 | 0.59017 | 0.60233 | 0.60711 | 0.61962 | 0.63238 | 10.7556
|  | O&M | Poll Attachment Costs |  | 5.1929 | -0.13473 | -0.13756 | -0.14045 | 0.45163 | 0.50815 | 0.52005 | 0.53223 | 0.5447 | 0.55746 | 0.57052 | 0.58389 | 0.59758 | 0.61159 | 0.62593 | 0.6406 | 0.65563 | 0.671 | 0.68674 | 0.70286 | 0.71935 | 0.73623 | 0.75351 | 0.7712 | 0.7893 | 0.80783 | 0.8268 | 0.8451 | 0.86496 | 13.6253
|  | O&M | Customer Service and Other Overhead |  | 40.753 | 3.1649 | 3.2191 | 3.2744 | 3.3307 | 3.3882 | 3.4469 | 3.5067 | 3.5677 | 3.63 | 3.6935 | 3.7582 | 3.8243 | 3.8916 | 3.9604 | 4.0305 | 4.102 | 4.1749 | 4.2493 | 4.3251 | 4.4025 | 4.4815 | 4.562 | 4.6441 | 4.7279 | 4.8133 | 4.9005 | 4.9894 | 5.08 | 98.1696
|  | O&M | Field Work Reimbursements |  | -3.8456 | -0.95955 | -0.89959 | -0.86644 | -0.76694 | -0.63076 | -0.53862 | -0.44997 | -0.36246 | -0.27535 | -0.18801 | -0.099923 | -0.040247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6.0779
| Telecom and Other Costs |  | Total |  | 46.2989 | 2.0706 | 2.1819 | 2.2675 | 3.3435 | 3.6995 | 3.8372 | 4.0062 | 4.1758 | 4.3467 | 4.5196 | 4.6949 | 4.8437 | 4.9748 | 5.0676 | 5.1623 | 5.2589 | 5.3575 | 5.4582 | 5.561 | 5.6658 | 5.7728 | 5.8821 | 5.9936 | 6.1074 | 6.2235 | 6.3344 | 6.4541 | 6.5774 | 116.4726
|  |  | Total |  | 614.5118 | 25.4678 | 42.9712 | 50.0468 | 81.063 | 85.0925 | 67.4016 | 65.2948 | 64.6694 | 64.8369 | 65.3805 | 66.1846 | 58.6223 | 52.2394 | 34.2755 | 35.4234 | 36.5239 | 37.7479 | 38.9062 | 40.0657 | 41.221 | 42.3988 | 42.2364 | 43.7618 | 45.3453 | 46.989 | 48.6877 | 50.4578 | 52.2966 | 1274.1658
|  |  | Costs (real) |  | 614.5118 | 27.4467 | 39.873 | 43.0904 | 64.7633 | 63.0812 | 46.364 | 41.6765 | 38.3013 | 35.6319 | 33.3401 | 31.3168 | 25.7387 | 21.2826 | 12.9572 | 12.4257 | 11.888 | 11.4006 | 10.9032 | 10.4186 | 9.9462 | 9.4928 | 8.7747 | 8.4361 | 8.1111 | 7.7991 | 7.4985 | 7.2108 | 6.9348 | 634.46
| O&M Costs |  | O&M Costs |  | 90.5962 | 4.1678 | 4.5318 | 5.2425 | 6.2262 | 5.7703 | 6.2622 | 6.7947 | 7.3414 | 7.9055 | 8.4895 | 9.0958 | 9.5585 | 9.9461 | 10.2218 | 10.5059 | 10.7984 | 11.0999 | 11.4102 | 11.7294 | 12.0576 | 12.3951 | 12.7361 | 13.088 | 13.451 | 13.8256 | 14.2046 | 14.6024 | 15.0141 | 234.6515
| CAPEX |  | CAPEX |  | 429.2488 | -6.9147 | 7.4107 | 12.439 | 59.528 | 69.5578 | 53 | 51.572 | 51.6158 | 52.4875 | 53.7822 | 55.3958 | 48.3652 | 42.2933 | 24.0537 | 24.9174 | 25.7255 | 26.648 | 27.496 | 28.3363 | 29.1634 | 30.0037 | 29.5003 | 30.6739 | 31.8943 | 33.1633 | 34.483 | 35.8554 | 37.2825 | 892.1083
| L&G O&M |  | L&G O&M |  | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
BENEFITS
| Metering Net Benefits |  | Net Benefits |  | -1.4661 | 0.0019191 | 0.0017992 | -1.2666 | -35.6302 | -39.2143 | -21.4868 | -18.688 | -16.6049 | -15.0848 | -13.3293 | -11.6833 | -1.6312 | 7.2945 | 27.7467 | 28.9221 | 30.0031 | 31.1495 | 32.2667 | 33.4184 | 34.875 | 36.7413 | 39.4238 | 40.6785 | 42.1307 | 43.8867 | 45.6345 | 48.0851 | 49.1398 | 299.5521
| Net Benefits (real) |  | Net Benefits (real) |  | -1.4661 | 0.0020682 | 0.0016695 | -1.0905 | -28.4659 | -29.0706 | -14.7803 | -11.9282 | -9.8345 | -8.29 | -6.7971 | -5.5282 | -0.7162 | 2.9718 | 10.4891 | 10.1452 | 9.7656 | 9.4077 | 9.0425 | 8.6901 | 8.415 | 8.2262 | 8.1904 | 7.8417 | 7.5361 | 7.2842 | 7.0282 | 6.8717 | 6.5161 | 5.404
| Cumulative Net Benefits |  | Cumulative Net Benefits |  |  | 0.0020682 | 0.0037377 | -1.0868 | -29.5527 | -58.6233 | -73.4035 | -85.3318 | -95.1662 | -103.4563 | -110.2534 | -115.7817 | -116.4979 | -113.526 | -103.0369 | -92.8917 | -83.1262 | -73.7184 | -64.6759 | -55.9858 | -47.5708 | -39.3447 | -31.1543 | -23.3126 | -15.7765 | -8.4922 | -1.464 | 5.4077 | 11.9239
CORP MODEL INPUTS (AMI Metering ONLY)
| Total O&M | O&M | Total O&M | 0 | 185.263 | 32.3825 | 35.5604 | 37.6078 | 21.5351 | 15.5347 | 14.4017 | 13.7228 | 13.0536 | 12.3494 | 11.5984 | 10.7887 | 10.2571 | 9.9461 | 10.2218 | 10.5059 | 10.7984 | 11.0999 | 11.4102 | 11.7294 | 12.0576 | 12.3951 | 12.7361 | 13.088 | 13.451 | 13.8256 | 14.2046 | 14.6024 | 15.0141 | 382.0575
| Meter Capital | CAPEX | Meter Capital | #VALUE! | 403.0409 | -6.9147 | 7.4107 | 11.1706 | 49.7482 | 54.9583 | 51.926 | 50.5031 | 50.5357 | 51.3885 | 52.6588 | 54.2435 | 47.411 | 41.4726 | 23.5382 | 24.387 | 25.1805 | 26.0871 | 26.9196 | 27.7443 | 28.5557 | 29.3798 | 28.8567 | 30.0098 | 31.2091 | 32.4563 | 33.7533 | 35.1022 | 36.5049 | 850.8365
| Network Capital | CAPEX | Network | 0 | 26.208 | 0 | 0 | 1.2683 | 9.7798 | 14.5995 | 1.074 | 1.0689 | 1.0801 | 1.099 | 1.1234 | 1.1523 | 0.95424 | 0.82074 | 0.51549 | 0.5304 | 0.54503 | 0.56087 | 0.57633 | 0.59196 | 0.60772 | 0.62388 | 0.64361 | 0.66403 | 0.68518 | 0.70708 | 0.72976 | 0.75324 | 0.77757 | 40.7131
AMI Applications
Disconnect/Reconnect
|  | CAPEX | CIS Remote Disconnect and Prepay Enablement | #REF! | 1.6169 | 0 | 0 | 0.95 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.95
|  | O&M | Management Costs (Annual) | #REF! | 9.2158 | 0 | 0 | 0 | 0.5 | 0.539 | 0.58104 | 0.62636 | 0.67522 | 0.72789 | 0.78466 | 0.84587 | 0.91184 | 0.98297 | 1.0596 | 1.1423 | 1.2314 | 1.3274 | 1.431 | 1.5426 | 1.6629 | 1.7926 | 1.9324 | 2.0832 | 2.2457 | 2.4208 | 2.6097 | 2.8132 | 3.0326 | 27.0468
|  | Revenue | Credit Write offs from Electric Only Service Areas (Revenue) | #REF! | 138.4556 | 11.2392 | 11.4753 | 11.7162 | 11.7829 | 11.8165 | 11.8413 | 11.8951 | 11.9701 | 12.0633 | 12.1725 | 12.2958 | 12.432 | 12.6041 | 12.907 | 13.2163 | 13.532 | 13.8544 | 14.1835 | 14.5195 | 14.8626 | 15.2129 | 15.5706 | 15.9358 | 16.3086 | 16.6893 | 17.0779 | 17.4748 | 17.8799 | 332.0968
|  | Revenue | UEU Electric Write Offs (Revenue)$ |  | 16.2183 | 3.2953 | 3.3645 | 3.4352 | 3.1613 | 2.7993 | 2.3922 | 2.0154 | 1.6545 | 1.3045 | 0.96147 | 0.62209 | 0.2836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25.2893
|  | O&M | UEU Labor & Overhead (O&M) |  | 1.4047 | 0.26682 | 0.27243 | 0.27815 | 0.25711 | 0.22924 | 0.19787 | 0.16885 | 0.14108 | 0.11416 | 0.087779 | 0.061693 | 0.035682 | 0.01394 | 0.014233 | 0.014532 | 0.014837 | 0.015149 | 0.015467 | 0.015791 | 0.016123 | 0.016462 | 0.016807 | 0.01716 | 0.017521 | 0.017889 | 0.018264 | 0.018648 | 0.019039 | 2.3168
| Disconnect/Reconnect Total |  | Total | #REF! | 166.9113 | 14.8014 | 15.1122 | 16.3795 | 16.7013 | 15.384 | 15.0124 | 14.7058 | 14.4409 | 14.2099 | 14.0064 | 13.8255 | 13.6631 | 13.6011 | 13.9809 | 14.3731 | 14.7782 | 15.1969 | 15.6299 | 16.0779 | 16.5417 | 17.022 | 17.5198 | 18.0361 | 18.5718 | 19.128 | 19.7058 | 20.3066 | 20.9316 | 388.6997
|  |  | Net Benefit |  | 30.603 | 0 | 0 | -0.95 | -0.94772 | 0.70036 | 1.4097 | 2.0613 | 2.6782 | 3.2688 | 3.8393 | 4.395 | 4.9399 | 5.3927 | 5.4117 | 5.4268 | 5.4374 | 5.4432 | 5.4437 | 5.4383 | 5.4263 | 5.4073 | 5.3805 | 5.3452 | 5.3005 | 5.2456 | 5.1796 | 5.1014 | 5.01 | -363.8143
CVR
|  | CAPEX | Upgrade Costs |  | 15.5066 | 0.25707 | 0.52699 | 0.54017 | 1.1073 | 1.135 | 1.1634 | 1.59 | 1.8335 | 1.8793 | 1.9263 | 1.9744 | 2.0238 | 2.0744 | 2.1262 | 2.1794 | 2.2339 | 2.2897 | 2.347 | 2.4056 | 2.4658 | 1.685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35.7642
|  | O&M | Management Costs |  | 18.7605 | 0.195 | 0.29213 | 0.39398 | 0.50075 | 0.61262 | 0.72976 | 0.88717 | 1.0698 | 1.261 | 1.4612 | 1.6705 | 1.8894 | 2.1182 | 2.3573 | 2.6069 | 2.8676 | 3.1397 | 3.4236 | 3.7198 | 4.0286 | 4.2768 | 4.3837 | 4.4933 | 4.6056 | 4.7208 | 4.8388 | 4.9598 | 5.0838 | 57.7053
| CVR Costs |  | Total |  | 34.2671 | 0.45207 | 0.81912 | 0.93415 | 1.6081 | 1.7476 | 1.8932 | 2.4772 | 2.9033 | 3.1403 | 3.3874 | 3.6449 | 3.9132 | 4.1926 | 4.4835 | 4.7863 | 5.1015 | 5.4295 | 5.7706 | 6.1254 | 6.4944 | 5.9617 | 4.3837 | 4.4933 | 4.6056 | 4.7208 | 4.8388 | 4.9598 | 5.0838 | 93.4696
|  | O&M | Annual Peak Savings EOL ($) |  | -34.7542 | 0 | -0.082922 | -0.25498 | -0.4356 | -0.84833 | -1.0984 | -1.3604 | -1.7149 | -2.1274 | -2.5595 | -3.0118 | -3.4852 | -3.9803 | -4.498 | -5.0391 | -5.6045 | -6.1949 | -6.8114 | -7.4549 | -8.1262 | -8.8265 | -9.3869 | -9.6215 | -9.8621 | -10.1086 | -10.3613 | -10.6204 | -10.8859 | -112.4943
|  | O&M | Annual Energy Savings EOL($) |  | -60.023 | 0 | -0.12012 | -0.37645 | -0.64706 | -1.3053 | -1.7604 | -2.2226 | -2.8702 | -3.4153 | -4.2564 | -5.312 | -6.044 | -6.2418 | -7.2509 | -8.3108 | -9.1409 | -10.6722 | -12.0941 | -13.6917 | -15.3488 | -16.4452 | -17.2498 | -17.437 | -17.6242 | -17.8113 | -17.9985 | -18.1856 | -18.3728 | -197.6486
| CVR Benefits |  | Total |  | -94.7772 | 0 | -0.20304 | -0.63144 | -1.0827 | -2.1537 | -2.8587 | -3.5829 | -4.5851 | -5.5427 | -6.8159 | -8.3238 | -9.5292 | -10.2221 | -11.7489 | -13.3499 | -14.7454 | -16.8672 | -18.9056 | -21.1465 | -23.475 | -25.2717 | -26.6367 | -27.0585 | -27.4862 | -27.9199 | -28.3598 | -28.806 | -29.2586 | -310.1429
|  |  | Net Benefit |  | 12.8198
Outage
|  | O&M | Automated analysis of system status including outage device prediction | 109.2718 | 60.0041 | 4.5967 | 4.6932 | 4.7918 | 4.8924 | 4.9764 | 5.0577 | 5.1389 | 5.2241 | 5.3123 | 5.4035 | 5.4972 | 5.5935 | 5.6923 | 5.7967 | 5.9184 | 6.0427 | 6.1696 | 6.2992 | 6.4315 | 6.5665 | 6.7044 | 6.8452 | 6.989 | 7.1357 | 7.2856 | 7.4386 | 7.5948 | 7.7543 | 145.0547
|  | O&M | Electric First Response (EFR) Investigations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | O&M | Storm Response Costs | 293.646 | 161.3751 | 12.1696 | 12.4251 | 12.686 | 12.9524 | 13.2102 | 13.4699 | 13.7336 | 14.0047 | 14.2824 | 14.5667 | 14.8576 | 15.155 | 15.459 | 15.7721 | 16.1033 | 16.4415 | 16.7867 | 17.1392 | 17.4992 | 17.8667 | 18.2418 | 18.6249 | 19.0161 | 19.4154 | 19.8231 | 20.2394 | 20.6644 | 21.0984 | 391.7021
|  | O&M | Non-storm response Costs | 58.7301 | 31.6739 | 3.307 | 3.3765 | 3.4474 | 3.5198 | 3.419 | 3.2746 | 3.1101 | 2.963 | 2.8253 | 2.694 | 2.5668 | 2.4423 | 2.3192 | 2.2268 | 2.2736 | 2.3213 | 2.37 | 2.4198 | 2.4706 | 2.5225 | 2.5755 | 2.6296 | 2.6848 | 2.7412 | 2.7987 | 2.8575 | 2.9175 | 2.9788 | 69.2994
|  | O&M | SAIDI Fines | 15.4696 | 8.4893 | 0.65867 | 0.6725 | 0.68663 | 0.70105 | 0.71156 | 0.72129 | 0.73081 | 0.74104 | 0.75178 | 0.76297 | 0.77457 | 0.78653 | 0.79885 | 0.81222 | 0.82928 | 0.84669 | 0.86447 | 0.88263 | 0.90116 | 0.92009 | 0.93941 | 0.95914 | 0.97928 | 0.99984 | 1.0208 | 1.0423 | 1.0642 | 1.0865 | 20.4533
| Outage Total |  | Total | 477.1174 | 261.5425 | 20.732 | 21.1673 | 21.6118 | 22.0657 | 22.3171 | 22.5235 | 22.7135 | 22.9328 | 23.1719 | 23.4271 | 23.6962 | 23.9774 | 24.2693 | 24.6078 | 25.1245 | 25.6522 | 26.1909 | 26.7409 | 27.3024 | 27.8758 | 28.4612 | 29.0589 | 29.6691 | 30.2921 | 30.9283 | 31.5778 | 32.2409 | 32.918 | 626.5096
|  |  | Net Benefit |  | 15.1118
Totals
| Applications Total |  |  |  | 367.9437 | 35.9854 | 36.8956 | 38.2941 | 39.2924 | 37.2951 | 36.5704 | 36.3135 | 35.6918 | 34.9793 | 34.005 | 32.8428 | 32.0245 | 31.8409 | 31.3233 | 30.934 | 30.7865 | 29.9501 | 29.2358 | 28.3592 | 27.4368 | 26.1732 | 24.3257 | 25.14 | 25.9833 | 26.8571 | 27.7626 | 28.7013 | 29.6747 | 798.536
| Application Net Benefits |  |  |  | 58.5346 | 0 | 0 | -0.95 | -1.5014 | 0.91156 | 2.0214 | 2.9029 | 3.8784 | 4.9019 | 5.9698 | 7.069 | 8.0876 | 8.9024 | 9.4282 | 9.7975 | 10.118 | 10.5874 | 11.0328 | 11.5143 | 12.007 | 12.8021 | 13.9564 | 14.0724 | 14.1817 | 14.2834 | 14.3766 | 14.4604 | 14.5337 | 185.9746
Financial Results
| Costs |  |  |  | -102.5021 | 0.0019191 | 0.0017992 | -2.2166 | -37.1316 | -38.3028 | -19.4654 | -15.7852 | -12.7265 | -10.1829 | -7.3595 | -4.6143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| Benefits |  |  |  | 159.5706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.4564 | 16.1969 | 37.1749 | 38.7196 | 40.1211 | 41.7369 | 43.2996 | 44.9327 | 46.882 | 49.5434 | 53.3802 | 54.7509 | 56.3124 | 58.17 | 60.0111 | 62.5455 | 63.6736
| Hybrid AMI Costs |  |  |  | 982.4555 | 61.4532 | 79.8668 | 88.3409 | 120.3554 | 122.3876 | 103.972 | 101.6083 | 100.3613 | 99.8163 | 99.3855 | 99.0274 | 90.6468 | 84.0803 | 65.5988 | 66.3574 | 67.3105 | 67.698 | 68.142 | 68.4249 | 68.6578 | 68.572 | 66.5621 | 68.9018 | 71.3286 | 73.8461 | 76.4503 | 79.1591 | 81.9713 | 2072.7018
| Net Benefits |  | Net Benefits |  | 57.0685 | 0.0019191 | 0.0017992 | -2.2166 | -37.1316 | -38.3028 | -19.4654 | -15.7852 | -12.7265 | -10.1829 | -7.3595 | -4.6143 | 6.4564 | 16.1969 | 37.1749 | 38.7196 | 40.1211 | 41.7369 | 43.2996 | 44.9327 | 46.882 | 49.5434 | 53.3802 | 54.7509 | 56.3124 | 58.17 | 60.0111 | 62.5455 | 63.6736 | 485.5266
| Net Benefits (real) |  | Net Benefits (real) |  | 57.0685 | 0.0020682 | 0.0016695 | -1.9085 | -29.6654 | -28.3948 | -13.3898 | -10.0754 | -7.5374 | -5.5962 | -3.7529 | -2.1834 | 2.8347 | 6.5987 | 14.0533 | 13.5819 | 13.0588 | 12.6053 | 12.1344 | 11.6842 | 11.3122 | 11.0925 | 11.0898 | 10.5545 | 10.0729 | 9.655 | 9.2424 | 8.9382 | 8.4434 | 47.8282
| Cumulative Net Benefits |  | Cumulative Net Benefits |  | -922.9276 | 0.0020682 | 0.0037377 | -1.9048 | -31.5702 | -59.965 | -73.3548 | -83.4302 | -90.9676 | -96.5638 | -100.3167 | -102.5001 | -99.6653 | -93.0666 | -79.0133 | -65.4315 | -52.3726 | -39.7673 | -27.6329 | -15.9486 | -4.6364 | 6.456 | 17.5458 | 28.1004 | 38.1732 | 47.8282 | 57.0706 | 66.0088 | 74.4522
CORP MODEL INPUTS (AMI Metering AND Applications)
| Total O&M |  | Total O&M | 0 | 536.0832 | 68.1108 | 71.929 | 74.4118 | 58.7201 | 51.6948 | 49.8086 | 48.4463 | 46.912 | 45.4494 | 43.6771 | 41.6572 | 40.2578 | 39.7126 | 39.4188 | 39.2606 | 39.3511 | 38.7603 | 38.299 | 37.683 | 37.0286 | 36.8834 | 37.0618 | 38.2279 | 39.4343 | 40.6828 | 41.9673 | 43.3037 | 44.6888 | 1142.8792
| Meter Capital |  | Meter Capital | 0 | 403.0409 | -6.9147 | 7.4107 | 11.1706 | 49.7482 | 54.9583 | 51.926 | 50.5031 | 50.5357 | 51.3885 | 52.6588 | 54.2435 | 47.411 | 41.4726 | 23.5382 | 24.387 | 25.1805 | 26.0871 | 26.9196 | 27.7443 | 28.5557 | 29.3798 | 28.8567 | 30.0098 | 31.2091 | 32.4563 | 33.7533 | 35.1022 | 36.5049 | 850.8365
| Network/Substation Capital |  | Network | 0 | 43.3315 | 0.25707 | 0.52699 | 2.7585 | 11.8871 | 15.7345 | 2.2374 | 2.6589 | 2.9136 | 2.9783 | 3.0496 | 3.1268 | 2.978 | 2.8951 | 2.6417 | 2.7098 | 2.7789 | 2.8506 | 2.9233 | 2.9976 | 3.0735 | 2.3088 | 0.64361 | 0.66403 | 0.68518 | 0.70708 | 0.72976 | 0.75324 | 0.77757 | 78.4273
982.4555
Note on C8: vdrehe: Default is the value of the contract based on a per read fee.
Note on C30: vdrehe: This is the cost of the contract based on asset values.

## Incriment (hidden)
Accelerated Gridstream Scenario
| ($Millions) |  | NPV | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026
Year
COSTS
|  | Year of Deployment |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| L+G Managed Service Contract (Accelerated Gridstream Scenario Supported Meters) | L+G Managed Service Contract (Accelerated Gridstream Scenario Supported Meters) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | L+G Managed Service Contract (Savings over Status Quo) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | Incremental Cost of Electric Meters | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | Incremental Cost of Gas Modules | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | Incremental Cost of Electric Meter Exchanges | #VALUE! | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
|  | Incremental Cost of Gas Module Exchanges | #VALUE! | 0 | 0 | 0 | #VALUE! | 3.7464 | 4.0629 | 4.2677 | 4.0769 | 4.0615 | 4.2041 | 4.3773 | 4.5637 | 4.7318 | 4.9015 | 5.0806 | #VALUE!
| Incremental Meter Hardware and Exchange Costs |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | AMI Network Hardware (Initial capital) | #VALUE! | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
|  | AMI Network Deployment (initial installation) | #VALUE! | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
| NOC Head End Costs | Set-up and Installation of Command Center | #VALUE! | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Project Management & Ongoing Support | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Total | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | Costs (real) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
5-Year Snapshot (2014-2018) (nominal $)
|  | 5 Year Costs | #VALUE!
|  | 5-Year Network Deployment | #VALUE!
|  | 5-Year Contract Savings | #VALUE!
BENEFITS

## Two Networks (R)
2-Two Vendors, Two Networks
should add line for stopped meter benefits
|  | ($Millions) |  |  |  | NPV | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
|  | Year |  |  |  |  | -1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
|  | COSTS | CAPEX VS O&M
|  |  |  | Year of Deployment |  |  | -1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
|  | L+G Managed Service Contract | O&M | L+G Managed Service Contract | This is based on the (read fees) X (annual AMR supported meters). It does not include AMI meters. | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
0
|  |  | CAPEX | AMR Electric Meter Hardware (Growth) | Continues in non-AMI areas until 2016 | 2.6769 | -1.5776 | 0.6574 | 1.2489 | 1.2411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5698
|  |  | CAPEX | AMR Electric Meter Hardware (Maintenance) | Continues in non-AMI areas until 2016 | 0.76656 | 0.2256 | 0.30188 | 0.31488 | 0.26953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1119
|  |  | CAPEX | AMR Electric Meter Hardware (Redeployed) | Continues in non-AMI areas until 2016 | 0 | [28 empty] | 0
|  |  | CAPEX | AMR Electric Meter Exchange (Growth) | Continues in non-AMI areas until 2016 | 2.0372 | -1.4443 | 0.60126 | 1.1411 | 0.6218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.91989
|  |  | O&M | AMR Electric Meter Exchange (Maintenance) | Continues in non-AMI areas until 2016 | 0.61179 | 0.20653 | 0.2761 | 0.2877 | 0.13504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.90537
|  |  | CAPEX | AMR Gas Meter Hardware (Growth) | Continues in non-AMI areas until 2016 | 8.4506 | -2.8151 | 2.6901 | 4.1151 | 3.0182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.0083
|  |  | CAPEX | AMR Gas Meter Hardware (Maintenance) | Continues in non-AMI areas until 2016 | 2.2746 | 0.96052 | 0.99899 | 1.0479 | 0.55745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5649
|  |  | CAPEX | AMR Gas Meter Exchange (Growth) | Continues in non-AMI areas until 2016 | 6.3455 | -2.2638 | 2.1611 | 3.3027 | 1.8732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.0732
|  |  | O&M | AMR Gas Meter Exchange (Maintenance) | Continues in non-AMI areas until 2016 | 1.7452 | 0.7724 | 0.80254 | 0.84105 | 0.34597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.762
|  |  | CAPEX | AMR Gas Modules for Maintenance | No modules ever purchased by PSE. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O&M | AMR Gas Module Exchanges | Only through 2015. | 0.66371 | 0.31807 | 0.31553 | 0.31574 | 0.12402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0734
|  |  | O&M | AMR Gas Module Visits | Only through 2015. | 1.0768 | 0.51603 | 0.51191 | 0.51224 | 0.20121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7414
|  |  | O&M | Battery Costs |  | 2.005 | 0.28415 | 0.44381 | 1.0183 | 0.89673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.643
|  | AMR Meter/Module Costs |  | Total |  | 28.6538 | -4.8175 | 9.7606 | 14.1456 | 9.2842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.373
|  | 90% of Hybrid AMI costs | CAPEX | AMI Electric Meter Hardware (Growth) | Begins in 2013, inclds all growth 2016 on. | 131.3043 | 0 | 0 | 0 | 15.554 | 19.9998 | 22.3651 | 21.1317 | 20.619 | 20.4118 | 20.4128 | 20.5767 | 20.8521 | 18.0682 | 3.7033 | 3.8213 | 3.9295 | 4.055 | 4.1704 | 4.2842 | 4.3948 | 4.5082 | 5.6669 | 5.8948 | 6.1319 | 6.3785 | 6.6351 | 6.902 | 7.1796 | 256.9298
|  | 90% of Hybrid AMI costs | CAPEX | AMI Electric Meter Hardware (Maintenance) | Begins in 2013, inclds all maintenance 2016 on. | 5.0998 | 0 | 0 | 0 | 0.052883 | 0.12199 | 0.2006 | 0.27666 | 0.35257 | 0.42938 | 0.5078 | 0.58842 | 0.67167 | 0.74721 | 0.77549 | 0.80477 | 0.83503 | 0.86635 | 0.89873 | 0.93217 | 0.96668 | 1.0023 | 1.0426 | 1.0846 | 1.1282 | 1.1736 | 1.2208 | 1.2699 | 1.321 | 15.4597
|  |  | CAPEX | AMI Electric Meter Exchange (Growth) | Begins in 2013, inclds all growth 2016 on. | 32.2648 | 0 | 0 | 0 | 3.3875 | 4.8961 | 5.6497 | 5.1033 | 4.8163 | 4.6367 | 4.5289 | 4.4759 | 4.4593 | 3.9743 | 1.3279 | 1.3689 | 1.4063 | 1.4497 | 1.4895 | 1.5287 | 1.5666 | 1.6055 | 2.0161 | 2.0952 | 2.1773 | 2.2627 | 2.3514 | 2.4436 | 2.5394 | 66.2226
|  |  | O&M | AMI Electric Meter Exchange (Maintenance) | Begins in 2013, inclds all maintenance 2016 on. | 1.8259 | 0 | 0 | 0 | 0.019149 | 0.044131 | 0.072495 | 0.099885 | 0.12717 | 0.15472 | 0.1828 | 0.21161 | 0.24132 | 0.26819 | 0.27807 | 0.28829 | 0.29884 | 0.30974 | 0.321 | 0.33262 | 0.3446 | 0.35695 | 0.37094 | 0.38548 | 0.4006 | 0.4163 | 0.43262 | 0.44958 | 0.46721 | 5.5249
|  | 90% of Hybrid AMI costs | CAPEX | AMI Gas Meter/Module Hardware (Growth) | Begins in 2013 | 67.9768 | 0 | 0 | 0 | 3.0278 | 6.5737 | 6.9119 | 6.6092 | 6.5908 | 6.8289 | 7.1171 | 7.4276 | 7.7086 | 7.9929 | 8.2932 | 8.5907 | 8.861 | 9.1785 | 9.4579 | 9.7305 | 9.9942 | 10.2593 | 8.8507 | 9.2067 | 9.577 | 9.9623 | 10.363 | 10.7798 | 11.2134 | 178.7508
This is probably overstated with a new gas solution |  | 90% of Hybrid AMI costs | CAPEX | AMI Gas Meter/Module Hardware (Maintenance) | Begins in 2013 | 18.2722 | 0 | 0 | 0 | 0.34375 | 0.68811 | 0.89776 | 1.1215 | 1.3597 | 1.6132 | 1.8826 | 2.169 | 2.3261 | 2.4353 | 2.5491 | 2.6676 | 2.7905 | 2.9185 | 3.0512 | 3.1888 | 3.3313 | 3.4788 | 3.6187 | 3.7643 | 3.9157 | 4.0732 | 4.237 | 4.4074 | 4.5847 | 54.1846
|  |  | CAPEX | AMI Gas Meter Exchange (Growth) | Begins in 2013 | 41.6794 | 0 | 0 | 0 | 1.8732 | 4.0629 | 4.2677 | 4.0769 | 4.0615 | 4.2041 | 4.3773 | 4.5637 | 4.7318 | 4.9015 | 5.0806 | 5.2578 | 5.4179 | 5.6065 | 5.7715 | 5.9321 | 6.0869 | 6.2421 | 5.3799 | 5.5908 | 5.81 | 6.0377 | 6.2744 | 6.5204 | 6.776 | 109.3344
this is probably overstated with a new gas solution |  |  | O&M | AMI Gas Meter Exchange (Maintenance) | Begins in 2013 | 10.0632 | 0 | 0 | 0 | 0.1914 | 0.38276 | 0.49889 | 0.62259 | 0.7541 | 0.89381 | 1.0421 | 1.1994 | 1.285 | 1.3441 | 1.4055 | 1.4694 | 1.5356 | 1.6044 | 1.6758 | 1.7496 | 1.826 | 1.905 | 1.9796 | 2.0573 | 2.1379 | 2.2217 | 2.3088 | 2.3993 | 2.4934 | 29.7819
We might want to reach out to Itron/Aclara and get a budgetary proposal from them to fill in this gap. How does the SilverSpring # compare to L+G's for gas modules? |  | 90% of Hybrid AMI costs | CAPEX | New AMI Gas Modules (Deployments) |  | 42.3691 | 0 | 0 | 0 | 12.0513 | 11.6259 | 5.7819 | 6.2645 | 6.6679 | 7.0093 | 7.3539 | 7.7113 | 2.156 | 0 | 0 | 0 | 0 | 0 | -1.1995e-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66.622
We might want to reach out to Itron/Aclara and get a budgetary proposal from them to fill in this gap. How does the SilverSpring # compare to L+G's for gas modules? |  |  | CAPEX | New AMI Gas Module Exchanges (Deployments) |  | 11.3149 | 0 | 0 | 0 | 2.4145 | 2.6267 | 1.7964 | 1.9389 | 2.0567 | 2.1554 | 2.2583 | 2.3657 | 0.6624 | 0.0022727 | 0 | 0 | 0 | 0 | -1.8622e-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.2773
this is probably overstated with a new gas solution |  |  | O&M | AMI Gas Module Visits |  | 0.58524 | 0 | 0 | 0 | 0.011131 | 0.02226 | 0.029014 | 0.036207 | 0.043856 | 0.05198 | 0.060605 | 0.069754 | 0.074733 | 0.078166 | 0.081739 | 0.085453 | 0.089304 | 0.093307 | 0.097456 | 0.10175 | 0.10619 | 0.11079 | 0.11513 | 0.11964 | 0.12433 | 0.12921 | 0.13427 | 0.13954 | 0.14501 | 1.732
this is probably overstated with a new gas solution |  | 90% of Hybrid AMI costs | CAPEX | AMI Gas Modules (Maintenance) |  | 2.7916 | 0 | 0 | 0 | 0.052517 | 0.10513 | 0.13716 | 0.17133 | 0.20773 | 0.24645 | 0.28763 | 0.33137 | 0.35537 | 0.37206 | 0.38945 | 0.40754 | 0.42633 | 0.44588 | 0.46616 | 0.48718 | 0.50895 | 0.53148 | 0.55286 | 0.57509 | 0.59822 | 0.62229 | 0.64732 | 0.67335 | 0.70044 | 8.2782
this is probably overstated with a new gas solution |  |  | O&M | AMI Gas Module Exchanges (Maintenance) |  | 0.78227 | 0 | 0 | 0 | 0.014878 | 0.029754 | 0.038781 | 0.048397 | 0.05862 | 0.06948 | 0.081008 | 0.093238 | 0.099893 | 0.10448 | 0.10926 | 0.11422 | 0.11937 | 0.12472 | 0.13027 | 0.13601 | 0.14194 | 0.14808 | 0.15389 | 0.15992 | 0.16619 | 0.17271 | 0.17948 | 0.18651 | 0.19383 | 2.3151
|  |  | O&M | FTE to Manage Inventory/Testing |  | 1.6884 | 0 | 0 | 0 | 0.1576 | 0.16075 | 0.16397 | 0.16725 | 0.17059 | 0.17401 | 0.17749 | 0.18104 | 0.18466 | 0.18835 | 0.19212 | 0.19596 | 0.19988 | 0.20388 | 0.20795 | 0.21211 | 0.21635 | 0.22068 | 0.22509 | 0.2296 | 0.23419 | 0.23887 | 0.24365 | 0.24852 | 0.25349 | 4.3024
in this section, can you distinguish "Labor" from "material". It isn't clear. |  | AMI Meter/Module Costs |  | Total |  | 368.018 | 0 | 0 | 0 | 39.1515 | 51.34 | 48.8114 | 47.6683 | 47.8867 | 48.8793 | 50.2704 | 51.9648 | 45.809 | 40.4771 | 24.1858 | 25.0718 | 25.9095 | 26.8566 | 27.738 | 28.6157 | 29.4846 | 30.3691 | 29.9725 | 31.1633 | 32.4015 | 33.689 | 35.0278 | 36.4199 | 37.8674 | 817.7157
0
|  | 1.3 X Hybrid AMI costs | CAPEX | AMI Network Installation (Hardware) |  | 15.8113 | 0 | 0 | 0 | 7.9792 | 12.7293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20.7085
|  | 1.3 X Hybrid AMI costs | CAPEX | AMI Network Installation (Labor) |  | 4.5702 | 0 | 0 | 0 | 2.3064 | 3.6794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.9858
|  | 1.3 X Hybrid AMI costs | CAPEX | AMI Network maintenance (Hardware) |  | 3.6008 | 0 | 0 | 0 | 0.33327 | 0.34027 | 0.34742 | 0.35471 | 0.36216 | 0.36977 | 0.37753 | 0.38546 | 0.39356 | 0.40182 | 0.41026 | 0.41888 | 0.42767 | 0.43665 | 0.44582 | 0.45518 | 0.46474 | 0.4745 | 0.48447 | 0.49464 | 0.50503 | 0.51563 | 0.52646 | 0.53752 | 0.54881 | 9.1995
|  | 1.3 X Hybrid AMI costs | O&M | AMI Network maintenance (Labor) |  | 9.8196 | 0 | 0 | 0 | 0.47605 | 0.97115 | 0.99057 | 1.0104 | 1.0306 | 1.0512 | 1.0722 | 1.0937 | 1.1155 | 1.1379 | 1.1606 | 1.1838 | 1.2075 | 1.2317 | 1.2563 | 1.2814 | 1.307 | 1.3332 | 1.3598 | 1.387 | 1.4148 | 1.4431 | 1.4719 | 1.5014 | 1.5314 | 25.5155
|  |  | O&M | Manual Meter Reading |  | 0.85023 | 0 | 0 | 0 | 0.065529 | 0.068535 | 0.07161 | 0.074661 | 0.077761 | 0.080972 | 0.08431 | 0.087781 | 0.091382 | 0.095117 | 0.098992 | 0.10301 | 0.10717 | 0.11148 | 0.11594 | 0.12054 | 0.1253 | 0.13021 | 0.13532 | 0.14062 | 0.14614 | 0.15187 | 0.15782 | 0.16401 | 0.17044 | 2.2842
|  |  | O&M | Network Overhead and management |  | 4.9708 | 0 | 0 | 0 | 0.3546 | 0.48226 | 0.49191 | 0.50175 | 0.51178 | 0.52202 | 0.53246 | 0.54311 | 0.55397 | 0.56505 | 0.57635 | 0.58788 | 0.59963 | 0.61163 | 0.62386 | 0.63634 | 0.64906 | 0.66204 | 0.67528 | 0.68879 | 0.70257 | 0.71662 | 0.73095 | 0.74557 | 0.76048 | 12.7889
|  |  |  | Cost of Implimentation of Disconnect/Reconnect Program |  | 0 | [28 empty] | 0
|  |  |  | Cost of Maintaining Disconnect/Reconnect Program |  | 0 | [28 empty] | 0
|  | Network Costs |  | Total |  | 39.6229 | 0 | 0 | 0 | 11.515 | 18.2709 | 1.9015 | 1.9415 | 1.9823 | 2.024 | 2.0665 | 2.11 | 2.1545 | 2.1998 | 2.2462 | 2.2936 | 2.342 | 2.3914 | 2.4419 | 2.4935 | 2.5461 | 2.5999 | 2.6549 | 2.7111 | 2.7685 | 2.8272 | 2.8872 | 2.9485 | 3.0111 | 76.4823
|  |  | CAPEX | Software Licence Fee (per endpoint, one time) |  | 5.3788 | 0 | 0 | 0 | 0.88293 | 0.97078 | 0.8003 | 0.7882 | 0.7923 | 0.80379 | 0.8206 | 0.84177 | 0.63565 | 0.49388 | 0.18012 | 0.18625 | 0.19185 | 0.19838 | 0.20424 | 0.20999 | 0.21556 | 0.22121 | 0.2301 | 0.23936 | 0.24899 | 0.259 | 0.26942 | 0.28026 | 0.29153 | 10.4152
|  | 2 X the Hybrid AMI cost | CAPEX | Set-up and Installation of Command Center and Second Head End System for Gas |  | 0.082475 | 0 | 0 | 0.09579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
probably need to double this. | Looking into refresh rate and is refresh capex? | 2 X the Hybrid AMI cost | CAPEX | ECC Security Head End Appliances (Per Set) - Requires 1-set each for production, Disaster Recovery, testing (one time cost) |  | 0.87974 | 0 | 0 | 1.0218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O&M | Software Maintenance Fee (per endpoint/year) |  | 12.3606 | 0 | 0 | 0 | 0.17659 | 0.37445 | 0.54237 | 0.7114 | 0.8848 | 1.0641 | 1.2506 | 1.4452 | 1.6027 | 1.7351 | 1.8076 | 1.8828 | 1.9607 | 2.0416 | 2.1253 | 2.2119 | 2.3015 | 2.3941 | 2.4903 | 2.5905 | 2.6947 | 2.8031 | 2.9159 | 3.0331 | 3.1551
|  | 2X Hybrid AMI costs | CAPEX | Deployment Project Management |  | 16.8764 | 0 | 0 | 1.4191 | 1.4489 | 1.4793 | 1.5104 | 1.5421 | 1.5745 | 1.6076 | 1.6413 | 1.6758 | 1.711 | 1.7469 | 1.7836 | 1.8211 | 1.8593 | 1.8984 | 1.9382 | 1.9789 | 2.0205 | 2.0629 | 2.1062 | 2.1505 | 2.1956 | 2.2417 | 2.2888 | 2.3369 | 2.3859 | 41.4139
|  | NOC Head End Costs |  | Total |  | 35.578 | 0 | 0 | 2.5367 | 2.5084 | 2.8246 | 2.8531 | 3.0417 | 3.2516 | 3.4755 | 3.7125 | 3.9628 | 3.9493 | 3.9759 | 3.7713 | 3.8901 | 4.0119 | 4.1383 | 4.2678 | 4.4008 | 4.5375 | 4.6782 | 4.8267 | 4.9803 | 5.1393 | 5.3038 | 5.4741 | 5.6503 | 5.8326 | 90.0382
|  |  |  | Testing/Security |  | 0
increase by 1/3 due to overlapping in combined territory | Done | 30% More than Hybrid AMI Costs | O&M | Backhaul Costs (Licences and Data) |  | 5.458 | 0 | 0 | 0 | 0.42649 | 0.56405 | 0.53151 | 0.54245 | 0.55363 | 0.56503 | 0.57667 | 0.58855 | 0.60068 | 0.61305 | 0.62568 | 0.63857 | 0.65173 | 0.66515 | 0.67886 | 0.69285 | 0.70712 | 0.72169 | 0.73656 | 0.75174 | 0.76723 | 0.78303 | 0.78925 | 0.8055 | 0.8221 | 13.9823
increase by 1/3 due to overlapping in combined territory | Done | 30% More than Hybrid AMI Costs | O&M | Pole Attachment Costs |  | 6.8254 | -0.13473 | -0.13756 | -0.14045 | 0.58711 | 0.6606 | 0.67607 | 0.6919 | 0.70811 | 0.7247 | 0.74168 | 0.75906 | 0.77685 | 0.79506 | 0.81371 | 0.83279 | 0.85231 | 0.87231 | 0.89277 | 0.91371 | 0.93515 | 0.9571 | 0.97956 | 1.0026 | 1.0261 | 1.0502 | 1.0748 | 1.0986 | 1.1244 | 17.8366
evaluate this line for possible benefits from a new gas solution | ?? |  | O&M | Customer Service and Other Overhead |  | 40.753 | 3.1649 | 3.2191 | 3.2744 | 3.3307 | 3.3882 | 3.4469 | 3.5067 | 3.5677 | 3.63 | 3.6935 | 3.7582 | 3.8243 | 3.8916 | 3.9604 | 4.0305 | 4.102 | 4.1749 | 4.2493 | 4.3251 | 4.4025 | 4.4815 | 4.562 | 4.6441 | 4.7279 | 4.8133 | 4.9005 | 4.9894 | 5.08 | 98.1696
|  | Discontinued post 2016 | O&M | Field Work Reimbursements |  | -2.1935 | -1: -0.95955; 1: -0.89959; 2: -0.86644; 3: -0.76694 | -3.4925
|  | Telecom and Other Costs |  | Total |  | 50.843 | 2.0706 | 2.1819 | 2.2675 | 3.5774 | 4.6129 | 4.6545 | 4.7411 | 4.8295 | 4.9197 | 5.0118 | 5.1058 | 5.2018 | 5.2998 | 5.3998 | 5.5018 | 5.606 | 5.7123 | 5.8209 | 5.9317 | 6.0448 | 6.1603 | 6.2781 | 6.3984 | 6.5212 | 6.6465 | 6.7646 | 6.8935 | 7.0266 | 126.496
|  |  |  | Total |  | 617.3825 | 25.4678 | 42.9712 | 51.3151 | 81.3455 | 86.8128 | 66.3599 | 64.3207 | 63.6623 | 63.7424 | 64.1701 | 64.8363 | 57.8132 | 51.9526 | 35.6031 | 36.7573 | 37.8693 | 39.0986 | 40.2685 | 41.4417 | 42.613 | 43.8074 | 43.7321 | 45.2531 | 46.8305 | 48.4666 | 50.1536 | 51.9121 | 53.7377 | 1286.5113
|  |  |  | Costs (real) |  | 617.3825 | 27.4467 | 39.873 | 44.1824 | 64.989 | 64.3564 | 45.6474 | 41.0547 | 37.7048 | 35.0304 | 32.7229 | 30.6789 | 25.3834 | 21.1657 | 13.4591 | 12.8936 | 12.3259 | 11.8085 | 11.285 | 10.7764 | 10.2821 | 9.8082 | 9.0854 | 8.7236 | 8.3768 | 8.0444 | 7.7242 | 7.4186 | 7.1258 | 637.105
|  | O&M Costs |  | O&M Costs |  | 99.8917 | 4.1678 | 4.5318 | 5.2425 | 6.7473 | 7.1489 | 7.5541 | 8.0136 | 8.4887 | 8.982 | 9.4954 | 10.0307 | 10.451 | 10.8162 | 11.11 | 11.4126 | 11.724 | 12.0447 | 12.3747 | 12.714 | 13.0628 | 13.4212 | 13.7836 | 14.1573 | 14.5426 | 14.94 | 15.34 | 15.7611 | 16.197 | 256.9576
|  | CAPEX |  | CAPEX |  | 422.824 | -6.9147 | 7.4107 | 13.7073 | 59.2893 | 69.8994 | 50.6664 | 49.379 | 49.4613 | 50.3164 | 51.5659 | 53.1127 | 46.6636 | 41.1365 | 24.4931 | 25.3447 | 26.1453 | 27.0539 | 27.8938 | 28.7277 | 29.5502 | 30.3862 | 29.9485 | 31.0958 | 32.2879 | 33.5266 | 34.8137 | 36.1511 | 37.5408 | 882.1477
|  | L&G O&M |  | L&G O&M |  | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
BENEFITS
|  | Metering Net Benefits |  | Net Benefits |  | -4.3368 | 0.0019191 | 0.0017992 | -2.5349 | -35.9127 | -40.9346 | -20.445 | -17.7139 | -15.5977 | -13.9903 | -12.1189 | -10.3351 | -0.82212 | 7.5813 | 26.4192 | 27.5882 | 28.6577 | 29.7988 | 30.9044 | 32.0424 | 33.483 | 35.3327 | 37.9281 | 39.1872 | 40.6455 | 42.409 | 44.1686 | 46.6308 | 47.6987 | 241.5758
|  | Net Benefits (real) |  | Net Benefits (real) |  | -4.3347 | 0.0020682 | 0.0016695 | -2.1826 | -28.6915 | -30.3458 | -14.0636 | -11.3065 | -9.2379 | -7.6885 | -6.1799 | -4.8903 | -0.36096 | 3.0886 | 9.9873 | 9.6773 | 9.3277 | 8.9998 | 8.6608 | 8.3323 | 8.0791 | 7.9108 | 7.8796 | 7.5542 | 7.2704 | 7.039 | 6.8025 | 6.6639 | 6.325 | -11.1372
|  | Cumulative Net Benefits |  | Cumulative Net Benefits |  |  | 0.0020682 | 0.0037377 | -2.1788 | -30.8704 | -61.2162 | -75.2799 | -86.5864 | -95.8243 | -103.5128 | -109.6927 | -114.583 | -114.944 | -111.8554 | -101.8681 | -92.1908 | -82.8632 | -73.8634 | -65.2026 | -56.8703 | -48.7912 | -40.8804 | -33.0008 | -25.4466 | -18.1761 | -11.1372 | -4.3347 | 2.3292 | 8.6542
CORP MODEL INPUTS (AMI Metering ONLY)
|  | Total O&M | O&M | Total O&M | 0 | 194.5586 | 32.3825 | 35.5604 | 37.6078 | 22.0561 | 16.9133 | 15.6935 | 14.9417 | 14.201 | 13.426 | 12.6043 | 11.7236 | 11.1497 | 10.8162 | 11.11 | 11.4126 | 11.724 | 12.0447 | 12.3747 | 12.714 | 13.0628 | 13.4212 | 13.7836 | 14.1573 | 14.5426 | 14.94 | 15.34 | 15.7611 | 16.197 | 404.3636
|  | Meter Capital | CAPEX | Meter Capital | #VALUE! | 375.6242 | -6.9147 | 7.4107 | 11.1706 | 46.3387 | 50.7004 | 48.0082 | 46.694 | 46.7323 | 47.5353 | 48.7264 | 50.2097 | 43.9234 | 38.4938 | 22.1191 | 22.9185 | 23.6665 | 24.5205 | 25.3055 | 26.0836 | 26.8495 | 27.6276 | 27.1278 | 28.2114 | 29.3383 | 30.5102 | 31.729 | 32.9964 | 34.3145 | 793.3073
|  | Network Capital | CAPEX | Network | 0 | 47.1998 | 0 | 0 | 2.5367 | 12.9507 | 19.1991 | 2.6581 | 2.685 | 2.729 | 2.7811 | 2.8395 | 2.903 | 2.7402 | 2.6426 | 2.374 | 2.4262 | 2.4788 | 2.5334 | 2.5883 | 2.6441 | 2.7008 | 2.7586 | 2.8208 | 2.8845 | 2.9496 | 3.0164 | 3.0847 | 3.1546 | 3.2263 | 87.7228
AMI Applications
Disconnect/Reconnect
|  |  | CAPEX | CIS Remote Disconnect and Prepay Enablement | #REF! | 1.6169 | 0 | 0 | 0.95 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.95
|  |  | O&M | Management Costs (Annual) | #REF! | 9.2158 | 0 | 0 | 0 | 0.5 | 0.539 | 0.58104 | 0.62636 | 0.67522 | 0.72789 | 0.78466 | 0.84587 | 0.91184 | 0.98297 | 1.0596 | 1.1423 | 1.2314 | 1.3274 | 1.431 | 1.5426 | 1.6629 | 1.7926 | 1.9324 | 2.0832 | 2.2457 | 2.4208 | 2.6097 | 2.8132 | 3.0326 | 27.0468
|  |  | Revenue | Credit Write offs from Electric Only Service Areas (Revenue) | #REF! | 138.4556 | 11.2392 | 11.4753 | 11.7162 | 11.7829 | 11.8165 | 11.8413 | 11.8951 | 11.9701 | 12.0633 | 12.1725 | 12.2958 | 12.432 | 12.6041 | 12.907 | 13.2163 | 13.532 | 13.8544 | 14.1835 | 14.5195 | 14.8626 | 15.2129 | 15.5706 | 15.9358 | 16.3086 | 16.6893 | 17.0779 | 17.4748 | 17.8799 | 332.0968
|  |  | Revenue | UEU Electric Write Offs (Revenue)$ |  | 16.2183 | 3.2953 | 3.3645 | 3.4352 | 3.1613 | 2.7993 | 2.3922 | 2.0154 | 1.6545 | 1.3045 | 0.96147 | 0.62209 | 0.2836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25.2893
|  |  | O&M | UEU Labor & Overhead (O&M) |  | 1.4047 | 0.26682 | 0.27243 | 0.27815 | 0.25711 | 0.22924 | 0.19787 | 0.16885 | 0.14108 | 0.11416 | 0.087779 | 0.061693 | 0.035682 | 0.01394 | 0.014233 | 0.014532 | 0.014837 | 0.015149 | 0.015467 | 0.015791 | 0.016123 | 0.016462 | 0.016807 | 0.01716 | 0.017521 | 0.017889 | 0.018264 | 0.018648 | 0.019039 | 2.3168
|  | Disconnect/Reconnect Total |  | Total | #REF! | 166.9113 | 14.8014 | 15.1122 | 16.3795 | 16.7013 | 15.384 | 15.0124 | 14.7058 | 14.4409 | 14.2099 | 14.0064 | 13.8255 | 13.6631 | 13.6011 | 13.9809 | 14.3731 | 14.7782 | 15.1969 | 15.6299 | 16.0779 | 16.5417 | 17.022 | 17.5198 | 18.0361 | 18.5718 | 19.128 | 19.7058 | 20.3066 | 20.9316 | 388.6997
|  |  |  | Net Benefit |  | 30.603
CVR
|  |  | CAPEX | Upgrade Costs |  | 15.5066 | 0.25707 | 0.52699 | 0.54017 | 1.1073 | 1.135 | 1.1634 | 1.59 | 1.8335 | 1.8793 | 1.9263 | 1.9744 | 2.0238 | 2.0744 | 2.1262 | 2.1794 | 2.2339 | 2.2897 | 2.347 | 2.4056 | 2.4658 | 1.685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35.7642
|  |  | O&M | Management Costs |  | 18.7605 | 0.195 | 0.29213 | 0.39398 | 0.50075 | 0.61262 | 0.72976 | 0.88717 | 1.0698 | 1.261 | 1.4612 | 1.6705 | 1.8894 | 2.1182 | 2.3573 | 2.6069 | 2.8676 | 3.1397 | 3.4236 | 3.7198 | 4.0286 | 4.2768 | 4.3837 | 4.4933 | 4.6056 | 4.7208 | 4.8388 | 4.9598 | 5.0838 | 57.7053
|  | CVR Costs |  | Total |  | 34.2671 | 0.45207 | 0.81912 | 0.93415 | 1.6081 | 1.7476 | 1.8932 | 2.4772 | 2.9033 | 3.1403 | 3.3874 | 3.6449 | 3.9132 | 4.1926 | 4.4835 | 4.7863 | 5.1015 | 5.4295 | 5.7706 | 6.1254 | 6.4944 | 5.9617 | 4.3837 | 4.4933 | 4.6056 | 4.7208 | 4.8388 | 4.9598 | 5.0838 | 93.4696
|  |  | O&M | Annual Peak Savings EOL ($) |  | -34.7542 | 0 | -0.082922 | -0.25498 | -0.4356 | -0.84833 | -1.0984 | -1.3604 | -1.7149 | -2.1274 | -2.5595 | -3.0118 | -3.4852 | -3.9803 | -4.498 | -5.0391 | -5.6045 | -6.1949 | -6.8114 | -7.4549 | -8.1262 | -8.8265 | -9.3869 | -9.6215 | -9.8621 | -10.1086 | -10.3613 | -10.6204 | -10.8859 | -112.4943
|  |  | O&M | Annual Energy Savings EOL($) |  | -60.023 | 0 | -0.12012 | -0.37645 | -0.64706 | -1.3053 | -1.7604 | -2.2226 | -2.8702 | -3.4153 | -4.2564 | -5.312 | -6.044 | -6.2418 | -7.2509 | -8.3108 | -9.1409 | -10.6722 | -12.0941 | -13.6917 | -15.3488 | -16.4452 | -17.2498 | -17.437 | -17.6242 | -17.8113 | -17.9985 | -18.1856 | -18.3728 | -197.6486
|  | CVR Benefits |  | Total |  | -94.7772 | 0 | -0.20304 | -0.63144 | -1.0827 | -2.1537 | -2.8587 | -3.5829 | -4.5851 | -5.5427 | -6.8159 | -8.3238 | -9.5292 | -10.2221 | -11.7489 | -13.3499 | -14.7454 | -16.8672 | -18.9056 | -21.1465 | -23.475 | -25.2717 | -26.6367 | -27.0585 | -27.4862 | -27.9199 | -28.3598 | -28.806 | -29.2586 | -310.1429
|  |  |  | Net Benefit |  | 12.8198
Outage
|  |  | O&M | Automated analysis of system status including outage device prediction | 109.2718 | 60.0041 | 4.5967 | 4.6932 | 4.7918 | 4.8924 | 4.9764 | 5.0577 | 5.1389 | 5.2241 | 5.3123 | 5.4035 | 5.4972 | 5.5935 | 5.6923 | 5.7967 | 5.9184 | 6.0427 | 6.1696 | 6.2992 | 6.4315 | 6.5665 | 6.7044 | 6.8452 | 6.989 | 7.1357 | 7.2856 | 7.4386 | 7.5948 | 7.7543 | 145.0547
|  |  | O&M | Electric First Response (EFR) Investigations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O&M | Storm Response Costs | 293.646 | 161.3751 | 12.1696 | 12.4251 | 12.686 | 12.9524 | 13.2102 | 13.4699 | 13.7336 | 14.0047 | 14.2824 | 14.5667 | 14.8576 | 15.155 | 15.459 | 15.7721 | 16.1033 | 16.4415 | 16.7867 | 17.1392 | 17.4992 | 17.8667 | 18.2418 | 18.6249 | 19.0161 | 19.4154 | 19.8231 | 20.2394 | 20.6644 | 21.0984 | 391.7021
|  |  | O&M | Non-storm response Costs | 58.7301 | 31.6739 | 3.307 | 3.3765 | 3.4474 | 3.5198 | 3.419 | 3.2746 | 3.1101 | 2.963 | 2.8253 | 2.694 | 2.5668 | 2.4423 | 2.3192 | 2.2268 | 2.2736 | 2.3213 | 2.37 | 2.4198 | 2.4706 | 2.5225 | 2.5755 | 2.6296 | 2.6848 | 2.7412 | 2.7987 | 2.8575 | 2.9175 | 2.9788 | 69.2994
|  |  | O&M | SAIDI Fines | 15.4696 | 8.4893 | 0.65867 | 0.6725 | 0.68663 | 0.70105 | 0.71156 | 0.72129 | 0.73081 | 0.74104 | 0.75178 | 0.76297 | 0.77457 | 0.78653 | 0.79885 | 0.81222 | 0.82928 | 0.84669 | 0.86447 | 0.88263 | 0.90116 | 0.92009 | 0.93941 | 0.95914 | 0.97928 | 0.99984 | 1.0208 | 1.0423 | 1.0642 | 1.0865 | 20.4533
|  | Outage Total |  | Total | 477.1174 | 261.5425 | 20.732 | 21.1673 | 21.6118 | 22.0657 | 22.3171 | 22.5235 | 22.7135 | 22.9328 | 23.1719 | 23.4271 | 23.6962 | 23.9774 | 24.2693 | 24.6078 | 25.1245 | 25.6522 | 26.1909 | 26.7409 | 27.3024 | 27.8758 | 28.4612 | 29.0589 | 29.6691 | 30.2921 | 30.9283 | 31.5778 | 32.2409 | 32.918 | 626.5096
|  |  |  | Net Benefit |  | 15.1118
Totals
|  | Applications Total |  |  |  | 367.9437 | 35.9854 | 36.8956 | 38.2941 | 39.2924 | 37.2951 | 36.5704 | 36.3135 | 35.6918 | 34.9793 | 34.005 | 32.8428 | 32.0245 | 31.8409 | 31.3233 | 30.934 | 30.7865 | 29.9501 | 29.2358 | 28.3592 | 27.4368 | 26.1732 | 24.3257 | 25.14 | 25.9833 | 26.8571 | 27.7626 | 28.7013 | 29.6747 | 798.536
|  | Application Net Benefits |  |  |  | 58.5346 | 0 | 0 | -0.95 | -1.5014 | 0.91156 | 2.0214 | 2.9029 | 3.8784 | 4.9019 | 5.9698 | 7.069 | 8.0876 | 8.9024 | 9.4282 | 9.7975 | 10.118 | 10.5874 | 11.0328 | 11.5143 | 12.007 | 12.8021 | 13.9564 | 14.0724 | 14.1817 | 14.2834 | 14.3766 | 14.4604 | 14.5337 | 185.9746
Financial Results
|  | Costs |  |  | -181.2206 | -101.3035 | 0.0019191 | 0.0017992 | -3.4849 | -37.4141 | -40.0231 | -18.4237 | -14.8111 | -11.7193 | -9.0884 | -6.1491 | -3.2661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Benefits |  |  | 262.3118 | 155.5013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.2655 | 16.4837 | 35.8474 | 37.3856 | 38.7757 | 40.3862 | 41.9372 | 43.5567 | 45.49 | 48.1347 | 51.8845 | 53.2596 | 54.8272 | 56.6924 | 58.5452 | 61.0912 | 62.2324
|  | Two Vendors, Two Networks Costs |  |  |  | 985.3262 | 61.4532 | 79.8668 | 89.6092 | 120.6379 | 124.1079 | 102.9303 | 100.6342 | 99.3541 | 98.7217 | 98.1751 | 97.6792 | 89.8377 | 83.7935 | 66.9263 | 67.6914 | 68.6559 | 69.0487 | 69.5044 | 69.8009 | 70.0498 | 69.9806 | 68.0579 | 70.3931 | 72.8139 | 75.3237 | 77.9162 | 80.6134 | 83.4124 | 2085.0472
|  | Net Benefits |  | Net Benefits |  | 54.1978 | 0.0019191 | 0.0017992 | -3.4849 | -37.4141 | -40.0231 | -18.4237 | -14.8111 | -11.7193 | -9.0884 | -6.1491 | -3.2661 | 7.2655 | 16.4837 | 35.8474 | 37.3856 | 38.7757 | 40.3862 | 41.9372 | 43.5567 | 45.49 | 48.1347 | 51.8845 | 53.2596 | 54.8272 | 56.6924 | 58.5452 | 61.0912 | 62.2324 | 427.5504
|  | Net Benefits (real) |  | Net Benefits (real) |  | 54.1978 | 0.0020682 | 0.0016695 | -3.0005 | -29.891 | -29.6701 | -12.6732 | -9.4536 | -6.9409 | -4.9946 | -3.1357 | -1.5454 | 3.19 | 6.7155 | 13.5514 | 13.114 | 12.6209 | 12.1974 | 11.7526 | 11.3264 | 10.9763 | 10.7771 | 10.7791 | 10.267 | 9.8072 | 9.4097 | 9.0166 | 8.7304 | 8.2523 | 45.1832
|  | Cumulative Net Benefits |  | Cumulative Net Benefits |  | -995.0673 | 0.0020682 | 0.0037377 | -2.9968 | -32.8878 | -62.5579 | -75.2311 | -84.6848 | -91.6257 | -96.6203 | -99.756 | -101.3014 | -98.1115 | -91.3959 | -77.8445 | -64.7305 | -52.1096 | -39.9122 | -28.1596 | -16.8332 | -5.8568 | 4.9202 | 15.6993 | 25.9663 | 35.7735 | 45.1832 | 54.1998 | 62.9302 | 71.1825
CORP MODEL INPUTS (AMI Metering AND Applications)
|  | Total O&M |  | Total O&M | 0 | 545.3787 | 68.1108 | 71.929 | 74.4118 | 59.2412 | 53.0734 | 51.1005 | 49.6652 | 48.0593 | 46.526 | 44.683 | 42.592 | 41.1504 | 40.5827 | 40.307 | 40.1673 | 40.2767 | 39.7051 | 39.2636 | 38.6676 | 38.0338 | 37.9095 | 38.1093 | 39.2972 | 40.526 | 41.7971 | 43.1026 | 44.4624 | 45.8717 | 1165.1853
|  | Meter Capital |  | Meter Capital | 0 | 375.6242 | -6.9147 | 7.4107 | 11.1706 | 46.3387 | 50.7004 | 48.0082 | 46.694 | 46.7323 | 47.5353 | 48.7264 | 50.2097 | 43.9234 | 38.4938 | 22.1191 | 22.9185 | 23.6665 | 24.5205 | 25.3055 | 26.0836 | 26.8495 | 27.6276 | 27.1278 | 28.2114 | 29.3383 | 30.5102 | 31.729 | 32.9964 | 34.3145 | 793.3073
|  | Network/Substation Capital |  | Network | 0 | 64.3233 | 0.25707 | 0.52699 | 4.0268 | 15.058 | 20.3341 | 3.8215 | 4.275 | 4.5624 | 4.6604 | 4.7657 | 4.8775 | 4.764 | 4.717 | 4.5002 | 4.6056 | 4.7127 | 4.8231 | 4.9353 | 5.0497 | 5.1666 | 4.4436 | 2.8208 | 2.8845 | 2.9496 | 3.0164 | 3.0847 | 3.1546 | 3.2263 | 125.4371
985.3262

## Full Deployment (R)
3-Full Deployment
| ($Millions) |  |  |  | NPV | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | TCO
| Year |  |  |  |  | -1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
COSTS
|  |  | Year of Deployment |  |  | -1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | TCO
| L+G Contract | O&M | L+G Contract |  | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX
| L+G Termination Fees | O&M | L+G Termination Fees | Meter Reduction fees are the result of falling below the meter minimum in 2016 and then decreasing to the meter floor in 2017. Complete termination occurs in 2018. | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX
|  | CAPEX | AMR Electric Meter Hardware (Growth) |  | 2.6769 | -1.5776 | 0.6574 | 1.2489 | 1.2411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5698
|  | CAPEX | AMR Electric Meter Hardware (Maintenance) |  | 0.76656 | 0.2256 | 0.30188 | 0.31488 | 0.26953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1119
|  | CAPEX | AMR Electric Meter Exchange (Growth) |  | 2.0372 | -1.4443 | 0.60126 | 1.1411 | 0.6218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.91989
|  | O&M | AMR Electric Meter Exchange (Maintenance) |  | 0.61179 | 0.20653 | 0.2761 | 0.2877 | 0.13504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.90537
|  | CAPEX | AMR Gas Meter Hardware (Growth) |  | 8.4506 | -2.8151 | 2.6901 | 4.1151 | 3.0182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.0083
|  | CAPEX | AMR Gas Meter Hardware (Maintenance) |  | 2.2746 | 0.96052 | 0.99899 | 1.0479 | 0.55745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5649
|  | CAPEX | AMR Gas Meter Exchange (Growth) |  | 6.3455 | -2.2638 | 2.1611 | 3.3027 | 1.8732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.0732
|  | O&M | AMR Gas Meter Exchange (Maintenance) |  | 1.7452 | 0.7724 | 0.80254 | 0.84105 | 0.34597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.762
|  | CAPEX | AMR Gas Modules for Maintenance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | O&M | AMR Gas Module Exchanges |  | 0.66371 | 0.31807 | 0.31553 | 0.31574 | 0.12402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0734
|  | O&M | AMR Gas Module Visits |  | 1.0768 | 0.51603 | 0.51191 | 0.51224 | 0.20121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7414
|  | O&M | Battery Costs |  | 2.005 | 0.28415 | 0.44381 | 1.0183 | 0.89673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.643
| AMR Meter/Module Costs |  | Total |  | 28.6538 | -4.8175 | 9.7606 | 14.1456 | 9.2842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.373
9.3175
|  | CAPEX | AMI Electric Meter Hardware (Growth) |  | 165.6048 | 0 | 0 | 0 | 53.7104 | 58.886 | 71.536 | 3.4409 | 3.4028 | 3.4977 | 3.615 | 3.7447 | 3.8626 | 3.9847 | 4.1148 | 4.2458 | 4.3661 | 4.5055 | 4.6338 | 4.7602 | 4.8831 | 5.0091 | 6.2965 | 6.5498 | 6.8132 | 7.0873 | 7.3723 | 7.6689 | 7.9773 | 272.946
|  | CAPEX | AMI Electric Meter Hardware (Maintenance) |  | 6.9403 | 0 | 0 | 0 | 0.18262 | 0.38666 | 0.63801 | 0.6631 | 0.6886 | 0.71495 | 0.74225 | 0.77057 | 0.79989 | 0.83023 | 0.86166 | 0.89419 | 0.92781 | 0.96262 | 0.99859 | 1.0357 | 1.0741 | 1.1137 | 1.1585 | 1.2051 | 1.2535 | 1.304 | 1.3564 | 1.411 | 1.4677 | 19.2063
|  | CAPEX | AMI Electric Meter Exchange (Growth) |  | 46.0129 | 0 | 0 | 0 | 7.7356 | 19.1719 | 23.2677 | 1.1181 | 1.1046 | 1.1343 | 1.1712 | 1.212 | 1.249 | 1.2872 | 1.3279 | 1.3689 | 1.4063 | 1.4497 | 1.4895 | 1.5287 | 1.5666 | 1.6055 | 2.0161 | 2.0952 | 2.1773 | 2.2627 | 2.3514 | 2.4436 | 2.5394 | 78.746
|  | O&M | AMI Electric Meter Exchange (Maintenance) |  | 2.2132 | 0 | 0 | 0 | 0.026301 | 0.12589 | 0.20752 | 0.21547 | 0.22353 | 0.23186 | 0.24048 | 0.24941 | 0.25865 | 0.26819 | 0.27807 | 0.28829 | 0.29884 | 0.30974 | 0.321 | 0.33262 | 0.3446 | 0.35695 | 0.37094 | 0.38548 | 0.4006 | 0.4163 | 0.43262 | 0.44958 | 0.46721 | 6.1507
|  | CAPEX | AMI Gas Meter/Module Hardware (Growth) |  | 78.2176 | 0 | 0 | 0 | 6.7285 | 7.3042 | 7.6799 | 7.3436 | 7.3231 | 7.5877 | 7.9079 | 8.2529 | 8.5651 | 8.881 | 9.2146 | 9.5453 | 9.8455 | 10.1984 | 10.5088 | 10.8117 | 11.1047 | 11.3992 | 9.8341 | 10.2297 | 10.6412 | 11.0692 | 11.5144 | 11.9775 | 12.4593 | 201.9763
|  | CAPEX | AMI Gas Meter/Module Hardware (Maintenance) |  | 20.4252 | 0 | 0 | 0 | 0.49315 | 1.0535 | 1.7568 | 1.8436 | 1.9321 | 2.0243 | 2.1205 | 2.2212 | 2.3261 | 2.4353 | 2.5491 | 2.6676 | 2.7905 | 2.9185 | 3.0512 | 3.1888 | 3.3313 | 3.4788 | 3.6187 | 3.7643 | 3.9157 | 4.0732 | 4.237 | 4.4074 | 4.5847 | 57.5541
|  | CAPEX | AMI Gas Meter Exchange (Growth) |  | 43.176 | 0 | 0 | 0 | 3.7464 | 4.0629 | 4.2677 | 4.0769 | 4.0615 | 4.2041 | 4.3773 | 4.5637 | 4.7318 | 4.9015 | 5.0806 | 5.2578 | 5.4179 | 5.6065 | 5.7715 | 5.9321 | 6.0869 | 6.2421 | 5.3799 | 5.5908 | 5.81 | 6.0377 | 6.2744 | 6.5204 | 6.776 | 111.2076
|  | O&M | AMI Gas Meter Exchange (Maintenance) |  | 11.2586 | 0 | 0 | 0 | 0.27458 | 0.58602 | 0.97624 | 1.0235 | 1.0716 | 1.1216 | 1.1738 | 1.2283 | 1.285 | 1.3441 | 1.4055 | 1.4694 | 1.5356 | 1.6044 | 1.6758 | 1.7496 | 1.826 | 1.905 | 1.9796 | 2.0573 | 2.1379 | 2.2217 | 2.3088 | 2.3993 | 2.4934 | 31.6524
|  | CAPEX | New AMI Gas Modules (Deployments) |  | 52.1667 | 0 | 0 | 0 | 20.1034 | 22.4825 | 28.259 | 0 | 0 | 0 | 1.1286e-14 | -1.1523e-14 | 1.1765e-14 | -1.2013e-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70.8449
|  | CAPEX | New AMI Gas Module Exchanges (Deployments) |  | 12.9436 | 0 | 0 | 0 | 3.4173 | 6.3632 | 7.9903 | 0 | 0 | 0 | 3.1788e-15 | -3.2424e-15 | 3.3072e-15 | -3.3733e-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.7707
|  | O&M | AMI Gas Module Visits |  | 0.65476 | 0 | 0 | 0 | 0.015969 | 0.03408 | 0.056774 | 0.059522 | 0.062319 | 0.065227 | 0.068263 | 0.071433 | 0.074733 | 0.078166 | 0.081739 | 0.085453 | 0.089304 | 0.093307 | 0.097456 | 0.10175 | 0.10619 | 0.11079 | 0.11513 | 0.11964 | 0.12433 | 0.12921 | 0.13427 | 0.13954 | 0.14501 | 1.8408
|  | CAPEX | AMI Gas Modules (Maintenance) |  | 3.1205 | 0 | 0 | 0 | 0.075342 | 0.16095 | 0.26839 | 0.28166 | 0.29518 | 0.30926 | 0.32397 | 0.33935 | 0.35537 | 0.37206 | 0.38945 | 0.40754 | 0.42633 | 0.44588 | 0.46616 | 0.48718 | 0.50895 | 0.53148 | 0.55286 | 0.57509 | 0.59822 | 0.62229 | 0.64732 | 0.67335 | 0.70044 | 8.793
|  | O&M | AMI Gas Modude Exchanges (Maintenance) |  | 0.87519 | 0 | 0 | 0 | 0.021345 | 0.045554 | 0.075888 | 0.079561 | 0.083299 | 0.087187 | 0.091245 | 0.095482 | 0.099893 | 0.10448 | 0.10926 | 0.11422 | 0.11937 | 0.12472 | 0.13027 | 0.13601 | 0.14194 | 0.14808 | 0.15389 | 0.15992 | 0.16619 | 0.17271 | 0.17948 | 0.18651 | 0.19383 | 2.4605
|  | O&M | FTE to Manage Inventory/Testing |  | 1.6884 | 0 | 0 | 0 | 0.1576 | 0.16075 | 0.16397 | 0.16725 | 0.17059 | 0.17401 | 0.17749 | 0.18104 | 0.18466 | 0.18835 | 0.19212 | 0.19596 | 0.19988 | 0.20388 | 0.20795 | 0.21211 | 0.21635 | 0.22068 | 0.22509 | 0.2296 | 0.23419 | 0.23887 | 0.24365 | 0.24852 | 0.25349 | 4.3024
|  |  | Cost of Implimentation of Disconnect/Reconnect Program |  | 0 | [28 empty] | 0
|  |  | Cost of Maintaining Disconnect/Reconnect Program |  | 0 | [28 empty] | 0
| AMI Meter/Module Costs |  | Total |  | 445.2977 | 0 | 0 | 0 | 96.6885 | 120.8241 | 147.144 | 20.3131 | 20.4193 | 21.1522 | 22.0095 | 22.9301 | 23.7928 | 24.6753 | 25.6049 | 26.5403 | 27.4234 | 28.4232 | 29.3521 | 30.2765 | 31.1908 | 32.1213 | 31.7014 | 32.9617 | 34.2723 | 35.6351 | 37.0521 | 38.5256 | 40.0579 | 885.4518
|  | CAPEX | AMI Network Installation (Hardware) |  | 14.9209 | 0 | 0 | 0 | 9.5904 | 9.7918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.3821
|  | CAPEX | AMI Network Installation (Labor) |  | 4.3129 | 0 | 0 | 0 | 2.7721 | 2.8303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.6024
|  | CAPEX | AMI Network maintenance (Hardware) |  | 2.9319 | 0 | 0 | 0 | 0.26041 | 0.26697 | 0.27373 | 0.28068 | 0.28783 | 0.29519 | 0.30276 | 0.31056 | 0.31859 | 0.32686 | 0.33538 | 0.34415 | 0.35318 | 0.36249 | 0.37209 | 0.38197 | 0.39216 | 0.40267 | 0.4135 | 0.42467 | 0.43619 | 0.44808 | 0.46034 | 0.47299 | 0.48604 | 7.5901
|  | O&M | AMI Network maintenance (Labor) |  | 7.5535 | 0 | 0 | 0 | 0.36619 | 0.74704 | 0.76198 | 0.77722 | 0.79276 | 0.80862 | 0.82479 | 0.84128 | 0.85811 | 0.87527 | 0.89278 | 0.91063 | 0.92885 | 0.94742 | 0.96637 | 0.9857 | 1.0054 | 1.0255 | 1.046 | 1.067 | 1.0883 | 1.1101 | 1.1323 | 1.1549 | 1.178 | 19.6273
|  | O&M | Manual Meter Reading |  | 0.85023 | 0 | 0 | 0 | 0.065529 | 0.068535 | 0.07161 | 0.074661 | 0.077761 | 0.080972 | 0.08431 | 0.087781 | 0.091382 | 0.095117 | 0.098992 | 0.10301 | 0.10717 | 0.11148 | 0.11594 | 0.12054 | 0.1253 | 0.13021 | 0.13532 | 0.14062 | 0.14614 | 0.15187 | 0.15782 | 0.16401 | 0.17044 | 2.2842
|  | O&M | Network Overhead and management |  | 2.4854 | 0 | 0 | 0 | 0.1773 | 0.24113 | 0.24595 | 0.25087 | 0.25589 | 0.26101 | 0.26623 | 0.27155 | 0.27698 | 0.28252 | 0.28817 | 0.29394 | 0.29982 | 0.30581 | 0.31193 | 0.31817 | 0.32453 | 0.33102 | 0.33764 | 0.34439 | 0.35128 | 0.35831 | 0.36547 | 0.37278 | 0.38024 | 6.3945
| Network Costs |  | Total |  | 33.0547 | 0 | 0 | 0 | 13.2319 | 13.9457 | 1.3533 | 1.3834 | 1.4142 | 1.4458 | 1.4781 | 1.5112 | 1.5451 | 1.5798 | 1.6153 | 1.6517 | 1.689 | 1.7272 | 1.7663 | 1.8064 | 1.8474 | 1.8894 | 1.9325 | 1.9766 | 2.0219 | 2.0683 | 2.1159 | 2.1647 | 2.2147 | 60.8806
|  | O&M | SaaS/NOC/Deployment Services |  | 52.2675 | 0 | 0 | 2.9043 | 4.9495 | 5.9743 | 4.9833 | 5.0608 | 5.0959 | 5.1321 | 5.1694 | 5.2077 | 5.2473 | 5.288 | 5.3299 | 5.4418 | 5.5561 | 5.6728 | 5.7919 | 5.9136 | 6.0377 | 6.1645 | 6.294 | 6.4262 | 6.5611 | 6.6989 | 6.8396 | 6.9832 | 7.1298 | 126.9011
|  | CAPEX | Deployment Project Management |  | 1.738 | 0 | 0 | 0.70955 | 0.72446 | 0.73967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1737
|  |  | Testing/Security |  | 0
| NOC Head End Costs |  | Total |  | 54.0056 | 0 | 0 | 3.6139 | 5.6739 | 6.714 | 4.9833 | 5.0608 | 5.0959 | 5.1321 | 5.1694 | 5.2077 | 5.2473 | 5.288 | 5.3299 | 5.4418 | 5.5561 | 5.6728 | 5.7919 | 5.9136 | 6.0377 | 6.1645 | 6.294 | 6.4262 | 6.5611 | 6.6989 | 6.8396 | 6.9832 | 7.1298 | 129.0748
|  | O&M | Backhaul Costs (Licences and Data) |  | 4.1985 | 0 | 0 | 0 | 0.32807 | 0.43388 | 0.40885 | 0.41727 | 0.42587 | 0.43464 | 0.44359 | 0.45273 | 0.46206 | 0.47158 | 0.48129 | 0.49121 | 0.50133 | 0.51166 | 0.5222 | 0.53296 | 0.54394 | 0.55515 | 0.56659 | 0.57826 | 0.59017 | 0.60233 | 0.60711 | 0.61962 | 0.63238 | 10.7556
|  | O&M | Poll Attachment Costs |  | 5.1929 | -0.13473 | -0.13756 | -0.14045 | 0.45163 | 0.50815 | 0.52005 | 0.53223 | 0.5447 | 0.55746 | 0.57052 | 0.58389 | 0.59758 | 0.61159 | 0.62593 | 0.6406 | 0.65563 | 0.671 | 0.68674 | 0.70286 | 0.71935 | 0.73623 | 0.75351 | 0.7712 | 0.7893 | 0.80783 | 0.8268 | 0.8451 | 0.86496 | 13.6253
|  | O&M | Customer Service and Other Overhead |  | 40.753 | 3.1649 | 3.2191 | 3.2744 | 3.3307 | 3.3882 | 3.4469 | 3.5067 | 3.5677 | 3.63 | 3.6935 | 3.7582 | 3.8243 | 3.8916 | 3.9604 | 4.0305 | 4.102 | 4.1749 | 4.2493 | 4.3251 | 4.4025 | 4.4815 | 4.562 | 4.6441 | 4.7279 | 4.8133 | 4.9005 | 4.9894 | 5.08 | 98.1696
|  | O&M | Field Work Reimbursements |  | -2.3241 | -0.95955 | -0.89959 | -0.86644 | -0.6211 | -0.33335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3.68
| Telecom and Other Costs |  | Total |  | 43.6219 | 2.0706 | 2.1819 | 2.2675 | 3.1613 | 3.563 | 3.9669 | 4.0389 | 4.1124 | 4.1874 | 4.264 | 4.3421 | 4.4219 | 4.5032 | 4.5863 | 4.6711 | 4.7576 | 4.8459 | 4.936 | 5.028 | 5.1219 | 5.2177 | 5.3155 | 5.4153 | 5.5172 | 5.6212 | 5.7273 | 5.8345 | 5.945 | 108.1148
|  |  | Total |  | #VALUE! | 25.4678 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  | Costs (real) |  | #VALUE! | 27.4467 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| O&M Costs |  | O&M Costs |  | 129.5713 | 4.1678 | 4.5318 | 8.1468 | 10.9185 | 11.5463 | 11.5102 | 11.7478 | 11.9461 | 12.15 | 12.3599 | 12.5761 | 12.7986 | 13.0274 | 13.2628 | 13.5738 | 13.8925 | 14.2195 | 14.5546 | 14.8981 | 15.2499 | 15.6104 | 15.9732 | 16.3453 | 16.7272 | 17.1191 | 17.5212 | 17.9329 | 18.3565 | 318.8538
| CAPEX |  | CAPEX |  | 475.0624 | -6.9147 | 7.4107 | 11.8802 | 117.1213 | 133.5005 | 145.9374 | 19.0485 | 19.0958 | 19.7675 | 20.561 | 21.415 | 22.2085 | 23.0189 | 23.8736 | 24.7312 | 25.5336 | 26.4496 | 27.2917 | 28.1263 | 28.9478 | 29.7825 | 29.2702 | 30.4345 | 31.6453 | 32.9043 | 34.2136 | 35.5751 | 36.991 | 893.0413
| L&G O&M |  | L+G O&M |  | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX
BENEFITS
Network
|  |  | Contract Costs and Network Maintenance |  | 167.0786 | 0 | 0 | 0 | 5.592 | 8.8261 | 13.9864 | 14.5981 | 15.3067 | 16.0579 | 16.8539 | 17.6894 | 18.5662 | 19.4866 | 20.4525 | 21.4664 | 22.5305 | 23.6473 | 24.8196 | 26.0499 | 27.3412 | 28.6965 | 30.119 | 31.612 | 33.1791 | 34.8238 | 36.55 | 38.3618 | 40.2634 | 167.4158
|  |  | Total |  | 167.0786 | 0 | 0 | 0 | 5.592 | 8.8261 | 13.9864 | 14.5981 | 15.3067 | 16.0579 | 16.8539 | 17.6894 | 18.5662 | 19.4866 | 20.4525 | 21.4664 | 22.5305 | 23.6473 | 24.8196 | 26.0499 | 27.3412 | 28.6965 | 30.119 | 31.612 | 33.1791 | 34.8238 | 36.55 | 38.3618 | 40.2634 | 167.4158
| Net Benefits |  | Net Benefits |  | #VALUE! | 0.0019191 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Net Benefits (real) |  | Net Benefits (real) |  | #VALUE! | 0.0020682 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Cumulative Net Benefits |  | Cumulative Net Benefits |  |  | 0.0020682 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
CORP MODEL INPUTS
| Total O&M |  | Total O&M |  | #VALUE! | 32.3825 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Meter Capital |  | Meter Capital |  | 452.8968 | -6.9147 | 7.4107 | 11.8802 | 104.4984 | 120.6115 | 145.6637 | 18.7678 | 18.808 | 19.4723 | 20.2583 | 21.1045 | 21.8899 | 22.692 | 23.5382 | 24.387 | 25.1805 | 26.0871 | 26.9196 | 27.7443 | 28.5557 | 29.3798 | 28.8567 | 30.0098 | 31.2091 | 32.4563 | 33.7533 | 35.1022 | 36.5049 | 860.4666
| Network Capital |  | Network Capital |  | 22.1656 | 0 | 0 | 0 | 12.6229 | 12.889 | 0.27373 | 0.28068 | 0.28783 | 0.29519 | 0.30276 | 0.31056 | 0.31859 | 0.32686 | 0.33538 | 0.34415 | 0.35318 | 0.36249 | 0.37209 | 0.38197 | 0.39216 | 0.40267 | 0.4135 | 0.42467 | 0.43619 | 0.44808 | 0.46034 | 0.47299 | 0.48604 | 32.5746
#VALUE!
AMI Benefits
Disconnect/Reconnect
|  | CAPEX | CIS Remote Disconnect and Prepay Enablement |  | 1.6169 | 0 | 0 | 0.95 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.95
|  | O&M | Management Costs (Annual) |  | 9.2158 | 0 | 0 | 0 | 0.5 | 0.539 | 0.58104 | 0.62636 | 0.67522 | 0.72789 | 0.78466 | 0.84587 | 0.91184 | 0.98297 | 1.0596 | 1.1423 | 1.2314 | 1.3274 | 1.431 | 1.5426 | 1.6629 | 1.7926 | 1.9324 | 2.0832 | 2.2457 | 2.4208 | 2.6097 | 2.8132 | 3.0326 | 27.0468
| Disconnect/Reconnect Costs | Revenue | Credit Write offs from Electric Only Service Areas (Revenue) |  | 136.255 | 11.2392 | 11.4753 | 11.7162 | 11.9623 | 11.6369 | 11.3027 | 10.9133 | 11.1807 | 11.4537 | 11.7324 | 12.017 | 12.3075 | 12.6041 | 12.907 | 13.2163 | 13.532 | 13.8544 | 14.1835 | 14.5195 | 14.8626 | 15.2129 | 15.5706 | 15.9358 | 16.3086 | 16.6893 | 17.0779 | 17.4748 | 17.8799 | 328.3337
|  | Revenue | UEU Electric Write Offs (Revenue)$ |  | 16.2183 | 3.2953 | 3.3645 | 3.4352 | 3.1613 | 2.7993 | 2.3922 | 2.0154 | 1.6545 | 1.3045 | 0.96147 | 0.62209 | 0.2836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25.2893
|  | O&M | UEU Labor & Overhead (O&M) |  | 1.4047 | 0.26682 | 0.27243 | 0.27815 | 0.25711 | 0.22924 | 0.19787 | 0.16885 | 0.14108 | 0.11416 | 0.087779 | 0.061693 | 0.035682 | 0.01394 | 0.014233 | 0.014532 | 0.014837 | 0.015149 | 0.015467 | 0.015791 | 0.016123 | 0.016462 | 0.016807 | 0.01716 | 0.017521 | 0.017889 | 0.018264 | 0.018648 | 0.019039 | 2.3168
|  |  | Total |  | 164.7107 | 14.8014 | 15.1122 | 16.3795 | 16.8807 | 15.2044 | 14.4739 | 13.7239 | 13.6515 | 13.6002 | 13.5663 | 13.5466 | 13.5386 | 13.6011 | 13.9809 | 14.3731 | 14.7782 | 15.1969 | 15.6299 | 16.0779 | 16.5417 | 17.022 | 17.5198 | 18.0361 | 18.5718 | 19.128 | 19.7058 | 20.3066 | 20.9316 | 384.9366
|  |  | Net Benefit |  | 32.8036
CVR
|  | CAPEX | Upgrade Costs |  | 15.5066 | 0.25707 | 0.52699 | 0.54017 | 1.1073 | 1.135 | 1.1634 | 1.59 | 1.8335 | 1.8793 | 1.9263 | 1.9744 | 2.0238 | 2.0744 | 2.1262 | 2.1794 | 2.2339 | 2.2897 | 2.347 | 2.4056 | 2.4658 | 1.685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35.7642
|  | O&M | Management Costs |  | 18.7605 | 0.195 | 0.29213 | 0.39398 | 0.50075 | 0.61262 | 0.72976 | 0.88717 | 1.0698 | 1.261 | 1.4612 | 1.6705 | 1.8894 | 2.1182 | 2.3573 | 2.6069 | 2.8676 | 3.1397 | 3.4236 | 3.7198 | 4.0286 | 4.2768 | 4.3837 | 4.4933 | 4.6056 | 4.7208 | 4.8388 | 4.9598 | 5.0838 | 57.7053
| CVR Costs |  | Total |  | 34.2671 | 0.45207 | 0.81912 | 0.93415 | 1.6081 | 1.7476 | 1.8932 | 2.4772 | 2.9033 | 3.1403 | 3.3874 | 3.6449 | 3.9132 | 4.1926 | 4.4835 | 4.7863 | 5.1015 | 5.4295 | 5.7706 | 6.1254 | 6.4944 | 5.9617 | 4.3837 | 4.4933 | 4.6056 | 4.7208 | 4.8388 | 4.9598 | 5.0838 | 93.4696
|  | O&M | Annual Peak Savings EOL ($) |  | -34.7542 | 0 | -0.082922 | -0.25498 | -0.4356 | -0.84833 | -1.0984 | -1.3604 | -1.7149 | -2.1274 | -2.5595 | -3.0118 | -3.4852 | -3.9803 | -4.498 | -5.0391 | -5.6045 | -6.1949 | -6.8114 | -7.4549 | -8.1262 | -8.8265 | -9.3869 | -9.6215 | -9.8621 | -10.1086 | -10.3613 | -10.6204 | -10.8859 | -112.4943
|  | O&M | Annual Energy Savings EOL($) |  | -60.023 | 0 | -0.12012 | -0.37645 | -0.64706 | -1.3053 | -1.7604 | -2.2226 | -2.8702 | -3.4153 | -4.2564 | -5.312 | -6.044 | -6.2418 | -7.2509 | -8.3108 | -9.1409 | -10.6722 | -12.0941 | -13.6917 | -15.3488 | -16.4452 | -17.2498 | -17.437 | -17.6242 | -17.8113 | -17.9985 | -18.1856 | -18.3728 | -197.6486
| CVR Benefits |  | Total |  | -94.7772 | 0 | -0.20304 | -0.63144 | -1.0827 | -2.1537 | -2.8587 | -3.5829 | -4.5851 | -5.5427 | -6.8159 | -8.3238 | -9.5292 | -10.2221 | -11.7489 | -13.3499 | -14.7454 | -16.8672 | -18.9056 | -21.1465 | -23.475 | -25.2717 | -26.6367 | -27.0585 | -27.4862 | -27.9199 | -28.3598 | -28.806 | -29.2586 | -310.1429
|  |  | Net Benefit |  | 12.8198
Outage
|  | O&M | Automated analysis of system status including outage device prediction | 108.6356 | 59.6485 | 4.5967 | 4.6932 | 4.7918 | 4.8924 | 4.9369 | 4.9794 | 5.0119 | 5.1171 | 5.2246 | 5.3343 | 5.4463 | 5.5607 | 5.6775 | 5.7967 | 5.9184 | 6.0427 | 6.1696 | 6.2992 | 6.4315 | 6.5665 | 6.7044 | 6.8452 | 6.989 | 7.1357 | 7.2856 | 7.4386 | 7.5948 | 7.7543 | 144.4474
|  | O&M | Electric First Response (EFR) Investigations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | O&M | Storm Response Costs | 293.1604 | 161.1037 | 12.1696 | 12.4251 | 12.686 | 12.9524 | 13.18 | 13.4101 | 13.6367 | 13.923 | 14.2154 | 14.514 | 14.8187 | 15.1299 | 15.4477 | 15.7721 | 16.1033 | 16.4415 | 16.7867 | 17.1392 | 17.4992 | 17.8667 | 18.2418 | 18.6249 | 19.0161 | 19.4154 | 19.8231 | 20.2394 | 20.6644 | 21.0984 | 391.2386
|  | O&M | Non-storm response Costs | 52.7972 | 28.3574 | 3.307 | 3.3765 | 3.4474 | 3.5198 | 3.0507 | 2.5437 | 1.9253 | 1.9657 | 2.007 | 2.0492 | 2.0922 | 2.1361 | 2.181 | 2.2268 | 2.2736 | 2.3213 | 2.37 | 2.4198 | 2.4706 | 2.5225 | 2.5755 | 2.6296 | 2.6848 | 2.7412 | 2.7987 | 2.8575 | 2.9175 | 2.9788 | 63.636
|  | O&M | SAIDI Fines | 15.3266 | 8.4094 | 0.65867 | 0.6725 | 0.68663 | 0.70105 | 0.70268 | 0.70367 | 0.70225 | 0.717 | 0.73206 | 0.74743 | 0.76313 | 0.77915 | 0.79552 | 0.81222 | 0.82928 | 0.84669 | 0.86447 | 0.88263 | 0.90116 | 0.92009 | 0.93941 | 0.95914 | 0.97928 | 0.99984 | 1.0208 | 1.0423 | 1.0642 | 1.0865 | 20.3168
Net Benefit
| Outage Total |  | Total | 469.9197 | 257.5189 | 20.732 | 21.1673 | 21.6118 | 22.0657 | 21.8703 | 21.6368 | 21.2761 | 21.7229 | 22.1791 | 22.6449 | 23.1204 | 23.6059 | 24.1017 | 24.6078 | 25.1245 | 25.6522 | 26.1909 | 26.7409 | 27.3024 | 27.8758 | 28.4612 | 29.0589 | 29.6691 | 30.2921 | 30.9283 | 31.5778 | 32.2409 | 32.918 | 619.6389
|  |  | Net Benefit |  | 19.1353
| Total |  |  |  | 361.7196 | 35.9854 | 36.8956 | 38.2941 | 39.4718 | 36.6687 | 35.1451 | 33.8943 | 33.6925 | 33.3769 | 32.7827 | 31.9882 | 31.5285 | 31.6732 | 31.3233 | 30.934 | 30.7865 | 29.9501 | 29.2358 | 28.3592 | 27.4368 | 26.1732 | 24.3257 | 25.14 | 25.9833 | 26.8571 | 27.7626 | 28.7013 | 29.6747 | 787.9022
| Application Net Benefits |  |  |  | 64.7586 | 0 | 0 | -0.95 | -1.6808 | 1.5379 | 3.4467 | 5.322 | 5.8777 | 6.5043 | 7.1921 | 7.9237 | 8.5836 | 9.07 | 9.4282 | 9.7975 | 10.118 | 10.5874 | 11.0328 | 11.5143 | 12.007 | 12.8021 | 13.9564 | 14.0724 | 14.1817 | 14.2834 | 14.3766 | 14.4604 | 14.5337 | 196.6084
Financial Results
|  |  | Costs |  | #VALUE! | 0.0019191 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Benefits |  | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Full Deployment Costs |  |  |  | #VALUE! | 61.4532 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Net Benefits |  | Net Benefits |  | #VALUE! | 0.0019191 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Net Benefits (real) |  | Net Benefits (real) |  | #VALUE! | 0.0020682 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Cumulative Net Benefits |  | Cumulative Net Benefits |  |  | 0.0020682 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
CORP MODEL INPUTS (AMI Metering AND Applications)
| Total O&M |  | Total O&M |  | #VALUE! | 68.1108 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Meter Capital |  | Meter Capital |  | 452.8968 | -6.9147 | 7.4107 | 11.8802 | 104.4984 | 120.6115 | 145.6637 | 18.7678 | 18.808 | 19.4723 | 20.2583 | 21.1045 | 21.8899 | 22.692 | 23.5382 | 24.387 | 25.1805 | 26.0871 | 26.9196 | 27.7443 | 28.5557 | 29.3798 | 28.8567 | 30.0098 | 31.2091 | 32.4563 | 33.7533 | 35.1022 | 36.5049 | 860.4666
| Network/Substation Capital |  | Network |  | 39.2891 | 0.25707 | 0.52699 | 1.4902 | 14.7302 | 14.0241 | 1.4371 | 1.8707 | 2.1213 | 2.1745 | 2.229 | 2.285 | 2.3424 | 2.4012 | 2.4616 | 2.5235 | 2.5871 | 2.6522 | 2.7191 | 2.7876 | 2.858 | 2.0876 | 0.4135 | 0.42467 | 0.43619 | 0.44808 | 0.46034 | 0.47299 | 0.48604 | 70.2889
#VALUE!

## L+G Proposal (R)
L+G Proposal
| ($Millions) |  |  |  | NPV | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
| Year |  |  |  |  | -1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
| COSTS | CAPEX VS O&M
|  |  | Year of Deployment |  |  | -1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
| L+G Managed Service Contract | O&M | L+G Managed Service Contract | This is based on the (read fees) X (annual AMR supported meters). It does not include AMI meters. | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Same as Hybrid AMI | CAPEX | AMR Electric Meter Hardware (Growth) | Continues in non-AMI areas until 2016 | 2.6769 | -1.5776 | 0.6574 | 1.2489 | 1.2411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5698
| Same as Hybrid AMI | CAPEX | AMR Electric Meter Hardware (Maintenance) | Continues in non-AMI areas until 2016 | 0.76656 | 0.2256 | 0.30188 | 0.31488 | 0.26953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1119
| Same as Hybrid AMI | CAPEX | AMR Electric Meter Hardware (Redeployed) | Continues in non-AMI areas until 2016 | 0 | [28 empty] | 0
| Same as Hybrid AMI | CAPEX | AMR Electric Meter Exchange (Growth) | Continues in non-AMI areas until 2016 | 2.0372 | -1.4443 | 0.60126 | 1.1411 | 0.6218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.91989
| Same as Hybrid AMI | O&M | AMR Electric Meter Exchange (Maintenance) | Continues in non-AMI areas until 2016 | 0.61179 | 0.20653 | 0.2761 | 0.2877 | 0.13504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.90537
| Same as Hybrid AMI | CAPEX | AMR Gas Meter Hardware (Growth) | Continues in non-AMI areas until 2016 | 8.4506 | -2.8151 | 2.6901 | 4.1151 | 3.0182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.0083
| Same as Hybrid AMI | CAPEX | AMR Gas Meter Hardware (Maintenance) | Continues in non-AMI areas until 2016 | 2.2746 | 0.96052 | 0.99899 | 1.0479 | 0.55745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5649
| Same as Hybrid AMI | CAPEX | AMR Gas Meter Exchange (Growth) | Continues in non-AMI areas until 2016 | 6.3455 | -2.2638 | 2.1611 | 3.3027 | 1.8732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.0732
| Same as Hybrid AMI | O&M | AMR Gas Meter Exchange (Maintenance) | Continues in non-AMI areas until 2016 | 1.7452 | 0.7724 | 0.80254 | 0.84105 | 0.34597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.762
| Same as Hybrid AMI | CAPEX | AMR Gas Modules for Maintenance | No modules ever purchased by PSE. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Same as Hybrid AMI | O&M | AMR Gas Module Exchanges | Only through 2015. | 0.66371 | 0.31807 | 0.31553 | 0.31574 | 0.12402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0734
| Same as Hybrid AMI | O&M | AMR Gas Module Visits | Only through 2015. | 1.0768 | 0.51603 | 0.51191 | 0.51224 | 0.20121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7414
| Same as Hybrid AMI | O&M | Battery Costs |  | 2.005 | 0.28415 | 0.44381 | 1.0183 | 0.89673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.643
| AMR Meter/ Module Costs |  | Total |  | 28.6538 | -4.8175 | 9.7606 | 14.1456 | 9.2842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.373
| Same as Hybrid AMI | CAPEX | AMI Electric Meter Hardware (Growth) | Begins in 2013, inclds all growth 2016 on. | 145.8937 | 0 | 0 | 0 | 17.2822 | 22.222 | 24.8501 | 23.4797 | 22.91 | 22.6798 | 22.6809 | 22.863 | 23.169 | 20.0758 | 4.1148 | 4.2458 | 4.3661 | 4.5055 | 4.6338 | 4.7602 | 4.8831 | 5.0091 | 6.2965 | 6.5498 | 6.8132 | 7.0873 | 7.3723 | 7.6689 | 7.9773 | 285.4775
| Same as Hybrid AMI | CAPEX | AMI Electric Meter Hardware (Maintenance) | Begins in 2013, inclds all maintenance 2016 on. | 5.6665 | 0 | 0 | 0 | 0.058759 | 0.13555 | 0.22288 | 0.3074 | 0.39175 | 0.47708 | 0.56422 | 0.6538 | 0.7463 | 0.83023 | 0.86166 | 0.89419 | 0.92781 | 0.96262 | 0.99859 | 1.0357 | 1.0741 | 1.1137 | 1.1585 | 1.2051 | 1.2535 | 1.304 | 1.3564 | 1.411 | 1.4677 | 17.1774
| Same as Hybrid AMI | CAPEX | AMI Electric Meter Exchange (Growth) | Begins in 2013, inclds all growth 2016 on. | 32.2648 | 0 | 0 | 0 | 3.3875 | 4.8961 | 5.6497 | 5.1033 | 4.8163 | 4.6367 | 4.5289 | 4.4759 | 4.4593 | 3.9743 | 1.3279 | 1.3689 | 1.4063 | 1.4497 | 1.4895 | 1.5287 | 1.5666 | 1.6055 | 2.0161 | 2.0952 | 2.1773 | 2.2627 | 2.3514 | 2.4436 | 2.5394 | 66.2226
| Same as Hybrid AMI | O&M | AMI Electric Meter Exchange (Maintenance) | Begins in 2013, inclds all maintenance 2016 on. | 1.8259 | 0 | 0 | 0 | 0.019149 | 0.044131 | 0.072495 | 0.099885 | 0.12717 | 0.15472 | 0.1828 | 0.21161 | 0.24132 | 0.26819 | 0.27807 | 0.28829 | 0.29884 | 0.30974 | 0.321 | 0.33262 | 0.3446 | 0.35695 | 0.37094 | 0.38548 | 0.4006 | 0.4163 | 0.43262 | 0.44958 | 0.46721 | 5.5249
| Only Meter Cost | CAPEX | AMI Gas Meter Hardware (Growth) | Begins in 2013 | 52.4513 | 0 | 0 | 0 | 2.3363 | 5.0723 | 5.3333 | 5.0997 | 5.0855 | 5.2692 | 5.4916 | 5.7312 | 5.948 | 6.1674 | 6.3991 | 6.6287 | 6.8372 | 7.0822 | 7.2978 | 7.5081 | 7.7116 | 7.9161 | 6.8293 | 7.104 | 7.3897 | 7.6869 | 7.9961 | 8.3178 | 8.6523 | 137.9252
| Only Meter Cost | CAPEX | AMI Gas Meter Hardware (Maintenance) | Begins in 2013 | 12.6891 | 0 | 0 | 0 | 0.23872 | 0.47786 | 0.62345 | 0.77879 | 0.94423 | 1.1202 | 1.3074 | 1.5062 | 1.6153 | 1.6912 | 1.7702 | 1.8525 | 1.9379 | 2.0267 | 2.1189 | 2.2145 | 2.3134 | 2.4158 | 2.513 | 2.6141 | 2.7192 | 2.8286 | 2.9424 | 3.0607 | 3.1838 | 37.6282
| Same as Hybrid AMI | CAPEX | AMI Gas Meter Exchange (Growth) | Begins in 2013 | 41.6794 | 0 | 0 | 0 | 1.8732 | 4.0629 | 4.2677 | 4.0769 | 4.0615 | 4.2041 | 4.3773 | 4.5637 | 4.7318 | 4.9015 | 5.0806 | 5.2578 | 5.4179 | 5.6065 | 5.7715 | 5.9321 | 6.0869 | 6.2421 | 5.3799 | 5.5908 | 5.81 | 6.0377 | 6.2744 | 6.5204 | 6.776 | 109.3344
| Only Meter Cost | O&M | AMI Gas Meter Exchange (Maintenance) | Begins in 2013 | 10.0632 | 0 | 0 | 0 | 0.1914 | 0.38276 | 0.49889 | 0.62259 | 0.7541 | 0.89381 | 1.0421 | 1.1994 | 1.285 | 1.3441 | 1.4055 | 1.4694 | 1.5356 | 1.6044 | 1.6758 | 1.7496 | 1.826 | 1.905 | 1.9796 | 2.0573 | 2.1379 | 2.2217 | 2.3088 | 2.3993 | 2.4934 | 29.7819
| No Costs | CAPEX | New AMI Gas Modules (Deployments) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAPEX | New AMI Gas Module Exchanges (Deployments) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | O&M | AMI Gas Module Visits |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAPEX | AMI Gas Modules (Maintenance) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | O&M | AMI Gas Modude Exchanges (Maintenance) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | O&M | FTE to Manage Inventory/Testing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| AMI Meter/ Module Costs |  | Total |  | 302.5339 | 0 | 0 | 0 | 25.3872 | 37.2936 | 41.5185 | 39.5682 | 39.0907 | 39.4357 | 40.1752 | 41.2049 | 42.1961 | 39.2527 | 21.2379 | 22.0055 | 22.7275 | 23.5475 | 24.3069 | 25.0615 | 25.8063 | 26.5642 | 26.5438 | 27.6016 | 28.7015 | 29.8452 | 31.0345 | 32.2712 | 33.5572 | 689.0723
| No Costs | CAPEX | AMI Network Installation (Hardware) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAPEX | AMI Network Installation (Labor) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAPEX | AMI Network maintenance (Hardware) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | O&M | AMI Network maintenance (Labor) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | O&M | Manual Meter Reading |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | O&M | Network Overhead and management |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cost of Implimentation of Disconnect/Reconnect Program |  | 0 | [28 empty] | 0
|  |  | Cost of Maintaining Disconnect/Reconnect Program |  | 0 | [28 empty] | 0
| Network Costs |  | Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| No Costs | CAPEX | Software Licence Fee |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAPEX | Set-up and Installation of Command Center |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAPEX | ECC Security Head End Appliances (Per Set) - Requires 1-set each for production, Disaster Recovery, testing (one time cost) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | O&M | Software Maintenance Fee (per endpoint/year) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CAPEX | Deployment Project Management |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| NOC Head End Costs |  | Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
|  |  | Testing/Security |  | 0
| Same as Hybrid AMI | O&M | Backhaul Costs (Licences and Data) |  | 4.1985 | 0 | 0 | 0 | 0.32807 | 0.43388 | 0.40885 | 0.41727 | 0.42587 | 0.43464 | 0.44359 | 0.45273 | 0.46206 | 0.47158 | 0.48129 | 0.49121 | 0.50133 | 0.51166 | 0.5222 | 0.53296 | 0.54394 | 0.55515 | 0.56659 | 0.57826 | 0.59017 | 0.60233 | 0.60711 | 0.61962 | 0.63238 | 10.7556
|  | O&M | Poll Attachment Costs |  | -1.7979 | -0.13473 | -0.13756 | -0.14045 | -0.1434 | -0.14641 | -0.14948 | -0.15262 | -0.15583 | -0.1591 | -0.16244 | -0.16585 | -0.16934 | -0.17289 | -0.17652 | -0.18023 | -0.18401 | -0.18788 | -0.19182 | -0.19585 | -0.19997 | -0.20416 | -0.20845 | -0.21283 | -0.2173 | -0.22186 | -0.22652 | -0.23128 | -0.23614 | -4.371
|  | O&M | Customer Service and Other Overhead |  | 40.753 | 3.1649 | 3.2191 | 3.2744 | 3.3307 | 3.3882 | 3.4469 | 3.5067 | 3.5677 | 3.63 | 3.6935 | 3.7582 | 3.8243 | 3.8916 | 3.9604 | 4.0305 | 4.102 | 4.1749 | 4.2493 | 4.3251 | 4.4025 | 4.4815 | 4.562 | 4.6441 | 4.7279 | 4.8133 | 4.9005 | 4.9894 | 5.08 | 98.1696
|  | O&M | Field Work Reimbursements |  | -3.8456 | -0.95955 | -0.89959 | -0.86644 | -0.76694 | -0.63076 | -0.53862 | -0.44997 | -0.36246 | -0.27535 | -0.18801 | -0.099923 | -0.040247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6.0779
| Telecom and Other Costs |  | Total |  | 39.308 | 2.0706 | 2.1819 | 2.2675 | 2.7485 | 3.0449 | 3.1676 | 3.3214 | 3.4753 | 3.6302 | 3.7866 | 3.9452 | 4.0767 | 4.1903 | 4.2651 | 4.3414 | 4.4193 | 4.4987 | 4.5796 | 4.6622 | 4.7465 | 4.8324 | 4.9201 | 5.0095 | 5.1008 | 5.1938 | 5.2811 | 5.3777 | 5.4763 | 98.4763
|  |  | Total |  | 866.3144 | 25.4678 | 39.6972 | 45.7906 | 69.4187 | 74.1218 | 80.01 | 79.7582 | 81.2241 | 83.6214 | 86.5277 | 89.8259 | 93.1634 | 92.658 | 77.1575 | 80.562 | 84.0494 | 87.7694 | 91.5703 | 95.5148 | 99.6052 | 103.872 | 107.5319 | 112.4498 | 117.5986 | 122.9892 | 128.6255 | 134.5347 | 140.722 | 2121.9547
|  |  | Costs (real) |  | 866.3144 | 27.4467 | 36.8351 | 39.4258 | 55.4604 | 54.9483 | 55.037 | 50.9083 | 48.1061 | 45.9552 | 44.1239 | 42.5033 | 40.9043 | 37.7492 | 29.1679 | 28.2592 | 27.3569 | 26.508 | 25.662 | 24.8375 | 24.0338 | 23.2563 | 22.3399 | 21.6773 | 21.0354 | 20.4135 | 19.8098 | 19.226 | 18.6603 | 873.9512
| O&M Costs |  | O&M Costs |  | 57.2997 | 4.1678 | 4.5318 | 5.2425 | 4.662 | 3.4718 | 3.739 | 4.0439 | 4.3566 | 4.6787 | 5.0115 | 5.3562 | 5.6031 | 5.8026 | 5.9487 | 6.0991 | 6.2537 | 6.4128 | 6.5764 | 6.7445 | 6.9171 | 7.0944 | 7.2707 | 7.4523 | 7.6393 | 7.8318 | 8.0225 | 8.2266 | 8.4369 | 142.9083
| CAPEX |  | CAPEX |  | 313.196 | -6.9147 | 7.4107 | 11.1706 | 32.7579 | 36.8667 | 40.9472 | 38.8458 | 38.2094 | 38.3872 | 38.9503 | 39.7938 | 40.6698 | 37.6405 | 19.5543 | 20.2478 | 20.8931 | 21.6333 | 22.3101 | 22.9792 | 23.6357 | 24.3023 | 24.1932 | 25.1588 | 26.1629 | 27.2072 | 28.2931 | 29.4223 | 30.5966 | 673.0134
| L&G O&M |  | L&G O&M |  | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
BENEFITS
| Metering Net Benefits |  | Net Benefits |  | -253.2686 | 0.0019191 | 3.2758 | 2.9896 | -23.9859 | -28.2436 | -34.0951 | -33.1515 | -33.1596 | -33.8693 | -34.4764 | -35.3247 | -36.1723 | -33.124 | -15.1353 | -16.2165 | -17.5224 | -18.872 | -20.3974 | -22.0307 | -23.5091 | -24.7319 | -25.8717 | -28.0095 | -30.1226 | -32.1135 | -34.3033 | -35.9918 | -39.2856 | -631.4486
| Net Benefits (real) |  | Net Benefits (real) |  | -253.2686 | 0.0020682 | 3.0396 | 2.5741 | -19.1629 | -20.9377 | -23.4532 | -21.16 | -19.6392 | -18.6133 | -17.5809 | -16.7147 | -15.8818 | -13.4949 | -5.7216 | -5.6883 | -5.7033 | -5.6997 | -5.7163 | -5.7288 | -5.6725 | -5.5373 | -5.3749 | -5.3995 | -5.3882 | -5.3301 | -5.2831 | -5.1435 | -5.2094 | -261.4517
| Cumulative Net Benefits |  | Cumulative Net Benefits |  |  | 0.0020682 | 3.0417 | 5.6158 | -13.5472 | -34.4849 | -57.9381 | -79.0981 | -98.7373 | -117.3506 | -134.9315 | -151.6462 | -167.528 | -181.0229 | -186.7445 | -192.4328 | -198.1361 | -203.8358 | -209.5521 | -215.2809 | -220.9534 | -226.4907 | -231.8656 | -237.2651 | -242.6533 | -247.9834 | -253.2665 | -258.41 | -263.6194
CORP MODEL INPUTS (AMI Metering ONLY)
| Total O&M | O&M | Total O&M | 0 | 553.1183 | 32.3825 | 32.2864 | 34.6199 | 36.6608 | 37.2551 | 39.0628 | 40.9125 | 43.0147 | 45.2342 | 47.5774 | 50.0321 | 52.4936 | 55.0175 | 57.6032 | 60.3142 | 63.1562 | 66.1361 | 69.2602 | 72.5355 | 75.9694 | 79.5697 | 83.3387 | 87.291 | 91.4356 | 95.782 | 100.3325 | 105.1124 | 110.1254 | 1448.9413
| Meter Capital | CAPEX | Meter Capital | #VALUE! | 313.196 | -6.9147 | 7.4107 | 11.1706 | 32.7579 | 36.8667 | 40.9472 | 38.8458 | 38.2094 | 38.3872 | 38.9503 | 39.7938 | 40.6698 | 37.6405 | 19.5543 | 20.2478 | 20.8931 | 21.6333 | 22.3101 | 22.9792 | 23.6357 | 24.3023 | 24.1932 | 25.1588 | 26.1629 | 27.2072 | 28.2931 | 29.4223 | 30.5966 | 673.0134
| Network Capital | CAPEX | Network | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AMI Applications
Disconnect/Reconnect
|  | CAPEX | CIS Remote Disconnect and Prepay Enablement | #REF! | 1.6169 | 0 | 0 | 0.95 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.95
|  | O&M | Management Costs (Annual) | #REF! | 9.2158 | 0 | 0 | 0 | 0.5 | 0.539 | 0.58104 | 0.62636 | 0.67522 | 0.72789 | 0.78466 | 0.84587 | 0.91184 | 0.98297 | 1.0596 | 1.1423 | 1.2314 | 1.3274 | 1.431 | 1.5426 | 1.6629 | 1.7926 | 1.9324 | 2.0832 | 2.2457 | 2.4208 | 2.6097 | 2.8132 | 3.0326 | 27.0468
|  | Revenue | Credit Write offs from Electric Only Service Areas (Revenue) | #REF! | 138.4556 | 11.2392 | 11.4753 | 11.7162 | 11.7829 | 11.8165 | 11.8413 | 11.8951 | 11.9701 | 12.0633 | 12.1725 | 12.2958 | 12.432 | 12.6041 | 12.907 | 13.2163 | 13.532 | 13.8544 | 14.1835 | 14.5195 | 14.8626 | 15.2129 | 15.5706 | 15.9358 | 16.3086 | 16.6893 | 17.0779 | 17.4748 | 17.8799 | 332.0968
|  | Revenue | UEU Electric Write Offs (Revenue)$ |  | 16.2183 | 3.2953 | 3.3645 | 3.4352 | 3.1613 | 2.7993 | 2.3922 | 2.0154 | 1.6545 | 1.3045 | 0.96147 | 0.62209 | 0.2836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25.2893
|  | O&M | UEU Labor & Overhead (O&M) |  | 1.4047 | 0.26682 | 0.27243 | 0.27815 | 0.25711 | 0.22924 | 0.19787 | 0.16885 | 0.14108 | 0.11416 | 0.087779 | 0.061693 | 0.035682 | 0.01394 | 0.014233 | 0.014532 | 0.014837 | 0.015149 | 0.015467 | 0.015791 | 0.016123 | 0.016462 | 0.016807 | 0.01716 | 0.017521 | 0.017889 | 0.018264 | 0.018648 | 0.019039 | 2.3168
| Disconnect/Reconnect Total |  | Total | #REF! | 166.9113 | 14.8014 | 15.1122 | 16.3795 | 16.7013 | 15.384 | 15.0124 | 14.7058 | 14.4409 | 14.2099 | 14.0064 | 13.8255 | 13.6631 | 13.6011 | 13.9809 | 14.3731 | 14.7782 | 15.1969 | 15.6299 | 16.0779 | 16.5417 | 17.022 | 17.5198 | 18.0361 | 18.5718 | 19.128 | 19.7058 | 20.3066 | 20.9316 | 388.6997
|  |  | Net Benefit |  | 30.603 | 0 | 0 | -0.95 | -0.94772 | 0.70036 | 1.4097 | 2.0613 | 2.6782 | 3.2688 | 3.8393 | 4.395 | 4.9399 | 5.3927 | 5.4117 | 5.4268 | 5.4374 | 5.4432 | 5.4437 | 5.4383 | 5.4263 | 5.4073 | 5.3805 | 5.3452 | 5.3005 | 5.2456 | 5.1796 | 5.1014 | 5.01 | -363.8143
CVR
|  | CAPEX | Upgrade Costs |  | 15.5066 | 0.25707 | 0.52699 | 0.54017 | 1.1073 | 1.135 | 1.1634 | 1.59 | 1.8335 | 1.8793 | 1.9263 | 1.9744 | 2.0238 | 2.0744 | 2.1262 | 2.1794 | 2.2339 | 2.2897 | 2.347 | 2.4056 | 2.4658 | 1.685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35.7642
|  | O&M | Management Costs |  | 18.7605 | 0.195 | 0.29213 | 0.39398 | 0.50075 | 0.61262 | 0.72976 | 0.88717 | 1.0698 | 1.261 | 1.4612 | 1.6705 | 1.8894 | 2.1182 | 2.3573 | 2.6069 | 2.8676 | 3.1397 | 3.4236 | 3.7198 | 4.0286 | 4.2768 | 4.3837 | 4.4933 | 4.6056 | 4.7208 | 4.8388 | 4.9598 | 5.0838 | 57.7053
| CVR Costs |  | Total |  | 34.2671 | 0.45207 | 0.81912 | 0.93415 | 1.6081 | 1.7476 | 1.8932 | 2.4772 | 2.9033 | 3.1403 | 3.3874 | 3.6449 | 3.9132 | 4.1926 | 4.4835 | 4.7863 | 5.1015 | 5.4295 | 5.7706 | 6.1254 | 6.4944 | 5.9617 | 4.3837 | 4.4933 | 4.6056 | 4.7208 | 4.8388 | 4.9598 | 5.0838 | 93.4696
|  | O&M | Annual Peak Savings EOL ($) |  | -34.7542 | 0 | -0.082922 | -0.25498 | -0.4356 | -0.84833 | -1.0984 | -1.3604 | -1.7149 | -2.1274 | -2.5595 | -3.0118 | -3.4852 | -3.9803 | -4.498 | -5.0391 | -5.6045 | -6.1949 | -6.8114 | -7.4549 | -8.1262 | -8.8265 | -9.3869 | -9.6215 | -9.8621 | -10.1086 | -10.3613 | -10.6204 | -10.8859 | -112.4943
|  | O&M | Annual Energy Savings EOL($) |  | -60.023 | 0 | -0.12012 | -0.37645 | -0.64706 | -1.3053 | -1.7604 | -2.2226 | -2.8702 | -3.4153 | -4.2564 | -5.312 | -6.044 | -6.2418 | -7.2509 | -8.3108 | -9.1409 | -10.6722 | -12.0941 | -13.6917 | -15.3488 | -16.4452 | -17.2498 | -17.437 | -17.6242 | -17.8113 | -17.9985 | -18.1856 | -18.3728 | -197.6486
| CVR Benefits |  | Total |  | -94.7772 | 0 | -0.20304 | -0.63144 | -1.0827 | -2.1537 | -2.8587 | -3.5829 | -4.5851 | -5.5427 | -6.8159 | -8.3238 | -9.5292 | -10.2221 | -11.7489 | -13.3499 | -14.7454 | -16.8672 | -18.9056 | -21.1465 | -23.475 | -25.2717 | -26.6367 | -27.0585 | -27.4862 | -27.9199 | -28.3598 | -28.806 | -29.2586 | -310.1429
|  |  | Net Benefit |  | 12.8198
Outage
|  | O&M | Automated analysis of system status including outage device prediction | 109.2718 | 60.0041 | 4.5967 | 4.6932 | 4.7918 | 4.8924 | 4.9764 | 5.0577 | 5.1389 | 5.2241 | 5.3123 | 5.4035 | 5.4972 | 5.5935 | 5.6923 | 5.7967 | 5.9184 | 6.0427 | 6.1696 | 6.2992 | 6.4315 | 6.5665 | 6.7044 | 6.8452 | 6.989 | 7.1357 | 7.2856 | 7.4386 | 7.5948 | 7.7543 | 145.0547
|  | O&M | Electric First Response (EFR) Investigations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | O&M | Storm Response Costs | 293.646 | 161.3751 | 12.1696 | 12.4251 | 12.686 | 12.9524 | 13.2102 | 13.4699 | 13.7336 | 14.0047 | 14.2824 | 14.5667 | 14.8576 | 15.155 | 15.459 | 15.7721 | 16.1033 | 16.4415 | 16.7867 | 17.1392 | 17.4992 | 17.8667 | 18.2418 | 18.6249 | 19.0161 | 19.4154 | 19.8231 | 20.2394 | 20.6644 | 21.0984 | 391.7021
|  | O&M | Non-storm response Costs | 58.7301 | 31.6739 | 3.307 | 3.3765 | 3.4474 | 3.5198 | 3.419 | 3.2746 | 3.1101 | 2.963 | 2.8253 | 2.694 | 2.5668 | 2.4423 | 2.3192 | 2.2268 | 2.2736 | 2.3213 | 2.37 | 2.4198 | 2.4706 | 2.5225 | 2.5755 | 2.6296 | 2.6848 | 2.7412 | 2.7987 | 2.8575 | 2.9175 | 2.9788 | 69.2994
|  | O&M | SAIDI Fines | 15.4696 | 8.4893 | 0.65867 | 0.6725 | 0.68663 | 0.70105 | 0.71156 | 0.72129 | 0.73081 | 0.74104 | 0.75178 | 0.76297 | 0.77457 | 0.78653 | 0.79885 | 0.81222 | 0.82928 | 0.84669 | 0.86447 | 0.88263 | 0.90116 | 0.92009 | 0.93941 | 0.95914 | 0.97928 | 0.99984 | 1.0208 | 1.0423 | 1.0642 | 1.0865 | 20.4533
| Outage Total |  | Total | 477.1174 | 261.5425 | 20.732 | 21.1673 | 21.6118 | 22.0657 | 22.3171 | 22.5235 | 22.7135 | 22.9328 | 23.1719 | 23.4271 | 23.6962 | 23.9774 | 24.2693 | 24.6078 | 25.1245 | 25.6522 | 26.1909 | 26.7409 | 27.3024 | 27.8758 | 28.4612 | 29.0589 | 29.6691 | 30.2921 | 30.9283 | 31.5778 | 32.2409 | 32.918 | 626.5096
|  |  | Net Benefit |  | 15.1118
Totals
| Applications Total |  |  |  | 367.9437 | 35.9854 | 36.8956 | 38.2941 | 39.2924 | 37.2951 | 36.5704 | 36.3135 | 35.6918 | 34.9793 | 34.005 | 32.8428 | 32.0245 | 31.8409 | 31.3233 | 30.934 | 30.7865 | 29.9501 | 29.2358 | 28.3592 | 27.4368 | 26.1732 | 24.3257 | 25.14 | 25.9833 | 26.8571 | 27.7626 | 28.7013 | 29.6747 | 798.536
| Application Net Benefits |  |  |  | 58.5346 | 0 | 0 | -0.95 | -1.5014 | 0.91156 | 2.0214 | 2.9029 | 3.8784 | 4.9019 | 5.9698 | 7.069 | 8.0876 | 8.9024 | 9.4282 | 9.7975 | 10.118 | 10.5874 | 11.0328 | 11.5143 | 12.007 | 12.8021 | 13.9564 | 14.0724 | 14.1817 | 14.2834 | 14.3766 | 14.4604 | 14.5337 | 185.9746
Financial Results
| Costs |  |  |  | -199.5298 | -221.8865 | 0 | 0 | -25.4873 | -27.3321 | -32.0738 | -30.2486 | -29.2812 | -28.9674 | -28.5067 | -28.2557 | -28.0847 | -24.2216 | -5.7071 | -6.419 | -7.4044 | -8.2846 | -9.3646 | -10.5164 | -11.5021 | -11.9298 | -11.9153 | -13.9371 | -15.9409 | -17.8302 | -19.9267 | -21.5314 | -24.7518
| Benefits |  |  |  | 5.165 | 0 | 3.2758 | 2.0396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| L+G Proposal Costs |  |  |  | 1234.258 | 61.4532 | 76.5928 | 84.0847 | 108.7111 | 111.4169 | 116.5804 | 116.0717 | 116.916 | 118.6007 | 120.5327 | 122.6688 | 125.1879 | 124.4988 | 108.4808 | 111.496 | 114.8359 | 117.7195 | 120.8062 | 123.874 | 127.042 | 130.0452 | 131.8576 | 137.5898 | 143.5819 | 149.8463 | 156.3881 | 163.236 | 170.3967 | 2920.4906
| Net Benefits |  | Net Benefits |  | -194.734 | 0.0019191 | 3.2758 | 2.0396 | -25.4873 | -27.3321 | -32.0738 | -30.2486 | -29.2812 | -28.9674 | -28.5067 | -28.2557 | -28.0847 | -24.2216 | -5.7071 | -6.419 | -7.4044 | -8.2846 | -9.3646 | -10.5164 | -11.5021 | -11.9298 | -11.9153 | -13.9371 | -15.9409 | -17.8302 | -19.9267 | -21.5314 | -24.7518 | -445.474
| Net Benefits (real) |  | Net Benefits (real) |  | -194.734 | 0.0020682 | 3.0396 | 1.7561 | -20.3624 | -20.2619 | -22.0628 | -19.3072 | -17.3422 | -15.9194 | -14.5367 | -13.3699 | -12.3308 | -9.868 | -2.1575 | -2.2516 | -2.41 | -2.5021 | -2.6244 | -2.7347 | -2.7754 | -2.671 | -2.4754 | -2.6867 | -2.8514 | -2.9594 | -3.0689 | -3.077 | -3.2822 | -191.663
| Cumulative Net Benefits |  | Cumulative Net Benefits |  | 0.0020682 | 0.0020682 | 3.0417 | 4.7978 | -15.5646 | -35.8266 | -57.8894 | -77.1965 | -94.5387 | -110.4581 | -124.9948 | -138.3646 | -150.6955 | -160.5635 | -162.7209 | -164.9726 | -167.3826 | -169.8847 | -172.509 | -175.2437 | -178.0191 | -180.6901 | -183.1655 | -185.8522 | -188.7036 | -191.663 | -194.732 | -197.809 | -201.0912
CORP MODEL INPUTS (AMI Metering AND Applications)
| Total O&M |  | Total O&M | 0 | 903.9385 | 68.1108 | 68.655 | 71.4239 | 73.8458 | 73.4152 | 74.4698 | 75.636 | 76.8731 | 78.3342 | 79.6561 | 80.9005 | 82.4943 | 84.784 | 86.8002 | 89.0688 | 91.7089 | 93.7964 | 96.149 | 98.4891 | 100.9404 | 104.0579 | 107.6644 | 112.4309 | 117.419 | 122.6391 | 128.0951 | 133.8137 | 139.8001 | 2209.763
| Meter Capital |  | Meter Capital | 0 | 313.196 | -6.9147 | 7.4107 | 11.1706 | 32.7579 | 36.8667 | 40.9472 | 38.8458 | 38.2094 | 38.3872 | 38.9503 | 39.7938 | 40.6698 | 37.6405 | 19.5543 | 20.2478 | 20.8931 | 21.6333 | 22.3101 | 22.9792 | 23.6357 | 24.3023 | 24.1932 | 25.1588 | 26.1629 | 27.2072 | 28.2931 | 29.4223 | 30.5966 | 673.0134
| Network/Substation Capital |  | Network | 0 | 17.1235 | 0.25707 | 0.52699 | 1.4902 | 2.1073 | 1.135 | 1.1634 | 1.59 | 1.8335 | 1.8793 | 1.9263 | 1.9744 | 2.0238 | 2.0744 | 2.1262 | 2.1794 | 2.2339 | 2.2897 | 2.347 | 2.4056 | 2.4658 | 1.685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37.7142
1234.258

## JM-Dashboard (R)
Cost $MM
|  | NPV 2012-2026 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017
Option 0 - Status Quo | [8 empty] | Network, Meters, Modules; Purchase, Install, Maintain, Read
| O&M Costs | 110.4318 | 4.1697 | 4.5336 | 5.2442 | 8.7399 | 9.8974 | 9.1866
| CAPEX | 265.1467 | -6.9147 | 7.4107 | 11.1706 | 18.703 | 21.9943 | 22.7418 | Meter Growth & Attrition, Modules after 2016, N/W after 2016
| L&G O&M | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Option 4 - Green Field AMI
O&M Costs
CAPEX
L+G O&M
Option 5 - Acclerated L+G | [8 empty] | entire N/W upgrades 2014-2016, Oppotunistic Exchanges, Planned Exchanges
| O&M Costs | 90.5962 | 4.1678 | 4.5318 | 5.2425 | 6.2262 | 5.7703 | 6.2622
| CAPEX | 429.2488 | -6.9147 | 7.4107 | 12.439 | 59.528 | 69.5578 | 53 | All in option 0, plus n/w upgrade and opportunistic/planned meters/modules and exchanges
| L&G O&M | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
Delta between Status Quo and Option 5 |  |  | 2012: Increase/(decrease)
| O&M Costs | -19.8357 | -0.0019191 | -0.0017992 | -0.0017329 | -2.5137 | -4.1271 | -2.9244
| CAPEX | 164.1021 | 0 | 0 | 1.2683 | 40.825 | 47.5634 | 30.2582 | n/w upgrade and opportunistic/planned meters/modules and exchanges
| L&G O&M | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Total | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0
| Total (O&M) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Changes to current 5 year capital budget
Current Budget
|  | Demonstrations | 2013: 0.3
|  | AMI Network | 2016: 10; 2017: 10 | start 1 year earlier
|  | AMI Meters | 2015: 10; 2016: 10; 2017: 10 | start 1 year earlier
|  | Total |  | 0.3 | 0 | 10 | 20 | 20
| Delta SQ to 5 (Incremental Capital) |  |  | 0 | 1.2683 | 40.825 | 47.5634 | 30.2582
| Increase/(decrease) |  |  | -0.3 | 1.2683 | 30.825 | 27.5634 | 10.2582 | 69.6149

## Costs (R)
Pricing Data and Assumptions
AMR Costs
Meters/Modules/Batteries
| AMR Meter Pricing | Meter Cost 2011 | Module Costs 2011 | Post-April 2016 Meter+ Module Cost
ELECTRIC
| Residential Electric Single Phase | XXXXX | XXXXX | XXXXX
| C&I Electric | XXXXX | XXXXX | XXXXX
| Weighted Customer Average | XXXXX | XXXXX | XXXXX
GAS
| Residential Gas | XXXXX | XXXXX | XXXXX
| C&I Gas | XXXXX | XXXXX | XXXXX
| Weighted Customer Average | XXXXX | XXXXX | XXXXX
|  | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
|  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
ELECTRIC AMR
| Weighted Customer Average Electric AMR meter without Module | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Electric Module | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Weighted Customer Average Electric AMR Meter (includes module post 2016) | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
GAS AMR
| Weighted Customer Average Gas AMR meter without Module | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Gas Module | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Weighted Customer Average Gas AMR Meter(includes module post 2016) | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
Installation/Removal/Exchange
| ELECTRIC | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
Electric Installation
| Residential | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Commercial | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Industrial | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Weighted Customer Average | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
Electric Removal
| Residential | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Commercial | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Industrial | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Weighted Customer Average | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Electric Meter Exchange Weighted Customer Average | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| GAS | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
Gas Installation
| Residential | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Commercial | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Industrial | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Weighted Customer Average | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
Gas Removal
| Residential | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Commercial | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Industrial | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Weighted Customer Average | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Gas Meter Exchange Weighted Customer Average | 144.0785 | 146.9601 | 149.8993 | 152.8973 | 155.9552 | 159.0743 | 162.2558 | 165.5009 | 168.8109 | 172.1871 | 175.6309 | 179.1435 | 182.7264 | 186.3809 | 190.1085 | 193.9107 | 197.7889 | 201.7447 | 205.7796 | 209.8952 | 214.0931 | 218.3749 | 222.7424 | 227.1973 | 231.7412 | 236.376 | 241.1036 | 245.9256 | 250.8442
|  | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Gas Module Exchange | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| FTE to Manage Module Maintenance Flags/Inventory/ Testing (Annual $) | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Hybrid AMI ScenarioFTE to Manage Module Maintenance Flags/Inventory/ Testing (Annual $) | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
Electric Module "Maintenance"
| New Electric module purchases for maintenance work | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
AMR Gas Module Maintenance Work
| PSE Gas Module Visits | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| PSE Gas Module Exchanges | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| PSE Gas Module Purchases | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| New PSE Gas Module Purchases | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| New PSE Gas Module Exchanges | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
AMR Gas Module Maintenance Work (Hybrid AMI Scenario)
| PSE Gas Module Visits | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| PSE Gas Module Exchanges | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| PSE Gas Module Purchases | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| New PSE Gas Module Purchases | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| New PSE Gas Module Exchanges | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
Reimbursements
| Gas Module and Field Work Reimbursements | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Electric Module and Field Work Reimbursements | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Meter Shop Reimbursements | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
Gas Battery Program
| Cost of Battery Pruchases | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Cost of Battery Disposals | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Cost of Installations (Labor including overhead) | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Honeywell Alternative | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Total Cost of Battery Program | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
Network Maintenance
|  | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
AMR Network Maintenance Prices and Assumptions
| Network Construction Management (1/2 FTE) | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Network Maintenance Management (FTE) | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| CM Field Visit Price | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| MCC Field Visit Price | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| CM Preventive Maintenance Visit Price | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| CM Installation Price | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Mcc Installation Price | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Price Cellmasters (TOPs) | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Price MCC's (Concentrators) | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Cellmaster annual visits free (TOP) (% of device population) | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| MCC annual visits free (Concentrator) (% of device population) | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Manual Meter Read ($/read/month) | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
Backhaul and FCC Costs
| Backhaul (Data Costs) | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Backhaul (PSE Maintenance) | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| FCC License Renewal Costs | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| FCC Transfer Cost | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
OVERHEAD
| Project Manager for L+G transition | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Unmetered energy (currently billed to L+G) | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Unmetered energy (PSE needs to pay to other utilities) | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Electric Meter Commodities and Standards Engineering | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Gas Module Specification | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
POLE ATTACHMENTS
| 1/2 FTE to Manage Pole Attachments | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| 3rd Party Pole Attachment Leases Estimate | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Performance Analysis (Customer Services expenses, dataraker) | 2012: 2012 Cost
|  | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026
| Meter Shop Annual Expenses | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Customer Service Expenses | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| DataRaker (Cost is per meter per month) | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| DataRaker Reimbursement | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Downtime and Outage Expenses | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| 4 FTE Analysts/Engineers | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| 2 FTE Corporate Managers | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Technology training - Field (8hr day 2x/year - 12 people) Field O&M | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| EA Annual Maintenance Fee | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Server Hardware and Software Maintenance Analyst | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Total Performance Costs | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
L+G Contract Costs and Terms
|  | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
| L+G Meter read fee | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Effective Read Fee | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| L+G Proposal | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Annual Contract Costs | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| L+G Read Fee without credits pre 4/1/2016 | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| L+G Read Fee without credits post 4/1/2016 | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| L+G Credits | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Load Research & Energy Efficiency Portion | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| L+G Budgeted Contract Costs (IT Only) | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| L+G Budgeted Contract Costs (Incl. IT, EE and LR) | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Hypothetical AMR extension | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Annual Contract Costs (Model Calculated) | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Annual Contract Costs with Credits (Model Calculated) | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Annual Contract Costs with Credits minus load Research portion (Model Calculated) | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| L+G Proposal | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| PSE Read Fees with L+G Hypothetical L+G Extension | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
Termination Costs
| Prior to 4/1/2016 | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| After 4/1/2016 | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
Combined Meter Reduction Fee
Pre 4/1/2016
| Electric | 2012: XXXXX; 2013: XXXXX; 2014: XXXXX; 2015: XXXXX; 2016: XXXXX; 2017: XXXXX; 2018: XXXXX; 2019: XXXXX; 2020: XXXXX; 2021: XXXXX; 2022: XXXXX
| Gas | 2012: XXXXX; 2013: XXXXX; 2014: XXXXX; 2015: XXXXX; 2016: XXXXX; 2017: XXXXX; 2018: XXXXX; 2019: XXXXX; 2020: XXXXX; 2021: XXXXX; 2022: XXXXX
| Customer Average | 2012: XXXXX; 2013: XXXXX; 2014: XXXXX; 2015: XXXXX; 2016: XXXXX; 2017: XXXXX; 2018: XXXXX; 2019: XXXXX; 2020: XXXXX; 2021: XXXXX; 2022: XXXXX
| 4/1/2016 to 10/1/2022 | 2012: XXXXX; 2013: XXXXX; 2014: XXXXX; 2015: XXXXX; 2016: XXXXX; 2017: XXXXX; 2018: XXXXX; 2019: XXXXX; 2020: XXXXX; 2021: XXXXX; 2022: XXXXX
|  | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
| Total Meter Minimum | XXXXX 2012: XXXXX; XXXXX 2013: XXXXX; XXXXX 2014: XXXXX; XXXXX 2015: XXXXX; XXXXX 2016: XXXXX; XXXXX 2017: XXXXX; XXXXX 2018: XXXXX; XXXXX 2019: XXXXX; XXXXX 2020: XXXXX; XXXXX 2021: XXXXX; XXXXX 2022: XXXXX; XXXXX 2023: XXXXX
| Electric Meter Minimum | XXXXX 2012: XXXXX; XXXXX 2013: XXXXX; XXXXX 2014: XXXXX; XXXXX 2015: XXXXX; XXXXX 2016: XXXXX; XXXXX 2017: XXXXX; XXXXX 2018: XXXXX; XXXXX 2019: XXXXX; XXXXX 2020: XXXXX; XXXXX 2021: XXXXX; XXXXX 2022: XXXXX; XXXXX 2023: XXXXX
| Gas Meter Minimum | XXXXX 2012: XXXXX; XXXXX 2013: XXXXX; XXXXX 2014: XXXXX; XXXXX 2015: XXXXX; XXXXX 2016: XXXXX; XXXXX 2017: XXXXX; XXXXX 2018: XXXXX; XXXXX 2019: XXXXX; XXXXX 2020: XXXXX; XXXXX 2021: XXXXX; XXXXX 2022: XXXXX; XXXXX 2023: XXXXX
| Total Cushion | XXXXX 2012: XXXXX; XXXXX 2013: XXXXX; XXXXX 2014: XXXXX; XXXXX 2015: XXXXX; XXXXX 2016: XXXXX; XXXXX 2017: XXXXX; XXXXX 2018: XXXXX; XXXXX 2019: XXXXX; XXXXX 2020: XXXXX; XXXXX 2021: XXXXX; XXXXX 2022: XXXXX; XXXXX 2023: XXXXX
| Electric Cushion | XXXXX 2012: XXXXX; XXXXX 2013: XXXXX; XXXXX 2014: XXXXX; XXXXX 2015: XXXXX; XXXXX 2016: XXXXX; XXXXX 2017: XXXXX; XXXXX 2018: XXXXX; XXXXX 2019: XXXXX; XXXXX 2020: XXXXX; XXXXX 2021: XXXXX; XXXXX 2022: XXXXX; XXXXX 2023: XXXXX
| Gas Cushion | XXXXX 2012: XXXXX; XXXXX 2013: XXXXX; XXXXX 2014: XXXXX; XXXXX 2015: XXXXX; XXXXX 2016: XXXXX; XXXXX 2017: XXXXX; XXXXX 2018: XXXXX; XXXXX 2019: XXXXX; XXXXX 2020: XXXXX; XXXXX 2021: XXXXX; XXXXX 2022: XXXXX; XXXXX 2023: XXXXX
| Cushion Growth | XXXXX 2012: XXXXX; XXXXX 2013: XXXXX; XXXXX 2014: XXXXX; XXXXX 2015: XXXXX; XXXXX 2016: XXXXX; XXXXX 2017: XXXXX; XXXXX 2018: XXXXX; XXXXX 2019: XXXXX; XXXXX 2020: XXXXX; XXXXX 2021: XXXXX; XXXXX 2022: XXXXX; XXXXX 2023: XXXXX
Numbers in red below are assumed:
| Meter Floor | XXXXX 2012: XXXXX; XXXXX 2013: XXXXX; XXXXX 2014: XXXXX; XXXXX 2015: XXXXX; XXXXX 2016: XXXXX; XXXXX 2017: XXXXX; XXXXX 2018: XXXXX; XXXXX 2019: XXXXX; XXXXX 2020: XXXXX; XXXXX 2021: XXXXX; XXXXX 2022: XXXXX; XXXXX 2023: XXXXX; XXXXX 2024: XXXXX; XXXXX 2025: XXXXX; XXXXX 2026: XXXXX; XXXXX 2027: XXXXX
AMI Pricing
|  | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
AMI Meters/Modules
| Residential Electric | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Commercial Electric | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Industrial Electric | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Weighted Electric Average | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
|  | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Residential Gas Module | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Commercial Gas Module | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Industrial Gas Module | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Weighted Average Gas Module | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Weighted Average Gas Meter/Module | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
Installation/Removal/Exchange
|  | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
Electric Meter Exchange
| Selective Meter Exchange Cost | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| L+G Deployment Cost (Weighted Average) | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| L+G Deployment Cost Residential | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| L+G Deployment Cost C&I (Polyphase) | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Meter Minimum Electric Meter Exchange | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Meter Floor Electric Meter Exchange | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Full Deployment Electric Meter Exchange | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Mass Deployment Pricing Electric Meter Exchange | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
Gas Module Exchange Model Inputs
| Gas Module Exchange | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Gas Module Exchange Full Deployment | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Other Pricing Numbers for Reference | 2012: Gradual; 2013: Full-Deploy
| Electric Meter Exchange Silver Spring | 2012: XXXXX; 2013: XXXXX
| Gas Module Exchange Silver Spring | 2012: XXXXX; 2013: XXXXX
Two way Network Deployment and Maintenance
| Manual Meter Reads $/year | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| AMI Network Pricing | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
Hardware
| Access Point (Silver Spring) | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Concentrator (Silver Spring) | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Price AMI Collectors (TOP) (CAPEX) (L+G) | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Price AMI Routers (Concentrators) (CAPEX) (L+G) | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Network Hardware Cost (Hybrid Network new Vendor) | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Network Hardware Cost (Greenfield Scenarios New Vendor) | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Hybrid-L+G AMI Upgrade | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| % of Status Quo Already Hybrid-L+G | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
Saas, NOC, Set-up Costs
| Set-up, installation, config. Of command center (one time) | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Project Management (one time over three years) | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Software License Fee (per endpoint/one-time) | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Software Maintenance Fee (per endpoint/year) | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| ECC Security Head End Appliances (Per Set) - Requires 1-set each for production, Disaster Recovery, testing (one time cost) | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Appliances for disaster recovery (per year) | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Backhaul Costs (per Collector/month) | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
Deployment
| AMI Collector Preventive Maintenance Cost | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| AMI Concentrator Preventive Maintenance Cost | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| AMI Collector Installation Price (CAPEX)-outsourced | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| AMI Router/Concentrator Installation Price (CAPEX)-outsourced | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Network Deployment Cost (Network Replacement) | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Network Deployment Cost (Dual Network) | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Hybrid-L+G Upgrade | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| % of Status Quo Already Hybrid-L+G | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Smartsynch Pricing | 2012: ($)
| Single-phase meter | 2012: XXXXX; 2013: XXXXX
| Polyphase meter | 2012: XXXXX; 2013: XXXXX
| ZigBee Communications Adder | 2012: XXXXX; 2013: XXXXX
| Average PSE | 2012: XXXXX; 2013: XXXXX
|  | XXXXX | XXXXX
| Cellular Two-way $/Meter/Month | 2012: XXXXX; 2013: XXXXX
| Residential | 2012: XXXXX; 2013: XXXXX
| Commercial | 2012: XXXXX; 2013: XXXXX
| PSE Average | 2012: XXXXX; 2013: XXXXX
Total Intellectual Property Development Cost (millions $)
XXXXX
Note on B180: vdrehe: Zero growth is assumed because of a strenghtening meshing network

## Quantities (R)
Assumptions and Rates | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
| 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
Financial Assumptions
Discount Rate | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Inflation Materials | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Inflation Labor | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Inflation Fuel | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
June 2011 CPI-U All items less shelter | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
| XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
TCO Contract Escalation pre 2016 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Growth Rate of L+G Contract Costs post 2023 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
TCO Contract Escalation post 2016 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Cost Assumptions
AMR Electric Meter/Module Failure Rate (% population requiring Exchange annually given a declining population i.e. AMI transition Scenarios) | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
AMR Electric Meter/Module Failure Rate (% population requiring Exchange annually given a replenishing population i.e. Status Quo Scenario) | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
AMR Gas Module Failure Rate (% module population requiring Exchange annually) | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
L+G AMR Gas Module Exchange Rate | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
PSE AMR Gas Module Exchange Rate | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
PSE AMR Gas Module Visits Rate | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
% of Module Work Reimbursements MARP/MDMS | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
% of Module Work Reimbursements ZCON | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
AMI Rates
AMI Electric Meter Failure/Retirement Rate | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
AMI Gas Meter Failture/Retirement Rate | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
AMI Gas Module Failure Rate (% Population Requiring exchange annually) | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
AMI Gas Module Visit Rate | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
L+G Billable Meters | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
AMR Network growth | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Stores Overhead % | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Network Maintenance Assumptions | AMR | AMI
% of current AMR network converted to AMI | XXXXXX | XXXXXX
L&G Cellmaster maintenance visits | XXXXXX | XXXXXX
L&G MCC maintenance visits | XXXXXX | XXXXXX
Network Equipment (Cellmasters and MCCs) Failure Rate | XXXXXX | XXXXXX
Manual Meter Reading Assumptions
Manual Meter Reading with AMI | XXXXXX
Manual Meter Reading with AMR | XXXXXX
2011 Electric Customers | XXXXXX
2011 Gas Customers | XXXXXX
PSE Customer Forecast
Year | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
| 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
Electric Customer Forecast | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Gas Customer Forecast | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Total | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
L+G Billable Meters | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Gas Only | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Electric Only | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Electric and Gas Combined | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
| XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Total Gas Customers | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
% Electric | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
% Natural Gas | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Customer Growth Rate |  | -2.448% | 1.461% | 2.403% | 2.556% | 2.537% | 2.439% | 2.216% | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Electric Customer Average Growth Rate 2010-2019 | 1.56%
Gas Customer Average Growth Rate 2010-2020 | 2.2%
Annual Meter Retirements
Electric | 0.4114% | 0.4114% | 0.5329% | 0.5329% | 0.5329% | 0.5329% | 0.5329% | 0.6373% | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Gas | 0.68% | 0.68% | 0.68% | 0.68% | 0.68% | 0.68% | 0.68% | 0.68% | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
PSE Gas Module Exchange Rate | 6.326% | 6.04% | 5.767% | 5.506% | 5.258% | 5.258% | 5.258% | 5.258% | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
2011 Customers (% of total) | Electric | Gas
Residential | 51.77% | 38.22%
Commercial | 6.514% | 2.952%
Industrial&Other | 0.3863% | 0.1618%
% of total customer | 58.67% | 41.33%
Status Quo Annual Meter Replacements (Growth vs Attrition)
Electric Total Replacements | 4602.9313 | -26813.8976 | 18633.7072 | 29751.1293 | 31512.6103 | 31004.3722 | 29664.7307 | 29276.8452 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Growth | 0 | -31288.1156 | 12769.7671 | 23760.5687 | 25386.7633 | 24746.65 | 23282.9333 | 21508.0647 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Attrition | 4602.9313 | 4474.218 | 5863.9401 | 5990.5605 | 6125.847 | 6257.7223 | 6381.7974 | 7768.7805 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Growth % | 0% | 116.7% | 68.53% | 79.86% | 80.56% | 79.82% | 78.49% | 73.46% | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Attrition % | 100% | -16.69% | 31.47% | 20.14% | 19.44% | 20.18% | 21.51% | 26.54% | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Gas Total Replacements | 13540.5805 | -10148.1226 | 19770.9515 | 27101.2909 | 29686.4689 | 31378.8871 | 32319.2044 | 30817.711 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Growth | 8180 | -15403.9562 | 14417.0817 | 21600.5375 | 24022.3634 | 25541.1021 | 26302.562 | 24633.5604 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Attirtion | 5360.5805 | 5255.8336 | 5353.8698 | 5500.7534 | 5664.1055 | 5837.785 | 6016.6424 | 6184.1506 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Growth % | 60.41% | 151.8% | 72.92% | 79.7% | 80.92% | 81.4% | 81.38% | 79.93% | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Attrition % | 39.59% | -51.79% | 27.08% | 20.3% | 19.08% | 18.6% | 18.62% | 20.07% | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Hybrid AMI Scenario AMR Annual Meter Replacements (Growth vs Attrition)
Electric Total Replacements | 4602.9313 | -26813.8976 | 18633.7072 | 29751.1293 | 15449.9553 | 0 | 0 | 0 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Growth | 0 | -31288.1156 | 12769.7671 | 23760.5687 | 12693.3817 | 0 | 0 | 0 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Attrition | 4602.9313 | 4474.218 | 5863.9401 | 5990.5605 | 2756.5736 | 0 | 0 | 0 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Growth % | 0% | 116.7% | 68.53% | 79.86% | 80.56% | 79.82% | 78.49% | 73.46% | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Attrition % | 100% | -16.69% | 31.47% | 20.14% | 19.44% | 20.18% | 21.51% | 26.54% | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
[9 empty] | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Gas Total Replacements | 13540.5805 | -10148.1226 | 19770.9515 | 27101.2909 | 14229.603 | 0 | 0 | 0 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Growth | 8180 | -15403.9562 | 14417.0817 | 21600.5375 | 12011.1817 | 0 | 0 | 0 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Attirtion | 5360.5805 | 5255.8336 | 5353.8698 | 5500.7534 | 2218.4213 | 0 | 0 | 0 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Growth % | 60.41% | 151.8% | 72.92% | 79.7% | 80.92% | 81.4% | 81.38% | 79.93% | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Attrition % | 39.59% | -51.79% | 27.08% | 20.3% | 19.08% | 18.6% | 18.62% | 20.07% | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
[9 empty] | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
|  | 0 | 0 | 295454.144 | 318168.8378 | 256902.2397 | 247811.4677 | 243978.6079 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Cumulative AMI Deployment by Option
Year | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
Hybrid AMI | 0 | 0 | 0 | 0 | 295454.144 | 613622.9818 | 870525.2214 | 1118336.6892 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Electric (Business) | 0 | 0 | 0 | 0 | 32865.2301 | 93785.3271 | 166836.6553 | 226523.8589 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Electric (Fill-in) | 0 | 0 | 0 | 0 | 82109.0762 | 165985.7703 | 251525.531 | 338601.5821 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Gas (Business) | 0 | 0 | 0 | 0 | 42349.6056 | 114638.4167 | 172266.3061 | 219142.3961 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Gas (Fill-in) | 0 | 0 | 0 | 0 | 138130.232 | 239213.4677 | 279896.729 | 334068.8521 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Gradual AMI | 0 | 0 | 69719.1136 | 137470.1489 | 209378.0516 | 282391.5067 | 354822.8092 | 423910.8783 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Hybrid-New Vendor | 0 | 0 | 0 | 0 | 92842.6997 | 162365.4088 | 227133.7145 | 284474.551 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Meter Minimum | 0 | 0 | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Meter Floor | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Hybrid-L+G | 0 | 0 | 69719.1136 | 137470.1489 | 209378.0516 | 282391.5067 | 354822.8092 | 423910.8783 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Two Vendors - Two Networks | 0 | 0 | 0 | 0 | 295454.144 | 613622.9818 | 870525.2214 | 1118336.6892 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
L+G Electric | 0 | 0 | 0 | 0 | 114974.3063 | 259771.0974 | 418362.1863 | 565125.441 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
New Vendor Gas | 0 | 0 | 0 | 0 | 180479.8376 | 353851.8844 | 452163.0351 | 553211.2482 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Full Deployment | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | 2082357.0072 | 2128498.6323 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Electric | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | 1197556.6501 | 1219064.7149 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Gas | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | 884800.357 | 909433.9174 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Full Deployment % Two-Way (Cumulatively Deployed) | 0% | 0% | 0% | 0% | #VALUE! | #VALUE! | 100% | 100% | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Electric | 0% | 0% | 0% | 0% | #VALUE! | #VALUE! | 100% | 100% | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Gas | 0% | 0% | 0% | 0% | #VALUE! | #VALUE! | 100% | 100% | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
AMR Meters by Option
Hybrid AMI Scenario | 1907218.75 | 1860526.6782 | 1887713.527 | 1933074.6332 | 1687029.6159 | 1419148.5301 | 1211831.7857 | 1010161.9431 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Electric | 1118898.0833 | 1087609.9678 | 1100379.7348 | 1124140.3036 | 1034552.7606 | 914502.6194 | 779194.4638 | 653939.2739 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Gas | 788320.6667 | 772916.7105 | 787333.7922 | 808934.3296 | 652476.8553 | 504645.9107 | 432637.3219 | 356222.6692 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
[9 empty] | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Full Deployment Scenario | 1907218.75 | 1860526.6782 | 1887713.527 | 1933074.6332 | #VALUE! | #VALUE! | 0 | 0 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Electric | 1118898.0833 | 1087609.9678 | 1100379.7348 | 1124140.3036 | #VALUE! | #VALUE! | 0 | 0 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Gas | 788320.6667 | 772916.7105 | 787333.7922 | 808934.3296 | #VALUE! | #VALUE! | 0 | 0 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
L+G Supported Meters by Option
Year | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026
Hybrid AMI Scenario | 1907218.75 | 1860526.6782 | 1887713.527 | 1933074.6332 | 1687029.6159 | 1419148.5301 | 1211831.7857 | 1010161.9431 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Gradual AMI | 1907218.75 | 1860526.6782 | 1817994.4134 | 1795604.4843 | 1773105.7083 | 1750380.0052 | 1727534.198 | 1704587.754 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Hybrid-New Vendor | 1907218.75 | 1860526.6782 | 1887713.527 | 1933074.6332 | 1259760.7067 | 623468.701 | 0 | 0 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Meter Minimum | 1907218.75 | 1860526.6782 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Meter Floor | 1907218.75 | 1860526.6782 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Hybrid-L+G | 1907218.75 | 1860526.6782 | 1887713.527 | 1933074.6332 | 1982483.7598 | 2032771.5119 | 2082357.0072 | 2128498.6323 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
L+G Proposal | 1907218.75 | 1860526.6782 | 1887713.527 | 1933074.6332 | 1982483.7598 | 2032771.5119 | 2082357.0072 | 2128498.6323 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Two Vendors-Two Networks | 1907218.75 | 1860526.6782 | 1887713.527 | 1933074.6332 | 1802003.9222 | 1678919.6275 | 1630193.972 | 1575287.3841 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Full Deployment | 1907218.75 | 1860526.6782 | 1887713.527 | 1933074.6332 | #VALUE! | #VALUE! | 0 | 0 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
AMR Meters on Two-way Network | [8 empty] | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Hybrid-New Vendor | 0 | 0 | 0 | 0 | 629880.3534 | 1246937.402 | 1855223.2927 | 1844024.0813 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Number of Meters Manually Read | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2026 % of Total Population | [13 empty] | Notes
Gradual AMI | 0 | 0 | 55.7753 | 109.9761 | 167.5024 | 225.9132 | 283.8582 | 339.1287 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Hybrid-New Vendor | 0 | 0 | 0 | 0 | 20490.3325 | 40546.3725 | 60314.3129 | 59997.19 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Meter Minimum | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Meter Floor | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Full Deployment | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | 1665.8856 | 1702.7989 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Network Hardware Numbers Based on Scenario
AMR Network Hardware Growth (status quo)
Cellmasters | 167 | 171.175 | 175.4544 | 179.8407 | 184.3368 | 188.9452 | 193.6688 | 198.5105 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
MCC's | 8230 | 8435.75 | 8646.6437 | 8862.8098 | 9084.3801 | 9311.4896 | 9544.2768 | 9782.8838 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
AMI Network Hardware Growth for Two Networks Two Vendors | [8 empty] | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Access Point | 217.1 | 217.1 | 217.1 | 217.1 | 217.1 | 217.1 | 217.1 | 217.1 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Concentrator | 10699 | 10699 | 10699 | 10699 | 10699 | 10699 | 10699 | 10699 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
AMI Network Hardware (for Network Hybrid Scenario including Gas Territory) (New Vendor) | 0
Access Point | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Concentrator | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
AMI Network Hardware Growth for Greenfield Scenarios
Access Point | 595 | 595 | 595 | 595 | 595 | 595 | 595 | 595 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Concentrator | 1783 | 1783 | 1783 | 1783 | 1783 | 1783 | 1783 | 1783 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Hybrid-L+G Network Hardware for Territory Wide (Hybrid AMI Scenario, Two Vendors and Full Deployment)
Take Out Point | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Concentrator | 8230 | 8230 | 8230 | 8230 | 8230 | 8230 | 8230 | 8230 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Gas Battery Maintenance
Full Time PSE Employees | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Battery Purchase |  | 25000 | 55000 | 95000 | 95000 |  |  |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Batteries change-outs in non-program years (quantity yearly) | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Batteries change-outs in Battery Replacement Program years (quantity Yearly) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
All Poletop Devices (MCCs, concentrators) | 8152 | %
|  |  | % Hybrid-L+G in 2012 | 13.54%
PSE Gas Only Service Territory
Gas Only TOPs | 369 | 25%
Gas Only Poletop Population (Concentrators and MCCs) | 1107 | 75%
Total Non-PSE Poletops (% of Total Devices) | 1476 | 18.11%
Concentrators | 177 | 15.99%
MCCs | 930 | 84.01%
PSE Electric Only and Electric and Gas Service Territory
Total PSE Only Territory (% of total) | 6680 | 81.94%
Concentrators | 877 | 13.13%
MCCs | 5562 | 83.26%
Other | 241 | 3.608%
All Oportunistic Exchanges
Poor Performing LP and Demand Meters |  |  |  | 2666.6667 | 2666.6667 | 2666.6667
CVR Meters
Credit Remote Disconnect/Reconnect Program Meters |  |  |  | 56000
UEU Remote Disconnect/Reconnect Program Meters

## Applications (hidden)
| 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026
Manual Meter Read ($/read/month) | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
Read Fees | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
Difference | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Cost for 0.05% manual read rate | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Cost for 1% manual read rate | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Cost for 2% manual read rate | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Cost for 3% manual read rate | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Savings for 0.05% manual read rate | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Savings for 1% manual read rate | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Savings for 2% manual read rate | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!

## Disconnect TCO
Disconnect/Reconnect Scenario TCO
|  |  | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
Status Quo
Costs ($ Millions)
| CIS Remote Disconnect and Prepay Enablement |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Management Costs (Annual) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Credit Write offs from Electric Only Service Areas (Revenue) |  | 11.2392 | 11.4753 | 11.7162 | 11.9623 | 12.2135 | 12.47 | 12.7318 | 12.9992 | 13.2722 | 13.5509 | 13.8355 | 14.126 | 14.4227 | 14.7255 | 15.0348 | 15.3505 | 15.6729 | 16.002 | 16.338 | 16.6811 | 17.0314 | 17.3891 | 17.7543 | 18.1271 | 18.5078 | 18.8964 | 19.2933 | 19.6984
| UEU Electric Write Offs (Revenue)$ |  | 3.2953 | 3.3645 | 3.4352 | 3.5073 | 3.581 | 3.6562 | 3.7329 | 3.8113 | 3.8914 | 3.9731 | 4.0565 | 4.1417 | 4.2287 | 4.3175 | 4.4081 | 4.5007 | 4.5952 | 4.6917 | 4.7903 | 4.8909 | 4.9936 | 5.0984 | 5.2055 | 5.3148 | 5.4264 | 5.5404 | 5.6567 | 5.7755
| UEU Labor & Overhead (O&M) |  | 0.26682 | 0.27243 | 0.27815 | 0.28399 | 0.28995 | 0.29604 | 0.30226 | 0.30861 | 0.31509 | 0.3217 | 0.32846 | 0.33536 | 0.3424 | 0.34959 | 0.35693 | 0.36443 | 0.37208 | 0.37989 | 0.38787 | 0.39602 | 0.40433 | 0.41282 | 0.42149 | 0.43035 | 0.43938 | 0.44861 | 0.45803 | 0.46765
| Total |  | 14.8014 | 15.1122 | 15.4295 | 15.7536 | 16.0844 | 16.4222 | 16.767 | 17.1191 | 17.4786 | 17.8457 | 18.2204 | 18.6031 | 18.9937 | 19.3926 | 19.7999 | 20.2156 | 20.6402 | 21.0736 | 21.5162 | 21.968 | 22.4293 | 22.9004 | 23.3813 | 23.8723 | 24.3736 | 24.8854 | 25.408 | 25.9416
Hybrid AMI
Costs ($ Millions)
| CIS Remote Disconnect and Prepay Enablement |  | 0 | 0 | 0.95 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Management Costs (Annual) |  | 0 | 0 | 0 | 0.5 | 0.539 | 0.58104 | 0.62636 | 0.67522 | 0.72789 | 0.78466 | 0.84587 | 0.91184 | 0.98297 | 1.0596 | 1.1423 | 1.2314 | 1.3274 | 1.431 | 1.5426 | 1.6629 | 1.7926 | 1.9324 | 2.0832 | 2.2457 | 2.4208 | 2.6097 | 2.8132 | 3.0326
| Credit Write offs from Electric Only Service Areas (Revenue) |  | 11.2392 | 11.4753 | 11.7162 | 11.7829 | 11.8165 | 11.8413 | 11.8951 | 11.9701 | 12.0633 | 12.1725 | 12.2958 | 12.432 | 12.6041 | 12.907 | 13.2163 | 13.532 | 13.8544 | 14.1835 | 14.5195 | 14.8626 | 15.2129 | 15.5706 | 15.9358 | 16.3086 | 16.6893 | 17.0779 | 17.4748 | 17.8799
| UEU Electric Write Offs (Revenue)$ |  | 3.2953 | 3.3645 | 3.4352 | 3.1613 | 2.7993 | 2.3922 | 2.0154 | 1.6545 | 1.3045 | 0.96147 | 0.62209 | 0.2836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| UEU Labor & Overhead (O&M) |  | 0.26682 | 0.27243 | 0.27815 | 0.25711 | 0.22924 | 0.19787 | 0.16885 | 0.14108 | 0.11416 | 0.087779 | 0.061693 | 0.035682 | 0.01394 | 0.014233 | 0.014532 | 0.014837 | 0.015149 | 0.015467 | 0.015791 | 0.016123 | 0.016462 | 0.016807 | 0.01716 | 0.017521 | 0.017889 | 0.018264 | 0.018648 | 0.019039
| Total |  | 14.8014 | 15.1122 | 15.4295 | 15.2013 | 14.845 | 14.4314 | 14.0794 | 13.7657 | 13.482 | 13.2217 | 12.9796 | 12.7513 | 12.6181 | 12.9213 | 13.2308 | 13.5468 | 13.8695 | 14.1989 | 14.5353 | 14.8787 | 15.2294 | 15.5874 | 15.9529 | 16.3261 | 16.7072 | 17.0962 | 17.4934 | 17.899
Full Deployment
Costs ($ Millions)
| CIS Remote Disconnect and Prepay Enablement |  | 0 | 0 | 0.95 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Management Costs (Annual) |  | 0 | 0 | 0 | 0.5 | 0.539 | 0.58104 | 0.62636 | 0.67522 | 0.72789 | 0.78466 | 0.84587 | 0.91184 | 0.98297 | 1.0596 | 1.1423 | 1.2314 | 1.3274 | 1.431 | 1.5426 | 1.6629 | 1.7926 | 1.9324 | 2.0832 | 2.2457 | 2.4208 | 2.6097 | 2.8132 | 3.0326
| Credit Write offs from Electric Only Service Areas (Revenue) |  | 11.2392 | 11.4753 | 11.7162 | 11.9623 | 11.6369 | 11.3027 | 10.9133 | 11.1807 | 11.4537 | 11.7324 | 12.017 | 12.3075 | 12.6041 | 12.907 | 13.2163 | 13.532 | 13.8544 | 14.1835 | 14.5195 | 14.8626 | 15.2129 | 15.5706 | 15.9358 | 16.3086 | 16.6893 | 17.0779 | 17.4748 | 17.8799
| UEU Electric Write Offs (Revenue)$ |  | 3.2953 | 3.3645 | 3.4352 | 3.1613 | 2.7993 | 2.3922 | 2.0154 | 1.6545 | 1.3045 | 0.96147 | 0.62209 | 0.2836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| UEU Labor & Overhead (O&M) |  | 0.26682 | 0.27243 | 0.27815 | 0.25711 | 0.22924 | 0.19787 | 0.16885 | 0.14108 | 0.11416 | 0.087779 | 0.061693 | 0.035682 | 0.01394 | 0.014233 | 0.014532 | 0.014837 | 0.015149 | 0.015467 | 0.015791 | 0.016123 | 0.016462 | 0.016807 | 0.01716 | 0.017521 | 0.017889 | 0.018264 | 0.018648 | 0.019039
| Total |  | 14.8014 | 15.1122 | 15.4295 | 15.3807 | 14.6654 | 13.8928 | 13.0976 | 12.9763 | 12.8723 | 12.7816 | 12.7007 | 12.6268 | 12.6181 | 12.9213 | 13.2308 | 13.5468 | 13.8695 | 14.1989 | 14.5353 | 14.8787 | 15.2294 | 15.5874 | 15.9529 | 16.3261 | 16.7072 | 17.0962 | 17.4934 | 17.899
Assumptions
Prepay Costs ($ Millions)
|  | 2013 | 2013 1: 2014; 2014 2: 2015; 2015 3: 2016; 2016 4: 2017
| CIS Remote Disconnect and Prepay Enablement | 0 | 2013 1: 0.95; 2014 2: 0.95; 2015 3: 0; 2016 4: 0
| Management Costs (Annual) | 0.5
Assumptions/Data
| Discount Rate | 7.8%
| Inflation Rate | 2.1%
| % Electric One-way in Hybrid AMI Scenario |  | 100% | 100% | 100% | 90.13% | 78.17% | 65.43% | 53.99% | 43.41% | 33.52% | 24.2% | 15.34% | 6.847% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| % Electric One-way in Full Deployment Scenario |  | 100% | 100% | 100% | 100% | 68.3% | 35.81% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Data from the IT 5 year Project Portfolio
| ($ Millions) | 2013 | 2013 1: 2014; 2014 2: 2015; 2015 3: 2016; 2016 4: 2017; 2017 5: Total
| CIS Phase 2: Remote connect/disconnect & Smart Meter enablement | 0 | 2013 1: 0.65; 2014 2: 0.65; 2015 3: 0; 2016 4: 0; 2017 5: 1.3
| CIS Phase 2: Pre paid meter billing enablement | 0 | 2013 1: 0.3; 2014 2: 0.3; 2015 3: 0; 2016 4: 0; 2017 5: 0.6
|  | 0 | 2013 1: 0.95; 2014 2: 0.95; 2015 3: 0; 2016 4: 0; 2017 5: 1.9

## CVR TCO
CVR TCO | NOTE: All updates to this sheet should be made in the original spreadsheet "CVR Analysis Updated 2013.xls" on SharePoint, and then pasted into this model.
| -1 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
| 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
Program Information
Yearly Substations Upgraded (EOL) | 3 | 6 | 6 | 6 | 6 | 6 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative Substations Upgraded (EOL) | 3 | 9 | 15 | 21 | 27 | 33 | 41 | 50 | 59 | 68 | 77 | 86 | 95 | 104 | 113 | 122 | 131 | 140 | 149 | 158 | 164 | 164 | 164 | 164 | 164 | 164 | 164 | 164
Cost of Substation Upgrade LDC ($) | -85690 | -87832.25 | -90028.0562 | -92278.7577 | -94585.7266 | -96950.3698 | -99374.129 | -101858.4822 | -104404.9443 | -107015.0679 | -109690.4446 | -112432.7057 | -115243.5233 | -118124.6114 | -121077.7267 | -124104.6699 | -127207.2866 | -130387.4688 | -133647.1555 | -136988.3344 | -140413.0428 | -143923.3688 | -147521.4531 | -151209.4894 | -154989.7266 | -158864.4698 | -162836.0815 | -166906.9836
Cost of Substation Upgrade EOL ($) | -171380 | -175664.5 | -180056.1125 | -184557.5153 | -189171.4532 | -193900.7395 | -198748.258 | -203716.9645 | -208809.8886 | -214030.1358 | -219380.8892 | -224865.4114 | -230487.0467 | -236249.2229 | -242155.4534 | -248209.3398 | -254414.5733 | -260774.9376 | -267294.311 | -273976.6688 | -280826.0855 | -287846.7377 | -295042.9061 | -302418.9788 | -309979.4532 | -317728.9396 | -325672.1631 | -333813.9671
Meters | 1500 | 3000 | 3000 | 3000 | 3000 | 3000 | 4000 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Variable Program Management Costs ($)/Substation | -15000 | -15375 | -15759.375 | -16153.3594 | -16557.1934 | -16971.1232 | -17395.4013 | -17830.2863 | -18276.0435 | -18732.9445 | -19201.2682 | -19681.2999 | -20173.3324 | -20677.6657 | -21194.6073 | -21724.4725 | -22267.5843 | -22824.2739 | -23394.8808 | -23979.7528 | -24579.2466 | -25193.7278 | -25823.571 | -26469.1602 | -27130.8892 | -27809.1615 | -28504.3905 | -29217.0003
Fixed Program Management Costs ($) (1FTE Engineer) | -150000 | -153750 | -157593.75 | -161533.5938 | -165571.9336 | -169711.2319 | -173954.0127 | -178302.8631 | -182760.4346 | -187329.4455 | -192012.6816 | -196812.9987 | -201733.3236 | -206776.6567 | -211946.0731 | -217244.725 | -222675.8431 | -228242.7392 | -233948.8077 | -239797.5278 | -245792.466 | -251937.2777 | -258235.7096 | -264691.6024 | -271308.8924 | -278091.6147 | -285043.9051 | -292170.0027
Fixed Program Management Costs ($) (1FTE Engineer and 1/2 an IT Analyst) | -225000 | -230625 | -236390.625 | -242300.3906 | -248357.9004 | -254566.8479 | -260931.0191 | -267454.2946 | -274140.6519 | -280994.1682 | -288019.0224 | -295219.498 | -302599.9855 | -310164.9851 | -317919.1097 | -325867.0875 | -334013.7646 | -342364.1088 | -350923.2115 | -359696.2918 | -368688.6991 | -377905.9165 | -387353.5645 | -397037.4036 | -406963.3387 | -417137.4221 | -427565.8577 | -438255.0041
Energy and Capacity Costs
Average Avoided Energy Cost ($/MWh) | 42.51 | 44.34 | 46.32 | 47.77 | 50.72 | 54.15 | 56.58 | 59.41 | 58.41 | 62.02 | 67.42 | 67.95 | 62.98 | 66.36 | 69.59 | 70.54 | 76.37 | 80.68 | 85.54 | 90.17 | 91.17 | 92.17 | 93.17 | 94.17 | 95.17 | 96.17 | 97.17 | 98.17
Average Avoided Capacity Cost ($/kW-year) | 202.15 | 207.2038 | 212.3838 | 217.6934 | 223.1358 | 228.7142 | 234.432 | 240.2928 | 246.3001 | 252.4576 | 258.7691 | 265.2383 | 271.8693 | 278.666 | 285.6327 | 292.7735 | 300.0928 | 307.5951 | 315.285 | 323.1671 | 331.2463 | 339.5275 | 348.0157 | 356.716 | 365.634 | 374.7748 | 384.1442 | 393.7478
PSE Annual Load Forecast (GWh) | 23209.3998 | 23235.2217 | 23447.6577 | 23597.5183 | 23776.6086 | 23751.8275 | 23813.3272 | 23924.318 | 24445.4595 | 24977.9529 | 25522.0455 | 26077.9901 | 26646.0447 | 27226.4733 | 27819.5453 | 28425.5361 | 29044.7272 | 29677.406 | 30323.8665 | 30984.4087 | 31659.3395 | 32348.9722 | 33053.6272 | 33773.6315 | 34509.3197 | 35261.0333 | 36029.1215 | 36813.9408
PSE Peak Load Forecast (MW) | 4897.9595 | 4930.2792 | 4969.9512 | 4984.585 | 5008.5741 | 5028.9256 | 5032.4265 | 5049.75 | 5030.8814 | 5033.5695 | 5084.3527 | 5154.6938 | 5231.5237 | 5309.0081 | 5388.7803 | 5470.5157 | 5559.1609 | 5652.1393 | 5497.0754
Savings Calculations
Annual Peak Savings LDC (kW) | 0 | 400.1951 | 1200.5852 | 2000.9753 | 2801.3654 | 3601.7555 | 4402.1456 | 5469.3324 | 6669.9176 | 7870.5028 | 9071.0879 | 10271.6731 | 11472.2583 | 12672.8434 | 13873.4286 | 15074.0138 | 16274.599 | 17475.1841 | 18675.7693 | 19876.3545 | 21076.9396 | 21877.3297 | 21877.3297 | 21877.3297 | 21877.3297 | 21877.3297 | 21877.3297 | 21877.3297 | 331094.7098
Annual Peak Savings LDC ($) | 0 | 82921.9164 | 254984.8929 | 435599.192 | 625084.8405 | 823772.5219 | 1032003.9094 | 1314241.3422 | 1642801.6777 | 1986968.6292 | 2347317.1772 | 2724441.2973 | 3118954.55 | 3531490.6897 | 3962704.2897 | 4413271.388 | 4883890.151 | 5375281.5576 | 5888190.1032 | 6423384.5251 | 6981658.5492 | 7427954.4439 | 7613653.3049 | 7803994.6376 | 7999094.5035 | 8199071.8661 | 8404048.6627 | 8614149.8793 | 105213858.7026
Annual Energy Savings LDC (MWh) | 0 | 2709.0835 | 8127.2506 | 13545.4177 | 18963.5847 | 24381.7518 | 29799.9188 | 37024.1416 | 45151.3922 | 53278.6428 | 61405.8934 | 69533.144 | 77660.3946 | 85787.6452 | 93914.8958 | 102042.1464 | 110169.397 | 118296.6475 | 126423.8981 | 134551.1487 | 142678.3993 | 148096.5664 | 148096.5664 | 148096.5664 | 148096.5664 | 148096.5664 | 148096.5664 | 148096.5664 | 2241315.1085
Annual Energy Savings LDC ($) | 0 | 120120.7638 | 376454.2476 | 647064.6015 | 961833.0171 | 1320271.8591 | 1686079.4084 | 2199604.2524 | 2637292.818 | 3304341.4257 | 4139985.3319 | 4724777.1333 | 4891051.6502 | 5692868.1333 | 6535537.5961 | 7198053.004 | 8413636.8452 | 9544173.5241 | 10814300.247 | 12132477.0816 | 13007989.667 | 13650060.5246 | 13798157.091 | 13946253.6574 | 14094350.2238 | 14242446.7902 | 14390543.3566 | 14538639.923 | 184349603.487
Upgrade Costs LDC | -257070 | -526993.5 | -540168.3375 | -553672.5459 | -567514.3596 | -581702.2186 | -794993.0321 | -916726.3401 | -939644.4986 | -963135.6111 | -987214.0013 | -1011894.3514 | -1037191.7101 | -1063121.5029 | -1089699.5405 | -1116942.029 | -1144865.5797 | -1173487.2192 | -1202824.3997 | -1232895.0097 | -842478.2566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -17760170.5435
Management Costs | -195000 | -292125 | -393984.375 | -500754.1406 | -612616.1543 | -729758.2973 | -887165.4649 | -1069817.1783 | -1261046.9989 | -1461169.6748 | -1670510.3302 | -1889404.7872 | -2118199.8982 | -2357253.8867 | -2606936.6997 | -2867630.3697 | -3139729.3877 | -3423641.0876 | -3719786.0417 | -4028598.4678 | -4276788.9092 | -4383708.6319 | -4493301.3477 | -4605633.8814 | -4720774.7284 | -4838794.0966 | -4959763.949 | -5083758.0478 | -67016768.785
LDC Overall Program | -452070 | -616075.8198 | -302713.5721 | 28237.1069 | 406787.3437 | 832583.8652 | 1035924.8208 | 1527302.0762 | 2079402.9983 | 2867004.7691 | 3829578.1776 | 4547919.292 | 4854614.5919 | 5803983.4334 | 6801605.6456 | 7626751.9934 | 9012932.0289 | 10322326.7749 | 11779879.9088 | 13294368.1291 | 14870381.0505 | 16694306.3365 | 16918509.0482 | 17144614.4136 | 17372669.9989 | 17602724.5596 | 17834828.0703 | 18069031.7545 | 204786522.8612
NPV LDC Program | NOTE: All updates to this sheet should be made in the original spreadsheet "CVR Analysis Updated 2013.xls" on SharePoint, and then pasted into this model. -1: 41110047.3278
Annual Peak Savings EOL ($) | 0 | 103652.3955 | 318731.1161 | 544498.99 | 781356.0506 | 1029715.6524 | 1290004.8867 | 1642801.6777 | 2053502.0972 | 2483710.7865 | 2934146.4716 | 3405551.6216 | 3898693.1876 | 4414363.3621 | 4953380.3621 | 5516589.235 | 6104862.6888 | 6719101.947 | 7360237.629 | 8029230.6564 | 8727073.1866 | 9284943.0548 | 9517066.6312 | 9754993.297 | 9998868.1294 | 10248839.8326 | 10505060.8284 | 10767687.3491 | 131517323.3782
Annual Peak Savings EOL (kW) | 0 | 500.2438 | 1500.7315 | 2501.2191 | 3501.7067 | 4502.1944 | 5502.682 | 6836.6655 | 8337.397 | 9838.1285 | 11338.8599 | 12839.5914 | 14340.3228 | 15841.0543 | 17341.7858 | 18842.5172 | 20343.2487 | 21843.9802 | 23344.7116 | 24845.4431 | 26346.1745 | 27346.6622 | 27346.6622 | 27346.6622 | 27346.6622 | 27346.6622 | 27346.6622 | 27346.6622 | 413868.3873
Annual Energy Savings EOL($) | 0 | 150150.9547 | 470567.8094 | 808830.7519 | 1202291.2713 | 1650339.8239 | 2107599.2605 | 2749505.3155 | 3296616.0225 | 4130426.7822 | 5174981.6649 | 5905971.4166 | 6113814.5627 | 7116085.1667 | 8169421.9951 | 8997566.255 | 10517046.0565 | 11930216.9051 | 13517875.3088 | 15165596.352 | 16259987.0838 | 17062575.6557 | 17247696.3637 | 17432817.0717 | 17617937.7797 | 17803058.4877 | 17988179.1957 | 18173299.9037 | 230437004.3588
Annual Energy Savings EOL(MWh) | 0 | 3386.3544 | 10159.0632 | 16931.7721 | 23704.4809 | 30477.1897 | 37249.8986 | 46280.177 | 56439.2402 | 66598.3035 | 76757.3667 | 86916.43 | 97075.4932 | 107234.5565 | 117393.6197 | 127552.6829 | 137711.7462 | 147870.8094 | 158029.8727 | 168188.9359 | 178347.9992 | 185120.708 | 185120.708 | 185120.708 | 185120.708 | 185120.708 | 185120.708 | 185120.708 | 2801643.8856
Upgrade Costs | -514140 | -1053987 | -1080336.675 | -1107345.0919 | -1135028.7192 | -1163404.4372 | -1589986.0641 | -1833452.6802 | -1879288.9972 | -1926271.2221 | -1974428.0027 | -2023788.7027 | -2074383.4203 | -2126243.0058 | -2179399.0809 | -2233884.058 | -2289731.1594 | -2346974.4384 | -2405648.7994 | -2465790.0193 | -1684956.5132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -35520341.0869
Management Costs | -195000 | -292125 | -393984.375 | -500754.1406 | -612616.1543 | -729758.2973 | -887165.4649 | -1069817.1783 | -1261046.9989 | -1461169.6748 | -1670510.3302 | -1889404.7872 | -2118199.8982 | -2357253.8867 | -2606936.6997 | -2867630.3697 | -3139729.3877 | -3423641.0876 | -3719786.0417 | -4028598.4678 | -4276788.9092 | -4383708.6319 | -4493301.3477 | -4605633.8814 | -4720774.7284 | -4838794.0966 | -4959763.949 | -5083758.0478 | -67016768.785
EOL Overall Program | -709140 | -1092308.6498 | -685022.1245 | -254769.4906 | 236002.4485 | 786892.7418 | 920452.6182 | 1489037.1347 | 2209782.1236 | 3226696.6718 | 4464189.8036 | 5398329.5482 | 5819924.4318 | 7046951.6362 | 8336466.5766 | 9412641.0624 | 11192448.1982 | 12878703.3261 | 14752678.0967 | 16700438.5211 | 19025314.848 | 21963810.0787 | 22271461.6472 | 22582176.4873 | 22896031.1807 | 23213104.2237 | 23533476.0751 | 23857229.2051 | 259417217.8651
NPV EOL Program | NOTE: All updates to this sheet should be made in the original spreadsheet "CVR Analysis Updated 2013.xls" on SharePoint, and then pasted into this model. -1: 49704541.8036
AMI Peak Savings | 0 | 20730.4791 | 63746.2232 | 108899.798 | 156271.2101 | 205943.1305 | 258000.9773 | 328560.3355 | 410700.4194 | 496742.1573 | 586829.2943 | 681110.3243 | 779738.6375 | 882872.6724 | 990676.0724 | 1103317.847 | 1220972.5378 | 1343820.3894 | 1472047.5258 | 1605846.1313 | 1745414.6373 | 1856988.611 | 1903413.3262 | 1950998.6594 | 1999773.6259 | 2049767.9665 | 2101012.1657 | 2153537.4698 | 26303464.6756
AMI Energy Savings | 0 | 30030.1909 | 94113.5619 | 161766.1504 | 240458.2543 | 330067.9648 | 421519.8521 | 549901.0631 | 659323.2045 | 826085.3564 | 1034996.333 | 1181194.2833 | 1222762.9125 | 1423217.0333 | 1633884.399 | 1799513.251 | 2103409.2113 | 2386043.381 | 2703575.0618 | 3033119.2704 | 3251997.4168 | 3412515.1311 | 3449539.2727 | 3486563.4143 | 3523587.5559 | 3560611.6975 | 3597635.8391 | 3634659.9807 | 46087400.8718
AMI Installation Premium | -257070 | -526993.5 | -540168.3375 | -553672.5459 | -567514.3596 | -581702.2186 | -794993.0321 | -916726.3401 | -939644.4986 | -963135.6111 | -987214.0013 | -1011894.3514 | -1037191.7101 | -1063121.5029 | -1089699.5405 | -1116942.029 | -1144865.5797 | -1173487.2192 | -1202824.3997 | -1232895.0097 | -842478.2566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -17760170.5435
Annual Incrimental Savings | -257070 | -476232.83 | -382308.5524 | -283006.5976 | -170784.8952 | -45691.1233 | -115472.2026 | -38264.9414 | 130379.1254 | 359691.9027 | 634611.626 | 850410.2563 | 965309.8399 | 1242968.2028 | 1534860.931 | 1785889.069 | 2179516.1694 | 2556376.5512 | 2972798.1879 | 3406070.392 | 4154933.7975 | 5269503.7421 | 5352952.599 | 5437562.0737 | 5523361.1818 | 5610379.6641 | 5698648.0048 | 5788197.4506 | 54630695.0039
NPV Incrimental Savings | NOTE: All updates to this sheet should be made in the original spreadsheet "CVR Analysis Updated 2013.xls" on SharePoint, and then pasted into this model. -1: 8594494.4759 | 8594494.4759
% Incremental Savings | NOTE: All updates to this sheet should be made in the original spreadsheet "CVR Analysis Updated 2013.xls" on SharePoint, and then pasted into this model. -1: 20.91%
AMI Hybrid Network Scenario | bar: NOTE: All updates to this sheet should be made in the original spreadsheet "CVR Analysis Updated 2013.xls" on SharePoint, and then pasted into this model. 19
Yearly Substations Upgraded (LDC) | 0 | 0 | 0 | 6 | 6 | 6 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative Substations Upgraded (LDC) | 0 | 0 | 0 | 6 | 12 | 18 | 26 | 35 | 44 | 53 | 62 | 71 | 80 | 89 | 98 | 107 | 116 | 125 | 134 | 143 | 149 | 149 | 149 | 149 | 149 | 149 | 149 | 149
Annual Peak Savings LDC (kW) | 0 | 400.1951 | 1200.5852 | 2000.9753 | 2801.3654 | 2801.3654 | 2801.3654 | 2801.3654 | 2801.3654 | 2801.3654 | 2801.3654 | 2801.3654 | 2801.3654 | 2801.3654 | 2801.3654 | 2801.3654 | 2801.3654 | 2801.3654 | 2801.3654 | 2801.3654 | 2801.3654 | 2801.3654 | 2801.3654 | 2801.3654 | 2801.3654 | 2801.3654 | 2801.3654 | 2801.3654 | 62430.4288
Annual Peak Savings LDC ($) | 0 | 82921.9164 | 254984.8929 | 435599.192 | 625084.8405 | 640711.9615 | 656729.7605 | 673148.0045 | 689976.7047 | 707226.1223 | 724906.7753 | 743029.4447 | 761605.1808 | 780645.3103 | 800161.4431 | 820165.4792 | 840669.6162 | 861686.3566 | 883228.5155 | 905309.2284 | 927941.9591 | 951140.5081 | 974919.0208 | 999291.9963 | 1024274.2962 | 1049881.1536 | 1076128.1824 | 1103031.387 | 17765358.5256
Annual Energy Savings LDC (MWh) | 0 | 2709.0835 | 8127.2506 | 13545.4177 | 18963.5847 | 18963.5847 | 18963.5847 | 18963.5847 | 18963.5847 | 18963.5847 | 18963.5847 | 18963.5847 | 18963.5847 | 18963.5847 | 18963.5847 | 18963.5847 | 18963.5847 | 18963.5847 | 18963.5847 | 18963.5847 | 18963.5847 | 18963.5847 | 18963.5847 | 18963.5847 | 18963.5847 | 18963.5847 | 18963.5847 | 18963.5847 | 422617.0309
Annual Energy Savings LDC ($) | 0 | 120120.7638 | 376454.2476 | 647064.6015 | 961833.0171 | 1026878.1127 | 1072959.6235 | 1126626.5683 | 1107662.9836 | 1176121.5244 | 1278524.8819 | 1288575.5818 | 1194326.5657 | 1258423.4821 | 1319675.8608 | 1337691.2662 | 1448248.9652 | 1529982.0153 | 1622145.0371 | 1709946.4343 | 1728910.019 | 1747873.6038 | 1766837.1885 | 1785800.7732 | 1804764.3579 | 1823727.9426 | 1842691.5274 | 1861655.1121 | 30437447.4752
Upgrade Costs LDC | -257070 | -526993.5 | -540168.3375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1324231.8375
Annual Peak Savings EOL ($) | 0 | 0 | 0 | 0 | 223244.5859 | 457651.4011 | 703639.0291 | 1041776.6737 | 1437451.468 | 1852258.8917 | 2286908.2793 | 2742132.4745 | 3218688.5618 | 3717358.6207 | 4238950.5022 | 4784298.6286 | 5354264.8172 | 5949739.1287 | 6571640.7402 | 7220918.8453 | 7898553.5802 | 8435710.4583 | 8646603.2198 | 8862768.3003 | 9084337.5078 | 9311445.9455 | 9544232.0941 | 9782837.8965 | 94728895.7144
Annual Peak Savings EOL (kW) | 0 | 0 | 0 | 0 | 1000.4876 | 2000.9753 | 3001.4629 | 4335.4464 | 5836.1779 | 7336.9094 | 8837.6408 | 10338.3723 | 11839.1037 | 13339.8352 | 14840.5667 | 16341.2981 | 17842.0296 | 19342.761 | 20843.4925 | 22344.224 | 23844.9554 | 24845.4431 | 24845.4431 | 24845.4431 | 24845.4431 | 24845.4431 | 24845.4431 | 24845.4431 | 302647.5113
Annual Energy Savings EOL($) | 0 | 0 | 0 | 0 | 343511.7918 | 733484.3662 | 1149599.5966 | 1743588.7366 | 2307631.2158 | 3080318.2782 | 4033441.5917 | 4755457.5043 | 5047451.5576 | 5992492.7719 | 6991139.9766 | 7803199.0531 | 9223966.6234 | 10564161.5343 | 12069531.5257 | 13638858.4642 | 14716317.4239 | 15501974.2238 | 15670163.1597 | 15838352.0956 | 16006541.0316 | 16174729.9675 | 16342918.9034 | 16511107.8393 | 167211182.5227
Annual Energy Savings EOL(MWh) | 0 | 0 | 0 | 0 | 6772.7088 | 13545.4177 | 20318.1265 | 29348.4049 | 39507.4682 | 49666.5314 | 59825.5947 | 69984.6579 | 80143.7211 | 90302.7844 | 100461.8476 | 110620.9109 | 120779.9741 | 130939.0374 | 141098.1006 | 151257.1638 | 161416.2271 | 168188.9359 | 168188.9359 | 168188.9359 | 168188.9359 | 168188.9359 | 168188.9359 | 168188.9359 | 2048744.4208
Upgrade Costs | 0 | 0 | 0 | -1107345.0919 | -1135028.7192 | -1163404.4372 | -1589986.0641 | -1833452.6802 | -1879288.9972 | -1926271.2221 | -1974428.0027 | -2023788.7027 | -2074383.4203 | -2126243.0058 | -2179399.0809 | -2233884.058 | -2289731.1594 | -2346974.4384 | -2405648.7994 | -2465790.0193 | -1684956.5132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -34440004.4119
Management Costs | -195000 | -292125 | -393984.375 | -500754.1406 | -612616.1543 | -729758.2973 | -887165.4649 | -1069817.1783 | -1261046.9989 | -1461169.6748 | -1670510.3302 | -1889404.7872 | -2118199.8982 | -2357253.8867 | -2606936.6997 | -2867630.3697 | -3139729.3877 | -3423641.0876 | -3719786.0417 | -4028598.4678 | -4276788.9092 | -4383708.6319 | -4493301.3477 | -4605633.8814 | -4720774.7284 | -4838794.0966 | -4959763.949 | -5083758.0478 | -57705335.7393
AMI Adjusted EOL Overall Program | -452070 | -616075.8198 | -302713.5721 | -525435.439 | 406029.3618 | 965563.1069 | 1105776.4808 | 1681870.1247 | 2402386.3759 | 3428483.9196 | 4678843.1954 | 5616001.5154 | 6029488.5475 | 7265423.2926 | 8563592.002 | 9643839.9994 | 11437689.4748 | 13134953.5088 | 15021110.9773 | 16980644.485 | 19309977.5599 | 22252990.1621 | 22565221.2411 | 22880579.284 | 23199142.4651 | 23520990.9126 | 23846206.7583 | 24174874.1871 | 216673312.2491
NPV EOL Program | NOTE: All updates to this sheet should be made in the original spreadsheet "CVR Analysis Updated 2013.xls" on SharePoint, and then pasted into this model. -1: 52100930.2305
NPV Incrimental Savings | NOTE: All updates to this sheet should be made in the original spreadsheet "CVR Analysis Updated 2013.xls" on SharePoint, and then pasted into this model. -1: 10990882.9028
% Incremental Savings | NOTE: All updates to this sheet should be made in the original spreadsheet "CVR Analysis Updated 2013.xls" on SharePoint, and then pasted into this model. -1: 26.74%
-31409950.2661 | -452070 | -819118.5 | -934152.7125 | -1608099.2325 | -1747644.8735 | -1893162.7345 | -2477151.529 | -2903269.8585 | -3140335.9961 | -3387440.8969 | -3644938.3328 | -3913193.49 | -4192583.3185 | -4483496.8925 | -4786335.7806 | -5101514.4276 | -5429460.5471 | -5770615.5261 | -6125434.8411 | -6494388.4872 | -5961745.4224 | -4383708.6319 | -4493301.3477 | -4605633.8814 | -4720774.7284
83510880.4967 | 0 | 203042.6802 | 631439.1404 | 1082663.7935 | 2153674.2352 | 2858725.8414 | 3582928.0098 | 4585139.9832 | 5542722.372 | 6815924.8166 | 8323781.5283 | 9529195.0053 | 10222071.866 | 11748920.1851 | 13349927.7826 | 14745354.427 | 16867150.0219 | 18905569.0348 | 21146545.8184 | 23475032.9722 | 25271722.9823 | 26636698.794 | 27058522.5888 | 27486213.1654 | 27919917.1935
52100930.2305
Note on F141: WASMS9: number applies to "Other categorry of costs in Financial Summary" sheets

## OMS TCO
Key
Input Value
Calculated Value
Assumption
not included in model
Inputs | Hard/ Soft | FTE | Hard Value | Inputs | Source | Comments | Assumptions/ Source | TCO Status Quo Cost | AMI TCO | Annual Savings
Financial Drivers
Discount Rate |  |  | 7% |  | Julie Witt | From template (plug)
Inflation Rate |  |  | 2.1% |  | Julie Witt | From template (plug)
Payroll Overhead Rate |  |  | 61% |  | Julie Witt | From template (plug) | [5 empty] | b) Automated analysis of system status including outage device prediction | 172376.1312
Potelco crew size |  |  | 4 |  | David Brodie | [6 empty] | a) Investigations savings | 0
Depreciation Rate |  |  | 15% |  |  |  | Plug |  |  |  |  | Outages
Discount Rate |  |  | 7.8% |  | Plug |  | Typical discount rate |  |  |  |  | % of outages requiring "hunting"
Asset Life (years) |  |  | 30 |  | Finance | From template (plug) | [5 empty] | Hours spent hunting per outage
Salvage Value (% of total cost) |  |  | 10% |  | Finance | From template (plug) | [5 empty] | FTE
Annual FTE Hours |  |  | 2080 |  | Larissa Ljubarskaya | May not be needed | 1 FTE= 2080 hours |  |  |  |  | 1) Total Storm Response savings | 131562.7488
Blended FTE Rate |  |  |  |  | Julie Witt | Currently not used
[12 empty] | 2) Non Storm Response Savings | 1607443.872
SYSTEM SUPPORT- TOTAL |  |  | 54500 | [8 empty] | Average SAIDI fine per year | 38745.4
Capital - DMS Retirement |  |  | 45000 | 45000 | George Hendrickson
ESRI (Intolight) |  |  | 2500 | 2500 | Ray Harris
Custom Call Out Tool |  |  | 7000 | 7000 | Need to confirm
IT Support for DMS | Hard | 0 | 0 |  | Confirm if there are no savings- John McClain |  | Benefit to begin in Y3 (2013)
Reduction in FTEs (ECS analysts) |  |  |  |  | George Hendrickson | Review MRT process maps | Reduction in ECS Analysts
Hourly FTE Rate |  |  |  | 40 | Michele Gould |  | Currently $30 with 3.4% raise in 2012
Annual FTE LoadedRate |  |  |  | 133952
Capital- custom call out tool replacement
CLX |  |  |  |  | Bob Bisschoff | Will likely not be a reduction in costs to maintain CLX. License is based on a per meter count.
DDD |  |  |  |  | Ernie Willard | Little to no maintenance costs
ORGANIZATION AND PROCESS- TOTAL |  |  | 3831975.2064 |  |  |  |  | 20731957.104 | 18781828.952 | 1950128.152
1) Total System Operations savings |  |  | 1220386.44
a) Manual wallboard savings | Soft | 0.5 | 71212.232
FTE |  |  |  | 0.5 | Bruce Bjorklund |  | PSE Estimate
Hourly FTE Rate |  |  |  | 42.53 | Bruce Bjorklund |  | Sys ops base rate
Annual FTE LoadedRate |  |  |  | 142424.464
b) Automated analysis of system status including outage device prediction | Soft | 9.2 | 1149174.208 |  |  |  |  | 4596696.832 | 4424320.7008 | 172376.1312
Total FTEs in department |  |  |  | 46 | Bruce Bjorklund |  | number includes dispatch and supervisors
Estimated Efficiency gains |  |  |  | 20% | PA | Discussed efficiencies with Gas Mobile Worce implementation (John Klippert) as a benchmark. | Per best practice of implementing OMS, there will be a 20% efficiency in job skills role consolidation, better automated monitoring and analysis of the electrical system. Additional gains in auto call out, load prediction, printing, and mapping | Steve Kerr (PA) suggests another 1-5% improvement. | 23%
FTE efficiency |  |  |  | 9.2 |  |  |  |  | 10.58
Hourly FTE Rate |  |  |  | 37.3 | Bruce Bjorklund |  | Sys ops base rate (low range)
Annual FTE LoadedRate |  |  |  | 124910.24
Inputs | Hard/ Soft | FTE | Hard Value | Inputs | Source | Comments | Assumptions/ Source
2) Total Service Provider (Field Operations) |  |  | 106553.75
a) Aborted switching savings | Soft | 0.24578 | 56923.75 |  |  | Aborted switchhing covers planned and unplanned.
No of switching dispatched crews/ year |  |  |  | 260 | Bruce Bjorklund | Confirmed- Bruce Bjorklund | PSE Estimate from prior business case. aborted switching estimate covers planned an unplanned outages.
% EFR |  |  |  | 75% | David Brodie |  | PSE Estimate
% Patelco |  |  |  | 25% | David Brodie |  | PSE Estimate
EFR switching jobs |  |  |  | 195
Patelco switching jobs |  |  |  | 65
EFT hourly FTE cost |  |  |  | 41.73 | Holly Lewis |  | Serviceman base rate
Loaded Hourly FTE Rate |  |  |  | 131.5 | Kevin Popich |  | Fully loaded serviceman rate
Loaded Potelco crew cost/ hour |  |  |  | 700 | David Brodie |  | Fully loaded service crew rate
Avg lost time per crew (EFT/ Potelco) |  |  |  | 1.375 | David Brodie |  | PSE Estimate: 25% 30 mins, 25% 1 hour, 50% 2 hours.
OMS factor |  |  |  | 50% | PA |  | Based on Toronto Hydro’s experience, aborted switching instructions can be mitigated by 80% with the implementation of an OMS/DMS that accurately presents crew locations, notes and tags. Conservative assumption for PSE is 50%
b) Planned outages - unmetered services |  |  | 80416.875 |  | Tony Blas (Potelco) | If unmetered services are not known, the planned outage maintenance will need to be rescheduled.
Total planned outages |  |  |  | 1671 | Bill Esser | plug number
% with unknown unmetered services |  |  |  | 5% |  | Following up with Stan Cornish (TLM report form CLX).
Avg crew cost/ hour |  |  |  | 700
Avg lost time per crew (EFT/ Potelco) |  |  |  | 1.375 | David Brodie |  | PSE Estimate: 25% 30 mins, 25% 1 hour, 50% 2 hours.
c) Planned outages - inaccurate customer data |  |  | 91905 |  | Tony Blas (Potelco) | If customers are not accurately mapped to circuits, the planned outage maintenance will need to be rescheduled. Find out that people have not been notfified. Follow up with Tony Blas.
Total planned outages |  |  |  | 1671 | Bill Esser | plug number | [13 empty] | 58582.9691
% requiring rescheduling due to missing customer data |  |  |  | 10% |  | plug number
Avg lost time per crew (EFT/ Potelco) |  |  |  | 1.375 | David Brodie |  | PSE Estimate: 25% 30 mins, 25% 1 hour, 50% 2 hours.
Avg crew cost/ hour |  |  |  | 400 |  | Need crew cost
d) Trouble call efficiency | Soft | 0.13635 | 49630
Total trouble calls |  |  |  | 2836 | Kristi Schnitker |  | From 2010 SP report
% of trouble calls with inefficient routing |  |  |  | 5% | Tony Blas, Rich johnson, Turushia Thomas | Per Turusha and Rich Johnson | Potelco estimate: 35%; Per PSE - this has become an exception
Time lost per occurance |  |  |  | 0.5 | Tony Blas |  | Potelco estimate: 35-40 mins
Avg crew cost/ hour |  |  |  | 700 | David Brodie
3) Total EFR savings |  |  | 688566.9456
a) Investigations savings | Soft | 2.4555 | 671636.25 |  |  |  |  | 0 | 0 | 0
Outages |  |  |  | 11350 |  | RFP Statistics | 2007-2009 average
% of outages requiring "hunting" |  |  |  | 30% | Holly Lewis, David Brodie |  | Patrolling happens on 2836 events where Patelco is called out. This is roughly 20% of all events. An additional 10% can be conservatively assumed for EFR only investigations | Saving an additional 10-20%? | 15%
Hours spent hunting per outage |  |  |  | 1 | Kristi Schnitker | On average takes 1 person 1-2 hours. OH doesn’t take as long. 2 people at night for OH. Underground 2 people. | PSE Estimate 66 mins
FTE |  |  |  | 1.5 | David Brodie |  | PSE Estimate: 60 % of OH work is core hours (1 person crew) 2) 40% of OH work is non core (2 person hours) 3) 30% of work is UG 4) UG crews are 2 people
Hourly FTE Rate |  |  |  | 41.73 | Holly Lewis
Loaded Hourly FTE Rate |  |  |  | 131.5 | Kevin Popich |  | Fully loaded serviceman rate
b) Post event investigations | Soft | 0.12115 | 16930.6956 |  | Krista Malmgren
Hours per engineer per year |  |  |  | 18 | Jennifer Boyer |  | PSE Estimate
Engineers |  |  |  | 14 | Jennifer Boyer |  | PSE Estimate
Hourly FTE Rate |  |  |  | 41.73 | Holly Lewis
Annual FTE LoadedRate |  |  |  | 67.1853 |  | Standard loading | Standard 61% loading
Inputs | Hard/ Soft | FTE | Hard Value | Inputs | Source | Comments | Assumptions/ Source
4) Total Planning savings |  |  | 428388.8 |  |  | Krista to update framework to include: 1) outage investigation for reliability projects 2) outage investigation for the EFR response to customer complaints
a) DMS Model maintenance savings | Hard | 1 | 174137.6 |  |  | Data will be provided for SynerGEE modeling automatically | Benefit to begin in Y3 (2013)
Current FTE time spent on model maintenance |  |  |  | 1 | Don Yuen | 1 FTE realized in 2013, 1 in 2014. | Assumes manual entry in current state
Hourly FTE Rate |  |  |  | 52 | Krista Malmgren
Annual FTE LoadedRate |  |  |  | 174137.6 |  | confirm loaded rates for planning
b) Auditing savings | Soft | 0.36923 | 43276.8
Hours saved per analyst per year |  |  |  | 192 | Don Yuen | Krista spends 5-7 hours outage coordination. | PSE Estimate
Analysts |  |  |  | 4 | Don Yuen |  | PSE Estimate
Hourly FTE cost |  |  |  | 35 | Krista Malmgren
Loaded Hourly FTE Rate |  |  |  | 56.35
c) Outage investigation for reliability projects | Soft | 1.1538 | 200928 |  |  | Krista to provide numbers
Projects |  |  |  | 600 | Don Yuen |  | PSE Estimate
Net savings in hours |  |  |  | 4 | Don Yuen |  | PSE Estimate
FTE Rate |  |  |  | 52 | Krista Malmgren
Loaded Hourly FTE Rate |  |  |  | 83.72
d) Post event complaint investigations savings | Soft | 0.057692 | 10046.4
Reduction in complaints |  |  |  | 20 | Don Yuen | Additional 26 complaints handled by call center. May be added to that function. | PSE Estimate
Hours spent per complaint |  |  |  | 6 | Don Yuen |  | PSE Estimate
Hourly FTE cost |  |  |  | 52 | Krista Malmgren |  | PSE Estimate
Loaded Hourly FTE Rate |  |  |  | 83.72
5) Total Maps and Records savings | Hard | 9 | 1204415.2708 |  |  |  | Savings realized in 2014
Method 2 Calculation (20% efficiency + outsourcing of low to moderate tasks) |  |  | 889775.9428 |  |  |  | 20% efficiency + outsourcing of low to moderate tasks- see MRT outsourcing alternative.
Method 1 Calculation (50% efficiency on total FTE) |  |  | 937917.984
Number of FTEs in electric mapping |  |  |  | 18 | Mark Maass | Based on number in department | 2010 MRT Sourcing Study- number of FTEs performing low to moderate value tasks
Estimated efficiency potential in eliminating the use fo raster maps |  |  |  | 50% | PA | Review MRT process maps | Reduction from 3 source systems to 1 system; streamlined processes.
Hourly FTE Rate |  |  |  | 31.02 | Mark Maass |  | Currently $30 with 3.4% raise in 2012
Annual FTE LoadedRate |  |  |  | 103879.776
Annual cost of map printing |  |  |  | 3000 | Mark Maass |  | Per Mark Maass
Incremental FTE reduction- due to MapFrame |  |  |  | 3 | PA |  | Service Provider will be updating maps in the field. License and implementation cost of Mapframe are included in the project cost projections.
Hourly FTE Rate |  |  |  | 31.02 | Mark Maass |  | Currently $30 with 3.4% raise in 2012
Annual FTE LoadedRate |  |  |  | 103879.776
6) Intolight (Streetlight) savings | Hard | 1.5 | 183664
Current number of PSE FTES |  |  |  | 1 | Paul Kinberg |  | This function will be automated via the OMS system and will come through the regular system dispatch group.
Hourly FTE Rate |  |  |  | 36.32 | Danielle Troupe |  | Per Intolight
Loaded FTE Rate |  |  |  | 59.32 | Danielle Troupe |  | Per Intolight
Annual FTE LoadedRate |  |  |  | 123385.6
Current number of Potelco FTES |  |  |  | 0.5 | Paul Kinberg | Need to confirm rate and if this savings can be realized. | There is one Potelco person that serves PSE (and another utility) as a dispatcher. This will be an automated function with OMS.
Hourly FTE Rate |  |  |  | 36 |  |  | plug rate
Loaded FTE Rate |  |  |  | 59.32 | Danielle Troupe |  | Assumes rate is same as PSE
Annual FTE LoadedRate |  |  |  | 120556.8
7) Total New Builds savings | Hard |  | 779098.32 |  |  | put 50% in y4 and 100% in y 5 | 50% realized in Y4 and 100% in Y5
MRT FTEs dedicated to electric as builts) |  |  |  | 7.5 | Sourcing evaluation findings - Sept 2010 | confirm % of electric to gas mappers and that both mapping and merging of as builts should be included (9.3 + 5.8) | 15.1 total FTEs dedicated to as builts, roughly have of these allocated to electric maps. Other activities and FTEs that MRT performs are excluded from this analysis.
Hourly FTE Rate |  |  |  | 31.02 |  |  | Currently $30 with 3.4% raise in 2012
Annual FTE LoadedRate |  |  |  | 103879.776
FTE time to build design functionality in Electric Office for Potelco |  |  |  | 3.5
Annual FTE cost |  |  |  | 150000
Cost to build design functionality in Electric Office |  |  |  | 750000 | Patrick Seager | move to costs summary- one time cost
Additional Electric Office Engineering Design License | [6 empty] | Per GE - no incremental license fees
8) Avoided inquiry/ investigation cost | Hard | 0 | 0 |  | Jennifer Tada
Estimated annual FTE reduction in audit response |  |  |  | 0 |  | Included in planning savings | initial estimate= 4 analysts for 40 hours each for a major storm.
Annual FTE cost |  |  |  | 150000
9) Total Call Center savings |  |  |  |  | Nancy Mesquita
% reduction in call volumes | [5 empty] | More accurate information provided to customers | Assumes reduced call volumes
reduction in avg minutes per call
FTE Rate
TOTAL AVOIDED OUTAGE MINUTES |  |  | 3782885.2466
Inputs | Hard/ Soft | FTE | Hard Value | Inputs | Source | Comments | Assumptions/ Source
1) Total Storm Response savings | Hard |  | 986720.616 |  |  |  |  | 12169554.264 | 12037991.5152 | 131562.7488
% reduction in duration |  |  |  | 10% | PA | Our estimate | Basedon our experience. Conservative estimate of reduction in storm duration. | An additional 1-3% improvement (2%). | 12%
5 yr avg storm hours/ year |  |  |  | 321 | Brenda Bartell |  | 5 year average
5 yr avg storm costs/hour |  |  |  | 24396 | Brenda Bartell |  | 5 year average exlcuding 2006 major storm. O&M only. | 7831116
Ratio of overtime compared to straight time |  |  |  | 84% | Larissa Ljubarskaya |  | PSE Data- This is the % of OT dollars to REG dollars for PSE resources. Applying this to total amount assuming a similar split for Potelco.
Incremental Reduction due to use of automated callout tool |  |  |  | 5% | PA |  | Call out tool will provide 5% or more reduction in storm duration
2) Non Storm Response Savings | Hard |  | 583594.272 |  |  |  |  | 3307034.208 | 1699590.336 | 1607443.872
Non- Storm Outages |  |  |  | 9274 | Larissa Ljubarskaya |  | PSE Data
Labor cost per outage |  |  |  | 552 | Larissa Ljubarskaya |  | PSE DATA- labor only
Total non-storm labor cost |  |  |  | 5119248
2010 Customer Minutes of Interruption |  |  |  | 554760885 | PSE Outage DB |  | 2010 Outage Data
Non-storm cost per CMI |  |  |  | 0.0092278
% of value of CMI improvement |  |  |  | 10% | PA |  | 1) Other utilities have seen an overall long-term reduction in SAIDI between 5-15 minutes following the initial implementation of an OMS-DMS system 2) Storm and major storm savings excluded 3) Includes revenue gain from decrease in duration. | An additional 1-3% (2%) | 12%
Estimated reduction in CMI |  |  |  | 55476088.5 | PA |  | Basedon our experience. Conservative estimate of reduction in storm duration. |  | 66571306.2
Ratio of overtime compared to straight time |  |  |  | 76% | Larissa Ljubarskaya |  | PSE Data- This is the % of OT dollars to REG dollars for PSE resources. Applying this to total amount assuming a similar split for Potelco. | PSE's discussion with Oncor indicated that there is significant savings in non-storm outage responses here because work is more evenly distributed throughout the day. | 40%
Incremental Reduction due to use of automated callout tool |  |  |  | 5% | PA |  | Call out tool will provide 5% or more reduction in SAIDI
Incremental CMI due to use of call out tool |  |  |  | 27738044.25
3) Total Avoided Net Revenue loss | Hard |  | 20341.2324 |  | Pam Rasanen |  | NEED TO ADD THIS IN
2010 Customer Outage Minutes |  |  |  | 554760885 | PSE Outage DB | PSE Outage Data
% reduction in duration |  |  |  | 10% | PA |  | Basedon our experience. Conservative estimate of reduction in storm duration.
Gain in customer minutes |  |  |  | 55476088.5
Gain in customer hours |  |  |  | 924601.475
Average blended customer distribution rate |  |  |  | 0.022 | Pam Rasanen | Regulatory | Distribution cost reflects the net revenue gain of avoided load loss.
4) Avoided penalties- minutes | Hard |  | 116236.2 |  | Jennifer Tada |  |  | 658671.8 | 619926.4 | 38745.4
Average SAIDI fine per year |  |  |  | 774908 | Mei Kass |  | Based on 4 year aveage
Estimated % reductions |  |  |  | 15% | Jennifer Tada | Conservative estimate | Conservative estimate. Fines are currently based on magnitude of difference between actual and target. Implementing OMS will reduce variance between SAIDI actual and target because of better information. |  | 20%
5) Improved Asset Management | Hard |  | 2075992.9261 |  |  |  | Benefit will not be realized until 2014
Total Outages |  |  |  | 13683 | Larissa Ljubarskaya |  | Based on 2009 Annual number
Total Non-Storm Cost |  |  |  | 17444394 | Larissa Ljubarskaya |  | 9274 outages * 1,881 cost per outage
Average Annual Storm Cost |  |  |  | 24075464.5225 | Brenda Bartell |  | Average annual storm cost (2003-2010)
Cost per outage |  |  |  | 3034.4119
Estimated % reductions |  |  |  | 5% | PA Estimate | Conservative estimate | Conservative estimate based on other OMS implementations.
6) Total Avoided O&M outage cost savings |  |  | 0 |  | Krista | May be double counting
7) Total Avoided capital outage cost savings |  |  | 0 |  | Krista | May be double counting
Number of outages avoided
Cost per avoided outage - O&M
Cost per avoided outage - Capital
8) Avoided penalties- implementation |  |  |  |  | Mei Kass | No written penalties. Commission may disallow cost recovery/ earning on costs if system not implemented on time.
Annual penalty for not implementing OMS
# of years delay
9) Avoided penalties- outages |  |  | 0 |  | Mei Kass
Number of Customer Interruptions (CI) avoided
Cost per avoided customer interruption - penalties
10) Avoided legal claims- minutes Legal/Claims |  |  | 0
Cost per avoided customer minutes of interruption - Legal/Claims
|  |  | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
TCO Status Quo
Automated analysis of system status including outage device prediction |  |  | 4596696.832 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Electric First Response (EFR) Investigations |  |  | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Storm Response Costs |  |  | 12169554.264 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Non-storm response Costs |  |  | 3307034.208 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
SAIDI Fines |  |  | 658671.8 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Total |  |  | 20731957.104 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
TCO AMI
Automated analysis of system status including outage device prediction |  |  | 4424320.7008 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Electric First Response (EFR) Investigations |  |  | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Storm Response Costs |  |  | 12037991.5152 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Non-storm response Costs |  |  | 1699590.336 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
SAIDI Fines |  |  | 619926.4 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Total |  |  | 18781828.952 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!

## Other Applications
Theft/Diversion
|  | Baseline Theft | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3%
|  | Baseline Theft Detected | 0.01% | 0.01% | 0.01% | 0.01% | 0.01% | 0.01% | 0.01% | 0.01% | 0.01% | 0.01% | 0.01% | 0.01% | 0.01% | 0.01% | 0.01% | 0.01% | 0.01% | 0.01% | 0.01% | 0.01% | 0.01% | 0.01% | 0.01% | 0.01% | 0.01%
|  | Energy Cost | 44.34 | 46.32 | 47.77 | 50.72 | 54.15 | 56.58 | 59.41 | 58.41 | 62.02 | 67.42 | 67.95 | 62.98 | 66.36 | 69.59 | 70.54 | 76.37 | 80.68 | 85.54 | 90.17 | 92.4163 | 94.7641 | 97.2008 | 99.7053 | 102.2823 | 104.9466
|  | % AMI with Hybrid AMI | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | % AMI with Full Deployment | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | % of Theft detected with AMI | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20%
|  | Theft Detected with AMR | 0.6% | 0.6% | 0.6% | 0.6% | 0.6% | 0.6% | 0.6% | 0.6% | 0.6% | 0.6% | 0.6% | 0.6% | 0.6% | 0.6% | 0.6% | 0.6% | 0.6% | 0.6% | 0.6% | 0.6% | 0.6% | 0.6% | 0.6% | 0.6% | 0.6%
| Status Quo |  | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037
| Total Sales (GWh) |  | 23209.4 | 23210.4 | 23211.4 | 23212.4 | 23213.4 | 23214.4 | 23215.4 | 23216.4 | 23217.4 | 23218.4 | 23219.4 | 23220.4 | 23221.4 | 23222.4 | 23223.4 | 23224.4 | 23225.4 | 23226.4 | 23227.4 | 23228.4 | 23229.4 | 23230.4 | 23231.4 | 23232.4 | 23233.4
| Theft (GWh) |  | 696.282 | 696.312 | 696.342 | 696.372 | 696.402 | 696.432 | 696.462 | 696.492 | 696.522 | 696.552 | 696.582 | 696.612 | 696.642 | 696.672 | 696.702 | 696.732 | 696.762 | 696.792 | 696.822 | 696.852 | 696.882 | 696.912 | 696.942 | 696.972 | 697.002
| Theft Lost Revenue ($M) |  | 30873.1439 | 32253.1718 | 33264.2573 | 35319.9878 | 37710.1683 | 39404.1226 | 41376.8074 | 40682.0977 | 43198.2944 | 46961.5358 | 47332.7469 | 43872.6238 | 46229.1631 | 48481.4045 | 49145.3591 | 53209.4228 | 56214.7582 | 59603.5877 | 62832.4397 | 64400.5067 | 66039.4078 | 67740.4146 | 69488.8458 | 71287.899 | 73147.9832
| Theft Detected Status Quo (GWh) |  | 2.3209 | 2.321 | 2.3211 | 2.3212 | 2.3213 | 2.3214 | 2.3215 | 2.3216 | 2.3217 | 2.3218 | 2.3219 | 2.322 | 2.3221 | 2.3222 | 2.3223 | 2.3224 | 2.3225 | 2.3226 | 2.3227 | 2.3228 | 2.3229 | 2.323 | 2.3231 | 2.3232 | 2.3233
| Cost |  | 2.3209: 478258.1501
Hybrid AMI
| Theft Detected With Hybrid AMI (GWh) |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Improved Theft Loss ($M) |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Theft Program |  | 0 | 0 | 0 | 1 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Cost Savings |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| NPV |  | 2.3209: #VALUE!
Full Deployment
| Theft Detected With AMI (GWh) |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Improved Theft Loss ($M) |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Theft Program |  | 0 | 0 | 0 | 1 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Cost Savings |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| NPV |  | 2.3209: #VALUE!
Hi/Low Voltage
| Benefit = Avoidance of 50% of claims scaled according to AMI Rollout |  | 2.3215: Jenny Boyer--> Power Quality doing investigations, would be reduced almost to 0 because PSE would be able to determine voltage remotely.
| Benefit = Avoidance of 50% of field trips for Hi/Lo voltage claims @ 16 hrs per field trip |  | 2.3215: Also customer satisfaction
Distribution Automation
| Benefit = $30K per circuit from avoided communications costs rolled out for 5% of feeders per year |  | 2.3215: Talk to Jeff Kensok

## Business Case (R)
[6 empty] | Status Quo | Hybrid AMI | Two Vendors | Full Deploy | L+G Proposal
[5 empty] | Administrative Costs | 26.9909 | 34.2671 | 34.2671 | 34.2671
[5 empty] | Revenue Savings | -74.6811 | -94.7772 | -94.7772 | -94.7772
[6 empty] | 0 | -20.0961 | -20.0961 | -20.0961
[5 empty] | CVR TCO | 26.9909 | 14.1711 | 14.1711 | 14.1711
[5 empty] | Benefits (TCO) | #REF! | #REF! | #REF! | #REF!
[5 empty] | Costs (TCO) | #REF! | #REF! | #REF! | #REF!
[5 empty] | Benefits |  | 159.5706 | 155.5013 | #VALUE! | XXXX
[5 empty] | Costs |  | 102.5021 | 101.3035 | #VALUE! | XXXX
|  |  | Financial Data 25 Years | [8 empty] | Business Case Results
($M) |  | Status Quo | Two Vendors, Two Networks | Hybrid AMI | Full Deployment | L+G Proposal | [6 empty] | ($M)
Core Metering Functions: Purchase, Install, Maintain Meters, Modules and Network; Read Meters | [11 empty] | Model Period | 25 years
| O&M Internal | 110.4318 | 99.8917 | 90.5962 | 129.5713 | 57.2997 | [5 empty] | Payback Period | 18 Years
| O&M L+G Contract | XXXXXX | XXXXX | XXXXX | XXXX | XXXXX | [5 empty] | IRR | 11.04%
| Capital | 265.1467 | 422.824 | 429.2488 | 475.0624 | 313.196 |  |  |  |  | Metering Only | O&M Savings | #VALUE!
| TCO | 375.5785 | 522.7157 | 519.845 | 604.6337 | 370.4957 |  |  |  |  | Metering Only | Capital Costs | 164.1021
[12 empty] | NPV | 57.0685
AMI Enabled Benefits: | [11 empty] | O&M Savings | 230.0638
| Meter Reading |  | -147.1372 | -144.2665 | -229.0552 | 5.0828 | [5 empty] | Capital Investment | 172.9953
| Remote Connect/Prepay |  | 30.603 | 30.603 | 32.8036 | 30.603
| CVR |  | 12.8198 | 12.8198 | 12.8198 | 12.8198
| Outage |  | 15.1118 | 15.1118 | 19.1353 | 15.1118
| Total |  | -88.6026 | -85.7319 | -164.2965 | 63.6174
| TOTAL NPV |  | -235.7398 | -229.9984 | -393.3517 | -194.734 | [5 empty] | Discount Rate | XXXXXX
[12 empty] | Inflation | XXXXXX
Table 3 - Components of the AMI Business Case
AMI Application | Quantified Net Benefits ($M 2013) | Qualitative Benefits | PSE Business Leader
Advanced Meter Reading | -1.4661 | Operational efficiency, fewer manual reads improved meter and customer information, lower risk technology, improved equipment quality, enhanced distribution communications for electric and gas. | Customer Care
Remote Disconnect/ Reconnect/ Prepay | 30.603 | Fewer write offs, faster service on/off, reduced truck rolls, more customer billing and payment options, customer energy empowerment. | Customer Care
Outage | 15.1118 | Fewer and shorter outages, faster restoration, improved notification, better informed customers. | Electric Operations
Conservation Voltage Reduction | 12.8198 | Reduced power and capacity costs, increased system efficiency, load management. | System Planning
Dynamic/TOU Pricing | N/A | Peak load management, customer empowerment. | Rates
EV Metering/ Pricing | N/A | Increased revenue and load management. | Rates
Theft | #VALUE! | Decreased energy losses, increased safety | Meter Network Services
Demand Response | N/A | Peak load management | Energy Efficiency
Web and In-Home Energy Display | N/A | Customer empowerment. | IT
Customer Generation | N/A | Billing enablement and customer service. | Energy Efficiency
Power Quality | N/A | Improved voltage and power quality for customers. | Major Accounts
Hybrid AMI vs. Two Networks Two Vendors
| Hybrid AMI | Two Networks, Two Vendors
L+G Managed Service Contract | XXXXX | XXXXX
AMR Meter/ Module Costs | 28.6538 | 28.6538
AMI Meter/ Module Costs | 395.4346 | 368.018
Network Costs | 29.4991 | 35.578
NOC Head End Costs | 19.9586 | 39.6229
Telecom and Other Costs | 46.2989 | 50.843
NPV (Metering Only) | -1.4661 | -4.3368
NPV (w/Applications) | 57.0685 | 54.1978
Benefits
| Costs Hybrid AMI | Benefits Hybrid AMI | Costs Full Deployment | Benefits Full Deployment |  | Status Quo |  |  |  | Costs | Net Benefits
AMI Metering Costs | 614.5118 |  | #VALUE! |  | Metering Costs | 613.0458 | Hybrid AMI | Two Vendors, Two Networks | Full Deployment | Hybrid AMI | Net Benefits Hybrid AMI | Two Vendors, Two Networks | Net Benefits Full Deployment
Metering |  | 613.0458 |  | 613.0458 | Metering | 613.0458 | 614.5118 | 617.3825 | #VALUE! |  | -1.4661 | -4.3368 | #VALUE!
Remote /Prepay |  | 30.603 |  | 32.8036 | Remote /Prepay | 197.5143 |  |  |  |  | 613.0458 | 613.0458 | 613.0458
CVR |  | 12.8198 |  | 12.8198 | CVR | 26.9909 | 166.9113 | 166.9113 | 164.7107 |  | 30.603 | 30.603 | 32.8036
Outage |  | 15.1118 |  | 19.1353 | Outage | 276.6542 | 14.1711 | 14.1711 | 14.1711 |  | 12.8198 | 12.8198 | 12.8198
Theft |  | #VALUE! |  | #VALUE! | Theft | 478.2582 | 261.5425 | 261.5425 | 257.5189 |  | 15.1118 | 15.1118 | 19.1353
Total |  |  |  |  | AMI Costs |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! |  | #VALUE!
[10 empty] | 1057.1367 | 0 |  | 0
O&M vs. CAPEX
| O&M | CAPEX
Status Quo | 766.147 | 273.3771 | 1039.524 | 1039.524
Hybrid AMI | 536.0832 | 446.3723 | 982.4555 | 982.4555
Two Vendors, Two Networks | 545.3787 | 439.9475 | 985.3262 | 985.3262
Full Deployment | #VALUE! | 492.1859 | #VALUE! | #VALUE!
L+G Proposal | 903.9385 | 330.3195 | 1234.258 | 1234.258
Costs for meter/module hardware go down
Network, and NOC costs go up
With the assumptions as they are, it costs slightly more to pursue the "Two Networks, Two Vendors" scenario.

## PPCharts
Notes on Total O&M
Status quo O&M starts off high to accomodate the L+G contrac and then declines with the ownership transition, but then continues to climb over time with growth and inflation.
Full Deployment O&M starts off high to accomodate the L+G contract and then spikes in 2017because of the termination fee .
O&M with the Hybrid AMI option decreases over time as L+G AMR contract costs decline but is slightly higher than the full deployment option in later years because in the full deployment option the network costs are primiary O&M based whereas the network costs for the hybrid AMI option are primarily capital.
(see the "Analysis" tab for further detail)
Notes on Meter CAPEX
Hybrid AMI - An initial jump in CAPEX occurs with deployment and then decreases initially as business deployments end and then is steady through the 10 year deployment. After 10 years, deployments end and capital continues for growth only.
In the full deployment scenario, there is an initial spike for the three year deployment and then capital continues with meter/customer growth.
Notes on Network CAPEX
(with Applications)
For All Scenarios-The drop off in CAPEX around 2034 results from end of the CVR Captial project deployment.
Hybrid AMI and Full Deployment -The large spike in 2016 relates to the network deployment. The costs are distributd slightly differently due to different ownership models, existing equipment, etc.
Notes on Network Capital
Hybrid AMI - Network capital spikes for both Hybrid AMI and Full Deployment . However the Full deployment scenario has two full years of deployment activity because the whole newtwork needs to be built from scratch. Where in the Hybrid AMI scneario, there is only one year of major deployment because some of that network is already in place. The Hybrid AMI scenario also has slightly higher up front capital costs due to software licencing.
There is more capital expenditures over the 10 year deployment with the Hybrid AMI scenario and that is why that line is slighly higher in the initial 10 year period. This is because some of the meter head end costs are drawn out over that period.

## Market Ops
Quantifiable Market Opportunity
Providing Meter Reads to Electric Utilities (For PSE's Gas Only Customers)
Number of Customers | XXXXXX
Annual Revenue per Customer | 12
Total Market Opportunity | #VALUE!
Providing Meter Reads to Water Utilities (For all of PSE's Customers)
Number of Customers | XXXXXX
Annual Revenue per Customer | 12
Total Market Opportunity | #VALUE!
Assumptions
Price Per Read | 1

## Validation
Status Quo: No AMI CAPEX because no AMI.
Hybrid AMI: Increased
Full Deployment: Large spike in capital over three year deployment followed by gradual increases in CAPEX as PSE adds meters for growth and attrition.

## L+GPricing (R)
AMR/AMI Hybrid
| Landis+Gyr Rev 01/18/2013 |  |  | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031
Year
Deployment Approach
|  | Year of Deployment |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
|  | Electric Customer Forecast (Cumulative) |  | 1118793.5396 | 1128742.791 | 1144738.4281 | 1165864.2181 | 1188821.1788 | 1212023.2386 | 1234615.4071 | 1256715.3025 | 1278765.5965 | 1301054.5599 | 1323424.0249 | 1345820.2975 | 1368502.3559 | 1391566.4867 | 1415019.3301
|  | Gas Customer Forecast (Cumulative) |  | 788798.7531 | 803870.1341 | 821019.7387 | 840291.6593 | 860897.2251 | 882136.5161 | 903691.2278 | 925576.6959 | 947749.6474 | 970250.3479 | 993032.3078 | 1016102.1198 | 1039614.2911 | 1063670.2927 | 1088282.9346
| AMI Meters & Modules | AMI Single Phase Electric Meter Hardware | Begins in 2013, inclds all growth 2016 on. |  |  |  |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
|  | AMI Polyphase Electric Meter Hardware (no reactive power) | Begins in 2013, inclds all maintenance 2016 on. |  |  |  |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
|  | AMI Polyphase Electric Meter Hardware (with Reactive Power) | [5 empty] | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
|  | AMI Residential Gas Module Hardware | Begins in 2013 |  |  |  |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
|  | AMI Commercial/Industrial Gas Module Hardware | Begins in 2013 | 5: XXXXXXX; 6: XXXXXXX; 7: XXXXXXX
| Network Quantities* | L+G Hybrid Concentrator |  | 1: 829
|  | L+G 2-way Concentrator |  | 1: 705; 2: 120; 3: 120; 4: 120; 5: XXXXXXX; 6: XXXXXXX; 7: XXXXXXX
|  | L+G 2-way Router |  | 1: 41
|  | L+G 2-way Collector/TOP |  | 1: 43; 2: 7; 3: 7; 4: 7; 5: XXXXXXX; 6: XXXXXXX; 7: XXXXXXX
| Electric Meter Allocation | % of Population with Form Factor |  | 1: Form Factor
| Res | 0.123% | bar: 1
| Res | 88.72% | bar: 1
| Res | 0.05386% | bar: 1
| C+I | 1.937% | bar: 1
| C+I | 0.04629% | bar: 1
| C+I | 1.482% | bar: 1
| C+I | 4.973% |  | 1: 12S
| C+I | 0.06908% |  | 1: 15S
| C+I | 2.595% |  | 1: 16S
| COSTS/RATES |  |  | 1: 2012 Costs of Hardware/Asset ($); 2: 2012 Costs of Installation/Labor ($); 3: Cost of Maintenance ($)
| Meter/Module Hardware Costs | AMI Single Phase Electric Meter with Module Hardware (no disconnect) Focus AX Form 2S |  | 1: XXXXXXX; 2: XXXXXXX; 3: N/A
|  | AMI Single Phase Electric Meter with Module Hardware (with disconnect) Form 2s |  | 1: XXXXXXX; 2: XXXXXXX; 3: N/A
|  | AMI Polyphase Electric Meter with Module Hardware (no reactive power) All Forms No A Base |  | 1: XXXXXXX; 2: XXXXXXX; 3: N/A
|  | AMI Polyphase Electric Meter with Module Hardware (with reactive power) |  | 1: XXXXXXX; 2: XXXXXXX; 3: N/A
|  | AMI Residential Gas Module Hardware American Residential |  | 1: XXXXXXX; 2: XXXXXXX; 3: N/A
|  | AMI Commercial/Industrial Gas Module Hardware American Commercial |  | 1: XXXXXXX; 2: XXXXXXX; 3: N/A
| Network Equipment Unit Costs | L+G Hybrid Concentrator |  | 1: XXXXXXX; 2: XXXXXXX
|  | L+G 2-way Concentrator |  | 1: XXXXXXX; 2: XXXXXXX; 5: To remove the cost would probably be 1/2.
|  | L+G 2-way Router |  | 1: XXXXXXX; 2: XXXXXXX
|  | L+G 2-way Collector/TOP |  | 1: XXXXXXX; 2: XXXXXXX
|  | L+G Network equipment battery |  | 1: XXXXXXX; 2: XXXXXXX
| Gas Module Battery | AMI Gas module battery |  | 1: XXXXXXX; 2: XXXXXXX; 3: N/A
| Software Head End Costs (PSE Owns and Hosts) | Set-up, Installation, Config, Test of Command Center |  | 1: XXXXXXX; 2: XXXXXXX; 3: XXXXXXX
|  | Annual Software Maintenance Fees (per endpoint)** See Below |  | 1: XXXXXXX; 2: XXXXXXX; 3: XXXXXXX
|  | Project Management & Ongoing Support - Network Deployment Project Services - 36 Mo) |  | 1: XXXXXXX; 2: XXXXXXX; 3: XXXXXXX
|  | Software and Annual Maintenance - Includes Command Center HES and Meter Software ($1.75), ECC Advanced Security ($1.00) - Per Endpoint |  | 1: XXXXXXX; 2: XXXXXXX; 3: XXXXXXX
|  | ECC Security Head End Appliances (Per Set) - Requires 1-set each for production, Disaster Recovery, testing |  | 1: XXXXXXX; 2: XXXXXXX; 3: XXXXXXX
|  | Appliances for Disaster Recovery, maintenance fees, etc. |  | 1: XXXXXXX; 2: XXXXXXX; 3: XXXXXXX
| Software Head End Costs (SaaS)** | This assumes that L+G is providing the current level of Head End hosting and maintenance plus onsite support and maintenance services. Advanced Security licensing and Hosting Services would be in additon to the Fee shown. |  | 1: XXXXXXX; 2: XXXXXXX; 3: XXXXXXX
| Telecom Costs | WAN Backhaul Costs (Licenses and Data) *Note: PSE will go to Verizon for the provider |  | 1: XXXXXXX; 3: N/A
Device Life
|  | Device |  | 1: Lifetime (years)
|  | AMI Gas module battery life |  | 1: 20
|  | AMI Gas Modules (Res) |  | 1: 20
|  | AMI Gas Modules (Commercia) |  | 1: 20
|  | AMI Single Phase Electric Meter with Module Hardware (no disconnect) |  | 1: 20
|  | AMI Single Phase Electric Meter with Module Hardware (with disconnect) |  | 1: 20
|  | AMI Polyphase Electric Meter with Module Hardware (no reactive power) |  | 1: 20
|  | AMI Polyphase Electric Meter with Module Hardware (with reactive power) |  | 1: 20
3 Year Warranty and extender can be added.
*Need L+G to do a sanity check on these numbers. We expect we will have part of the network equipment by 2016 and will need to do a 1 for 1 replacement of the balance. Please estimate past 2018 for average growth amounts based on customer forecast on lines 8 &9
**Please price this according to the amount of endpoints installed per year.
Landis+Gyr Note:
Endpoint Installation pricing is based on another recent deployment that used union labor. Final pricing is subject to final scope of work and local prevailing wage rate adjustments.
Landis+Gyr Note:
Set-up, Installation, Config, Test of Command Center Pricing is basedo n 250 man hours of work.
Landis+Gyr Note: The SaaS Fee is based on the current scope of work under the current Agreement. Further clarification of roles and responsiblities may be needed for this business case analysis
*XXXXXXX
XXXXXXX
XXXXXXX
XXXXXXX
XXXXXXX

## Hybrid AMI Meter Deployment (R)
AMI Deployment Scenario for Hybrid Network
|  |  |  | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
Population Counts | Electric Meters |  |  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
|  | Count |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
|  | Growth |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
|  |  |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
|  | Total Meters |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
|  |  |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
|  | 2 Way Network Availability |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
|  | 2 Way Network Utilization |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
Opportunistic Exchanges | Disconnect/Reconnect
|  | Disc Rate | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
|  | Collection Visits/Disc | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
|  | Exchange | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
|  | Repeat | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
|  | Disconnect/Reconnect | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
| Growth |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
| Attrition |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
|  |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
| Read Performance Improvements |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
|  | LP | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
|  | Demand | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
|  |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
| CVR |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
|  |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
| Total Opportunistic Exchanges |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
|  |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
|  | Total | XXXXXXX
Programmed Exchanges | Programmed Exchange |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
|  | Life (years) | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
|  | Rollout additional | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
|  |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
|  |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
| One Way Electric Meters Remaining |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
| % One way Electric |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
|  | AMI Deployment Total Electric |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
|  | Total | XXXXXXX
|  | Total Exchanged | XXXXXXX
|  | Final Population | XXXXXX
Population Counts | Gas Meters
|  | Count |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
|  | Growth |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
|  |  |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
|  | Total Meters |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
|  |  |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
|  | Total One-Way Meters Remaining (year beginning) |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
|  | % 1 Way |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
|  |  |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
Opportunistic Exchanges | Growth |  |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
| Module Attrition |  | XXXXXXX | 2016 4: XXXXXXX; 2017 5: XXXXXXX; 2018 6: XXXXXXX; 2019 7: XXXXXXX; 2020 8: XXXXXXX; 2021 9: XXXXXXX; 2022 10: XXXXXXX; 2023 11: XXXXXXX; 2024 12: XXXXXXX; 2025 13: XXXXXXX; 2026 14: XXXXXXX; 2027 15: XXXXXXX
| Sample Test |  | XXXXXXX | 2016 4: XXXXXXX; 2017 5: XXXXXXX; 2018 6: XXXXXXX; 2019 7: XXXXXXX; 2020 8: XXXXXXX; 2021 9: XXXXXXX; 2022 10: XXXXXXX; 2023 11: XXXXXXX; 2024 12: XXXXXXX; 2025 13: XXXXXXX
| Total Opportunistic Exchanges | [6 empty] | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
|  |  | Rolling Sum |  |  |  |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
[8 empty] | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
[8 empty] | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
Programmed Exchanges | [7 empty] | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
|  | Life (years) | XXXXXXX |  |  |  |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
[8 empty] | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
| Battery Replacement | [6 empty] | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
| Rollout Additional | [6 empty] | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
| Total Annual Program Gas Exchanges | [6 empty] | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
[8 empty] | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
|  |  | Rolling Sum |  |  |  |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
[8 empty] | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
[8 empty] | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
|  | AMI Deployment Total Gas |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
Note on C10: John McClaine: Need to ensure that 2 way meters are only installed in 2 way network areas until network rollout is complete.

## Deployment wPilots (R)
AMI Deployment Scenario for Hybrid Network
|  |  |  | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
Population Counts | Electric Meters |  |  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
|  | Count | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
|  | Growth | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
|  |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
|  | Total Meters | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
|  |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
|  | 2 Way Network Availability | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
|  | 2 Way Network Utilization | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Opportunistic Exchanges | Disconnect/Reconnect |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
|  | Disc Rate | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
|  | Collection Visits/Disc | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
|  | Exchange | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
|  | Repeat | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
|  | Disconnect/Reconnect | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
| Growth |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
| Attrition |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
|  |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
| Read Performance Improvements |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
|  | LP | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
|  | Demand | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
|  |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
| CVR |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
|  |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
| Total Opportunistic Exchanges |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
|  |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
|  | Total | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
|  |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
|  |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Programmed Exchanges | Programmed Exchange |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
|  | Life (years) | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
|  | Rollout additional | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
|  |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
|  |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
| One Way Electric Meters Remaining |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
| % One way Electric |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
|  | AMI Deployment Total Electric | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
|  | Total | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
|  | Total Exchanged | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
|  | Final Population | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
|  |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
|  |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Population Counts | Gas Meters |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
|  | Count | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
|  | Growth | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
|  |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
|  | Total Meters | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
|  |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
|  | Total One-Way Meters Remaining (year beginning) | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
|  | % 1 Way | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
|  |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Opportunistic Exchanges | Growth |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
| Module Attrition |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
| Sample Test |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
|  |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
|  |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
| Total Opportunistic Exchanges |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
|  |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
|  |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
|  |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Programmed Exchanges |  |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
|  | Life (years) | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
|  |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
| Battery Replacement |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
| Rollout Additional |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
| Total Annual Program Gas Exchanges |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
|  |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
|  |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
|  | AMI Deployment Total Gas |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX

## Reimbursements (R)
S | YEAR | MONTH | MARP | MDMS | ZCON | ZCON_NTF | MC01 | ELECTRIC | MONTH |  | Totals | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
E | 2010 | 1 | 270 | 122 | 15 | 386 | 0 | 2010 | MARP |  |  | 270 | 91 | 44 | 77 | 174 | 28 | 37 | 59 | 101 | 162 | 125 | 194
E | 2010 | 2 | 91 | 144 | 31 | 236 | 0 |  | MDMS |  |  | 122 | 144 | 107 | 97 | 378 | 285 | 100 | 104 | 140 | 104 | 25 | 73
E | 2010 | 3 | 44 | 107 | 21 | 159 | 0 |  | ZCON |  |  | 15 | 31 | 21 | 15 | 34 | 17 | 28 | 20 | 10 | 23 | 8 | 9
E | 2010 | 4 | 77 | 97 | 15 | 150 | 0 |  | ZCON_NTF |  |  | 386 | 236 | 159 | 150 | 331 | 341 | 452 | 510 | 255 | 801 | 450 | 317
E | 2010 | 5 | 174 | 378 | 34 | 331 | 0 |  | MC01 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E | 2010 | 6 | 28 | 285 | 17 | 341 | 0 | 2011 | MARP |  |  | 177 | 136 | 214 | 108 | 137 | 137 | 203 | 163 | 199 | 167 | 171 | 202
E | 2010 | 7 | 37 | 100 | 28 | 452 | 0 |  | MDMS |  |  | 83 | 49 | 69 | 63 | 72 | 92 | 35 | 43 | 52 | 35 | 37 | 87
E | 2010 | 8 | 59 | 104 | 20 | 510 | 0 |  | ZCON |  |  | 10 | 8 | 33 | 19 | 27 | 11 | 17 | 13 | 11 | 16 | 23 | 17
E | 2010 | 9 | 101 | 140 | 10 | 255 | 0 |  | ZCON_NTF |  |  | 529 | 364 | 385 | 333 | 472 | 354 | 458 | 424 | 282 | 276 | 414 | 369
E | 2010 | 10 | 162 | 104 | 23 | 801 | 0 |  | MC01 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E | 2010 | 11 | 125 | 25 | 8 | 450 | 0 | GAS
E | 2010 | 12 | 194 | 73 | 9 | 317 | 0 | 2010 | MARP |  |  | 564 | 452 | 291 | 5 | 663 | 520 | 414 | 432 | 343 | 291 | 231 | 315
E | 2011 | 1 | 177 | 83 | 10 | 529 | 0 |  | MDMS |  |  | 1285 | 1285 | 1479 | 567 | 1651 | 552 | 578 | 873 | 322 | 534 | 495 | 743
E | 2011 | 2 | 136 | 49 | 8 | 364 | 0 |  | ZCON |  |  | 397 | 633 | 788 | 305 | 586 | 154 | 206 | 53 | 60 | 201 | 235 | 210
E | 2011 | 3 | 214 | 69 | 33 | 385 | 0 |  | ZCON_NTF |  |  | 208 | 289 | 286 | 315 | 632 | 418 | 715 | 180 | 226 | 1250 | 835 | 317
E | 2011 | 4 | 108 | 63 | 19 | 333 | 0 |  | MC01 |  |  | 297 | 278 | 469 | 105 | 531 | 173 | 258 | 284 | 126 | 232 | 531 | 471
E | 2011 | 5 | 137 | 72 | 27 | 472 | 0 | 2011 | MARP |  | 744 | 151 | 198 | 171 | 70 | 15 | 22 | 2 | 1 | 103 | 4 | 7 | 0
E | 2011 | 6 | 137 | 92 | 11 | 354 | 0 |  | MDMS |  | 3872 | 443 | 298 | 523 | 393 | 330 | 464 | 350 | 300 | 179 | 238 | 165 | 189
E | 2011 | 7 | 203 | 35 | 17 | 458 | 0 | 4207.2436 | ZCON |  | 4781 | 456 | 752 | 833 | 616 | 355 | 293 | 137 | 226 | 130 | 180 | 156 | 647
E | 2011 | 8 | 163 | 43 | 13 | 424 | 0 | 8495.7818 | ZCON_NTF |  | 10675 | 643 | 1403 | 1390 | 1138 | 632 | 686 | 457 | 967 | 1102 | 1041 | 423 | 793
E | 2011 | 9 | 199 | 52 | 11 | 282 | 0 | 2902.5164 | MC01 |  | 5105 | 340 | 450 | 538 | 641 | 767 | 673 | 314 | 396 | 336 | 272 | 192 | 186
[11 empty] | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018
[9 empty] | ZCON Gas Modules |  | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
81.67%
E | 2011 | 12 | 202 | 87 | 17 | 369 | 0 | Current | ELECTRIC | Total % | 2011: Annual Totals
G | 2010 | 1 | 564 | 1285 | 397 | 208 | 297 | 2010 | MARP | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
G | 2010 | 2 | 452 | 1285 | 633 | 289 | 278 |  | MDMS | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
G | 2010 | 3 | 291 | 1479 | 788 | 286 | 469 |  | ZCON | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
G | 2010 | 4 | 5 | 567 | 305 | 315 | 105 |  | ZCON_NTF | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
G | 2010 | 5 | 663 | 1651 | 586 | 632 | 531 |  | MC01 | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
G | 2010 | 6 | 520 | 552 | 154 | 418 | 173 |  |  | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
G | 2010 | 7 | 414 | 578 | 206 | 715 | 258 | 2011 | MARP | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
G | 2010 | 8 | 432 | 873 | 53 | 180 | 284 |  | MDMS | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
G | 2010 | 9 | 343 | 322 | 60 | 226 | 126 |  | ZCON | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
G | 2010 | 10 | 291 | 534 | 201 | 1250 | 232 |  | ZCON_NTF | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
G | 2010 | 11 | 231 | 495 | 235 | 835 | 531 |  | MC01 | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
G | 2010 | 12 | 315 | 743 | 210 | 317 | 471 |  |  | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
G | 2011 | 1 | 151 | 443 | 456 | 643 | 340 |  | GAS | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
G | 2011 | 2 | 198 | 298 | 752 | 1403 | 450 | 2010 | MARP | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
G | 2011 | 3 | 171 | 523 | 833 | 1390 | 538 |  | MDMS | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
G | 2011 | 4 | 70 | 393 | 616 | 1138 | 641 |  | ZCON | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
G | 2011 | 5 | 15 | 330 | 355 | 632 | 767 |  | ZCON_NTF | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
G | 2011 | 6 | 22 | 464 | 293 | 686 | 673 |  | MC01 | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
G | 2011 | 7 | 2 | 350 | 137 | 457 | 314 |  |  | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
G | 2011 | 8 | 1 | 300 | 226 | 967 | 396 | 2011 | MARP | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
G | 2011 | 9 | 103 | 179 | 130 | 1102 | 336 |  | MDMS | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
G | 2011 | 10 | 4 | 238 | 180 | 1041 | 272 |  | ZCON | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
G | 2011 | 11 | 7 | 165 | 156 | 423 | 192 |  | ZCON_NTF | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
G | 2011 | 12 | 0 | 189 | 647 | 793 | 186 |  | MC01 | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
[10 empty] | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
[9 empty] | Total Reimbursements 2010 |  | 2011: XXXXX; 2012: XXXXX; 2013: XXXXX
[9 empty] | Total Reimbursements 2011 |  | 2011: XXXXX; 2012: XXXXX; 2013: XXXXX
[9 empty] | Change in Reimbursements |  | 2011: XXXXX; 2012: XXXXX; 2013: XXXXX
[8 empty] | Post 2016 | ELECTRIC | Reduction in Reimbursements
[8 empty] | 2010 | MARP | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
[9 empty] | MDMS | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
[9 empty] | ZCON | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
[9 empty] | ZCON_NTF | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
[9 empty] | MC01 | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
[9 empty] | 0 | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
[8 empty] | 2011 | MARP | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
[9 empty] | MDMS | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
[9 empty] | ZCON | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
[9 empty] | ZCON_NTF | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
[9 empty] | MC01 | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
[9 empty] | 0 | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
[9 empty] | GAS | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
[8 empty] | 2010 | MARP | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
[9 empty] | MDMS | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
[9 empty] | ZCON | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
[9 empty] | ZCON_NTF | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
[9 empty] | MC01 | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
[9 empty] | 0 | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
[8 empty] | 2011 | MARP | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
[9 empty] | MDMS | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
[9 empty] | ZCON | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
[9 empty] | ZCON_NTF | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
[9 empty] | MC01 | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
[9 empty] | 0 | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
[9 empty] | Reduction in Gas Reimbursements |  | 2011: XXXXX; 2013: XXXXX
[9 empty] | Reduction in Electric Reimbursements |  | 2011: XXXXX
Module Work Calculations
Cost is 22.4 + module cost
[10 empty] | Number | 2011: New for PSE
E | 2011 | 10 | 167 | 35 | 16 | 276 | 0 |  | Total PSE Modules Exchanged | XXXXX
E | 2011 | 11 | 171 | 37 | 23 | 414 | 0 |  | Total PSE Visited | XXXXX
[9 empty] | Total Visits/Exchanges reimbursed | XXXXX
[9 empty] | Total Visited Not exchanged | XXXXX
[9 empty] | L+G Modules Exchanged | XXXXX | 2012: XXXXX
[9 empty] | Total Exchanges | XXXXX

## Field Work Assumptions (R)
Updated 6/3
| L+G Contract Reimbursable Field Work Estimates 2013-2017: | [17 empty] | 2012 | 2013 | 2014 | 2015 | 2016 | 2017
[19 empty] | Actual | Released 07/17/12 | Assumed | Assumed | Assumed | Assumed
|  |  |  | 2013 |  | 2014 |  | 2015 |  | 2016- Q1 |  | 2016 Q2-Q4 |  | 2017 |  |  |  | CPI* | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| Svc Type | BILL_TYPE | Volume | Charge | Volume | Charge | Volume | Charge | Volume | Charge | Volume | Charge | Volume | Charge
first 4 lines & Billing MARP override | G | MARP | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX |  |  |  |  | 2012 | 2013 | 2014 | 2015 | 2016 | 2017
last 3 lines & Billing Investigate | G | MDMS | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX |  |  | Gas MR Visit |  | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
PSE ZCON Mod Inv | G | ZCON | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX |  |  | Elec MR Visit |  | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
PSE ZCON Mod Inv | G | ZCON_NTF | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX |  |  | Gas Meter Inv. |  | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
PSE ZCON Meter Investigate & Recall | G | MC01_GFR | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX |  |  | DataRaker |  | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
PSE ZCON Meter Investigate & Recall | G | MC01_MTR SHOP | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX |  |  | Annual DataRaker |  | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
PSE ZCON Meter Investigate & Recall | G | MWNR | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX |  |  |  |  | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
first 4 lines & Billing MARP override | E | MARP | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX |  |  |  |  | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
last 3 lines & Billing Investigate | E | MDMS | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX |  | MC01 | Gas Meter Ex |  | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
PSE ZCON Mod Inv | E | ZCON | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX |  | MC01 | Gas Meter Repair |  | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
PSE ZCON Mod Inv | E | ZCON_NTF | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX |  |  | Gas Module Cost |  | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
|  | EFR |  | 209069.2215 | 6119.955 | 192678.9282 | 5752.7577 | 185557.7865 | 1380.6618 | 45656.2671 | 4141.9855 | 0 | 5301.7415 | 0
|  | GFR |  | 671212.6047 | 17284.1036 | 632243.2287 | 16247.0573 | 608966.3727 | 3899.2938 | 149837.187 | 11697.8813 | 634870.2175 | 14973.2881 | 833655.1862
|  | MTR SHOP |  | 77352.0611 |  | 72872.8978 |  | 70182.2884 |  | 17271.4696 |  | 51814.4088 |  | 68034.2887
Total
| Total Field Work Reimbursments |  |  | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX | XXXXX
| YEAR |  | MONTH |  | MARP | MDMS | ZCON | ZCON_NTF | MC01 | MWNR |  |  | YEAR |  | MONTH |  | MARP | MDMS | ZCON | ZCON_NTF | MC01 | MWNR
| - | ---------- | ---------- |  | ---------- | ---------- | ---------- | ---------- | ---------- |  |  |  | - | ---------- | ---------- |  | ---------- | ---------- | 2012: ----------; 2013: ----------; 2014: ----------
| E | 2010 | 6 |  | 28 | 209 | 17 | 341 | 0 | 0 |  |  | G | 2010 | 6 |  | 520 | 528 | 154 | 418 | 173 | 0
| E | 2010 | 7 |  | 37 | 79 | 28 | 452 | 0 | 0 |  |  | G | 2010 | 7 |  | 414 | 567 | 206 | 715 | 258 | 0
| E | 2010 | 8 |  | 59 | 98 | 20 | 510 | 0 | 0 |  |  | G | 2010 | 8 |  | 432 | 870 | 53 | 180 | 284 | 0
| E | 2010 | 9 |  | 101 | 132 | 10 | 255 | 0 | 0 |  |  | G | 2010 | 9 |  | 343 | 317 | 60 | 226 | 126 | 0
| E | 2010 | 10 |  | 162 | 101 | 23 | 801 | 0 | 0 |  |  | G | 2010 | 10 |  | 291 | 489 | 201 | 1250 | 232 | 0
| E | 2010 | 11 |  | 125 | 21 | 8 | 450 | 0 | 0 |  |  | G | 2010 | 11 |  | 231 | 463 | 235 | 835 | 531 | 0
| E | 2010 | 12 |  | 194 | 64 | 9 | 317 | 0 | 0 |  |  | G | 2010 | 12 |  | 315 | 741 | 210 | 317 | 471 | 0
| E | 2011 | 1 |  | 177 | 76 | 10 | 529 | 0 | 0 |  |  | G | 2011 | 1 |  | 151 | 443 | 456 | 643 | 340 | 0
| E | 2011 | 2 |  | 136 | 48 | 8 | 364 | 0 | 0 |  |  | G | 2011 | 2 |  | 198 | 298 | 752 | 1403 | 450 | 0
| E | 2011 | 3 |  | 214 | 54 | 33 | 385 | 0 | 0 |  |  | G | 2011 | 3 |  | 171 | 522 | 833 | 1390 | 538 | 0
| E | 2011 | 4 |  | 108 | 59 | 19 | 333 | 0 | 0 |  |  | G | 2011 | 4 |  | 70 | 391 | 616 | 1138 | 641 | 0
| E | 2011 | 5 |  | 137 | 68 | 27 | 472 | 0 | 0 |  |  | G | 2011 | 5 |  | 15 | 308 | 355 | 632 | 767 | 0
| E | 2011 | 6 |  | 137 | 88 | 11 | 354 | 0 | 0 |  |  | G | 2011 | 6 |  | 22 | 438 | 293 | 686 | 673 | 0
| E | 2011 | 7 |  | 203 | 32 | 17 | 458 | 0 | 0 |  |  | G | 2011 | 7 |  | 2 | 341 | 137 | 457 | 314 | 0
| E | 2011 | 8 |  | 163 | 41 | 13 | 424 | 0 | 0 |  |  | G | 2011 | 8 |  | 1 | 292 | 226 | 967 | 396 | 0
| E | 2011 | 9 |  | 199 | 52 | 11 | 282 | 0 | 0 |  |  | G | 2011 | 9 |  | 103 | 174 | 130 | 1102 | 336 | 0
| E | 2011 | 10 |  | 167 | 32 | 16 | 276 | 0 | 0 |  |  | G | 2011 | 10 |  | 4 | 223 | 180 | 1041 | 272 | 0
| E | 2011 | 11 |  | 171 | 37 | 23 | 414 | 0 | 0 |  |  | G | 2011 | 11 |  | 7 | 161 | 156 | 423 | 192 | 0
| E | 2011 | 12 |  | 211 | 86 | 18 | 388 | 0 | 0 |  |  | G | 2011 | 12 |  | 0 | 189 | 673 | 825 | 207 | 0
| E | 2012 | 1 |  | 116 | 33 | 23 | 221 | 0 | 0 |  |  | G | 2012 | 1 |  | 1 | 154 | 544 | 692 | 377 | 0
| E | 2012 | 2 |  | 233 | 43 | 77 | 402 | 0 | 0 |  |  | G | 2012 | 2 |  | 0 | 378 | 772 | 929 | 372 | 0
| E | 2012 | 3 |  | 183 | 75 | 27 | 370 | 0 | 0 |  |  | G | 2012 | 3 |  | 10 | 333 | 724 | 858 | 284 | 3
| E | 2012 | 4 |  | 123 | 96 | 13 | 305 | 0 | 0 |  |  | G | 2012 | 4 |  | 3 | 223 | 387 | 547 | 76 | 30
| E | 2012 | 5 |  | 117 | 48 | 19 | 347 | 0 | 0 |  |  | G | 2012 | 5 |  | 0 | 241 | 263 | 624 | 66 | 34
|  | Avg Monthly |  |  | 145.875 | 70 | 20 | 393.75 | 0 | 0 |  |  |  | Avg Monthly |  |  | 11.9091 | 246.2727 | 381.0909 | 769.5455 | 262.9091 | 30
|  | Avg Annual | 12 | E | 1750.5 | 840 | 240 | 4725 | 0 |  |  |  |  | Avg Annual | 12 | G | 142.9091 | 2955.2727 | 4573.0909 | 9234.5455 | 3154.9091 | 360
| 2013 | Vol Reduction Est: | 10% | E | 1575.45 | 756 | 216 | 4252.5 | 0 |  |  |  | 2013 | Vol Reduction Est: | 8% | G | 131.4764 | 2718.8509 | 4207.2436 | 8495.7818 | 2902.5164 | 331.2
| 2014 | Vol Reduction Est: | 10% | E | 1417.905 | 680.4 | 194.4 | 3827.25 | 0 |  |  |  | 2014 | Vol Reduction Est: | 8% | G | 120.9583 | 2501.3428 | 3870.6641 | 7816.1193 | 2670.3151 | 304.704
| 2015 | Vol Reduction Est: | 6% | E | 1332.8307 | 639.576 | 182.736 | 3597.615 | 0 |  |  |  | 2015 | Vol Reduction Est: | 6% | G | 113.7008 | 2351.2623 | 3638.4243 | 7347.1521 | 2510.0962 | 286.4218
| 2016 | Vol Reduction Est: | 4% | E | 1279.5175 | 613.993 | 175.4266 | 3453.7104 | 0 |  |  |  | 2016 | Vol Reduction Est: | 4% | G | 109.1527 | 2257.2118 | 3492.8873 | 7053.266 | 2409.6923 | 274.9649
| 2017 | Vol Reduction Est: | 4% | E | 1228.3368 | 589.4332 | 168.4095 | 3315.562 | 0 |  |  |  | 2017 | Vol Reduction Est: | 4% | G | 104.7866 | 2166.9233 | 3353.1718 | 6771.1354 | 2313.3046 | 263.9663
| CPI* | 4.4% is the June to June 12 month Annual CPI-U Change for all items less shelter and not seasonally adjusted
| S23-V23 | CPI assumptions provided by corporate planning.
| # of Months credit owed PSE |  | XXXXX
XXXXX

## SSPriceing (R)
SaaS/NOC/Deployment Services
C+I Deployment | Quantity | ASP | Total
|  | ($) | ($M)
Capital Expenditure
Residential Meters | XXXXXXX | XXXXXXX | XXXXXXX
Commercial Meters | XXXXXXX | XXXXXXX | XXXXXXX
Residential Network Interface Cards | XXXXXXX | XXXXXXX | XXXXXXX
Commercial Network Interface Cards | XXXXXXX | XXXXXXX | XXXXXXX
Residential Gas IMUs | XXXXXXX | XXXXXXX | XXXXXXX
Commercial Gas IMUs | XXXXXXX | XXXXXXX | XXXXXXX
Access Point | XXXXXXX | XXXXXXX | XXXXXXX
Relay | XXXXXXX | XXXXXXX | XXXXXXX
Network Infrastructure |  |  | XXXXXXX
Tools |  |  | XXXXXXX
Initial Deployment Support (1) |  |  | XXXXXXX
Meter Installation |  |  | XXXXXXX
Gas IMU Installation |  |  | XXXXXXX
Network Infrastructure Installation |  |  | XXXXXXX
Total Capital Expenditure |  |  | XXXXXXX
Operating Expense
Environment Setup, Installation, Configuration, and Test (2) |  |  | XXXXXXX
SaaS Fees - Production Environment |  |  | XXXXXXX
SaaS Fees - Disaster Recovery Environment |  |  | XXXXXXX
SaaS Fees - Development Environment |  |  | XXXXXXX
SaaS Fees - Test Environment |  |  | XXXXXXX
WAN Backhaul |  |  | XXXXXXX
Ongoing Deployment Support (3) |  |  | XXXXXXX
Tools Software Maintenance and Support (4) |  |  | XXXXXXX
Total Operating Expense |  |  | XXXXXXX
TOTAL |  |  | XXXXXXX
XXXXXXX
XXXXXXX
XXXXXXX
XXXXXXX
XXXXXXX
XXXXXXX
XXXXXXX
Full Deployment | Quantity | ASP | Total
|  | ($) | ($M)
Capital Expenditure
Residential Meters | XXXXXXX | XXXXXXX | XXXXXXX
Commercial Meters | XXXXXXX | XXXXXXX | XXXXXXX
Residential Network Interface Cards | XXXXXXX | XXXXXXX | XXXXXXX
Commercial Network Interface Cards | XXXXXXX | XXXXXXX | XXXXXXX
Residential Gas IMUs | XXXXXXX | XXXXXXX | XXXXXXX
Commercial Gas IMUs | XXXXXXX | XXXXXXX | XXXXXXX
Access Point | XXXXXXX | XXXXXXX | XXXXXXX
Relay | XXXXXXX | XXXXXXX | XXXXXXX
Network Infrastructure |  |  | XXXXXXX
Tools |  |  | XXXXXXX
Initial Deployment Support (1) |  |  | XXXXXXX
Meter Installation |  |  | XXXXXXX
Gas IMU Installation |  |  | XXXXXXX
Network Infrastructure Installation |  |  | XXXXXXX
Total Capital Expenditure |  |  | XXXXXXX
Operating Expense
Environment Setup, Installation, Configuration, and Test (2) |  |  | XXXXXXX
SaaS Fees - Production Environment |  |  | XXXXXXX
SaaS Fees - Disaster Recovery Environment |  |  | XXXXXXX
SaaS Fees - Development Environment |  |  | XXXXXXX
SaaS Fees - Test Environment |  |  | XXXXXXX
WAN Backhaul |  |  | XXXXXXX
Ongoing Deployment Support (3) |  |  | XXXXXXX
Tools Software Maintenance and Support (4) |  |  | XXXXXXX
Total Operating Expense |  |  | XXXXXXX
TOTAL |  |  | XXXXXXX
Pricing Notes
XXXXXXXX
XXXXXXXX
XXXXXXXX
XXXXXXXX
XXXXXXXX
XXXXXXXX

## SaSSNOC (R)
C+I
($M)
| Year | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 |  | TOTAL
Capital Expenditure
| Residential Meters | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
| Commercial Meters | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
| Residential Network Interface Cards | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
| Commercial Network Interface Cards | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
| Residential Gas IMUs | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
| Commercial Gas IMUs | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
| Access Point | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
| Relay | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
| Network Infrastructure | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
| Tools | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
| Initial Deployment Support (1) | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
| Meter Installation | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
| Gas IMU Installation | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
| Network Infrastructure Installation | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
| Total Capital Expenditure | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Operating Expense
| Environment Setup, Installation, Configuration, and Test (2) | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
| SaaS Fees - Production Environment | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
| SaaS Fees - Disaster Recovery Environment | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
| SaaS Fees - Development Environment | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
| SaaS Fees - Test Environment | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
| WAN Backhaul | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
| Ongoing Deployment Support (3) | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
| Tools Software Maintenance and Support (4) | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
| Total Operating Expense | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
|  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
| TOTAL | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Pricing Notes
XXXXXX
XXXXXX
XXXXXX
XXXXXX
XXXXXX
XXXXXX
Full Deployment
($M)
| Year | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 |  | TOTAL
Capital Expenditure
| Residential Meters | XXXXXX | XXXXXX | XXXXXX | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | XXXXXX
| Commercial Meters | XXXXXX | XXXXXX | XXXXXX | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | XXXXXX
| Residential Network Interface Cards | XXXXXX | XXXXXX | XXXXXX | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | XXXXXX
| Commercial Network Interface Cards | XXXXXX | XXXXXX | XXXXXX | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | XXXXXX
| Residential Gas IMUs | XXXXXX | XXXXXX | XXXXXX | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | XXXXXX
| Commercial Gas IMUs | XXXXXX | XXXXXX | XXXXXX | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | XXXXXX
| Access Point | XXXXXX | XXXXXX | XXXXXX | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | XXXXXX
| Relay | XXXXXX | XXXXXX | XXXXXX | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | XXXXXX
| Network Infrastructure | XXXXXX | XXXXXX | XXXXXX | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | XXXXXX
| Tools | XXXXXX | XXXXXX | XXXXXX | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | XXXXXX
| Initial Deployment Support (1) | XXXXXX | XXXXXX | XXXXXX | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | XXXXXX
| Meter Installation | XXXXXX | XXXXXX | XXXXXX | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | XXXXXX
| Gas IMU Installation | XXXXXX | XXXXXX | XXXXXX | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | XXXXXX
| Network Infrastructure Installation | XXXXXX | XXXXXX | XXXXXX | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | XXXXXX
| Total Capital Expenditure | XXXXXX | XXXXXX | XXXXXX | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | XXXXXX
Operating Expense
| Environment Setup, Installation, Configuration, and Test (2) | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
| SaaS Fees - Production Environment | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
| SaaS Fees - Disaster Recovery Environment | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
| SaaS Fees - Development Environment | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
| SaaS Fees - Test Environment | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
| WAN Backhaul | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
| Ongoing Deployment Support (3) | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
| Tools Software Maintenance and Support (4) | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
| Total Operating Expense | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
|  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
| TOTAL | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Pricing Notes
XXXXXXX
XXXXXXX
XXXXXXX
XXXXXXX
XXXXXXX
XXXXXXX

## GasExch
GFR Average Times for Removal and Installation of Meters
| CFS Tech |  | Regulators
Event | Est. Intallation Time in Minutes | Est. Removal Time in Minutes | Est. Removal Time in Minutes
Drive | 7.5 | 7.5 | 5
Set-Up | 4.5 | 2.5 | 2
Removal | 3 | 3 | 2
Install | 5 | 0 | 5
Relight/ Customer Comm. | 10 | 5 | 10
Paperwork | 10 | 6 | 5
Pick-Up/ Drop-Off Material | 5 | 3 | 3
Handling and Moving
Testing
Checking AMR Module
Painting (27% of the Time)
Total Time (minutes) | 45 | 27 | 32
CFS Technician Hourly Wage | 31.6 | 31.45 | 31.45
Est. OH's and assessments | 70.8188 | 70.4826 | 70.4826
TOTAL Loaded Hourly Wage | 102.4188 | 101.9326 | 101.9326
Cost Per Minute | 1.707 | 1.6989 | 1.6989
Total Cost | 76.8141 | 45.8697 | 54.3641
Total Install and Remove | 122.6837
OVERHEAD (Based on YTD Rolling 12) | 224.1%
COR Unit Cost |  |  | 50.8301
Note on A187: jmccla: from cellnet -- total number of unique meters in Mtr Rdg Flat Rate TOU tab of CN Bill Summary compare to Navigator 'All Route Summary Report' total meters on production routes. Adjusted Daily Contract Performance Statistics Total billing meters at end of accrual month
Note on A206: jmccla: From Michaels at first of year
Note on A212: jmccla: From last invoice analysis, average lease cost
Note on B248: Puget Sound Energy: reduce to 20 hrs per week starting january 2010
Note on D184: John McClaine: From Rachel Montoya
Note on D214: jmccla: From Theresa
Note on D235: John McClaine: Should be in Invoice for July
Note on D236: John McClaine: call Mike or Dirk
Note on F184: John McClaine: Loaded cost of 1/2 lead
Note on H187: John McClaine: Jane, end of accrual month from MDW -- prod routes
Note on H190: John McClaine: All route summary report, prod route total and Grand Total Last day of billing month

## ElecExch
SINGLE-PHASE METER
Task |  | Job Class |  | Time -min. | $ per meter | Direct Labor
Testing meter |  | Meter Tester |  | 20 | 13.95
Process mtr doc. |  | Operating Clerk |  | 5 | 2.9
Install meter |  | Serviceman |  | 10 | 11.15
Transportation |  | Group 6 |  | 10 | 2.23
-----
|  |  |  | TOTAL= | 30.23 | 17.042
POLY-PHASE METER
Task |  | Job Class |  | Time -min. | $ per meter
Testing meter |  | Meter Tester |  | 20 | 13.95
Process mtr doc. |  | Operating Clerk |  | 5 | 2.9
Install meter |  | Meter Journeyman |  | 60 | 64.08
Transportation |  | Group 3 |  | 30 | 2.1
-----
|  |  |  | TOTAL= | 83.03 | 49.2575
CURRENT or POTENTIAL TRANSFORMER
Task |  | Job Class |  | Time -min. | $ per transformer
Testing transformer |  | Meter Journeyman |  | 10 | 10.68
Process transf. doc. |  | Operating Clerk |  | 3 | 1.74
Wire & install trfr. |  | Meter Journeyman |  | 45 | 48.06
Transportation |  | Group 3 |  | 30 | 2.1
-----
|  |  |  | TOTAL= | 62.58 | 36.8107
TEST SWITCH
Task |  | Job Class |  | Time -min. | $ per item
Process equip. doc. |  | Operating Clerk |  | 3 | 1.74
Install sw. or trfr. |  | Meter Journeyman |  | 30 | 32.04
Transportation |  | Group 3 |  | 15 | 1.05
-----
|  |  |  | TOTAL= | 34.83 | 20.56
UG PRIMARY METERING CABINET
Task |  | Job Class |  | Time -hrs | $ per cabinet
Inspection |  | Meter Journeyman |  | 0.75 | 48.0577
Setup/Installation |  | Meter Journeyman |  | 4 | 256.308
Transportation |  | Group 3 |  | 4 | 16.8
-----
|  |  |  | TOTAL= | 321.1658 | 185.25
OH PRIMARY METERING CLUSTER
Task |  | Job Class |  | Time -hrs | $ per meter
Construction |  | Meter Journeyman |  | 8 | 512.616
Installation |  | Meter Journeyman |  | 6 | 384.462
Transportation |  | Group 3 |  | 3 | 12.6
-----
|  |  |  | TOTAL= | 909.678 | 546
SINGLE-PHASE or POLYPHASE METER (removal)
Task |  | Job Class |  | Time -min. | $ per meter removal
Remove meter |  | Serviceman |  | 5 | 5.58
Process mtr cards |  | Operating Clerk |  | 3 | 1.74
Transportation |  | Group 6 |  | 5 | 1.12
-----
|  |  |  | TOTAL= | 8.44 | 4.4553
CURRENT or POTENTIAL TRANSFORMER (removal)
Task |  | Job Class |  | Time -min. | $ per transf removal
Remove transformer |  | Meter Journeyman |  | 15 | 16.02
Process trf. cards |  | Meter Clerk |  | 3 | 1.74
Transportation |  | Group 3 |  | 30 | 2.1
-----
|  |  |  | TOTAL= | 19.86 | 10.8095
TEST SWITCH or PHASE SHIFTING TRANSFORMER (removal)
Task |  | Job Class |  | Time -min. | $ per removal
Remove equipment |  | Meter Journeyman |  | 15 | 16.02
Process equip. cards |  | Meter Clerk |  | 3 | 1.74
Transportation |  | Group 3 |  | 30 | 2.1
-----
|  |  |  | TOTAL= | 19.86 | 10.8095
OH PRIMARY METERING CLUSTER (removal)
Task |  | Job Class |  | Time -hrs | $ per removal
Dismantle cluster |  | Meter Helper |  | 1 | 42.24
-----
|  |  |  | TOTAL= | 42.24 | 25.7091
UG PRIMARY PADMOUNT METERING ENCLOSURE (removal)
Task |  | Job Class |  | Time -hrs | $ per removal
Remove meters & |  | Meter Helper |  | 2 | 84.48
instrument transformers |  |  |  |  | -----
|  |  |  | TOTAL= | 84.48 | 51.4181
PROGRAM ELECTRONIC METER
Task |  | Job Class |  | Time -hrs | $
Program Meter |  | Meter Technician |  | 8 | 327.68
|  |  |  | TOTAL= | 327.68 | 199.44
INSTALL CELL PHONE AND ANTENNA
Task |  | Job Class |  | Time -hrs | $
Install Cell Phone |  | Meter Technician |  | 2 | 83.46
|  |  |  | TOTAL= | 83.46 | 50.7973
NOTE: Payroll Overhead and Distribution included in labor.
RESIDENTIAL GAS | 250/425
Task |  | Job Class |  | Time -min. | $ per meter | Direct Labor
Install meter & regulator |  | CFS |  | 42 | 36.17
-----
|  |  |  | TOTAL= | 36.17 | 22.0146
COMMERCIAL GAS | 1000
Task |  | Job Class |  | Time -min. | $ per meter | Direct Labor
Install meter & regulator |  | CFS |  | 42 | 36.17
-----
|  |  |  | TOTAL= | 36.17 | 22.0146
COMMERCIAL GAS | 1400-2300
Task |  | Job Class |  | Time -min. | $ per meter | Direct Labor
Install meter & regulator |  | CFS |  | 45 | 38.75
-----
|  |  |  | TOTAL= | 38.75 | 23.5849
INDUSTRIAL GAS A | 3000, 5000, 7000
Task |  | Job Class |  | Time -min. | $ per meter | Direct Labor
Install meter & regulator |  | Utility Worker |  | 140 | 103.01
|  | Fitter III |  | 140 | 126.4
|  | Operating Clerk |  | 20 | 11.59
|  | Administrative |  | 60 | 32.47
|  | Pressure Control |  | 20 | 18.06
|  | Instrumentation |  | 30 | 27.08
-----
|  |  |  | TOTAL= | 318.61 | 177.4376
INDUSTRIAL GAS B | 11000 to 30000
Task |  | Job Class |  | Time -min. | $ per meter | Direct Labor
Install meter & regulator |  | Utility Worker |  | 960 | 706.36
|  | Fitter III |  | 960 | 866.72
|  | Operating Clerk |  | 20 | 11.59
|  | Administrative |  | 60 | 32.47
|  | Pressure Control |  | 40 | 36.11
|  | Instrumentation |  | 30 | 27.08
-----
|  |  |  | TOTAL= | 1680.33 | 1006.2386
INDUSTRIAL GAS C | over 30000
Task |  | Job Class |  | Time -min. | $ per meter | Direct Labor
Install meter & regulator |  | Utility Worker |  | 4800 | 3531.79
|  | Fitter III |  | 4800 | 4333.58
|  | Operating Clerk |  | 20 | 11.59
|  | Administrative |  | 60 | 32.47
|  | Pressure Control |  | 60 | 54.17
|  | Instrumentation |  | 30 | 27.08
-----
|  |  |  | TOTAL= | 7990.68 | 4846.9872
Source: PSE Cost of Metering 2011
PSE Monthly Invoice, July 2011
Demand Backup Reads |  |  | Number |  | Cost
| Loaded Lead |  |  |  | 0 | Validate this on other page
Automated Meter Reads |  |  | 1882905 |  |  |  | Total Meters AMR | 1886897
|  | 2011 | 1.3141 |  | 1.3735 |  | Total Gas Meters AMR | 778246
|  | 2010 | 1.3446 |  |  |  | Total Elec Meters AMR | 1108651
|  | 2009 | 1.317 |  |  |  | Total Meters Navigator | 1886897 | AMR Cellnet
Cost |  | 2008 | 1.2899 |  |  |  |  | 1890040 | All
|  | 2007 | 1.2634
|  | 2006 | 1.2374
|  | 2005 | 1.2119
|  | 2004 | 1.187 |  | Calculated | Delta
|  |  | Actual |  | 2474282.1537 | 111916.6863
Cellnet Invoice |  |  | 2586198.84
Ratio -- elec/total |  |  | 58.76%
Meter Read Credit | -548000 | electric | -321978.76
|  | gas | -226021.24
2010
|  | 2009 | 16070.91
Ops Center Lease |  | 2008 | 15740.41
|  | 2007 | 17348.7
|  | 2006 | 15099.569
|  | 2005 | 14789
|  | 2004 | 14485
AMR Network Lease
AMR Field Maint |  |  | Number of Jobs
| Elec | MARP | 131 | 77 | 10087
|  | MDMS | 12 | 77 | 924
|  | ZCON | 11 | 77 | 847
|  | ZCON_NTF | 0 | 77 | 0
| Gas | MARP | 20 | 22.4 | 448
|  | MDMS | 51 | 22.4 | 1142.4
|  | ZCON | 48 | 22.4 | 1075.2
|  | ZCON_NTF | 0 | 22.4 | 0
|  | MC01 (TEST) | 77 | 25 | 1925
|  | MC01 (ORDER) | 100 | 125 | 12500
|  |  | 2004 | 23.89
|  |  | 2005 | 24.39
|  |  | 2006 | 24.9
|  |  | 2007 | 25.43
|  |  | 2008 | 25.95
|  |  | 2009 | 26.4949
|  |  | 2010 | 27.0513
|  |  | 2011 | 27.6194
72000 July 2006
DR Fee |  |  | 0 |  | 6.7 | 10,000 typical
Batteries |  |  | 0 |  | November only
SAS 70 |  |  | 0
% EII
EA | Oracle | 95% | 2500 |  | 2375
| Engineering | 90% | 0 |  | 0
| total |  |  |  | 2375
MTE | EII | 85% | 4600 |  | 3910
| MNS | 80% | 0 |  | 0
PAUL CILLIS
CRAIG BOICE |  |  | 0
DATARAKER |  |  | 57000

## Gas Install
250
Item | Description | Qty/Hours | Unit cost | $ Cost
Diaphragm250/275 |  | 1 | 50.14 | 50
Regulator |  | 1 | 23.1 | 23
Stores overhead |  |  | 8.79% | 4.4
Small Tools Expense |  |  | 7.5% | 2
Meter installation |  | 1 | 36.3 | 36.3
-----
115.7
General overhead |  |  | 16.5% | 19.09
-----
|  |  | TOTAL= | 134.79
=====
250 AMR
Item | Description | Qty/Hours | Unit cost | $ Cost
Diaphragm250/275AMR |  | 1 | 72.6 | 73
Regulator |  | 1 | 23.1 | 23
A9 Valve |  | 1 | 25.09 | 25
Stores overhead (A9 Valve) |  |  | 8.79% | 2.2
Stores overhead |  |  | 8.79% | 6.42
Small Tools Expense |  |  | 7.5% | 2
Meter installation |  | 1 | 36.3 | 36.3
-----
167.92
General overhead |  |  | 16.5% | 27.71
-----
|  |  | TOTAL= | 195.63
=====
425
Item | Description | Qty/Hours | Unit cost | $ Cost
Diaphragm425 |  | 1 | 130.32 | 130
Regulator |  | 1 | 23.1 | 23
Stores overhead |  |  | 8.79% | 11.43
Small Tools Expense |  |  | 7.5% | 2
Meter installation |  | 1 | 36.3 | 36.3
-----
202.73
General overhead |  |  | 16.5% | 33.45
-----
|  |  | TOTAL= | 236.18
=====
425 AMR
Item | Description | Qty/Hours | Unit cost | $ Cost
Diaphragm425AMR |  | 1 | 175.17 | 175
Regulator |  | 1 | 23.1 | 23
Meter Bar |  | 1 | 252.38 | 252
Stores overhead (meter bar) |  |  | 8.79% | 22.15
Stores overhead |  |  | 8.79% | 15.38
Small Tools Expense |  |  | 7.5% | 2
Meter installation |  | 1 | 36.3 | 36.3
-----
525.83
General overhead |  |  | 16.5% | 86.76
-----
|  |  | TOTAL= | 612.59
=====
630 AMR
Item | Description | Qty/Hours | Unit cost | $ Cost
Diaphragm630AMR |  | 1 | 423.59 | 424
Regulator |  | 1 | 23.1 | 23
Meter Bar |  | 1 | 252.38 | 252
Stores overhead (meter bar) |  |  | 8.79% | 22.15
Stores overhead |  |  | 8.79% | 37.27
Small Tools Expense |  |  | 7.5% | 2
Meter installation |  | 1 | 36.3 | 36.3
-----
796.72
General overhead |  |  | 16.5% | 131.46
-----
|  |  | TOTAL= | 928.18
=====
1000
Item | Description | Qty/Hours | Unit cost | $ Cost
Diaphragm1000TC |  | 1 | 739.72 | 740
Regulator |  | 1 | 109 | 109
Stores overhead |  |  | 8.79% | 65.05
Small Tools Expense |  |  | 7.5% | 2
Meter installation |  | 1 | 36.3 | 36.3
-----
952.35
General overhead |  |  | 16.5% | 157.14
-----
|  |  | TOTAL= | 1109.49
=====
1000 AMR
Item | Description | Qty/Hours | Unit cost | $ Cost
Diaphragm1000AMRTC |  | 1 | 853.47 | 853
Regulator |  | 1 | 109 | 109
Meter Bar (1000) |  | 1 | 222.69 | 223
Stores overhead (meter bar) |  |  | 8.79% | 19.6
Stores overhead |  |  | 8.79% | 74.98
Small Tools Expense |  |  | 7.5% | 2
Meter installation |  | 1 | 36.3 | 36.3
-----
1317.88
General overhead |  |  | 16.5% | 217.45
-----
|  |  | TOTAL= | 1535.33
=====
1400
Item | Description | Qty/Hours | Unit cost | $ Cost
Diaphragm1400TC |  | 1 | 803.48 | 803
Regulator |  | 1 | 191 | 191
Stores overhead |  |  | 8.79% | 70.58
Small Tools Expense |  |  | 7.5% | 2
Meter installation |  | 1 | 38.9 | 38.9
-----
1105.48
General overhead |  |  | 16.5% | 182.4
-----
|  |  | TOTAL= | 1287.88
=====
2300
Item | Description | Qty/Hours | Unit cost | $ Cost
Diaphragm2300TC |  | 1 | 960.75 | 961
Regulator |  | 1 | 191 | 191
Stores overhead |  |  | 8.79% | 84.47
Small Tools Expense |  |  | 7.5% | 2
Meter installation |  | 1 | 38.9 | 38.9
-----
1277.37
General overhead |  |  | 16.5% | 210.77
-----
|  |  | TOTAL= | 1488.14
=====
3000
Item | Description | Qty/Hours | Unit cost | $ Cost
Rotary3000TC |  | 1 | 656.57 | 657
Regulator |  | 1 | 1843.43 | 1843
Stores overhead |  |  | 8.79% | 57.75
Small Tools Expense |  |  | 7.5% | 14
Meter installation |  | 1 | 327.09 | 327.09
-----
2898.84
General overhead |  |  | 16.5% | 478.31
-----
|  |  | TOTAL= | 3377.15
=====
5000
Item | Description | Qty/Hours | Unit cost | $ Cost
Rotary5000TC |  | 1 | 282.67 | 283
Regulator |  | 1 | 2217.33 | 2217
Stores overhead |  |  | 8.79% | 24.88
Small Tools Expense |  |  | 7.5% | 14
Meter installation |  | 1 | 327.09 | 327.09
-----
2865.97
General overhead |  |  | 16.5% | 472.89
-----
|  |  | TOTAL= | 3338.86
=====
7000
Item | Description | Qty/Hours | Unit cost | $ Cost
Rotary7000TC |  | 1 | 305.82 | 306
Regulator |  | 1 | 2194.18 | 2194
Stores overhead |  |  | 8.79% | 26.9
Small Tools Expense |  |  | 7.5% | 14
Meter installation |  | 1 | 327.09 | 327.09
-----
2867.99
General overhead |  |  | 16.5% | 473.22
-----
|  |  | TOTAL= | 3341.21
=====
11000
Item | Description | Qty/Hours | Unit cost | $ Cost
Rotary11000TC |  | 1 | 847.93 | 848
Regulator |  | 1 | 2252.07 | 2252
Stores overhead |  |  | 8.79% | 74.54
Small Tools Expense |  |  | 7.5% | 78
Meter installation |  | 1 | 1734.67 | 1734.67
-----
4987.21
General overhead |  |  | 16.5% | 822.89
-----
|  |  | TOTAL= | 5810.1
=====
16000
Item | Description | Qty/Hours | Unit cost | $ Cost
Rotary16000TC |  | 1 | 312.64 | 313
Regulator |  | 1 | 3100 | 3100
Stores overhead |  |  | 8.79% | 27.51
Small Tools Expense |  |  | 7.5% | 78
Meter installation |  | 1 | 1734.67 | 1734.67
-----
5253.18
General overhead |  |  | 16.5% | 866.77
-----
|  |  | TOTAL= | 6119.95
=====
18000
Item | Description | Qty/Hours | Unit cost | $ Cost
Turbine18000 |  | 1 | 2198.73 | 2199
Regulator |  | 1 | 3100 | 3100
Stores overhead |  |  | 8.79% | 193.29
Small Tools Expense |  |  | 7.5% | 78
Meter installation |  | 1 | 1734.67 | 1734.67
-----
7304.96
General overhead |  |  | 16.5% | 1205.32
-----
|  |  | TOTAL= | 8510.28
=====
23000
Item | Description | Qty/Hours | Unit cost | $ Cost
Rotary23000TC |  | 1 | 2978.32 | 2978
Regulator |  | 1 | 13000 | 13000
Stores overhead |  |  | 8.79% | 261.77
Small Tools Expense |  |  | 7.5% | 78
Meter installation |  | 1 | 1734.67 | 1734.67
-----
18052.44
General overhead |  |  | 16.5% | 2978.65
-----
|  |  | TOTAL= | 21031.09
=====
30000
Item | Description | Qty/Hours | Unit cost | $ Cost
Turbine30000 |  | 1 | 2943.96 | 2944
Regulator |  | 1 | 13000 | 13000
Stores overhead |  |  | 8.79% | 258.78
Small Tools Expense |  |  | 7.5% | 78
Meter installation |  | 1 | 8257.52 | 8257.52
-----
24538.3
General overhead |  |  | 16.5% | 4048.82
-----
|  |  | TOTAL= | 28587.12
=====
38000
Item | Description | Qty/Hours | Unit cost | $ Cost
Rotary38000TC |  | 1 | 3125.26 | 3125
Regulator |  | 1 | 13000 | 13000
Stores overhead |  |  | 8.79% | 274.69
Small Tools Expense |  |  | 7.5% | 374
Meter installation |  | 1 | 8257.52 | 8257.52
-----
25031.21
General overhead |  |  | 16.5% | 4130.15
-----
|  |  | TOTAL= | 29161.36
=====
60000
Item | Description | Qty/Hours | Unit cost | $ Cost
Turbine60000 |  | 1 | 4731.65 | 4732
Regulator |  | 1 | 13000 | 13000
Large Industrial Meter Assembly |  | 1 | 5000 | 5000
Stores overhead |  |  | 8.79% | 415.94
Small Tools Expense |  |  | 7.5% | 374
Meter installation |  | 1 | 8257.52 | 8257.52
-----
31779.46
General overhead |  |  | 16.5% | 5243.61
-----
|  |  | TOTAL= | 37023.07
=====
150000
Item | Description | Qty/Hours | Unit cost | $ Cost
Turbine150000 |  | 1 | 11529.44 | 11529
Regulator |  | 1 | 13000 | 13000
Large Industrial Meter Assembly |  | 1 | 5000 | 5000
Stores overhead |  |  | 8.79% | 1013.4
Small Tools Expense |  |  | 7.5% | 374
Meter installation |  | 1 | 8257.52 | 8257.52
-----
39173.92
General overhead |  |  | 16.5% | 6463.7
-----
|  |  | TOTAL= | 45637.62
=====

## BatteryProgram (R)
Gas Battery Replacement Program |  | Gas Battery Replacement Program
|  |  |  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35
Line # | Source |  |  | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
1 | Calculated |  | Cost of Battery Pruchases | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
2 | Calculated |  | Cost of Battery Disposals | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
3 | Calculated |  | Cost of Installations (Labor including overhead) | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
4 | Calculated |  | Honeywell Alternative | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
5 | Calculated |  | Total Cost of Battery Program | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
|  |  |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
6
7
8 |  |  | Pricing | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
9
10 | Sue Beardsley |  | Battery | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
11 | Sue Beardsley |  | Battery Disposal Fee | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
12 | Sue Beardsley |  | Cost per Battery + Installation in a Route Based Replacement | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
13 | John McClaine |  | Honeywell Annual Maintenance Fees | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
14 | John McClaine |  | Honeywell Site Licence | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
15 | John McClaine |  | Honeywell Phone Fees per field FTE | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
16 | Estimate |  | Minmum Battery Stock | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
17 | Sue Beardsley |  | Cost of Installations Route Based | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
18 | Sue Beardsley |  | Cost of Installations non-Route Based | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
19
20 |  |  | Quantities | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
21 | Theresa Burch |  | Stock of Batteries | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
22 | Calculated |  | Battery Purchases | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
23 | Theresa Burch |  | Battery Aging Forecast | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
24 |  |  | Battery Forecast Adjusted | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
26 | Calculated with input from Sue Beardsley |  | Battery Installations Proactive | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
27 |  |  | Battery Installations Reactive | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
28 |  |  | Battery Installations w/AMI | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
29 | From Model |  | AMI Gas Modules Deployed in Hybrid AMI Scenario | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
30 | Calculated with input from Sue Beardsley |  | Route or Non-Route Based | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
31 | Calculated |  | Number of FTE's Required | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
32 | Calculated |  | Number of PSE Staff | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
33 | Calculated |  | Number of Temporary Staff | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
34
35
36
37 | Sue Beardsley and Geoffrey Parker |  | Route vs Non Route Costs
38 | Calculated |  |  | 2012: Route Based; 2013: Non-Route; 2014: Non-Route Sue
39 | Calculated |  | Batteries Changed per Day | 2012: XXXXXXX; 2013: XXXXXXX; 2014: XXXXXXX; 2015: XXXXXXX
40 | Calculated |  | Batteries Changed per Year | 2012: XXXXXXX; 2013: XXXXXXX; 2014: XXXXXXX; 2015: XXXXXXX
41 |  |  | Cost of Battery Installation Labor + Overhead only per battery | 2012: XXXXXXX; 2013: XXXXXXX; 2014: XXXXXXX; 2015: XXXXXXX
42 |  |  | Batteries Changed per FTE per year | 2012: XXXXXXX; 2013: XXXXXXX; 2014: XXXXXXX; 2015: XXXXXXX
43 | Corporate Rate |  | Annual Working Days | 2012: XXXXXXX; 2013: XXXXXXX; 2014: XXXXXXX; 2015: XXXXXXX
44 |  |  | Annual Cost per FTE | 2012: XXXXXXX; 2013: XXXXXXX; 2014: XXXXXXX; 2015: XXXXXXX
45 |  |  |  | 2012: XXXXXXX; 2013: XXXXXXX; 2014: XXXXXXX; 2015: XXXXXXX
46 |  |  | Average Module Replacement Rate | 2012: XXXXXXX; 2013: XXXXXXX; 2014: XXXXXXX; 2015: XXXXXXX
47 |  |  | Inflation Rate | 2012: XXXXXXX; 2013: XXXXXXX; 2014: XXXXXXX; 2015: XXXXXXX
48 | bar: 2012 to 2015
Comparison of Battery Programs | bar: 2012 to 2015
|  |  | Nominal Spend 2014-2016 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023
| Proactive w/Status Quo |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
| Proactive w/AMI |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
| Reactive w/Status Quo |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
| Reactive w/AMI |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
[5 empty] | 2014 | 2015 | 2016 | 2017 | 2-Year Total | 3-Year Total | 2-Year Savings | 3-Year Savings | Probabilities
|  |  |  | Proactive w/Status Quo | 443807.9837 | 1018284.3837 | 1793468.881 | 1991319.8569 | 1462092.3674 | 3255561.2484 | 0 |  | 0.45 | 1465002.5618
|  |  |  | Proactive w/AMI | 443807.9837 | 1018284.3837 | 269020.3322 | 0 | 1462092.3674 | 1731112.6996 | 0 | 1524448.5489 | 0.55 | 952111.9848 | XXXXXXX
|  |  |  | Reactive w/Status Quo | 443807.9837 | 702225.8942 | 1325609.4154 | 2748095.9067 | 1146033.8779 | 2471643.2933 | 316058.4895 | 783917.9551 | 0.45 | 1112239.482 | XXXXXXX
|  |  |  | Reactive w/AMI | 443807.9837 | 702225.8942 | 269020.3322 | 0 | 1146033.8779 | 1415054.21 | 316058.4895 | 1840507.0384 | 0.55 | 778279.8155 | XXXXXXX
|  |  |  | 0 | [10 empty] | XXXXXXX
[13 empty] | 1 |  | XXXXXXX
[13 empty] | 526595.249 |  | XXXXXXX
1

## BatteryProgramAlt (R)
Gas Battery Replacement Program |  | Gas Battery Replacement Program
|  |  |  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35
Line # | Source |  |  | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037
1 | Calculated |  | Cost of Battery Pruchases | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
2 | Calculated |  | Cost of Battery Disposals | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
3 | Calculated |  | Cost of Installations (Labor including overhead) | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
4 | Calculated |  | Honeywell Alternative | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
5 | Calculated |  | Total Cost of Battery Program | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
6
7
8 |  |  | Pricing | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037
9
10 | Sue Beardsley |  | Battery | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
11 | Sue Beardsley |  | Battery Disposal Fee | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
12 | Sue Beardsley |  | Cost per Battery + Installation in a Route Based Replacement | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
13 | John McClaine |  | Honeywell Annual Maintenance Fees | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
14 | John McClaine |  | Honeywell Site Licence | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
15 | John McClaine |  | Honeywell Phone Fees per field FTE | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
16 | Estimate |  | Minmum Battery Stock | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
17 | Sue Beardsley |  | Cost of Installations Route Based | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
18 | Sue Beardsley |  | Cost of Installations non-Route Based | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
19
20 |  |  | Quantities | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037
21 | Theresa Burch |  | Stock of Batteries | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
22 | Calculated |  | Battery Purchases | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
23 | Theresa Burch |  | Battery Aging Forecast | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
24 |  |  | Battery Forecast Adjusted | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
25 |  |  |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
26 | Calculated with input from Sue Beardsley |  | Battery Installations Proactive | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
27 | With delay + smoothing |  | Battery Installations Reactive | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
28 |  |  | Battery Installations w/AMI | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
29 | From Model |  | AMI Gas Modules Deployed in Hybrid AMI Scenario | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
30 | Calculated with input from Sue Beardsley |  | Route or Non-Route Based | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
31 | Calculated |  | Number of FTE's Required | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
32 | Calculated |  | Number of PSE Staff | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
33 | Calculated |  | Number of Temporary Staff | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
34
35
36
37 | Sue Beardsley and Geoffrey Parker |  | Route vs Non Route Costs
38 | Calculated |  |  | 2012: Route Based; 2013: Non-Route; 2014: Non-Route Sue
39 | Calculated |  | Batteries Changed per Day | 2012: XXXXXXX; 2013: XXXXXXX; 2014: XXXXXXX
40 | Calculated |  | Batteries Changed per Year | 2012: XXXXXXX; 2013: XXXXXXX; 2014: XXXXXXX
41 |  |  | Cost of Battery Installation Labor + Overhead only per battery | 2012: XXXXXXX; 2013: XXXXXXX; 2014: XXXXXXX
42 |  |  | Batteries Changed per FTE per year | 2012: XXXXXXX; 2013: XXXXXXX; 2014: XXXXXXX
43 | Corporate Rate |  | Annual Working Days | 2012: XXXXXXX; 2013: XXXXXXX; 2014: XXXXXXX
44 |  |  | Annual Cost per FTE | 2012: XXXXXXX; 2013: XXXXXXX; 2014: XXXXXXX
45 |  |  |  | 2012: XXXXXXX; 2013: XXXXXXX; 2014: XXXXXXX
46 |  |  | Average Module Replacement Rate | 2012: XXXXXXX; 2013: XXXXXXX; 2014: XXXXXXX
47 |  |  | Inflation Rate | 2012: XXXXXXX; 2013: XXXXXXX; 2014: XXXXXXX
48

## Costs-Secondary
SMALL SINGLE-PHASE, SECONDARY VOLTAGE SERVICE (200AMP)
Item |  | Description | Qty/Hours | Unit cost | $ Cost
kWh mtr,30A/240V/3W/plain 1-ph. |  |  | 1 | 24.33 | 24
Stores overhead |  |  |  | 8.79% | 2.11
Small Tools Expense |  |  |  | 7.5% | 1
Meter installation |  |  | 1 | 19.24 | 19.24
-----
46.35
General overhead |  |  |  | 16.5% | 7.65
-----
|  |  |  | TOTAL= | 54
=====
SMALL SINGLE-PHASE, SECONDARY VOLTAGE SERVICE (200AMP) AMR
Item |  | Description | Qty/Hours | Unit cost | $ Cost
KWH mtr,30A/240V/3W/AMR 1-ph. |  |  | 1 | 26.55 | 27
Stores overhead |  |  |  | 8.79% | 2.37
Small Tools Expense |  |  |  | 7.5% | 1
Meter installation |  |  | 1 | 19.24 | 19.24
-----
49.61
General overhead |  |  |  | 16.5% | 8.19
-----
|  |  |  | TOTAL= | 57.8
=====
SMALL SINGLE-PHASE, SECONDARY VOLTAGE SERVICE (320AMP) AMR
Item |  | Description | Qty/Hours | Unit cost | $ Cost
KWH mtr,50A/240V/3W/AMR 1-ph CL320. |  |  | 1 | 125.49 | 125
Stores overhead |  |  |  | 8.79% | 10.99
Small Tools Expense |  |  |  | 7.5% | 1
Meter installation |  |  | 1 | 19.24 | 19.24
-----
156.23
General overhead |  |  |  | 16.5% | 25.78
-----
|  |  |  | TOTAL= | 182.01
=====
LARGE SINGLE-PHASE, SECONDARY VOLTAGE SERVICE (401A-800A) AMR
Item |  | Description | Qty/Hours | Unit cost | $ Cost
Materials:
KWH mtr,2.5A/240V/3W/AMR 1-ph. |  |  | 1 | 146.31 | 146
Current trf - 600v,200/5A,Bar |  |  | 2 | 75.65 | 151
-----
| Total materials: |  |  |  | 297
Stores overhead |  |  |  | 8.79% | 26
Small Tools Expense |  |  |  | 7.5% | 6
Meter installation |  |  | 1 | 19.24 | 19.24
C.T. installation |  |  | 2 | 63.95 | 127.9
-----
476.14
General overhead |  |  |  | 16.5% | 78.56
-----
|  |  |  | TOTAL= | 554.7
=====
SMALL THREE-PHASE, SECONDARY VOLTAGE SERVICE (200A) AMR
Item |  | Description | Qty/Hours | Unit cost | $ Cost
KWH mtr,30A/120V/4W/dem'd 3-phElectronicAMR. |  |  | 1 | 151.45 | 151.45
Stores overhead |  |  |  | 8.79% | 13.31
Small Tools Expense |  |  |  | 7.5% | 4
Meter installation |  |  | 1 | 79.36 | 79.36
-----
248.12
General overhead |  |  |  | 16.5% | 40.94
-----
|  |  |  | TOTAL= | 289.06
=====
LARGE THREE-PHASE, SECONDARY VOLTAGE SERVICE (201A-800A) AMR | [5 empty] | LARGE THREE-PHASE, SECONDARY VOLTAGE SERVICE (201A-800A) AMR
Item |  | Description | Qty/Hours | Unit cost | $ Cost | Item |  | Description | Qty/Hours | Unit cost | $ Cost
REMOTE METERING: | [5 empty] | REMOTE METERING:
Materials: | [5 empty] | Materials:
KWH/KVARH mtr,2.5A/120V/4W/ElectronicAMR 3-ph. |  |  | 1 | 322.11 | 322 | Elster A3RAL, MID |  |  | 1 | 594.05 | 594
Current trf - 600v,200/5A,Bar |  |  | 3 | 75.65 | 227 | Current trf - 600v,200/5A,Bar |  |  | 3 | 75.65 | 227
Test sw. 10-position |  |  | 1 | 47.41 | 47 | Test sw. 10-position |  |  | 1 | 47.41 | 47
[5 empty] | ------- | [5 empty] | -------
| Total materials: |  |  |  | 596 |  | Total materials: |  |  |  | 868
Stores overhead |  |  |  | 8.79% | 52 | Stores overhead |  |  |  | 8.79% | 76
Small Tools Expense |  |  |  | 7.5% | 14 | Small Tools Expense |  |  |  | 7.5% | 0
Meter installation |  |  | 1 | 79.36 | 79.36 | Meter installation |  |  | 1 | 79.36 | 79.36
C.T. installation |  |  | 3 | 63.95 | 191.85 | C.T. installation |  |  | 3 | 63.95 | 191.85
Test sw. installation |  |  | 1 | 35.5 | 35.5 | Test sw. installation |  |  | 1 | 35.5 | 35.5
[5 empty] | ------- | [5 empty] | -------
[5 empty] | 968.71 | [5 empty] | 1250.71
General overhead |  |  |  | 16.5% | 159.84 | General overhead |  |  |  | 16.5% | 206.37
[5 empty] | ------- | [5 empty] | -------
|  |  |  | TOTAL= | 1128.55 |  |  |  |  | TOTAL= | 1457.08
=======
SWITCHBOARD:
Item |  | Description | Qty/Hours | Unit cost | $ Cost |  | Switch board metering
KWH/KVARH mtr,2.5A/120V/4W/ElectronicAMR 3-ph. |  |  | 1 | 322.11 | 322 | [5 empty] | Qty | unit cost | Extended cost
Current trf - 600v,1500/5A,Window |  |  | 3 | 162.08 | 486 |  | 4 function meter (Elster A3 with phone modem) |  |  |  | 1 | 595 | 595
Test sw. 10-position |  |  | 1 | 47.41 | 47 |  | Current transformer- 600V 1500/5A, Window |  |  |  | 3 | 121.21 | 363.63
[7 empty] | Test switch 10-position |  |  |  | 1 | 47.02 | 47.02
[11 empty] | Total Material |  | 1005.65
-------
| Total materials: |  |  |  | 855 |  | Store overhead |  |  |  |  | 8% | 80.452
[7 empty] | Small Tools Expense |  |  |  |  | 7.5% | 13
Stores overhead |  |  |  | 8.79% | 75 |  | Meter installation |  |  |  | 1 | 74.1 | 74.1
Small Tools Expense |  |  |  | 7.5% | 14 |  | CT installation |  |  |  | 3 | 59.84 | 179.52
Meter installation |  |  | 1 | 79.36 | 79.36 |  | Test switch installation |  |  |  | 1 | 33.26 | 33.26
C.T. installation |  |  | 3 | 63.95 | 191.85 | [7 empty] | 1352.722
Test sw. installation |  |  | 1 | 35.5 | 35.5
[7 empty] | General overhead |  |  |  |  | 16% | 216.4355
-------
[5 empty] | 1250.71 | [6 empty] | Total | 1569.1575
General overhead |  |  |  | 16.5% | 206.37
-------
|  |  |  | TOTAL= | 1457.08
=======
Switch board metering
[11 empty] | Qty | unit cost | Extended cost
[7 empty] | 4 function meter (Elster A3 with phone modem) |  |  |  | 1 | 595 | 595
[7 empty] | Current transformer- 600V 600/5A, Window |  |  |  | 3 | 117.06 | 351.18
[7 empty] | Test switch 10-position |  |  |  | 1 | 47.02 | 47.02
[11 empty] | Total Material |  | 993.2
[7 empty] | Store overhead |  |  |  |  | 8% | 79.456
[7 empty] | Small Tools Expense |  |  |  |  | 7.5% | 13
[7 empty] | Meter installation |  |  |  | 1 | 74.1 | 74.1
[7 empty] | CT installation |  |  |  | 3 | 59.84 | 179.52
[7 empty] | Test switch installation |  |  |  | 1 | 33.26 | 33.26
1339.276
[7 empty] | General overhead |  |  |  |  | 16% | 214.2842
[12 empty] | Total | 1553.5602

## MetrCsts
SMALL SINGLE-PHASE, SECONDARY VOLTAGE SERVICE (200AMP)
Item |  | Description | Qty/Hours | Unit cost | $ Cost
kWh mtr,30A/240V/3W/plain 1-ph. |  |  | 1 | 26.52 | 27
Stores overhead |  |  |  | 8% | 2.16
Small Tools Expense |  |  |  | 7.5% | 1
Meter installation |  |  | 1 | 30.23 | 30.23
-----
60.39
General overhead |  |  |  | 16% | 9.66
-----
|  |  |  | TOTAL= | 70.05
=====
SMALL SINGLE-PHASE, SECONDARY VOLTAGE SERVICE (200AMP) AMR
Item |  | Description | Qty/Hours | Unit cost | $ Cost
KWH mtr,30A/240V/3W/AMR 1-ph. |  |  | 1 | 26.52 | 27
Stores overhead |  |  |  | 8% | 2.16
Small Tools Expense |  |  |  | 7.5% | 1
Meter installation |  |  | 1 | 30.23 | 30.23
-----
60.39
General overhead |  |  |  | 16% | 9.66
-----
|  |  |  | TOTAL= | 70.05
=====
SMALL SINGLE-PHASE, SECONDARY VOLTAGE SERVICE (320AMP) AMR
Item |  | Description | Qty/Hours | Unit cost | $ Cost
KWH mtr,50A/240V/3W/AMR 1-ph CL320. |  |  | 1 | 89.66 | 90
Stores overhead |  |  |  | 8% | 7.2
Small Tools Expense |  |  |  | 7.5% | 1
Meter installation |  |  | 1 | 30.23 | 30.23
-----
128.43
General overhead |  |  |  | 16% | 20.55
-----
|  |  |  | TOTAL= | 148.98
=====
LARGE SINGLE-PHASE, SECONDARY VOLTAGE SERVICE (401A-800A) AMR
Item |  | Description | Qty/Hours | Unit cost | $ Cost
Materials:
KWH mtr,2.5A/240V/3W/AMR 1-ph. |  |  | 1 | 145.51 | 146
Current trf - 600v,200/5A,Bar |  |  | 2 | 102.1 | 204
-----
| Total materials: |  |  |  | 350
Stores overhead |  |  |  | 8% | 28
Small Tools Expense |  |  |  | 7.5% | 7
Meter installation |  |  | 1 | 30.23 | 30.23
C.T. installation |  |  | 2 | 62.58 | 125.16
-----
540.39
General overhead |  |  |  | 16% | 86.46
-----
|  |  |  | TOTAL= | 626.85
=====
SMALL THREE-PHASE, SECONDARY VOLTAGE SERVICE (200A) AMR
Item |  | Description | Qty/Hours | Unit cost | $ Cost
KWH mtr,30A/120V/4W/dem'd 3-phElectronicAMR. |  |  | 1 | 175.56 | 175.56
Stores overhead |  |  |  | 8% | 14.04
Small Tools Expense |  |  |  | 7.5% | 4
Meter installation |  |  | 1 | 83.03 | 83.03
-----
276.63
General overhead |  |  |  | 16% | 44.26
-----
|  |  |  | TOTAL= | 320.89
=====
LARGE THREE-PHASE, SECONDARY VOLTAGE SERVICE (201A-800A) AMR
Item |  | Description | Qty/Hours | Unit cost | $ Cost
REMOTE METERING:
Materials:
KWH/KVARH mtr,2.5A/120V/4W/ElectronicAMR 3-ph. |  |  | 1 | 322.11 | 322
Current trf - 600v,200/5A,Bar |  |  | 3 | 102.1 | 306
Test sw. 10-position |  |  | 1 | 47.4 | 47
-------
| Total materials: |  |  |  | 675
Stores overhead |  |  |  | 8% | 54
Small Tools Expense |  |  |  | 7.5% | 14
Meter installation |  |  | 1 | 83.03 | 83.03
C.T. installation |  |  | 3 | 62.58 | 187.74
Test sw. installation |  |  | 1 | 34.83 | 34.83
-------
1048.6
General overhead |  |  |  | 16% | 167.78
-------
|  |  |  | TOTAL= | 1216.38
=======
SWITCHBOARD:
KWH/KVARH mtr,2.5A/120V/4W/ElectronicAMR 3-ph. |  |  | 1 | 322.11 | 322
Current trf - 600v,1500/5A,Window |  |  | 3 | 143.14 | 429
Test sw. 10-position |  |  | 1 | 47.4 | 47
-------
| Total materials: |  |  |  | 798
Stores overhead |  |  |  | 8% | 64
Small Tools Expense |  |  |  | 7.5% | 14
Meter installation |  |  | 1 | 83.03 | 83.03
C.T. installation |  |  | 3 | 62.58 | 187.74
Test sw. installation |  |  | 1 | 34.83 | 34.83
-------
1181.6
General overhead |  |  |  | 16% | 189.06
-------
|  |  |  | TOTAL= | 1370.66
=======
Source: PSE Cost of Metering

## MeterForecast
2011-08-01 |  |  |  | Electric |  |  |  |  | Gas
Date | Year | Month | YearMo | Customers | Meters | Customers AARG | Meters AARG |  | Customers | Meters | Customers AARG | Meters AARG
2003-06-01 | 2003 | 6 | 2003M06 | 992430 | 990782 |  |  |  | 632758 | 656000
2003-07-01 | 2003 | 7 | 2003M07 | 993927 | 992573 |  |  |  | 632963 | 657343
2003-08-01 | 2003 | 8 | 2003M08 | 995629 | 993662 |  |  |  | 633640 | 658925
2003-09-01 | 2003 | 9 | 2003M09 | 997548 | 995742 |  |  |  | 636278 | 661226
2003-10-01 | 2003 | 10 | 2003M10 | 999211 | 997603 |  |  |  | 639371 | 663316
2003-11-01 | 2003 | 11 | 2003M11 | 1000488 | 998954 |  |  |  | 642942 | 665278
2003-12-01 | 2003 | 12 | 2003M12 | 1001686 | 1000523 |  |  |  | 644629 | 667020
2004-01-01 | 2004 | 1 | 2004M01 | 1003575 | 1002258 |  |  |  | 654235 | 668582
2004-02-01 | 2004 | 2 | 2004M02 | 1004859 | 1004220 |  |  |  | 656018 | 670496
2004-03-01 | 2004 | 3 | 2004M03 | 1006686 | 1006027 |  |  |  | 657449 | 672641
2004-04-01 | 2004 | 4 | 2004M04 | 1008191 | 1007815 |  |  |  | 658772 | 674456
2004-05-01 | 2004 | 5 | 2004M05 | 1009620 | 1009619 |  |  |  | 660037 | 676158
2004-06-01 | 2004 | 6 | 2004M06 | 1011002 | 1011096 | 1.871% | 2.05% | 0.1461% | 661290 | 677886 | 4.509% | 3.336% | 0.2549%
2004-07-01 | 2004 | 7 | 2004M07 | 1012154 | 1013025 | 1.834% | 2.061% | 0.1904% | 662247 | 679546 | 4.626% | 3.378% | 0.2443%
2004-08-01 | 2004 | 8 | 2004M08 | 1013788 | 1015527 | 1.824% | 2.2% | 0.2464% | 663682 | 682105 | 4.741% | 3.518% | 0.3752%
2004-09-01 | 2004 | 9 | 2004M09 | 1015226 | 1016659 | 1.772% | 2.101% | 0.1113% | 665957 | 683150 | 4.664% | 3.316% | 0.153%
2004-10-01 | 2004 | 10 | 2004M10 | 1017678 | 1018449 | 1.848% | 2.09% | 0.1758% | 668325 | 685087 | 4.529% | 3.282% | 0.2827%
2004-11-01 | 2004 | 11 | 2004M11 | 1020114 | 1020060 | 1.962% | 2.113% | 0.1579% | 670935 | 687183 | 4.354% | 3.293% | 0.305%
2004-12-01 | 2004 | 12 | 2004M12 | 1022182 | 1021851 | 2.046% | 2.132% | 0.1753% | 672530 | 689132 | 4.328% | 3.315% | 0.2828%
2005-01-01 | 2005 | 1 | 2005M01 | 1023515 | 1024693 | 1.987% | 2.238% | 0.2774% | 675203 | 692496 | 3.205% | 3.577% | 0.4858%
2005-02-01 | 2005 | 2 | 2005M02 | 1024891 | 1025546 | 1.994% | 2.124% | 0.08318% | 677221 | 693510 | 3.232% | 3.432% | 0.1462%
2005-03-01 | 2005 | 3 | 2005M03 | 1026318 | 1026399 | 1.95% | 2.025% | 0.08311% | 678649 | 694524 | 3.225% | 3.253% | 0.146%
2005-04-01 | 2005 | 4 | 2005M04 | 1027723 | 1028113 | 1.937% | 2.014% | 0.1667% | 679930 | 696290 | 3.212% | 3.237% | 0.2536%
2005-05-01 | 2005 | 5 | 2005M05 | 1028859 | 1029862 | 1.906% | 2.005% | 0.1698% | 681102 | 697909 | 3.191% | 3.217% | 0.232%
2005-06-01 | 2005 | 6 | 2005M06 | 1030434 | 1031532 | 1.922% | 2.021% | 0.1619% | 682243 | 699820 | 3.169% | 3.236% | 0.2731%
2005-07-01 | 2005 | 7 | 2005M07 | 1031547 | 1032966 | 1.916% | 1.968% | 0.1388% | 682625 | 701227 | 3.077% | 3.191% | 0.2006%
2005-08-01 | 2005 | 8 | 2005M08 | 1032812 | 1034817 | 1.877% | 1.9% | 0.1789% | 683204 | 702962 | 2.941% | 3.058% | 0.2468%
2005-09-01 | 2005 | 9 | 2005M09 | 1035165 | 1036513 | 1.964% | 1.953% | 0.1636% | 684385 | 704664 | 2.767% | 3.149% | 0.2415%
2005-10-01 | 2005 | 10 | 2005M10 | 1037370 | 1038283 | 1.935% | 1.947% | 0.1705% | 687805 | 706295 | 2.915% | 3.096% | 0.2309%
2005-11-01 | 2005 | 11 | 2005M11 | 1039339 | 1040087 | 1.885% | 1.963% | 0.1734% | 691252 | 708170 | 3.028% | 3.054% | 0.2648%
2005-12-01 | 2005 | 12 | 2005M12 | 1040187 | 1041831 | 1.761% | 1.955% | 0.1674% | 694210 | 710155 | 3.224% | 3.051% | 0.2795%
2006-01-01 | 2006 | 1 | 2006M01 | 1040406 | 1043144 | 1.65% | 1.801% | 0.1259% | 696168 | 711761 | 3.105% | 2.782% | 0.2256%
2006-02-01 | 2006 | 2 | 2006M02 | 1041880 | 1044613 | 1.658% | 1.859% | 0.1406% | 698014 | 713333 | 3.07% | 2.858% | 0.2204%
2006-03-01 | 2006 | 3 | 2006M03 | 1043308 | 1046243 | 1.655% | 1.933% | 0.1558% | 699406 | 715034 | 3.059% | 2.953% | 0.2379%
2006-04-01 | 2006 | 4 | 2006M04 | 1045144 | 1048431 | 1.695% | 1.976% | 0.2087% | 700769 | 716969 | 3.065% | 2.97% | 0.2699%
2006-05-01 | 2006 | 5 | 2006M05 | 1046483 | 1050288 | 1.713% | 1.983% | 0.1768% | 701697 | 718853 | 3.024% | 3.001% | 0.2621%
2006-06-01 | 2006 | 6 | 2006M06 | 1047772 | 1052278 | 1.683% | 2.011% | 0.1891% | 702581 | 720500 | 2.981% | 2.955% | 0.2286%
2006-07-01 | 2006 | 7 | 2006M07 | 1048701 | 1053801 | 1.663% | 2.017% | 0.1445% | 703017 | 722046 | 2.987% | 2.969% | 0.2141%
2006-08-01 | 2006 | 8 | 2006M08 | 1050330 | 1052278 | 1.696% | 1.687% | -0.1447% | 703799 | 720500 | 3.014% | 2.495% | -0.2146%
2006-09-01 | 2006 | 9 | 2006M09 | 1051680 | 1056492 | 1.595% | 1.928% | 0.3989% | 706264 | 724985 | 3.197% | 2.884% | 0.6186%
2006-10-01 | 2006 | 10 | 2006M10 | 1053630 | 1058520 | 1.567% | 1.949% | 0.1916% | 709123 | 726961 | 3.099% | 2.926% | 0.2718%
2006-11-01 | 2006 | 11 | 2006M11 | 1054995 | 1059826 | 1.506% | 1.898% | 0.1232% | 711628 | 728538 | 2.948% | 2.876% | 0.2165%
2006-12-01 | 2006 | 12 | 2006M12 | 1056410 | 1060733 | 1.56% | 1.814% | 0.08551% | 713001 | 729636 | 2.707% | 2.743% | 0.1505%
2007-01-01 | 2007 | 1 | 2007M01 | 1058261 | 1061642 | 1.716% | 1.773% | 0.08562% | 714936 | 730940 | 2.696% | 2.695% | 0.1784%
2007-02-01 | 2007 | 2 | 2007M02 | 1059625 | 1061979 | 1.703% | 1.662% | 0.03173% | 716730 | 732453 | 2.681% | 2.68% | 0.2066%
2007-03-01 | 2007 | 3 | 2007M03 | 1060769 | 1061574 | 1.674% | 1.465% | -0.03815% | 717979 | 733762 | 2.656% | 2.619% | 0.1784%
2007-04-01 | 2007 | 4 | 2007M04 | 1061581 | 1066569 | 1.573% | 1.73% | 0.4683% | 719378 | 735240 | 2.656% | 2.548% | 0.201%
2007-05-01 | 2007 | 5 | 2007M05 | 1062430 | 1068183 | 1.524% | 1.704% | 0.1511% | 720062 | 736441 | 2.617% | 2.447% | 0.1631%
2007-06-01 | 2007 | 6 | 2007M06 | 1063463 | 1069774 | 1.498% | 1.663% | 0.1487% | 721113 | 738121 | 2.638% | 2.446% | 0.2276%
2007-07-01 | 2007 | 7 | 2007M07 | 1064619 | 1070861 | 1.518% | 1.619% | 0.1015% | 722013 | 739517 | 2.702% | 2.42% | 0.1888%
2007-08-01 | 2007 | 8 | 2007M08 | 1065367 | 1072469 | 1.432% | 1.919% | 0.1499% | 723273 | 741005 | 2.767% | 2.846% | 0.2008%
2007-09-01 | 2007 | 9 | 2007M09 | 1066224 | 1073766 | 1.383% | 1.635% | 0.1208% | 724567 | 742422 | 2.592% | 2.405% | 0.1909%
2007-10-01 | 2007 | 10 | 2007M10 | 1067095 | 1075463 | 1.278% | 1.601% | 0.1578% | 726556 | 743839 | 2.458% | 2.322% | 0.1905%
2007-11-01 | 2007 | 11 | 2007M11 | 1068424 | 1076696 | 1.273% | 1.592% | 0.1145% | 727923 | 745179 | 2.29% | 2.284% | 0.1798%
2007-12-01 | 2007 | 12 | 2007M12 | 1069365 | 1077853 | 1.226% | 1.614% | 0.1073% | 729499 | 746564 | 2.314% | 2.32% | 0.1855%
2008-01-01 | 2008 | 1 | 2008M01 | 1070283 | 1079094 | 1.136% | 1.644% | 0.115% | 731992 | 747889 | 2.386% | 2.319% | 0.1772%
2008-02-01 | 2008 | 2 | 2008M02 | 1071244 | 1080130 | 1.097% | 1.709% | 0.09591% | 733724 | 748895 | 2.371% | 2.245% | 0.1343%
2008-03-01 | 2008 | 3 | 2008M03 | 1071662 | 1081273 | 1.027% | 1.856% | 0.1057% | 734903 | 749886 | 2.357% | 2.197% | 0.1322%
2008-04-01 | 2008 | 4 | 2008M04 | 1072639 | 1082453 | 1.042% | 1.489% | 0.109% | 735817 | 751040 | 2.285% | 2.149% | 0.1537%
2008-05-01 | 2008 | 5 | 2008M05 | 1072583 | 1083333 | 0.9556% | 1.418% | 0.08123% | 736614 | 751947 | 2.299% | 2.106% | 0.1206%
2008-06-01 | 2008 | 6 | 2008M06 | 1072970 | 1084517 | 0.894% | 1.378% | 0.1092% | 737412 | 752813 | 2.26% | 1.99% | 0.115%
2008-07-01 | 2008 | 7 | 2008M07 | 1072622 | 1085743 | 0.7517% | 1.39% | 0.1129% | 738122 | 753984 | 2.231% | 1.956% | 0.1553%
2008-08-01 | 2008 | 8 | 2008M08 | 1072832 | 1086662 | 0.7007% | 1.323% | 0.08457% | 738753 | 755027 | 2.14% | 1.892% | 0.1381%
2008-09-01 | 2008 | 9 | 2008M09 | 1073319 | 1087459 | 0.6654% | 1.275% | 0.07329% | 739409 | 755941 | 2.048% | 1.821% | 0.1209%
2008-10-01 | 2008 | 10 | 2008M10 | 1074003 | 1088632 | 0.6474% | 1.224% | 0.1077% | 740878 | 757470 | 1.971% | 1.833% | 0.2019%
2008-11-01 | 2008 | 11 | 2008M11 | 1074284 | 1089751 | 0.5485% | 1.213% | 0.1027% | 742734 | 758823 | 2.035% | 1.831% | 0.1783%
2008-12-01 | 2008 | 12 | 2008M12 | 1075403 | 1090691 | 0.5646% | 1.191% | 0.08618% | 743836 | 759913 | 1.965% | 1.788% | 0.1434%
2009-01-01 | 2009 | 1 | 2009M01 | 1076216 | 1091359 | 0.5543% | 1.137% | 0.06121% | 745311 | 760693 | 1.82% | 1.712% | 0.1025%
2009-02-01 | 2009 | 2 | 2009M02 | 1076921 | 1092052 | 0.5299% | 1.104% | 0.06346% | 746370 | 761408 | 1.724% | 1.671% | 0.0939%
2009-03-01 | 2009 | 3 | 2009M03 | 1077587 | 1093024 | 0.5529% | 1.087% | 0.08893% | 746878 | 762227 | 1.629% | 1.646% | 0.1074%
2009-04-01 | 2009 | 4 | 2009M04 | 1077925 | 1094302 | 0.4928% | 1.095% | 0.1168% | 747048 | 762746 | 1.526% | 1.559% | 0.06804%
2009-05-01 | 2009 | 5 | 2009M05 | 1078185 | 1094577 | 0.5223% | 1.038% | 0.02512% | 746902 | 763262 | 1.397% | 1.505% | 0.0676%
2009-06-01 | 2009 | 6 | 2009M06 | 1078310 | 1095370 | 0.4977% | 1.001% | 0.0724% | 746680 | 763879 | 1.257% | 1.47% | 0.08077%
2009-07-01 | 2009 | 7 | 2009M07 | 1078406 | 1095965 | 0.5392% | 0.9415% | 0.05429% | 745645 | 764429 | 1.019% | 1.385% | 0.07195%
2009-08-01 | 2009 | 8 | 2009M08 | 1078630 | 1096704 | 0.5404% | 0.9241% | 0.06738% | 745282 | 765028 | 0.8838% | 1.325% | 0.0783%
2009-09-01 | 2009 | 9 | 2009M09 | 1079057 | 1097431 | 0.5346% | 0.917% | 0.06625% | 745452 | 765702 | 0.8173% | 1.291% | 0.08802%
2009-10-01 | 2009 | 10 | 2009M10 | 1079657 | 1098248 | 0.5264% | 0.8833% | 0.07439% | 746424 | 766522 | 0.7486% | 1.195% | 0.107%
2009-11-01 | 2009 | 11 | 2009M11 | 1080238 | 1098688 | 0.5542% | 0.8201% | 0.04005% | 747534 | 767371 | 0.6463% | 1.126% | 0.1106%
2009-12-01 | 2009 | 12 | 2009M12 | 1080675 | 1099399 | 0.4902% | 0.7984% | 0.06467% | 748853 | 768075 | 0.6745% | 1.074% | 0.09166%
2010-01-01 | 2010 | 1 | 2010M01 | 1081605 | 1099864 | 0.5007% | 0.7793% | 0.04228% | 750252 | 768947 | 0.6629% | 1.085% | 0.1134%
2010-02-01 | 2010 | 2 | 2010M02 | 1082130 | 1100655 | 0.4837% | 0.7878% | 0.07187% | 751020 | 769510 | 0.623% | 1.064% | 0.07316%
2010-03-01 | 2010 | 3 | 2010M03 | 1082384 | 1101608 | 0.4452% | 0.7853% | 0.08651% | 751395 | 770204 | 0.6048% | 1.047% | 0.09011%
2010-04-01 | 2010 | 4 | 2010M04 | 1082603 | 1102180 | 0.434% | 0.7199% | 0.0519% | 751659 | 771049 | 0.6172% | 1.089% | 0.1096%
2010-05-01 | 2010 | 5 | 2010M05 | 1082623 | 1102800 | 0.4116% | 0.7512% | 0.05622% | 751183 | 771706 | 0.5732% | 1.106% | 0.08514%
2010-06-01 | 2010 | 6 | 2010M06 | 1082944 | 1103467 | 0.4297% | 0.7392% | 0.06045% | 750496 | 772393 | 0.5111% | 1.115% | 0.08894%
2010-07-01 | 2010 | 7 | 2010M07 | 1084831.3556 | 1104199 | 0.5958% | 0.7513% | 0.06629% | 749722 | 773000 | 0.5468% | 1.121% | 0.07853%
2010-08-01 | 2010 | 8 | 2010M08 | 1085512.8922 | 1104865 | 0.6381% | 0.7441% | 0.06028% | 748770 | 773611 | 0.468% | 1.122% | 0.07898%
2010-09-01 | 2010 | 9 | 2010M09 | 1086396.1787 | 1105390 | 0.6801% | 0.7252% | 0.04749% | 749031 | 774200 | 0.4801% | 1.11% | 0.07608%
2010-10-01 | 2010 | 10 | 2010M10 | 1087571.8755 | 1105990 | 0.7331% | 0.7049% | 0.05425% | 750443 | 774859 | 0.5384% | 1.088% | 0.08505%
2010-11-01 | 2010 | 11 | 2010M11 | 1088682.8168 | 1106473 | 0.7818% | 0.7086% | 0.04365% | 752134 | 775412 | 0.6154% | 1.048% | 0.07132%
2010-12-01 | 2010 | 12 | 2010M12 | 1089631.7508 | 1106992 | 0.8288% | 0.6907% | 0.04688% | 753636 | 775936 | 0.6387% | 1.023% | 0.06753%
2011-01-01 | 2011 | 1 | 2011M01 | 1090401.745 | 1107693 | 0.8133% | 0.7118% | 0.06328% | 755120 | 776618 | 0.6488% | 0.9976% | 0.08782%
2011-02-01 | 2011 | 2 | 2011M02 | 1091131.6544 | 1108206 | 0.8318% | 0.686% | 0.04629% | 756055 | 777219 | 0.6704% | 1.002% | 0.07733%
2011-03-01 | 2011 | 3 | 2011M03 | 1091840.1862 | 1108764 | 0.8736% | 0.6496% | 0.05033% | 756654 | 777934 | 0.6999% | 1.004% | 0.09191%
2011-04-01 | 2011 | 4 | 2011M04 | 1092645.7705 | 1109455 | 0.9277% | 0.6601% | 0.06228% | 756637 | 778432 | 0.6623% | 0.9575% | 0.06397%
2011-05-01 | 2011 | 5 | 2011M05 | 1093373.457 | 1109915 | 0.993% | 0.6452% | 0.04144% | 756210 | 779035 | 0.6692% | 0.9497% | 0.0774%
2011-06-01 | 2011 | 6 | 2011M06 | 1094175.1814 | 1110587 | 1.037% | 0.6452% | 0.06051% | 755987 | 779779 | 0.7316% | 0.9562% | 0.09541%
2011-07-01 | 2011 | 7 | 2011M07 | 1094851.1631 | 1111190 | 0.9236% | 0.6331% | 0.05427% | 756198.7582 | 780302 | 0.8639% | 0.9446% | 0.06703% | 1891492
2011-08-01 | 2011 | 8 | 2011M08 | 1095802.8997 | 1111926.5868 | 0.9479% | 0.6391% | 0.06624% | 756226.6141 | 780918.5628 | 0.9958% | 0.9446% | 0.07895% | 1892845.1495
2011-09-01 | 2011 | 9 | 2011M09 | 1096988.7399 | 1112714.1352 | 0.975% | 0.6626% | 0.07078% | 757196.8083 | 781661.9771 | 1.09% | 0.9638% | 0.09511% | 1894376.1124
2011-10-01 | 2011 | 10 | 2011M10 | 1098526.6097 | 1113578.0874 | 1.007% | 0.6861% | 0.07758% | 759326.4624 | 782561.1736 | 1.184% | 0.994% | 0.1149% | 1896139.261
2011-11-01 | 2011 | 11 | 2011M11 | 1099996.4786 | 1114427.5506 | 1.039% | 0.7189% | 0.07622% | 761602.9463 | 783480.2164 | 1.259% | 1.041% | 0.1173% | 1897907.767
2011-12-01 | 2011 | 12 | 2011M12 | 1101357.8273 | 1115253.7994 | 1.076% | 0.7463% | 0.07409% | 763491.5479 | 784347.7059 | 1.308% | 1.084% | 0.1106% | 1899601.5053
2012-01-01 | 2012 | 1 | 2012M01 | 1102701.5999 | 1116076.5028 | 1.128% | 0.7568% | 0.07371% | 765264.5849 | 785200.1387 | 1.343% | 1.105% | 0.1086% | 1901276.6415
2012-02-01 | 2012 | 2 | 2012M02 | 1103993.8627 | 1116888.3446 | 1.179% | 0.7835% | 0.07269% | 766646.6355 | 786000.9186 | 1.401% | 1.13% | 0.1019% | 1902889.2632
2012-03-01 | 2012 | 3 | 2012M03 | 1105259.7056 | 1117694.7517 | 1.229% | 0.8055% | 0.07215% | 767711.5212 | 786759.9918 | 1.461% | 1.135% | 0.09648% | 1904454.7435
2012-04-01 | 2012 | 4 | 2012M04 | 1106614.4765 | 1118520.6005 | 1.278% | 0.8171% | 0.07383% | 768552.8618 | 787489.8673 | 1.575% | 1.164% | 0.09268% | 1906010.4679
2012-05-01 | 2012 | 5 | 2012M05 | 1107882.8967 | 1119328.0941 | 1.327% | 0.8481% | 0.07214% | 768872.9098 | 788150.9418 | 1.675% | 1.17% | 0.08388% | 1907479.0358
2012-06-01 | 2012 | 6 | 2012M06 | 1109218.7715 | 1120150.3871 | 1.375% | 0.8611% | 0.07341% | 769223.7195 | 788816.649 | 1.751% | 1.159% | 0.08439% | 1908967.0361
2012-07-01 | 2012 | 7 | 2012M07 | 1110412.2573 | 1120942.2805 | 1.421% | 0.8776% | 0.07065% | 768977.2413 | 789403.3188 | 1.69% | 1.166% | 0.07432% | 1910345.5992
2012-08-01 | 2012 | 8 | 2012M08 | 1111866.145 | 1121790.4999 | 1.466% | 0.8871% | 0.07561% | 769071.5059 | 790035.8674 | 1.699% | 1.168% | 0.08007% | 1911826.3673
2012-09-01 | 2012 | 9 | 2012M09 | 1113532.2903 | 1122684.6001 | 1.508% | 0.896% | 0.07964% | 770087.1465 | 790791.8231 | 1.702% | 1.168% | 0.09559% | 1913476.4232
2012-10-01 | 2012 | 10 | 2012M10 | 1115517.5373 | 1123647.4419 | 1.547% | 0.9042% | 0.08569% | 772290.9896 | 791706.5712 | 1.707% | 1.169% | 0.1155% | 1915354.0131
2012-11-01 | 2012 | 11 | 2012M11 | 1117394.9516 | 1124587.2028 | 1.582% | 0.9116% | 0.08356% | 774645.6352 | 792641.5744 | 1.713% | 1.169% | 0.118% | 1917228.7773
2012-12-01 | 2012 | 12 | 2012M12 | 1119120.7947 | 1125494.5607 | 1.613% | 0.9182% | 0.08062% | 776610.5758 | 793525.0442 | 1.718% | 1.17% | 0.1113% | 1919019.6049
2013-01-01 | 2013 | 1 | 2013M01 | 1120876.2811 | 1126408.4332 | 1.648% | 0.9257% | 0.08113% | 778554.2621 | 794406.0229 | 1.737% | 1.172% | 0.1109% | 1920814.456
2013-02-01 | 2013 | 2 | 2013M02 | 1122532.5267 | 1127301.2015 | 1.679% | 0.9323% | 0.0792% | 780111.8436 | 795236.2475 | 1.756% | 1.175% | 0.1044% | 1922537.449
2013-03-01 | 2013 | 3 | 2013M03 | 1124117.9792 | 1128178.9998 | 1.706% | 0.938% | 0.07781% | 781362.949 | 796026.3984 | 1.778% | 1.178% | 0.09926% | 1924205.3981
2013-04-01 | 2013 | 4 | 2013M04 | 1125752.9323 | 1129067.5919 | 1.729% | 0.9429% | 0.0787% | 782422.4916 | 796791.7446 | 1.805% | 1.181% | 0.09605% | 1925859.3365
2013-05-01 | 2013 | 5 | 2013M05 | 1127261.0558 | 1129929.2609 | 1.749% | 0.9471% | 0.07626% | 782978.1014 | 797491.0175 | 1.835% | 1.185% | 0.08768% | 1927420.2784
2013-06-01 | 2013 | 6 | 2013M06 | 1128800.8289 | 1130797.9185 | 1.765% | 0.9505% | 0.07682% | 783599.2424 | 798199.5187 | 1.869% | 1.189% | 0.08876% | 1928997.4372
2013-07-01 | 2013 | 7 | 2013M07 | 1130162.1901 | 1131628.6939 | 1.779% | 0.9533% | 0.07341% | 783661.2062 | 798834.6038 | 1.91% | 1.195% | 0.0795% | 1930463.2977
2013-08-01 | 2013 | 8 | 2013M08 | 1131758.2465 | 1132509.8251 | 1.789% | 0.9556% | 0.0778% | 784092.089 | 799519.0424 | 1.953% | 1.2% | 0.08561% | 1932028.8675
2013-09-01 | 2013 | 9 | 2013M09 | 1133544.0543 | 1133544.0543 | 1.797% | 0.9673% | 0.09124% | 785461.9559 | 800328.3157 | 1.997% | 1.206% | 0.1011% | 1933872.3701
2013-10-01 | 2013 | 10 | 2013M10 | 1135634.7572 | 1135634.7572 | 1.803% | 1.067% | 0.1841% | 788021.5103 | 801295.2532 | 2.037% | 1.211% | 0.1207% | 1936930.0104
2013-11-01 | 2013 | 11 | 2013M11 | 1137598.3718 | 1137598.3718 | 1.808% | 1.157% | 0.1726% | 790706.4636 | 802278.7798 | 2.073% | 1.216% | 0.1226% | 1939877.1516
2013-12-01 | 2013 | 12 | 2013M12 | 1139393.21 | 1139393.21 | 1.811% | 1.235% | 0.1575% | 792962.2712 | 803205.889 | 2.106% | 1.22% | 0.1154% | 1942599.099
2014-01-01 | 2014 | 1 | 2014M01 | 1141107.0114 | 1141107.0114 | 1.805% | 1.305% | 0.1502% | 795181.8188 | 804852.3228 | 2.136% | 1.315% | 0.2046% | 1945959.3343
2014-02-01 | 2014 | 2 | 2014M02 | 1142709.1157 | 1142709.1157 | 1.797% | 1.367% | 0.1402% | 796979.273 | 806445.8775 | 2.162% | 1.41% | 0.1976% | 1949154.9932
2014-03-01 | 2014 | 3 | 2014M03 | 1144231.0145 | 1144231.0145 | 1.789% | 1.423% | 0.133% | 798444.0594 | 807998.3548 | 2.186% | 1.504% | 0.1921% | 1952229.3693
2014-04-01 | 2014 | 4 | 2014M04 | 1145802.124 | 1145802.124 | 1.781% | 1.482% | 0.1371% | 799688.7207 | 809524.5403 | 2.207% | 1.598% | 0.1885% | 1955326.6643
2014-05-01 | 2014 | 5 | 2014M05 | 1147243.9067 | 1147243.9067 | 1.773% | 1.532% | 0.1257% | 800414.6171 | 810985.1323 | 2.227% | 1.692% | 0.1801% | 1958229.039
2014-06-01 | 2014 | 6 | 2014M06 | 1148719.4684 | 1148719.4684 | 1.765% | 1.585% | 0.1285% | 801211.4144 | 812457.6074 | 2.248% | 1.786% | 0.1812% | 1961177.0758
2014-07-01 | 2014 | 7 | 2014M07 | 1150020.7591 | 1150020.7591 | 1.757% | 1.625% | 0.1132% | 801436.0261 | 813857.2372 | 2.268% | 1.881% | 0.172% | 1963877.9963
2014-08-01 | 2014 | 8 | 2014M08 | 1151567.6123 | 1151567.6123 | 1.75% | 1.683% | 0.1343% | 802041.2704 | 815309.5149 | 2.289% | 1.975% | 0.1781% | 1966877.1273
2014-09-01 | 2014 | 9 | 2014M09 | 1153314.2881 | 1153314.2881 | 1.744% | 1.744% | 0.1514% | 803600.173 | 816890.2493 | 2.309% | 2.069% | 0.1935% | 1970204.5374
2014-10-01 | 2014 | 10 | 2014M10 | 1155380.7172 | 1155380.7172 | 1.739% | 1.739% | 0.1789% | 806347.3033 | 818630.3657 | 2.326% | 2.163% | 0.2126% | 1974011.0829
2014-11-01 | 2014 | 11 | 2014M11 | 1157326.9944 | 1157326.9944 | 1.734% | 1.734% | 0.1682% | 809206.0951 | 820387.6508 | 2.34% | 2.257% | 0.2142% | 1977714.6452
2014-12-01 | 2014 | 12 | 2014M12 | 1159110.8776 | 1159110.8776 | 1.731% | 1.731% | 0.1539% | 811612.1455 | 822087.8525 | 2.352% | 2.351% | 0.2068% | 1981198.7301
2015-01-01 | 2015 | 1 | 2015M01 | 1160816.6856 | 1160816.6856 | 1.727% | 1.727% | 0.1469% | 813958.7111 | 823782.822 | 2.361% | 2.352% | 0.2058% | 1984599.5076
2015-02-01 | 2015 | 2 | 2015M02 | 1162415.1315 | 1162415.1315 | 1.724% | 1.724% | 0.1375% | 815864.4026 | 825422.5002 | 2.37% | 2.353% | 0.1986% | 1987837.6317
2015-03-01 | 2015 | 3 | 2015M03 | 1163937.5833 | 1163937.5833 | 1.722% | 1.722% | 0.1308% | 817423.5803 | 827019.3488 | 2.377% | 2.354% | 0.1931% | 1990956.932
2015-04-01 | 2015 | 4 | 2015M04 | 1165514.5614 | 1165514.5614 | 1.72% | 1.72% | 0.1353% | 818749.4779 | 828588.2484 | 2.384% | 2.355% | 0.1893% | 1994102.8098
2015-05-01 | 2015 | 5 | 2015M05 | 1166964.2919 | 1166964.2919 | 1.719% | 1.719% | 0.1242% | 819543.7545 | 830089.9533 | 2.39% | 2.356% | 0.1809% | 1997054.2452
2015-06-01 | 2015 | 6 | 2015M06 | 1168453.113 | 1168453.113 | 1.718% | 1.718% | 0.1274% | 820413.1277 | 831604.1615 | 2.397% | 2.357% | 0.1821% | 2000057.2745
2015-07-01 | 2015 | 7 | 2015M07 | 1169769.5669 | 1169769.5669 | 1.717% | 1.717% | 0.1125% | 820698.4447 | 833044.0659 | 2.403% | 2.358% | 0.1728% | 2002813.6328
2015-08-01 | 2015 | 8 | 2015M08 | 1171340.3614 | 1171340.3614 | 1.717% | 1.717% | 0.1341% | 821379.0096 | 834538.5983 | 2.411% | 2.359% | 0.1791% | 2005878.9596
2015-09-01 | 2015 | 9 | 2015M09 | 1173118.9127 | 1173118.9127 | 1.717% | 1.717% | 0.1516% | 823041.4597 | 836165.3148 | 2.419% | 2.36% | 0.1945% | 2009284.2275
2015-10-01 | 2015 | 10 | 2015M10 | 1175225.218 | 1175225.218 | 1.718% | 1.718% | 0.1792% | 825925.383 | 837955.755 | 2.428% | 2.361% | 0.2137% | 2013180.973
2015-11-01 | 2015 | 11 | 2015M11 | 1177211.4269 | 1177211.4269 | 1.718% | 1.718% | 0.1687% | 828929.051 | 839764.4503 | 2.437% | 2.362% | 0.2154% | 2016975.8772
2015-12-01 | 2015 | 12 | 2015M12 | 1179034.1751 | 1179034.1751 | 1.719% | 1.719% | 0.1546% | 831476.6204 | 841515.6993 | 2.448% | 2.363% | 0.2081% | 2020549.8744
2016-01-01 | 2016 | 1 | 2016M01 | 1180780.485 | 1180780.485 | 1.72% | 1.72% | 0.1479% | 833969.016 | 843262.3298 | 2.458% | 2.365% | 0.2071% | 2024042.8149
2016-02-01 | 2016 | 2 | 2016M02 | 1182420.6099 | 1182420.6099 | 1.721% | 1.721% | 0.1387% | 836009.8269 | 844952.3636 | 2.469% | 2.366% | 0.2% | 2027372.9736
2016-03-01 | 2016 | 3 | 2016M03 | 1183985.7612 | 1183985.7612 | 1.722% | 1.722% | 0.1322% | 837687.7468 | 846597.5235 | 2.479% | 2.367% | 0.1943% | 2030583.2847
2016-04-01 | 2016 | 4 | 2016M04 | 1185606.8454 | 1185606.8454 | 1.724% | 1.724% | 0.1367% | 839113.3256 | 848212.3325 | 2.487% | 2.368% | 0.1904% | 2033819.1778
2016-05-01 | 2016 | 5 | 2016M05 | 1187098.4274 | 1187098.4274 | 1.725% | 1.725% | 0.1256% | 839971.1036 | 849755.3492 | 2.493% | 2.369% | 0.1816% | 2036853.7766
2016-06-01 | 2016 | 6 | 2016M06 | 1188629.0816 | 1188629.0816 | 1.727% | 1.727% | 0.1288% | 840876.6864 | 851307.3412 | 2.494% | 2.369% | 0.1823% | 2039936.4228
2016-07-01 | 2016 | 7 | 2016M07 | 1189982.1085 | 1189982.1085 | 1.728% | 1.728% | 0.1137% | 841151.1839 | 852779.0004 | 2.492% | 2.369% | 0.1726% | 2042761.1089
2016-08-01 | 2016 | 8 | 2016M08 | 1191591.3168 | 1191591.3168 | 1.729% | 1.729% | 0.135% | 841806.3129 | 854303.3526 | 2.487% | 2.368% | 0.1784% | 2045894.6694
2016-09-01 | 2016 | 9 | 2016M09 | 1193409.6231 | 1193409.6231 | 1.73% | 1.73% | 0.1524% | 843456.6051 | 855961.5464 | 2.48% | 2.368% | 0.1937% | 2049371.1695
2016-10-01 | 2016 | 10 | 2016M10 | 1195558.7152 | 1195558.7152 | 1.73% | 1.73% | 0.1798% | 846369.534 | 857788.7795 | 2.475% | 2.367% | 0.213% | 2053347.4947
2016-11-01 | 2016 | 11 | 2016M11 | 1197583.6098 | 1197583.6098 | 1.731% | 1.731% | 0.1691% | 849408.1463 | 859635.1061 | 2.471% | 2.366% | 0.2148% | 2057218.7159
2016-12-01 | 2016 | 12 | 2016M12 | 1199440.6487 | 1199440.6487 | 1.731% | 1.731% | 0.1548% | 851983.3911 | 861423.1646 | 2.466% | 2.366% | 0.2076% | 2060863.8133
2017-01-01 | 2017 | 1 | 2017M01 | 1201218.5481 | 1201218.5481 | 1.731% | 1.731% | 0.148% | 854511.7616 | 863207.7709 | 2.463% | 2.365% | 0.2067% | 2064426.319
2017-02-01 | 2017 | 2 | 2017M02 | 1202887.347 | 1202887.347 | 1.731% | 1.731% | 0.1387% | 856579.144 | 864934.6718 | 2.46% | 2.365% | 0.1997% | 2067822.0188
2017-03-01 | 2017 | 3 | 2017M03 | 1204479.0764 | 1204479.0764 | 1.731% | 1.731% | 0.1322% | 858275.9229 | 866615.7985 | 2.458% | 2.365% | 0.194% | 2071094.8749
2017-04-01 | 2017 | 4 | 2017M04 | 1206127.1343 | 1206127.1343 | 1.731% | 1.731% | 0.1366% | 859721.8636 | 868266.8664 | 2.456% | 2.364% | 0.1902% | 2074394.0007
2017-05-01 | 2017 | 5 | 2017M05 | 1207642.5837 | 1207642.5837 | 1.731% | 1.731% | 0.1255% | 860586.0882 | 869844.4465 | 2.454% | 2.364% | 0.1814% | 2077487.0302
2017-06-01 | 2017 | 6 | 2017M06 | 1209196.5809 | 1209196.5809 | 1.73% | 1.73% | 0.1285% | 861499.2184 | 871431.2016 | 2.453% | 2.364% | 0.1821% | 2080627.7826
2017-07-01 | 2017 | 7 | 2017M07 | 1210568.3255 | 1210568.3255 | 1.73% | 1.73% | 0.1133% | 861768.7749 | 872936.114 | 2.451% | 2.364% | 0.1724% | 2083504.4395
2017-08-01 | 2017 | 8 | 2017M08 | 1212198.9978 | 1212198.9978 | 1.729% | 1.729% | 0.1345% | 862427.747 | 874494.8892 | 2.45% | 2.364% | 0.1782% | 2086693.8869
2017-09-01 | 2017 | 9 | 2017M09 | 1214040.7633 | 1214040.7633 | 1.729% | 1.729% | 0.1517% | 864105.3151 | 876190.5434 | 2.448% | 2.363% | 0.1935% | 2090231.3067
2017-10-01 | 2017 | 10 | 2017M10 | 1216217.2272 | 1216217.2272 | 1.728% | 1.728% | 0.179% | 867078.7964 | 878059.545 | 2.447% | 2.363% | 0.2129% | 2094276.7722
2017-11-01 | 2017 | 11 | 2017M11 | 1218265.5679 | 1218265.5679 | 1.727% | 1.727% | 0.1681% | 870179.3263 | 879947.8707 | 2.445% | 2.363% | 0.2146% | 2098213.4386
2017-12-01 | 2017 | 12 | 2017M12 | 1220141.4144 | 1220141.4144 | 1.726% | 1.726% | 0.1537% | 872805.209 | 881776.5621 | 2.444% | 2.363% | 0.2074% | 2101917.9766
2018-01-01 | 2018 | 1 | 2018M01 | 1222042.4182 | 1222042.4182 | 1.734% | 1.734% | 0.1556% | 875384.9094 | 883601.9636 | 2.443% | 2.363% | 0.2066% | 2105644.3818
2018-02-01 | 2018 | 2 | 2018M02 | 1223831.5333 | 1223831.5333 | 1.741% | 1.741% | 0.1462% | 877492.0757 | 885368.2606 | 2.441% | 2.362% | 0.1995% | 2109199.7939
2018-03-01 | 2018 | 3 | 2018M03 | 1225541.8015 | 1225541.8015 | 1.749% | 1.749% | 0.1396% | 879219.4394 | 887087.6828 | 2.44% | 2.362% | 0.1938% | 2112629.4843
2018-04-01 | 2018 | 4 | 2018M04 | 1227309.4815 | 1227309.4815 | 1.756% | 1.756% | 0.144% | 880690.1405 | 888776.3747 | 2.439% | 2.362% | 0.19% | 2116085.8562
2018-05-01 | 2018 | 5 | 2018M05 | 1228942.3464 | 1228942.3464 | 1.764% | 1.764% | 0.1329% | 881564.5295 | 890389.7881 | 2.438% | 2.362% | 0.1812% | 2119332.1345
2018-06-01 | 2018 | 6 | 2018M06 | 1230614.7227 | 1230614.7227 | 1.771% | 1.771% | 0.1359% | 882488.9767 | 892012.5858 | 2.436% | 2.362% | 0.1819% | 2122627.3085
2018-07-01 | 2018 | 7 | 2018M07 | 1232102.2844 | 1232102.2844 | 1.779% | 1.779% | 0.1207% | 882751.7915 | 893551.292 | 2.435% | 2.362% | 0.1722% | 2125653.5763
2018-08-01 | 2018 | 8 | 2018M08 | 1233854.1136 | 1233854.1136 | 1.786% | 1.786% | 0.142% | 883412.956 | 895145.0566 | 2.433% | 2.361% | 0.178% | 2128999.1703
2018-09-01 | 2018 | 9 | 2018M09 | 1235821.8363 | 1235821.8363 | 1.794% | 1.794% | 0.1592% | 885116.3018 | 896878.7729 | 2.432% | 2.361% | 0.1933% | 2132700.6092
2018-10-01 | 2018 | 10 | 2018M10 | 1238131.5951 | 1238131.5951 | 1.802% | 1.802% | 0.1866% | 888144.8494 | 898789.6402 | 2.43% | 2.361% | 0.2126% | 2136921.2352
2018-11-01 | 2018 | 11 | 2018M11 | 1240312.4912 | 1240312.4912 | 1.81% | 1.81% | 0.1758% | 891300.8794 | 900719.9459 | 2.427% | 2.361% | 0.2143% | 2141032.4371
2018-12-01 | 2018 | 12 | 2018M12 | 1242319.4495 | 1242319.4495 | 1.818% | 1.818% | 0.1615% | 893969.8149 | 902589.0941 | 2.425% | 2.36% | 0.2071% | 2144908.5436
2019-01-01 | 2019 | 1 | 2019M01 | 1244244.0976 | 1244244.0976 | 1.817% | 1.817% | 0.1547% | 896589.5039 | 904454.625 | 2.422% | 2.36% | 0.2063% | 2148698.7225
2019-02-01 | 2019 | 2 | 2019M02 | 1246055.6174 | 1246055.6174 | 1.816% | 1.816% | 0.1454% | 898723.8441 | 906259.4811 | 2.42% | 2.36% | 0.1992%
2019-03-01 | 2019 | 3 | 2019M03 | 1247787.1977 | 1247787.1977 | 1.815% | 1.815% | 0.1388% | 900468.2804 | 908016.2384 | 2.417% | 2.359% | 0.1935%
2019-04-01 | 2019 | 4 | 2019M04 | 1249577.0014 | 1249577.0014 | 1.814% | 1.814% | 0.1432% | 901950.0926 | 909741.5713 | 2.414% | 2.359% | 0.1897%
2019-05-01 | 2019 | 5 | 2019M05 | 1251229.3019 | 1251229.3019 | 1.814% | 1.814% | 0.1321% | 902821.0105 | 911389.8219 | 2.411% | 2.359% | 0.1809%
2019-06-01 | 2019 | 6 | 2019M06 | 1252921.4906 | 1252921.4906 | 1.813% | 1.813% | 0.1351% | 903743.9884 | 913047.7771 | 2.409% | 2.358% | 0.1816%
2019-07-01 | 2019 | 7 | 2019M07 | 1254424.9452 | 1254424.9452 | 1.812% | 1.812% | 0.1199% | 903990.2085 | 914619.7574 | 2.406% | 2.358% | 0.1719%
2019-08-01 | 2019 | 8 | 2019M08 | 1256196.7092 | 1256196.7092 | 1.811% | 1.811% | 0.141% | 904645.7355 | 916248.2674 | 2.403% | 2.358% | 0.1777%
2019-09-01 | 2019 | 9 | 2019M09 | 1258187.2956 | 1258187.2956 | 1.81% | 1.81% | 0.1582% | 906369.5383 | 918020.1629 | 2.401% | 2.357% | 0.193%
2019-10-01 | 2019 | 10 | 2019M10 | 1260524.4195 | 1260524.4195 | 1.809% | 1.809% | 0.1854% | 909452.1094 | 919973.618 | 2.399% | 2.357% | 0.2123%
2019-11-01 | 2019 | 11 | 2019M11 | 1262728.5104 | 1262728.5104 | 1.807% | 1.807% | 0.1745% | 912665.5343 | 921947.0172 | 2.397% | 2.357% | 0.214%
2019-12-01 | 2019 | 12 | 2019M12 | 1264753.5548 | 1264753.5548 | 1.806% | 1.806% | 0.1601% | 915382.5308 | 923858.1301 | 2.395% | 2.356% | 0.2069%
2020-01-01 | 2020 | 1 | 2020M01 | 1266691.8291 | 1266691.8291 | 1.804% | 1.804% | 0.153% | 918050.8064 | 925765.7672 | 2.394% | 2.356% | 0.2061%
2020-02-01 | 2020 | 2 | 2020M02 | 1268513.667 | 1268513.667 | 1.802% | 1.802% | 0.1436% | 920223.3214 | 927611.4601 | 2.392% | 2.356% | 0.199%
2020-03-01 | 2020 | 3 | 2020M03 | 1270253.3221 | 1270253.3221 | 1.8% | 1.8% | 0.137% | 921997.0867 | 929407.9844 | 2.391% | 2.356% | 0.1933%
2020-04-01 | 2020 | 4 | 2020M04 | 1272051.6026 | 1272051.6026 | 1.799% | 1.799% | 0.1414% | 923502.9412 | 931172.4736 | 2.39% | 2.356% | 0.1895%
2020-05-01 | 2020 | 5 | 2020M05 | 1273709.4593 | 1273709.4593 | 1.797% | 1.797% | 0.1302% | 924382.8021 | 932857.9973 | 2.388% | 2.356% | 0.1807%
2020-06-01 | 2020 | 6 | 2020M06 | 1275407.6477 | 1275407.6477 | 1.795% | 1.795% | 0.1331% | 925316.0796 | 934553.4665 | 2.387% | 2.355% | 0.1814%
2020-07-01 | 2020 | 7 | 2020M07 | 1276913.8552 | 1276913.8552 | 1.793% | 1.793% | 0.118% | 925555.6909 | 936160.8331 | 2.386% | 2.355% | 0.1717%
2020-08-01 | 2020 | 8 | 2020M08 | 1278693.4292 | 1278693.4292 | 1.791% | 1.791% | 0.1392% | 926214.1957 | 937826.0335 | 2.384% | 2.355% | 0.1776%
2020-09-01 | 2020 | 9 | 2020M09 | 1280696.3405 | 1280696.3405 | 1.789% | 1.789% | 0.1564% | 927965.4902 | 939637.8686 | 2.383% | 2.355% | 0.1928%
2020-10-01 | 2020 | 10 | 2020M10 | 1283053.3566 | 1283053.3566 | 1.787% | 1.787% | 0.1837% | 931106.9369 | 941635.4106 | 2.381% | 2.355% | 0.2121%
2020-11-01 | 2020 | 11 | 2020M11 | 1285276.5722 | 1285276.5722 | 1.786% | 1.786% | 0.173% | 934379.7565 | 943653.031 | 2.379% | 2.354% | 0.2138%
2020-12-01 | 2020 | 12 | 2020M12 | 1287319.3147 | 1287319.3147 | 1.784% | 1.784% | 0.1587% | 937143.2266 | 945606.7583 | 2.377% | 2.354% | 0.2066%
2021-01-01 | 2021 | 1 | 2021M01 | 1289276.678 | 1289276.678 | 1.783% | 1.783% | 0.1518% | 939853.5123 | 947556.4995 | 2.375% | 2.354% | 0.2058%
2021-02-01 | 2021 | 2 | 2021M02 | 1291116.7798 | 1291116.7798 | 1.782% | 1.782% | 0.1425% | 942054.6547 | 949442.6312 | 2.372% | 2.353% | 0.1987%
2021-03-01 | 2021 | 3 | 2021M03 | 1292873.9396 | 1292873.9396 | 1.781% | 1.781% | 0.1359% | 943846.824 | 951278.3383 | 2.37% | 2.353% | 0.193%
2021-04-01 | 2021 | 4 | 2021M04 | 1294690.6518 | 1294690.6518 | 1.78% | 1.78% | 0.1403% | 945364.3134 | 953081.2005 | 2.367% | 2.353% | 0.1892%
2021-05-01 | 2021 | 5 | 2021M05 | 1296363.9835 | 1296363.9835 | 1.779% | 1.779% | 0.1291% | 946241.1185 | 954803.2525 | 2.365% | 2.352% | 0.1804%
2021-06-01 | 2021 | 6 | 2021M06 | 1298077.5812 | 1298077.5812 | 1.777% | 1.777% | 0.132% | 947172.5038 | 956535.4657 | 2.362% | 2.352% | 0.1811%
2021-07-01 | 2021 | 7 | 2021M07 | 1299594.8927 | 1299594.8927 | 1.776% | 1.776% | 0.1168% | 947394.446 | 958177.5766 | 2.36% | 2.352% | 0.1714%
2021-08-01 | 2021 | 8 | 2021M08 | 1301389.2252 | 1301389.2252 | 1.775% | 1.775% | 0.1379% | 948045.8175 | 959878.9593 | 2.357% | 2.351% | 0.1772%
2021-09-01 | 2021 | 9 | 2021M09 | 1303409.4175 | 1303409.4175 | 1.773% | 1.773% | 0.155% | 949816.5649 | 961730.5304 | 2.355% | 2.351% | 0.1925%
2021-10-01 | 2021 | 10 | 2021M10 | 1305787.9625 | 1305787.9625 | 1.772% | 1.772% | 0.1822% | 953011.4114 | 963772.3374 | 2.353% | 2.351% | 0.2119%
2021-11-01 | 2021 | 11 | 2021M11 | 1308028.7394 | 1308028.7394 | 1.77% | 1.77% | 0.1713% | 956341.7195 | 965834.8326 | 2.35% | 2.351% | 0.2135%
2021-12-01 | 2021 | 12 | 2021M12 | 1310084.8145 | 1310084.8145 | 1.768% | 1.768% | 0.1569% | 959152.6592 | 967832.1943 | 2.349% | 2.35% | 0.2064%
2022-01-01 | 2022 | 1 | 2022M01 | 1312053.5888 | 1312053.5888 | 1.767% | 1.767% | 0.1501% | 961909.691 | 969825.5489 | 2.347% | 2.35% | 0.2055%
2022-02-01 | 2022 | 2 | 2022M02 | 1313902.789 | 1313902.789 | 1.765% | 1.765% | 0.1407% | 964146.7717 | 971753.951 | 2.345% | 2.35% | 0.1984%
2022-03-01 | 2022 | 3 | 2022M03 | 1315667.3721 | 1315667.3721 | 1.763% | 1.763% | 0.1341% | 965966.087 | 973630.8487 | 2.344% | 2.35% | 0.1928%
2022-04-01 | 2022 | 4 | 2022M04 | 1317492.8026 | 1317492.8026 | 1.761% | 1.761% | 0.1386% | 967503.9264 | 975474.082 | 2.342% | 2.35% | 0.189%
2022-05-01 | 2022 | 5 | 2022M05 | 1319172.7527 | 1319172.7527 | 1.759% | 1.759% | 0.1273% | 968385.6716 | 977234.551 | 2.34% | 2.349% | 0.1801%
2022-06-01 | 2022 | 6 | 2022M06 | 1320894.4023 | 1320894.4023 | 1.758% | 1.758% | 0.1303% | 969321.9181 | 979005.2386 | 2.338% | 2.349% | 0.1809%
2022-07-01 | 2022 | 7 | 2022M07 | 1322417.4088 | 1322417.4088 | 1.756% | 1.756% | 0.1152% | 969530.4281 | 980683.4785 | 2.337% | 2.349% | 0.1711%
2022-08-01 | 2022 | 8 | 2022M08 | 1324223.5071 | 1324223.5071 | 1.755% | 1.755% | 0.1364% | 970176.3408 | 982422.1052 | 2.334% | 2.349% | 0.177%
2022-09-01 | 2022 | 9 | 2022M09 | 1326260.9909 | 1326260.9909 | 1.753% | 1.753% | 0.1536% | 971965.2202 | 984314.1104 | 2.332% | 2.348% | 0.1922%
2022-10-01 | 2022 | 10 | 2022M10 | 1328664.9766 | 1328664.9766 | 1.752% | 1.752% | 0.1809% | 975207.8058 | 986400.3494 | 2.329% | 2.348% | 0.2115%
2022-11-01 | 2022 | 11 | 2022M11 | 1330930.3468 | 1330930.3468 | 1.751% | 1.751% | 0.1702% | 978586.3098 | 988507.4174 | 2.326% | 2.347% | 0.2132%
2022-12-01 | 2022 | 12 | 2022M12 | 1333008.9712 | 1333008.9712 | 1.75% | 1.75% | 0.1559% | 981432.1166 | 990547.6679 | 2.323% | 2.347% | 0.206%
2023-01-01 | 2023 | 1 | 2023M01 | 1334999.1948 | 1334999.1948 | 1.749% | 1.749% | 0.1491% | 984223.1738 | 992583.8775 | 2.32% | 2.347% | 0.2051%
2023-02-01 | 2023 | 2 | 2023M02 | 1336868.3037 | 1336868.3037 | 1.748% | 1.748% | 0.1398% | 986481.3925 | 994553.5066 | 2.317% | 2.346% | 0.198%
2023-03-01 | 2023 | 3 | 2023M03 | 1338651.7657 | 1338651.7657 | 1.747% | 1.747% | 0.1332% | 988311.5759 | 996470.3465 | 2.313% | 2.346% | 0.1924%
2023-04-01 | 2023 | 4 | 2023M04 | 1340497.4231 | 1340497.4231 | 1.746% | 1.746% | 0.1377% | 989853.9743 | 998352.7573 | 2.31% | 2.345% | 0.1886%
2023-05-01 | 2023 | 5 | 2023M05 | 1342195.0148 | 1342195.0148 | 1.745% | 1.745% | 0.1265% | 990725.0792 | 1000150.452 | 2.307% | 2.345% | 0.1797%
2023-06-01 | 2023 | 6 | 2023M06 | 1343934.6881 | 1343934.6881 | 1.744% | 1.744% | 0.1294% | 991652.352 | 1001958.6515 | 2.304% | 2.345% | 0.1805%
2023-07-01 | 2023 | 7 | 2023M07 | 1345471.4977 | 1345471.4977 | 1.743% | 1.743% | 0.1142% | 991835.9803 | 1003672.3389 | 2.301% | 2.344% | 0.1707%
2023-08-01 | 2023 | 8 | 2023M08 | 1347295.1361 | 1347313.4351 | 1.742% | 1.744% | 0.1367% | 992468.5879 | 1005448.0174 | 2.298% | 2.344% | 0.1766%
2023-09-01 | 2023 | 9 | 2023M09 | 1349352.7745 | 1349352.7745 | 1.741% | 1.741% | 0.1511% | 994272.1072 | 1007380.8862 | 2.295% | 2.343% | 0.1919%
2023-10-01 | 2023 | 10 | 2023M10 | 1351781.1933 | 1351781.1933 | 1.74% | 1.74% | 0.1796% | 997564.7399 | 1009512.8129 | 2.293% | 2.343% | 0.2112%
2023-11-01 | 2023 | 11 | 2023M11 | 1354066.9899 | 1354066.9899 | 1.738% | 1.738% | 0.1688% | 1000997.5159 | 1011666.2102 | 2.29% | 2.343% | 0.2129%
2023-12-01 | 2023 | 12 | 2023M12 | 1356161.7833 | 1356161.7833 | 1.737% | 1.737% | 0.1545% | 1003887.0176 | 1013751.4438 | 2.288% | 2.343% | 0.2057%
2024-01-01 | 2024 | 1 | 2024M01 | 1358166.1502 | 1358166.1502 | 1.735% | 1.735% | 0.1476% | 1006720.3613 | 1015832.526 | 2.286% | 2.342% | 0.2049%
2024-02-01 | 2024 | 2 | 2024M02 | 1360047.0342 | 1360047.0342 | 1.734% | 1.734% | 0.1383% | 1009009.1396 | 1017845.5306 | 2.284% | 2.342% | 0.1978%
2024-03-01 | 2024 | 3 | 2024M03 | 1361840.4433 | 1361840.4433 | 1.732% | 1.732% | 0.1317% | 1010860.7843 | 1019804.5988 | 2.282% | 2.342% | 0.1921%
2024-04-01 | 2024 | 4 | 2024M04 | 1363696.7176 | 1363696.7176 | 1.731% | 1.731% | 0.1361% | 1012418.2606 | 1021728.4546 | 2.28% | 2.341% | 0.1883%
2024-05-01 | 2024 | 5 | 2024M05 | 1365402.0617 | 1365402.0617 | 1.729% | 1.729% | 0.1249% | 1013289.4046 | 1023565.6419 | 2.278% | 2.341% | 0.1795%
2024-06-01 | 2024 | 6 | 2024M06 | 1367150.182 | 1367295.9313 | 1.727% | 1.738% | 0.1385% | 1014217.4544 | 1025413.5042 | 2.276% | 2.341% | 0.1802%
2024-07-01 | 2024 | 7 | 2024M07 | 1368692.2891 | 1369212.3942 | 1.726% | 1.765% | 0.14% | 1014383.7915 | 1027164.4848 | 2.273% | 2.341% | 0.1705%
2024-08-01 | 2024 | 8 | 2024M08 | 1370526.6145 | 1371193.5355 | 1.724% | 1.772% | 0.1445% | 1015008.1746 | 1028978.7499 | 2.271% | 2.34% | 0.1763%
2024-09-01 | 2024 | 9 | 2024M09 | 1372599.836 | 1373228.0001 | 1.723% | 1.769% | 0.1482% | 1016828.4086 | 1030953.6628 | 2.269% | 2.34% | 0.1916%
2024-10-01 | 2024 | 10 | 2024M10 | 1375051.3632 | 1375345.5296 | 1.721% | 1.743% | 0.154% | 1020168.9038 | 1033131.9485 | 2.266% | 2.34% | 0.2108%
2024-11-01 | 2024 | 11 | 2024M11 | 1377358.7631 | 1377434.6488 | 1.72% | 1.726% | 0.1517% | 1023650.764 | 1035331.9593 | 2.263% | 2.339% | 0.2125%
2024-12-01 | 2024 | 12 | 2024M12 | 1379472.5291 | 1379484.817 | 1.719% | 1.72% | 0.1486% | 1026576.3482 | 1037462.127 | 2.26% | 2.339% | 0.2053%
2025-01-01 | 2025 | 1 | 2025M01 | 1381494.153 | 1381517.6917 | 1.718% | 1.719% | 0.1471% | 1029444.8576 | 1039588.0984 | 2.257% | 2.339% | 0.2045%
2025-02-01 | 2025 | 2 | 2025M02 | 1383390.2692 | 1383526.1589 | 1.716% | 1.726% | 0.1452% | 1031755.9776 | 1041644.3344 | 2.254% | 2.338% | 0.1974%
2025-03-01 | 2025 | 3 | 2025M03 | 1385197.4542 | 1385518.0185 | 1.715% | 1.739% | 0.1438% | 1033619.6752 | 1043645.3167 | 2.251% | 2.338% | 0.1917%
2025-04-01 | 2025 | 4 | 2025M04 | 1387068.7584 | 1387525.923 | 1.714% | 1.747% | 0.1447% | 1035182.4591 | 1045610.2455 | 2.248% | 2.337% | 0.1879%
2025-05-01 | 2025 | 5 | 2025M05 | 1388786.589 | 1389503.4477 | 1.713% | 1.765% | 0.1423% | 1036043.3119 | 1047486.4532 | 2.246% | 2.337% | 0.1791%
2025-06-01 | 2025 | 6 | 2025M06 | 1390547.9775 | 1391492.6337 | 1.711% | 1.77% | 0.143% | 1036962.5079 | 1049373.599 | 2.243% | 2.337% | 0.1798%
2025-07-01 | 2025 | 7 | 2025M07 | 1392099.7936 | 1393439.4501 | 1.71% | 1.769% | 0.1397% | 1037103.571 | 1051161.6769 | 2.24% | 2.336% | 0.1701%
2025-08-01 | 2025 | 8 | 2025M08 | 1393948.532 | 1395452.0251 | 1.709% | 1.769% | 0.1442% | 1037713.9838 | 1053014.645 | 2.237% | 2.336% | 0.176%
2025-09-01 | 2025 | 9 | 2025M09 | 1396040.0828 | 1397518.831 | 1.708% | 1.769% | 0.1479% | 1039548.1655 | 1055032.1624 | 2.234% | 2.336% | 0.1912%
2025-10-01 | 2025 | 10 | 2025M10 | 1398516.1291 | 1399670.1143 | 1.706% | 1.769% | 0.1537% | 1042938.1846 | 1057258.0178 | 2.232% | 2.335% | 0.2105%
2025-11-01 | 2025 | 11 | 2025M11 | 1400845.4631 | 1401792.4595 | 1.705% | 1.768% | 0.1514% | 1046473.3064 | 1059506.1902 | 2.23% | 2.335% | 0.2122%
2025-12-01 | 2025 | 12 | 2025M12 | 1402977.8974 | 1403875.1733 | 1.704% | 1.768% | 0.1484% | 1049440.7997 | 1061683.0331 | 2.227% | 2.335% | 0.205%
2026-01-01 | 2026 | 1 | 2026M01 | 1405016.3101 | 1405940.222 | 1.703% | 1.768% | 0.1469% | 1052349.0534 | 1063855.4692 | 2.225% | 2.334% | 0.2042%
2026-02-01 | 2026 | 2 | 2026M02 | 1406927.1251 | 1407980.4413 | 1.701% | 1.768% | 0.1449% | 1054687.5323 | 1065956.5472 | 2.223% | 2.334% | 0.1971%
2026-03-01 | 2026 | 3 | 2026M03 | 1408747.4812 | 1410003.7555 | 1.7% | 1.767% | 0.1435% | 1056568.9436 | 1068001.1216 | 2.22% | 2.334% | 0.1914%
2026-04-01 | 2026 | 4 | 2026M04 | 1410632.9212 | 1412043.3704 | 1.699% | 1.767% | 0.1444% | 1058143.2488 | 1070008.8636 | 2.218% | 2.333% | 0.1876%
2026-05-01 | 2026 | 5 | 2026M05 | 1412361.8401 | 1414051.9737 | 1.698% | 1.767% | 0.142% | 1059000.3905 | 1071925.8545 | 2.216% | 2.333% | 0.1788%
2026-06-01 | 2026 | 6 | 2026M06 | 1414134.3938 | 1416072.3014 | 1.696% | 1.766% | 0.1427% | 1059917.0837 | 1073854.0218 | 2.214% | 2.333% | 0.1796%
2026-07-01 | 2026 | 7 | 2026M07 | 1415692.9084 | 1418049.3144 | 1.695% | 1.766% | 0.1394% | 1060038.2313 | 1075680.7779 | 2.211% | 2.333% | 0.1698%
2026-08-01 | 2026 | 8 | 2026M08 | 1417551.9616 | 1420092.9431 | 1.693% | 1.766% | 0.1439% | 1060639.1685 | 1077573.9376 | 2.209% | 2.332% | 0.1757%
2026-09-01 | 2026 | 9 | 2026M09 | 1419656.4333 | 1422191.4382 | 1.692% | 1.765% | 0.1476% | 1062490.838 | 1079635.4706 | 2.207% | 2.332% | 0.1909%
2026-10-01 | 2026 | 10 | 2026M10 | 1422149.9166 | 1424375.4785 | 1.69% | 1.765% | 0.1533% | 1065932.3382 | 1081910.1578 | 2.205% | 2.332% | 0.2102%
2026-11-01 | 2026 | 11 | 2026M11 | 1424492.8646 | 1426529.7849 | 1.688% | 1.765% | 0.151% | 1069521.7565 | 1084207.6391 | 2.202% | 2.331% | 0.2119%
2026-12-01 | 2026 | 12 | 2026M12 | 1426634.9653 | 1428643.6282 | 1.686% | 1.764% | 0.148% | 1072531.2745 | 1086432.1645 | 2.2% | 2.331% | 0.2048%
2027-01-01 | 2027 | 1 | 2027M01 | 1428681.09 | 1430739.4159 | 1.684% | 1.764% | 0.1465% | 1075480.6809 | 1088652.2416 | 2.198% | 2.331% | 0.2039%
2027-02-01 | 2027 | 2 | 2027M02 | 1430597.5193 | 1432809.9464 | 1.682% | 1.763% | 0.1445% | 1077847.6229 | 1090799.2785 | 2.196% | 2.331% | 0.1968%
2027-03-01 | 2027 | 3 | 2027M03 | 1432421.9413 | 1434863.2668 | 1.681% | 1.763% | 0.1431% | 1079747.4297 | 1092888.4911 | 2.194% | 2.33% | 0.1912%
2027-04-01 | 2027 | 4 | 2027M04 | 1434312.6777 | 1436933.203 | 1.679% | 1.763% | 0.1441% | 1081333.3917 | 1094940.0113 | 2.192% | 2.33% | 0.1874%
2027-05-01 | 2027 | 5 | 2027M05 | 1436044.4108 | 1438971.6102 | 1.677% | 1.762% | 0.1417% | 1082186.1112 | 1096898.6141 | 2.189% | 2.33% | 0.1786%
2027-06-01 | 2027 | 6 | 2027M06 | 1437820.9212 | 1441022.034 | 1.675% | 1.762% | 0.1423% | 1083099.0091 | 1098868.5586 | 2.187% | 2.329% | 0.1793%
2027-07-01 | 2027 | 7 | 2027M07 | 1439380.6426 | 1443028.5559 | 1.673% | 1.762% | 0.139% | 1083198.0644 | 1100734.6033 | 2.185% | 2.329% | 0.1695%
2027-08-01 | 2027 | 8 | 2027M08 | 1441246.689 | 1445103.0268 | 1.672% | 1.761% | 0.1436% | 1083786.2338 | 1102668.436 | 2.182% | 2.329% | 0.1754%
2027-09-01 | 2027 | 9 | 2027M09 | 1443363.4581 | 1447233.5866 | 1.67% | 1.761% | 0.1472% | 1085650.7017 | 1104774.33 | 2.18% | 2.328% | 0.1906%
2027-10-01 | 2027 | 10 | 2027M10 | 1445877.198 | 1449451.5119 | 1.668% | 1.76% | 0.153% | 1089137.9255 | 1107098.1165 | 2.177% | 2.328% | 0.2099%
2027-11-01 | 2027 | 11 | 2027M11 | 1448239.3054 | 1451639.4837 | 1.667% | 1.76% | 0.1507% | 1092774.217 | 1109444.964 | 2.174% | 2.328% | 0.2115%
2027-12-01 | 2027 | 12 | 2027M12 | 1450398.5772 | 1453786.5716 | 1.666% | 1.76% | 0.1477% | 1095817.4865 | 1111717.0977 | 2.171% | 2.327% | 0.2044%
2028-01-01 | 2028 | 1 | 2028M01 | 1452460.9794 | 1455915.4367 | 1.664% | 1.76% | 0.1462% | 1098798.8646 | 1113984.6231 | 2.168% | 2.327% | 0.2036%
2028-02-01 | 2028 | 2 | 2028M02 | 1454392.8994 | 1458018.893 | 1.663% | 1.759% | 0.1443% | 1101185.009 | 1116177.394 | 2.165% | 2.327% | 0.1965%
2028-03-01 | 2028 | 3 | 2028M03 | 1456232.7855 | 1460105.1571 | 1.662% | 1.759% | 0.1429% | 1103094.0374 | 1118311.0132 | 2.162% | 2.326% | 0.1908%
2028-04-01 | 2028 | 4 | 2028M04 | 1458142.021 | 1462208.7417 | 1.661% | 1.759% | 0.1439% | 1104682.8801 | 1120406.1193 | 2.159% | 2.326% | 0.187%
2028-05-01 | 2028 | 5 | 2028M05 | 1459890.8652 | 1464280.5099 | 1.661% | 1.759% | 0.1415% | 1105523.1447 | 1122406.2064 | 2.156% | 2.325% | 0.1782%
2028-06-01 | 2028 | 6 | 2028M06 | 1461685.9573 | 1466364.6607 | 1.66% | 1.759% | 0.1421% | 1106425.3034 | 1124417.9463 | 2.154% | 2.325% | 0.1789%
2028-07-01 | 2028 | 7 | 2028M07 | 1463260.8212 | 1468404.1704 | 1.659% | 1.758% | 0.1389% | 1106496.981 | 1126323.4777 | 2.151% | 2.325% | 0.1692%
2028-08-01 | 2028 | 8 | 2028M08 | 1465146.8285 | 1470512.7664 | 1.658% | 1.758% | 0.1434% | 1107069.5445 | 1128298.5275 | 2.148% | 2.324% | 0.175%
2028-09-01 | 2028 | 9 | 2028M09 | 1467287.6703 | 1472678.4275 | 1.658% | 1.758% | 0.1471% | 1108947.315 | 1130449.8297 | 2.146% | 2.324% | 0.1903%
2028-10-01 | 2028 | 10 | 2028M10 | 1469831.6188 | 1474932.8954 | 1.657% | 1.758% | 0.1529% | 1112483.9546 | 1132824.2622 | 2.144% | 2.324% | 0.2096%
2028-11-01 | 2028 | 11 | 2028M11 | 1472221.0555 | 1477156.8055 | 1.656% | 1.758% | 0.1506% | 1116174.2583 | 1135222.4843 | 2.141% | 2.323% | 0.2113%
2028-12-01 | 2028 | 12 | 2028M12 | 1474403.9158 | 1479339.0316 | 1.655% | 1.758% | 0.1475% | 1119260.4828 | 1137544.4793 | 2.139% | 2.323% | 0.2041%
Formulas:
Date = DATE([Year],[Month],1)

## ElectricForecast2012
F2012 Electric Load Forecast
Customers
Customers
Year | Month | Date | Residential | Commercial | Industrial | Streetlight | Resale | Total | Transport
2012 | Annual Average, Not Year-End |  | 963068.4245 | 120194.1764 | 3628.3619 | 3510.2984 | 8 | 1090409.2613 | 17
2013 |  |  | 961990.4196 | 119553.8595 | 3551.2602 | 3557.0758 | 8 | 1088660.6152 | 17
2014 |  |  | 974423.9448 | 120497.8561 | 3517.827 | 3625.1114 | 8 | 1102072.7394 | 17
2015 |  |  | 993636.3944 | 122619.2356 | 3507.105 | 3726.0732 | 8 | 1123496.8082 | 17
2016 |  |  | 1013382.8169 | 124989.3367 | 3496.3052 | 3833.6324 | 8 | 1145710.0912 | 17
2017 |  |  | 1032759.6322 | 127452.9726 | 3483.6592 | 3962.9051 | 8 | 1167667.1691 | 17
2018 |  |  | 1051475.1109 | 129889.1924 | 3469.7273 | 4107.4162 | 8 | 1188949.4467 | 17
2019 |  |  | 1069860.9289 | 132381.9529 | 3455.5952 | 4253.9982 | 8 | 1209960.4752 | 17
2020 |  |  | 1088300.1533 | 134947.4205 | 3441.9751 | 4402.3235 | 8 | 1231099.8724 | 17
2021 |  |  | 1106913.4151 | 137560.7914 | 3428.3192 | 4552.3872 | 8 | 1252462.913 | 17
2022 |  |  | 1125465.0206 | 140195.2119 | 3414.4598 | 4704.7725 | 8 | 1273787.4648 | 17
2023 |  |  | 1143993.912 | 142871.7753 | 3400.709 | 4860.3323 | 8 | 1295134.7286 | 17
2024 |  |  | 1162577.7287 | 145679.8414 | 3386.8036 | 5019.9411 | 8 | 1316672.3149 | 17
2025 |  |  | 1181246.5207 | 148605.2703 | 3372.5079 | 5182.7616 | 8 | 1338415.0605 | 17
2026 |  |  | 1199932.3951 | 151577.292 | 3358.0359 | 5348.7941 | 8 | 1360224.5171 | 17
2027 |  |  | 1218662.2237 | 154611.5645 | 3343.7122 | 5519.4363 | 8 | 1382144.9368 | 17
2028 |  |  | 1237431.0727 | 157704.5002 | 3329.4474 | 5695.0232 | 8 | 1404168.0436 | 17
2029 |  |  | 1256208.9564 | 160854.7586 | 3315.1556 | 5875.3757 | 8 | 1426262.2462 | 17
2030 |  |  | 1275102.3669 | 164067.2018 | 3300.7495 | 6060.9469 | 8 | 1448539.2651 | 17
2031 |  |  | 1294061.4699 | 167336.554 | 3286.2035 | 6251.934 | 8 | 1470944.1614 | 17
2032 |  |  | 1312994.9582 | 170664.945 | 3271.5694 | 6447.8769 | 8 | 1493387.3496 | 17
2033 |  |  | 1331927.715 | 174059.3781 | 3256.9488 | 6649.6714 | 8 | 1515901.7132 | 17
2012 | 1 | 2012-01-01 | 960473.7917 | 119509.2537 | 3625.5395 | 3475.7384 | 8 | 1087092.3233 | 17
2012 | 2 | 2012-02-01 | 961127.824 | 119542.4808 | 3628.2448 | 3478.9331 | 8 | 1087785.4827 | 17
2012 | 3 | 2012-03-01 | 961511.7456 | 119621.7199 | 3630.7577 | 3484.3607 | 8 | 1088256.5839 | 17
2012 | 4 | 2012-04-01 | 961862.9623 | 119809.1355 | 3630.355 | 3490.772 | 8 | 1088801.2247 | 17
2012 | 5 | 2012-05-01 | 962096.6476 | 119993.5167 | 3629.9444 | 3497.5313 | 8 | 1089225.64 | 17
2012 | 6 | 2012-06-01 | 962432.4201 | 120194.0686 | 3629.5315 | 3504.4661 | 8 | 1089768.4863 | 17
2012 | 7 | 2012-07-01 | 962596.4491 | 120402.9338 | 3629.079 | 3511.5064 | 8 | 1090147.9683 | 17
2012 | 8 | 2012-08-01 | 963092.1486 | 120518.5535 | 3628.6257 | 3519.0123 | 8 | 1090766.3401 | 17
2012 | 9 | 2012-09-01 | 963805.8739 | 120628.1421 | 3628.1717 | 3527.0116 | 8 | 1091597.1993 | 17
2012 | 10 | 2012-10-01 | 964914.915 | 120659.5665 | 3627.4348 | 3535.553 | 8 | 1092745.4693 | 17
2012 | 11 | 2012-11-01 | 965988.2791 | 120690.0571 | 3626.6979 | 3544.5746 | 8 | 1093857.6087 | 17
2012 | 12 | 2012-12-01 | 966918.0376 | 120760.6884 | 3625.9609 | 3554.1218 | 8 | 1094866.8087 | 17
2013 | 1 | 2013-01-01 | 968077.3742 | 120826.1935 | 3625.3283 | 3560.6383 | 8 | 1096097.5343 | 17
2013 | 2 | 2013-02-01 | 969063.6812 | 120979.539 | 3624.6955 | 3567.0651 | 8 | 1097242.9808 | 17
2013 | 3 | 2013-03-01 | 969972.1758 | 121150.0406 | 3624.0625 | 3573.3622 | 8 | 1098327.6411 | 17
2013 | 4 | 2013-04-01 | 955469.373 | 118597.3481 | 3530.0159 | 3533.1893 | 8 | 1081137.9263 | 17
2013 | 5 | 2013-05-01 | 956280.9738 | 118747.8675 | 3529.126 | 3538.4903 | 8 | 1082104.4577 | 17
2013 | 6 | 2013-06-01 | 957155.1254 | 118919.0801 | 3528.2825 | 3543.9044 | 8 | 1083154.3924 | 17
2013 | 7 | 2013-07-01 | 957871.8211 | 119094.068 | 3527.5667 | 3549.758 | 8 | 1084051.2137 | 17
2013 | 8 | 2013-08-01 | 958954.0668 | 119174.7456 | 3526.8641 | 3554.2352 | 8 | 1085217.9117 | 17
2013 | 9 | 2013-09-01 | 960263.3556 | 119264.818 | 3526.2608 | 3559.0297 | 8 | 1086621.4642 | 17
2013 | 10 | 2013-10-01 | 961973.2527 | 119274.6268 | 3525.2546 | 3564.4477 | 8 | 1088345.5818 | 17
2013 | 11 | 2013-11-01 | 963650.04 | 119279.6178 | 3524.2589 | 3568.3756 | 8 | 1090030.2924 | 17
2013 | 12 | 2013-12-01 | 965153.7957 | 119338.3694 | 3523.4064 | 3572.4141 | 8 | 1091595.9857 | 17
2014 | 1 | 2014-01-01 | 966735.3156 | 119393.497 | 3522.5702 | 3580.9727 | 8 | 1093240.3554 | 17
2014 | 2 | 2014-02-01 | 968187.2021 | 119532.3543 | 3521.79 | 3588.1812 | 8 | 1094837.5275 | 17
2014 | 3 | 2014-03-01 | 969518.3399 | 119707.4075 | 3520.8911 | 3595.8836 | 8 | 1096350.5221 | 17
2014 | 4 | 2014-04-01 | 970822.4415 | 119970.4766 | 3519.9562 | 3604.4807 | 8 | 1097925.3551 | 17
2014 | 5 | 2014-05-01 | 972044.4668 | 120215.8052 | 3519.0444 | 3612.11 | 8 | 1099399.4264 | 17
2014 | 6 | 2014-06-01 | 973321.1016 | 120482.2108 | 3518.1026 | 3620.2336 | 8 | 1100949.6485 | 17
2014 | 7 | 2014-07-01 | 974426.2149 | 120751.6501 | 3517.3239 | 3629.1434 | 8 | 1102332.3323 | 17
2014 | 8 | 2014-08-01 | 975887.0423 | 120923.9729 | 3516.5572 | 3637.0556 | 8 | 1103972.628 | 17
2014 | 9 | 2014-09-01 | 977558.6364 | 121102.8382 | 3515.8199 | 3645.4507 | 8 | 1105830.7452 | 17
2014 | 10 | 2014-10-01 | 979609.7874 | 121196.0298 | 3514.8784 | 3654.5467 | 8 | 1107983.2423 | 17
2014 | 11 | 2014-11-01 | 981597.958 | 121281.1466 | 3513.9449 | 3662.5257 | 8 | 1110063.5752 | 17
2014 | 12 | 2014-12-01 | 983378.831 | 121416.8845 | 3513.0456 | 3670.7533 | 8 | 1111987.5145 | 17
2015 | 1 | 2015-01-01 | 985205.3394 | 121468.7812 | 3512.1195 | 3680.0047 | 8 | 1113874.2448 | 17
2015 | 2 | 2015-02-01 | 986870.8916 | 121611.3535 | 3511.2302 | 3687.9161 | 8 | 1115689.3914 | 17
2015 | 3 | 2015-03-01 | 988383.5502 | 121792.2118 | 3510.2602 | 3696.1444 | 8 | 1117390.1667 | 17
2015 | 4 | 2015-04-01 | 989843.8388 | 122064.1321 | 3509.3428 | 3705.0387 | 8 | 1119130.3523 | 17
2015 | 5 | 2015-05-01 | 991198.757 | 122320.1203 | 3508.4522 | 3712.9618 | 8 | 1120748.2913 | 17
2015 | 6 | 2015-06-01 | 992585.4695 | 122598.0551 | 3507.4377 | 3721.2671 | 8 | 1122420.2293 | 17
2015 | 7 | 2015-07-01 | 993775.32 | 122879.1269 | 3506.6166 | 3730.2108 | 8 | 1123899.2742 | 17
2015 | 8 | 2015-08-01 | 995312.516 | 123060.5735 | 3505.8276 | 3738.2369 | 8 | 1125625.154 | 17
2015 | 9 | 2015-09-01 | 997049.8123 | 123249.6663 | 3504.9254 | 3746.792 | 8 | 1127559.196 | 17
2015 | 10 | 2015-10-01 | 999164.0687 | 123351.4513 | 3503.9776 | 3756.1312 | 8 | 1129783.6287 | 17
2015 | 11 | 2015-11-01 | 1001209.6767 | 123444.1113 | 3503.0659 | 3764.5761 | 8 | 1131929.43 | 17
2015 | 12 | 2015-12-01 | 1003037.4924 | 123591.2445 | 3502.004 | 3773.5984 | 8 | 1133912.3393 | 17
2016 | 1 | 2016-01-01 | 1004907.3059 | 123679.4229 | 3501.1661 | 3783.9042 | 8 | 1135879.7991 | 17
2016 | 2 | 2016-02-01 | 1006609.36 | 123855.8031 | 3500.3673 | 3792.8007 | 8 | 1137766.3311 | 17
2016 | 3 | 2016-03-01 | 1008148.1339 | 124069.0411 | 3499.6276 | 3801.9577 | 8 | 1139526.7602 | 17
2016 | 4 | 2016-04-01 | 1009622.2207 | 124371.6934 | 3498.6899 | 3811.6624 | 8 | 1141312.2664 | 17
2016 | 5 | 2016-05-01 | 1010982.0472 | 124655.8053 | 3497.7857 | 3820.294 | 8 | 1142963.9322 | 17
2016 | 6 | 2016-06-01 | 1012365.779 | 124962.0528 | 3496.8414 | 3829.2694 | 8 | 1144661.9425 | 17
2016 | 7 | 2016-07-01 | 1013540.8655 | 125270.07 | 3495.9256 | 3838.7874 | 8 | 1146153.6485 | 17
2016 | 8 | 2016-08-01 | 1015066.5421 | 125476.1121 | 3495.0619 | 3847.2181 | 8 | 1147892.9342 | 17
2016 | 9 | 2016-09-01 | 1016791.382 | 125691.0061 | 3494.1568 | 3856.0604 | 8 | 1149840.6053 | 17
2016 | 10 | 2016-10-01 | 1018896.3842 | 125815.0159 | 3493.0697 | 3865.4915 | 8 | 1152077.9612 | 17
2016 | 11 | 2016-11-01 | 1020928.9046 | 125928.64 | 3492.027 | 3873.7655 | 8 | 1154231.3373 | 17
2016 | 12 | 2016-12-01 | 1022734.8777 | 126097.3777 | 3490.9435 | 3882.3775 | 8 | 1156213.5764 | 17
2017 | 1 | 2017-01-01 | 1024577.4651 | 126174.6335 | 3489.7592 | 3895.8549 | 8 | 1158145.7127 | 17
2017 | 2 | 2017-02-01 | 1026243.2533 | 126341.9452 | 3488.6393 | 3907.891 | 8 | 1159989.7287 | 17
2017 | 3 | 2017-03-01 | 1027739.3986 | 126549.4339 | 3487.4764 | 3920.2214 | 8 | 1161704.5304 | 17
2017 | 4 | 2017-04-01 | 1029164.3553 | 126847.6447 | 3486.4021 | 3933.0874 | 8 | 1163439.4896 | 17
2017 | 5 | 2017-05-01 | 1030467.8323 | 127126.3253 | 3485.3692 | 3944.8464 | 8 | 1165032.3732 | 17
2017 | 6 | 2017-06-01 | 1031790.9511 | 127428.151 | 3484.2976 | 3956.9682 | 8 | 1166668.3678 | 17
2017 | 7 | 2017-07-01 | 1032895.4619 | 127731.9632 | 3483.1641 | 3969.6194 | 8 | 1168088.2085 | 17
2017 | 8 | 2017-08-01 | 1034353.0864 | 127931.7963 | 3482.0817 | 3981.1642 | 8 | 1169756.1287 | 17
2017 | 9 | 2017-09-01 | 1036012.5079 | 128141.5582 | 3480.9605 | 3993.143 | 8 | 1171636.1696 | 17
2017 | 10 | 2017-10-01 | 1038059.6194 | 128259.7238 | 3479.7572 | 4005.7067 | 8 | 1173812.807 | 17
2017 | 11 | 2017-11-01 | 1040033.2594 | 128368.2797 | 3478.5985 | 4017.2022 | 8 | 1175905.3399 | 17
2017 | 12 | 2017-12-01 | 1041778.3959 | 128534.2162 | 3477.4041 | 4029.1567 | 8 | 1177827.173 | 17
2018 | 1 | 2018-01-01 | 1043563.0764 | 128606.7184 | 3476.2249 | 4042.1609 | 8 | 1179696.1806 | 17
2018 | 2 | 2018-02-01 | 1045168.0589 | 128770.6542 | 3475.1096 | 4053.7326 | 8 | 1181475.5553 | 17
2018 | 3 | 2018-03-01 | 1046606.1557 | 128975.4492 | 3473.9559 | 4065.6057 | 8 | 1183129.1666 | 17
2018 | 4 | 2018-04-01 | 1047975.8905 | 129274.2339 | 3472.7129 | 4078.0027 | 8 | 1184808.84 | 17
2018 | 5 | 2018-05-01 | 1049225.8487 | 129554.3676 | 3471.5098 | 4089.3637 | 8 | 1186349.0897 | 17
2018 | 6 | 2018-06-01 | 1050501.5657 | 129859.2285 | 3470.2753 | 4101.1788 | 8 | 1187940.2484 | 17
2018 | 7 | 2018-07-01 | 1051559.4969 | 130167.1646 | 3469.0994 | 4113.6099 | 8 | 1189317.3709 | 17
2018 | 8 | 2018-08-01 | 1052980.1107 | 130370.0777 | 3467.9735 | 4124.9986 | 8 | 1190951.1605 | 17
2018 | 9 | 2018-09-01 | 1054609.1452 | 130583.7715 | 3466.8171 | 4136.8968 | 8 | 1192804.6306 | 17
2018 | 10 | 2018-10-01 | 1056632.8328 | 130704.8613 | 3465.5661 | 4149.4498 | 8 | 1194960.71 | 17
2018 | 11 | 2018-11-01 | 1058581.2849 | 130816.6352 | 3464.3578 | 4160.9789 | 8 | 1197031.2569 | 17
2018 | 12 | 2018-12-01 | 1060297.864 | 130987.1466 | 3463.1252 | 4173.0157 | 8 | 1198929.1515 | 17
2019 | 1 | 2019-01-01 | 1062054.4446 | 131062.9595 | 3461.9496 | 4186.1075 | 8 | 1200773.4612 | 17
2019 | 2 | 2019-02-01 | 1063625.7684 | 131232.4588 | 3460.8352 | 4197.9114 | 8 | 1202524.9738 | 17
2019 | 3 | 2019-03-01 | 1065034.3793 | 131443.7132 | 3459.6916 | 4210.1539 | 8 | 1204155.9379 | 17
2019 | 4 | 2019-04-01 | 1066378.1281 | 131750.5527 | 3458.4788 | 4223.0404 | 8 | 1205818.2 | 17
2019 | 5 | 2019-05-01 | 1067604.8803 | 132038.2689 | 3457.3018 | 4234.9294 | 8 | 1207343.3805 | 17
2019 | 6 | 2019-06-01 | 1068864.1047 | 132350.6097 | 3456.1047 | 4247.2969 | 8 | 1208926.116 | 17
2019 | 7 | 2019-07-01 | 1069907.4617 | 132666.2333 | 3454.9581 | 4260.2956 | 8 | 1210296.9486 | 17
2019 | 8 | 2019-08-01 | 1071323.3055 | 132875.0831 | 3453.8575 | 4272.2904 | 8 | 1211932.5364 | 17
2019 | 9 | 2019-09-01 | 1072953.5439 | 133094.7692 | 3452.7333 | 4284.8182 | 8 | 1213793.8646 | 17
2019 | 10 | 2019-10-01 | 1074984.8874 | 133220.1979 | 3451.5558 | 4298.0159 | 8 | 1215962.657 | 17
2019 | 11 | 2019-11-01 | 1076939.6423 | 133336.3868 | 3450.4166 | 4310.2092 | 8 | 1218044.6549 | 17
2019 | 12 | 2019-12-01 | 1078660.6013 | 133512.2019 | 3449.2591 | 4322.9096 | 8 | 1219952.9719 | 17
2020 | 1 | 2020-01-01 | 1080426.4282 | 133591.6602 | 3448.1454 | 4335.7426 | 8 | 1221809.9764 | 17
2020 | 2 | 2020-02-01 | 1082000.925 | 133766.784 | 3447.0863 | 4347.3201 | 8 | 1223570.1154 | 17
2020 | 3 | 2020-03-01 | 1083417.3481 | 133984.1594 | 3446.0035 | 4359.3273 | 8 | 1225214.8383 | 17
2020 | 4 | 2020-04-01 | 1084770.7664 | 134299.2405 | 3444.8117 | 4371.9451 | 8 | 1226894.7636 | 17
2020 | 5 | 2020-05-01 | 1086007.0479 | 134594.7498 | 3443.6567 | 4383.5952 | 8 | 1228437.0496 | 17
2020 | 6 | 2020-06-01 | 1087278.6055 | 134915.014 | 3442.4873 | 4395.7319 | 8 | 1230039.8388 | 17
2020 | 7 | 2020-07-01 | 1088332.6549 | 135238.7537 | 3441.3644 | 4408.4996 | 8 | 1231429.2726 | 17
2020 | 8 | 2020-08-01 | 1089766.9794 | 135453.8116 | 3440.2851 | 4420.276 | 8 | 1233089.352 | 17
2020 | 9 | 2020-09-01 | 1091421.4456 | 135679.6771 | 3439.187 | 4432.5739 | 8 | 1234980.8836 | 17
2020 | 10 | 2020-10-01 | 1093485.7083 | 135808.9276 | 3438.0236 | 4445.511 | 8 | 1237186.1706 | 17
2020 | 11 | 2020-11-01 | 1095472.4719 | 135928.3989 | 3436.8954 | 4457.4601 | 8 | 1239303.2263 | 17
2020 | 12 | 2020-12-01 | 1097221.4583 | 136107.869 | 3435.7552 | 4469.8996 | 8 | 1241242.9821 | 17
2021 | 1 | 2021-01-01 | 1099014.183 | 136188.8393 | 3434.5923 | 4483.256 | 8 | 1243128.8705 | 17
2021 | 2 | 2021-02-01 | 1100603.1515 | 136367.1889 | 3433.4857 | 4495.3902 | 8 | 1244907.2164 | 17
2021 | 3 | 2021-03-01 | 1102033.9706 | 136588.1831 | 3432.356 | 4507.9521 | 8 | 1246570.4619 | 17
2021 | 4 | 2021-04-01 | 1103395.0843 | 136908.0309 | 3431.1971 | 4521.0837 | 8 | 1248263.396 | 17
2021 | 5 | 2021-05-01 | 1104631.9342 | 137207.6311 | 3430.0682 | 4533.238 | 8 | 1249810.8715 | 17
2021 | 6 | 2021-06-01 | 1105901.5197 | 137531.6424 | 3428.9303 | 4545.842 | 8 | 1251415.9343 | 17
2021 | 7 | 2021-07-01 | 1106948.0911 | 137858.7215 | 3427.7573 | 4559.0235 | 8 | 1252801.5933 | 17
2021 | 8 | 2021-08-01 | 1108379.0784 | 138074.7123 | 3426.625 | 4571.1768 | 8 | 1254459.5925 | 17
2021 | 9 | 2021-09-01 | 1110032.3004 | 138301.1738 | 3425.4783 | 4583.7895 | 8 | 1256350.742 | 17
2021 | 10 | 2021-10-01 | 1112100.883 | 138429.2154 | 3424.281 | 4596.9743 | 8 | 1258559.3538 | 17
2021 | 11 | 2021-11-01 | 1114088.3444 | 138547.4302 | 3423.1166 | 4609.1459 | 8 | 1260676.0371 | 17
2021 | 12 | 2021-12-01 | 1115832.4408 | 138726.7284 | 3421.9433 | 4621.7745 | 8 | 1262610.8869 | 17
2022 | 1 | 2022-01-01 | 1117619.3958 | 138806.1779 | 3420.7745 | 4635.161 | 8 | 1264489.5092 | 17
2022 | 2 | 2022-02-01 | 1119182.8832 | 138985.1307 | 3419.6621 | 4647.3743 | 8 | 1266243.0503 | 17
2022 | 3 | 2022-03-01 | 1120603.064 | 139207.8252 | 3418.5332 | 4660.0168 | 8 | 1267897.4393 | 17
2022 | 4 | 2022-04-01 | 1121955.3417 | 139531.9128 | 3417.3507 | 4673.1889 | 8 | 1269585.7942 | 17
2022 | 5 | 2022-05-01 | 1123183.4388 | 139835.3703 | 3416.1996 | 4685.3913 | 8 | 1271128.4 | 17
2022 | 6 | 2022-06-01 | 1124446.2108 | 140164.0794 | 3415.0461 | 4698.0572 | 8 | 1272731.3934 | 17
2022 | 7 | 2022-07-01 | 1125481.9567 | 140496.4499 | 3413.8609 | 4711.3246 | 8 | 1274111.5921 | 17
2022 | 8 | 2022-08-01 | 1126908.4449 | 140715.6584 | 3412.7203 | 4723.5829 | 8 | 1275768.4065 | 17
2022 | 9 | 2022-09-01 | 1128561.1455 | 140946.2413 | 3411.5693 | 4736.3424 | 8 | 1277663.2985 | 17
2022 | 10 | 2022-10-01 | 1130635.9277 | 141076.7247 | 3410.4003 | 4749.7179 | 8 | 1279880.7706 | 17
2022 | 11 | 2022-11-01 | 1132628.4391 | 141196.978 | 3409.2681 | 4762.1082 | 8 | 1282004.7934 | 17
2022 | 12 | 2022-12-01 | 1134373.9994 | 141379.9936 | 3408.1324 | 4775.0046 | 8 | 1283945.13 | 17
2023 | 1 | 2023-01-01 | 1136163.2117 | 141460.8983 | 3406.9737 | 4788.7034 | 8 | 1285827.7871 | 17
2023 | 2 | 2023-02-01 | 1137725.1865 | 141642.6786 | 3405.8731 | 4801.2363 | 8 | 1287582.9745 | 17
2023 | 3 | 2023-03-01 | 1139141.9995 | 141868.9267 | 3404.756 | 4814.226 | 8 | 1289237.9083 | 17
2023 | 4 | 2023-04-01 | 1140489.812 | 142198.3787 | 3403.5796 | 4827.7715 | 8 | 1290927.5418 | 17
2023 | 5 | 2023-05-01 | 1141711.3009 | 142506.6617 | 3402.4361 | 4840.3438 | 8 | 1292468.7425 | 17
2023 | 6 | 2023-06-01 | 1142968.653 | 142840.9286 | 3401.291 | 4853.4077 | 8 | 1294072.2803 | 17
2023 | 7 | 2023-07-01 | 1143995.3919 | 143178.6422 | 3400.128 | 4867.0924 | 8 | 1295449.2545 | 17
2023 | 8 | 2023-08-01 | 1145419.4876 | 143400.7732 | 3399.0102 | 4879.7391 | 8 | 1297107.0101 | 17
2023 | 9 | 2023-09-01 | 1147074.6764 | 143634.645 | 3397.8814 | 4892.8833 | 8 | 1299008.0861 | 17
2023 | 10 | 2023-10-01 | 1149159.7173 | 143766.5954 | 3396.6861 | 4906.6304 | 8 | 1301237.6291 | 17
2023 | 11 | 2023-11-01 | 1151162.0728 | 143888.1412 | 3395.5277 | 4919.3607 | 8 | 1303373.1024 | 17
2023 | 12 | 2023-12-01 | 1152915.4345 | 144074.034 | 3394.3654 | 4932.593 | 8 | 1305324.4268 | 17
2024 | 1 | 2024-01-01 | 1154714.7297 | 144169.9032 | 3393.2168 | 4946.611 | 8 | 1307232.4608 | 17
2024 | 2 | 2024-02-01 | 1156283.9863 | 144368.2305 | 3392.1262 | 4959.4539 | 8 | 1309011.7968 | 17
2024 | 3 | 2024-03-01 | 1157706.8438 | 144611.9019 | 3391.0175 | 4972.7693 | 8 | 1310690.5326 | 17
2024 | 4 | 2024-04-01 | 1159059.5386 | 144960.639 | 3389.7874 | 4986.6452 | 8 | 1312404.6102 | 17
2024 | 5 | 2024-05-01 | 1160283.5968 | 145287.6524 | 3388.5898 | 4999.527 | 8 | 1313967.366 | 17
2024 | 6 | 2024-06-01 | 1161544.5004 | 145641.2721 | 3387.3907 | 5012.8978 | 8 | 1315594.0611 | 17
2024 | 7 | 2024-07-01 | 1162570.9954 | 145998.6447 | 3386.1862 | 5026.8787 | 8 | 1316990.705 | 17
2024 | 8 | 2024-08-01 | 1164000.9601 | 146238.3843 | 3385.0268 | 5039.8154 | 8 | 1318672.1867 | 17
2024 | 9 | 2024-09-01 | 1165666.0352 | 146490.4194 | 3383.8566 | 5053.2613 | 8 | 1320601.5725 | 17
2024 | 10 | 2024-10-01 | 1167767.6675 | 146638.245 | 3382.6515 | 5067.3078 | 8 | 1322863.8718 | 17
2024 | 11 | 2024-11-01 | 1169784.8185 | 146775.2016 | 3381.4826 | 5080.3162 | 8 | 1325029.8189 | 17
2024 | 12 | 2024-12-01 | 1171549.0727 | 146977.6024 | 3380.3114 | 5093.81 | 8 | 1327008.7965 | 17
2025 | 1 | 2025-01-01 | 1173359.9208 | 147073.6089 | 3379.1042 | 5108.066 | 8 | 1328928.6999 | 17
2025 | 2 | 2025-02-01 | 1174936.5139 | 147274.2021 | 3377.9546 | 5121.1466 | 8 | 1330717.8172 | 17
2025 | 3 | 2025-03-01 | 1176364.425 | 147521.1566 | 3376.7876 | 5134.7116 | 8 | 1332405.0808 | 17
2025 | 4 | 2025-04-01 | 1177720.8591 | 147875.3414 | 3375.543 | 5148.8415 | 8 | 1334128.585 | 17
2025 | 5 | 2025-05-01 | 1178946.0953 | 148207.4258 | 3374.3298 | 5161.9779 | 8 | 1335697.8288 | 17
2025 | 6 | 2025-06-01 | 1180208.863 | 148566.6103 | 3373.1178 | 5175.6102 | 8 | 1337332.2014 | 17
2025 | 7 | 2025-07-01 | 1181233.2706 | 148929.6503 | 3371.8827 | 5189.8519 | 8 | 1338732.6556 | 17
2025 | 8 | 2025-08-01 | 1182666.7998 | 149172.6817 | 3370.6914 | 5203.035 | 8 | 1340421.2079 | 17
2025 | 9 | 2025-09-01 | 1184338.7169 | 149428.2122 | 3369.4903 | 5216.7167 | 8 | 1342361.1361 | 17
2025 | 10 | 2025-10-01 | 1186453.2608 | 149577.5487 | 3368.26 | 5230.9856 | 8 | 1344638.0551 | 17
2025 | 11 | 2025-11-01 | 1188480.3411 | 149715.8576 | 3367.0646 | 5244.2254 | 8 | 1346815.4886 | 17
2025 | 12 | 2025-12-01 | 1190249.1826 | 149920.9481 | 3365.8682 | 5257.9706 | 8 | 1348801.9694 | 17
2026 | 1 | 2026-01-01 | 1192063.643 | 150017.8152 | 3364.6433 | 5272.4966 | 8 | 1350726.598 | 17
2026 | 2 | 2026-02-01 | 1193638.4191 | 150221.5542 | 3363.4745 | 5285.8433 | 8 | 1352517.2911 | 17
2026 | 3 | 2026-03-01 | 1195061.6032 | 150472.6869 | 3362.2893 | 5299.6784 | 8 | 1354204.2579 | 17
2026 | 4 | 2026-04-01 | 1196412.3558 | 150833.397 | 3361.0487 | 5314.0781 | 8 | 1355928.8796 | 17
2026 | 5 | 2026-05-01 | 1197629.7143 | 151171.6821 | 3359.8379 | 5327.4923 | 8 | 1357496.7266 | 17
2026 | 6 | 2026-06-01 | 1198885.9331 | 151537.6277 | 3358.6299 | 5341.4177 | 8 | 1359131.6084 | 17
2026 | 7 | 2026-07-01 | 1199900.9715 | 151907.5909 | 3357.4048 | 5355.9649 | 8 | 1360529.9321 | 17
2026 | 8 | 2026-08-01 | 1201332.3456 | 152155.1596 | 3356.2222 | 5369.4634 | 8 | 1362221.1907 | 17
2026 | 9 | 2026-09-01 | 1203007.4653 | 152415.4157 | 3355.0314 | 5383.4782 | 8 | 1364169.3906 | 17
2026 | 10 | 2026-10-01 | 1205133.9981 | 152567.6262 | 3353.8072 | 5398.0953 | 8 | 1366461.5268 | 17
2026 | 11 | 2026-11-01 | 1207172.565 | 152708.7862 | 3352.6162 | 5411.6968 | 8 | 1368653.6642 | 17
2026 | 12 | 2026-12-01 | 1208949.7268 | 152918.1626 | 3351.4256 | 5425.8244 | 8 | 1370653.1395 | 17
2027 | 1 | 2027-01-01 | 1210774.9921 | 153017.8844 | 3350.2367 | 5440.7335 | 8 | 1372591.8466 | 17
2027 | 2 | 2027-02-01 | 1212356.5739 | 153227.123 | 3349.0972 | 5454.536 | 8 | 1374395.3302 | 17
2027 | 3 | 2027-03-01 | 1213783.017 | 153483.2323 | 3347.9408 | 5468.7844 | 8 | 1376090.9746 | 17
2027 | 4 | 2027-04-01 | 1215137.4516 | 153851.8632 | 3346.7115 | 5483.5834 | 8 | 1377827.6096 | 17
2027 | 5 | 2027-05-01 | 1216355.842 | 154198.1822 | 3345.5053 | 5497.4712 | 8 | 1379405.0006 | 17
2027 | 6 | 2027-06-01 | 1217611.9453 | 154571.2242 | 3344.3037 | 5511.8259 | 8 | 1381047.2993 | 17
2027 | 7 | 2027-07-01 | 1218624.0554 | 154949.017 | 3343.0933 | 5526.7851 | 8 | 1382450.9507 | 17
2027 | 8 | 2027-08-01 | 1220057.8642 | 155202.4966 | 3341.9185 | 5540.7713 | 8 | 1384151.0506 | 17
2027 | 9 | 2027-09-01 | 1221737.1865 | 155467.3777 | 3340.7372 | 5555.2282 | 8 | 1386108.5297 | 17
2027 | 10 | 2027-10-01 | 1223875.7662 | 155622.7678 | 3339.5221 | 5570.2689 | 8 | 1388416.325 | 17
2027 | 11 | 2027-11-01 | 1225924.5642 | 155767.4487 | 3338.3332 | 5584.3523 | 8 | 1390622.6984 | 17
2027 | 12 | 2027-12-01 | 1227707.4264 | 155980.1563 | 3337.1474 | 5598.8958 | 8 | 1392631.6259 | 17
2028 | 1 | 2028-01-01 | 1229540.953 | 156081.2874 | 3335.9532 | 5614.201 | 8 | 1394580.3946 | 17
2028 | 2 | 2028-02-01 | 1231127.5167 | 156294.3235 | 3334.8071 | 5628.399 | 8 | 1396393.0464 | 17
2028 | 3 | 2028-03-01 | 1232556.8255 | 156555.1348 | 3333.6454 | 5643.0418 | 8 | 1398096.6476 | 17
2028 | 4 | 2028-04-01 | 1233912.5057 | 156930.7366 | 3332.4338 | 5658.2265 | 8 | 1399841.9026 | 17
2028 | 5 | 2028-05-01 | 1235128.614 | 157283.531 | 3331.2431 | 5672.4988 | 8 | 1401423.8868 | 17
2028 | 6 | 2028-06-01 | 1236381.8835 | 157663.3039 | 3330.0591 | 5687.232 | 8 | 1403070.4786 | 17
2028 | 7 | 2028-07-01 | 1237386.2099 | 158048.2101 | 3328.8417 | 5702.559 | 8 | 1404473.8207 | 17
2028 | 8 | 2028-08-01 | 1238817.2034 | 158306.488 | 3327.6579 | 5716.9205 | 8 | 1406176.2698 | 17
2028 | 9 | 2028-09-01 | 1240497.09 | 158576.3791 | 3326.4677 | 5731.7585 | 8 | 1408139.6953 | 17
2028 | 10 | 2028-10-01 | 1242643.3974 | 158734.5922 | 3325.2648 | 5747.1816 | 8 | 1410458.436 | 17
2028 | 11 | 2028-11-01 | 1244697.9928 | 158881.8108 | 3324.086 | 5761.6574 | 8 | 1412673.5471 | 17
2028 | 12 | 2028-12-01 | 1246482.6807 | 159098.2055 | 3322.9094 | 5776.6026 | 8 | 1414688.3981 | 17
2029 | 1 | 2029-01-01 | 1248319.0673 | 159200.9264 | 3321.7043 | 5792.3173 | 8 | 1416642.0153 | 17
2029 | 2 | 2029-02-01 | 1249904.4168 | 159417.7882 | 3320.5448 | 5806.9191 | 8 | 1418457.6689 | 17
2029 | 3 | 2029-03-01 | 1251330.7874 | 159683.2658 | 3319.3679 | 5821.9609 | 8 | 1420163.3819 | 17
2029 | 4 | 2029-04-01 | 1252683.4308 | 160066.0202 | 3318.157 | 5837.5362 | 8 | 1421913.1441 | 17
2029 | 5 | 2029-05-01 | 1253895.0423 | 160425.6167 | 3316.9648 | 5852.2106 | 8 | 1423497.8344 | 17
2029 | 6 | 2029-06-01 | 1255145.9551 | 160812.6874 | 3315.7781 | 5867.3589 | 8 | 1425149.7795 | 17
2029 | 7 | 2029-07-01 | 1256146.0791 | 161205.0652 | 3314.5569 | 5883.1147 | 8 | 1426556.8159 | 17
2029 | 8 | 2029-08-01 | 1257580.3732 | 161468.249 | 3313.3675 | 5897.894 | 8 | 1428267.8838 | 17
2029 | 9 | 2029-09-01 | 1259268.6732 | 161743.1229 | 3312.1709 | 5913.1437 | 8 | 1430245.1108 | 17
2029 | 10 | 2029-10-01 | 1261431.51 | 161904.3782 | 3310.9497 | 5928.969 | 8 | 1432583.8069 | 17
2029 | 11 | 2029-11-01 | 1263502.0152 | 162054.6043 | 3309.7506 | 5943.8569 | 8 | 1434818.227 | 17
2029 | 12 | 2029-12-01 | 1265300.1257 | 162275.379 | 3308.5544 | 5959.2272 | 8 | 1436851.2863 | 17
2030 | 1 | 2030-01-01 | 1267153.0863 | 162380.2676 | 3307.3538 | 5975.3785 | 8 | 1438824.0861 | 17
2030 | 2 | 2030-02-01 | 1268751.6964 | 162601.5684 | 3306.1957 | 5990.4208 | 8 | 1440657.8813 | 17
2030 | 3 | 2030-03-01 | 1270189.763 | 162872.2228 | 3305.0213 | 6005.9099 | 8 | 1442380.9169 | 17
2030 | 4 | 2030-04-01 | 1271553.0148 | 163262.8468 | 3303.7801 | 6021.936 | 8 | 1444149.5778 | 17
2030 | 5 | 2030-05-01 | 1272772.5641 | 163629.9168 | 3302.5575 | 6037.0655 | 8 | 1445750.1039 | 17
2030 | 6 | 2030-06-01 | 1274032.0396 | 164024.8764 | 3301.3435 | 6052.6741 | 8 | 1447418.9335 | 17
2030 | 7 | 2030-07-01 | 1275036.6789 | 164425.1354 | 3300.132 | 6068.8883 | 8 | 1448838.8345 | 17
2030 | 8 | 2030-08-01 | 1276480.9412 | 164693.5108 | 3298.9503 | 6084.1381 | 8 | 1450565.5404 | 17
2030 | 9 | 2030-09-01 | 1278182.381 | 164973.436 | 3297.7637 | 6099.8664 | 8 | 1452561.4472 | 17
2030 | 10 | 2030-10-01 | 1280364.6156 | 165137.507 | 3296.5204 | 6116.1734 | 8 | 1454922.8164 | 17
2030 | 11 | 2030-11-01 | 1282451.3548 | 165290.3165 | 3295.2971 | 6131.5378 | 8 | 1457176.5062 | 17
2030 | 12 | 2030-12-01 | 1284260.267 | 165514.8172 | 3294.0785 | 6147.3746 | 8 | 1459224.5372 | 17
2031 | 1 | 2031-01-01 | 1286122.9965 | 165619.7799 | 3292.8646 | 6164.0161 | 8 | 1461207.6571 | 17
2031 | 2 | 2031-02-01 | 1287725.7717 | 165844.9144 | 3291.6956 | 6179.5108 | 8 | 1463049.8925 | 17
2031 | 3 | 2031-03-01 | 1289164.4508 | 166120.1968 | 3290.5111 | 6195.4526 | 8 | 1464778.6114 | 17
2031 | 4 | 2031-04-01 | 1290526.4935 | 166518.0543 | 3289.2619 | 6211.9264 | 8 | 1466553.736 | 17
2031 | 5 | 2031-05-01 | 1291741.1173 | 166891.843 | 3288.0309 | 6227.4891 | 8 | 1468156.4804 | 17
2031 | 6 | 2031-06-01 | 1292994.9663 | 167293.8365 | 3286.8117 | 6243.5132 | 8 | 1469827.1277 | 17
2031 | 7 | 2031-07-01 | 1293988.6463 | 167701.3268 | 3285.5865 | 6260.1166 | 8 | 1471243.6763 | 17
2031 | 8 | 2031-08-01 | 1295426.7188 | 167974.3687 | 3284.3893 | 6275.7627 | 8 | 1472969.2395 | 17
2031 | 9 | 2031-09-01 | 1297125.2139 | 168258.9696 | 3283.1894 | 6291.8895 | 8 | 1474967.2623 | 17
2031 | 10 | 2031-10-01 | 1299311.8233 | 168425.5782 | 3281.935 | 6308.5913 | 8 | 1477335.9277 | 17
2031 | 11 | 2031-11-01 | 1301401.0074 | 168580.8104 | 3280.6984 | 6324.3535 | 8 | 1479594.8696 | 17
2031 | 12 | 2031-12-01 | 1303208.433 | 168808.9693 | 3279.4682 | 6340.5857 | 8 | 1481645.4563 | 17
2032 | 1 | 2032-01-01 | 1305071.7655 | 168914.1151 | 3278.2419 | 6357.6584 | 8 | 1483629.7809 | 17
2032 | 2 | 2032-02-01 | 1306672.1825 | 169143.4827 | 3277.0625 | 6373.5487 | 8 | 1485474.2765 | 17
2032 | 3 | 2032-03-01 | 1308107.1738 | 169423.9649 | 3275.8688 | 6389.8911 | 8 | 1487204.8986 | 17
2032 | 4 | 2032-04-01 | 1309465.3405 | 169829.8182 | 3274.62 | 6406.7668 | 8 | 1488984.5455 | 17
2032 | 5 | 2032-05-01 | 1310674.088 | 170211.1875 | 3273.3892 | 6422.7414 | 8 | 1490589.4061 | 17
2032 | 6 | 2032-06-01 | 1311923.2038 | 170621.152 | 3272.1735 | 6439.1854 | 8 | 1492263.7148 | 17
2032 | 7 | 2032-07-01 | 1312908.7842 | 171036.8724 | 3270.9508 | 6456.211 | 8 | 1493680.8184 | 17
2032 | 8 | 2032-08-01 | 1314344.8016 | 171315.5533 | 3269.7541 | 6472.298 | 8 | 1495410.407 | 17
2032 | 9 | 2032-09-01 | 1316045.2213 | 171605.8126 | 3268.557 | 6488.8789 | 8 | 1497416.4697 | 17
2032 | 10 | 2032-10-01 | 1318241.0631 | 171775.8719 | 3267.3052 | 6506.043 | 8 | 1499798.2833 | 17
2032 | 11 | 2032-11-01 | 1320337.5398 | 171934.4088 | 3266.0691 | 6522.2868 | 8 | 1502068.3045 | 17
2032 | 12 | 2032-12-01 | 1322148.3347 | 172167.1011 | 3264.8412 | 6539.0134 | 8 | 1504127.2904 | 17
2033 | 1 | 2033-01-01 | 1324015.8523 | 172273.0031 | 3263.6135 | 6556.6339 | 8 | 1506117.1028 | 17
2033 | 2 | 2033-02-01 | 1325616.3944 | 172507.1084 | 3262.4349 | 6573.0338 | 8 | 1507966.9716 | 17
2033 | 3 | 2033-03-01 | 1327049.2726 | 172793.1658 | 3261.243 | 6589.8878 | 8 | 1509701.5692 | 17
2033 | 4 | 2033-04-01 | 1328404.4091 | 173207.3386 | 3259.9945 | 6607.2716 | 8 | 1511487.0137 | 17
2033 | 5 | 2033-05-01 | 1329607.5718 | 173596.5237 | 3258.7639 | 6623.7598 | 8 | 1513094.6192 | 17
2033 | 6 | 2033-06-01 | 1330851.8892 | 174014.6447 | 3257.5515 | 6640.7185 | 8 | 1514772.8039 | 17
2033 | 7 | 2033-07-01 | 1331829.1303 | 174438.7614 | 3256.3312 | 6658.252 | 8 | 1516190.4748 | 17
2033 | 8 | 2033-08-01 | 1333262.8408 | 174723.1976 | 3255.1351 | 6674.8568 | 8 | 1517924.0302 | 17
2033 | 9 | 2033-09-01 | 1334964.9396 | 175019.2278 | 3253.9407 | 6691.9566 | 8 | 1519938.0646 | 17
2033 | 10 | 2033-10-01 | 1337169.7752 | 175192.8092 | 3252.6914 | 6709.634 | 8 | 1522332.9098 | 17
2033 | 11 | 2033-11-01 | 1339273.2926 | 175354.7208 | 3251.4558 | 6726.4008 | 8 | 1524613.87 | 17
2033 | 12 | 2033-12-01 | 1341087.2118 | 175592.0364 | 3250.2301 | 6743.6509 | 8 | 1526681.1291 | 17

## GasForecast2011
| SOURCE:PSE 2011 Forecast | [5 empty] | F2011 Electric Forecasts
Forecast of Customers (year end)
|  | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 10-19 aarg
| Total Firm Customers | 1069364 | 1075402 | 1080675 | 1089631.7508 | 1101357.8273 | 1119120.7947 | 1139393.21 | 1159110.8776 | 1179034.1751 | 1199440.6487 | 1220141.4144 | 1242319.4495 | 1.561%
| Additions | 0 | 6038 | 5273 | 8956.7508 | 11726.0765 | 17762.9674 | 20272.4153 | 19717.6676 | 19923.2975 | 20406.4736 | 20700.7657 | 22178.035
| % Change | 1.226% | 0.5646% | 0.4903% | 0.8288% | 1.076% | 1.613% | 1.811% | 1.731% | 1.719% | 1.731% | 1.726% | 1.818%
| Residential | 943759 | 949889 | 954898 | 961481.1628 | 970530.3946 | 985509.2324 | 1002980.0952 | 1020018.3656 | 1037376.0377 | 1055219.3675 | 1073298.8657 | 1092803.3951 | 1.51% | 88.24%
| Commercial | 118531 | 118422 | 118706 | 120993.3835 | 123519.9655 | 126151.1085 | 128792.1792 | 131303.0188 | 133717.4608 | 136141.4083 | 138617.3231 | 141138.5619 | 1.942% | 11.1%
| Industrial | 3733 | 3679 | 3637 | 3631.6364 | 3619.5408 | 3606.4048 | 3592.0818 | 3576.7993 | 3559.9716 | 3543.3277 | 3527.2563 | 3511.8514 | -0.3883% | 0.3333%
| Street Lights | 3333 | 3404 | 3426 | 3517.5681 | 3679.9263 | 3846.0489 | 4020.8537 | 4204.6938 | 4372.7049 | 4528.5452 | 4689.9694 | 4857.6411 | 3.956% | 0.3228%
| Resale | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0% | 0.0007342%
| Transportation** | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 0% | 0.00156%
** Not included in the Firm Schedules | [14 empty] | 0.6584%
F2011 Gas Forecast
Source: PSE 2011 Forecast
Forecast of Customers (year end)
|  | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 10-19 aarg
| Total | 743836 | 748853 | 753637.23 | 763491.5479 | 776610.5758 | 792962.2712 | 811612.1455 | 831476.6204 | 851983.3911 | 872805.209 | 893969.8149 | 915382.5308 | 2.184%
| Additions | 14337 | 5017 | 4784.23 | 9854.3179 | 13119.0279 | 16351.6954 | 18649.8743 | 19864.4749 | 20506.7707 | 20821.8179 | 21164.6059 | 21412.7159
| % Change | 1.965% | 0.6745% | 0.6389% | 1.308% | 1.718% | 2.106% | 2.352% | 2.448% | 2.466% | 2.444% | 2.425% | 2.395%
| Residential | 686720 | 691850 | 696989.23 | 705969.1701 | 718086.4669 | 733336.5551 | 750887.5826 | 769700.3512 | 789192.8982 | 808988.2732 | 829100.3376 | 849433.7359 | 2.222% | 92.47%
| Commercial | 53999 | 53950 | 53628 | 54533.7386 | 55561.7926 | 56687.7875 | 57810.867 | 58886.9009 | 59925.8503 | 60976.3078 | 62052.0283 | 63153.6221 | 1.833% | 7.143%
| Industrial | 2584 | 2514 | 2480 | 2463.1416 | 2447.8043 | 2432.4338 | 2416.6933 | 2400.8991 | 2384.6909 | 2368.631 | 2352.7381 | 2337.1557 | -0.657% | 0.3226%
| Coml Interrupt | 387 | 370 | 353 | 336.4975 | 325.512 | 316.4949 | 308.0026 | 299.4693 | 290.9517 | 282.997 | 275.7109 | 269.0171 | -2.974% | 0.04407%
| Ind Interrupt | 20 | 19 | 18 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | -1.3% | 0.002096%
| Coml Transpo | 36 | 48 | 67 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 0.3274% | 0.009037%
| Ind Transpo | 90 | 102 | 102 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 0.216% | 0.01362%
0.3914%

## Termination (R)
|  | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023
Asset termination |  | 37.8 | 31.3 | 24.6 | 17.8 | 10.9 | 3.6 | 1.5 | 1.2 | 0.9 | 0.6 | 0.4 | 0.1 | 0
$12M pullforward |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transition fees | bar: 2011 to 2023
Penalty |  | 30 | 30 | 30 | 30 | 30 | 30 | 28 | 25 | 21 | 17 | 12 | 7 | 0
Total term fees (lump sum) |  | 67.8 | 61.3 | 54.6 | 47.8 | 40.9 | 33.6 | 29.5 | 26.2 | 21.9 | 17.6 | 12.4 | 7.1 | 0
Reduction amount (per meter) |  | 38.73 | 35 | 31.19 | 27.31 | 23.35 | 19.18 | 16.85 | 14.98 | 12.53 | 10.08 | 7.06 | 4.04 | 0
Annual discount rate (L+G assumed) | 0%
Annual discount rate (PSE assumed) | 8.25%
Assumes payment at beginning of year for all years
Asset Term (using L+G rate) |  | 37.8 | 31.3 | 24.6 | 17.8 | 10.9 | 3.6 | 1.5 | 1.2 | 0.9 | 0.6 | 0.4 | 0.1 | 0
Asset Term (using PSE rate) |  | 37.8 | 28.9145 | 20.9932 | 14.0325 | 7.9381 | 2.4219 | 0.93223 | 0.68895 | 0.47733 | 0.29397 | 0.18104 | 0.041811 | 0
Penalty (using L+G rate) | [6 empty] | 30 | 28 | 25 | 21 | 17 | 12 | 7 | 0
Penalty (using PSE rate) | [6 empty] | 30 | 25.8661 | 21.3346 | 16.5552 | 12.3805 | 8.0731 | 4.3504 | 0
Total term fees (lump sum) (using L+G rate) | [6 empty] | 33.6 | 29.5 | 26.2 | 21.9 | 17.6 | 12.4 | 7.1 | 0
Total term fees (lump sum) (using PSE rate) | [6 empty] | 32.4219 | 26.7983 | 22.0235 | 17.0326 | 12.6744 | 8.2542 | 4.3922 | 0
Meter Value/Reduction Amount (dollars) Total | 16.96 | 16.96 | 13.568 | 10.176 | 6.784 | 3.392 | 1.8 | 0.96771 | 0.79997 | 0.62067 | 0.42856 | 0.29629 | 0.07692 | 0
Electric | 11.78 | 2011: 11.78; 2012: 9.424; 2013: 7.068; 2014: 4.712; 2015: 2.356
Gas | 17.67 | 2011: 17.67; 2012: 14.136; 2013: 10.602; 2014: 7.068; 2015: 3.534
Asset Termination ($M) or current minimum * value |  | 29.6808 | 23.7447 | 17.8085 | 11.5331 | 5.597 | 2.8801 | 1.5 | 1.2 | 0.9 | 0.6 | 0.4 | 0.1 | 0
Electric |  | 2011: 12.1195; 2012: 9.6956; 2013: 7.2717; 2014: 4.7093; 2015: 2.2854
Gas |  | 2011: 12.7441; 2012: 10.1953; 2013: 7.6464; 2014: 4.952; 2015: 2.4032
annual escalator | 2.5% | 0.482 | 0.48742 | 0.49291 | 0.49845 | 0.50406 | 0.50973 | 0.52247 | 0.53553 | 0.54892 | 0.56265 | 0.57671 | 0.59113 | 0.60591
Minimum Revenue (price/read) | 0.482 | [5 empty] | 7340333.2104 | 9718305.1198 | 9639942.0566 | 9551586.8995 | 9452789.0208 | 9343081.5064 | 9221980.6231 | 9088985.2696
Lost Profit | 12% | 0 | 0 | 0 | 0 | 0 | 880839.9853 | 1166196.6144 | 1156793.0468 | 1146190.4279 | 1134334.6825 | 1121169.7808 | 1106637.6748 | 1090678.2324
Penalty $M (NPV of Lost Profit) |  | 4.9896 | 5.3388 | 5.7126 | 6.1124 | 6.5403 | 6.1173 | 5.3793 | 4.5991 | 3.7748 | 2.9047 | 1.9869 | 1.0193 | 0
Purchase of network in 2014 | -3.456
Proposed Royalty ($/yr -- to be paid monthly) | 0.69408
cost/read |  | 1.37 | 1.37 | 1.37 | 1.37 | 1.37 | 0.482 | 0.482 | 0.482 | 0.482 | 0.482 | 0.482 | 0.482
|  | 28770822 | 28770822 | 28770822 | 27948822 | 27126822 | 13517222.4 | 8965489.2 | 8676289.2 | 8387089.2 | 8097889.2 | 7808689.2 | 7519489.2
$M |  | 28.7708 | 28.7708 | 28.7708 | 27.9488 | 27.1268 | 13.5172 | 8.9655 | 8.6763 | 8.3871 | 8.0979 | 7.8087 | 7.5195
One year's Revenue (1 meter) |  | 16.44 | 16.44 | 16.44 | 16.44 | 16.44 | 5.784 | 5.784 | 5.784 | 5.784 | 5.784 | 5.784 | 5.784
Termination for Convenience and Reduction Fees
Meter Minimum |  | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023
Total | 50000 | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX
Electric | 1106360 | 2011: XXXXXXXX; 2012: XXXXXXXX; 2013: XXXXXXXX; 2014: XXXXXXXX; 2015: XXXXXXXX; 2016: XXXXXXXX
Gas | 775582 | 2011: XXXXXXXX; 2012: XXXXXXXX; 2013: XXXXXXXX; 2014: XXXXXXXX; 2015: XXXXXXXX; 2016: XXXXXXXX
Reduction Fees In Dollars/Meter |  | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023
Asset Value (Until 4/1/2016)
Electric |  | 2011: XXXXXXXX; 2012: XXXXXXXX; 2013: XXXXXXXX; 2014: XXXXXXXX; 2015: XXXXXXXX; 2016: XXXXXXXX
Gas |  | 2011: XXXXXXXX; 2012: XXXXXXXX; 2013: XXXXXXXX; 2014: XXXXXXXX; 2015: XXXXXXXX; 2016: XXXXXXXX
Revenue Value |  | 2011: XXXXXXXX; 2012: XXXXXXXX; 2013: XXXXXXXX; 2014: XXXXXXXX; 2015: XXXXXXXX; 2016: XXXXXXXX
Pre 4/1/2016 | 1.381 | 2011: XXXXXXXX; 2012: XXXXXXXX; 2013: XXXXXXXX; 2014: XXXXXXXX; 2015: XXXXXXXX; 2016: XXXXXXXX
4/1/2016 to 10/1/2022 | 0.482 | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX
10/1/2022 to Term | 0 | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | 0
|  | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX
Combined Meter Reduction Fee |  | 2011: XXXXXXXX; 2012: XXXXXXXX; 2013: XXXXXXXX; 2014: XXXXXXXX; 2015: XXXXXXXX; 2016: XXXXXXXX
Pre 4/1/2016 | Electric | 2011: XXXXXXXX; 2012: XXXXXXXX; 2013: XXXXXXXX; 2014: XXXXXXXX; 2015: XXXXXXXX; 2016: XXXXXXXX
| Gas | 2011: XXXXXXXX; 2012: XXXXXXXX; 2013: XXXXXXXX; 2014: XXXXXXXX; 2015: XXXXXXXX; 2016: XXXXXXXX
4/1/2016 to 10/1/2022 |  | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX
Termination Fees |  | 2011 | 2012 | 2013 | 2014 | 2015 | 2016* | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023
Asset Value
| Electric | 2011: XXXXXXXX; 2012: XXXXXXXX; 2013: XXXXXXXX; 2014: XXXXXXXX; 2015: XXXXXXXX; 2016*: XXXXXXXX
| Gas | 2011: XXXXXXXX; 2012: XXXXXXXX; 2013: XXXXXXXX; 2014: XXXXXXXX; 2015: XXXXXXXX; 2016*: XXXXXXXX
| Total Assets | 2011: XXXXXXXX; 2012: XXXXXXXX; 2013: XXXXXXXX; 2014: XXXXXXXX; 2015: XXXXXXXX; 2016*: XXXXXXXX
Revenue |  | 2011: XXXXXXXX; 2012: XXXXXXXX; 2013: XXXXXXXX; 2014: XXXXXXXX; 2015: XXXXXXXX; 2016*: XXXXXXXX
| Prior to 4/1/2016 | 2011: XXXXXXXX; 2012: XXXXXXXX; 2013: XXXXXXXX; 2014: XXXXXXXX; 2015: XXXXXXXX; 2016*: XXXXXXXX
| After 4/1/2016 | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | 0
|  | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX
Grand Total |  | 2011: XXXXXXXX; 2012: XXXXXXXX; 2013: XXXXXXXX; 2014: XXXXXXXX; 2015: XXXXXXXX; 2016*: XXXXXXXX
| Prior to 4/1/2016 | 2011: XXXXXXXX; 2012: XXXXXXXX; 2013: XXXXXXXX; 2014: XXXXXXXX; 2015: XXXXXXXX; 2016*: XXXXXXXX
| After 4/1/2016 | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | 0
|  | 2011 | 2012 | 2013 | 2014 | 2015 | 2016* | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023
| Electric Module Asset Value | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX
| Gas Module Asset Value | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX
| One Year Revenue to Meter Minimum | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX
|  | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX
|  | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX
|  | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX
| Accelerated Refund of Credits if Termination | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX
|  | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX
|  | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX
| Annual Credit and Repayment | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX
|  | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX
Total Termination Costs (Jan 1) |  | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX
|  | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX
|  | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX
Effective Termination Costs |  | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX | XXXXXXXX

## Readfee (R)
| 2012-01-01 | 2012-02-01 | 2012-03-01 | Prices | 2012-04-01 | 2012-05-01 | 2012-06-01 | 2012-07-01 | 2012-08-01 | 2012-09-01 | 2012-10-01 | 2012-11-01 | 2012-12-01
TOTAL METERS PSE | XXXXXXX | XXXXXXX
ELECTRIC | XXXXXXX | XXXXXXX
GAS | XXXXXXX | XXXXXXX
Monthly Change | XXXXXXX | XXXXXXX | XXXXXXX |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PSE AMR DATA
Electric
CUK | XXXXXXX | XXXXXXX |  | XXXXXXX
CUM | XXXXXXX | XXXXXXX |  | XXXXXXX
DEK (dmd, kvr) | XXXXXXX | XXXXXXX |  | XXXXXXX
DEM | XXXXXXX | XXXXXXX
KVR | XXXXXXX | XXXXXXX
TDM | XXXXXXX | XXXXXXX
TDV | XXXXXXX | XXXXXXX
TOU (cum) | XXXXXXX | XXXXXXX
Gas | XXXXXXX | XXXXXXX
CUM | XXXXXXX | XXXXXXX
Other? | XXXXXXX | XXXXXXX
Total Meters | XXXXXXX | XXXXXXX | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | XXXXXXX | XXXXXXX | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
CELLNET INVOICE -- BILLABLE READS
Base AMR read - cum 1ph240V | XXXXXXX | XXXXXXX
Base AMR read - cum 1ph120V | XXXXXXX | XXXXXXX
1phTOU | XXXXXXX | XXXXXXX
1phDEM | XXXXXXX | XXXXXXX
Network | XXXXXXX | XXXXXXX
PolykWH | XXXXXXX | XXXXXXX
PolyVAR | XXXXXXX | XXXXXXX
PolyDEM | XXXXXXX | XXXXXXX
Gas | XXXXXXX | XXXXXXX
sum | XXXXXXX | XXXXXXX | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
sum w/o VARS | XXXXXXX | XXXXXXX | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LP Reads - BILLABLE
1ph | XXXXXXX | XXXXXXX
1phVAR | XXXXXXX | XXXXXXX
Polyphase LP - CUM -PolykWH | XXXXXXX | XXXXXXX
PolyVAR | XXXXXXX | XXXXXXX
ResGas | XXXXXXX | XXXXXXX
Gas (was Cigas) | XXXXXXX | XXXXXXX
| XXXXXXX | XXXXXXX
sum | XXXXXXX | XXXXXXX | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
sum w/o VARS | XXXXXXX | XXXXXXX | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Meter Count Cellnet - Prod Routes | XXXXXXX | XXXXXXX | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Invoiced Meter Read Counts | XXXXXXX | XXXXXXX | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Meter Count PSE - Prod Routes | XXXXXXX | XXXXXXX | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Delta - match on Mtr Rds Billing tab | XXXXXXX | XXXXXXX | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CELLNET INVOICE - NON-BILLABLE READS
Base AMR read - cum 1ph240V | XXXXXXX | XXXXXXX
Base AMR read - cum 1ph120V | XXXXXXX | XXXXXXX
1phTOU | XXXXXXX | XXXXXXX
1phDEM | XXXXXXX | XXXXXXX
Network | XXXXXXX | XXXXXXX
PolykWH | XXXXXXX | XXXXXXX
PolyVAR | XXXXXXX | XXXXXXX
PolyDEM | XXXXXXX | XXXXXXX
Gas | XXXXXXX | XXXXXXX
sum | XXXXXXX | XXXXXXX | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
sum w/o VARS | XXXXXXX | XXXXXXX | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LP Reads - NON-BILLABLE
1ph | XXXXXXX | XXXXXXX
1phVAR | XXXXXXX | XXXXXXX
Polyphase LP - CUM -PolykWH | XXXXXXX | XXXXXXX
PolyVAR | XXXXXXX | XXXXXXX
ResGas | XXXXXXX | XXXXXXX
Gas (was Cigas) | XXXXXXX | XXXXXXX
sum | XXXXXXX | XXXXXXX | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
sum w/o VARS | XXXXXXX | XXXXXXX | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cellnet LP Heard
Electric | XXXXXXX | XXXXXXX
Gas | XXXXXXX | XXXXXXX
Total | XXXXXXX | XXXXXXX | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
% Billed Heard | XXXXXXX | XXXXXXX | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
% Requested Billed | XXXXXXX | XXXXXXX | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Cellnet LP Perf.
Electric
Gas
Total
Percent Billed
MDW LP
CN Requested
1phkWH | XXXXXXX | XXXXXXX
1phVAR | XXXXXXX | XXXXXXX
PolykWH | XXXXXXX | XXXXXXX
PolyVAR | XXXXXXX | XXXXXXX
ResGas | XXXXXXX | XXXXXXX
CIGas | XXXXXXX | XXXXXXX
| XXXXXXX | XXXXXXX | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Conservation
1phkWH | XXXXXXX | XXXXXXX
1phVAR | XXXXXXX | XXXXXXX
PolykWH | XXXXXXX | XXXXXXX
PolyVAR | XXXXXXX | XXXXXXX
ResGas | XXXXXXX | XXXXXXX
CIGas | XXXXXXX | XXXXXXX
Load Research
1phkWH | XXXXXXX | XXXXXXX
1phVAR | XXXXXXX | XXXXXXX
PolykWH | XXXXXXX | XXXXXXX
PolyVAR | XXXXXXX | XXXXXXX
ResGas | XXXXXXX | XXXXXXX
CIGas | XXXXXXX | XXXXXXX
Revenue
1phkWH | XXXXXXX | XXXXXXX
1phVAR | XXXXXXX | XXXXXXX
PolykWH | XXXXXXX | XXXXXXX
PolyVAR | XXXXXXX | XXXXXXX
ResGas | XXXXXXX | XXXXXXX
CIGas | XXXXXXX | XXXXXXX
Starbucks
1phkWH | XXXXXXX | XXXXXXX
1phVAR | XXXXXXX | XXXXXXX
PolykWH | XXXXXXX | XXXXXXX
PolyVAR | XXXXXXX | XXXXXXX
ResGas | XXXXXXX | XXXXXXX
CIGas | XXXXXXX | XXXXXXX
Lease Costs | JAN | FEB | MAR |  | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
2011 | 14572.65 | 74414.25 | 30809.36
2010 | 2253.43 | 0 | 70591.97 |  | 22312.12 | 1576.12 | 6931.73 | 2117.74 | 18192.63 | 7531.7 | 3168.5 | 2351.66 | 23484.25
2009 | 25075.84 | 97065.76 | 2534 |  | 12056.19 | 22982.5 | 3587.56 | 2660.57 | 12320.69 | 7949.72 | 24084.08 | 534.34 | 15991.18
2008 | 12551.56 | 6462.37 | 39860.85 |  | 8574 | 1405.27 | 68481.74 | 1600.6 | 989.11 | 16332.15 | 6518.07 | 1527.91 | 8828.51
2007 | 2533 | 12189 | 27691 |  | 6945 | 8469.56 | 54694.73 | 3465.99 | 1974.51 | 5375.42 | 3065.35 | 17032.82 | 36407.92
2006 | 6917 | 1075 | 8533 |  | 10408 | 53534 | 3214 | 4539 |  | 14599 | 16814 | 1064
2005 | 6595 | 11468 | 2267 |  | 10042 | 993 | 4326 | 52997 | 13483 | 1005 | 1531 | 20250 | 29075
2004 | 12393 | 1826 | 17652 |  | 10020 | 1362 | 3266 |  | 1374 | 6436 | 6801 | 15269 | 25588
BILL
Read | XXXXXXX | XXXXXXX | XXXXXXX
Fees
Other Receivables
Demand Credits | XXXXXXX | XXXXXXX
LP Credits | XXXXXXX | XXXXXXX
PSE Monthly Credit | XXXXXXX | XXXXXXX
total | XXXXXXX | XXXXXXX | XXXXXXX |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| XXXXXXX | XXXXXXX | XXXXXXX |  | -1.3972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| XXXXXXX | XXXXXXX | XXXXXXX
% change reads | XXXXXXX | XXXXXXX | XXXXXXX |  | -100% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| XXXXXXX | XXXXXXX | XXXXXXX
| XXXXXXX | XXXXXXX | XXXXXXX |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!

## Pole Attachments
CM/MCC SITE RENTAL/LEASE REIMBURSEMENTS (Receivables)
thru July
Lessor | CM Name / Description | For What | TERM | 2008 | 2009 | 2010 | Average | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
Seattle City Light | MCC & CM pole attachments. | MCC Pole attachments less energy charges (12.84% tax) | Annual lease Jan-Dec? | 129950.37 | 151921.97 | 108914.09
3806.37
Seattle City Light | Mill Creek CM site lease | 1 comm. tower location | Annual lease Jan-Dec | 12602.95 | 13107.07 | 13632.37
SBA | Segwick CM site lease | [a.k.a. "Locker Road" site] | Monthly | 5165.4 | 5320.32 | 3196.62
City of Poulsbo | Poulsbo CM land lease | Annual fee | Annual fee April 1 - March 31 | 6934.61 | 4061.65 | 4142.88
VoiceStream/T-Mobile | Poulsbo CM site lease | Annual lease | Annual fee April 1 - March 31 | 2756.85 | 2811.99 | 2868.99
VoiceStream/T-Mobile | Paine Field | Annual lease | Annual Lease (Feb) | 12895.76 | 13282.63 | 13681.11
Comcast (was AT&T) | Oak Harbor CM site lease |  | Annual fee March 1 - Feb 28 | 2400 | 2400 | 2400
Tanner Electric | Bubba Hill CM site lease | Annual CM Lease is $1500/yr | Annual Lease (jan) |  | 1500
" " | MCC pole attachments. | MCC Pole attachments less energy charges | Annual Lease (jan) |  | 2222.64 | 2436
Ratelco/Crista | Crista (Shoreline) CM site lease |  | Monthly | 8571.04 | 9715.61 | 5331.24 | Double billed July 2009
Snohomish PUD | MCC pole attachments. |  | Annual (march) | 43287.22 | 41588.4
" " | MCC Pole contact Fees |  | (march & Oct) | 6852.44 | 7232.16
Verizon | MCC's on Snohomish Poles | Annual Pole Attachment fees |  | 9050 | 10298.89
Crown Castle (Was Global Signal) | Clearview CM (Phase V) | New Phase V CM in Snohomish County | Monthly | 9986.88 | 11135.2 | 6119.26 | Double Billed July 2009
Elmhurst Mutual Power | MCC pole attachment | $ per MCC times # MCCs | Annual ? | 200.2 | 157 | 128
SpectraSite | Lake Serene CN | Annual CM Lease | Annual ? | 17765.07 | 18475.67
SpectraSite | Chehalis CM | Annual CM Lease | Annual ? | 11843.4 | 12317.14 | 12317.14
SpectraSite | Lake Stevens CM | Annual CM Lease | Annual ? | 11387.88 | 24338.18
SpectraSite | Ranier CM | Annual CM Lease | Annual ? |  | 11843.39
Comcast (was AT&T) | Gig Harbor CM | Annual CM Lease | Annual ? | 15903.84 | 7895.6 | 8211.42
American Tower | Ford Hill CM | CM Lease | Monthly | 12634.56 | 12824.04 | 7480.69
City of Tacoma | MCC pole attachments. | streetlight mounted MCC's | Annual | 13005.5 | 305.64
" " " | License Fee | Annual License Fee of 5% of Annual Revenue |  | 30212.75 | 30449.44
Tacoma Public Utilities | MCC Pole Attachment |  |  | 237.72 | 6661.4 | 7605.18
Peninsula Power & Light | MCC pole attachments. | Annual |  | 12649.5 | 12649.5 | 12942.74
City of Centralia | MCC Pole Attachmet | Annual |  | 170.1 | 178.65
TOTALS |  |  | Totals | 376464.04 | 418500.55 | 211407.73 | 335457.44 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  | PSE Resp = 50% | 188232.02 | 209250.275 | 105703.865
181206.6257
|  |  |  | 15686.0017 | 17437.5229 | 15100.5521
| AVG per Month | 16074.6922

## JCTCO (R)
COST ELEMENTS - PSE
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
|  |  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 6 | 11 | 12 | 13
| Amount/Rate | Quantity | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2016 | 2021 | 2022 | 2023
Network hardware/software and programs
Meter Costs
Electric
Residential Meters | XXXXXX | (GA tab) |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Commercial Meters | XXXXXX | (GA tab) |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Electric Residential Meter Installation | XXXXXX | (GA tab) |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Electric Commercial Meter Installation | XXXXXX | (GA tab) |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Gas
Residential Meters | XXXXXX | (GA tab) |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Commercial Meters | XXXXXX | (GA tab) |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Gas Residential Meter Installation | XXXXXX | (GA tab) |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Gas Commercial Meter Installation | XXXXXX | (GA tab) |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Total Meter Costs |  |  |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Battery Expenses
Battery Costs (Purchase for Replacement Program ) | XXXXXX |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Battery Costs (Purchases for Replacement-non program years) | XXXXXX |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Disposal | XXXXXX |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Avg. Battery CPU (Replacement) | XXXXXX |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Labor Costs | XXXXXX |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Honeywell | XXXXXX |  | 1 1 2011: XXXXXX
Seal Costs | XXXXXX | (GA tab) | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
3rd Party Pole Attachment Leases & Energy Usage |  |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
EA annual Maintenace fee($275K/yr) |  |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Server hardware & software maint. incl sys security(1 analyst) | XXXXXX | 1 | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Total |  |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Operation expenses
Monthly Read fees
Electric - Weighed Average | XXXXXX |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Gas Weighted Average | XXXXXX |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Total Monthly Read Fees | XXXXXX |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Infrastructure – Leased office space reimbursements |  |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Manual Meter Reading expenses - Lead expense
Other Meter Reading expenses (Scheduling)
Downtime, outage and failures expenses (500/month) | XXXXXX |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Performance Analysis (Customer Services expenses, dataraker) |  |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
ZCON Field Services Reimbursements |  |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Meter Shop Expenses | XXXXXX |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Field Expenses -Meter (Includes $8 mod exchange) | XXXXXX |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Gas Operations and Gas Meter Exchange | XXXXXX |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Customer Service Expenses | XXXXXX |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
DataRaker (Cost is per meter per month) | XXXXXX |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
DataRaker (L+G share per month) | XXXXXX |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Consulting costs (Monthly) | XXXXXX |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Technology training - Field (8hr day 2x/year - 12 people) Field O&M
People | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Lunch | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Auditing (internal and external)
Personel
Information technology related personnel - Analysts/Engineers | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Corporate Level Management time | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Future O&M Costs |  |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Disaster Recovery
Pole top attachment inventory costs | 0
Additional Meter Reading
Module Testing cost | 43
Electric | 35.35 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Gas | 53 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Module O&M
Electricity (pole attachments)
Additional Staffing:
Management
Analysts
Engineers
Future Network/Hardware/Programs
Network
Network Instatllation and Integration
Network Licenses (FCC and other)
Software Licenses
Server Costs - Vendor costs
Telecom Costs
Module Costs
Electric
Gas
Outage Management Interface (no current charge until OMS migration)
Pole Attachments
CellMasters |  | XXXXXX
MCC's |  | XXXXXX
Repeaters |  | XXXXXX
Connectors |  | XXXXXX
TOP's |  | XXXXXX
Long term expenses
Replacement
Future upgrade or scalability expenses
Decommissioning expenses
Asset Management Interface
Warranties and licenses
License tracking - compliance
Migration expenses?
Risks: susceptibility to vulnerabilities, availability of upgrades, patches and licensing policies
TOTALS: |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Price per Read per Year: |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Net Present Value |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Per Read Fees - Weighted
Electric & Gas |  |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Gas |  |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Average Read Fee |  |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
PSE Costs in addition to Monthly L+G Read fees |  |  |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
Assumptions
Escalation Rate (Other) | XXXXXX
Escalation Rate L+G Fees | XXXXXX |  |  |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
COLA & CPI | XXXXXX |  |  |  | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX | XXXXXX
XXXXXX
Pole Attachment Leases (Monthly Avg 2008-2010) | XXXXXX | (pole attachement tab)
XXXXXX
XXXXXX
XXXXXX
XXXXXX
XXXXXX
XXXXXX
XXXXXX
XXXXXX | XXXXXX
Monthly Lease Reimbursements from L+G (2006 agreement) | XXXXXX
XXXXXX
Note on AP18: jcummi: sum C64+C72+C44+C34
Note on AQ72: jcummi: For March only - includes Manual Reads for Jeff Co at 10,167.84 discounted by $2501.29 = $7,666.55

## IT L+G Read Fee Forecast (R)
L&G CONTRACT FINANCIAL PROJECTIONS
V's Forecast
Year: | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 |  | Organization
|  | Actual | Forecast & Actual | Forecast | Forecast | Forecast | Forecast
Contract Invoice Sum (Read Fees) (A) |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
Acutal Credits (per contract - not included in any calculations) |  | XXXXXXX
Payment to L+G per contract begin April 1, 2016
Accounting Based Allowed Credits ( B ) |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
"BUDGET" after Allowed Credits |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
DataRaker Credits (C) (per contract not included in any calculations) |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | [24 empty] | Theresa Burch's Budget
Energy Efficiency & Load Research Allocations (LP+Demand Credits) (D) |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | [23 empty] | #DIV/0! | Energy Effic.
IT Portion less Departmental Allocations (row 16) |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | #DIV/0!
Proposal (Calculated by JC) |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
L+G's Acutal Invoice Totals: |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | Total Read costs less contracted credit amounts
Budget Amount being transferred to IT in 2013 |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
CC budget in 2012** |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
Shortfall** |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
Pre- CPI adjustment |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
Savings |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
A. Key Assumptions:
Electric and Gas growth rates are PSE's corp planning rates. Updated 6/12
B. Key Assumptions:
2013 Contract price increase is based on 45% of the Seattle/Tacoma/Bremerton June-to-June 12 month percentage change to the CPI-U (not seasonally adjusted and all items less shelter), per contract.
Years 2013-2016: Contract Escalator is PSE's Corp planning CPI assumptions projection each year on contract prices.
Electric meter and gas meter growth is same as A.
C. Based on memo sent by Mike Stranik on 8/1/11.
D. Compensates PSE for Gas Meter data analysis performed by DataRaker to help identify slowed or stopped gas meters/modules quicker.
Amount adjusts annually with CPI-U as outlined in contract. Credits go to Theresa Burch's cost center. Separte billing invoice.
E. LP Credits based on average monthly credit of $14k in past 12 months. L+G has indicated that the Performance Metric cannot be met, therefore credits are assumed to continue but at a lower rate due to two-way (AMI) demonstrations being deployed. Credits go to Energy Efficiency and Load Research.
F. Field Work Reimbursements are based on average volumes seen over past 24 months. We would expect that the volumes could decrease as defective modules are replaced with new modules. Field work fees per unit increase annually with CPI-U as outlined in contract.
G. This total represents the portion of the L+G Bill that Customer Care would have paid for. It is the total invoice less the portion paid by Energy Efficiency and Rates, and Field Work Reimbursements.
***Year 2016: Effective April 1, 2016, PSE takes ownership of Network and read fee drops to $.525 per read, subject to agreement on this rate in scheduled contract discussion for 2014.

## L+G Forecast (R)
(Updated June 2013) | 2010-01-01 | 2010-02-01 | 2010-03-01 | 2010-04-01 | 2010-05-01 | 2010-06-01 | 2010-07-01 | 2010-08-01 | 2010-09-01 | 2010-10-01 | 2010-11-01 | 2010-12-01 |  | 2011-01-01 | 2011-02-01 | 2011-03-01 | 2011-04-01 | 2011-05-01 | 2011-06-01 | 2011-07-01 | 2011-08-01 | 2011-09-01 | 2011-10-01 | 2011-11-01 | 2011-12-01 |  | 2012-01-01 | 2012-02-01 | 2012-03-01 | 2012-04-01 | 2012-05-01 | 2012-06-01 | 2012-07-01 | 2012-08-01 | 2012-09-01 | 2012-10-01 | 2012-11-01 | 2012-12-01 |  | 2013-01-01 | 2013-02-01 | 2013-03-01 | 2013-04-01 | 2013-05-01 | 2013-06-01 | 2013-07-01 | 2013-08-01 | 2013-09-01 | 2013-10-01 | 2013-11-01 | 2013-12-01 |  | 2014-01-01 | 2014-02-01 | 2014-03-01 | 2014-04-01 | 2014-05-01 | 2014-06-01 | 2014-07-01 | 2014-08-01 | 2014-09-01 | 2014-10-01 | 2014-11-01 | 2014-12-01 |  | 2015-01-01 | 2015-02-01 | 2015-03-01 | 2015-04-01 | 2015-05-01 | 2015-06-01 | 2015-07-01 | 2015-08-01 | 2015-09-01 | 2015-10-01 | 2015-11-01 | 2015-12-01 |  | 2016-01-01 | 2016-02-01 | 2016-03-01 | 2016-04-01 | 2016-05-01 | 2016-06-01 | 2016-07-01 | 2016-08-01 | 2016-09-01 | 2016-10-01 | 2016-11-01 | 2016-12-01 |  | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 |  | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 |  | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 |  | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 |  | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 |  | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | time axis 2023-01-01 to 2026-12-01
PSE Meters - all meters
Electric | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
Gas | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
Total | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
Growth (month over month) | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
12 mo avg mo Growth | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
[13 empty] | 0.8275% | [12 empty] | Annuual Gr. | [12 empty] | Annuual Gr. | [12 empty] | Annuual Gr.
Elec Growth Forecasted | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
Gas GrowthForecasted | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
% electric | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
% electric reads | [39 empty] | 0.5873 | 0.5872 | 0.5869 | 0.5827 | 0.5826 | 0.5821 | 0.582 | 0.5818 | 0.5817 | 0.5816 | 0.5815 | 0.5813 |  | 0.5812 | 0.581 | 0.5809 | 0.5808 | 0.5806 | 0.5805 | 0.5804 | 0.5803 | 0.5802 | 0.5801 | 0.58 | 0.5799 |  | 0.5798 | 0.5797 | 0.5796 | 0.5795 | 0.5794 | 0.5793 | 0.5792 | 0.5792 | 0.5791 | 0.579 | 0.5789 | 0.5788 |  | 0.5787 | 0.5786 | 0.5785 | 0.5784 | 0.5783 | 0.5782 | 0.5781 | 0.578 | 0.5779 | 0.5778 | 0.5777 | 0.5776 |  | 0.5775 | 0.5774 | 0.5773 | 0.5772 | 0.5771 | 0.577 | 0.5769 | 0.5768 | 0.5766 | 0.5765 | 0.5764 | 0.5763 |  | 0.5762 | 0.5761 | 0.576 | 0.5758 | 0.5757 | 0.5756 | 0.5755 | 0.5753 | 0.5752 | 0.5751 | 0.575 | 0.5748 |  | 0.5747 | 0.5746 | 0.5745 | 0.5743 | 0.5742 | 0.5741 | 0.5739 | 0.5738 | 0.5737 | 0.5736 | 0.5734 | 0.5733 |  | 0.5732 | 0.573 | 0.5729 | 0.5728 | 0.5727 | 0.5725 | 0.5724 | 0.5723 | 0.5722 | 0.572 | 0.5719 | 0.5718 |  | 0.5716 | 0.5715 | 0.5714 | 0.5713 | 0.5711 | 0.571 | 0.5709 | 0.5708 | 0.5706 | 0.5705 | 0.5704 | 0.5703 |  | 0.5701 | 0.57 | 0.5699 | 0.5698 | 0.5696 | 0.5695 | 0.5694 | 0.5693 | 0.5691 | 0.569 | 0.5689 | 0.5688 |  | 0.5686 | 0.5685 | 0.5684 | 0.5683 | 0.5682 | 0.5681 | 0.568 | 0.5679 | 0.5678 | 0.5677 | 0.5676 | 0.5675 | 0.5674 | 0.5673 | 0.5672 | 0.5671 | 0.567 | 0.5669 | 0.5668 | 0.5667 | 0.5666 | 0.5665 | 0.5664 | 0.5663 | 0.5662 | 0.5661 | 0.566 | 0.5659 | 0.5658 | 0.5657 | 0.5656 | 0.5655 | 0.5654 | 0.5653 | 0.5652 | 0.5651 | 0.565 | 0.5649 | 0.5648 | 0.5647 | 0.5646 | 0.5645 | 0.5644 | 0.5643 | 0.5642 | 0.5641 | 0.564 | 0.5639
CN Meters
Total | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
Electric | [31 empty] | 1116999.6413 | 1117943.8653 | 1118603.9833 | 1119341.5481 | 1120134.7572 | 1120547.1413 | 1121607.1896 |  | 1122202.3244 | 1123227 | 1123787.357 | 1104034.8626 | 1105285.4019 | 1105749.2521 | 1106785.0339 | 1107868.8567 | 1109002.5532 | 1110187.3413 | 1111422.4869 | 1112706.3136 |  | 1114027.7438 | 1115387.1251 | 1116784.4502 | 1118218.8716 | 1119696.8868 | 1121217.8808 | 1122780.8128 | 1124384.3342 | 1126026.6587 | 1127705.0729 | 1129416.8232 | 1131159.1002 |  | 1132921.9525 | 1134703.1318 | 1136500.5528 | 1138312.368 | 1140136.7327 | 1141971.7569 | 1143815.7644 | 1145667.2731 | 1147525.0874 | 1149388.619 | 1151257.353 | 1153130.8607 |  | 1155011.2958 | 1156897.9161 | 1158789.7921 | 1160685.9317 | 1162585.3976 | 1164487.347 | 1166391.2262 | 1168296.548 | 1170202.8661 | 1172109.8477 | 1174017.0567 | 1175923.9768 |  | 1177827.8657 | 1179728.3672 | 1181625.1143 | 1183517.7461 | 1185405.8138 | 1187288.8249 | 1189166.349 | 1191038.0514 | 1192903.7821 | 1194763.6867 | 1196617.9453 | 1198466.7725 |  | 1200310.0093 | 1202147.8712 | 1203980.6384 | 1205808.7751 | 1207632.7793 | 1209453.1792 | 1211270.4829 | 1213085.0707 | 1214897.2061 | 1216706.9347 | 1218514.3022 | 1220319.3704 |  | 1222122.1377 | 1223922.7805 | 1225721.641 | 1227519.0987 | 1229315.5837 | 1231111.5782 | 1232907.555 | 1234703.8368 | 1236500.6093 | 1238297.7907 | 1240095.4369 | 1241893.7273 |  | 1243692.8142 | 1245492.9781 | 1247294.4787 | 1249097.5479 | 1250902.39 | 1252709.1794 | 1254518.0754 | 1256329.2104 | 1258142.7449 | 1259958.7258 | 1261777.1848 | 1263598.0867 |  | 1265421.3415 | 1267246.7269 | 1269073.8777 | 1270902.2604 | 1272731.4223 | 1274561.0344 | 1276390.8743 | 1278220.7067 | 1280050.3338 | 1281879.5767 | 1283708.2888 | 1285536.3411 |  | 1287363.6132 | 1289190.1518 | 1291016.1165 | 1292841.8204 | 1294667.4763 | 1296493.1988 | 1298319.0395 | 1300144.9997 | 1301971.1023 | 1303797.3608 | 1305623.8106 | 1307450.4916 |  | 2023-01-01: 1309277.3757; 2023-02-01: 1311104.4816; 2023-03-01: 1312931.8066
Gas | [31 empty] | 786631.4916 | 787568.6669 | 788326.1395 | 789275.7366 | 790125.9785 | 790692.4712 | 791821.8361 |  | 792573.5296 | 793313 | 794496.4974 | 795312.9856 | 796583.6949 | 797434.5145 | 798692.8749 | 799981.6578 | 801300.9508 | 802648.9193 | 804023.121 | 805420.8705 |  | 806840.9355 | 808280.9741 | 809739.3558 | 811214.0562 | 812704.8009 | 814211.9775 | 815735.6051 | 817276.0443 | 818832.7819 | 820403.3934 | 821986.4626 | 823580.8369 |  | 825184.6303 | 826797.1053 | 828417.7713 | 830045.9762 | 831681.6964 | 833325.1672 | 834976.5684 | 836636.3948 | 838305.1195 | 839983.1424 | 841670.9199 | 843369.1012 |  | 845078.1805 | 846798.1771 | 848528.4476 | 850267.8933 | 852014.5988 | 853766.1215 | 855519.7274 | 857273.3417 | 859026.0101 | 860778.6523 | 862531.5306 | 864284.9945 |  | 866039.8677 | 867796.3025 | 869554.4064 | 871314.8331 | 873077.5891 | 874842.6703 | 876610.3322 | 878380.5303 | 880153.1868 | 881928.5076 | 883706.3555 | 885486.7432 |  | 887269.8335 | 889055.6092 | 890844.0637 | 892635.2274 | 894429.0706 | 896225.5937 | 898024.5988 | 899826.0406 | 901629.8194 | 903435.751 | 905243.619 | 907053.3541 |  | 908864.799 | 910677.8453 | 912492.4207 | 914308.5485 | 916126.2147 | 917945.4852 | 919766.428 | 921589.1564 | 923413.7581 | 925240.3848 | 927069.0715 | 928900.0255 |  | 930733.3981 | 932569.2981 | 934407.7722 | 936248.9091 | 938092.671 | 939939.0707 | 941788.0477 | 943639.5883 | 945493.6137 | 947350.0446 | 949208.6689 | 951069.4016 |  | 952931.9703 | 954796.246 | 956662.1691 | 958529.7073 | 960398.8731 | 962269.6573 | 964142.1105 | 966016.2846 | 967892.2486 | 969770.1086 | 971649.9579 | 973531.9708 |  | 975416.1991 | 977302.746 | 979191.6846 | 981082.9891 | 982976.6289 | 984872.4911 | 986770.4331 | 988670.2788 | 990571.8119 | 992474.7294 | 994378.8117 | 996283.963 |  | 2023-01-01: 998190.2253; 2023-02-01: 1000097.5356; 2023-03-01: 1002005.848
Growth | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
Percent of All Meters | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
CN Invoice
Daily Reads | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
1ph240V | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
1ph120V | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
1phTOU | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
1phDEM | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
Network | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
PolykWH | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
PolyVAR | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
PolyDEM | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
Gas | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
sum | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
sum w/o VARS | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
LP Reads
1ph | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
1phVAR | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
PolykWH | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
PolyVAR | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
ResGas | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
Gas (was Cigas) | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
sum | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
sum w/o VARS | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
Total Invoiced Sum | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
Total Sum | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
Daily Reads
1ph240V | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
1ph120V | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
1phTOU | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
1phDEM | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
Network | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
PolykWH | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
PolyVAR | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
PolyDEM | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
Gas | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
Sum Daily | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
LP Reads
1ph | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
1phVAR | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
PolykWH | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
PolyVAR | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
ResGas | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
Gas (was Cigas) | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
Sum LP | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
LP meters billed at Downgraded Rates | [39 empty] | 4557.04 | 4752.76 | 4831.58 | 4915.64 | 5285.09 | 5300 | 5300 | 5300 | 5300 | 5300 | 5300 | 5300 |  | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 |  | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 |  | 4500 | 4500 | 4500
Actual Invoice sum (prior to credits) | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
Forecasted Amount | [20 empty] | 2598570.6631 |  | 2594845.3365 | 2599756.1792 | 2600725 |  | 2652839.2364 | 2655697.3701 | 2656953.0771 | 2658950.208 | 2660546.7606 | 2657326.0206 | 2665851.5998 | 2670673.4784 | 2672932.147 | 2675320.561 | 2678085.1396 | 2680879.5636 |  | 2709423.6567 | 2712430.9398 | 2715504.5346 | 2719094.0476 | 2721658.0498 | 2725272.8969 | 2728996.4931 | 2732379.8295 | 2735792.2042 | 2739339.8718 | 2743024.0504 | 2746814.5856 |  | 2780417.1988 | 2784451.9643 | 2788565.8082 | 2792772.5491 | 2797090.8283 | 2801522.6299 | 2806000.5748 | 2810519.0564 | 2815134.5468 | 2819815.9126 | 2824569.1478 | 2829386.5189 |  | 2865575.8999 | 2870537.6893 | 2875538.6255 | 2880565.7888 | 2885624.5456 | 2890719.3946 | 2895816.0988 | 2900939.991 | 2906105.6669 | 2911269.1276 | 2916463.3034 | 2921684.0307 |  | 2960195.0903 | 2965527.0047 | 2970875.3423 | 1078462.875 | 1080414.825 | 1082370.975 | 1084331.85 | 1086291.15 | 1088254.125 | 1090211.85 | 1092174.3 | 1094136.225 |  | 1124476.5532 | 1126486.586 | 1128495.5416 | 1130501.8043 | 1132509.6827 | 1134513.791 | 1136518.4379 | 1138519.3146 | 1140519.1141 | 1142515.682 | 1144513.8658 | 1146506.125 |  | 1178887.3098 | 1180930.0684 | 1182973.9327 | 1185014.4799 | 1187055.5799 | 1189096.68 | 1191135.5686 | 1193175.563 | 1195214.4517 | 1197253.8932 | 1199293.8875 | 1201331.1177 |  | 1235905.3891 | 1237998.8604 | 1240093.4244 | 1242185.7172 | 1244279.7562 | 1246372.6169 | 1248468.3593 | 1250564.0589 | 1252663.7331 | 1254760.6111 | 1256862.5565 | 1258962.8413 |  | 1296008.6677 | 1298174.705 | 1300341.3259 | 1302509.6974 | 1304681.57 | 1306856.3602 | 1309033.4845 | 1311214.11 | 1313396.486 | 1315582.9467 | 1317772.325 | 1319962.8703 |  |  |  | 1359687.9262 | 1361946.6536 | 1364208.9816 | 1366470.1094 | 1368735.4379 | 1371001.3664 | 1373266.6948 | 1375535.0237 | 1377800.9522 | 1380072.8816 |  | 1427255.6042 | 1429592.4286 | 1431932.9582 | 1434273.4879 | 1436616.4878 | 1438963.8105 | 1441309.2806 | 1443655.3682 | 1446003.3086 | 1448353.1015 | 1450703.512 | 1453053.9226 |  | 1498846.6498 | 1501265.9405 | 1503691.5911 | 1503692.5911 | 1503693.5911 | 1503694.5911 | 1503695.5911 | 1503696.5911 | 1503697.5911 | 1503698.5911 | 1503699.5911 | 1503700.5911 | 1503701.5911 | 1503702.5911 | 1503703.5911 | 1503704.5911 | 1503705.5911 | 1503706.5911 | 1503707.5911 | 1503708.5911 | 1503709.5911 | 1503710.5911 | 1503711.5911 | 1503712.5911 | 1503713.5911 | 1503714.5911 | 1503715.5911 | 1503716.5911 | 1503717.5911 | 1503718.5911 | 1503719.5911 | 1503720.5911 | 1503721.5911 | 1503722.5911 | 1503723.5911 | 1503724.5911 | 1503725.5911 | 1503726.5911 | 1503727.5911 | 1503728.5911 | 1503729.5911 | 1503730.5911 | 1503731.5911 | 1503732.5911 | 1503733.5911 | 1503734.5911 | 1503735.5911 | 1503736.5911
Difference | [20 empty] | 11306.3011 |  | -274.9801 | -3981.1027 | 3810.9094 |  | 6094.6694 | 3990.8765 | 2981.5088 | 2258.6319 | 8859.842 | 2407.9273 | 9143.6061 | 12770.3922 | 14864.9183 | 14643.824 | 14300.3729 | 17084.3522 |  | 21048.0035 | 19321.3322 | 17504.4177 | 45139.6153 | 46462.946 | 39792.4418 | 40485.961 | 40770.11 | 40951.6416 | 41112.6995 | 41281.7054 | 41499.7755 |  | 43438.4401 | 43398.6318 | 43335.528 | 43294.5449 | 43294.4805 | 43321.1833 | 43472.3803 | 43571.8304 | 43681.6402 | 43768.6259 | 43849.4649 | 43911.1014 |  | 44005.6217 | 44063.7806 | 44120.374 | 44188.4291 | 44265.1279 | 44362.1158 | 44440.0066 | 44514.266 | 44611.2704 | 44671.9518 | 44755.5719 | 44829.7295 |  | 45462.2782 | 45545.0261 | 45609.3967 | 15931.125 | 15957.375 | 15984.15 | 16010.4 | 16035.6 | 16066.05 | 16088.625 | 16117.5 |  |  | 16589.7724 | 16617.2407 | 16644.1704 | 16672.1773 | 16699.107 | 16726.5753 | 16754.5822 | 16782.0504 | 16810.0573 | 16833.2169 | 16863.9167 | 16889.2307 |  | 17364.2772 | 17390.8137 | 17420.1144 | 17444.4396 | 17474.846 | 17502.4882 | 17529.0247 | 17557.2198 | 17582.0977 | 17611.9513 | 17639.0407 | 17665.0243
Performance Credits:
DEMAND CREDITS INCL in INVOICE | [6 empty] | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  |  |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  |  | XXXXXXX | XXXXXXX | [23 empty] | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
LP CREDITS INCL in INVOICE | [6 empty] | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  |  |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
ORR/RVA Performance Credits | [36 empty] | -58.35 | -0.9 |  | -60.6 | -32.55 | -5.55 | -0.3 | -8.25 | -1 | -1 | -1 | -1 | -1 | -1 | -1 |  | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 |  | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 |  | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 |  | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 |  | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 |  | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 |  | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | bar: 2023-01-01 to 2026-12-01
Total Energy Eff Credits in Invoice | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total IT Credits in Budget | [26 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -58.35 | -0.9 |  | -60.6 | -32.55 | -5.55 | -0.3 | -8.25 | -1 | -1 | -1 | -1 | -1 | -1 | -1 |  | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 |  | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 |  | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 |  | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 |  | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 |  | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 |  | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | bar: 2023-01-01 to 2026-12-01
Contract Credits/Payback:
Actual Credits/Payback per contract | [16 empty] | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  |  |  |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
Allowable Credits per Accounting Rules | [16 empty] | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX
Departmental Allocations:
Load Research & EEI | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
Load Research & EEI less credits | [26 empty] | -31841.51 | -12956.45 | -31946.01 | -37532.78 | -31739.0331 | -32296.58 | -32122.16 | -32180.82 | -31923.8916 | -31266.92 | -28000.33 | -27950.5091 |  | -28908.6825 | -28844.5548 | -28420.49 | -28210.79 | -27238.06 | -30771.8414 | -30720.7831 | -30649.2559 | -30604.3543 | -30611.9083 | -30658.2071 | -30678.6761 |  | -28909.6031 | -29003.5939 | -29097.3885 | -29183.5475 | -29255.4552 | -35319.7272 | -35366.5264 | -35420.3531 | -35480.2068 | -35547.0881 | -35619.9963 | -35700.5401 |  | -42242.2734 | -42315.9875 | -42395.9936 | -42469.7076 | -42543.4217 | -42617.949 | -42691.663 | -42772.4823 | -42846.1964 | -42927.0157 | -43000.7298 | -43081.3506 |  | -43652.8143 | -43727.3663 | -43816.0896 | -3390.45 | -3396.225 | -3402 | -3408.825 | -3415.65 | -3421.425 | -3428.25 | -3434.55 | -3440.85 |  | -3535.8696 | -3542.3327 | -3548.7959 | -3554.7204 | -3561.7221 | -3567.6467 | -3574.6484 | -3580.5729 | -3587.036 | -3594.0378 | -3599.9623 | -3606.4254 |  | -3708.4776 | -3715.1117 | -3721.193 | -3728.3799 | -3734.4612 | -3741.0953 | -3747.7295 | -3753.8108 | -3760.9977 | -3767.079 | -3773.7131 | -3780.3473 |  | -3888.8485 | -3895.6621 | -3902.4757 | -3909.2892 | -3915.535 | -3922.9164 | -3929.1622 | -3935.4079 | -3942.7893 | -3949.0351 | -3956.4165 | -3962.6622 |  | -4079.4093 | -4086.4116 | -4092.8303 | -4099.8326 | -4106.8349 | -4114.4207 | -4120.8394 | -4128.4252 | -4134.844 | -4142.4298 | -4148.8485 | -4155.8508 |  | -4281.0207 | -4288.2217 | -4296.0228 | -4303.2239 | -4310.4249 | -4317.0259 | -4324.827 | -4331.428 | -4339.2291 | -4346.4301 | -4354.2313 | -4361.4323 |  | -4495.7931 | -4502.5862 | -4510.6144 | -4518.0251 | -4525.4357 | -4533.4639 | -4540.8746 | -4548.2852 | -4555.6959 | -4563.1065 | -4571.1347 | -4578.5454 | 0 | -4722.832 | -4730.4639 | -4738.7317 | -4745.7275 | -4787.0666 | -4832.8576 | -4881.8285 | -4932.0714 | -4987.4022 | -5047.8209 | -5113.9634 | -5185.8298 | -5265.3281 | -5310.4831 | -5391.8893 | -5480.9273 | -5578.2332 | -5646.2837 | -5715.6062 | -5785.5646 | -5861.247 | -5938.8373 | -6017.6995 | -6097.8338 | -6179.24 | -6259.3742 | -6341.4164 | -6428.5465 | -6516.3126 | -6603.4426 | -6688.6648 | -6776.4308 | -6865.4689 | -6956.4149 | -7047.9969 | -7140.8508 | -7235.6127 | -7330.3746 | -7427.0445 | -7524.9864 | -7623.5642 | -7724.05 | -7825.1717 | -7928.2015 | -8032.5032 | -8137.4409 | -8243.6505 | -8352.4041
Total Projected Read Fee less anticipated Performance Credits and any credit/payback amounts | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
Jeff Co. Add'l Charges | [41 empty] | 7666.55
IT Budget Amount (Total Read Costs less dept. allocations | [13 empty] | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX |  | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
Forecasted | [13 empty] | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | [14 empty] | 2510485 | 2493441 | 2496401 | 2473673.2255 | 2463075.0236 | 2484836.4259 | 2488024.4914 | 2491334.3775 | 2494720.4399 | 2498208.4884 | 2501806.7516 | 2505491.5631 | [68 empty] | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX | XXXXXXX
Accrued | [35 empty] | Other Credits |  |  |  | 2392787 | 2493237 | 2483232 | 2458672 | 2459239
[36 empty] | -223354.92 |  |  |  | 77598.3575 | -18606.0806 | 4008.0535 | -3174.061 | -2644.9696
[27 empty] | 2012 | [5 empty] | L+G Actual Invoice Totals will be: | [6 empty] | 2013 | [5 empty] | L+G Actual Invoice Totals will be: | [6 empty] | 2014 | [5 empty] | L+G Actual Invoice Totals will be: | [6 empty] | 2015 | [5 empty] | L+G Actual Invoice Totals will be: | [6 empty] | 2016 |  |  | 2016 Price post April 1. |  |  | L+G Actual Invoice Totals will be: | [6 empty] | 2017 | [5 empty] | L+G Actual Invoice Totals will be: | [6 empty] | 2018 | [5 empty] | L+G Actual Invoice Totals will be: | [6 empty] | 2019 | [5 empty] | L+G Actual Invoice Totals will be: | [6 empty] | 2020 | [5 empty] | L+G Actual Invoice Totals will be: | [6 empty] | 2021 | [5 empty] | L+G Actual Invoice Totals will be: | [6 empty] | 2022 | [5 empty] | L+G Actual Invoice Totals will be: | [6 empty] | 2023-01-01: 2023
[19 empty] | Prices in effect Jan - March | [5 empty] | Prices in effect |  | June 2011 CPI | [5 empty] | 31876654.2408 | [6 empty] | June 2012 CPI | [5 empty] | 32294360.5105 | [6 empty] | June 2013 CPI | [5 empty] | 33127908.8841 | [6 empty] | June 2014 CPI | [5 empty] | 34188011.9171 | [6 empty] | June 2015 CPI |  |  | all reads |  |  | 18392293.2864 | [6 empty] | June 2016 CPI | [5 empty] | 13425194.401 | [6 empty] | June 2017 CPI | [5 empty] | 14071181.1948 | [6 empty] | June 2018 CPI | [5 empty] | 14749195.4614 | [6 empty] | June 2019 CPI | [5 empty] | 15465348.1464 | [6 empty] | June 2019 CPI | [5 empty] | 16224634.4309 | [6 empty] | June 2021 CPI | [5 empty] | 17029169.5028 | [6 empty] | 2023-01-01: June 2022 CPI
[14 empty] | Mo. Credits |  |  |  |  | 2011 | [5 empty] | April 27,2011 |  | 0.043888 | Actual |  |  |  |  | -5160854.88 | [6 empty] | 0.021035 | Actual |  |  |  |  | -4188670.88 | [6 empty] | 0.024013 | Forecast |  |  |  |  | -4102011.96 | [6 empty] | 0.024562 | Forecast |  |  |  |  | -4000011.96 | [6 empty] | 0.025261 | Forecast |  |  |  |  | 1285714.26 | [6 empty] | 0.025894 | Forecast |  |  |  |  | 1714273.68 | [6 empty] | 0.026457 | Forecast |  |  |  |  | 1714273.68 | [6 empty] | 0.02705 | Forecast |  |  |  |  | 1714273.68 | [6 empty] | 0.027695 | Forecast |  |  |  |  | 1714273.68 | [6 empty] | 0.028387 | Forecast |  |  |  |  | 1714273.68 | [6 empty] | 0.029108 | Forecast |  |  |  |  | 1714273.68 | [6 empty] | 2023-01-01: 0.029847; 2023-02-01: Forecast
Monthly Credit 2011 | [13 empty] | 2011 | XXXXXXX |  |  | CumE1 CumG | XXXXXXX |  |  |  |  | CumE1 CumG | XXXXXXX |  | XXXXXXX | CumE1 CumG |  |  |  |  | XXXXXXX | [6 empty] | XXXXXXX | CumE1 CumG |  |  |  |  | XXXXXXX | [6 empty] | XXXXXXX | CumE1 CumG |  |  |  |  | XXXXXXX | [6 empty] | XXXXXXX | CumE1 CumG |  |  |  |  | XXXXXXX | [6 empty] | XXXXXXX | CumE1 CumG |  | XXXXXXX | CumE1 CumG |  | XXXXXXX | [6 empty] | XXXXXXX | CumE1 CumG |  |  |  |  | XXXXXXX | [6 empty] | XXXXXXX | CumE1 CumG |  |  |  |  | XXXXXXX | [6 empty] | XXXXXXX | CumE1 CumG |  |  |  |  | XXXXXXX | [6 empty] | XXXXXXX | CumE1 CumG |  |  |  |  | XXXXXXX | [6 empty] | XXXXXXX | CumE1 CumG |  |  |  |  | XXXXXXX | [6 empty] | XXXXXXX | CumE1 CumG |  |  |  |  | XXXXXXX | [6 empty] | 2023-01-01: XXXXXXX; 2023-02-01: CumE1 CumG
Monthly Credit 2012 | [13 empty] | 2012 | XXXXXXX |  |  | TOUE1 | XXXXXXX |  |  |  |  | TOUE1 | XXXXXXX |  | XXXXXXX | TOUE1 | [11 empty] | XXXXXXX | TOUE1 | [11 empty] | XXXXXXX | TOUE1 | [11 empty] | XXXXXXX | TOUE1 | [11 empty] | XXXXXXX | TOUE1 |  | XXXXXXX | TOUE1 | [8 empty] | XXXXXXX | TOUE1 | [11 empty] | XXXXXXX | TOUE1 | [11 empty] | XXXXXXX | TOUE1 | [11 empty] | XXXXXXX | TOUE1 | [11 empty] | XXXXXXX | TOUE1 | [11 empty] | XXXXXXX | TOUE1 | [11 empty] | 2023-01-01: XXXXXXX; 2023-02-01: TOUE1
Monthly Credit 2013 | [13 empty] | 2013 | XXXXXXX |  |  | DEME1 | XXXXXXX |  |  |  |  | DEME1 | XXXXXXX |  | XXXXXXX | DEME1 |  |  |  |  | Average Read Cost( Incl. total Credits): | [6 empty] | XXXXXXX | DEME1 |  |  |  |  | Average Read Cost( Incl. total Credits): | [6 empty] | XXXXXXX | DEME1 |  |  |  |  | Average Read Cost( Incl. total Credits): | [6 empty] | XXXXXXX | DEME1 |  |  |  |  | Average Read Cost( Incl. total Credits): | [6 empty] | XXXXXXX | DEME1 |  | XXXXXXX | DEME1 |  | Average Read Cost( Incl. total Credits): | [6 empty] | XXXXXXX | DEME1 |  |  |  |  | Average Read Cost( Incl. total Credits): | [6 empty] | XXXXXXX | DEME1 |  |  |  |  | Average Read Cost( Incl. total Credits): | [6 empty] | XXXXXXX | DEME1 |  |  |  |  | Average Read Cost( Incl. total Credits): | [6 empty] | XXXXXXX | DEME1 |  |  |  |  | Average Read Cost( Incl. total Credits): | [6 empty] | XXXXXXX | DEME1 |  |  |  |  | Average Read Cost( Incl. total Credits): | [6 empty] | XXXXXXX | DEME1 |  |  |  |  | Average Read Cost( Incl. total Credits): | [6 empty] | 2023-01-01: XXXXXXX; 2023-02-01: DEME1
Monthly Credit 2014 | [13 empty] | 2014 | XXXXXXX |  |  | LP1,LP2 | XXXXXXX |  |  |  |  | LP1,LP2 | XXXXXXX |  | XXXXXXX | LP1,LP2 |  |  |  |  | XXXXXXX | [6 empty] | XXXXXXX | LP1,LP2 |  |  |  |  | XXXXXXX | [6 empty] | XXXXXXX | LP1,LP2 |  |  |  |  | XXXXXXX | [6 empty] | XXXXXXX | LP1,LP2 |  |  |  |  | XXXXXXX | [6 empty] | XXXXXXX | LP1,LP2 |  | XXXXXXX | LP1,LP2 |  | XXXXXXX | [6 empty] | XXXXXXX | LP1,LP2 |  |  |  |  | XXXXXXX | [6 empty] | XXXXXXX | LP1,LP2 |  |  |  |  | XXXXXXX | [6 empty] | XXXXXXX | LP1,LP2 |  |  |  |  | XXXXXXX | [6 empty] | XXXXXXX | LP1,LP2 |  |  |  |  | XXXXXXX | [6 empty] | XXXXXXX | LP1,LP2 |  |  |  |  | XXXXXXX | [6 empty] | XXXXXXX | LP1,LP2 |  |  |  |  | XXXXXXX | [6 empty] | 2023-01-01: XXXXXXX; 2023-02-01: LP1,LP2
Monthly Credit 2015 | [13 empty] | 2015 | XXXXXXX |  |  |  | XXXXXXX | [5 empty] | XXXXXXX |  | XXXXXXX | [51 empty] | XXXXXXX |  |  | XXXXXXX | [9 empty] | XXXXXXX | [25 empty] | XXXXXXX | [12 empty] | XXXXXXX | [12 empty] | XXXXXXX | [12 empty] | XXXXXXX | [12 empty] | 2023-01-01: XXXXXXX
Monthly Cost 2016 | [13 empty] | 2016 | XXXXXXX |  |  | CumE3 kVAR | XXXXXXX |  |  |  |  | CumE3 kVAR | XXXXXXX |  | XXXXXXX | CumE3 kVAR | [11 empty] | XXXXXXX | CumE3 kVAR | [11 empty] | XXXXXXX | CumE3 kVAR | [11 empty] | XXXXXXX | CumE3 kVAR | [11 empty] | XXXXXXX | CumE3 kVAR |  | XXXXXXX | CumE3 kVAR | [8 empty] | XXXXXXX | CumE3 kVAR | [11 empty] | XXXXXXX | CumE3 kVAR | [11 empty] | XXXXXXX | CumE3 kVAR | [11 empty] | XXXXXXX | CumE3 kVAR | [11 empty] | XXXXXXX | CumE3 kVAR | [11 empty] | XXXXXXX | CumE3 kVAR | [11 empty] | 2023-01-01: XXXXXXX; 2023-02-01: CumE3 kVAR
[18 empty] | TOUE3 | XXXXXXX |  |  |  |  | TOUE3 | XXXXXXX |  | XXXXXXX | TOUE3 | [11 empty] | XXXXXXX | TOUE3 | [11 empty] | XXXXXXX | TOUE3 | [11 empty] | XXXXXXX | TOUE3 | [11 empty] | XXXXXXX | TOUE3 |  | XXXXXXX | TOUE3 | [8 empty] | XXXXXXX | TOUE3 | [11 empty] | XXXXXXX | TOUE3 | [11 empty] | XXXXXXX | TOUE3 | [11 empty] | XXXXXXX | TOUE3 | [11 empty] | XXXXXXX | TOUE3 | [11 empty] | XXXXXXX | TOUE3 | [11 empty] | 2023-01-01: XXXXXXX; 2023-02-01: TOUE3
[18 empty] | DEME3 | XXXXXXX |  |  |  |  | DEME3 | XXXXXXX |  | XXXXXXX | DEME3 | [11 empty] | XXXXXXX | DEME3 | [11 empty] | XXXXXXX | DEME3 | [11 empty] | XXXXXXX | DEME3 | [11 empty] | XXXXXXX | DEME3 |  | XXXXXXX | DEME3 | [8 empty] | XXXXXXX | DEME3 | [11 empty] | XXXXXXX | DEME3 | [11 empty] | XXXXXXX | DEME3 | [11 empty] | XXXXXXX | DEME3 | [11 empty] | XXXXXXX | DEME3 | [11 empty] | XXXXXXX | DEME3 | [11 empty] | 2023-01-01: XXXXXXX; 2023-02-01: DEME3
[18 empty] | LPE3, LPG | XXXXXXX |  |  |  |  | LPE3, LPG | XXXXXXX |  | XXXXXXX | LPE3, LPG | [11 empty] | XXXXXXX | LPE3, LPG | [11 empty] | XXXXXXX | LPE3, LPG | [11 empty] | XXXXXXX | LPE3, LPG | [11 empty] | XXXXXXX | LPE3, LPG |  | XXXXXXX | LPE3, LPG | [8 empty] | XXXXXXX | LPE3, LPG | [11 empty] | XXXXXXX | LPE3, LPG | [11 empty] | XXXXXXX | LPE3, LPG | [11 empty] | XXXXXXX | LPE3, LPG | [11 empty] | XXXXXXX | LPE3, LPG | [11 empty] | XXXXXXX | LPE3, LPG | [11 empty] | 2023-01-01: XXXXXXX; 2023-02-01: LPE3, LPG
[14 empty] | Total 2011 | XXXXXXX | [11 empty] | Actual 2012 Meter Read Costs |  |  | XXXXXXX | [9 empty] | Actual 2013 Meter Read Costs |  |  | XXXXXXX | [9 empty] | Actual 2014 Meter Read Costs |  |  | XXXXXXX | [9 empty] | Actual 2015 Meter Read Costs |  |  | XXXXXXX | [9 empty] | Actual 2016 Meter Read Costs |  |  | XXXXXXX | [9 empty] | Actual 2017 Meter Read Costs |  |  | XXXXXXX | [9 empty] | Actual 2018 Meter Read Costs |  |  | XXXXXXX | [9 empty] | Actual 2019 Meter Read Costs |  |  | XXXXXXX | [9 empty] | Actual 2020 Meter Read Costs |  |  | XXXXXXX | [9 empty] | Actual 2021 Meter Read Costs |  |  | XXXXXXX | [9 empty] | Actual 2022 Meter Read Costs |  |  | XXXXXXX | [9 empty] | 2023-01-01: Actual 2023 Meter Read Costs; 2023-03-01: 4438061.6727
[27 empty] | Actual Contract Credit |  |  | -4937499.96 | [9 empty] | Contract Credits Allowed |  |  | -2080000 | [9 empty] | Contract Credits Allowed |  |  | -1764000 | [9 empty] | Contract Credits Allowed |  |  | -1459000 | [9 empty] | Contract Credits Allowed |  |  | -289000 | [9 empty] | Contract Payback |  |  | 1714285.68 | [9 empty] | Contract Payback |  |  | 1714285.68 | [9 empty] | Contract Payback |  |  | 1714285.68 | [9 empty] | Contract Payback |  |  | 1714285.68 | [9 empty] | Contract Payback |  |  | 1714285.68 | [9 empty] | Contract Payback |  |  | 1714285.68 | [9 empty] | 2023-01-01: Contract Payback; 2023-03-01: 428571.42
[40 empty] | Less anticipated Perfomance Credits |  |  | -188670.92 | [9 empty] | Less anticipated Perfomance Credits |  |  | -102012 | [9 empty] | Less anticipated Perfomance Credits |  |  | -12 | [9 empty] | Less anticipated Perfomance Credits |  |  | 0 | [9 empty] | Less anticipated Perfomance Credits |  |  | -12 | [9 empty] | Less anticipated Perfomance Credits |  |  | -12 | [9 empty] | Less anticipated Perfomance Credits |  |  | -12 | [9 empty] | Less anticipated Perfomance Credits |  |  | -12 | [9 empty] | Less anticipated Perfomance Credits |  |  | -12 | [9 empty] | Less anticipated Perfomance Credits |  |  | -12 | [9 empty] | 2023-01-01: Less anticipated Perf Credits; 2023-03-01: -3
[14 empty] | Average Read Cost: | [12 empty] | Total 2012 Cost |  |  | XXXXXXX | [9 empty] | Total 2013 'Cost' |  |  | XXXXXXX | [9 empty] | Total 2014 'Cost' |  |  | XXXXXXX | [9 empty] | Total 2015 'Cost' |  |  | XXXXXXX | [9 empty] | Contract Payback |  |  | XXXXXXX | [9 empty] | Total 2017 'Cost' |  |  | XXXXXXX | [9 empty] | Total 2018 'Cost' |  |  | XXXXXXX | [9 empty] | Total 2019 'Cost' |  |  | XXXXXXX | [9 empty] | Total 2020 'Cost' |  |  | XXXXXXX | [9 empty] | Total 2021 'Cost' |  |  | XXXXXXX | [9 empty] | Total 2022 'Cost' |  |  | XXXXXXX | [9 empty] | 2023-03-01: 4866630.0927
[14 empty] | XXXXXXX | [64 empty] | Total 2016 'Cost' |  |  | XXXXXXX
[27 empty] | IT Budget Amount: | [12 empty] | IT Budget Amount: | [12 empty] | IT Budget Amount: | [12 empty] | IT Budget Amount: | [12 empty] | IT Budget Amount: | [12 empty] | IT Budget Amount: | [12 empty] | IT Budget Amount: | [12 empty] | IT Budget Amount: | [12 empty] | IT Budget Amount: | [12 empty] | IT Budget Amount: | [12 empty] | IT Budget Amount: | [12 empty] | 2023-01-01: IT Budget Amount:; 2023-03-01: 4852438.0651
[27 empty] | Total 2012 less allowed credits & dept alloc. |  |  | 28952542.327 | [9 empty] | Total 2013 less allowed credits & dept alloc. |  |  | 29677038.5369 | [9 empty] | Total 2014 less allowed credits & dept alloc. |  |  | 30867992.8577 | [9 empty] | Total 2015 less allowed credits & dept alloc. |  |  | 32217095.1464 | [9 empty] | Total 2016 less allowed credits/payback & dept alloc. |  |  | 19227073.0513 | [9 empty] | Total 2015 less allowed credits & dept alloc. |  |  | 15096614.3108 | [9 empty] | Total 2015 less allowed credits & dept alloc. |  |  | 15740522.4787 | [9 empty] | Total 2019 less allowed credits & dept alloc. |  |  | 16416358.9413 | [9 empty] | Total 2020 less allowed credits & dept alloc. |  |  | 17130210.8493 | [9 empty] | Total 2021 less allowed credits & dept alloc. |  |  | 17887054.5932 | [9 empty] | Total 2022 less allowed credits & dept alloc. |  |  | 18688999.6222 | [9 empty] | 2023-01-01: Total 2015 less allowed credits & dept alloc.
[79 empty] | Monthly Payback per Contract beginning 04/16 |  |  | 142857.14 | [9 empty] | Monthly Payback per Contract |  |  | 142857.14 | [9 empty] | Monthly Payback per Contract |  |  | 142857.14 | [9 empty] | Monthly Payback per Contract |  |  | 142857.14 | [9 empty] | Monthly Payback per Contract |  |  | 142857.14 | [9 empty] | Monthly Payback per Contract |  |  | 142857.14 | [9 empty] | Monthly Payback per Contract |  |  | 142857.14
[14 empty] | Accounting based credit allowable amount: |  |  | XXXXXXX | [9 empty] | Accounting based credit allowable amount: |  |  | XXXXXXX |  | XXXXXXX | [7 empty] | Accounting based credit allowable amount: |  |  | XXXXXXX | [9 empty] | Accounting based credit allowable amount: |  |  | XXXXXXX | [9 empty] | Accounting based credit allowable amount: |  |  | XXXXXXX | [9 empty] | Accounting based credit allowable amount: |  |  | XXXXXXX
XXXXXXX
[27 empty] | Average Read Cost( Prior to Credits): | [12 empty] | Average Read Cost( Prior to Credits): | [12 empty] | Average Read Cost( Prior to Credits): | [12 empty] | Average Read Cost( Prior to Credits): | [12 empty] | Average Read Cost( Includes Payback): |  |  |  |  | Q1 Avg Read Fee | [7 empty] | Average Read Cost | [12 empty] | Average Read Cost | [12 empty] | Average Read Cost | [12 empty] | Average Read Cost | [12 empty] | Average Read Cost | [12 empty] | Average Read Cost | [12 empty] | 2023-01-01: Average Read Cost( Prior to Perf Credits):
[27 empty] | XXXXXXX | [12 empty] | XXXXXXX | [12 empty] | XXXXXXX | [12 empty] | XXXXXXX | [12 empty] | Annual | Q1 | Q2-4 |  |  | XXXXXXX | [7 empty] | XXXXXXX | [12 empty] | XXXXXXX | [12 empty] | XXXXXXX | [12 empty] | XXXXXXX | [12 empty] | XXXXXXX | [12 empty] | XXXXXXX | [12 empty] | 2023-01-01: 0.70208
[79 empty] | XXXXXXX | XXXXXXX | XXXXXXX
[27 empty] | Average Read Cost(After Allowed Credits): | [12 empty] | Average Read Cost(After Allowed Credits): | [12 empty] | Average Read Cost(After Allowed Credits): | [12 empty] | Average Read Cost(After Allowed Credits): | [12 empty] | Average Read Cost(After Allowed Credits/Payback): |  |  |  |  | Q2-4 Avg Read Fee | [85 empty] | 2023-01-01: Average Read Cost(After Allowed Credits):
[79 empty] | Annual | Q1 | Q2-4 |  |  | XXXXXXX
[27 empty] | XXXXXXX | [12 empty] | XXXXXXX | [12 empty] | XXXXXXX | [12 empty] | XXXXXXX | [12 empty] | XXXXXXX | XXXXXXX | XXXXXXX | [88 empty] | 2023-01-01: 0.70208
[27 empty] | IT Average Read Cost(After Allowed Credits & Dept Alloc.): | [12 empty] | IT Average Read Cost(After Allowed Credits & Dept Alloc.): | [12 empty] | IT Average Read Cost(After Allowed Credits& Dept Alloc.): | [12 empty] | IT Average Read Cost(After Allowed Credits& Dept Alloc.): | [12 empty] | IT Average Read Cost(After Allowed Credits/Payback & Dept Alloc.): | [12 empty] | IT Average Read Cost(After Allowed Credits& Dept Alloc.): | [12 empty] | IT Average Read Cost(After Allowed Credits& Dept Alloc.): | [12 empty] | IT Average Read Cost(After Allowed Credits& Dept Alloc.): | [12 empty] | IT Average Read Cost(After Allowed Credits& Dept Alloc.): | [12 empty] | IT Average Read Cost(After Allowed Credits& Dept Alloc.): | [12 empty] | IT Average Read Cost(After Allowed Credits& Dept Alloc.): | [12 empty] | 2023-01-01: IT Average Read Cost(After Allowed Credits& Dept Alloc.):
[27 empty] | XXXXXXX | [12 empty] | XXXXXXX | [12 empty] | XXXXXXX | [12 empty] | XXXXXXX | [12 empty] | Annual | Q1 | Q2-4 | [10 empty] | XXXXXXX | [12 empty] | XXXXXXX | [12 empty] | XXXXXXX | [12 empty] | XXXXXXX | [12 empty] | XXXXXXX | [12 empty] | XXXXXXX | [12 empty] | 2023-01-01: 0.70003
[79 empty] | XXXXXXX | XXXXXXX | XXXXXXX
sum Ele reads | [39 empty] | 1123873 | 1125573 | 1127001 | 1108863 | 1108871 | 1119892 | 1121043 | 1122249 | 1123519 | 1124826 | 1126186 | 1127569 |  | 1128989 | 1130403 | 1131851 | 1133360 | 1135551 | 1137841 | 1139572 | 1141346 | 1143160 | 1145016 | 1146905 | 1148815 |  | 1150787 | 1152774 | 1154797 | 1156851 | 1158936 | 1160997 | 1163030 | 1165075 | 1167134 | 1169209 | 1171293 | 1173393 |  | 1175504 | 1177627 | 1179760 | 1181901 | 1184044 | 1186187 | 1188334 | 1190480 | 1192628 | 1194779 | 1196928 | 1199080 |  | 1201231 | 1203380 | 1205527 | 1207673 | 1209817 | 1211960 | 1214099 | 1216239 | 1218375 | 1220514 | 1222646 | 1224777 |  | 1226908 | 1229037 | 1231164 | 1233290 | 1235414 | 1237539 | 1239663 | 1241788 | 1243912 | 1246034 | 1248158 | 1250282 |  | 1252404 | 1254527 | 1256650 | 1258773 | 1260893 | 1263018 | 1265143 | 1267266 | 1269395 | 1271523 | 1273654 | 1275786 |  | 1277917 | 1280055 | 1282191 | 1284333 | 1286475 | 1288620 | 1290768 | 1292919 | 1295074 | 1297233 | 1299392 | 1301554 |  | 1303718 | 1305884 | 1308055 | 1310224 | 1312397 | 1314570 | 1316744 | 1318920 | 1321097 | 1323275 | 1325450 | 1327632 |  | 1329811 | 1331990 | 1334171 | 1336356 | 1338540 | 1340725 | 1342914 | 1345101 | 1347290 | 1349480 | 1351672 | 1353863 |  | 2023-01-01: 1356055; 2023-02-01: 1358249; 2023-03-01: 1360443
sum Gas reads | [39 empty] | 789646 | 791236 | 793291 | 793995 | 794549 | 789371 | 790504 | 791667 | 792854 | 794082 | 795355 | 796661 |  | 797995 | 799387 | 800803 | 802210 | 802993 | 803738 | 805103 | 806482 | 807876 | 809282 | 810696 | 812116 |  | 813535 | 814950 | 816358 | 817754 | 819139 | 820564 | 822039 | 823515 | 824992 | 826472 | 827953 | 829437 |  | 830926 | 832420 | 833920 | 835425 | 836939 | 838459 | 839982 | 841505 | 843027 | 844547 | 846067 | 847587 |  | 849106 | 850625 | 852143 | 853661 | 855179 | 856694 | 858210 | 859723 | 861234 | 862745 | 864254 | 865761 |  | 867268 | 868774 | 870278 | 871783 | 873286 | 874788 | 876291 | 877794 | 879296 | 880798 | 882301 | 883803 |  | 885304 | 886806 | 888308 | 889808 | 891310 | 892813 | 894315 | 895819 | 897324 | 898830 | 900336 | 901844 |  | 903354 | 904864 | 906377 | 907891 | 909408 | 910925 | 912445 | 913967 | 915491 | 917017 | 918545 | 920075 |  | 921607 | 923139 | 924674 | 926210 | 927747 | 929284 | 930822 | 932362 | 933901 | 935441 | 936982 | 938524 |  | 940067 | 941609 | 943152 | 944697 | 946243 | 947790 | 949336 | 950884 | 952433 | 953983 | 955534 | 957084 |  | 2023-01-01: 958635; 2023-02-01: 960187; 2023-03-01: 961739
invoice less dept.alloc
[40 empty] | 2470385.3575 | 2474630.9194 | 2479573.5035 | 2455497.939 | 2456594.0304 | 2466374.2803 | 2469455.4156 | 2472626.1303 | 2475901.8749 | 2479280.9307 | 2482749.8045 | 2486301.8007 |  | 2549068.1556 | 2553048.7386 | 2557131.8917 | 2561293.4566 | 2565539.8926 | 2569880.7193 | 2574160.6681 | 2578525.8729 | 2582971.6998 | 2587499.1986 | 2592098.6865 | 2596773.8774 |  | 2657743.6715 | 2662573.588 | 2667437.9246 | 2672323.3188 | 2677231.6626 | 2682154.9964 | 2687100.0959 | 2692068.9094 | 2697063.8668 | 2702085.8268 | 2707122.6685 | 2712188.6173 |  | 2774746.6646 | 2779921.2791 | 2785116.5227 | 1059141.3 | 1061061.225 | 1062984.825 | 1064912.625 | 1066839.9 | 1068766.65 | 1070694.975 | 1072622.25 | 1074550.575 |  | 1104349.9112 | 1106326.0126 | 1108301.5754 | 1110273.9066 | 1112247.8536 | 1114218.5691 | 1116188.2073 | 1118155.6912 | 1120121.0207 | 1122087.4274 | 1124048.9868 | 1126009.4689 |  | 1157813.5551 | 1159823.143 | 1161831.6253 | 1163840.6604 | 1165845.2727 | 1167852.0964 | 1169857.8145 | 1171863.5325 | 1173870.3562 | 1175873.8629 | 1177880.1337 | 1179884.7461 |  | 1213843.0258 | 1215902.3864 | 1217960.6541 | 1220019.4469 | 1222076.579 | 1224137.0752 | 1226197.5713 | 1228257.5425 | 1230322.0132 | 1232385.3911 | 1234452.133 | 1236519.4428 |  | 1272905.4086 | 1275035.2675 | 1277165.1265 | 1279299.0701 | 1281434.7643 | 1283573.9596 | 1285714.3219 | 1287858.769 | 1290006.1336 | 1292158.1664 | 1294309.6157 | 1296464.5662 |  | 1335485.4175 | 1337705.7394 | 1339930.862 | 1342155.3845 | 1344382.3073 | 1346609.2302 | 1348837.9533 | 1351068.4767 | 1353299.6001 | 1355531.9238 | 1357763.6473 | 1359998.3713 |  | 1401884.2508 | 1404182.7868 | 1406484.4105 | 1408788.5045 | 1411092.5985 | 1413399.1627 | 1415706.3444 | 1418014.1437 | 1420323.1781 | 1422633.4476 | 1424946.8049 | 1427258.3095 |  | 2023-01-01: 1472239.1755; 2023-02-01: 1474621.579; 2023-03-01: 1477005.8906
Total Cost - Electric Reads - Actual | [39 empty] | 1614580.664 | 1617042.108 | 1619056.7519 | 1593767.2112 | 1594157.6531 | 1611717.2748 | 1613214.728 | 1614751.7208 | 1616378.2462 | 1618095.4193 | 1619888.3995 | 1621687.269 |  | 1640009.6406 | 1642148.6789 | 1644365.6701 | 1646672.771 | 1649927.5227 | 1653332.1177 | 1655786.8 | 1658306.2284 | 1660900.1907 | 1663558.0497 | 1666290.0137 | 1669090.0847 |  | 1690795.4131 | 1693735.7816 | 1696727.9217 | 1699750.0344 | 1702811.6859 | 1705823.9729 | 1708797.9602 | 1711792.8967 | 1714812.5946 | 1717855.1479 | 1720911.2003 | 1724000.5018 |  | 1746684.4391 | 1749838.9697 | 1753011.3277 | 623532 | 624662.85 | 625793.175 | 626927.7 | 628061.175 | 629194.65 | 630330.225 | 631465.8 | 632600.85 |  | 650145.4349 | 651309.8751 | 652472.6996 | 653633.3696 | 654795.6555 | 655955.787 | 657114.8413 | 658273.357 | 659429.7183 | 660589.3112 | 661744.0567 | 662897.725 |  | 681622.3757 | 682804.909 | 683987.4423 | 685170.5285 | 686350.2976 | 687532.8309 | 688713.1528 | 689894.0276 | 691076.0081 | 692255.2243 | 693436.0991 | 694616.9739 |  | 714602.5241 | 715814.7301 | 717026.9788 | 718239.1847 | 719449.7301 | 720663.0716 | 721876.4131 | 723088.6619 | 724304.8424 | 725519.3623 | 726736.6784 | 727953.9945 |  | 749380.0764 | 750635.2344 | 751888.6418 | 753144.9668 | 754402.4588 | 755662.285 | 756922.1112 | 758184.8549 | 759449.3493 | 760716.7612 | 761983.0061 | 763251.0016 |  | 786223.7859 | 787531.3755 | 788841.9655 | 790151.9554 | 791462.5454 | 792773.1354 | 794085.5257 | 795398.5161 | 796712.7066 | 798027.4972 | 799341.0877 | 800657.6785 |  | 825315.8396 | 826668.2828 | 828023.8138 | 829381.1975 | 830736.7286 | 832095.9649 | 833453.9662 | 834813.2025 | 836171.8213 | 837532.2928 | 838894.6169 | 840255.7059 |  | 2023-01-01: 866736.3485; 2023-02-01: 868139.3336; 2023-03-01: 869543.5907
Total Cost - Gas Reads Acutal | [39 empty] | 1073794.9893 | 1076067.4996 | 1078943.365 | 1080187.2212 | 1081037.4507 | 1073763.1803 | 1075295.8041 | 1076857.9987 | 1078462.3164 | 1080131.7531 | 1081853.9456 | 1083627.5412 |  | 1096969.1181 | 1098904.6536 | 1100864.6102 | 1102805.2332 | 1103868.8251 | 1104869.3288 | 1106741.3945 | 1108640.9976 | 1110552.7159 | 1112489.2369 | 1114429.6691 | 1116385.3328 |  | 1130774.8651 | 1132738.1272 | 1134690.3297 | 1136627.3254 | 1138547.7317 | 1140533.3059 | 1142578.1321 | 1144632.8284 | 1146681.8019 | 1148742.028 | 1150796.5313 | 1152853.7995 |  | 1168048.3731 | 1170143.0089 | 1172254.6179 | 438999.75 | 439794.6 | 440593.65 | 441393.75 | 442194.375 | 442993.425 | 443793 | 444591 | 445390.575 |  | 457741.3459 | 458559.4702 | 459378.6717 | 460196.2574 | 461014.9202 | 461831.4287 | 462649.0144 | 463463.9072 | 464279.3385 | 465093.154 | 465905.8924 | 466719.1693 |  | 479900.657 | 480734.3457 | 481566.3759 | 482399.5118 | 483230.4364 | 484061.3609 | 484893.3911 | 485724.3156 | 486556.3459 | 487386.7176 | 488218.7478 | 489049.1195 |  | 503130.3502 | 503984.3184 | 504837.151 | 505690.5514 | 506543.384 | 507397.92 | 508251.3203 | 509105.2885 | 509960.9601 | 510816.0639 | 511672.8711 | 512529.1105 |  | 527605.7415 | 528487.4447 | 529370.315 | 530254.9359 | 531140.1403 | 532027.0953 | 532914.0502 | 533803.3393 | 534692.6283 | 535584.835 | 536476.4581 | 537370.4154 |  | 553543.6522 | 554463.5856 | 555385.9193 | 556307.6529 | 557231.1868 | 558154.1206 | 559078.2546 | 560002.3886 | 560927.1226 | 561851.8567 | 562777.7909 | 563703.1251 |  | 581065.2044 | 582018.0902 | 582972.2111 | 583926.332 | 584882.3056 | 585837.6617 | 586794.2528 | 587750.2264 | 588708.0527 | 589665.2614 | 590624.3227 | 591582.149 |  | 2023-01-01: 610226.659; 2023-02-01: 611213.7093; 2023-03-01: 612202.0316
Total amount allocated and credited | [39 empty] | -217990.2958 | -218478.6881 | -218426.6133 | -218456.4933 | -218601.0733 | -219106.1748 | -219055.1165 | -218983.5892 | -218938.6876 | -218946.2416 | -218992.5405 | -219013.0094 |  | -187910.6031 | -188004.5939 | -188098.3885 | -188184.5475 | -188256.4552 | -188320.7272 | -188367.5264 | -188421.3531 | -188481.2068 | -188548.0881 | -188620.9963 | -188701.5401 |  | -163826.6068 | -163900.3208 | -163980.3269 | -164054.041 | -164127.755 | -164202.2823 | -164275.9964 | -164356.8157 | -164430.5297 | -164511.349 | -164585.0631 | -164665.684 |  | -139986.1476 | -140060.6996 | -140149.4229 | -3390.45 | -3396.225 | -3402 | -3408.825 | -3415.65 | -3421.425 | -3428.25 | -3434.55 | -3440.85 |  | -3536.8696 | -3543.3327 | -3549.7959 | -3555.7204 | -3562.7221 | -3568.6467 | -3575.6484 | -3581.5729 | -3588.036 | -3595.0378 | -3600.9623 | -3607.4254 |  | -3709.4776 | -3716.1117 | -3722.193 | -3729.3799 | -3735.4612 | -3742.0953 | -3748.7295 | -3754.8108 | -3761.9977 | -3768.079 | -3774.7131 | -3781.3473 |  | -3889.8485 | -3896.6621 | -3903.4757 | -3910.2892 | -3916.535 | -3923.9164 | -3930.1622 | -3936.4079 | -3943.7893 | -3950.0351 | -3957.4165 | -3963.6622 |  | -4080.4093 | -4087.4116 | -4093.8303 | -4100.8326 | -4107.8349 | -4115.4207 | -4121.8394 | -4129.4252 | -4135.844 | -4143.4298 | -4149.8485 | -4156.8508 |  | -4282.0207 | -4289.2217 | -4297.0228 | -4304.2239 | -4311.4249 | -4318.0259 | -4325.827 | -4332.428 | -4340.2291 | -4347.4301 | -4355.2313 | -4362.4323 |  | -4496.7931 | -4503.5862 | -4511.6144 | -4519.0251 | -4526.4357 | -4534.4639 | -4541.8746 | -4549.2852 | -4556.6959 | -4564.1065 | -4572.1347 | -4579.5454 |  | 2023-01-01: -4723.832; 2023-02-01: -4731.4639; 2023-03-01: -4739.7317
Electric portion | [39 empty] | -183111.8485 | -183522.098 | -183478.3552 | -183503.4544 | -183624.9016 | -184049.1868 | -184006.2978 | -183946.215 | -183908.4976 | -183914.843 | -183953.734 | -183970.9279 |  | -157844.9066 | -157923.8589 | -158002.6464 | -158075.0199 | -158135.4224 | -158189.4109 | -158228.7222 | -158273.9366 | -158324.2137 | -158380.394 | -158441.6369 | -158509.2937 |  | -137614.3497 | -137676.2695 | -137743.4746 | -137805.3944 | -137867.3142 | -137929.9171 | -137991.837 | -138059.7252 | -138121.645 | -138189.5332 | -138251.453 | -138319.1745 |  | -117588.364 | -117650.9877 | -117725.5153 | -2847.978 | -2852.829 | -2857.68 | -2863.413 | -2869.146 | -2873.997 | -2879.73 | -2885.022 | -2890.314 |  | -2970.9705 | -2976.3995 | -2981.8285 | -2986.8051 | -2992.6866 | -2997.6632 | -3003.5446 | -3008.5212 | -3013.9503 | -3019.8317 | -3024.8083 | -3030.2374 |  | -3115.9611 | -3121.5338 | -3126.6421 | -3132.6791 | -3137.7874 | -3143.3601 | -3148.9328 | -3154.041 | -3160.0781 | -3165.1864 | -3170.759 | -3176.3317 |  | -3267.4727 | -3273.1961 | -3278.9195 | -3284.643 | -3289.8894 | -3296.0898 | -3301.3362 | -3306.5827 | -3312.783 | -3318.0295 | -3324.2298 | -3329.4763 |  | -3427.5438 | -3433.4257 | -3438.8175 | -3444.6994 | -3450.5813 | -3456.9534 | -3462.3451 | -3468.7172 | -3474.1089 | -3480.481 | -3485.8728 | -3491.7547 |  | -3596.8974 | -3602.9462 | -3609.4992 | -3615.5481 | -3621.5969 | -3627.1417 | -3633.6947 | -3639.2395 | -3645.7924 | -3651.8413 | -3658.3943 | -3664.4431 |  | -3777.3062 | -3783.0124 | -3789.7561 | -3795.9811 | -3802.206 | -3808.9497 | -3815.1746 | -3821.3996 | -3827.6245 | -3833.8495 | -3840.5932 | -3846.8181 |  | 2023-01-01: -3968.0189; 2023-02-01: -3974.4296; 2023-03-01: -3981.3746
Gas Portion | [39 empty] | -34878.4473 | -34956.5901 | -34948.2581 | -34953.0389 | -34976.1717 | -35056.988 | -35048.8186 | -35037.3743 | -35030.19 | -35031.3987 | -35038.8065 | -35042.0815 |  | -30065.6965 | -30080.735 | -30095.7422 | -30109.5276 | -30121.0328 | -30131.3164 | -30138.8042 | -30147.4165 | -30156.9931 | -30167.6941 | -30179.3594 | -30192.2464 |  | -26212.2571 | -26224.0513 | -26236.8523 | -26248.6466 | -26260.4408 | -26272.3652 | -26284.1594 | -26297.0905 | -26308.8848 | -26321.8158 | -26333.6101 | -26346.5094 |  | -22397.7836 | -22409.7119 | -22423.9077 | -542.472 | -543.396 | -544.32 | -545.412 | -546.504 | -547.428 | -548.52 | -549.528 | -550.536 |  | -565.8991 | -566.9332 | -567.9673 | -568.9153 | -570.0355 | -570.9835 | -572.1037 | -573.0517 | -574.0858 | -575.206 | -576.154 | -577.1881 |  | -593.5164 | -594.5779 | -595.5509 | -596.7008 | -597.6738 | -598.7353 | -599.7967 | -600.7697 | -601.9196 | -602.8926 | -603.9541 | -605.0156 |  | -622.3758 | -623.4659 | -624.5561 | -625.6463 | -626.6456 | -627.8266 | -628.8259 | -629.8253 | -631.0063 | -632.0056 | -633.1866 | -634.186 |  | -652.8655 | -653.9859 | -655.0129 | -656.1332 | -657.2536 | -658.4673 | -659.4943 | -660.708 | -661.735 | -662.9488 | -663.9758 | -665.0961 |  | -685.1233 | -686.2755 | -687.5237 | -688.6758 | -689.828 | -690.8841 | -692.1323 | -693.1885 | -694.4367 | -695.5888 | -696.837 | -697.9892 |  | -719.4869 | -720.5738 | -721.8583 | -723.044 | -724.2297 | -725.5142 | -726.6999 | -727.8856 | -729.0713 | -730.257 | -731.5416 | -732.7273 |  | 2023-01-01: -755.8131; 2023-02-01: -757.0342; 2023-03-01: -758.3571
Accural use Electric -using acutal $ | [39 empty] | 1431468.8155 | 1433520.01 | 1435578.3967 | 1410263.7568 | 1410532.7515 | 1427668.088 | 1429208.4302 | 1430805.5059 | 1432469.7486 | 1434180.5763 | 1435934.6654 | 1437716.341 |  | 1482164.734 | 1484224.82 | 1486363.0237 | 1488597.751 | 1491792.1003 | 1495142.7068 | 1497558.0778 | 1500032.2918 | 1502575.977 | 1505177.6557 | 1507848.3768 | 1510580.791 |  | 1553181.0634 | 1556059.5121 | 1558984.4471 | 1561944.6399 | 1564944.3717 | 1567894.0557 | 1570806.1232 | 1573733.1715 | 1576690.9497 | 1579665.6147 | 1582659.7473 | 1585681.3273 |  | 1629096.0751 | 1632187.9821 | 1635285.8124 | 620684.022 | 621810.021 | 622935.495 | 624064.287 | 625192.029 | 626320.653 | 627450.495 | 628580.778 | 629710.536 |  | 647174.4644 | 648333.4756 | 649490.8711 | 650646.5645 | 651802.9689 | 652958.1238 | 654111.2966 | 655264.8357 | 656415.768 | 657569.4794 | 658719.2484 | 659867.4877 |  | 678506.4145 | 679683.3752 | 680860.8002 | 682037.8493 | 683212.5101 | 684389.4708 | 685564.2201 | 686739.9866 | 687915.93 | 689090.038 | 690265.3401 | 691440.6422 |  | 711335.0514 | 712541.5339 | 713748.0593 | 714954.5418 | 716159.8407 | 717366.9818 | 718575.0769 | 719782.0792 | 720992.0594 | 722201.3328 | 723412.4486 | 724624.5182 |  | 745952.5326 | 747201.8086 | 748449.8243 | 749700.2674 | 750951.8775 | 752205.3316 | 753459.766 | 754716.1377 | 755975.2403 | 757236.2802 | 758497.1334 | 759759.2469 |  | 782626.8886 | 783928.4293 | 785232.4663 | 786536.4074 | 787840.9485 | 789145.9937 | 790451.831 | 791759.2766 | 793066.9142 | 794375.6559 | 795682.6934 | 796993.2354 |  | 821538.5333 | 822885.2704 | 824234.0577 | 825585.2165 | 826934.5226 | 828287.0152 | 829638.7915 | 830991.8029 | 832344.1968 | 833698.4433 | 835054.0238 | 836408.8878 |  | 2023-01-01: 862768.3296; 2023-02-01: 864164.9039; 2023-03-01: 865562.2161
Accural use Gas using actual $ | [39 empty] | 1038916.542 | 1041110.9095 | 1043995.1068 | 1045234.1822 | 1046061.2789 | 1038706.1923 | 1040246.9854 | 1041820.6245 | 1043432.1263 | 1045100.3544 | 1046815.1391 | 1048585.4596 |  | 1066903.4216 | 1068823.9186 | 1070768.868 | 1072695.7056 | 1073747.7922 | 1074738.0125 | 1076602.5903 | 1078493.5811 | 1080395.7228 | 1082321.5429 | 1084250.3097 | 1086193.0864 |  | 1104562.6081 | 1106514.0759 | 1108453.4774 | 1110378.6788 | 1112287.2909 | 1114260.9407 | 1116293.9726 | 1118335.7379 | 1120372.9171 | 1122420.2121 | 1124462.9212 | 1126507.29 |  | 1145650.5894 | 1147733.297 | 1149830.7102 | 438457.278 | 439251.204 | 440049.33 | 440848.338 | 441647.871 | 442445.997 | 443244.48 | 444041.472 | 444840.039 |  | 457175.4468 | 457992.537 | 458810.7043 | 459627.3421 | 460444.8847 | 461260.4453 | 462076.9107 | 462890.8555 | 463705.2527 | 464517.948 | 465329.7384 | 466141.9812 |  | 479307.1405 | 480139.7678 | 480970.825 | 481802.811 | 482632.7626 | 483462.6256 | 484293.5944 | 485123.5459 | 485954.4262 | 486783.8249 | 487614.7937 | 488444.1039 |  | 502507.9744 | 503360.8524 | 504212.5949 | 505064.9051 | 505916.7384 | 506770.0933 | 507622.4944 | 508475.4633 | 509329.9538 | 510184.0583 | 511039.6845 | 511894.9245 |  | 526952.876 | 527833.4589 | 528715.3022 | 529598.8027 | 530482.8867 | 531368.6279 | 532254.5559 | 533142.6312 | 534030.8933 | 534921.8862 | 535812.4824 | 536705.3192 |  | 552858.5289 | 553777.3101 | 554698.3956 | 555618.9771 | 556541.3588 | 557463.2365 | 558386.1223 | 559309.2001 | 560232.686 | 561156.2679 | 562080.9539 | 563005.1359 |  | 580345.7175 | 581297.5164 | 582250.3528 | 583203.288 | 584158.0759 | 585112.1474 | 586067.5529 | 587022.3408 | 587978.9813 | 588935.0043 | 589892.7812 | 590849.4217 |  | 2023-01-01: 609470.8459; 2023-02-01: 610456.6751; 2023-03-01: 611443.6745
Total Cost - Electric Reads - using percentage | [39 empty] | 1578883.0211 | 1581393.9615 | 1583456.2686 | 1558113.2477 | 1558568.6675 | 1575302.8349 | 1576811.4271 | 1578359.9395 | 1579985.0218 | 1581700.7684 | 1583491.1884 | 1585314.4787 |  | 1603595.8547 | 1605709.0422 | 1607606.8521 | 1609819.3714 | 1613173.9005 | 1616306.0477 | 1618841.522 | 1621431.0745 | 1623794.258 | 1626486.1052 | 1629223.6622 | 1632010.0471 |  | 1628130.3452 | 1630959.7103 | 1633809.2387 | 1636950.4934 | 1639826.292 | 1642710.8733 | 1645608.2071 | 1648519.4349 | 1651445.9805 | 1654388.3468 | 1657339.4323 | 1660307.5718 |  | 1682165.7708 | 1685197.5774 | 1688241.4706 | 620550.8877 | 621675.7717 | 622802.809 | 623932.307 | 625061.4974 | 626190.3802 | 627320.1859 | 628449.3763 | 629579.1819 |  | 647039.1989 | 648196.9967 | 649354.4789 | 650510.0678 | 651666.6033 | 652821.2455 | 653975.2566 | 655128.0054 | 656279.4919 | 657431.6096 | 658580.8872 | 659729.5337 |  | 678363.5478 | 679540.9654 | 680717.7351 | 681894.8288 | 683069.3312 | 684245.1292 | 685420.2794 | 686595.4296 | 687771.2276 | 688945.0822 | 690120.5563 | 691295.0586 |  | 711191.2147 | 712397.7941 | 713603.7332 | 714809.9798 | 716015.2536 | 717222.4982 | 718429.7429 | 719636.68 | 720846.2534 | 722055.1866 | 723266.0907 | 724477.3274 |  | 745795.8648 | 747043.7491 | 748291.6335 | 749541.9111 | 750793.2143 | 752046.5688 | 753300.6071 | 754557.0386 | 755815.1796 | 757076.0556 | 758336.5898 | 759599.1752 |  | 784969.742 | 786274.8477 | 787583.1177 | 788890.6845 | 790199.6577 | 791508.2793 | 792818.6589 | 794129.39 | 795441.1759 | 796753.3135 | 798065.451 | 799378.9948 |  | 821364.5684 | 822711.2807 | 824059.802 | 825409.7707 | 826618.63 | 827969.8153 | 829321.3624 | 830673.2712 | 832025.9035 | 833379.2594 | 834734.4241 | 836088.5035 |  | 2023-01-01: 862438.2948; 2023-02-01: 863833.9068; 2023-03-01: 865230.6365
Total Cost - Gas Reads - usuing percentage | [39 empty] | 1109492.6321 | 1111715.646 | 1114543.8483 | 1115841.1846 | 1116626.4363 | 1110177.6201 | 1111699.105 | 1113249.78 | 1114855.5407 | 1116526.4039 | 1118251.1566 | 1120000.3314 |  | 1133382.904 | 1135344.2903 | 1137623.4281 | 1139658.6327 | 1140622.4472 | 1141895.3989 | 1143686.6725 | 1145516.1516 | 1147658.6486 | 1149561.1814 | 1151496.0207 | 1153465.3704 |  | 1151197.6596 | 1153198.211 | 1155213.0192 | 1156957.1587 | 1158989.7039 | 1161028.4565 | 1163076.2221 | 1165133.8078 | 1167202.2197 | 1169281.8133 | 1171367.5694 | 1173465.3789 |  | 1188914.2271 | 1191057.035 | 1193208.3854 | 438590.4123 | 439385.4533 | 440182.016 | 440980.318 | 441778.4026 | 442576.2698 | 443374.7891 | 444172.8737 | 444971.3931 |  | 457311.7123 | 458130.0159 | 458948.0965 | 459764.8388 | 460582.2503 | 461398.3235 | 462213.9508 | 463028.6858 | 463842.5288 | 464656.8178 | 465469.0995 | 466280.9352 |  | 479451.0073 | 480283.1776 | 481114.8901 | 481946.8316 | 482776.9415 | 483607.9672 | 484438.5351 | 485269.1029 | 486100.1286 | 486929.7807 | 487760.5775 | 488590.6875 |  | 502652.8111 | 503505.5923 | 504357.921 | 505210.4671 | 506062.3255 | 506915.5769 | 507768.8284 | 508621.8624 | 509476.7598 | 510331.2046 | 511187.0424 | 512043.1153 |  | 527110.5438 | 527992.5184 | 528874.493 | 529758.159 | 530642.55 | 531528.3908 | 532414.7148 | 533302.7303 | 534191.954 | 535083.1108 | 535974.026 | 536866.391 |  | 554797.6961 | 555720.1134 | 556644.7671 | 557568.9238 | 558494.0745 | 559418.9767 | 560345.1214 | 561271.5146 | 562198.6533 | 563126.0405 | 564053.4276 | 564981.8088 |  | 580520.6824 | 581472.5061 | 582425.6085 | 583379.7338 | 584474.9685 | 585430.3474 | 586385.9821 | 587341.8725 | 588298.2746 | 589255.1882 | 590213.3808 | 591170.806 |  | 2023-01-01: 609801.8807; 2023-02-01: 610788.6722; 2023-03-01: 611776.2541
Total amount allocated and credited | [39 empty] | -217990.2958 | -218478.6881 | -218426.6133 | -218456.4933 | -218601.0733 | -219106.1748 | -219055.1165 | -218983.5892 | -218938.6876 | -218946.2416 | -218992.5405 | -219013.0094 |  | -187910.6031 | -188004.5939 | -188098.3885 | -188184.5475 | -188256.4552 | -188320.7272 | -188367.5264 | -188421.3531 | -188481.2068 | -188548.0881 | -188620.9963 | -188701.5401 |  | -121584.3333 | -121584.3333 | -121584.3333 | -121584.3333 | -121584.3333 | -121584.3333 | -121584.3333 | -121584.3333 | -121584.3333 | -121584.3333 | -121584.3333 | -121584.3333 |  | -96333.3333 | -96333.3333 | -96333.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 |  | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 |  | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 |  | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 |  | -4282.0207 | -4289.2217 | -4297.0228 | -4304.2239 | -4311.4249 | -4318.0259 | -4325.827 | -4332.428 | -4340.2291 | -4347.4301 | -4355.2313 | -4362.4323 |  | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | bar: 2023-01-01 to 2023-03-01
Electric portion | [39 empty] | -133192.0707 | -133490.4784 | -133458.6607 | -133476.9174 | -133565.2558 | -133873.8728 | -133842.6762 | -133798.973 | -133771.5381 | -133776.1536 | -133804.4422 | -133816.9488 |  | -114813.3785 | -114870.8069 | -114928.1154 | -114980.7585 | -115024.6941 | -115063.9643 | -115092.5586 | -115125.4468 | -115162.0174 | -115202.8818 | -115247.4287 | -115296.641 |  | -74288.0277 | -74288.0277 | -74288.0277 | -74288.0277 | -74288.0277 | -74288.0277 | -74288.0277 | -74288.0277 | -74288.0277 | -74288.0277 | -74288.0277 | -74288.0277 |  | -58859.6667 | -58859.6667 | -58859.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -0.611 | -0.611 | -0.611 | -0.611 | -0.611 | -0.611 | -0.611 | -0.611 | -0.611 | -0.611 | -0.611 | -0.611 |  | -0.611 | -0.611 | -0.611 | -0.611 | -0.611 | -0.611 | -0.611 | -0.611 | -0.611 | -0.611 | -0.611 | -0.611 |  | -0.611 | -0.611 | -0.611 | -0.611 | -0.611 | -0.611 | -0.611 | -0.611 | -0.611 | -0.611 | -0.611 | -0.611 |  | -0.611 | -0.611 | -0.611 | -0.611 | -0.611 | -0.611 | -0.611 | -0.611 | -0.611 | -0.611 | -0.611 | -0.611 |  | -2616.3146 | -2620.7145 | -2625.481 | -2629.8808 | -2634.2806 | -2638.3138 | -2643.0803 | -2647.1135 | -2651.88 | -2656.2798 | -2661.0463 | -2665.4461 |  | -0.611 | -0.611 | -0.611 | -0.611 | -0.611 | -0.611 | -0.611 | -0.611 | -0.611 | -0.611 | -0.611 | -0.611 |  | 2023-01-01: -0.611; 2023-02-01: -0.611; 2023-03-01: -0.611
Gas Portion | [39 empty] | -84798.2251 | -84988.2097 | -84967.9526 | -84979.5759 | -85035.8175 | -85232.302 | -85212.4403 | -85184.6162 | -85167.1495 | -85170.088 | -85188.0982 | -85196.0607 |  | -73097.2246 | -73133.787 | -73170.2731 | -73203.789 | -73231.7611 | -73256.7629 | -73274.9678 | -73295.9064 | -73319.1895 | -73345.2063 | -73373.5676 | -73404.8991 |  | -47296.3057 | -47296.3057 | -47296.3057 | -47296.3057 | -47296.3057 | -47296.3057 | -47296.3057 | -47296.3057 | -47296.3057 | -47296.3057 | -47296.3057 | -47296.3057 |  | -37473.6667 | -37473.6667 | -37473.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -0.389 | -0.389 | -0.389 | -0.389 | -0.389 | -0.389 | -0.389 | -0.389 | -0.389 | -0.389 | -0.389 | -0.389 |  | -0.389 | -0.389 | -0.389 | -0.389 | -0.389 | -0.389 | -0.389 | -0.389 | -0.389 | -0.389 | -0.389 | -0.389 |  | -0.389 | -0.389 | -0.389 | -0.389 | -0.389 | -0.389 | -0.389 | -0.389 | -0.389 | -0.389 | -0.389 | -0.389 |  | -0.389 | -0.389 | -0.389 | -0.389 | -0.389 | -0.389 | -0.389 | -0.389 | -0.389 | -0.389 | -0.389 | -0.389 |  | -1665.706 | -1668.5072 | -1671.5419 | -1674.3431 | -1677.1443 | -1679.7121 | -1682.7467 | -1685.3145 | -1688.3491 | -1691.1503 | -1694.185 | -1696.9862 |  | -0.389 | -0.389 | -0.389 | -0.389 | -0.389 | -0.389 | -0.389 | -0.389 | -0.389 | -0.389 | -0.389 | -0.389 |  | 2023-01-01: -0.389; 2023-02-01: -0.389; 2023-03-01: -0.389
Accural use Electric using %elec to gas method | [39 empty] | 1445690.9504 | 1447903.4831 | 1449997.6078 | 1424636.3303 | 1425003.4117 | 1441428.9621 | 1442968.7509 | 1444560.9665 | 1446213.4837 | 1447924.6148 | 1449686.7462 | 1451497.53 |  | 1488782.4762 | 1490838.2353 | 1492678.7367 | 1494838.6129 | 1498149.2064 | 1501242.0833 | 1503748.9634 | 1506305.6277 | 1508632.2406 | 1511283.2234 | 1513976.2334 | 1516713.4061 |  | 1553842.3175 | 1556671.6826 | 1559521.211 | 1562662.4657 | 1565538.2643 | 1568422.8456 | 1571320.1794 | 1574231.4072 | 1577157.9528 | 1580100.3192 | 1583051.4047 | 1586019.5441 |  | 1623306.1041 | 1626337.9107 | 1629381.804 | 620550.8877 | 621675.7717 | 622802.809 | 623932.307 | 625061.4974 | 626190.3802 | 627320.1859 | 628449.3763 | 629579.1819 |  | 647038.5879 | 648196.3857 | 649353.8679 | 650509.4568 | 651665.9923 | 652820.6345 | 653974.6456 | 655127.3944 | 656278.8809 | 657430.9986 | 658580.2762 | 659728.9227 |  | 678362.9368 | 679540.3544 | 680717.1241 | 681894.2178 | 683068.7202 | 684244.5182 | 685419.6684 | 686594.8186 | 687770.6166 | 688944.4712 | 690119.9453 | 691294.4476 |  | 711190.6037 | 712397.1831 | 713603.1222 | 714809.3688 | 716014.6426 | 717221.8872 | 718429.1319 | 719636.069 | 720845.6424 | 722054.5756 | 723265.4797 | 724476.7164 |  | 745795.2538 | 747043.1381 | 748291.0225 | 749541.3001 | 750792.6033 | 752045.9578 | 753299.9961 | 754556.4276 | 755814.5686 | 757075.4446 | 758335.9788 | 759598.5642 |  | 782353.4274 | 783654.1332 | 784957.6367 | 786260.8037 | 787565.3771 | 788869.9655 | 790175.5786 | 791482.2765 | 792789.296 | 794097.0336 | 795404.4047 | 796713.5487 |  | 821363.9574 | 822710.6697 | 824059.191 | 825409.1597 | 826618.019 | 827969.2043 | 829320.7514 | 830672.6602 | 832025.2925 | 833378.6484 | 834733.8131 | 836087.8925 |  | 2023-01-01: 862437.6838; 2023-02-01: 863833.2958; 2023-03-01: 865230.0255
Accural use Gas using %elec to gas method | [39 empty] | 1024694.407 | 1026727.4363 | 1029575.8957 | 1030861.6087 | 1031590.6188 | 1024945.3181 | 1026486.6647 | 1028065.1638 | 1029688.3912 | 1031356.3159 | 1033063.0584 | 1034804.2707 |  | 1060285.6794 | 1062210.5033 | 1064453.155 | 1066454.8437 | 1067390.6862 | 1068638.636 | 1070411.7048 | 1072220.2452 | 1074339.4592 | 1076215.9751 | 1078122.4531 | 1080060.4713 |  | 1103901.3539 | 1105901.9053 | 1107916.7136 | 1109660.8531 | 1111693.3982 | 1113732.1508 | 1115779.9165 | 1117837.5021 | 1119905.914 | 1121985.5077 | 1124071.2638 | 1126169.0732 |  | 1151440.5605 | 1153583.3683 | 1155734.7187 | 438590.4123 | 439385.4533 | 440182.016 | 440980.318 | 441778.4026 | 442576.2698 | 443374.7891 | 444172.8737 | 444971.3931 |  | 457311.3233 | 458129.6269 | 458947.7075 | 459764.4498 | 460581.8613 | 461397.9345 | 462213.5618 | 463028.2968 | 463842.1398 | 464656.4288 | 465468.7105 | 466280.5462 |  | 479450.6183 | 480282.7886 | 481114.5011 | 481946.4426 | 482776.5525 | 483607.5782 | 484438.1461 | 485268.7139 | 486099.7396 | 486929.3917 | 487760.1885 | 488590.2985 |  | 502652.4221 | 503505.2033 | 504357.532 | 505210.0781 | 506061.9365 | 506915.1879 | 507768.4394 | 508621.4734 | 509476.3708 | 510330.8156 | 511186.6534 | 512042.7263 |  | 527110.1548 | 527992.1294 | 528874.104 | 529757.77 | 530642.161 | 531528.0018 | 532414.3258 | 533302.3413 | 534191.565 | 535082.7218 | 535973.637 | 536866.002 |  | 553131.9901 | 554051.6061 | 554973.2252 | 555894.5807 | 556816.9302 | 557739.2647 | 558662.3747 | 559586.2001 | 560510.3042 | 561434.8901 | 562359.2427 | 563284.8226 |  | 580520.2934 | 581472.1171 | 582425.2195 | 583379.3448 | 584474.5795 | 585429.9584 | 586385.5931 | 587341.4835 | 588297.8856 | 589254.7992 | 590212.9918 | 591170.417 |  | 2023-01-01: 609801.4917; 2023-02-01: 610788.2832; 2023-03-01: 611775.8651
Difference…
Electric | [39 empty] | -14222.1349 | -14383.4731 | -14419.2111 | -14372.5735 | -14470.6601 | -13760.8742 | -13760.3207 | -13755.4607 | -13743.7351 | -13744.0385 | -13752.0807 | -13781.1889
Gas | [39 empty] | 14222.1349 | 14383.4731 | 14419.2111 | 14372.5735 | 14470.6601 | 13760.8742 | 13760.3207 | 13755.4607 | 13743.7351 | 13744.0385 | 13752.0807 | 13781.1889

## Glossary
Glossary
| CVR | Conservation Voltage Reduction (No network)
| VO | Voltage Optimization (network)
Load Profile Service
| AMR | *AMR-Automatic meter reading, or AMR, is the technology of automatically collecting consumption, diagnostic, and status data from water meter or energy metering devices (gas, electric) and transferring that data to a central database for billing, troubleshooting, and analyzing.
| AMI | *AMI-Advanced Metering Infrastructure are systems that measure, collect and analyse energy usage, and communicate with metering devices such as electricity meters, gas meters, heat meters, and water meters, either on request or on a schedule. These systems include hardware, software, communications, consumer energy displays and controllers, customer associated systems, Meter Data Management (MDM) software, and supplier business systems. -Wikipedia
| Point-to-Point | *Point-to-point-The simplest topology is a permanent link between two endpoints. Switched point-to-point topologies are the basic model of conventional telephony. The value of a permanent point-to-point network is unimpeded communications between the two endpoints.
| Mesh | *Mesh- Mesh networking (topology) is a type of networking where each node must not only capture and disseminate its own data, but also serve as a relay for other nodes, that is, it must collaborate to propagate the data in the network.
| PLC | *PLC – Power Line Carrier- are systems for carrying data on a conductor also used for electric power transmission.