## Figure 8
New WBS | New Description | % OMRC | Column2 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022
R.10009.08.05.05 | E-POLE REPLACEMENT PLAN-DIST |  | 4156110.4917 | 6156870.23 | 4636458.63 | 4485470.63 | 3719809.97 | 2863673.37 | 3074380.12 | 5230590 | 8965969 | 6625922 | 6824700 | 7029441 | 4598066
R.10009.08.05.07 | E-POLE REPLACEMENT PLAN-TRANS | 0.15 | 1992736.8667 | 4282445.9 | 1611042.28 | 2680653.71 | 2095945.32 | 927104.94 | 359229.05 | 1275520 | 2728747 | 2195023 | 2260874 | 2328700 | 2299033
R.10009.08.05.08 | E-POLE REPLACEMENT PROGRAM-REMOVAL-DIST |  | 2017: 0; 2018: 0; 2019: 0; 2020: 0; 2021: 0; 2022: 0
[5 empty] | 600 | 526 | 379 | 277 | 432 | 344 | 177
[5 empty] | 102 | 177 | 116 | 48 | 46 | 58 | 57
[5 empty] | 7727.4311 | 8527.5107 | 9814.802 | 10338.171 | 7116.6206 | 15205.2035
[5 empty] | 15794.5322 | 15144.9362 | 18068.4941 | 19314.6862 | 7809.3272 | 21991.7241
|  | 600 | Column2: 102
|  | 526 | Column2: 177
|  | 379 | Column2: 116
|  | 277 | Column2: 48
|  | 432 | Column2: 46
|  | 304 | Column2: 40

## Figure 9
Leak Grade | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018
Grade A and BA | 714 | 673 | 519 | 469 | 527 | 507 | 460 | 336 | 355 | 266 | 352 | 364 | 346
Grade B1 and B2 | 524 | 555 | 401 | 273 | 293 | 352 | 408 | 177 | 191 | 119 | 88 | 126 | 114
Grade C | 678 | 1004 | 677 | 676 | 756 | 838 | 922 | 440 | 458 | 276 | 132 | 191 | 189
Total New Leaks (all grades) | 1916 | 2232 | 1597 | 1418 | 1576 | 1697 | 1790 | 953 | 1004 | 661 | 572 | 681 | 649

## Figure 10
| Active Grade C Leaks - Planned | Active Grade C Leaks - Actuals | Active Grade B Leaks - Planned | Active Grade B Leaks -Actuals | Active Grade C Leaks - New Plan
2013 | 2628 | 2397 | 220 | 149
2014 | 2500 | 2105 | 160 | 126
2015 | 2372 | 1785 | 100 | 63 | 2372
2016 | 2244 | 989 | 100 | 100 | 900
2017 | 2116 |  | 100 | 50 | 600
2018 | 1988 |  | 100 | 25 | 300
2019 |  |  |  | 25 | 150
2020 |  |  |  | 25 | 125
2021 |  |  |  | 25 | 125
New Goal as of 8/29/16 - Get to 1st quartile forleaks which means total active leaks less than 147 (B & C together)
| Active C Leaks | Active B leaks | Active Nonhazardous Leak Count - Planned | Active Nonhazardous Leak Count - Actual | Active Nonhazardous Leak Count - Previous Planned
2013 | 2628 | 220 |  | 2546 | 2848
2014 | 2500 | 160 |  | 2231 | 2660
2015 | 2372 | 100 |  | 1848 | 2472
2016 | 900 | 100 |  | 1042 | 1000
2017 | 600 | 70 |  | 828 | 670
2018 | 500 | 70 | 558 | 558 | 570
2019 | 370 | 70 | 440
2020 | 250 | 60 | 310
2021 | 160 | 50 | 210
2022 | 100 | 50 | 150
2023 | 100 | 50 | 150
2024 | 100 | 50 | 150
| Active C leaks | Active B leaks | Active Nonhazardous Leak Count - Planned | Active Nonhazardous Leak Count - Actual
2012 | 2628 | 286 |  | 2914
2013 | 2397 | 149 |  | 2546
2014 | 2105 | 126 |  | 2231
2015 | 1785 | 63 |  | 1848
2016 | 989 | 53 |  | 1042
2017 | 728 | 100 |  | 828
2018 | 482 | 76 | 558 | 558
2019 |  |  | 440
2020 |  |  | 310
2021 |  |  | 210
2022 |  |  | 150
2023 |  |  | 150
2024 |  |  | 150

## Figure 11
Gas and Electric Damages: 2015 - 2018
| 2015 | 2016 | 2017 | 2018
Damages
Gas | 1020 | 1011 | 976 | 1035
Elec | 330 | 311 | 318 | 293
Total damages | 1350 | 1322 | 1294 | 1328
Locates
Gas Locates | 169879 | 185497 | 256325 | 302118
Total locates | 298298 | 329950 | 444044 | 514048
Ratios
Gas damage ratio (to enable comparison with AGA data) | 6.0043 | 5.4502 | 3.8077 | 3.4258
Damage ratio--total damages (Damages per 1,000 locates) | 4.5257 | 4.0067 | 2.9141 | 2.5834

## Figure 12
| Post Construction Inspection | Blocked Sewer | Legacy Inspection
Average Prior to Program | 0 | 35.5 | 0
Average Since Inception of Program | 19.3 | 70.8 | 20.3

## Figure 13
Material | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 Plan
DuPont Actuals | 6.5 | 10.5 | 28.6 | 27.4 | 27.9 | 38.8 | 30
[5 empty] | 147312 | 204864
|  |  |  | Total Footage | 352176 | (Including 3 months in 2016 brings it to 400,000)
|  |  |  | Number of Projects | 300 | (Shane Richards has exact number)

## Figure 3
Annual IEEE benchmark survey information translated to picture.