## Sheet4
Funding Type | RRM 18
Row Labels | Count of Project Description
AIR-23 | 1
BRW-16 | 1
BTN-36 | 1
CAS-15 | 1
CHI-12 | 1
CPV-15 | 1
CUS-13 | 1
DGR-16 | 1
EGT-12 | 1
ELL-14 | 1
ETN-13 | 1
FCR-14 | 1
FRA-16 | 1
GRV-16 | 1
GWR-16 | 1
HAZ-13 | 1
HKX-16 | 1
KIN-24 | 1
KLA-17 | 1
KNO-14 | 1
MCA-16 | 1
MCW-15 | 1
MER-13 | 2
MKI-17 | 1
MOT-16 | 1
MST-26 | 1
MUR-13 | 1
NNO-15 | 1
ORT-23 | 1
PAT-15 | 1
PEA-17 | 1
PET-12 | 1
PLG-13 | 1
RIT-16 | 1
RIV-16 | 1
RJN-12 | 1
ROC-16 | 1
RPT-16 | 1
SHE-17 | 1
SKE-26 | 1
SLA-16 | 1
SNQ-13 | 1
SNQ-17 | 1
SST-14 | 1
SUN-13 | 1
SWD-12 | 1
KWH-23 | 1
Grand Total | 48

## 2017 and 2018 RRM
Project Description | Leading Order | Project PM | Funding Type | Start | Finish | baseline Yr | status | SAIDI | County | WBS from IW32 | Reliability Report Program | Ricks Guess | CKT | Include
2602E116 SKE-26/MIL17 Add GOP | 101104352 | Ibarra, V | RRM 18 | 2017-12-15 | 2018-01-10 | new | completed | 0 | Kitsap | R.10009.08.02.11 | Sectionalizing Devices | Distribution Sectionalizing Devices | SKE-26 | Include
2404E074 MER-13 REL PRJ on SE 32 ST | 101102527 | Tuntland, J | RRM 18 | 2017-01-17 | 2018-01-18 | 2018 baseline | completed | 0.091232 | King | R.10009.08.02.10 | Other System Reliability Projects |  | MER-13 | Include
2202E016 FRA-16 Forsman Rd | 101108566 | Ibarra, V | RRM 18 | 2017-12-15 | 2018-01-18 | new | completed | 0 | Kitsap | R.10009.08.02.11 | Exclude | EFR project | FRA-16 | Include
3504E144 RIT-16 Recloser | 101085827 | Brock, S | RRM 18 | 2017-12-15 | 2018-01-19 | new | completed | 0.01072 | Skagit | R.10009.08.02.12 | Sectionalizing Devices | Distribution Sectionalizing Devices | RIT-16 | Include
2014E136 CAS-15/16 SR903 | 101100415 | Tuntland, J | RRM 18 | 2017-12-15 | 2018-01-19 | new | completed | 0 | Kittitas | R.10009.08.02.07 | Other System Reliability Projects |  | CAS-15 | Include
1901W131 PLG-13 Hawks Prairie Recl 2017 RI (Recloser) | 101102501 | Potelco | RRM 18 | 2017-11-01 | 2018-02-05 | 2018 baseline | completed | 0.068545 | Thurston | R.10009.08.02.12 | Sectionalizing Devices | Distribution Sectionalizing Devices | PLG-13 | Include
1701W076 AIR-23 OLD HWY 99 2017 RI RECL (Recloser) | 101105407 | Potelco | RRM 18 | 2018-01-30 | 2018-02-08 | 2018 baseline | completed | 0 | Thurston | R.10009.08.02.12 | Sectionalizing Devices | Distribution Sectionalizing Devices | AIR-23 | Include
3803E117 SST-14 Ohio St Reconductor | 101086623 | Brock, S | RRM 18 | 2017-04-03 | 2018-02-16 | 2018 baseline | completed | 0.018383 | Whatcom | R.10009.08.02.17 | Other System Reliability Projects |  | SST-14 | Include
2004E002 DGR-16 BUTTE AVE SE FDR TIE TO ELL-14 (Net Auto G | 101102048 | Tuntland, J | RRM 18 | 2017-04-03 | 2018-02-28 | 2018 baseline | completed | 0.00088167 | Pierce | R.10009.08.02.17 | Other System Reliability Projects |  | DGR-16 | Include
2206E104 FCR-14 SE KENT-KANGLEY RD 2017 RI (recloser) | 101102506 | Potelco | RRM 18 | 2017-03-01 | 2018-02-28 | 2018 baseline | completed | 0.0098663 | King | R.10009.08.02.12 | Sectionalizing Devices | Distribution Sectionalizing Devices | FCR-14 | Include
1905E064 KNO-14 Tehaleh New UG Fdr | 101102047 | Tuntland, J | RRM 18 | 2017-03-01 | 2018-03-06 | 2018 baseline | completed | 0 | Pierce | R.10009.07.01.03 | Other System Reliability Projects |  | KNO-14 | Include
1802W096 MKI-17 Blvd Rd SE Recl 2017 RI (Recloser) | 101102503 | Potelco | RRM 18 | 2017-05-22 | 2018-03-08 | 2018 baseline | completed | 0.01587 | Thurston | R.10009.08.02.12 | Sectionalizing Devices | Distribution Sectionalizing Devices | MKI-17 | Include
2408E117 SNQ-13 UG CONV 8400 LF Snoqualmie Parkway | 101107833 | Tuntland, J | RRM 18 | 2017-12-15 | 2018-03-12 | new | completed | 0 | King | R.10009.08.02.28 | Exclude | Capacity | SNQ-13 | Include
2404E047 MER-13 A&C FDR TW ON SE 32 ST | 101102046 | Tuntland, J | RRM 18 | 2017-01-17 | 2018-03-23 | 2018 baseline | completed | 0.091232 | King | R.10009.08.02.14 | Tree Wire | treewire | MER-13 | Include
1701W003 PAT-15 Yelm Hwy Recl 2017 RI (Recloser) | 101102502 | Potelco | RRM 18 | 2018-01-29 | 2018-03-27 | 2018 baseline | completed | 0.18998 | Thurston | R.10009.08.02.12 | Sectionalizing Devices | Distribution Sectionalizing Devices | PAT-15 | Include
3101E048 CPV-15 Fort Casey Road Tree Wire | 101095674 | Brock, S | RRM 18 | 2016-11-01 | 2018-03-30 | 2018 baseline | completed | 0.016681 | Island | R.10009.08.02.14 | Tree Wire | treewire | CPV-15 | Include
2104E137 PEA-17 FEEDER TIE TO ELL-14 (Net Auto Grid) | 101106104 | Tuntland, J | RRM 18 | 2017-04-03 | 2018-03-30 | 2018 baseline | completed | 0.018305 | King | R.10009.12.03.04 | Other System Reliability Projects | Other System Reliability Projects | PEA-17 | Include
1902E103 GRV-16 104TH ST RECL 2017 RI (Recloser) | 101102504 | Potelco | RRM 18 | 2017-03-01 | 2018-04-03 | 2018 baseline | completed | 0.030229 | Pierce | R.10009.08.02.12 | Sectionalizing Devices | Distribution Sectionalizing Devices | GRV-16 | Include
2304E122&119 NNO-15 Marine View TW | 101086640 | Tuntland, J | RRM 18 | 2014-06-09 | 2018-04-13 | 2018 baseline | completed | 0.00029564 | King | R.10009.08.02.14 | Tree Wire | treewire | NNO-15 | Include
2601E004 SWD-12 Stottlemyre Recl 2017 RI | 101102456 | Potelco | RRM 18 | 2017-03-22 | 2018-04-19 | 2018 baseline | completed | 0.041594 | Kitsap | R.10009.08.02.12 | Sectionalizing Devices | Distribution Sectionalizing Devices | SWD-12 | Include
2502E120 MCW-15 Illahee Rd Recl 2017 RI | 101102458 | Potelco | RRM 18 | 2017-04-03 | 2018-04-20 | 2018 baseline | completed | 0.12839 | Kitsap | R.10009.08.02.12 | Sectionalizing Devices | Distribution Sectionalizing Devices | MCW-15 | Include
2408E126 SNQ-17 MEADOWBRO X948 RECL 2017 | 101102902 | Potelco | RRM 18 | 2017-03-01 | 2018-04-24 | 2018 baseline | completed | 0.051725 | King | R.10009.08.02.12 | Sectionalizing Devices | Distribution Sectionalizing Devices | SNQ-17 | Include
2406E042 KLA-17 Recon 1750' A&Cph 336TW 251Av SE | 101095827 | Tuntland, J | RRM 18 | 2017-07-10 | 2018-04-30 | 2018 baseline | completed | 0.017033 | King | R.10009.08.02.14 | Tree Wire | treewire | KLA-17 | Include
2105E071 MST-26 D ST SE FEEDER | 101102051 | Tuntland, J | RRM 18 | 2017-02-01 | 2018-05-02 | 2019 baseline | completed | 0 | King | R.10009.08.02.17 | Other System Reliability Projects |  | MST-26 | Include
3802E032 SLA-16 HAXTON WAY RECL 2017 | 101102505 | Potelco | RRM 18 | 2017-03-01 | 2018-05-11 | 2018 baseline | completed | 0.0062977 | Whatcom | R.10009.08.02.12 | Sectionalizing Devices | Distribution Sectionalizing Devices | SLA-16 | Include
3501E107 BRW-16 3 Phase UG | 101092451 | Tuntland, J | RRM 18 | 2016-06-01 | 2018-05-25 | 2018 baseline | completed | 0.10393 | Skagit | R.10009.08.02.25 | Other System Reliability Projects |  | BRW-16 | Include
2502E104 MUR-13 Wing Pt Recl 2017 RI | 101102457 | Potelco | RRM 18 | 2017-04-03 | 2018-05-31 | 2018 baseline | completed | 0.063984 | Kitsap | R.10009.08.02.12 | Sectionalizing Devices | Distribution Sectionalizing Devices | MUR-13 | Include
2802E064 KIN-24 Twin Spits Recl 2017 RI | 101102454 | Potelco | RRM 18 | 2017-03-01 | 2018-06-06 | 2018 baseline | completed | 0.53194 | Kitsap | R.10009.08.02.12 | Sectionalizing Devices | Distribution Sectionalizing Devices | KIN-24 | Include
2104E142 ELL-14 FDR TIE TO DGR-16 & PEA-17 (Net Auto Grid) | 101106105 | Tuntland, J | RRM 18 | 2017-05-01 | 2018-06-11 | 2018 baseline | completed | 0 | King | R.10009.12.03.04 | Other System Reliability Projects | Feeder ties | ELL-14 | Include
4001E092 CUS-13 INSTALL RECLOSER 2017RI (Recloser) | 101104484 | Potelco | RRM 18 | 2018-01-02 | 2018-06-27 | 2018 baseline | completed | 0.0072213 | Whatcom | R.10009.08.02.12 | Sectionalizing Devices | Distribution Sectionalizing Devices | CUS-13 | Include
3404E076 MTV Alley Project 1st - 2nd St | 101085638 | Brock, S | RRM 18 | 2017-12-15 | 2018-06-28 | new | completed | 0 | Skagit | R.10009.08.02.05 | Other System Reliability Projects |  | RIV-16 | Include
2401W020 CHI-12 Holly Rd Recl & GOPT 2017 RI | 101102459 | Potelco | RRM 18 | 2017-04-03 | 2018-07-06 | 2018 baseline | completed | 0.41861 | Kitsap | R.10009.08.02.12 | Sectionalizing Devices | Distribution Sectionalizing Devices | CHI-12 | Include
1801E076 MCA-16 PACIFIC FEEDER TW (OH Outage Tree Wire) | 101091963 | Kumar, D | RRM 18 | 2017-09-08 | 2018-07-16 | 2018 baseline | completed | 0.19142 | Thurston | R.10009.08.02.14 | Tree Wire | treewire | MCA-16 | Include
2405E113 HAZ-13 INST REC 11456 NEWCASTLE | 101110976 | Tuntland, J | RRM 18 | 2018-03-05 | 2018-07-27 | 2018 baseline | completed | 0 | King | R.10009.08.02.12 | Sectionalizing Devices |  | HAZ-13 | Include
2304E101 RJN-12, 26 SOU-24 Southcenter Vault Room JCP & S | 101089099 | Ibarra, V | RRM 18 | 2017-03-01 | 2018-08-01 | 2018 baseline | completed | 0 | King | R.10009.08.02.25 | Other System Reliability Projects |  | RJN-12 | Include
HKX-16 CEDARDALE RECLOSER | 101099585 | Brock, S | RRM 18 | 2016-01-03 | 2018-08-06 | 2018 baseline | completed | 0.14145 | Skagit | R.10009.08.02.12 | Sectionalizing Devices | Distribution Sectionalizing Devices | HKX-16 | Include
2505143 KWH-23 FDR TW Recond W LK Samm | 101102467 | Tuntland, J | RRM 18 | 2018-01-02 | 2018-08-31 | 2018 baseline | completed | 0.0047337 | King | R.10009.08.02.14 | Tree Wire | treewire | KWH-23 | Include
DA - PAD-15 (Padilla Bay Pipeline, Anacortes) | 141003921 | Lombard, B | RRM 18 DA | 2017-08-08 | 2018-08-31 | 2018 baseline | completed | 0 | Skagit | R.10009.12.03.01 | Distribution Automation | Distribution Automation | PAD-15 | exclude
1603W012 ROC-16 WADDLE CR 3PH #2TW AND 3 PHASING | 101095549 | Kumar, D | RRM 18 | 2015-10-29 | 2018-09-05 | 2018 baseline | completed | 0.010721 | Thurston | R.10009.08.02.17 | Other System Reliability Projects |  | ROC-16 | Include
1904E098 SUN-13 NEW PMH9 (UG Capacity) | 101104571 | Tuntland, J | RRM 18 | 2018-01-02 | 2018-09-14 | 2018 baseline | completed | 0 | Pierce | R.10009.07.01.03 | Other System Reliability Projects |  | SUN-13 | Include
1710E096 GWR-16 REPL OLD RECL E724&E725 (Recloser) | 101105408 | Potelco | RRM 18 | 2017-08-07 | 2018-09-18 | 2018 baseline | completed | 0 | King | R.10009.08.02.12 | Sectionalizing Devices | Distribution Sectionalizing Devices | GWR-16 | Include
1802W104 MOT-16 Mottman Rd SW 336 TW | 101085529 | Kumar, D | RRM 18 | 2016-12-21 | 2018-09-19 | 2018 baseline | completed | 0.0042299 | Thurston | R.10009.08.02.14 | Tree Wire | treewire | MOT-16 | Include
1805E036 ORT-23 208 ST E UG TIE | 101077717 | Tuntland, J | RRM 18 | 2013-05-07 | 2018-09-21 | 2018 baseline | completed | 0.020085 | Pierce | R.10009.08.02.10 | Other System Reliability Projects |  | ORT-23 | Include
2405E092 EGT-12 A&C FDR TW Project (OH Outage Tree Wire) | 101109244 | Tuntland, J | RRM 18 | 2018-01-02 | 2018-09-21 | 2018 baseline | completed | 0.045482 | King | R.10009.08.02.14 | Tree Wire | treewire | EGT-12 | Include
DA - BKB-13 | 141003513 | Lombard, B | RRM 18 DA | 2017-11-01 | 2018-10-09 | 2018 baseline | completed | 0.0016068 | Skagit | R.10009.12.03.01 | Distribution Automation | Distribution Automation | BKB-13 | exclude
2401E040 RPT 16 PM SW RPLC 2261 | 101085535 | Ibarra, V | RRM 18 | 2016-08-15 | 2018-10-19 | 2018 baseline | completed | 0 | Kitsap | R.10009.08.02.25 | Other System Reliability Projects |  | RPT-16 | Include
3503E096 BTN-36 PULVER RD (Repl CU w/Tree Wire) | 101095672 | Brock, S | RRM 18 | 2016-03-15 | 2018-10-22 | 2018 baseline | completed | 0.0014196 | Skagit | R.10009.08.02.22 | Tree Wire | treewire | BTN-36 | Include
DA CAM-26 DISTRIBUTION AUTOMATION-CMM (Cambridge, Kent)--2 | 141003662 | Lombard, B | RRM 18 DA | 2017-11-01 | 2018-10-23 | 2018 baseline | completed | 0.53696 | King | R.10009.12.03.01 | Distribution Automation | Distribution Automation | CAM-26 | exclude
3403E048 PET-12 FEEDER TIE TO BTN-38 | 101085572 | Brock, S | RRM 18 | 2018-02-12 | 2018-10-26 | 2018 baseline | completed | 0.020768 | Skagit | R.10009.08.02.17 | Other System Reliability Projects |  | PET-12 | Include
2112E088 ETN-13 Stampede KX334 RECL 2017 | 101102903 | Potelco | RRM 18 | 2017-03-01 | 2018-10-26 | 2018 baseline | completed | 0.0035582 | Kittitas | R.10009.08.02.12 | Sectionalizing Devices | Distribution Sectionalizing Devices | ETN-13 | Include
2401E008 SHE-17 Pine Rd & Sylvan Recl 2017 RI | 101102455 | Potelco | RRM 18 | 2017-03-01 | 2018-11-07 | 2018 baseline | completed | 0.14367 | Kitsap | R.10009.08.02.12 | Sectionalizing Devices | Distribution Sectionalizing Devices | SHE-17 | Include
DA 1904E020 WOO-23, -26, -27 DA PROJECT | 141003148 | Lombard, B | RRM 18 DA | 2017-11-01 | 2018-11-07 | 2018 baseline | completed | 0.22429 | Pierce | R.10009.12.03.01 | Distribution Automation | Distribution Automation | WOO-23 | exclude
DA - PAN-12 (Panther Lake, Kent) | 141003665 | Lombard, B | RRM 18 DA | 2017-08-08 | 2018-12-20 | 2018 baseline | completed | 0.17165 | King | R.10009.12.03.01 | Distribution Automation | Distribution Automation | PAN-12 | exclude
DA PET-16 (Peths Corner, Mt. Vernon)--3403E096 DISTRIBUTIO | 141003762 | Lombard, B | RRM 18 DA | 2018-01-02 | 2018-12-21 | 2018 baseline | completed | 0.026432 | Skagit | R.10009.12.03.01 | Distribution Automation | Distribution Automation | PET-16 | exclude
2604E097 ING-15 NE 132ND TRIPSAVER 2016 | 101099046 |  | RRM 2017 |  | 2017-01-11 |  | completed |  | King | R.10009.08.02.15 |  |  | ING-15 | Include
2604E002 KNM-26 68TH AVE TRIPSAVER 2016 | 101099044 |  | RRM 2017 |  | 2017-01-17 |  | completed |  | King | R.10009.08.02.15 |  |  | KNM-26 | Include
2607E074 DUV-15 NE BIG RO TRIPSAVER 2016 | 101099080 |  | RRM 2017 |  | 2017-01-18 |  | completed |  | King | R.10009.08.02.15 |  |  | DUV-15 | Include
2605E017 NBO-22 112TH AVE TRIPSAVER 2016 | 101099045 |  | RRM 2017 |  | 2017-01-18 |  | completed |  | King | R.10009.08.02.15 |  |  | NBO-22 | Include
2605E030 WAY-12 VALLEY VI TRIPSAVER 2016 | 101099079 |  | RRM 2017 |  | 2017-01-18 |  | completed |  | King | R.10009.08.02.15 |  |  | WAY-12 | Include
1818E132 THO-13 HANSON RD TRIPSAVER 2016 | 101099195 |  | RRM 2017 |  | 2017-01-19 |  | completed |  | Kittitas | R.10009.08.02.15 |  |  | THO-13 | Include
2306E076 LMC-25 SE JONES TRIPSAVER 2016 | 101099188 |  | RRM 2017 |  | 2017-01-20 |  | completed |  | King | R.10009.08.02.15 |  |  | LMC-25 | Include
2506E020 UHL-25 INST RECL X11229 2016 RI | 101097568 |  | RRM 2017 |  | 2017-01-24 |  | completed |  | King | R.10009.08.02.12 |  |  | UHL-25 | Include
2604E048 WAY-15 INST RECL X11740 2016 RI | 101097569 |  | RRM 2017 |  | 2017-01-30 |  | completed |  | King | R.10009.08.02.12 |  |  | WAY-15 | Include
2405E058 EGT-27 ALLEN RD RECL & GOP 2015 | 101094173 |  | RRM 2017 |  | 2017-01-31 |  | completed |  | King | R.10009.08.02.12 |  |  | EGT-27 | Include
2306E100 MIR-15 TIGER M R TRIPSAVER 2016 | 101099191 |  | RRM 2017 |  | 2017-02-02 |  | completed |  | King | R.10009.08.02.15 |  |  | MIR-15 | Include
2506E040 UHL-23 INST RECL X53 & X56 2016 | 101096197 |  | RRM 2017 |  | 2017-02-06 |  | completed |  | King | R.10009.08.02.12 |  |  | UHL-23 | Include
2405E044 SE 35TH PL & 164TH PL SE EASTGA | 101099187 |  | RRM 2017 |  | 2017-02-14 |  | completed |  | King | R.10009.08.02.15 |  |  | EGT-11 | Include
2015E078 CAS-16 SUNCADIA FDRTIE TO SR903 (OH Outage Duration) | 101085509 |  | RRM 2017 |  | 2017-02-17 |  | completed |  | Kittitas | R.10009.08.02.07 |  |  | CAS-16 | Include
2405E132 13245 SE MAY CRK RD(89TH)-PI | 101099800 |  | RRM 2017 |  | 2017-04-14 |  | completed |  | King | R.10009.08.02.09 |  |  | HAZ-16 | Include
2505E128 SBE-25 REL PRJT @ SURREY DOWNS (UG Conversion) | 101096121 |  | RRM 2017 |  | 2017-08-22 |  | completed |  | King | R.10009.08.02.10 |  |  | SBE-25 | Include
2606E088 DUV-13 Tree Wire NE 145th St (OH Rebuild) (2606E096 STILLWATER-COTTAGE BROOK RECOND) | 111020425 |  | RRM 2017 |  | 2017-09-26 |  | completed |  | King | R.10009.08.02.09 |  |  | DUV-13 | Include
2605E114 JUA-25 FDR TW NE 132 ST (OH Outage Tree Wire) | 101092469 |  | RRM 2017 |  | 2017-11-29 |  | completed |  | King | R.10009.08.02.14 |  |  | JUA-25 | Include
2604E041 KNM-27 NE 185th St TW (OH Outage Tree Wire) | 101101738 |  | RRM 2017 |  | 2017-12-15 |  | completed |  | King | R.10009.08.02.14 |  |  | KNM-27 | Include
3509E084 BRS-24 SAUK STORE RECLO 2016 RI | 101099586 |  | RRM 2017 |  | 2017-01-04 |  | completed |  | Skagit | R.10009.08.02.12 |  |  | BRS-24 | Include
3405E036 BIG-12 OLD DAY TRIPSAVER 2016 | 101098953 |  | RRM 2017 |  | 2017-01-04 |  | completed |  | Skagit | R.10009.08.02.15 |  |  | BIG-12 | Include
3704E128 ALG-15 NULLE RD TRIPSAVER 2016 | 101098956 |  | RRM 2017 |  | 2017-01-10 |  | completed |  | Skagit | R.10009.08.02.15 |  |  | ALG-15 | Include
4003E028 BHS-11 BADGER TRIPSAVER 2016 | 101099137 |  | RRM 2017 |  | 2017-01-12 |  | completed |  | Whatcom | R.10009.08.02.15 |  |  | BHS-11 | Include
4002E052 BHS-11 GUIDE TRIPSAVER 2016 | 101099138 |  | RRM 2017 |  | 2017-01-12 |  | completed |  | Whatcom | R.10009.08.02.15 |  |  | BHS-11 | Include
4001E084 CUS-13 PORTAL TRIPSAVER 2016 | 101099135 |  | RRM 2017 |  | 2017-01-12 |  | completed |  | Whatcom | R.10009.08.02.15 |  |  | CUS-13 | Include
4004E032 SCH-13 VAN BUREN TRIPSAVER 2016 | 101099133 |  | RRM 2017 |  | 2017-01-12 |  | completed |  | Whatcom | R.10009.08.02.15 |  |  | SCH-13 | Include
4004E044 SCH-16 MORGAN TRIPSAVER 2016 | 101099136 |  | RRM 2017 |  | 2017-01-12 |  | completed |  | Whatcom | R.10009.08.02.15 |  |  | SCH-16 | Include
3801E012 SLA-15 SLATER RD TRIPSAVER 2016 | 101099131 |  | RRM 2017 |  | 2017-01-12 |  | completed |  | Whatcom | R.10009.08.02.15 |  |  | SLA-15 | Include
2903E144 LGY-12 COMMERCIAL TRIPSAVR 2016 | 101099182 |  | RRM 2017 |  | 2017-01-17 |  | completed |  | Island | R.10009.08.02.15 |  |  | LGY-12 | Include
3101E036 CPV-15 ENGLE RD TRIPSAVER 2016 | 101098960 |  | RRM 2017 |  | 2017-01-20 |  | completed |  | Island | R.10009.08.02.15 |  |  | CPV-15 | Include
2903E048 BRO-15 SANDY PT TRIPSAVER 2016 | 101099061 |  | RRM 2017 |  | 2017-01-25 |  | completed |  | Island | R.10009.08.02.15 |  |  | BRO-15 | Include
3304E096 HKX-16 ESTATE DR TRIPSAVER (2016) | 101099151 |  | RRM 2017 |  | 2017-01-30 |  | completed |  | Skagit | R.10009.08.02.15 |  |  | HKX-16 | Include
3003E136 BRO-15 PARK AVE TRIPSAVER 2016 | 101099019 |  | RRM 2017 |  | 2017-01-30 |  | completed |  | Island | R.10009.08.02.15 |  |  | BRO-15 | Include
3506E096 HAM-13 CONDUCTOR SLAPPING (2016) (OH Rebuild) | 101095252 |  | RRM 2017 |  | 2017-02-14 |  | completed |  | Skagit | R.10009.08.02.09 |  |  | HAM-13 | Include
4003E080 LYN-16 FRONT ST GO RI 2017 (GOP) | 101103623 |  | RRM 2017 |  | 2017-03-02 |  | completed |  | Whatcom | R.10009.08.02.11 |  |  | LYN-16 | Include
4003E064 LYN-16 RCLU1590 130 MAIN ST, L (Recloser) | 101098497 |  | RRM 2017 |  | 2017-09-12 |  | completed |  | Whatcom | R.10009.08.02.12 |  |  | LYN-16 | Include
3505E084 NLM-13 TO HAM-13 FEEDER TIE (OH Outage Tree Wire) | 101085566 |  | RRM 2017 |  | 2017-11-29 |  | completed |  | Skagit | R.10009.08.02.14 |  |  | NLM-13 | Include
3802E028 LAB-25 LUMMI SHORE FDR PH3 (PH3) (OH Outage Duration) | 101089950 |  | RRM 2017 |  | 2018-01-03 |  | completed |  | Whatcom | R.10009.08.02.07 |  |  | LAB-25 | Include
4003E064 LYN-26 RCL1706 VINUP RD LYNDEN (Recloser) | 101098496 |  | RRM 2017 |  | 2018-03-29 |  | completed |  | Whatcom | R.10009.08.02.12 |  |  | LYN-26 | Include
4003E064 VIS-26 RCL3688 6917 ENTERPRISE (Recloser) | 101098498 |  | RRM 2017 |  | 2018-03-29 |  | completed |  | Whatcom | R.10009.08.02.12 |  |  | VIS-26 | Include
4003E064 VIS-26 RCL1983 1869 GRANDVIEW (Recloser) | 101098499 |  | RRM 2017 |  | 2018-03-29 |  | completed |  | Whatcom | R.10009.08.02.12 |  |  | VIS-26 | Include
2106E022 PIP-23 INSTALL RECLOSER 2016 RR | 101094170 |  | RRM 2017 |  | 2017-01-27 |  | completed |  | King | R.10009.08.02.12 |  |  | PIP-23 | Include
2205E072 ORC-17 INST TRIPSAVER X-1295 | 101099047 |  | RRM 2017 |  | 2017-02-01 |  | completed |  | King | R.10009.08.02.15 |  |  | ORC-17 | Include
2205E073 ORC-17 INST TRIPSAVER X-3416 | 101099048 |  | RRM 2017 |  | 2017-02-01 |  | completed |  | King | R.10009.08.02.15 |  |  | ORC-17 | Include
2305E035 PRE-11 REPLACE X676 RECL 2014 | 101084522 |  | RRM 2017 |  | 2017-02-02 |  | completed |  | King | R.10009.08.02.12 |  |  | PRE-11 | Include
2206E077 LWS-16 208th Ave SE TW (OH Outage Tree Wire) | 101096130 |  | RRM 2017 |  | 2017-03-14 |  | completed |  | King | R.10009.08.02.14 |  |  | LWS-16 | Include
2305E110 ROL-16 16045 116TH AVE SE RENTO | 101100156 |  | RRM 2017 |  | 2017-04-14 |  | completed |  | King | R.10009.08.02.12 |  |  | ROL-16 | Include
2104E044 BEL-25 311853-163443 Vault Leak (UG Rebuild) | 101093915 |  | RRM 2017 |  | 2017-07-25 |  | completed |  | King | R.10009.08.02.27 |  |  | BEL-25 | Include
2106E014 FCR-12 INSTALL GOP 2017 (GOP) | 101103648 |  | RRM 2017 |  | 2017-11-29 |  | completed |  | King | R.10009.08.02.11 |  |  | FCR-12 | Include
1801W066 PLG-16 ALONNA DR TRIPSAVER 16 | 101098950 |  | RRM 2017 |  | 2017-01-10 |  | completed |  | Thurston | R.10009.08.02.15 |  |  | PLG-16 | Include
1702E065 YEL-23 SR 702 S. TRIPSAVER 16 | 101099141 |  | RRM 2017 |  | 2017-01-11 |  | completed |  | Thurston | R.10009.08.02.15 |  |  | YEL-23 | Include
2005E032 DGR-15 DRIFTWOOD DR E #2TW P339 | 101091756 |  | RRM 2017 |  | 2017-01-19 |  | completed |  | Pierce | R.10009.08.02.14 |  |  | DGR-15 | Include
1603E123 LON-17 BALD HILLS RECL 2016 RI | 101099587 |  | RRM 2017 |  | 2017-01-24 |  | completed |  | Thurston | R.10009.08.02.11 |  |  | LON-17 | Include
1901E120 LUH-17 GLACIS RD TRIPSAVER 16 | 101099095 |  | RRM 2017 |  | 2017-01-26 |  | completed |  | Thurston | R.10009.08.02.15 |  |  | LUH-17 | Include
1904E090 HEM-15 122 AVE E 336TW P-6323 | 101091757 |  | RRM 2017 |  | 2017-02-17 |  | completed |  | Pierce | R.10009.08.02.14 |  |  | HEM-15 | Include
1801W087 LAC-17 CARPENTER RD 336TW O6326 (2016) (OH Outage Tree Wire) | 101091968 |  | RRM 2017 |  | 2017-02-20 |  | completed |  | Thurston | R.10009.08.02.14 |  |  | LAC-17 | Include
2004E010 EDG-12 8 ST E RECOND **OH** (OH Outage Duration) | 101085257 |  | RRM 2017 |  | 2017-04-28 |  | completed |  | Pierce | R.10009.08.02.07 |  |  | EDG-12 | Include
1905E007 RHO-15 S PRAIRIE RD 336TW P1272 (OH Outage Tree Wire) | 101091760 |  | RRM 2017 |  | 2017-05-12 |  | completed |  | Pierce | R.10009.08.02.14 |  |  | RHO-15 | Include
1801W024 FRG-22 S. Bay Rd Recl 2017 RI (Recloser) | 101102460 |  | RRM 2017 |  | 2017-06-12 |  | completed |  | Thurston | R.10009.08.02.12 |  |  | FRG-22 | Include
1803W046 GRI-13 INSTALL 1 RECL 2016 RI | 101099590 |  | RRM 2017 |  | 2017-06-15 |  | completed |  | Thurston | R.10009.08.02.12 |  |  | GRI-13 | Include
1601W090 BLU13 MILITARY RD WEST WIRE (OH Outage Tree Wire) | 101091969 |  | RRM 2017 |  | 2017-06-26 |  | completed |  | Thurston | R.10009.08.02.14 |  |  | BLU-13 | Include
1802W032 ELD-23 OVERHULSE RD FDR 336TW (OH Outage Tree Wire) | 101095548 |  | RRM 2017 |  | 2017-07-12 |  | completed |  | Thurston | R.10009.08.02.14 |  |  | ELD-23 | Include
1802W067 ELD-27 MUD BAY GOPT 2017 RI (GOP) | 101103938 |  | RRM 2017 |  | 2017-07-20 |  | completed |  | Thurston | R.10009.08.02.11 |  |  | ELD-27 | Include
1801W049 PLU-24 THURSTON AV GOPT 2017 RI (GOP) | 101103939 |  | RRM 2017 |  | 2017-07-26 |  | completed |  | Thurston | R.10009.08.02.11 |  |  | PLU-24 | Include
1602E060 LON-17 BALD HILL R2 RECLS 2017 (2 Reclosers) | 101103965 |  | RRM 2017 |  | 2017-07-27 |  | completed |  | Thurston | R.10009.08.02.12 |  |  | LON-17 | Include
1802W107 BAR-13 SAPP RD GOPT 2017 RI (GOP) | 101103964 |  | RRM 2017 |  | 2017-07-31 |  | completed |  | Thurston | R.10009.08.02.11 |  |  | BAR-13 | Include
2502E008 PMA-15 NE DAY RD TRIPSAVER 16 | 101099060 |  | RRM 2017 |  | 2017-01-10 |  | completed |  | Kitsap | R.10009.08.02.15 |  |  | PMA-15 | Include
2203E062 VAS-23 KINGSBURY RDTRIPSAVER 16 | 101099069 |  | RRM 2017 |  | 2017-01-13 |  | completed |  | King (Vashon) | R.10009.08.02.15 |  |  | VAS-23 | Include
2203E022 VAS-23 SW CEMETARY TRIPSAVER 16 | 101099560 |  | RRM 2017 |  | 2017-01-13 |  | completed |  | King (Vashon) | R.10009.08.02.15 |  |  | VAS-23 | Include
2303E072 VAS-12 SW 140TH ST TRIPSAVER 16 | 101099625 |  | RRM 2017 |  | 2017-01-16 |  | completed |  | King (Vashon) | R.10009.08.02.15 |  |  | VAS-12 | Include
2202E096 VAS-13 SW 240TH ST TRIPSAVER 16 | 101099622 |  | RRM 2017 |  | 2017-01-16 |  | completed |  | King (Vashon) | R.10009.08.02.15 |  |  | VAS-13 | Include
2202E044 VAS-13 SW 220TH ST TRIPSAVER 16 | 101099623 |  | RRM 2017 |  | 2017-01-16 |  | completed |  | King (Vashon) | R.10009.08.02.15 |  |  | VAS-13 | Include
2202E140 VAS-13 SW 280TH & VASHON TS 16 | 101099624 |  | RRM 2017 |  | 2017-01-16 |  | completed |  | King (Vashon) | R.10009.08.02.15 |  |  | VAS-13 | Include
2203E120 VAS-23 99TH AVE SW TRIPSAVER 16 | 101099559 |  | RRM 2017 |  | 2017-01-16 |  | completed |  | King (Vashon) | R.10009.08.02.15 |  |  | VAS-23 | Include
2203E084 VAS-23 75TH AVE SW TRIPSAVER 16 | 101099621 |  | RRM 2017 |  | 2017-01-16 |  | completed |  | King (Vashon) | R.10009.08.02.15 |  |  | VAS-23 | Include
2302E100 VAS-12 115TH AVE TRIPSAVER 16 | 101099627 |  | RRM 2017 |  | 2017-01-26 |  | completed |  | King (Vashon) | R.10009.08.02.15 |  |  | VAS-12 | Include
2302E012 FRA-13 Eastway Dr Tripsaver 16 | 101099616 |  | RRM 2017 |  | 2017-01-30 |  | completed |  | Kitsap | R.10009.08.02.15 |  |  | FRA-13 | Include
2702E088 CHR-23 PT GAMB.3 GOSW'S 2015 RI | 101093919 |  | RRM 2017 |  | 2017-02-01 |  | completed |  | Kitsap | R.10009.08.02.11 |  |  | CHR-23 | Include
2701E048 PGA-12 HWY 3 4-GOPT'S 2016 RI | 101099882 |  | RRM 2017 |  | 2017-02-08 |  | completed |  | Kitsap | R.10009.08.02.11 |  |  | PGA-12 | Include
2501W060 SIL-15 INST RECLOSER 2016 RI | 108100143 |  | RRM 2017 |  | 2017-03-16 |  | completed |  | Kitsap | R.10009.08.02.12 |  |  | SIL-15 | Include
2201E004 FRA-16 Install GOPT 2016 RI (GOP & Lateral Fuses) | 101099588 |  | RRM 2017 |  | 2017-05-12 |  | completed |  | Kitsap | R.10009.08.02.11 |  |  | FRA-16 | Include
2601E057 POU-15 FINN HILL GO SW 2017 RI (GOP) | 101103940 |  | RRM 2017 |  | 2017-06-19 |  | completed |  | Kitsap | R.10009.08.02.11 |  |  | POU-15 | Include
2501E139 TRA-23 Riddell Rd 3 GO sw 2017 RI (622650-155496) (GOP) | 101103671 |  | RRM 2017 |  | 2017-10-09 |  | completed |  | Kitsap | R.10009.08.02.11 |  |  | TRA-23 | Include
2203E018 VAS-23_22 Cemetary GO SW 2017 RI (GOP) | 101103943 |  | RRM 2017 |  | 2017-10-23 |  | completed |  | King (Vashon) | R.10009.08.02.11 |  |  | VAS-23 | Include

## Figure 6
2017 | 2018
| Company Wide SAIDI | CMI | No. of Projects
2014 | 61.2059 | 67660104
2015 | 52.689 | 58699497
2016 | 41.606 | 46855919
AVG 2014-2016 | 51.7725 | 57738506.6667
2017 | 50.9993 | 58004787 | 71
2018 | 43.1309 | 49551588 | 30
| Companywide SAIDI | CMI | Number of Projects
2014 | 13.8539 | 15314749
2015 | 11.1826 | 12458268
2016 | 20.4315 | 23009601
Average 2014-2016 | 15.1785 | 16927539.3333
2017 | 15.1772 | 17262033 | 55
2018 | 13.7971 | 15851016 | 35
| 2017 projects | 2018 projects | 2018 CMI | 2017 CMI | 2014-2016 avg CMI | 2016 CMI | 2015 CMI | 2014 CMI | Delta change from AVG 2014 to 2018
KNM-27 | 1 |  | 359558 | 222699 | 1600776.3333 | 4231726 | 521186 | 49417 | -1241218.3333 | GWR-16
ELD-23 | 1 |  | 85451 | 123649 | 691979 | 1931315 | 89971 | 54651 | -606528 | LON-17
LAC-17 | 1 |  | 110362 | 143011 | 670210.3333 | 1389655 | 283063 | 337913 | -559848.3333 | NUG-26
FRG-22 | 1 |  | 132627 | 119249 | 499871.3333 | 1011121 | 243484 | 245009 | -367244.3333 | ORT-22
HAM-13 | 1 |  | 74295 | 158359 | 430851.6667 | 698349 | 151769 | 442437 | -356556.6667 | SUM-21
RHO-15 | 1 |  | 38525 | 548394 | 319479 | 374395 | 211767 | 372275 | -280954 | NLM-15
HAZ-16 | 1 |  | 67132 | 33496 | 348007.6667 | 419443 | 47255 | 577325 | -280875.6667 | MIL-17
UHL-23 | 1 |  | 64703 | 57661 | 316377 | 224192 | 133122 | 591817 | -251674 | VAS-13
JUA-25 | 1 |  | 16501 | 29568 | 261959 | 672032 | 17496 | 96349 | -245458 | KIN-24
YEL-23 | 1 |  | 77225 | 528180 | 310717 | 922614 | 7370 | 2167 | -233492 | SKY-25
PIP-23 | 1 |  | 26980 | 15177 | 257174.6667 | 370427 | 22468 | 378629 | -230194.6667 | POU-15
FCR-12 | 1 |  | 137655 | 1476520 | 315670.6667 | 46239 | 26465 | 874308 | -178015.6667 | LOL-21
WAY-12 | 1 |  | 49172 | 52669 | 212734.6667 | 241627 | 261591 | 134986 | -163562.6667 | SIL-16
CPV-15 | 1 | 1 | 115700 | 306348 | 271218.6667 | 149286 | 78696 | 585674 | -155518.6667 | ETN-13
BLU-13 | 1 |  | 108424 | 34647 | 254295.3333 | 589182 | 70540 | 103164 | -145871.3333 | KNM-26
NLM-13 | 1 |  | 6407 | 54332 | 138721 | 197414 | 77900 | 140849 | -132314 | CLE-11
ORC-17 | 2 |  | 58837 | 44243 | 164154.6667 | 324327 | 23222 | 144915 | -105317.6667 | PRI-13
CUS-13 | 1 | 1 | 2244 | 164097 | 104024.3333 | 70962 | 101856 | 139255 | -101780.3333 | HOB-15
PMA-15 | 1 |  | 103165 | 345856 | 204279.3333 | 100722 | 118452 | 393664 | -101114.3333 | PTR-14
NBO-22 | 1 |  | 22914 | 29714 | 115647.6667 | 66857 | 48823 | 231263 | -92733.6667 | AIR-23
LAB-25 | 1 |  | 7629 | 231748 | 91208.6667 | 19084 | 179606 | 74936 | -83579.6667 | ELD-27
HEM-15 | 1 |  | 58411 | 303211 | 122105 | 101803 | 146256 | 118256 | -63694 | PGA-12
TRA-23 | 1 |  | 57890 | 17913 | 113734.6667 | 207305 | 97511 | 36388 | -55844.6667 | LON-25
EGT-11 | 1 |  | 105902 | 83234 | 154933.6667 | 137120 | 209114 | 118567 | -49031.6667 | BRS-24
UHL-25 | 1 |  | 8440 | 131342 | 43580 | 38118 | 34046 | 58576 | -35140 | COT-13
EDG-12 | 1 |  | 20296 | 119129 | 49531 | 12128 | 82545 | 53920 | -29235 | MIL-23
LYN-26 | 1 |  | 37730 | 500384 | 64782 | 26119 | 38165 | 130062 | -27052 | FLD-12
ROL-16 | 1 |  | 84446 | 168744 | 111067 | 190831 | 103218 | 39152 | -26621 | HAP-16
LWS-16 | 1 |  | 60613 | 37206 | 83934 | 172439 | 65826 | 13537 | -23321 | TOL-15
EGT-27 | 1 |  | 1447 | 26831 | 15574 | 7378 | 36011 | 3333 | -14127 | GRI-16
SBE-25 | 1 |  | 5165 | 4621 | 18875 | 10938 | 834 | 44853 | -13710 | SHD-18
BHS-11 | 2 |  | 23398 | 19023 | 30542.6667 | 24144 | 52391 | 15093 | -7144.6667 | WOB-23
BEL-25 | 1 |  | 18136 | 31483 | 23041 | 33999 | 18472 | 16652 | -4905 | SEQ-16
THO-13 | 1 |  | 38606 | 26751 | 42516 | 14654 | 6872 | 106022 | -3910 | GWR-13
LYN-16 | 2 |  | 0 | 1031 | 922.6667 | 2490 | 278 | 0 | -922.6667 | FLD-13
PLG-16 | 1 |  | 15886 | 5406 | 13155.6667 | 13668 | 24921 | 878 | 2730.3333 | LLS-17
PLU-24 | 1 |  | 133339 | 285684 | 111295.3333 | 303405 | 20989 | 9492 | 22043.6667 | KNM-23
VIS-26 | 2 |  | 223442 | 137946 | 190408.6667 | 126450 | 83740 | 361036 | 33033.3333 | BLA-13
BAR-13 | 1 |  | 154694 | 102833 | 114169.6667 | 272996 | 64579 | 4934 | 40524.3333 | GAR-16
DUV-13 | 1 |  | 236547 | 379066 | 189021 | 88511 | 289638 | 188914 | 47526 | WLS-16
SCH-16 | 1 |  | 157467 | 777267 | 86587.3333 | 81717 | 89166 | 88879 | 70879.6667 | MOT-14
SCH-13 | 1 |  | 388667 | 619429 | 306805.6667 | 50432 | 659791 | 210194 | 81861.3333 | FRA-13
PRE-11 | 1 |  | 477521 | 145024 | 342216.6667 | 327014 | 70158 | 629478 | 135304.3333 | FAL-15
LMC-25 | 1 |  | 265370 | 152675 | 96294 | 165488 | 31298 | 92096 | 169076 | FRG-24
LUH-17 | 1 |  | 276459 | 151376 | 85859.3333 | 84412 | 161134 | 12032 | 190599.6667 | BLU-16
SLA-15 | 1 |  | 325126 | 648688 | 103286.6667 | 61754 | 41855 | 206251 | 221839.3333 | WIN-12
CAS-16 | 1 |  | 644767 | 6576 | 4191.3333 | 5719 | 964 | 5891 | 640575.6667 | FRA-16
BIG-12 | 1 |  | 989780 | 136311 | 326331.3333 | 258352 | 502288 | 218354 | 663448.6667 | MVW-13
MIR-15 | 1 |  | 866594 | 483905 | 141985.3333 | 218192 | 167085 | 40679 | 724608.6667 | PTR-16
BRO-15 | 2 |  | 1526198 | 178220 | 401671 | 129827 | 445955 | 629231 | 1124527 | SME-12
BRW-16 |  | 1 | 368411 | 201940 | 179356 | 126658 | 237109 | 174301 |  | MAN-15
BTN-36 |  | 1 | 310804 | 240756 | 278735 | 559838 | 72254 | 204113 |  | BRW-13
CAS-15 |  | 1 | 272747 | 1409005 | 1450959 | 1594364 | 618315 | 2140198 |  | FLD-15
DGR-16 |  | 1 | 8840 | 15212 | 165902.3333 | 287613 | 133607 | 76487 |  | SLA-16
EGT-12 |  | 1 | 968032 | 872826 | 252303 | 46631 | 689793 | 20485 |  | PMA-12
ELL-14 |  | 1 | 21179 | 37302 | 94535.6667 | 54097 | 13979 | 215531 |  | LMD-15
GRV-16 |  | 1 | 15501 | 216587 | 71271.6667 | 9621 | 79492 | 124702 |  | BLU-17
HAZ-13 |  | 1 | 19661 | 81770 | 12527.6667 | 10716 | 14888 | 11979 |  | LLT-13
KLA-17 |  | 1 | 33564 | 6140 | 140867 | 4140 | 228851 | 189610 |  | ING-13
KNO-14 |  | 1 | 38 | 2872 | 418.3333 | 1047 | 0 | 208 |  | WOL-23
KWH-23 |  | 1 | 105081 | 403024 | 70065 | 136028 | 40850 | 33317 |  | SWD-13
MCA-16 |  | 1 | 192358 | 132421 | 6246.6667 | 3481 | 11456 | 3803 |  | WIN-15
MCW-15 |  | 1 | 112438 | 194335 | 277380.3333 | 247342 | 358934 | 225865 |  | LGY-15
MER-13 |  | 2 | 27464 | 28679 | 190054 | 129381 | 252178 | 188603 |  | KEN-12
MOT-16 |  | 1 | 21213 | 1125 | 19110 | 26362 | 21175 | 9793 |  | PGA-13
MST-26 |  | 1 | 201116 | 14666 | 22018.6667 | 13038 | 31411 | 21607 |  | LGY-12
MUR-13 |  | 1 | 203587 | 112706 | 44221 | 26525 | 28230 | 77908 |  | SHE-16
NNO-15 |  | 1 | 44129 | 343536 | 328912 | 91548 | 594761 | 300427 |  | ALG-12
ORT-23 |  | 1 | 2648305 | 253560 | 317286 | 95439 | 765525 | 90894 |  | VAS-12
PEA-17 |  | 1 | 221601 | 156762 | 214413.6667 | 588236 | 43952 | 11053 |  | SIN-25
PET-12 |  | 1 | 119764 | 8944 | 16231.3333 | 8676 | 22085 | 17933 |  | SIL-13
PLG-13 |  | 1 | 207843 | 195605 | 323962.6667 | 571556 | 183249 | 217083 |  | LTA-18
RIT-16 |  | 1 | 215397 | 144549 | 211764.6667 | 198939 | 421966 | 14389 |  | LUH-14
RIV-16 |  | 1 | 10059 | 262576 | 71899 | 21401 | 84796 | 109500 |  | SWI-15
RJN-12 |  | 1 | 0 | 0 | 3340.6667 | 9091 | 604 | 327 |  | BEL-26
ROC-16 |  | 1 | 126243 | 322065 | 358499.6667 | 60430 | 350525 | 664544 |  | ING-15
RPT-16 |  | 1 | 115604 | 497740 | 117389 | 258111 | 4002 | 90054 |  | BCH-15
SHE-17 |  | 1 | 35553 | 28299 | 128328.6667 | 117939 | 111145 | 155902 |  | SKY-23
SKE-26 |  | 1 | 79855 | 131009 | 372259 | 258755 | 521421 | 336601 |  | HYA-13
SST-14 |  | 1 | 178 | 0 | 0 | 0 | 0 | 0 |  | SKE-22
SUN-13 |  | 1 | 37103 | 22877 | 10661 | 16351 | 15632 | 0 |  | BDI-13
SWD-12 |  | 1 | 239505 | 522219 | 208845 | 217875 | 244881 | 163779 |  | ORC-13
82 | 55 | 35 | 15851016 | 17262033 | 16927539.3333 | 23009601 | 12458268 | 15314749 |  | GRV-15
MIL-22
BLA-12
LTA-17
CHA-13
DGR-15
FCR-14
CHR-22
SNQ-13
RAI-13
LWS-14
MVW-17
CHR-23
LEA-17
MCA-15
SEM-13
PGA-16
WAY-15
KNO-11
GOO-15
EVE-13