## Tables
2023 Transfers to Plant (System Level)
| Business Cases | As Filed | Actual | (Under)/Over
1. Business Cases Included in GRC | 93 | 445376581 | 432014204.28 | -13362376.72
2. Additional Business Cases
a. Prior GRC Trailing Transfers | 17 | 0 | 1344368.08 | 1344368.08
b. Brand New Business Cases | 8 | 0 | 7619529.94 | 7619529.94
c. Bus. Case Provided-Timing Change | 5 | 0 | 23184311 | 23184311
Total Transfers | 123 | 445376581 | 464162413.3 | 18785832.3
2022 Transfers to Plant (System Level)
| Business Cases | As Filed | Actual | (Under)/Over
1. Business Cases Included in GRC | 96 | 449877418 | 467463176.67 | 17585758.67
2. Additional Business Cases
a. Prior GRC Trailing Transfers | 2 | 0 | 359230.6 | 359230.6
b. Brand New Business Cases | 3 | 0 | 1536192.74 | 1536192.74
c. Bus. Case Provided-Timing Change | 16 | 0 | 35970318.52 | 35970318.52
Total Transfers | 117 | 449877418 | 505328918.53 | 55451500.53
|  |  | Variance "New" versus Authorized TTP (System) | 1.023%

## Att A vs Att D vs Staff Check
Bench Request 2 - Avista Response
Native file (tab Attachment A also in pdf) - provides all transfers to plant (TTP) detail by Business Case on a system basis, as well as miscellaneous adjustments, i.e. accrual reversals, accounting corrections, etc., impacting total transfer to plant balances. Columns also provided, include balances: "As-Filed TTP", "Actual TTP", "Variance $ (Gross Plant)", "Variance %." If a variance item met the"$500k & +-10% TTP Threshold," it was labeled "yes" and the Direct Filed Exhibit # and page #, and the Variance Form (Attachment C) page # is provided. If the variance is > +- 10%, but < $500,000, that line item pointed to Attachment D for further information, as non-material (system values).
Attachment D - Included 2023 actual TTP detail (system values) that varied from that as-filed that was >10%+-, but < $500,000. This table listing included "New" Business Cases," as well as TTP variances that related to trailing costs from previously provided Business Cases (2021 or 2022) as well as early minor transfers related to 2024 Business Case.
Business Cases included in Attachment A (Native) versus Attachment D (System) |  |  |  |  | Filed 2023 Budgeted TTP Plan | Actual TTP | Variance $ over/(under) | BC Provided in Direct Filing
| [A] |  | [B] | [C] | [D] | [E] | [F] | [G] | [H]
| Native & Att. A |  | Att. D | Business Case | Gross Plant | Gross Plant | Gross Plant | Exh. Reference | Planned TTP Year & BC Per Direct Filing
1 | Att. A | 1 | Att. D | Gas Airway Heights HP Reinforcement | 0 | -4593 | -4593 | Exh. HLR-2, p. 420 | 2022 Trailing
2 | Att. A | 2 | Att. D | Gas Warden HP Reinforcement | 0 | 4353.86 | 4353.86 | New 2022 Report | 2022 Trailing
3 | Att. A | 3 | Att. D | N Lewiston Autotransformer - Failed Plant | 0 | 9612.5 | 9612.5 | Exh. HLR-2, p. 381 | 2022 Trailing
4 | Att. A | 4 | Att. D | Long Lake Plant Upgrade | 0 | 10792.64 | 10792.64 | Exh. JRT-4, p. 102 | 2021/2024 BC
5 | Att. A | 5 | Att. D | Gas Operator Qualification Compliance | 0 | 31087.27 | 31087.27 | Exh. HLR-2, p. 264 | 2021 BC - programmatic
6 | Att. A | 6 | Att. D | Primary URD Cable Replacement | 0 | 66023.9 | 66023.9 | Exh. HLR-2, p. 131 | 2021 trailing costs
7 | Att. A | 7 | Att. D | Apprentice/Craft Training | 0 | 62969.63 | 62969.63 | Exh. HLR-2, p.236 | 2021 BC - programmatic
8 | Att. A | 8 | Att. D | Gas HP Pipeline Remediation Program | 0 | 139101.69 | 139101.69 | Exh. HLR-2, p. 337 | 2022 BC - programmatic
9 | Att. A | 9 | Att. D | Nine Mile Powerhouse Crane Rehab | 0 | 229460.94 | 229460.94 | Exh. JRT-4, p. 243 | 2022 Trailing
10 | Att. A | 10 | Att. D | Gas ERT Replacement Program | 0 | 236729.77 | 236729.77 | Previous AMI BC, failures in 2023
11 | Att. A | 11 | Att. D | Asset Monitoring System | 0 | 264723.15 | 264723.15 | NEW
12 | Att. A | 12 | Att. D | Meter Minor Blanket | 0 | 246445.82 | 246445.82 | Exh. HLR-2, p. 118 | 2021 BC - programmatic
13 | Att. A | 13 | Att. D | Westside 230/115kV Station Brownfield Rebuild Project | 0 | 269092.18 | 269092.18 | Exh. HLR-2, p. 210 | 2021 trailing costs
14 | Att. A | 14 | Att. D | Clearwater Wind Generation Interconnection | 0 | 273299.74 | 273299.74 | Exh. HLR-2, p. 3 | 2021 (labeled New in error)
15 | Att. A | 15 | Att. D | CIP v5 Transition - Cyber Asset Electronic Access | 0 | 191787.05 | 191787.05 | New to 2022 GRC (Previous 2020 BC)
16 | Att. A | 16 | Att. D | Strategic Initiatives - Clean Energy Fund 2 | 0 | 55340.01 | 55340.01 | New 2022 Report | 2022 Trailing, new projects each year
17 | Att. A | 17 | Att. D | Strategic Initiatives - UIASSIST | 0 | 100526.57 | 100526.57 | 2022 BC, new projects each year, described in Att. D
18 | Att. A |  |  | T&D Reimbursable | 0 | -112027.25 | (a) | N/A timing of TTP vs receipt of reimbursement
19 | Att. A |  |  | Payment Card Industry Compliance (PCI) | 0 | -2207.46 | (b) | Misc. accrual reversals, corrections
20 | Att. A |  |  | Washington Advanced Metering Infrastructure Project | 0 | 1659.01 | (c) | Misc. accrual reversals, corrections
| -750 |  | -1299 | Misc. accrual reversals, corrections or additional TTP | x | -750.4 | (d) | Misc. accrual reversals, corrections
[6 empty] | 2073427.62 | 2186753.72
|  | Staff "Subject to Check" Filing" - New Business Cases |  |  |  | System Values
|  |  |  | New Business Cases - see 2023 Capital Report Attachment C |  |  | Attachment C New Business Cases: > $500,00 & 10% - Variance Explanation and New Business Case Provided in Attachment C of 2023 Report.
|  |  | 1 | Long Lake Stability Enhancement |  | 1114533.94
|  |  | 2 | Metro 115kV Substation |  | 545255.83
|  |  | 3 | NexGen Control System Networks |  | 694741.06
|  |  | 4 | Nine Mile Powerhouse Roof Replacement |  | 840745.18
|  |  | 5 | Noxon Rapids Spillgate Refurbishment |  | 3694443.99
New Business Cases - See Attachment D (see also Illustration No. 1 above)
|  |  | 6 | Asset Monitoring System |  | 264723.15 | Attachment D
|  |  | 7 | Clearwater Wind Generation Interconnection |  | 273299.74 | Attachment D
|  |  | 8 | CIP v5 Transition - Cyber Asset Electronic Access |  | 191787.05 | Attachment D
[5 empty] | 8 | 7619529.94
| [A] |  | [B] | [C] | [D] | [E]
| Native & Att. A |  | Att. D | Business Case | Gross Plant | Gross Plant
18 | Att. A |  |  | T&D Reimbursable | 0 | -112027.25 | (a) |  |  | N/A Receipt - Reimbursement
19 | Att. A |  |  | Payment Card Industry Compliance (PCI) | 0 | -2207.46 | (b) | -2207.46 |  | Misc.accrual reversal, correction, etc.
20 | Att. A |  |  | Washington Advanced Metering Infrastructure Project | 0 | 1659.01 | (c ) | 1659.01 |  | Misc.accrual reversal, correction, etc.
| -750 | (f) | -1299 | Misc. accrual reversals, corrections or additional TTP | x | -750.4 | (d ) | -750.4 | Attachment A Total | Misc.accrual reversal, correction, etc.
[8 empty] | -1298.85 | Attachment D Total
Attachment A seperately identified Items 18 - 20, and included a "Misc. accrual reversals, corrections or additional TTP" item of $750.00.
Whereas Attachment D excluded Item 18, and consolidated 19-20 with the Misc. accrual amount of $750.00 totaling $1,299.0
1.711%

## 2022 and 2023 Recons
2023 Provisonal Capital Report |  |  |  |  | 2022 Provisonal Capital Report
Per Native - Attachment A |  |  |  |  | Per Native - Attachment A
Business Cases Per Report | As-Filed | Actual | Spend (under) / over |  | Business Cases Per Report | As-Filed | Actual | Spend (under) / over
93 | 445376581 | 432014204.28 | -13362376.72 | Business Cases per Direct Filing - Docket UE-22000053, et.al., | 96 | 449877418 | 467463176.67 | 17585758.67 | Business Cases per Direct Filing - Docket UE-22000053, et.al.,
New and Revisions Business Cases per report: |  |  |  |  | New and Revisions Business Cases per report:
5 |  | 23184311 | 23184311 | Large Distinct Item variance, Business Cases provided with direct filing. Timing of item moved. | 16 |  | 35970318.52 | 35970318.52 | Large Distinct Item variance, Business Cases provided with direct filing. Timing of item moved.
17 |  | 1344368.08 | 1344368.08 | 2021/2022 prior cleanup itmes. Not new. | 2 |  | 359230.6 | 359230.6 | 2021/2022 prior cleanup itmes. Not new.
8 |  | 7619529.94 | 7619529.94 | New, Agrees to Staff's "Subject to Check" filing. | 3 |  | 1536192.74 | 1536192.74 | New, Agrees to Staff's "Subject to Check" filing.
30 |  |  |  |  | 21
123 | 445376581 | 464162413.3 | 18785832.3 |  | 117 | 449877418 | 505328918.53 | 55451500.53
2023 Provisional Capital Report |  |  |  |  | 2023 Provisional Capital Report
| System Planned | System Actual | Variance |  |  | System Planned | System Actual | Variance
| 445376581 | 464161663.31 | 18785082.31 |  |  | 449877418 | 505328918.53 | 55451500.53
|  |  |  | Total 2022-20223 |  |  |  | 31118689.92 | Less KF transferred early in 2022, rather than 2023.
|  |  | 1.711% | 1.023% |  |  |  | 24332810.61
0.3415%
Large and/or Distinct Items, timing differene: |  |  |  |  | Large and/or Distinct Items, timing differene:
Saddle Mountain 230/115kV Station (New) Integration Project Phase 2 |  |  | 17562125.24 |  | KF-Fuel Yard completed in 2022, versus 2023 as planned. |  |  | 31118689.92
Strategic Initiatives - South Landing (Catalyst) - Clean Energy Fund 3 |  |  | 2633563.37 |  | Westside 230/115kV Station Brownfield Rebuild Project |  |  | 3292230.01
Enterprise & Control Network Infrastructure |  |  | 736619.39 |  | Misc. non-material balances (14 items) |  |  | 1559399
Gas Overbuilt Pipe Replacement Program |  |  | 604990.41 |  |  |  |  | 35970318.93
Nine Mile HED Battery Building |  |  | 1647012.95
23184311.36

## Variance Summary - Att A 2023
Native Excel Detail ATTACHMENT E [PDF: ATTACHMENT A]
Avista Utilities
2023 Capital Additions (System-Basis) - Summary by Business Case
Support of the 2023 capital pro forma and provisional additions were provided with the Company’s direct filed case, including a description of each Business Case located within the respective direct testimony of Company witnesses Mr. Thackston (Exh. JRT-1T), Mr. Magalsky (Exh. KEM-1T), Ms. Rosentrater (Exh. HLR-1T), Mr. Kensok (Exh. JMK-1T), Mr. Howell (Exh. DRH-1T) and Mr. Kinney (Exh. SJK-1T). Additionally, an exhibit was filed with each witness’s testimony including each full Business Case as noted in Column (F). Additional support is provided as follows: Attachment B - Detail actual transfer-to-plant by month amounts and in-service dates Attachment C - Capital Variance Explanation Forms and supporting justification by Business Case Attachment D - Business Cases not included in direct filing under threshold Attachment E - Native Capital Adjustment excel file supporting transfers-to-plant and Net Plant After ADFIT balances Attachment F - Listing of Infrastructure Investment and Jobs Act and the Inflation Reduction Act Grant Opportunities
|  | (A) | (B) | (C) | (D) | (E) | (F) |  | (G)
|  | 2023 As-Filed TTP (1) | 2023 Actual TTP (1) | Variance $ over/(under) | Variance % over/(under) | $500k & +/- 10% TTP Threshold met? | Direct Filed Exhibit | Direct Filed Exhibit | Attach- ment C
Witness | Business Case | Gross Plant | Gross Plant | Gross Plant |  |  | Exh. # | Pg# | Pg#
Kensok | Atlas | 2948867 | 745956.45 | -2202910.55 | -74.7% | yes | Exh. JMK-2 | 133 | 3
Kensok | Basic Workplace Technology Delivery | 800005 | 2029988.73 | 1229983.73 | 153.7% | yes | Exh. JMK-2 | 3 | 9
Thackston | Cabinet Gorge Dam Fishway | 235000 | 754675.66 | 519675.66 | 221.1% | yes | Exh. JRT-4 | 30 | 26
Thackston | Cabinet Gorge HVAC Replacement | 1500000 | 0 | -1500000 | -100% | yes | Exh. JRT-4 | 169 | 30
Thackston | Cabinet Gorge Station Service | 5152936 | 0 | -5152936 | -100% | yes | Exh. JRT-4 | 178 | 31
Thackston | Cabinet Gorge Stop Log Replacement | 1200000 | 0 | -1200000 | -100% | yes | Exh. JRT-4 | 184 | 39
Thackston | Cabinet Gorge Unwatering Pumps | 395016 | 913476.23 | 518460.23 | 131.3% | yes | Exh. JRT-4 | 192 | 42
Thackston | Clark Fork Settlement Agreement | 5622720 | 4869943.58 | -752776.42 | -13.39% | yes | Exh. JRT-4 | 51 | 47
Kensok | Control and Safety Network Infrastructure | 1282468 | 528523.74 | -753944.26 | -58.79% | yes | Exh. JMK-2 | 227 | 48
Magalsky | Customer Experience Platform Program | 6300000 | 3951593.38 | -2348406.62 | -37.28% | yes | Exh. KEM-2 | 10 | 56
Magalsky | Customer Facing Technology Program | 4699999 | 3777725.56 | -922273.44 | -19.62% | yes | Exh. KEM-2 | 19 | 64
Magalsky | Customer Transactional Systems | 3500000 | 2589501.19 | -910498.81 | -26.01% | yes | Exh. KEM-2 | 31 | 65 |  | 1.03%
Kensok | Data Center Compute and Storage Systems | 2063801 | 3871279.93 | 1807478.93 | 87.58% | yes | Exh. JMK-2 | 12 | 66 |  | 0.3203%
Kensok | Digital Grid Network | 2121419 | 3485617.24 | 1364198.24 | 64.31% | yes | Exh. JMK-2 | 22 | 73
Rosentrater | Distribution System Enhancements | 7069995 | 12761898.68 | 5691903.68 | 80.51% | yes | Exh. HLR-2 | 39 | 93
Rosentrater | Downtown Network - Performance & Capacity | 1150000 | 567566.12 | -582433.88 | -50.65% | yes | Exh. HLR-2 | 77 | 147
Rosentrater | Elec Relocation and Replacement Program | 5399984 | 8575413.06 | 3175429.06 | 58.8% | yes | Exh. HLR-2 | 88 | 148
Rosentrater | Electric Storm | 6000012 | 4195426.75 | -1804585.25 | -30.08% | yes | Exh. HLR-2 | 95 | 150
Kensok | Endpoint Compute and Productivity Systems | 3416996 | 2815680.4 | -601315.6 | -17.6% | yes | Exh. JMK-2 | 32 | 151
Kensok | Energy Delivery Modernization & Operational Efficiency | 3449859 | 7639536.37 | 4189677.37 | 121.4% | yes | Exh. JMK-2 | 142 | 155
Kensok | Energy Resources Modernization & Operational Efficiency | 2679478 | 3400805.7 | 721327.7 | 26.92% | yes | Exh. JMK-2 | 153 | 164
Kensok | Enterprise & Control Network Infrastructure | 0 | 736619.39 | 736619.39 | 100% | yes | Exh. JMK-2 | 43 | 194 | not new - timing
Kensok | Enterprise Security | 1137498 | 4583151.28 | 3445653.28 | 302.9% | yes | Exh. JMK-2 | 202 | 198
Kensok | ET Modernization & Operational Efficiency - Technology | 2002429 | 3786094.5 | 1783665.5 | 89.08% | yes | Exh. JMK-2 | 80 | 205
Kensok | Fiber Network Lease Service Replacement | 1687126 | 2876485.11 | 1189359.11 | 70.5% | yes | Exh. JMK-2 | 91 | 271
Kensok | Financial & Accounting Technology | 2775001 | 3586985.57 | 811984.57 | 29.26% | yes | Exh. JMK-2 | 163 | 278
Rosentrater | Fleet Services Capital Plan | 5608016 | 7251911.97 | 1643895.97 | 29.31% | yes | Exh. HLR-2 | 252 | 284
Rosentrater | Gas Above Grade Pipe Remediation Program | 714000 | 180172.57 | -533827.43 | -74.77% | yes | Exh. HLR-2 | 400 | 285
Rosentrater | Gas Isolated Steel Replacement Program | 850008 | 2250494.09 | 1400486.09 | 164.8% | yes | Exh. HLR-2 | 340 | 349
Rosentrater | Gas Non-Revenue Program | 8500010 | 10779649.75 | 2279639.75 | 26.82% | yes | Exh. HLR-2 | 343 | 367
Rosentrater | Gas Overbuilt Pipe Replacement Program | 0 | 604990.41 | 604990.41 | 100% | yes | Exh. HLR-2 | 348 | 381 | not new - timing
Rosentrater | Gas PMC Program | 3799993 | 1494316.37 | -2305676.63 | -60.68% | yes | Exh. HLR-2 | 352 | 390
Rosentrater | Gas Regulator Station Replacement Program | 1000002 | 1742782.36 | 742780.36 | 74.28% | yes | Exh. HLR-2 | 355 | 404
Rosentrater | Gas Replacement Street and Highway Program | 3500000 | 6457715.46 | 2957715.46 | 84.51% | yes | Exh. HLR-2 | 363 | 417
Rosentrater | Gas Transient Voltage Mitigation Program | 965000 | 78325.44 | -886674.56 | -91.88% | yes | Exh. HLR-2 | 407 | 431
Kensok | Generation, Substation & Gas Location Security | 459001 | 1189311.44 | 730310.44 | 159.1% | yes | Exh. JMK-2 | 213 | 447
Thackston | HMI Control Software | 2550000 | 1772317.43 | -777682.57 | -30.5% | yes | Exh. JRT-4 | 81 | 452
Kensok | Identity and Access Governance | 418119 | 963456.23 | 545337.23 | 130.4% | yes | Exh. JMK-2 | 264 | 455
Thackston | KF_Fuel Yard Equipment Replacement | 30367127 | 935999.86 | -29431127.14 | -96.92% | yes | Exh. JRT-4 | 214 | 462 | Largest decrease variance - KF-Fuel Yard transferred in September 2022 with trailing costs into 2023. Orginally planned to transfer in Q1'2023. Used and Useful ealry, allowing transfer, also resulted in AFUDc savings.
Kensok | Land Mobile Radio & Real Time Communication Systems | 1005328 | 2123878.79 | 1118550.79 | 111.3% | yes | Exh. JMK-2 | 109 | 489
Thackston | Long Lake Stability Enhancement | 0 | 1114533.94 | 1114533.94 | 100% | yes | NEW |  | 496
Rosentrater | Metro 115kV Substation | 0 | 545255.83 | 545255.83 | 100% | yes | NEW |  | 507
Thackston | Monroe Street Abandoned Penstock Stabilization | 899992 | 36917.3 | -863074.7 | -95.9% | yes | Exh. JRT-4 | 226 | 529
Kensok | Network Backbone | 3879878 | 1450064.13 | -2429813.87 | -62.63% | yes | Exh. JMK-2 | 246 | 535
Rosentrater | New Revenue - Growth | 67348997 | 106963790.81 | 39614793.81 | 58.82% | yes | Exh. HLR-2 | 124 | 543 | New Revenue Growth - Largest increase variance - due to increased costs in transformers and meters due to supply chain issues due to COVID. Meters on a 18-month lead time.
Kensok | NexGen Control System Networks | 0 | 694741.06 | 694741.06 | 100% | yes | NEW |  | 544
Thackston | Nine Mile HED Battery Building | 0 | 1647012.95 | 1647012.95 | 100% | yes | Exh. JRT-4 | 234 | 561 | not new - timing
Thackston | Nine Mile Powerhouse Roof Replacement | 0 | 840745.18 | 840745.18 | 100% | yes | NEW |  | 562
Thackston | Nine Mile Units 3 & 4 Control Upgrade | 2000000 | 0 | -2000000 | -100% | yes | Exh. JRT-4 | 251 | 572
Thackston | Noxon Rapids Spillgate Refurbishment | 0 | 3694443.99 | 3694443.99 | 100% | yes | NEW |  | 590
Kensok | Outage Management System & Advanced Distribution Management System (OMS & ADMS) | 10000000 | 4655787.82 | -5344212.18 | -53.44% | yes | Exh. JMK-2 | 256 | 591
Rosentrater | Protection System Upgrade for PRC-002 | 11879164 | 33014.73 | -11846149.27 | -99.72% | yes | Exh. HLR-2 | 135 | 612
Thackston | Regulating Hydro | 2961000 | 3652796.43 | 691796.43 | 23.36% | yes | Exh. JRT-4 | 127 | 613
Rosentrater | Saddle Mountain 230/115kV Station (New) Integration Project Phase 2 | 0 | 17562125.24 | 17562125.24 | 100% | yes | Exh. HLR-2 | 144 | 618 | not new - timing
Rosentrater | SCADA - SOO and BuCC | 736223 | 2586168.86 | 1849945.86 | 251.3% | yes | Exh. HLR-2 | 151 | 621
Rosentrater | Strategic Initiatives - South Landing (Catalyst) - Clean Energy Fund 3 | 0 | 2633563.37 | 2633563.37 | 100% | yes | Exh. HLR-2 | 275 | 625 | not new - timing
Rosentrater | Substation - Asset Condition | 58412186 | 36908290.61 | -21503895.39 | -36.81% | yes | Exh. HLR-2 | 175 | 635
Kensok | Technology Failed Assets | 556208 | 1425606.31 | 869398.31 | 156.3% | yes | Exh. JMK-2 | 119 | 653
Rosentrater | Telematics 2025 | 808250 | 576.65 | -807673.35 | -99.93% | yes | Exh. HLR-2 | 297 | 673
Rosentrater | Transmission - Minor Rebuild | 3343418 | 6179858.9 | 2836440.9 | 84.84% | yes | Exh. HLR-2 | 182 | 676
Rosentrater | Transmission Construction - Compliance | 1550000 | 2087168.63 | 537168.63 | 34.66% | yes | Exh. HLR-2 | 188 | 700
Rosentrater | Transmission Major Rebuild - Asset Condition | 12000000 | 16186511.47 | 4186511.47 | 34.89% | yes | Exh. HLR-2 | 197 | 701
Rosentrater | Transmission NERC Low-Risk Priority Lines Mitigation | 2499984 | 818163.69 | -1681820.31 | -67.27% | yes | Exh. HLR-2 | 204 | 704
Magalsky | Transportation Electrification | 3900000 | 1523470.16 | -2376529.84 | -60.94% | yes | Exh. KEM-2 | 2 | 707
Thackston | Upper Falls Trash Rake Replacement | 1500000 | 2326061.36 | 826061.36 | 55.07% | yes | Exh. JRT-4 | 275 | 720
Rosentrater | Apprentice/Craft Training | 0 | 62969.63 | 62969.63 | 100% |  | Attachment D
Thackston | Asset Monitoring System | 0 | 264723.15 | 264723.15 | 100% |  | Attachment D
Thackston | Automation Replacement | 349999 | 0 | -349999 | -100% |  | Exh. JRT-4 | 3
Thackston | Base Load Hydro | 963504 | 544841.44 | -418662.56 | -43.45% |  | Exh. JRT-4 | 10
Thackston | Base Load Thermal Program | 2693105 | 2375701.32 | -317403.68 | -11.79% |  | Exh. JRT-4 | 18
Rosentrater | Capital Equipment Program | 2500008 | 2238311.65 | -261696.35 | -10.47% |  | Exh. HLR-2 | 241
Other | CIP v5 Transition - Cyber Asset Electronic Access | 0 | 191787.05 | 191787.05 | 100% |  | Attachment D
Rosentrater | Clearwater Wind Generation Interconnection | 0 | 273299.74 | 273299.74 | 100% |  | Attachment D
Rosentrater | Colstrip Transmission | 370002 | 125157.44 | -244844.56 | -66.17% |  | Exh. HLR-2 | 10
Rosentrater | Distribution Grid Modernization | 2239852 | 2127402.56 | -112449.44 | -5.02% |  | Exh. HLR-2 | 18
Rosentrater | Distribution Minor Rebuild | 11499986 | 12287281.54 | 787295.54 | 6.846% |  | Exh. HLR-2 | 30
Rosentrater | Downtown Network - Asset Condition | 1999999 | 2375387.73 | 375388.73 | 18.77% |  | Exh. HLR-2 | 61
Kinney | Energy Market Modernization & Operational Efficiency | 499974 | 257792.48 | -242181.52 | -48.44% |  | Exh. SJK-2 | 14
Kensok | Enterprise Business Continuity | 422064 | 0 | -422064 | -100% |  | Exh. JMK-2 | 197
Kensok | Enterprise Communication Systems | 2482488 | 2747446.24 | 264958.24 | 10.67% |  | Exh. JMK-2 | 52
Kensok | Enterprise Network Infrastructure | 2341928 | 1889234.12 | -452693.88 | -19.33% |  | Exh. JMK-2 | 236
Kensok | Environmental Control & Monitoring Systems | 964347 | 628058.89 | -336288.11 | -34.87% |  | Exh. JMK-2 | 70
Kensok | Facilities and Storage Location Security | 489088 | 583742.14 | 94654.14 | 19.35% |  | Exh. JMK-2 | 208
Rosentrater | Gas Airway Heights HP Reinforcement | 0 | -4593 | -4593 | 100% |  | Attachment D
Rosentrater | Gas Cathodic Protection Program | 715000 | 831623.57 | 116623.57 | 16.31% |  | Exh. HLR-2 | 315
Rosentrater | Gas ERT Replacement Program | 0 | 236729.77 | 236729.77 | 100% |  | Attachment D
Rosentrater | Gas Facility Replacement Program (GFRP) Aldyl A Pipe Replacement | 27687251 | 30291301.75 | 2604050.75 | 9.405% |  | Exh. HLR-2 | 323
Rosentrater | Gas HP Pipeline Remediation Program | 0 | 139101.69 | 139101.69 | 100% |  | Attachment D
Rosentrater | Gas Operator Qualification Compliance | 0 | 31087.27 | 31087.27 | 100% |  | Attachment D
Rosentrater | Gas Reinforcement Program | 1299999 | 912458.09 | -387540.91 | -29.81% |  | Exh. HLR-2 | 359
Rosentrater | Gas Telemetry Program | 210004 | 636273.55 | 426269.55 | 203% |  | Exh. HLR-2 | 366
Rosentrater | Gas Warden HP Reinforcement | 0 | 4353.86 | 4353.86 | 100% |  | Attachment D
Thackston | Generation DC Supplied System Update | 550001 | 303952.12 | -246048.88 | -44.74% |  | Exh. JRT-4 | 74
Thackston | Generation Masonry Building Rehabilitation | 493995 | 0 | -493995 | -100% |  | Exh. JRT-4 | 198
Kensok | High Voltage Protection (HVP) Refresh | 336542 | 341729.89 | 5187.89 | 1.542% |  | Exh. JMK-2 | 100
Kensok | Human Resources Technology | 500002 | 454637.2 | -45364.8 | -9.073% |  | Exh. JMK-2 | 174
Rosentrater | Jackson Prairie Natural Underground Storage Facility | 2369965 | 1911684.51 | -458280.49 | -19.34% |  | Exh. HLR-2 | 270
Rosentrater | Joint Use | 2950008 | 2872135.3 | -77872.7 | -2.64% |  | Exh. HLR-2 | 102
Rosentrater | LED Change-Out Program | 299964 | 173042.99 | -126921.01 | -42.31% |  | Exh. HLR-2 | 109
Kensok | Legal & Compliance Technology | 413072 | 264865.28 | -148206.72 | -35.88% |  | Exh. JMK-2 | 187
Thackston | Long Lake Plant Upgrade | 0 | 10792.64 | 10792.64 | 100% |  | Attachment D
Rosentrater | Meter Minor Blanket | 0 | 246445.82 | 246445.82 | 100% |  | Attachment D
Rosentrater | N Lewiston Autotransformer - Failed Plant | 0 | 9612.5 | 9612.5 | 100% |  | Attachment D
Thackston | Nine Mile Powerhouse Crane Rehab | 0 | 229460.94 | 229460.94 | 100% |  | Attachment D
Rosentrater | Oil Storage Improvements | 1762827 | 1530884.21 | -231942.79 | -13.16% |  | Exh. HLR-2 | 389
Kensok | Payment Card Industry Compliance (PCI) | 0 | -2207.46 | -2207.46 | 100% |  | Attachment D
Thackston | Peaking Generation Business Case | 458000 | 230600.37 | -227399.63 | -49.65% |  | Exh. JRT-4 | 113
Rosentrater | Primary URD Cable Replacement | 0 | 66023.9 | 66023.9 | 100% |  | Attachment D
Thackston | Right-of-Way Use Permits | 150012 | 383587.04 | 233575.04 | 155.7% |  | Exh. JRT-4 | 151
Kensok | Security Compliance | 250001 | 282490.92 | 32489.92 | 13% |  | Exh. JMK-2 | 272
Thackston | Spokane River License Implementation | 535000 | 701776.08 | 166776.08 | 31.17% |  | Exh. JRT-4 | 135
Rosentrater | Strategic Initiatives - Clean Energy Fund 2 | 0 | 55340.01 | 55340.01 | 100% |  | Attachment D
Rosentrater | Strategic Initiatives- UIASSIST | 0 | 100526.57 | 100526.57 | 100% |  | Attachment D
Rosentrater | Structures and Improvements/Furniture | 3349639 | 3828085.76 | 478446.76 | 14.28% |  | Exh. HLR-2 | 281
Rosentrater | Substation - Performance and Capacity | 11076449 | 10944384.22 | -132064.78 | -1.192% |  | Exh. HLR-2 | 429
Rosentrater | T&D Reimbursable | 0 | -112027.25 | -112027.25 | 100% |  | Attachment D
Rosentrater | Tribal Permits & Settlements | 249996 | 0 | -249996 | -100% |  | Exh. HLR-2 | 413
Rosentrater | Washington Advanced Metering Infrastructure Project | 0 | 1659.01 | 1659.01 | 100% |  | Attachment D
Rosentrater | Westside 230/115kV Station Brownfield Rebuild Project | 0 | 269092.18 | 269092.18 | 100% |  | Attachment D
Howell | Wildfire Resiliency Plan | 27000000 | 27120922.46 | 120922.46 | 0.4479% |  | Exh. DRH 2-4
Rosentrater | Wood Pole Management | 12999996 | 12514397.26 | -485598.74 | -3.735% |  | Exh. HLR-2 | 217
Rosentrater | WSDOT Control Zone Mitigation | 1200005 | 897519 | -302486 | -25.21% |  | Exh. HLR-2 | 229
Thackston | WSDOT Franchises | 99996 | 43590.31 | -56405.69 | -56.41% |  | Exh. JRT-4 | 157
| Misc. accrual reversals, corrections or additional TTP |  | -750.35 | -750.35 | 100%
| Total Capital (2) | 445376581 | 464161663.31 | 18785082.31
| Check |  | 0 | 17833423.21 | 94.93% | [yes] Variances Explained
|  |  |  | 951659.1 | 5.066%
(1) Excludes Colstrip Units 3 & 4 2022 and 2023 transfers-to-plant.
(2) Excludes business cases with transfer-to-plant direct to Idaho and Oregon only.
|  | System Planned | System Actual | Variance
|  | 445376581 | 464161663.31 | 18785082.31
4.218%
2023 Report
Net Plant after ADFIT
|  |  | 1.03% | electric - RY1 2023 AMA actuals over approved
| 993900 |  | 0.3203% | nat. gas - RY1 2023 AMA actuals over approved
2023 AMA reflects 2022 EOP and 2023 AMA transfers & Net Plant
|  |  | As-Filed | Actual | Under
|  | 93 | 445376581 | 432014204.28 | -13362376.72
New + Trailing, Cleanup, Timing (30)
|  | 8 |  | 7619529.94 | 7619529.94 | New
|  | 17 |  | 1344368.08 | 1344368.08 | 2022 Prior/cleanup
|  | 5 |  | 23184311.36 | 23184311.36 | BC provided, timing
|  | 30 |  | 32148209.38
|  | 123 | 445376581 | 464162413.66 | 18785832.66

## Variance Summary - Att A 2022
Native Excel Detail ATTACHMENT E [PDF: ATTACHMENT A]
Avista Utilities
2022 Capital Additions (System-Basis) - Summary by Business Case
Support of the 2022 capital pro forma and provisional additions were provided with the Company’s direct filed case, including a description of each Business Case located within the respective direct testimony of Company witnesses Mr. Thackston (Exh. JRT-1T), Mr. Magalsky (Exh. KEM-1T), Ms. Rosentrater (Exh. HLR-1T), Mr. Kensok (Exh. JMK-1T), Mr. Howell (Exh. DRH-1T) and Mr. Kinney (Exh. SJK-1T). Additionally, an exhibit was filed with each witness’s testimony including each full Business Case as noted in Column (F). Additional support is provided as follows: Attachment B - Detail actual transfer-to-plant by month amounts and in-service dates Attachment C - Capital Variance Explanation Forms and supporting justification by Business Case Attachment D - Business Cases not included in direct filing under threshold Attachment E - Native Capital Adjustment excel file supporting transfers-to-plant and Net Plant After ADFIT balances Attachment F - Listing of Infrastructure Investment and Jobs Act and the Inflation Reduction Act Grant Opportunities
|  | (A) | (B) | (C) | (D) | (E) | (F) |  | (G)
|  | 2022 As-Filed TTP (1) | 2022 Actual TTP (1) | Variance $ over/(under) | Variance % over/(under) | $500k & +/- 10% TTP Threshold met? | Direct Filed Exhibit Reference |  | Attach- ment C
Witness | Business Case | Gross Plant | Gross Plant | Gross Plant |  |  | Exh. # | Pg# | Pg#
Kensok | Basic Workplace Technology Delivery | 813479 | 2094785.11 | 1281306.11 | 157.5% | yes | Exh. JMK-2 | 3 | 2
Thackston | Cabinet Gorge Station Service | 7761859 | 0 | -7761859 | -100% | yes | Exh. JRT-4 | 178 | 12
Thackston | Cabinet Gorge Unit 4 Protection & Control Upgrade | 750000 | 3312747.58 | 2562747.58 | 341.7% | yes | Exh. JRT-4 | 45 | 18
Thackston | Clark Fork Settlement Agreement | 4839609 | 3501187.54 | -1338421.46 | -27.66% | yes | Exh. JRT-4 | 51 | 19
Magalsky | Customer Experience Platform Program | 5999915 | 4588240.32 | -1411674.68 | -23.53% | yes | Exh. KEM-2 | 10 | 20
Magalsky | Customer Transactional Systems | 3859166 | 2824042.82 | -1035123.18 | -26.82% | yes | Exh. KEM-2 | 31 | 21
Rosentrater | Distribution Grid Modernization | 2165010 | 2716700.75 | 551690.75 | 25.48% | yes | Exh. HLR-2 | 18 | 22
Rosentrater | Distribution Minor Rebuild | 11499986 | 15056011.15 | 3556025.15 | 30.92% | yes | Exh. HLR-2 | 30 | 23
Rosentrater | Downtown Network - Performance & Capacity | 1100000 | 358877.42 | -741122.58 | -67.37% | yes | Exh. HLR-2 | 77 | 28
Rosentrater | Elec Relocation and Replacement Program | 5399944 | 8595275.06 | 3195331.06 | 59.17% | yes | Exh. HLR-2 | 88 | 29
Magalsky | Electric Transportation | 2775000 | 1997583.91 | -777416.09 | -28.01% | yes | Exh. KEM-2 | 2 | 34
Kensok | Endpoint Compute and Productivity Systems | 3498321 | 5713123.48 | 2214802.48 | 63.31% | yes | Exh. JMK-2 | 32 | 35
Kensok | Energy Delivery Modernization & Operational Efficiency | 5560672 | 8762727.35 | 3202055.35 | 57.58% | yes | Exh. JMK-2 | 142 | 38
Kensok | Energy Resources Modernization & Operational Efficiency | 2727599 | 2205669.73 | -521929.27 | -19.14% | yes | Exh. JMK-2 | 153 | 45
Kensok | Enterprise & Control Network Infrastructure | 3243307 | 3904831.37 | 661524.37 | 20.4% | yes | Exh. JMK-2 | 43 | 73
Kensok | Enterprise Communication Systems | 1472733 | 4267359.9 | 2794626.9 | 189.8% | yes | Exh. JMK-2 | 52 | 88
Kensok | Enterprise Network Infrastructure | 2235285 | 363051.2 | -1872233.8 | -83.76% | yes | Exh. JMK-2 | 236 | 98
Kensok | Enterprise Security | 972340 | 2482394.66 | 1510054.66 | 155.3% | yes | Exh. JMK-2 | 202 | 112
Kensok | Fiber Network Lease Service Replacement | 1392970 | 687524.91 | -705445.09 | -50.64% | yes | Exh. JMK-2 | 91 | 118
Rosentrater | Fleet Services Capital Plan | 7904640 | 6911884.79 | -992755.21 | -12.56% | yes | Exh. HLR-2 | 252 | 128
Rosentrater | Gas Above Grade Pipe Remediation Program | 682000 | 0 | -682000 | -100% | yes | Exh. HLR-2 | 400 | 130
Rosentrater | Gas Airway Heights HP Reinforcement | 9634502 | 7867781.32 | -1766720.68 | -18.34% | yes | Exh. HLR-2 | 420 | 131
Rosentrater | Gas ERT Replacement Program | 0 | 778041.73 | 778041.73 | 100% | yes | New |  | 134
Rosentrater | Gas HP Pipeline Remediation Program | 599998 | 0 | -599998 | -100% | yes | Exh. HLR-2 | 337 | 147
Rosentrater | Gas Isolated Steel Replacement Program | 862754 | 1424684.86 | 561930.86 | 65.13% | yes | Exh. HLR-2 | 340 | 148
Rosentrater | Gas Non-Revenue Program | 9295000 | 10657765.26 | 1362765.26 | 14.66% | yes | Exh. HLR-2 | 343 | 149
Rosentrater | Gas PMC Program | 3500004 | 1657532.77 | -1842471.23 | -52.64% | yes | Exh. HLR-2 | 352 | 150
Rosentrater | Gas Reinforcement Program | 1299997 | 1892133.32 | 592136.32 | 45.55% | yes | Exh. HLR-2 | 359 | 161
Rosentrater | Gas Replacement Street and Highway Program | 3495650 | 4847699.6 | 1352049.6 | 38.68% | yes | Exh. HLR-2 | 363 | 162
Rosentrater | Gas Transient Voltage Mitigation Program | 875000 | 0 | -875000 | -100% | yes | Exh. HLR-2 | 407 | 163
Thackston | Generation DC Supplied System Update | 550001 | 18486.18 | -531514.82 | -96.64% | yes | Exh. JRT-4 | 74 | 166
Kensok | Identity and Access Governance (IAG) | 672255 | 0 | -672255 | -100% | yes | Exh. JMK-2 | 264 | 167
Rosentrater | Joint Use | 2749992 | 4340368.94 | 1590376.94 | 57.83% | yes | Exh. HLR-2 | 102 | 173 | KF-Fuel Yard transferred early in September 2022 with trailing costs into 2023. Orginally planned to transfer in Q1'2023. Used and Useful 09.2022, allowing transfer, resulted in AFUDC savings.
Thackston | KF_Fuel Yard Equipment Replacement | 0 | 31118689.92 | 31118689.92 | 100% | yes | Exh. JRT-4 | 214 | 174
Kensok | Land Mobile Radio & Real Time Communication Systems | 3569746 | 299516.07 | -3270229.93 | -91.61% | yes | Exh. JMK-2 | 109 | 188 | not new - timing
Rosentrater | N Lewiston Autotransformer - Failed Plant | 5554506 | 4394084.58 | -1160421.42 | -20.89% | yes | Exh. HLR-2 | 381 | 194
Rosentrater | New Revenue - Growth | 73429598 | 98845433.84 | 25415835.84 | 34.61% | yes | Exh. HLR-2 | 124 | 195 | New Revenue Growth - Largest increase variance - due to increased costs for transformers and meters due to supply chain issues due to COVID. Meters on a 18-month lead time.
Thackston | Nine Mile HED Battery Building | 800001 | 0 | -800001 | -100% | yes | Exh. JRT-4 | 234 | 196
Thackston | Nine Mile Powerhouse Crane Rehab | 1699988 | 1018790.32 | -681197.68 | -40.07% | yes | Exh. JRT-4 | 243 | 197
Rosentrater | Protection System Upgrade for PRC-002 | 80000 | 2772398.35 | 2692398.35 | 3365% | yes | Exh. HLR-2 | 135 | 198
Rosentrater | Saddle Mountain 230/115kV Station (New) Integration Project Phase 2 | 19962533 | 13416440.18 | -6546092.82 | -32.79% | yes | Exh. HLR-2 | 144 | 199
Thackston | Spokane River License Implementation | 629226 | 107452.18 | -521773.82 | -82.92% | yes | Exh. JRT-4 | 135 | 200
Rosentrater | Spokane Valley Transmission Reinforcement Project | 2000000 | 3037762.39 | 1037762.39 | 51.89% | yes | Exh. HLR-2 | 161 | 201
Rosentrater | Strategic Initiatives - Clean Energy Fund 2 | 0 | 555858.06 | 555858.06 | 100% | yes | New |  | 204
Thackston | Strategic Initiatives - Upriver Park | 225225 | 3823801.67 | 3598576.67 | 1598% | yes | Exh. JRT-4 | 142 | 216
Rosentrater | Structures and Improvements/Furniture | 3639388 | 6384230.91 | 2744842.91 | 75.42% | yes | Exh. HLR-2 | 281 | 217
Rosentrater | Substation - New Distribution Station Capacity Program | 5765300 | 4266887.44 | -1498412.56 | -25.99% | yes | Exh. HLR-2 | 168 | 238
Rosentrater | Substation - Station Rebuilds Program | 12998326 | 10685594.55 | -2312731.45 | -17.79% | yes | Exh. HLR-2 | 175 | 239
Rosentrater | Transmission Construction - Compliance | 2111069 | 4125980.75 | 2014911.75 | 95.45% | yes | Exh. HLR-2 | 188 | 240
Rosentrater | Transmission Major Rebuild - Asset Condition | 5680751 | 3549325.68 | -2131425.32 | -37.52% | yes | Exh. HLR-2 | 197 | 245
Rosentrater | Transmission NERC Low-Risk Priority Lines Mitigation | 2554255 | 1146219.28 | -1408035.72 | -55.13% | yes | Exh. HLR-2 | 204 | 248
Rosentrater | Westside 230/115kV Station Brownfield Rebuild Project | 0 | 3292230.01 | 3292230.01 | 100% | yes | Exh. HLR-2 | 210 | 249 | not new - timing
Rosentrater | Apprentice/Craft Training | 0 | 40544.66 | 40544.66 | 100% |  | Exh. HLR-2 | 236 |  | not new - timing
Kensok | Atlas | 1452641 | 1487355.31 | 34714.31 | 2.39% |  | Exh. JMK-2 | 133
Thackston | Automation Replacement | 349999 | 273450.61 | -76548.39 | -21.87% |  | Exh. JRT-4 | 3
Thackston | Base Load Hydro | 958925 | 639175.84 | -319749.16 | -33.34% |  | Exh. JRT-4 | 10
Thackston | Base Load Thermal Program | 2484254 | 2119961.75 | -364292.25 | -14.66% |  | Exh. JRT-4 | 18
Thackston | Cabinet Gorge 15 kV Bus Replacement | 0 | 13118 | 13118 | 100% |  | Exh. JRT-4 | 26 |  | not new - timing
Thackston | Cabinet Gorge Dam Fishway | 63475101 | 63506220.89 | 31119.89 | 0.04903% |  | Exh. JRT-4 | 30
Thackston | Cabinet Gorge Unit 3 Protection & Control Upgrade | 0 | -844.49 | -844.49 | 100% |  | Exh. JRT-4 | 39 |  | not new - timing
Thackston | Cabinet Gorge Unwatering Pumps | 395000 | 0 | -395000 | -100% |  | Exh. JRT-4 | 192
Rosentrater | Capital Tools & Stores | 2500008 | 2268240.55 | -231767.45 | -9.271% |  | Exh. HLR-2 | 241
Rosentrater | Colstrip Transmission | 325001 | 304255.81 | -20745.19 | -6.383% |  | Exh. HLR-2 | 10
Kensok | Control and Safety Network Infrastructure | 1324039 | 1259128.06 | -64910.94 | -4.902% |  | Exh. JMK-2 | 227
Thackston | CS2 Single Phase Transformer | 0 | -38168.85 | -38168.85 | 100% |  | Exh. JRT-4 | 64 |  | not new - timing
Magalsky | Customer Facing Technology Program | 4078651 | 3941179.02 | -137471.98 | -3.371% |  | Exh. KEM-2 | 19
Kensok | Data Center Compute and Storage Systems | 1260205 | 1535378.98 | 275173.98 | 21.84% |  | Exh. JMK-2 | 12
Kensok | Digital Grid Network | 2801323 | 2511644.92 | -289678.08 | -10.34% |  | Exh. JMK-2 | 22
Rosentrater | Distribution System Enhancements | 6930025 | 7225455.48 | 295430.48 | 4.263% |  | Exh. HLR-2 | 39
Rosentrater | Downtown Network - Asset Condition | 1600000 | 1826048.75 | 226048.75 | 14.13% |  | Exh. HLR-2 | 61
Rosentrater | Electric Storm | 6023406 | 6418007.14 | 394601.14 | 6.551% |  | Exh. HLR-2 | 95
Kinney | Energy Imbalance Market Modernization & Operational Efficiency | 0 | 485828.91 | 485828.91 | 100% |  | Exh. SJK-2 | 14 |  | not new - timing
Kensok | Enterprise Business Continuity | 93045 | 0 | -93045 | -100% |  | Exh. JMK-2 | 197
Kensok | Environmental Control & Monitoring Systems | 1123937 | 840877.53 | -283059.47 | -25.18% |  | Exh. JMK-2 | 70
Kensok | ET Modernization & Operational Efficiency - Technology | 1564548 | 1321960.69 | -242587.31 | -15.51% |  | Exh. JMK-2 | 80
Kensok | Facilities and Storage Location Security | 210919 | 519830.88 | 308911.88 | 146.5% |  | Exh. JMK-2 | 208
Kensok | Financial & Accounting Technology | 1788284 | 1342580.85 | -445703.15 | -24.92% |  | Exh. JMK-2 | 163
Rosentrater | Gas Cathodic Protection Program | 715000 | 873631.8 | 158631.8 | 22.19% |  | Exh. HLR-2 | 315
Rosentrater | Gas Facility Replacement Program (GFRP) Aldyl A Pipe Replacement | 25687251 | 26174099.31 | 486848.31 | 1.895% |  | Exh. HLR-2 | 323
Rosentrater | Gas Operator Qualification Compliance | 0 | 112479.02 | 112479.02 | 100% |  | Exh. HLR-2 | 264 |  | not new - timing
Rosentrater | Gas Overbuilt Pipe Replacement Program | 0 | 353521.34 | 353521.34 | 100% |  | Exh. HLR-2 | 348 |  | not new - timing
Rosentrater | Gas Regulator Station Replacement Program | 985579 | 688078.23 | -297500.77 | -30.19% |  | Exh. HLR-2 | 355
Rosentrater | Gas Telemetry Program | 303256 | 19376.3 | -283879.7 | -93.61% |  | Exh. HLR-2 | 366
Rosentrater | Gas Warden HP Reinforcement | 0 | 202292.95 | 202292.95 | 100% |  |  |  | See Attachment D | New
Thackston | Generation Masonry Building Rehabilitation | 493993 | 0 | -493993 | -100% |  | Exh. JRT-4 | 198
Kensok | Generation, Substation & Gas Location Security | 332159 | 390996.04 | 58837.04 | 17.71% |  | Exh. JMK-2 | 213
Kensok | High Voltage Protection (HVP) Refresh | 226712 | 448988.03 | 222276.03 | 98.04% |  | Exh. JMK-2 | 100
Thackston | HMI Control Software | 3500000 | 3597118.95 | 97118.95 | 2.775% |  | Exh. JRT-4 | 81
Kensok | Human Resources Technology | 499529 | 384845.76 | -114683.24 | -22.96% |  | Exh. JMK-2 | 174
Rosentrater | Jackson Prairie Joint Project | 2378977 | 2363328.56 | -15648.44 | -0.6578% |  | Exh. HLR-2 | 270
Rosentrater | LED Change-Out Program | 299964 | 259501.04 | -40462.96 | -13.49% |  | Exh. HLR-2 | 109
Kensok | Legal & Compliance Technology | 400015 | 555001.38 | 154986.38 | 38.75% |  | Exh. JMK-2 | 187
Thackston | Long Lake Plant Upgrade | 0 | 17125.23 | 17125.23 | 100% |  | Exh. JRT-4 | 102 |  | not new - timing
Rosentrater | Meter Minor Blanket | 0 | 344294.24 | 344294.24 | 100% |  | Exh. HLR-2 | 118 |  | not new - timing
Kensok | Network Backbone | 188444 | 0 | -188444 | -100% |  | Exh. JMK-2 | 246
Kensok | Payment Card Industry Compliance (PCI) | 0 | 18698.77 | 18698.77 | 100% |  | Exh. JMK-2 | 224 |  | not new - timing
Thackston | Peaking Generation Business Case | 445001 | 262829.47 | -182171.53 | -40.94% |  | Exh. JRT-4 | 113
Thackston | Post Falls Landing and Crane Pad Development | 0 | 141872.16 | 141872.16 | 100% |  | Exh. JRT-4 | 121 |  | not new - timing
Rosentrater | Primary URD Cable Replacement | 0 | 35223.53 | 35223.53 | 100% |  | Exh. HLR-2 | 131 |  | not new - timing
Thackston | Regulating Hydro | 2947845 | 2662222.99 | -285622.01 | -9.689% |  | Exh. JRT-4 | 127
Rosentrater | Saddle Mountain 230/115kV Station (New) Integration Project Phase 1 | 0 | 61087.43 | 61087.43 | 100% |  | Exh. HLR-2 | 141 |  | not new - timing
Rosentrater | SCADA - SOO and BuCC | 1026882 | 933768.6 | -93113.4 | -9.068% |  | Exh. HLR-2 | 151
Kensok | Security Compliance | 250001 | 169480.79 | -80520.21 | -32.21% |  | Exh. JMK-2 | 272
Rosentrater | Strategic Initiatives - Real Time Power System Simulator | 0 | 2529.1 | 2529.1 | 100% |  |  |  | See Attachment D | Non-material, Strategic Business Case is an on-going business case which has small projects identified each year
Rosentrater | Strategic Initiatives - South Landing (Catalyst) - Clean Energy Fund 3 | 2297174 | 1958548.21 | -338625.79 | -14.74% |  | Exh. HLR-2 | 275?
Kensok | Technology Failed Assets | 611563 | 877151.03 | 265588.03 | 43.43% |  | Exh. JMK-2 | 119
Kensok | Telecommunication & Network Distribution location Security | 0 | 120514.33 | 120514.33 | 100% |  |  |  | See Attachment D | Prior Business Case, on-going programmatic, seperated "Security" out from prior BC as is growing cost and concern
Rosentrater | Telematics 2025 | 438347 | 156154.85 | -282192.15 | -64.38% |  | Exh. HLR-2 | 297
Rosentrater | Transmission - Minor Rebuild | 3400375 | 3673299.43 | 272924.43 | 8.026% |  | Exh. HLR-2 | 182
Rosentrater | Tribal Permits & Settlements | 259776 | 88164.24 | -171611.76 | -66.06% |  | Exh. HLR-2 | 413
Thackston | Use Permits | 150012 | 265548.9 | 115536.9 | 77.02% |  | Exh. JRT-4 | 151
Rosentrater | Washington Advanced Metering Infrastructure Project | 0 | -25381.36 | -25381.36 | 100% |  | Exh. HLR-2 | 308 |  | not new - timing
Rosentrater | Wood Pole Management | 12999996 | 13011934.01 | 11938.01 | 0.09183% |  | Exh. HLR-2 | 217
Rosentrater | WSDOT Control Zone Mitigation | 749998 | 929099.23 | 179101.23 | 23.88% |  | Exh. HLR-2 | 229
Thackston | WSDOT Franchises | 99996 | 12960.41 | -87035.59 | -87.04% |  | Exh. JRT-4 | 157
Howell | Wildfire Resiliency Plan | 24544986 | 25603735.35 | 1058749.35 | 4.314% |  | Exh. DRH 2-4 | -
Rosentrater | Campus Repurposing Phase 2 | 0 | 11.7 | 11.7 | 100% |  | N/A Account cleanup
Kinney | Energy Imbalance Market | 12016376 | 10838171.21 | -1178204.79 | -9.805% |  | (3)
Rosentrater | T&D Reimbursable | 0 | 236175.47 | 236175.47 | 100% |  | N/A Timing TTP vs receipt
| Total Capital (2) | 449877418 | 505328918.53 | 55451500.53
| Check |  | 0.0099998 | 55780309.21 | 98.5% | [yes] Variances Explained [Excludes EIM Variance]
(1) Excludes Colstrip Units 3 and 4 2022 transfers-to-plant. |  |  |  | 849396.11 | 1.5%
(2) Excludes business cases with transfer-to-plant direct to Idaho and Oregon only.
(3) Energy Imbalance Market variance separately reported to the Commission in Dockets UE-200900, et., al. See Compliance filing dated July 15, 2022, which reported an understatement of net rate base per authorized in Docket UE-200900, and an annual revenue requirement owed customers of $284,000. The Company, therefore, deferred approximately $347,000 for amounts owed customers for the period October 1, 2021 through December 20, 2022.
|  |  | As-Filed | Actual | Under
|  | 96 | 449877418 | 467463176.67 | 17585758.67
New + Trailing, Cleanup, Timing (30)
|  | 3 |  | 1536192.74 | 1536192.74 | New
|  | 2 |  | 359230.6 | 359230.6 | 2022 Prior/cleanup
|  | 16 |  | 35970318.52 | 35970318.52 | BC provided, timing (1)
|  | 21 |  | 37865741.86
|  | 117 | 449877418 | 505328918.53 | 55451500.53
(1) 1 Business case - $31.1M associated with KF-Fuel Yard completed in 2022, versus 2023 as planned.

## TTP Detail - Attachment B 2023
[6 empty] | EOP |  | RY1 2023
[6 empty] | 556034.8692 | 2022 WA E | 556034.8692
[6 empty] | 4836435.3911 | 2023 WA E AMA | 1408798.2393 | RY1 Reg Lag (2023)
[6 empty] | 5392470.2603 |  | 1964833.1085 | 183563.3738 | RR @ Proposed ROR 7.03%
[6 empty] | WA Electric EOP |  | WA Electric 2023 AMA | RY2 (2024) of 2022-2023 impact only
503788.3522
8.308%
[5 empty] | System Actual | 496212.61 | 2022 WA G | 496212.61
[6 empty] | 133774.9575 | 2023 WA G AMA | 7985.6402 | RY1 Reg Lag (2023)
[6 empty] | 629987.5675 |  | 504198.2502 | 47104.424 | RR @ Proposed ROR 7.61%
[6 empty] | WA Nat. Gas EOP |  | WA Nat. Gas 2023 AMA | RY2 (2024) of 2022-2023 impact only
58856.2168
Total WA Approved Transfer
[5 empty] | 1.03% |  | Washington RY1 (2022-2023) Authorized | New Business Cases Total (EOP 2022/AMA 2023)
[6 empty] | WA E | 231792000 | 1964833.1085 | 0.8477%
[6 empty] | WA G | 62335000 | 504198.2502 | 0.8089%
[7 empty] | 294127000 | 2469031.3587 | 0.8394%
RY1 AMA 2022/2023 - Actual WA Transfer in RY1 versus Authorized <1%
[5 empty] | 12.25% |  | RY2 AMA 2022-2024 - Can not be determined, and not appropriate to calculated RY2 impact versus authorized until 2024 AMA completed, because of impact due to timing of authorized BCs TTP between years, and authorized impact on customer rates.
System Actual
0.3203%
|  | 2023 | 2022
| System New TTP | 7619529.94 | 1536192.74 | 9155722.68
| System TTP 2022-2023 Authorized | 445376581 | 449877418 | 895253999
| Variance "New" versus Authorized TTP (System) | 1.711% | 0.3415% | 1.023%
WA Net Transfer to Plant (level of Plant approved by the Commission:
Net Plant After ADFIT
| WA E | WA G | Total WA | %
Net Plant Variance | 20441 | 1634 | 22075 | 0.8929%
Approved Net Plant | 1968698 | 503561 | 2472259