## PCU Response BR02 - A&D Recon
Avista Dockets UE-240006 and UG-240007
Public Counsel Response to Bench Request No. 02, Att D Recon - Discrepancy between 17 Projects on Attach. D Pdf vs 20 Projects in Native Format Attach D
Washington Costs 2023
Business Cases inluded in Attachment A (Native) versus Attachment D (System) | [5 empty] | Allocations from Attach. B filed 3/29/24
Native & Attachment A | Attachment D | Pdf Attachment D (referred to in BR02) | Filed 2023 Budgeted TTP (Gross Plant) | Actual TTP (Gross Plant) | Variance $ over/(under) (Gross Plant) | Electric | Natural Gas | Planned TTP Year & BC Per Direct Filing
1 Att. A | 1 Att. D | Gas Airway Heights HP Reinforcement | 0 | -4593 | -4593 | 0 | -4593 | 2022 Trailing
2 Att. A | 2 Att. D | Gas Warden HP Reinforcement | 0 | 4353.86 | 4353.86 | 0 | 4354 | 2022 Trailing
3 Att. A | 3 Att. D | N Lewiston Autotransformer - Failed Plant | 0 | 9612.5 | 9612.5 | 6300 | 0 | 2022 Trailing
4 Att. A | 4 Att. D | Long Lake Plant Upgrade | 0 | 10792.64 | 10792.64 | 7073 | 0 | 2021/2024 BC
5 Att. A | 5 Att. D | Gas Operator Qualification Compliance | 0 | 31087.27 | 31087.27 | 24005 | 7082 | 2021 BC - programmatic
6 Att. A | 6 Att. D | Primary URD Cable Replacement | 0 | 66023.9 | 66023.9 | 39037 | 0 | 2021 trailing costs
7 Att. A | 7 Att. D | Apprentice / Craft Training | 0 | 62969.63 | 62969.63 | 30090 | 9502 | 2021 BC - programmatic
8 Att. A | 8 Att. D | Gas HP Pipeline Remediation Program | 0 | 139101.69 | 139101.69 | 0 | 139102 | 2022 BC - programmatic
9 Att. A | 9 Att. D | Nine Mile Powerhouse Crane Rehab | 0 | 229460.94 | 229460.94 | 150389 | 0 | 2022 Trailing
10 Att. A | 10 Att. D | Gas ERT Replacement Program | 0 | 236729.77 | 236729.77 | 0 | 31839 | Previous AMI BC, failures in 2023
11 Att. A | 11 Att. D | Asset Monitoring System | 0 | 264723.15 | 264723.15 | 173500 | 0 | New in 2023
12 Att. A | 12 Att. D | Meter Minor Blanket | 0 | 246445.82 | 246445.82 | 82170 | 0 | 2021 BC - programmatic
13 Att. A | 13 Att. D | Westside 230/115 kV Station Brownfield Rebuild Proj. | 0 | 269092.18 | 269092.18 | 175363 | 0 | 2021 trailing costs
14 Att. A | 14 Att. D | Clearwater Wind Generation Interconnection | 0 | 273299.74 | 273299.74 | 179121 | 0 | 2021 (labeled in new in error)
15 Att. A | 15 Att. D | CIP v5 Transition - Cyber Asset Electronic Access | 0 | 191787.05 | 191787.05 | 91645 | 28940 | New to 2022 GRC (Previous 2020 BC)
16 Att. A | 16 Att. D | Strategic Initiatives - Clean Energy Fund 2 | 0 | 55340.01 | 55340.01 | 55340 | 0 | 2022 trailing
17 Att. A | 17 Att. D | Strategic Initiatives - UIASSIST | 0 | 100526.57 | 100526.57 | 88976 | 0 | 2022 BC - programmatic
18 Att. A | x | Payment Card Industry Compliance | 0 | -2207.46 | 0 | -1055 | -333 | 2021 trailing costs
19 Att. A | x | Washington Advanced Metering Infrastructure Project | 0 | 1659.01 | 0 | 1659 | 0 | 2021 trailing costs
20 Att. A | x | T&D Reimbursable | 0 | -112027.25 | 0 | -73423 | 0 | N/A
-750 | -1299 | Misc. accrual reversals, corrections, or additional TTP | x | -750 | 0 | 0 | 0
|  |  |  | 2073428.02 | 2186753.72 | 1030190 | 215893
| ATT A | ATT D
Miscellaneous accrual reversals, corrections (Att A) | -750 | -750
Payment Card Industry Compliance (PCI) | -2207 | 0
Washington Advanced Metering Infrastructure Project | 1659 | 0
Miscellaneous accrual reversals, corrections (Att D) | -1298 | -1299

## PCU Response BR02 - 2023 New BC
Avista Dockets UE-240006 and UG-240007
Public Counsel Response to Bench Request No. 02 |  |  | Washington 2023 Costs
Allocations from Attach. B filed 3/29/24
Line # | 2023 New Business Cases (from Attachment C of 2023 Report) | 2023 Actual TTP (System) | WA Allocation - Electric | Washington Allocation - Gas | WA Electric Total | WA Gas Total | WA Total (Gas + Electric)
1 | Long Lake Stability Enhancement | 1114534 | 65.54% | 0% | 730466 | 0 | 730466
2 | Metro 115kV Substation | 545256 | 65.54% | 0% | 357361 | 0 | 357361
3 | NexGen Control System Networks | 694741 | 47.78% | 15.09% | 331981 | 104835 | 436816
4 | Nine Mile Powerhouse Roof Replacement | 840745 | 65.54% | 0% | 551024 | 0 | 551024
5 | Asset Monitoring System* | 264723 | 65.54% | 0% | 173500 | 0 | 173500
6 | Noxon Rapids Spillgate Refurbishment | 3694444 | 65.54% | 0% | 2421339 | 0 | 2421339
7 | CIP v5 Transition - Cyber Asset Electronic Access* | 264723 | 47.78% | 15.09% | 91645 | 28940 | 120585
8 | Clearwater Wind Generation Interconnection* | 273300 | 65.54% | 0% | 179121 | 0 | 179121
Totals: |  | 7692466 |  |  | 4836437 | 133775 | 4970212
| *Total of 2023 WA Attachment D New Business Cases: | 473206