## OM Detail (C)
Baker License |  | Designated Information is CONFIDENTIAL per Protective Order in WUTC Dockets UE-170033 and UG-170034
WBS Element | WBS Description | 2012 Budget | 2012 Actual | Variance | 2013 Budget | 2013 Actual | Variance | 2014 Budget | 2014 Actual | Variance | 2015 Budget | 2015 Actual | Variance | 2016 Budget | 2016 Actual | Variance
S.00774.01.02.01 | UB Fish Propagation O&M | 277169.9 | 263627.58 | 13542.32 | 286400.45 | 217185.12 | 69215.33 | 78090.96 | 82252.74 | -4161.78 | 78152.96 | 69263.62 | 8889.34 | 79000.96 | 70052.81 | 8948.15
S.00774.01.02.02 | Aquatics Reporting O&M | 18638 | 8739.5 | 9898.5 | 3312 | 4847.01 | -1535.01 | 13312 | 13607.15 | -295.15 | 19712 | 10600.2 | 9111.8 | 20012 | 8757.94 | 11254.06
S.00774.01.02.03 | LB Upstream Fish Passage Implem | 37722.28 | 26141.76 | 11580.52 | 33194.6 | 31475.74 | 1718.86 | 90111 | 22486 | 67625 | 23367 | 22834.64 | 532.36 | 26870 | 25685.16 | 1184.84
S.00774.01.02.04 | Connect Btwn Lk Shannon & Baker | 59587.23 | 59033.25 | 553.98 | 54085.91 | 46461.17 | 7624.74 | 15413.5 | 8866.56 | 6546.94 | 20213.5 | 18169.8 | 2043.7 | 42913.5 | 30428.21 | 12485.29
S.00774.01.02.05.01 | UB Downstream Fish Passage O&M | 120771.15 | 95181.57 | 25589.58 | 70125.98 | 49143.92 | 20982.06 | 53173 | 49702.1 | 3470.9 | 55194 | 46764.44 | 8429.56 | 52740 | 63526.09 | -10786.09
S.00774.01.02.05.02 | LB Downstream Fish Passage O&M |  |  | 0 | 84646.9 | 42686.34 | 41960.56 | 195376 | 216689.34 | -21313.34 | 93376 | 76769.14 | 16606.86 | 28640 | 2819.78 | 25820.22
S.00774.01.02.06 | Flow Implementation O&M | 56130.97 | 34481.77 | 21649.2 | 2244 |  | 2244 | 7277.08 | 0 | 7277.08 | 7277.04 |  | 7277.04 | 5877.84 |  | 5877.84
S.00774.01.02.08 | LB Gravel Replacement O&M | 36326.27 | 31306.87 | 5019.4 | 46849.47 | 43204.2 | 3645.27 | 32660 | 24141.68 | 8518.32 | 57028 | 34495.79 | 22532.21 | 35528 | 32199.17 | 3328.83
S.00774.01.02.09 | Large Woody Debris O&M | 80091.53 | 1733.9 | 78357.63 | 40529.78 | 22151.91 | 18377.87 | 11200 | 4861.62 | 6338.38 | 200 |  | 200 | 110 | 97.2 | 12.8
S.00774.01.02.10 | Shoreline Erosion O&M | 459.96 | 434.65 | 25.31 |  | -931.11 | 931.11 |  |  | 0 |  | 13.48 | -13.48 |  | 229.12 | -229.12
S.00774.02.02 | Programmatic Agreement O&M | 200561.52 | 138006.91 | 62554.61 | 189944.53 | 186424.15 | 3520.38 | 96716.04 | 86451.51 | 10264.53 | 117716.04 | 82518.82 | 35197.22 | 68264.96 | 47362.77 | 20902.19
S.00774.03.02.01 | Recreation Mgmt Report O&M | 8805.4 | 4876.33 | 3929.07 |  | 6485.47 | -6485.47 | 4175 | 6003.52 | -1828.52 | 6100 | 7769 | -1669 | 7100.04 | 4640.74 | 2459.3
S.00774.03.02.02 | Aesthetics Mgmt O&M | 26862 | 26380.04 | 481.96 | 27668 | 128190.96 | -100522.96 | 49824 | 16885 | 32939 | 4564 | 5895.27 | -1331.27 | 4620 | 4950.43 | -330.43
S.00774.03.02.04 | Bak Resr Rec Water Safety Pln O&M | 4428.96 | 6856.57 | -2427.61 | 4611 | 13210.21 | -8599.21 | 8559 | 16156.26 | -7597.26 | 5347 | 7276.2 | -1929.2 | 4620 | 5966.4 | -1346.4
S.00774.03.02.05 | Lower Baker Developd Recreatn O&M |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
S.00774.03.02.06 | UB Visitor Info Services Funding | 2798 | 2734 | 64 | 2882 | 2780 | 102 | 368388 | 356993 | 11395 | 13335 | 13124 | 211 | 13260 | 13294 | -34
S.00774.03.02.07 | UB Visitor Interpretive Svc Fundng | 30444 | 29748 | 696 | 31357 | 30248 | 1109 | 31004 | 30045 | 959 | 31054 | 30564 | 490 | 30879 | 30958 | -79
S.00774.03.02.08 | Dispersed Rec Mgmt Funding O&M | 29208 | 29967 | -759 | 31587 | 30470 | 1117 | 31232 | 30266 | 966 | 31282 | 30789 | 493 | 31106 | 31185 | -79
S.00774.03.02.10 | UB Trail& Trailhead Construction Funding | 52755 | 51549 | 1206 | 400192 | 386037 | 14155 | 341955 | 331378 | 10577 |  |  | 0 |  |  | 0
S.00774.03.02.12 | Developed Rec Monitoring & Funding O&M | 19185.23 | 5982 | 13203.23 |  |  | 0 |  |  | 0 |  |  | 0 | 32923 | 0 | 32923
S.00774.03.02.13 | UB Developed Rec Maint Fund | 91778 | 89682 | 2096 | 170618 | 164583 | 6035 | 137124 | 132882 | 4242 | 39959 | 39328 | 631 | 39734 | 0 | 39734
S.00774.03.02.14 | UB Trail & Trailhead Maint Funding | 85731 | 83773 | 1958 | 88303 | 85180 | 3123 | 87309 | 84608 | 2701 | 87450 | 86070 | 1380 | 86958 | 39835 | 47123
S.00774.03.02.16 | USDA - FS Rd Maint Funding O&M | 19587 | 19139 | 448 | 20174 | 19461 | 713 | 19947 | 19330 | 617 | 19980 | 19664 | 316 | 19867 | 87179 | -67312
S.00774.03.02.18 | Law Enforcement | 106328 | 109857.03 | -3529.03 | 109518 | 169068.16 | -59550.16 | 111286 | 108322 | 2964 | 109552 | 107525.56 | 2026.44 | 108284 | 128595.31 | -20311.31
S.00774.04.02 | Water Quality O&M | 91978.68 | 68167.03 | 23811.65 | 46405.66 | 18964.59 | 27441.07 | 41693.33 | 2820.44 | 38872.89 | 32007.04 | 7240.17 | 24766.87 | 31700.04 | 4144.1 | 27555.94
S.00774.05.02.01 | Terrestrial Res Mgmt Plan O&M | 25994.3 | 10340.36 | 15653.94 | 6129 | 5627.53 | 501.47 | 12394.2 | 10693.34 | 1700.86 | 12579.08 | 13585.03 | -1005.95 | 13746.68 | 16931.49 | -3184.81
S.00774.05.02.02 | Forest Habitat O&M | 5764 | 5636.56 | 127.44 | 6597 | 6197.47 | 399.53 | 5699 | 5611 | 88 | 704 | 704.39 | -0.39 |  | 55.85 | -55.85
S.00774.05.02.03 | Elk Habitat O&M | 57641 | 56419.55 | 1221.45 | 61371 | 47821.46 | 13549.54 | 56993 | 56073 | 920 | 57044 | 57218.4 | -174.4 | 57751 | 58652.62 | -901.62
S.00774.05.02.04 | Wetland Habitat O&M | 161396 | 157716.54 | 3679.46 | 43737.32 | 18073.59 | 25663.73 | 22797 | 22512 | 285 | 2818 | 2844.93 | -26.93 |  | 687.88 | -687.88
S.00774.05.02.05 | Aquatic Riparian Habitat O&M | 57641 | 58652.22 | -1011.22 | 59371 | -265540.21 | 324911.21 | 10743 | 9791.91 | 951.09 | 3750 | 9459.27 | -5709.27 | 5500 | 22833.77 | -17333.77
S.00774.05.02.06 | Osprey Nest Structures O&M | 5246 | 3341.78 | 1904.22 | 7244.64 |  | 7244.64 | 4330 | 2836.9 | 1493.1 | 4930 | 9642.57 | -4712.57 | 3830 | 15777.17 | -11947.17
S.00774.05.02.07 | Loon Floating Nest Platforms O&M | 5816.96 | 1901.48 | 3915.48 | 5821.17 | 10105.48 | -4284.31 | 1158.37 | 4234.35 | -3075.98 | 1360.24 | 1471.57 | -111.33 | 5158.68 | 2624.17 | 2534.51
S.00774.05.02.08 | Noxious Weeds O&M | 44147.43 | 43016.66 | 1130.77 | 37055.14 | 10070.95 | 26984.19 | 28913.86 | 20236.55 | 8677.31 | 28928.86 | 18443.31 | 10485.55 | 29140.64 | 26328.11 | 2812.53
S.00774.05.02.09 | Plants of Special Status O&M | 4797.58 | 1052.4 | 3745.18 | 3553.68 | 2696.89 | 856.79 | 3077.56 | 1760 | 1317.56 | 3077.56 |  | 3077.56 | 4577.56 | 7561.84 | -2984.28
S.00774.05.02.10 | Carex flava O&M | 7887.7 | 1209.52 | 6678.18 | 25185.72 | 21462.33 | 3723.39 | 4077.56 | -1500 | 5577.56 | 26577.56 | 22895.85 | 3681.71 | 3077.52 | 354.37 | 2723.15
S.00774.05.02.11 | Decaying & Legacy Wood O&M | 11528 | 11406.12 | 121.88 | 14320.2 | -17674.94 | 31995.14 | 13835.72 | 11576.55 | 2259.17 | 13888.44 | 12877.98 | 1010.46 | 14010.96 | 11995.77 | 2015.19
S.00774.05.02.12 | Bald Eagle Night Roost Survey O&M |  | 66 | -66 |  | -26336 | 26336 |  |  | 0 |  | 40.25 | -40.25 |  |  | 0
S.00774.05.02.13 | Bald Eagle Mgmt Plans O&M | 3024.74 | 31.08 | 2993.66 |  | 265.58 | -265.58 |  |  | 0 |  |  | 0 |  |  | 0
S.00774.05.02.14 | Use of Habitat Eval Proced O&M |  | 7 | -7 | 21760 | 90938.06 | -69178.06 | 22838 | 10718.09 | 12119.91 |  | 450.95 | -450.95 |  | 321.95 | -321.95
S.00774.05.02.18 | Native Plant Propagation O&M | 3500 |  | 3500 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
S.00774.06.02.01 | Baker River Coord Committee O&M | 8500 | 1114.43 | 7385.57 | 4000.08 | 3842.33 | 157.75 | 5686 | 3939.31 | 1746.69 | 5686 | 2288.16 | 3397.84 | 3286 | 2568.24 | 717.76
S.00774.06.02.02 | Required Funding: TERF O&M |  |  | 0 |  |  | 0 |  |  | 0 |  | 0.26 | -0.26 |  | 4.31 | -4.31
S.00774.06.02.03 | Required Funding: RAM O&M | 57641 | 56580.56 | 1060.44 | 59371 | -8051.13 | 67422.13 | 56993 | 56152 | 841 | 57044 | 57020.23 | 23.77 | 57751 | 58043.06 | -292.06
S.00774.08.02 | License Management O&M | 585462.6 | 744337.83 | -158875.23 | 712354.32 | 677077.72 | 35276.6 | 661385.16 | 671215.72 | -9830.56 | 795127.92 | 763654.21 | 31473.71 | 802832.09 | 841059.1 | -38227.01
S.00774.09.02 | Town of Concrete Improvements O&M | 45999.96 | 27000 | 18999.96 | 47000.04 | 27000 | 20000.04 | 24999.96 | 27000 | -2000.04 | 24999.96 | 27000 | -2000.04 | 24999.96 | 27000 | -2000.04
S.00774.10.02 | Tribal Cultural Agreements O&M | 651999.96 | 618748.34 | 33251.62 | 654999.96 | 637310.76 | 17689.2 | 641985 | 656430.01 | -14445.01 | 661248 | 676122.93 | -14874.93 | 681081.96 | 696406.59 | -15324.63
S.00774.11.02.01 | LA 203 exhibit G Proj Boundry O&M |  | 1188.03 | -1188.03 | 11373.96 | 4174.36 | 7199.6 | 15000 | 1183.02 | 13816.98 | 10000 | 8549.79 | 1450.21 | 5000 | 5713.77 | -713.77
S.00774.11.02.02 | LA 406 Gaging Plan O&M | 12138.96 |  | 12138.96 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
S.00774.11.02.03 | LA 410 Endangered Species Plan O&M | 199 |  | 199 |  | 2034.81 | -2034.81 | 0 | 0 | 0 |  |  | 0 |  | 893.08 | -893.08
S.00774.11.02.04 | Habitat Land Search Fees |  |  | 0 |  | 66677.68 | -66677.68 | 15000 | 6774.29 | 8225.71 | 15000 | 21545.1 | -6545.1 | 9999.99 | 44576.85 | -34576.86
| Total Baker License: | 3213674.27 | 2987165.22 | 226509.05 | 3525894.51 | 3011101.56 | 514792.95 | 3433732.3 | 3221985.96 | 211746.34 | 2577630.2 | 2422490.31 | 155139.89 | 2492752.38 | 2472296.22 | 20456.16
| Variance note: |  |  | (a) |  |  | (b) |  |  | (c) |  |  | (d)
Snoqualmie License
WBS Element | WBS Description | 2012 Budget | 2012 Actual | Variance | 2013 Budget | 2013 Actual | Variance | 2014 Budget | 2014 Actual | Variance | 2015 Budget | 2015 Actual | Variance | 2016 Budget | 2016 Actual | Variance
S.00628.04.02.02 | Recreation & Aesthetics O&M | 7000 | 3163.59 | 3836.41 | 36000 | 20842.49 | 15157.51 | 132567.56 | 72577.77 | 59989.79 | 102567.56 | 38762.75 | 63804.81 | 37495 | 17686.73 | 19808.27
S.00628.04.02.03 | Cultural & Historic O&M | 100377.99 | 48990.6 | 51387.39 | 92188 | 139476.67 | -47288.67 | 90188 | 100034.72 | -9846.72 | 79188 | 72957.6 | 6230.4 | 75024.04 | 67204.83 | 7819.21
S.00628.04.02.04 | Terrestrial O&M | 11470.04 | 5446.55 | 6023.49 | 11495.04 | 2575.86 | 8919.18 | 10495 | 2633.71 | 7861.29 | 8494.92 | 289.59 | 8205.33 | 3495 | 26.46 | 3468.54
S.00628.04.02.05 | Gamefish Enhancement Plan O&M |  | 31583.01 | -31583.01 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
S.00628.04.02.06 | SNO Noxious Weeds | 16282 | 17594.11 | -1312.11 | 12297 | 8834.55 | 3462.45 | 12297 | 2707.33 | 9589.67 | 7297 | 15715.39 | -8418.39 | 7297 | 14309.1 | -7012.1
S.00628.04.02.07 | Water Quality & Support O&M | 46322.98 | 24709.69 | 21613.29 | 52395.15 | 703.24 | 51691.91 | 59833.34 | 5973.98 | 53859.36 | 20000 | 3287.49 | 16712.51 | 25000 | 25327.08 | -327.08
S.00628.08.02 | License Process/Admin O&M | 304464.96 | 174177.26 | 130287.7 | 258882.37 | 182260.01 | 76622.36 | 368277.76 | 284314.22 | 83963.54 | 332314.6 | 264392.12 | 67922.48 | 348462.8 | 246119.85 | 102342.95
S.00628.09.02 | SNO T&D Related to Renovation O&M |  |  |  |  | 5419.87
| Total Snoqualmie License: | 485917.97 | 305664.81 | 180253.16 | 463257.56 | 360112.69 | 108564.74 | 673658.66 | 468241.73 | 205416.93 | 549862.08 | 395404.94 | 154457.14 | 496773.84 | 370674.05 | 126099.79
| Variance note: |  |  | (e) |  |  | (f) |  |  | (g) |  |  | (h) |  |  | (i)
General Variance Notes:
The large capital projects at Baker and Snoqualmie associated with license renewal have adversely affected severalhistoric properties located on , or near these facilities. Mitigation of the adverse impacts have resulted in years of consultation, amendments to the License (Snoqualmie) and Memorandums of Agreements ("MOA's") between PSE and affected parties. During years of this planning and consultation process, O&M budgets were often underrun as capital expenses displaced budgeted O&M activities. In addition, the costs of planning, rewrite of plans and report completion were less than budgeted. While implementation of the License still occurred, some of the expenditures have been delayed to future years to implement the goals of the MOAs. At both projects, O&M is changing from constructionoriented management to public outreach programs. As buildings/structures are demolished or materially altered, emphasis has shifted from building maintenance under historic property rules to public outreach programs or visitor experience .
BakerVariance Notes:
Resource Group task variances (Aquatic Resource Group, Baker River CoordinatingCommittee, Cultural Resource Group, Terrestial Resource Group, Recreation and Aestetics Management)are associated with level of group and technical team consultations conducted, additional meetings to address emergent issues. During under-runs, fewer than anticipated meetings, Outside Services, facilitation and associated work.) Also, decision outcomes of annual consultation w/Services, and other members of the groupon the article’s management plan, which confirms procedures and activities for the year, can result in changes in spending.
(a) -LargeWoody Debris storage site development under budget to scope change and portion of work reclassified as capital ($80K). Plant and weed treatment at Lake Shannon homestead sites did not occur due to unfavorable reservoir conditions ($12K). Town of Concrete and tribal payments were overestimated ($52K). Water Quality studies and coordination were less than anticipated ($86K). Much of year cultural efforts spent defining Lower Baker abutment MOA so budget underran. No carry over of budget.
(b) -Under run primarily reflects a correction to the original accounting for a deposit in years 1 & 2 (2008 & 2009) of the license for Article 505 - Aquatic Riparian Habitat ($325K reclassed as capital). In addition, less work on Articles 105, 109, 401, 504, and 508 than originally anticipated ($60K). O&M work related to the Floating Surface Collector project was reclassified to capital ($70K). Payments to the Town of Concrete and tribal payments were overestimated ($40K). Costs associated with Baker project boundary exhibit updates were less than budgeted as minimal updates were required. These under runs were offset by a reclassification of land search fees from capital to O&M and by prepayment of Article 514 funding obligations due within the first 10 years of the license. No carry over of budget.
(c) -LB Upstream Fish Passage studies were delayed a year due to Unit 4 commissioningdelays ($60K). Downstream Fish Passage consulting services less than anticipated. Costs associated with Baker project boundary exhibit updates were less than budgeted as minimal updates were required. Water Quality, Aesthetics Mgmt. and Cultural efforts were less than anticipated ($90K). Baker River upstream fish trap (UFT) Post-Construction Evaluation (PCE) to confirm that entrance attraction flow is sufficient for adult sockeye and Coho salmon under the increased maximum discharge of the new LB Unit 4 Powerhouse was delayed. Commissioning of UFT originally planned for 2013 was delayed until Oct 2015. The PCE consists largely of analysis of a full year of adult return data under the new flow condition, so funding planned for 2014 was deferred until 2017 and 2018. Carry over budget to 2017 and 2018 (~$60K) .
(d) -Due to high water levels, year end field work not completed ($100K) .Water Quality compliance data assessment less than anticipated ($25K). No carry over of budget.
-Continued-
Snoqualmie Variance Notes:
Water quality compliance related studies and monitoring were to begin after a certain period following the return to normal commercial operation following construction. Capital redevelopment construction completion was delayed in 2015 and 2016. The redevelopment project was completed on October 31, 2016.
(e) - Under run reflects charging of certain cultural and recreation related work to the capital redevelopment initiative project (instead of O&M). No carry over of budget
(f) - Under run reflects charging of certain cultural and recreation related work to the capital redevelopment initiative project (instead of O&M), partially offset by incremental costs for additional safety features. No carry over of budget
(g) Delay in initiating the Snoqualmie 402 channel surveys. Recreation related costs were less than budgeted due to recreation use monitoring under runs and anticipated visitor shuttle service not initiated . No carry over of budget
(h) - Summer interns started later than scheduled. Security costs associated with opening of the new museum at the depot less than originally thought. Anticipated consulting fees in association with the recreation studies were less than budgeted. Post construction license activities delayed due to continued capital Redevelopment work. Carry over of budget ~$25K to 2016
(i) - Open manager position, park visitor program support and license admin labor less than budgeted. Delay in water quality standards technical assessment work and documentation due to continued capital Redevelopment work .Carry over of budget ~$25K to 2017

## Baker Hydro License O&M (C)
Hydro Rate Year License O&M
Baker License | WBS Element | wbs Description |  | Rate Yr | 001/2018 | 002/2018 | 003/2018 | 004/2018 | 005/2018 | 006/2018 | 007/2018 | 008/2018 | 009/2018 | 010/2018 | 011/2018 | 012/2018
Baker License | S.00774.01.02.01 | UB Fish Propagation O&M |  | 82407.95 | 855.08 | 12711.17 | 554.17 | 1854.17 | 2854.17 | 354.17 | 354.17 | 354.17 | 554.17 | 60554.17 | 554.17 | 854.17
Baker License | S.00774.01.02.02 | Aquatics Reporting O&M |  | 20612 | 3315 | 187 | 3315 | 3137 | 165 | 3337 | 165 | 187 | 3315 | 187 | 3115 | 187
Baker License | S.00774.01.02.03 | LB Upstream Fish Passage Implem |  | 67181.15 | 2587.27 | 14723.08 | 7087.08 | 7087.08 | 7087.08 | 7087.08 | 87.08 | 87.08 | 87.08 | 21087.08 | 87.08 | 87.08
Baker License | S.00774.01.02.04 | Connect Btwn Lk Shannon & Baker |  | 46413.5 | 2500 | 2500 | 82.5 | 1000 | 16000 | 104.5 | 1222.75 | 1594 | 18709 |  | 200.75 | 2500
Baker License | S.00774.01.02.05.01 | UB Downstream Fish Passage O&M |  | 56782.1 | 179.85 | 4814.75 | 178.75 | 178.75 | 178.75 | 3178.75 | 4178.75 | 178.75 | 4178.75 | 20178.75 | 178.75 | 19178.75
Baker License | S.00774.01.02.05.02 | LB Downstream Fish Passage O&M |  | 32641.1 | 221.1 | 220 | 220 | 220 | 220 | 3220 | 4220 | 220 | 4220 | 220 | 220 | 19220
Baker License | S.00774.01.02.06 | Flow Implementation O&M |  | 5880.19 | 490.19 | 490 | 490 | 490 | 490 | 490 | 490 | 490 | 490 | 490 | 490 | 490
Baker License | S.00774.01.02.08 | LB Gravel Replacement O&M |  | 37528.03 | 3127.4 | 3127.33 | 3127.33 | 3127.33 | 3127.33 | 3127.33 | 3127.33 | 3127.33 | 3127.33 | 3127.33 | 3127.33 | 3127.33
Baker License | S.00774.01.02.09 | Large Woody Debris O&M |  | 110.04 | 9.17 | 9.17 | 9.17 | 9.17 | 9.17 | 9.17 | 9.17 | 9.17 | 9.17 | 9.17 | 9.17 | 9.17
Baker License | S.00774.02.02 | Programmatic Agreement O&M |  | 193016.4 | 6476.77 | 8676.33 | 20226.33 | 9976.33 | 22176.33 | 27726.33 | 19476.33 | 26426.33 | 14476.33 | 19226.33 | 12676.33 | 5476.33
Baker License | S.00774.03.02.01 | Recreation Mgmt Report O&M |  | 7100.04 | 591.67 | 591.67 | 591.67 | 591.67 | 591.67 | 591.67 | 591.67 | 591.67 | 591.67 | 591.67 | 591.67 | 591.67
Baker License | S.00774.03.02.02 | Aesthetics Mgmt O&M |  | 12755 |  | 8755 | [7 empty] | 4000
Baker License | S.00774.03.02.04 | Bak Resr Rec Water Safety Pln O&M |  | 4887 |  | 887 | [7 empty] | 4000
Baker License | S.00774.03.02.05 | Lower Baker Developd Recreatn O&M |  | 25106 |  | 25106
Baker License | S.00774.03.02.06 | UB Visitor Info Services Funding |  | 14304 |  | 14304
Baker License | S.00774.03.02.07 | UB Visitor Interpretive Svc Fundng |  | 40660 |  | 40660
Baker License | S.00774.03.02.08 | Dispersed Rec Mgmt Funding O&M |  | 33556 |  | 33556
Baker License | S.00774.03.02.13 | UB Developed Rec Maint Fund |  | 42864 |  | 42864
Baker License | S.00774.03.02.14 | UB Trail & Trailhead Maint Funding |  | 93807 |  | 93807
Baker License | S.00774.03.02.16 | USDA - FS Rd Maint Funding O&M |  | 21432 |  | 21432
Baker License | S.00774.03.02.18 | Law Enforcement |  | 116279 |  | 94279 | [7 empty] | 22000
Baker License | S.00774.04.02 | Water Quality O&M |  | 31700.04 | 2641.67 | 2641.67 | 2641.67 | 2641.67 | 2641.67 | 2641.67 | 2641.67 | 2641.67 | 2641.67 | 2641.67 | 2641.67 | 2641.67
Baker License | S.00774.05.02.01 | Terrestrial Res Mgmt Plan O&M |  | 13952.64 | 1162.72 | 1162.72 | 1162.72 | 1162.72 | 1162.72 | 1162.72 | 1162.72 | 1162.72 | 1162.72 | 1162.72 | 1162.72 | 1162.72
Baker License | S.00774.05.02.03 | Elk Habitat O&M |  | 61085 |  | 11085 | [7 empty] | 50000
Baker License | S.00774.05.02.05 | Aquatic Riparian Habitat O&M |  | 5500.08 | 458.34 | 458.34 | 458.34 | 458.34 | 458.34 | 458.34 | 458.34 | 458.34 | 458.34 | 458.34 | 458.34 | 458.34
Baker License | S.00774.05.02.06 | Osprey Nest Structures O&M |  | 4030.08 | 335.84 | 335.84 | 335.84 | 335.84 | 335.84 | 335.84 | 335.84 | 335.84 | 335.84 | 335.84 | 335.84 | 335.84
Baker License | S.00774.05.02.07 | Loon Floating Nest Platforms O&M |  | 4000.08 | 333.34 | 333.34 | 333.34 | 333.34 | 333.34 | 333.34 | 333.34 | 333.34 | 333.34 | 333.34 | 333.34 | 333.34
Baker License | S.00774.05.02.08 | Noxious Weeds O&M |  | 30140.74 | 984.81 | 4309.63 | 984.63 | 984.63 | 984.63 | 984.63 | 984.63 | 984.63 | 984.63 | 984.63 | 15984.63 | 984.63
Baker License | S.00774.05.02.09 | Plants of Special Status O&M |  | 3077.7 | 256.64 | 256.46 | 256.46 | 256.46 | 256.46 | 256.46 | 256.46 | 256.46 | 256.46 | 256.46 | 256.46 | 256.46
Baker License | S.00774.05.02.10 | Carex flava O&M |  | 3077.7 | 256.64 | 256.46 | 256.46 | 256.46 | 256.46 | 256.46 | 256.46 | 256.46 | 256.46 | 256.46 | 256.46 | 256.46
Baker License | S.00774.05.02.11 | Decaying & Legacy Wood O&M |  | 12217 |  | 2217 | [7 empty] | 10000
Baker License | S.00774.06.02.01 | Baker River Coord Committee O&M |  | 5685.96 | 23.83 | 23.83 | 23.83 | 23.83 | 2723.83 | 23.83 | 23.83 | 23.83 | 23.83 | 23.83 | 2723.83 | 23.83
Baker License | S.00774.06.02.03 | Required Funding: RAM O&M |  | 180177 |  | 35177 | [7 empty] | 145000
Baker License | S.00774.08.02 | License Management O&M |  | 884024.6 | 73707.69 | 73649.23 | 73707.69 | 73649.23 | 73707.69 | 73649.23 | 73707.69 | 73649.23 | 73649.23 | 73649.23 | 73649.23 | 73649.23
Baker License | S.00774.09.02 | Town of Concrete Improvements O&M |  | 24999.96 | 2083.33 | 2083.33 | 2083.33 | 2083.33 | 2083.33 | 2083.33 | 2083.33 | 2083.33 | 2083.33 | 2083.33 | 2083.33 | 2083.33
Baker License | S.00774.10.02 | Tribal Cultural Agreements O&M |  | 722561.04 | 60213.42 | 60213.42 | 60213.42 | 60213.42 | 60213.42 | 60213.42 | 60213.42 | 60213.42 | 60213.42 | 60213.42 | 60213.42 | 60213.42
Baker License | S.00774.11.02.01 | LA 203 exhibit G Proj Boundry O&M |  | 5000.04 | 416.67 | 416.67 | 416.67 | 416.67 | 416.67 | 416.67 | 416.67 | 416.67 | 416.67 | 416.67 | 416.67 | 416.67
Baker License | S.00774.11.02.04 | Habitat Land Search Fees |  | 9999.96 | 833.33 | 833.33 | 833.33 | 833.33 | 833.33 | 833.33 | 833.33 | 833.33 | 833.33 | 833.33 | 833.33 | 833.33
|  |  | Total Rate Year Baker License O&M: | 2956552.12 | 164061.77 | 619153.77 | 179589.73 | 171320.77 | 199307.23 | 192875.27 | 177629.98 | 176914.77 | 193407.77 | 504320.77 | 182599.52 | 195370.77
|  |  | Test Year O&M: | 2499721.87
|  |  | Adjustment: | 456830.25
(a)
Baker License | WBS Element | wbs Description | 2012 Budget | 2012 Actual | Variance | 2013 Budget | 2013 Actual | Variance | 2014 Budget | 2014 Actual | Variance | 2015 Budget | 2015 Actual | Variance | 2016 Budget | 2016 Actual | Variance
Baker License | S.00774.01.02.01 | UB Fish Propagation O&M | 277169.9 | 263627.58 | 13542.32 | 286400.45 | 217185.12 | 69215.33 | 78090.96 | 82252.74 | -4161.78 | 78152.96 | 69263.62 | 8889.34 | 79000.96 | 70052.81 | 8948.15
Baker License | S.00774.01.02.02 | Aquatics Reporting O&M | 18638 | 8739.5 | 9898.5 | 3312 | 4847.01 | -1535.01 | 13312 | 13607.15 | -295.15 | 19712 | 10600.2 | 9111.8 | 20012 | 8757.94 | 11254.06
Baker License | S.00774.01.02.03 | LB Upstream Fish Passage Implem | 37722.28 | 26141.76 | 11580.52 | 33194.6 | 31475.74 | 1718.86 | 90111 | 22486 | 67625 | 23367 | 22834.64 | 532.36 | 26870 | 25685.16 | 1184.84
Baker License | S.00774.01.02.04 | Connect Btwn Lk Shannon & Baker | 59587.23 | 59033.25 | 553.98 | 54085.91 | 46461.17 | 7624.74 | 15413.5 | 8866.56 | 6546.94 | 20213.5 | 18169.8 | 2043.7 | 42913.5 | 30428.21 | 12485.29
Baker License | S.00774.01.02.05.01 | UB Downstream Fish Passage O&M | 120771.15 | 95181.57 | 25589.58 | 70125.98 | 49143.92 | 20982.06 | 53173 | 49702.1 | 3470.9 | 55194 | 46764.44 | 8429.56 | 52740 | 63526.09 | -10786.09
Baker License | S.00774.01.02.05.02 | LB Downstream Fish Passage O&M |  |  | 0 | 84646.9 | 42686.34 | 41960.56 | 195376 | 216689.34 | -21313.34 | 93376 | 76769.14 | 16606.86 | 28640 | 2819.78 | 25820.22
Baker License | S.00774.01.02.06 | Flow Implementation O&M | 56130.97 | 34481.77 | 21649.2 | 2244 |  | 2244 | 7277.08 | 0 | 7277.08 | 7277.04 |  | 7277.04 | 5877.84 |  | 5877.84
Baker License | S.00774.01.02.08 | LB Gravel Replacement O&M | 36326.27 | 31306.87 | 5019.4 | 46849.47 | 43204.2 | 3645.27 | 32660 | 24141.68 | 8518.32 | 57028 | 34495.79 | 22532.21 | 35528 | 32199.17 | 3328.83
Baker License | S.00774.01.02.09 | Large Woody Debris O&M | 80091.53 | 1733.9 | 78357.63 | 40529.78 | 22151.91 | 18377.87 | 11200 | 4861.62 | 6338.38 | 200 |  | 200 | 110 | 97.2 | 12.8
Baker License | S.00774.02.02 | Programmatic Agreement O&M | 200561.52 | 138006.91 | 62554.61 | 189944.53 | 186424.15 | 3520.38 | 96716.04 | 86451.51 | 10264.53 | 117716.04 | 82518.82 | 35197.22 | 68264.96 | 47362.77 | 20902.19
Baker License | S.00774.03.02.01 | Recreation Mgmt Report O&M | 8805.4 | 4876.33 | 3929.07 |  | 6485.47 | -6485.47 | 4175 | 6003.52 | -1828.52 | 6100 | 7769 | -1669 | 7100.04 | 4640.74 | 2459.3
Baker License | S.00774.03.02.02 | Aesthetics Mgmt O&M | 26862 | 26380.04 | 481.96 | 27668 | 128190.96 | -100522.96 | 49824 | 16885 | 32939 | 4564 | 5895.27 | -1331.27 | 4620 | 4950.43 | -330.43
Baker License | S.00774.03.02.04 | Bak Resr Rec Water Safety Pln O&M | 4428.96 | 6856.57 | -2427.61 | 4611 | 13210.21 | -8599.21 | 8559 | 16156.26 | -7597.26 | 5347 | 7276.2 | -1929.2 | 4620 | 5966.4 | -1346.4
Baker License | S.00774.03.02.05 | Lower Baker Developd Recreatn O&M |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
Baker License | S.00774.03.02.06 | UB Visitor Info Services Funding | 2798 | 2734 | 64 | 2882 | 2780 | 102 | 368388 | 356993 | 11395 | 13335 | 13124 | 211 | 13260 | 13294 | -34
Baker License | S.00774.03.02.07 | UB Visitor Interpretive Svc Fundng | 30444 | 29748 | 696 | 31357 | 30248 | 1109 | 31004 | 30045 | 959 | 31054 | 30564 | 490 | 30879 | 30958 | -79
Baker License | S.00774.03.02.08 | Dispersed Rec Mgmt Funding O&M | 29208 | 29967 | -759 | 31587 | 30470 | 1117 | 31232 | 30266 | 966 | 31282 | 30789 | 493 | 31106 | 31185 | -79
Baker License | S.00774.03.02.13 | UB Developed Rec Maint Fund | 91778 | 89682 | 2096 | 170618 | 164583 | 6035 | 137124 | 132882 | 4242 | 39959 | 39328 | 631 | 39734 | 0 | 39734
Baker License | S.00774.03.02.14 | UB Trail & Trailhead Maint Funding | 85731 | 83773 | 1958 | 88303 | 85180 | 3123 | 87309 | 84608 | 2701 | 87450 | 86070 | 1380 | 86958 | 39835 | 47123
Baker License | S.00774.03.02.16 | USDA - FS Rd Maint Funding O&M | 19587 | 19139 | 448 | 20174 | 19461 | 713 | 19947 | 19330 | 617 | 19980 | 19664 | 316 | 19867 | 87179 | -67312
Baker License | S.00774.03.02.18 | Law Enforcement | 106328 | 109857.03 | -3529.03 | 109518 | 169068.16 | -59550.16 | 111286 | 108322 | 2964 | 109552 | 107525.56 | 2026.44 | 108284 | 128595.31 | -20311.31
Baker License | S.00774.04.02 | Water Quality O&M | 91978.68 | 68167.03 | 23811.65 | 46405.66 | 18964.59 | 27441.07 | 41693.33 | 2820.44 | 38872.89 | 32007.04 | 7240.17 | 24766.87 | 31700.04 | 4144.1 | 27555.94
Baker License | S.00774.05.02.01 | Terrestrial Res Mgmt Plan O&M | 25994.3 | 10340.36 | 15653.94 | 6129 | 5627.53 | 501.47 | 12394.2 | 10693.34 | 1700.86 | 12579.08 | 13585.03 | -1005.95 | 13746.68 | 16931.49 | -3184.81
Baker License | S.00774.05.02.03 | Elk Habitat O&M | 57641 | 56419.55 | 1221.45 | 61371 | 47821.46 | 13549.54 | 56993 | 56073 | 920 | 57044 | 57218.4 | -174.4 | 57751 | 58652.62 | -901.62
Baker License | S.00774.05.02.05 | Aquatic Riparian Habitat O&M | 57641 | 58652.22 | -1011.22 | 59371 | -265540.21 | 324911.21 | 10743 | 9791.91 | 951.09 | 3750 | 9459.27 | -5709.27 | 5500 | 22833.77 | -17333.77
Baker License | S.00774.05.02.06 | Osprey Nest Structures O&M | 5246 | 3341.78 | 1904.22 | 7244.64 |  | 7244.64 | 4330 | 2836.9 | 1493.1 | 4930 | 9642.57 | -4712.57 | 3830 | 15777.17 | -11947.17
Baker License | S.00774.05.02.07 | Loon Floating Nest Platforms O&M | 5816.96 | 1901.48 | 3915.48 | 5821.17 | 10105.48 | -4284.31 | 1158.37 | 4234.35 | -3075.98 | 1360.24 | 1471.57 | -111.33 | 5158.68 | 2624.17 | 2534.51
Baker License | S.00774.05.02.08 | Noxious Weeds O&M | 44147.43 | 43016.66 | 1130.77 | 37055.14 | 10070.95 | 26984.19 | 28913.86 | 20236.55 | 8677.31 | 28928.86 | 18443.31 | 10485.55 | 29140.64 | 26328.11 | 2812.53
Baker License | S.00774.05.02.09 | Plants of Special Status O&M | 4797.58 | 1052.4 | 3745.18 | 3553.68 | 2696.89 | 856.79 | 3077.56 | 1760 | 1317.56 | 3077.56 |  | 3077.56 | 4577.56 | 7561.84 | -2984.28
Baker License | S.00774.05.02.10 | Carex flava O&M | 7887.7 | 1209.52 | 6678.18 | 25185.72 | 21462.33 | 3723.39 | 4077.56 | -1500 | 5577.56 | 26577.56 | 22895.85 | 3681.71 | 3077.52 | 354.37 | 2723.15
Baker License | S.00774.05.02.11 | Decaying & Legacy Wood O&M | 11528 | 11406.12 | 121.88 | 14320.2 | -17674.94 | 31995.14 | 13835.72 | 11576.55 | 2259.17 | 13888.44 | 12877.98 | 1010.46 | 14010.96 | 11995.77 | 2015.19
Baker License | S.00774.06.02.01 | Baker River Coord Committee O&M | 8500 | 1114.43 | 7385.57 | 4000.08 | 3842.33 | 157.75 | 5686 | 3939.31 | 1746.69 | 5686 | 2288.16 | 3397.84 | 3286 | 2568.24 | 717.76
Baker License | S.00774.06.02.03 | Required Funding: RAM O&M | 57641 | 56580.56 | 1060.44 | 59371 | -8051.13 | 67422.13 | 56993 | 56152 | 841 | 57044 | 57020.23 | 23.77 | 57751 | 58043.06 | -292.06
Baker License | S.00774.08.02 | License Management O&M | 585462.6 | 744337.83 | -158875.23 | 712354.32 | 677077.72 | 35276.6 | 661385.16 | 671215.72 | -9830.56 | 795127.92 | 763654.21 | 31473.71 | 802832.09 | 841059.1 | -38227.01
Baker License | S.00774.09.02 | Town of Concrete Improvements O&M | 45999.96 | 27000 | 18999.96 | 47000.04 | 27000 | 20000.04 | 24999.96 | 27000 | -2000.04 | 24999.96 | 27000 | -2000.04 | 24999.96 | 27000 | -2000.04
Baker License | S.00774.10.02 | Tribal Cultural Agreements O&M | 651999.96 | 618748.34 | 33251.62 | 654999.96 | 637310.76 | 17689.2 | 641985 | 656430.01 | -14445.01 | 661248 | 676122.93 | -14874.93 | 681081.96 | 696406.59 | -15324.63
Baker License | S.00774.11.02.01 | LA 203 exhibit G Proj Boundry O&M |  | 1188.03 | -1188.03 | 11373.96 | 4174.36 | 7199.6 | 15000 | 1183.02 | 13816.98 | 10000 | 8549.79 | 1450.21 | 5000 | 5713.77 | -713.77
Baker License | S.00774.11.02.04 | Habitat Land Search Fees |  |  | 0 |  | 66677.68 | -66677.68 | 15000 | 6774.29 | 8225.71 | 15000 | 21545.1 | -6545.1 | 9999.99 | 44576.85 | -34576.86
|  | Total Baker License: | 2955251.38 | 2765742.39 | 189508.99 | 3053608.19 | 2534822.16 | 518786.03 | 3040443.3 | 2851766.87 | 188676.43 | 2574108.2 | 2418436.05 | 155672.15 | 2459829.38 | 2470104.03 | -10274.65
Baker Inter WBS Variability
Baker License | WBS Element | wbs Description | 2012 | 2013 | 2014 | 2015 | 2016 | Avg
Baker License | S.00774.01.02.01 | UB Fish Propagation O&M | 95.11% | 75.83% | 105.3% | 88.63% | 88.67% | 90.72%
Baker License | S.00774.01.02.02 | Aquatics Reporting O&M | 46.89% | 146.3% | 102.2% | 53.78% | 43.76% | 78.6%
Baker License | S.00774.01.02.03 | LB Upstream Fish Passage Implem | 69.3% | 94.82% | 24.95% | 97.72% | 95.59% | 76.48%
Baker License | S.00774.01.02.04 | Connect Btwn Lk Shannon & Baker | 99.07% | 85.9% | 57.52% | 89.89% | 70.91% | 80.66%
Baker License | S.00774.01.02.05.01 | UB Downstream Fish Passage O&M | 78.81% | 70.08% | 93.47% | 84.73% | 120.5% | 89.51%
Baker License | S.00774.01.02.05.02 | LB Downstream Fish Passage O&M | 0% | 50.43% | 110.9% | 82.22% | 9.846% | 50.68%
Baker License | S.00774.01.02.06 | Flow Implementation O&M | 61.43% | 0% | 0% | 0% | 0% | 12.29%
Baker License | S.00774.01.02.08 | LB Gravel Replacement O&M | 86.18% | 92.22% | 73.92% | 60.49% | 90.63% | 80.69%
Baker License | S.00774.01.02.09 | Large Woody Debris O&M | 2.165% | 54.66% | 43.41% | 0% | 88.36% | 37.72%
Baker License | S.00774.02.02 | Programmatic Agreement O&M | 68.81% | 98.15% | 89.39% | 70.1% | 69.38% | 79.16%
Baker License | S.00774.03.02.01 | Recreation Mgmt Report O&M | 55.38% | 0% | 143.8% | 127.4% | 65.36% | 78.38%
Baker License | S.00774.03.02.02 | Aesthetics Mgmt O&M | 98.21% | 463.3% | 33.89% | 129.2% | 107.2% | 166.3%
Baker License | S.00774.03.02.04 | Bak Resr Rec Water Safety Pln O&M | 154.8% | 286.5% | 188.8% | 136.1% | 129.1% | 179.1%
Baker License | S.00774.03.02.05 | Lower Baker Developd Recreatn O&M | 0% | 0% | 0% | 0% | 0% | 0%
Baker License | S.00774.03.02.06 | UB Visitor Info Services Funding | 97.71% | 96.46% | 96.91% | 98.42% | 100.3% | 97.95%
Baker License | S.00774.03.02.07 | UB Visitor Interpretive Svc Fundng | 97.71% | 96.46% | 96.91% | 98.42% | 100.3% | 97.95%
Baker License | S.00774.03.02.08 | Dispersed Rec Mgmt Funding O&M | 102.6% | 96.46% | 96.91% | 98.42% | 100.3% | 98.93%
Baker License | S.00774.03.02.13 | UB Developed Rec Maint Fund | 97.72% | 96.46% | 96.91% | 98.42% | 0% | 77.9%
Baker License | S.00774.03.02.14 | UB Trail & Trailhead Maint Funding | 97.72% | 96.46% | 96.91% | 98.42% | 45.81% | 87.06%
Baker License | S.00774.03.02.16 | USDA - FS Rd Maint Funding O&M | 97.71% | 96.47% | 96.91% | 98.42% | 438.8% | 165.7%
Baker License | S.00774.03.02.18 | Law Enforcement | 103.3% | 154.4% | 97.34% | 98.15% | 118.8% | 114.4%
Baker License | S.00774.04.02 | Water Quality O&M | 74.11% | 40.87% | 6.765% | 22.62% | 13.07% | 31.49%
Baker License | S.00774.05.02.01 | Terrestrial Res Mgmt Plan O&M | 39.78% | 91.82% | 86.28% | 108% | 123.2% | 89.81%
Baker License | S.00774.05.02.03 | Elk Habitat O&M | 97.88% | 77.92% | 98.39% | 100.3% | 101.6% | 95.21%
Baker License | S.00774.05.02.05 | Aquatic Riparian Habitat O&M | 101.8% | -447.3% | 91.15% | 252.2% | 415.2% | 82.61%
Baker License | S.00774.05.02.06 | Osprey Nest Structures O&M | 63.7% | 0% | 65.52% | 195.6% | 411.9% | 147.3%
Baker License | S.00774.05.02.07 | Loon Floating Nest Platforms O&M | 32.69% | 173.6% | 365.5% | 108.2% | 50.87% | 146.2%
Baker License | S.00774.05.02.08 | Noxious Weeds O&M | 97.44% | 27.18% | 69.99% | 63.75% | 90.35% | 69.74%
Baker License | S.00774.05.02.09 | Plants of Special Status O&M | 21.94% | 75.89% | 57.19% | 0% | 165.2% | 64.04%
Baker License | S.00774.05.02.10 | Carex flava O&M | 15.33% | 85.22% | -36.79% | 86.15% | 11.51% | 32.29%
Baker License | S.00774.05.02.11 | Decaying & Legacy Wood O&M | 98.94% | -123.4% | 83.67% | 92.72% | 85.62% | 47.51%
Baker License | S.00774.06.02.01 | Baker River Coord Committee O&M | 13.11% | 96.06% | 69.28% | 40.24% | 78.16% | 59.37%
Baker License | S.00774.06.02.03 | Required Funding: RAM O&M | 98.16% | -13.56% | 98.52% | 99.96% | 100.5% | 76.72%
Baker License | S.00774.08.02 | License Management O&M | 127.1% | 95.05% | 101.5% | 96.04% | 104.8% | 104.9%
Baker License | S.00774.09.02 | Town of Concrete Improvements O&M | 58.7% | 57.45% | 108% | 108% | 108% | 88.03%
Baker License | S.00774.10.02 | Tribal Cultural Agreements O&M | 94.9% | 97.3% | 102.3% | 102.2% | 102.3% | 99.79%
Baker License | S.00774.11.02.01 | LA 203 exhibit G Proj Boundry O&M | 0% | 36.7% | 7.887% | 85.5% | 114.3% | 48.87%
Baker License | S.00774.11.02.04 | Habitat Land Search Fees | 0% | 0% | 45.16% | 143.6% | 445.8% | 126.9%
|  | total | 93.59% | 83.01% | 93.79% | 93.95% | 100.4% | 92.95% | Baker Overall Budget Accuracy

## Sno Hydro License O&M (C)
Hydro Rate Year License O&M
Snoqualmie License | WBS Element | wbs Description | Rate Yr | 001/2018 | 002/2018 | 003/2018 | 004/2018 | 005/2018 | 006/2018 | 007/2018 | 008/2018 | 009/2018 | 010/2018 | 011/2018 | 012/2018
Snoqualmie License | S.00628.04.02.02 | Recreation & Aesthetics O&M | 47495.14 | 3124.76 | 3124.58 | 3124.58 | 3124.58 | 3124.58 | 5624.58 | 5624.58 | 5624.58 | 5624.58 | 3124.58 | 3124.58 | 3124.58
Snoqualmie License | S.00628.04.02.03 | Cultural & Historic O&M | 84024.44 | 7002.44 | 7002 | 7002 | 7002 | 7002 | 7002 | 7002 | 7002 | 7002 | 7002 | 7002 | 7002
Snoqualmie License | S.00628.04.02.04 | Terrestrial O&M | 3495.18 | 291.43 | 291.25 | 291.25 | 291.25 | 291.25 | 291.25 | 291.25 | 291.25 | 291.25 | 291.25 | 291.25 | 291.25
Snoqualmie License | S.00628.04.02.06 | SNO Noxious Weeds | 7297.19 | 608.2 | 608.09 | 608.09 | 608.09 | 608.09 | 608.09 | 608.09 | 608.09 | 608.09 | 608.09 | 608.09 | 608.09
Snoqualmie License | S.00628.04.02.07 | Water Quality & Support O&M | 15000 | 1250 | 1250 | 1250 | 1250 | 1250 | 1250 | 1250 | 1250 | 1250 | 1250 | 1250 | 1250
Snoqualmie License | S.00628.08.02 | License Process/Admin O&M | 380771.04 | 31753.98 | 31719.39 | 31753.98 | 31719.39 | 31753.98 | 31719.39 | 31753.98 | 31719.39 | 31719.39 | 31719.39 | 31719.39 | 31719.39
|  | Total Rate Year Snoqualmie License O&M: | 538082.99 | 44030.81 | 43995.31 | 44029.9 | 43995.31 | 44029.9 | 46495.31 | 46529.9 | 46495.31 | 46495.31 | 43995.31 | 43995.31 | 43995.31
|  | Test Year O&M: | 403705.68 | Staff uses test year due to observed budget variances
|  | Adjustment: | 134377.31
Snoqualmie License
| WBS Element | WBS Description | 2012 Budget | 2012 Actual | Variance | 2013 Budget | 2013 Actual | Variance | 2014 Budget | 2014 Actual | Variance | 2015 Budget | 2015 Actual | Variance | 2016 Budget | 2016 Actual | Variance
| S.00628.04.02.02 | Recreation & Aesthetics O&M | 7000 | 3163.59 | 3836.41 | 36000 | 20842.49 | 15157.51 | 132567.56 | 72577.77 | 59989.79 | 102567.56 | 38762.75 | 63804.81 | 37495 | 17686.73 | 19808.27
| S.00628.04.02.03 | Cultural & Historic O&M | 100377.99 | 48990.6 | 51387.39 | 92188 | 139476.67 | -47288.67 | 90188 | 100034.72 | -9846.72 | 79188 | 72957.6 | 6230.4 | 75024.04 | 67204.83 | 7819.21
| S.00628.04.02.04 | Terrestrial O&M | 11470.04 | 5446.55 | 6023.49 | 11495.04 | 2575.86 | 8919.18 | 10495 | 2633.71 | 7861.29 | 8494.92 | 289.59 | 8205.33 | 3495 | 26.46 | 3468.54
| S.00628.04.02.06 | SNO Noxious Weeds | 16282 | 17594.11 | -1312.11 | 12297 | 8834.55 | 3462.45 | 12297 | 2707.33 | 9589.67 | 7297 | 15715.39 | -8418.39 | 7297 | 14309.1 | -7012.1
| S.00628.04.02.07 | Water Quality & Support O&M | 46322.98 | 24709.69 | 21613.29 | 52395.15 | 703.24 | 51691.91 | 59833.34 | 5973.98 | 53859.36 | 20000 | 3287.49 | 16712.51 | 25000 | 25327.08 | -327.08
| S.00628.08.02 | License Process/Admin O&M | 304464.96 | 174177.26 | 130287.7 | 258882.37 | 182260.01 | 76622.36 | 368277.76 | 284314.22 | 83963.54 | 332314.6 | 264392.12 | 67922.48 | 348462.8 | 246119.85 | 102342.95
|  | Total Snoqualmie License: | 485917.97 | 274081.8 | 211836.17 | 463257.56 | 354692.82 | 108564.74 | 673658.66 | 468241.73 | 205416.93 | 549862.08 | 395404.94 | 154457.14 | 496773.84 | 370674.05 | 126099.79
Snoqualmie Inter-WBS Variability
Snoqualmie License |  |  | 2012 | 2013 | 2014 | 2015 | 2016 | Avg
| WBS Element | WBS Description
| S.00628.04.02.02 | Recreation & Aesthetics O&M | 45.19% | 57.9% | 54.75% | 37.79% | 47.17% | 48.56%
| S.00628.04.02.03 | Cultural & Historic O&M | 48.81% | 151.3% | 110.9% | 92.13% | 89.58% | 98.55%
| S.00628.04.02.04 | Terrestrial O&M | 47.49% | 22.41% | 25.09% | 3.409% | 0.7571% | 19.83%
| S.00628.04.02.06 | SNO Noxious Weeds | 108.1% | 71.84% | 22.02% | 215.4% | 196.1% | 122.7%
| S.00628.04.02.07 | Water Quality & Support O&M | 53.34% | 1.342% | 9.984% | 16.44% | 101.3% | 36.48%
| S.00628.08.02 | License Process/Admin O&M | 57.21% | 70.4% | 77.2% | 79.56% | 70.63% | 71%
|  | Total Snoqualmie License: | 56.4% | 76.56% | 69.51% | 71.91% | 74.62% | 69.8% | Snoqualmie overall budget accuracy
Staff