|  | Year 2000 Status – As Of End 3nd Qtr. 1999 |
| --- | --- |

|  | Inventory§ | Assessment‡ | Remediation | Unit Testing |
| --- | --- | --- | --- | --- |

|  | % Complete | Est Comp Date | % Complete | Est Comp Date | % Complete | Est Comp Date | % Complete | Est Comp Date |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Network Elements | 100% | 12/31/98 | 100% | 3/31/99 | 97% | 10/31/99 | 81% | 11/31/99 |
| Support Systems | 100% | 12/31/98 | 100% | 3/31/99 | 86% | 10/31/99 | 15% | 11/31/99 |
| Auxiliary Systems | 100% | 12/31/98 | 100% | 3/31/99 | 100% | 6/30/99 | 100% | 9/31/99 |

|  | Integration and System Test | Rollout |
| --- | --- | --- |

|  | %Complete | Est Comp Date | % Complete | Est Comp Date |
| --- | --- | --- | --- | --- |
| Network Elements | 0% | 9/31/99 | 81% | 11/31/99 |
| Support Systems | 0% | 9/31/99 | 13% | 11/31/99 |
| Auxiliary Systems | 0% | 9/31/99 | 100% | 9/31/99 |

§ Equipment that is put into service during 1999 is Inventoried and Assessed upon requisition.

‡ This will cover initial assessment, i.e. checking a component’s status with OEM.  Toledo Telephone Co., Inc. will re-check the status of critical components with OEMs thought 1999, in the event of a component’s status changing since initial assessment.

Year 2000 Contingency Plan Status As Of End 3nd Qtr, 1999

|  | Assessment of probability of failure and risk | Preparation of contingency plan |
| --- | --- | --- |

|  | % Complete | Est Comp Date | % Complete | Est Comp Date |
| --- | --- | --- | --- | --- |
| Network Elements | 100% | 4/30/99 | 95% | 11/30/99 |
| Support Systems | 100% | 4/30/99 | 95% | 11/30/99 |
| Auxiliary Systems | 100% | 4/30/99 | 95% | 11/30/99 |
| Electric Power | 100% | 4/30/99 | 95% | 11/30/99 |
| Suppliers | 100% | 4/30/99 | 95% | 11/30/99 |