## Sheet1
Table 4-1 2015-2019 SPECIFIC PROJECTS | [15 empty] | Overhead Rate | 20.28%
FP # | Pipeline Projects | District | Notes | 2015 Direct Cost | 2015 Loaded Cost | 2016 Direct Cost | 2016 Loaded Cost | 2017 Direct Cost | 2017 Loaded Cost | 2018 Direct Cost | 2018 Loaded Cost | 2019 Direct Cost | 2019 Loaded Cost | Total Direct | Total Loaded | 1.2028
200687 | Anacortes Bare Steel Replacement - Phase III | Mt. Vernon | Bare steel replacement as part of Pipe Replacement Program. Carry over from 2013 | 1950000 | 2345460 | 1950000 | 2345460 | 1950000 | 2345460 | 1950000 | 2345460 | 1950000 | 2345460 | 9750000 | 11727300
200686 | Longview Bare Steel Replacement - Phase IV | Longview | Bare steel replacement as part of Pipe Replacement Program | 1950000 | 2345460 | 2050000 | 2465740 | 2150000 | 2586020 | 2150000 | 2586020 | 0 | 0 | 8300000 | 9983240
302594 | Kelso Bare Steel Replacement - Phase I | Longview | Bare steel replacement as part of Pipe Replacement Program | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 2405600 | 2000000 | 2405600
300346 | 12" Longview HP Replacement - Phase I | Longview | Bare steel replacement as part of Pipe Replacement Program | 0 | 0 | 1191611 | 1433269.7108 | 1532071 | 1842774.9988 | 1702302 | 2047528.8456 | 1702302 | 2047528.8456 | 6128286 | 7371102.4008
306996 | Kelso Mill Street Replacement | Longview | 100 ft @ S. 11th | 125000 | 150350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 150350
200080 | Kitsap Phase IV Construction | Aberdeen | Transmission line construction. 4.25 miles. | 7000000 | 8419600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7000000 | 8419600
302595 | Kitsap Phase V ROW Acquisition | Aberdeen | ROW acquisition for transmission line | 0 | 0 | 500000 | 601400 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 601400
302595 | Kitsap Phase V Construction | Aberdeen | Transmission line construction. ≈ 3 miles | 0 | 0 | 0 | 0 | 5000000 | 6014000 | 0 | 0 | 0 | 0 | 5000000 | 6014000
300363 | Shelton Bare Steel Replacement - Phase I | Aberdeen | Bare steel replacement as part of Pipe Replacement Program | 0 | 0 | 1400000 | 1683920 | 1400000 | 1683920 | 1400000 | 1683920 | 1400000 | 1683920 | 5600000 | 6735680
306981 | McCleary 2" IP Reinforcement/Replacement | Aberdeen | Reinforce/replace 2" IP at gate with 3,100 ft of 4" HP | 0 | 0 | 0 | 0 | 270000 | 324756 | 0 | 0 | 0 | 0 | 270000 | 324756
306982 | Vance Creek Exposure | Aberdeen | 8" Grays Harbor Line - pipe exposed in creek. Replace approx. 800 ft. by HDD | 1000000 | 1202800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1202800
306983 | Camp Creek Exposure | Aberdeen | 8" Grays Harbor Line - pipe exposed in cree, off CC 100. Replace approx. 800 ft by HDD. | 1000000 | 1202800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1202800
307181 | Ferndale Reinforcement | Bellingham | Reinforcement near Olson Road and Mountain View Road | 603872 | 726337.2416 |  | 0 |  | 0 |  | 0 |  | 0 | 603872 | 726337.2416
300233 | Arlington 6" HP Reinforcement | Mt. Vernon | Previously on 5 year budget. | 0 | 0 | 1425180 | 1714206.504 | 0 | 0 | 0 | 0 | 0 | 0 | 1425180 | 1714206.504
306984 | Stanwood Reinforcement | Mt. Vernon | ≈ 1,500 ft of 4" PE (2017 Project) | 0 | 0 | 0 | 0 | 95000 | 114266 | 0 | 0 | 0 | 0 | 95000 | 114266
306985 | Sedro Woolley IP Reinforcement | Mt. Vernon | ≈ 500 ft at Highway 20 crossing (2016 project) | 0 | 0 | 85000 | 102238 | 0 | 0 | 0 | 0 | 0 | 0 | 85000 | 102238
306986 | 3" Burlington HP Line ROW | Mt. Vernon | 2015 project | 125000 | 150350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 150350
306986 | 3" Burlington HP Line Construction | Mt. Vernon | 6,700 ft HP steel. 2016 project | 0 | 0 | 675000 | 811890 | 0 | 0 | 0 | 0 | 0 | 0 | 675000 | 811890
306987 | Burlington Reinforcement at Peterson Road | Mt. Vernon | Replace about 6,500 ft 2 in with larger pipe. 2017 project | 0 | 0 | 0 | 0 | 240000 | 288672 | 0 | 0 | 0 | 0 | 240000 | 288672
302596 | 8" Attalia HP Line - Phase I | Kennewick | Phase I of a multi-phase replacement between the gate and Snake River. 1950s pipeline. ≈ 1 mile. | 0 | 0 | 1000000 | 1202800 | 1200000 | 1443360 | 1400000 | 1683920 | 1400000 | 1683920 | 5000000 | 6014000
306988 | Walla Walla HP Line | Walla Walla | HP Line from new Walla Walla gate | 0 | 0 | 0 | 0 | 1300000 | 1563640 | 0 | 0 | 0 | 0 | 1300000 | 1563640
302588 | ` | Kennewick | HP main to accommodate new growth and coordinate with City of Kennewick construction | 703521.44 | 846195.588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 703521.44 | 846195.588
200076 | Handord DOE | Kennewick | 12" HP line to Hanford Nuclear Reservation | 1812700 | 2180315.56 | 25520000 | 30695456 | 22600000 | 27183280 | 0 | 0 | 0 | 0 | 49932700 | 60059051.56
200688 | Bend Bare Steel Replacement - Phase IV | Bend | Continuation of bare steel replacement project. | 2000000 | 2405600 | 2000000 | 2405600 | 2000000 | 2405600 | 2000000 | 2405600 | 2000000 | 2405600 | 10000000 | 12028000
200689 | 12" Bend HP Line #1 Replacement | Bend | Replacing shallow/exposed line near high school and elementary | 0 | 0 | 1500000 | 1804200 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 1804200
306997 | 4" Madras HP Line | Bend |  | 0 | 0 | 500000 | 601400 | 500000 | 601400 | 500000 | 601400 | 500000 | 601400 | 2000000 | 2405600
302677 | Hermiston 2" Steel Reinforcement | Pendleton | ≈ 1,000 ft of 2" steel, will allow retirement of R-26. 5 year plan to address Cold Springs area. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
302640 | 6" Pilot Rock Line Replacement | Pendleton | ≈ 2,100 ft of 6" HP steel line to replace exisitng from rectifier @ Circle Road and CR-1386 to R-59. | 0 | 0 | 400000 | 481120 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 481120
302641 | 4" Pilot Rock IP Reinforcement | Pendleton | 4" plastic main reinforcement from R-64 to bridge in town. ≈ 2,500 ft | 0 | 0 | 400000 | 481120 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 481120
306989 | Umatilla 2" Reinforcement | Pendleton | Reinforce Umatilla IP system from the east, crossing under I-82, approx. 5,000 ft. 4 in HP steel | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 601400 | 0 | 0 | 500000 | 601400
303140 | Yakima Bare Steel Replacement | Yakima | Multi phase project | 0 | 0 | 0 | 0 | 0 | 0 | 1950000 | 2345460 | 1950000 | 2345460 | 3900000 | 4690920
303141 | Milton-Freewater Bare Steel Replacement | Pendleton |  | 0 | 0 | 1525000 | 1834270 | 1525000 | 1834270 | 1525000 | 1834270 |  | 0 | 4575000 | 5502810
303142 | Pendleton/Pilot Rock Bare Steel Replacement | Pendleton |  | 0 | 0 | 1600000 | 1924480 | 1600000 | 1924480 | 1600000 | 1924480 | 1600000 | 1924480 | 6400000 | 7697920
306990 | Pendleton 4" IP Reinforcement | Pendleton | 2,800 ft of 4 in PE connecting Ladow Ave to Tutuilla Road | 0 | 0 | 400000 | 481120 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 481120
306991 | Pendleton 4" HP Reinforcement | Pendleton | 2019 project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 360840 | 300000 | 360840
306992 | Pendleton Korvola Road 4 in PE Reinforcement | Pendleton | 2,700 ft of 4 in PE from Korvola and 45th to McKay Creek crossing | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 481120 | 0 | 0 | 400000 | 481120
304022 | 4" Grandview HP Line #3 Replacement | Yakima |  | 975000 | 1172730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 975000 | 1172730
307221 | 8" Future High Pressure | Yakima |  | 0 | 0 | 750000 | 902100 | 1000000 | 1202800 | 1000000 | 1202800 | 0 | 0 | 2750000 | 3307700
307225 | River Road Reinforcement | Yakima |  | 0 | 0 | 300000 | 360840 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 360840
307211 | Silverdale Reinforcement @ HWY3 | Bremerton |  | 0 | 0 | 871135 | 1047801.178 |  | 0 |  | 0 |  | 0 | 871135 | 1047801.178
306993 | Port Orchard Reinforcement | Bremerton | ≈ 1,850 ft of 4" PE. 2016 project. | 0 | 0 | 165000 | 198462 | 0 | 0 | 0 | 0 | 0 | 0 | 165000 | 198462
306994 | Manchester Reinforcement | Bremerton | ≈ 5,400 ft of 4" PE. 2017 project. | 0 | 0 | 0 | 0 | 200000 | 240560 | 0 | 0 | 0 | 0 | 200000 | 240560
306995 | Othello Reinforcement | Wenatchee | Reinforcement along Reynolds/14th Avenue, approx. 5,300 ft, 2016 project | 0 | 0 | 292000 | 351217.6 | 0 | 0 | 0 | 0 | 0 | 0 | 292000 | 351217.6
307026 | Ontario 6" IP Replacement | Eastern Oregon | ≈ 300 feet long | 244710 | 294337.188 |  | 0 |  | 0 |  | 0 |  | 0 | 244710 | 294337.188
307027 | Highway 3 Casing Removal | Bremerton | Replace casing/carrier pipe. High priority. | 162199 | 195092.9572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 162199 | 195092.9572
307024 | Sunnyside 2" IP Main | Yakima | Remove R-58 and replace house piping with 2" main and service lines at Sunnyside mental facility | 276000 | 331972.8 |  | 0 |  | 0 |  | 0 |  | 0 | 276000 | 331972.8
FP # | Gate Projects | District | Notes | 2015 Direct Cost | 2015 Loaded Cost | 2016 Direct Cost | 2016 Loaded Cost | 2017 Direct Cost | 2017 Loaded Cost | 2018 Direct Cost | 2018 Loaded Cost | 2019 Direct Cost | 2019 Loaded Cost | Total Direct | Total Loaded
101505 | Arlington Gate Upgrade | Mt. Vernon | Carry over from 2013 | 2000000 | 2405600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 2405600
302645 | McCleary Gate Heater | Aberdeen | Necessary for 2014 to coordinate with Williams | 125000 | 150350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 150350
302724 | McCleary Gate Upgrade | Aberdeen | Station rebuild with R-10, R-52 and O-2. Also includes replacing 8" line between CNGC and Williams. Unodorized gas for ≈100ft, pitting @ regs and odorizer, incorporates heater. | 1850000 | 2225180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1850000 | 2225180
302648 | Southridge Gate Station Project | Kennewick | Gate station to accommodate new growth | 958200 | 1152522.96 |  | 0 |  | 0 |  | 0 |  | 0 | 958200 | 1152522.96
200282 | Sun River Gate Upgrade | Bend | Previously on 5 year budget | 1877537.29 | 2258301.8524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1877537.29 | 2258301.8524
| Ontario Gate Upgrade | Eastern Oregon | Part of Frys Foods upgrade - include odorizer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
304020 | Bellingham Gate Upgrade | Bellingham | Carry over from 2014 | 545000 | 655526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 545000 | 655526
306998 | New Walla Walla Gate | Walla Walla |  | 0 | 0 | 0 | 0 | 2500000 | 3007000 | 0 | 0 | 0 | 0 | 2500000 | 3007000
FP # | Odorizer Projects | District | Notes | 2015 Direct Cost | 2015 Loaded Cost | 2016 Direct Cost | 2016 Loaded Cost | 2017 Direct Cost | 2017 Loaded Cost | 2018 Direct Cost | 2018 Loaded Cost | 2019 Direct Cost | 2019 Loaded Cost | Total Direct | Total Loaded
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0
FP # | Reg Projects | District | Notes | 2015 Direct Cost | 2015 Loaded Cost | 2016 Direct Cost | 2016 Loaded Cost | 2017 Direct Cost | 2017 Loaded Cost | 2018 Direct Cost | 2018 Loaded Cost | 2019 Direct Cost | 2019 Loaded Cost | Total Direct | Total Loaded
302652 | R-26 Relocate | Bremerton | Vault in narrow lot in residential area. Will require a new reg station with a building to reduce noise. Bremerton #2 priority. | 300000 | 360840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 360840
302653 | R-64 | Bremerton | Reg station in vault in street. Want to relocate, along with valve, to Walgreens property in Silverdale. Bremerton #5 priority. | 0 | 0 | 155000 | 186434 | 0 | 0 | 0 | 0 | 0 | 0 | 155000 | 186434
FP # | Valve Projects | District | Notes | 2015 Direct Cost | 2015 Loaded Cost | 2016 Direct Cost | 2016 Loaded Cost | 2017 Direct Cost | 2017 Loaded Cost | 2018 Direct Cost | 2018 Loaded Cost | 2019 Direct Cost | 2019 Loaded Cost | Total Direct | Total Loaded
302705 | V-22 | Bremerton | Burwell and Callow in Bremerton. 8" Rockwell plug valve located in drivline at bottom of hill. Need to relocate to parking area, out of driveline. Bremerton #4 priority. | 175000 | 210490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175000 | 210490
302713 | Chico Check Meter | Bremerton | Leaking Cameron valves | 0 | 0 | 175000 | 210490 | 0 | 0 | 0 | 0 | 0 | 0 | 175000 | 210490
302714 | V-23 Retirement and New Valve | Pendleton | Valve near college baseball fields and RR tracks. To be retired and replaced near R-52 to allow isolation of Pilot Rock line. | 190000 | 228532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190000 | 228532
306999 | V-13 | Bremerton | Sidney Avenue and Radey Street in Port Orchard. In a vault in drivelane with a bad lid. Want to relocate to back of ROW or in an easement | 125000 | 150350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 150350
307001 | V-29 | Pendleton | 4" valve off of 8" Boardman line | 101000 | 121482.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101000 | 121482.8
307002 | V-9 | Aberdeen | In a vault on Grays Harbor line | 0 | 0 | 165000 | 198462 | 0 | 0 | 0 | 0 | 0 | 0 | 165000 | 198462
FP # | Bridge/Exposure Projects | District | Notes | 2015 Direct Cost | 2015 Loaded Cost | 2016 Direct Cost | 2016 Loaded Cost | 2017 Direct Cost | 2017 Loaded Cost | 2018 Direct Cost | 2018 Loaded Cost | 2019 Direct Cost | 2019 Loaded Cost | Total Direct | Total Loaded
302663 | Bellingham Bridge Crossing Removal | Bellingham | Removing pipe from bridges, installing new reg station & 1700ft of 2", and remove ≈ 25-30 reg stations | 800000 | 962240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 962240
200394 | Squalicum Creek Exposure | Bellingham | Contractor bid from Michels Pipeline for $405,000. Commission has commented. | 750000 | 902100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 902100
307025 | Shelton 4" IP Bridge Removal | Aberdeen |  | 230311 | 277018.0708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 230311 | 277018.0708
307212 | Kelso Grade Street Bridge Removal | Longview |  | 250000 | 300700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 300700
302666 | Mt. Washington Bridge | Bend | Pedestrian bridge will be removed in the future. | 0 | 0 | 375000 | 451050 | 0 | 0 | 0 | 0 | 0 | 0 | 375000 | 451050
302668 | American Lane Bridge | Bend | Pipeline is encased in concrete (thrust block?) from city water project. May require replacement due to City of Bend project in the future. |  | 0 | 250000 | 300700 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 300700
FP # | Forced Relocations | District | Notes | 2015 Direct Cost | 2015 Loaded Cost | 2016 Direct Cost | 2016 Loaded Cost | 2017 Direct Cost | 2017 Loaded Cost | 2018 Direct Cost | 2018 Loaded Cost | 2019 Direct Cost | 2019 Loaded Cost | Total Direct | Total Loaded
307003 | Dakota Creek Bridge Relocate - Blaine | Bellingham |  | 850000 | 1022380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 850000 | 1022380
302670 | R-47 Relocate | Bremerton | County project to restore fish habitat. May replace or remove and add piping. | 120000 | 144336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 144336
302672 | Bremerton R-146 Project - Tremont Road | Bremerton | Includes relocating R-146, ≈400 ft of 2" steel IP main, ≈300 ft of 2" steel HP main, ≈1,500 ft of 4" steel HP main, and ≈7 HPSS | 466000 | 560504.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 466000 | 560504.8
307213 | Woodland Roundabout Forced Relocate | Longview | Lewis River Road and Old Pacific Highway | 175000 | 210490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175000 | 210490
305740 | College Place CARS Project | Walla Walla | Forced relocation along College Avenue | 2028003 | 2439282.0084 |  | 0 |  | 0 |  | 0 |  | 0 | 2028003 | 2439282.0084
FP # | Other Projects | District | Notes | 2015 Direct Cost | 2015 Loaded Cost | 2016 Direct Cost | 2016 Loaded Cost | 2017 Direct Cost | 2017 Loaded Cost | 2018 Direct Cost | 2018 Loaded Cost | 2019 Direct Cost | 2019 Loaded Cost | Total Direct | Total Loaded
302715 | 16" N. Whatcom Valve Vaults | Bellingham |  | 125000 | 150350 | 125000 | 150350 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 300700
|  |  | TOTAL SPECIFIC FUNDING PROJECTS | 33969053.73 | 40857977.8264 | 47744926 | 57427596.9928 | 47062071 | 56606258.9988 | 18077302 | 21743378.8456 | 14802302 | 17804208.8456 | 161655654.73 | 194439421.5092
FP # | Blanket FPs | State | Notes | 2015 Direct Cost | 2015 Loaded Cost | 2016 Direct Cost | 2016 Loaded Cost | 2017 Direct Cost | 2017 Loaded Cost | 2018 Direct Cost | 2018 Loaded Cost | 2019 Direct Cost | 2019 Loaded Cost | Total Direct | Total Loaded
101170 | Mains - OR | Oregon |  | 407000 | 489539.6 | 413105 | 496882.694 | 419301.575 | 504335.9344 | 425591.0986 | 511900.9734 | 431974.9651 | 519579.488 | 2096972.6387 | 2522238.6899
101171 | General Reinforcement - OR | Oregon |  | 102500 | 123287 | 126018.12 | 151574.5947 | 126018.12 | 151574.5947 | 126018.12 | 151574.5947 | 126018.12 | 151574.5947 | 606572.48 | 729585.3789
101172 | General Relocation/Replacement | Oregon | Emerging relocation, pipe replacement, valve replacement | 282000 | 339189.6 | 556764.6 | 669676.4609 | 556764.6 | 669676.4609 | 556764.6 | 669676.4609 | 556764.6 | 669676.4609 | 2509058.4 | 3017895.4435
101175 | General Gate Station Upgrade or Reg Station Replacement | Oregon | Emerging gate station station upgrade, reg station replacement, odorizer replacement | 102000 | 122685.6 | 103530 | 124525.884 | 105082.95 | 126393.7723 | 106659.1942 | 128289.6788 | 108259.0822 | 130214.024 | 525531.2264 | 632108.9591
101176 | Services - OR | Oregon |  | 953305.9659 | 1146636.4157 | 1000032 | 1202838.4896 | 1035036 | 1244941.3008 | 1071264 | 1288516.3392 |  | 0 | 4059637.9659 | 4882932.5453
101181 | Large Volume Meter Sets | Oregon |  | 41000 | 49314.8 | 42006 | 50524.8168 | 42006 | 50524.8168 | 42006 | 50524.8168 | 42006 | 50524.8168 | 209024 | 251414.0672
101190 | Mains - WA | Washington |  | 814000 | 979079.2 | 826210 | 993765.388 | 838603.15 | 1008671.8688 | 851182.1972 | 1023801.9469 | 863949.9302 | 1039158.9761 | 4193945.2775 | 5044477.3797
101191 | General Reinforcement | Washington |  | 284500 | 342196.6 | 255453.24 | 307259.1571 | 255453.24 | 307259.1571 | 264396 | 318015.5088 |  | 0 | 1059802.48 | 1274730.4229
101192 | General Relocation/Replacement | Washington | Emerging relocation, pipe replacement, valve replacement | 978000 | 1176338.4 | 981144 | 1180120.0032 | 981144 | 1180120.0032 | 1015488 | 1221428.9664 |  | 0 | 3955776 | 4758007.3728
101196 | General Gate Station Upgrade or Reg Station Replacement | Washington | Emerging gate station station upgrade, reg station replacement, odorizer replacement | 245000 | 294686 | 408552 | 491406.3456 | 408552 | 491406.3456 | 408552 | 491406.3456 | 408552 | 491406.3456 | 1879208 | 2260311.3824
101197 | Services - WA | Washington |  | 2859917.8976 | 3439909.2472 | 2902816.666 | 3491507.8859 | 2946358.916 | 3543880.5042 | 2990554.2998 | 3597038.7118 | 3035412.6143 | 3650994.2924 | 14735060.3936 | 17723330.6415
101201 | Large Volume Meter Sets | Washington |  | 102000 | 122685.6 | 102138.12 | 122851.7307 | 102138.12 | 122851.7307 | 102138.12 | 122851.7307 | 102138.12 | 122851.7307 | 510552.48 | 614092.5229
|  |  | TOTAL BLANKET FUNDING PROJECTS | 7171223.8634 | 8625548.0629 | 7717769.746 | 9282933.4505 | 7816458.671 | 9401636.4895 | 7960613.6299 | 9575026.074 | 5675075.4317 | 6825980.7293 | 36341141.3421 | 43711124.8063
|  |  | TOTAL SPECIFIC AND BLANKET FUNDING PROJECTS | 41140277.5934 | 49483525.8894 | 55462695.746 | 66710530.4433 | 54878529.671 | 66007895.4883 | 26037915.6299 | 31318404.9196 | 20477377.4317 | 24630189.5749 | 197996796.0721 | 238150546.3155

## Sheet2
FP # | Gate Projects | District | Notes | 2015 Direct Cost - Cascade Owned | 2015 Direct Cost - Non-Cascade Owned | Notes
101505 | Arlington Gate Upgrade | Mt. Vernon | #REF! | 1200000 | 800000
302645 | McCleary Gate Heater | Aberdeen | #REF! | 125000 | 0 | All Williams costs paid in 2014
302724 | McCleary Gate Upgrade | Aberdeen | #REF! | 1050000 | 800000
302648 | Southridge Gate Station Project | Kennewick | #REF! | 958200 | 0 | All Williams costs paid in 2014
200282 | Sun River Gate Upgrade | Bend | #REF! | 604837.29 | 1272700
304020 | Bellingham Gate Upgrade | Bellingham | Carry over from 2014 | 545000 | 0 | All Williams costs paid in 2014

## Sheet3
2015-2019 SPECIFIC PROJECTS | [15 empty] | Overhead Rate | 23.37%
FP # | Pipeline Projects | District | Notes | 2015 Direct Cost | 2015 Loaded Cost | 2016 Direct Cost | 2016 Loaded Cost | 2017 Direct Cost | 2017 Loaded Cost | 2018 Direct Cost | 2018 Loaded Cost | 2019 Direct Cost | 2019 Loaded Cost | Total Direct | Total Loaded | 1.2337
200687 | Anacortes Bare Steel Replacement - Phase III | Mt. Vernon | Bare steel replacement as part of Pipe Replacement Program. Carry over from 2013 | 1950000 | 2405715 | 1950000 | 2405715 | 1950000 | 2405715 | 1950000 | 2405715 | 1950000 | 2405715 | 9750000 | 12028575
300233 | Arlington 6" HP Reinforcement | Mt. Vernon | Previously on 5 year budget. | 0 | 0 | 1425180 | 1758244.566 | 0 | 0 | 0 | 0 | 0 | 0 | 1425180 | 1758244.566
306984 | Stanwood Reinforcement | Mt. Vernon | ≈ 1,500 ft of 4" PE (2017 Project) | 0 | 0 | 0 | 0 | 95000 | 117201.5 | 0 | 0 | 0 | 0 | 95000 | 117201.5
306985 | Sedro Woolley IP Reinforcement | Mt. Vernon | ≈ 500 ft at Highway 20 crossing (2016 project) | 0 | 0 | 85000 | 104864.5 | 0 | 0 | 0 | 0 | 0 | 0 | 85000 | 104864.5
306986 | 3" Burlington HP Line ROW | Mt. Vernon | 2015 project | 125000 | 154212.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 154212.5
306986 | 3" Burlington HP Line Construction | Mt. Vernon | 6,700 ft HP steel. 2016 project | 0 | 0 | 675000 | 832747.5 | 0 | 0 | 0 | 0 | 0 | 0 | 675000 | 832747.5
306987 | Burlington Reinforcement at Peterson Road | Mt. Vernon | Replace about 6,500 ft 2 in with larger pipe. 2017 project | 0 | 0 | 0 | 0 | 240000 | 296088 | 0 | 0 | 0 | 0 | 240000 | 296088
FP # | Gate Projects | District | Notes | 2015 Direct Cost | 2015 Loaded Cost | 2016 Direct Cost | 2016 Loaded Cost | 2017 Direct Cost | 2017 Loaded Cost | 2018 Direct Cost | 2018 Loaded Cost | 2019 Direct Cost | 2019 Loaded Cost | Total Direct | Total Loaded
101505 | Arlington Gate Upgrade | Mt. Vernon | Carry over from 2013 | 2000000 | 2467400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 2467400
FP # | Odorizer Projects | District | Notes | 2015 Direct Cost | 2015 Loaded Cost | 2016 Direct Cost | 2016 Loaded Cost | 2017 Direct Cost | 2017 Loaded Cost | 2018 Direct Cost | 2018 Loaded Cost | 2019 Direct Cost | 2019 Loaded Cost | Total Direct | Total Loaded
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0
FP # | Reg Projects | District | Notes | 2015 Direct Cost | 2015 Loaded Cost | 2016 Direct Cost | 2016 Loaded Cost | 2017 Direct Cost | 2017 Loaded Cost | 2018 Direct Cost | 2018 Loaded Cost | 2019 Direct Cost | 2019 Loaded Cost | Total Direct | Total Loaded
FP # | Valve Projects | District | Notes | 2015 Direct Cost | 2015 Loaded Cost | 2016 Direct Cost | 2016 Loaded Cost | 2017 Direct Cost | 2017 Loaded Cost | 2018 Direct Cost | 2018 Loaded Cost | 2019 Direct Cost | 2019 Loaded Cost | Total Direct | Total Loaded
FP # | Bridge/Exposure Projects | District | Notes | 2015 Direct Cost | 2015 Loaded Cost | 2016 Direct Cost | 2016 Loaded Cost | 2017 Direct Cost | 2017 Loaded Cost | 2018 Direct Cost | 2018 Loaded Cost | 2019 Direct Cost | 2019 Loaded Cost | Total Direct | Total Loaded
FP # | Forced Relocations | District | Notes | 2015 Direct Cost | 2015 Loaded Cost | 2016 Direct Cost | 2016 Loaded Cost | 2017 Direct Cost | 2017 Loaded Cost | 2018 Direct Cost | 2018 Loaded Cost | 2019 Direct Cost | 2019 Loaded Cost | Total Direct | Total Loaded
FP # | Other Projects | District | Notes | 2015 Direct Cost | 2015 Loaded Cost | 2016 Direct Cost | 2016 Loaded Cost | 2017 Direct Cost | 2017 Loaded Cost | 2018 Direct Cost | 2018 Loaded Cost | 2019 Direct Cost | 2019 Loaded Cost | Total Direct | Total Loaded
|  |  | TOTAL SPECIFIC FUNDING PROJECTS | 4075000 | 5027327.5 | 4135180 | 5101571.566 | 2285000 | 2819004.5 | 1950000 | 2405715 | 1950000 | 2405715 | 14395180 | 17759333.566