DOCKET NO.  UG-060518

Public Counsel Recommended Timeline – Avista Decoupling Pilot Evaluation

| Date | Activity |
| --- | --- |
| April 30, 2008 | Draft Evaluation Plan Filed with Commission and will include: - Thorough explanation of procedural elements of plan (process for evaluator procurement, plans for distributing RFP, expected qualifications of evaluator) - Draft RFP - Draft MOU re: Stakeholder Advisory Group |
| May 9, 2008 | Comments filed with Commission for any Party not endorsing the draft evaluation plan |
| May 10– 31, 2008 | Draft Plan and any Comments Reviewed by Commission Commission Guidance Re: Evaluation Plan implementation |
| June 16, 2008 | Distribution of RFP (by Commission or Stakeholder Advisory Group) |
| July 15, 2008 | Proposals Due from Potential Evaluators |
| August 6, 2008 | Stakeholder Advisory Group selects top 2-4 candidates to interview |
| August 18-22, 2008 | Stakeholder Advisory Group conducts interviews with candidates |
| September 5, 2008 | Joint Recommendation or Separate Recommendations filed with Commission re: Evaluator Selection |
| September 26, 2008 | Commission Selection of Evaluator |
| February 28, 2009 | All 2008 data provided to Evaluator, including complete DSM verification for 2008 |
| March 31, 2009 (or 30 days from receipt of 2008 data) | Final Evaluation Report filed with Commission |
| April 30, 2009 (or no earlier than 30 days after Final Evaluation Report filed) | Avista deadline to petition to extend or modify the pilot mechanism |
| TBD | Prehearing conference to set schedule for petition docket |
| June 30, 2009 | End of Pilot. Deferrals terminate if review process is not complete. |

ATTACHMENT A