## Slide 1: PSE – WUTC Meeting
December 10, 2010

## Slide 2: Agenda
December 10, 2010
Prior Obligation Update
  Roadmap Review
  Key Deliverables
  Final Scripting
  Prior Obligation Calculation Scenario
  Next Steps
2

## Slide 3
Prior Obligation Roadmap
Identify the Underlying Issues
Refine Processes and Continuously Improve
Document and Improve Pledge Related Processes
Review Prior Obligation process and refine as needed
Review Process of Customers who do not contact immediately after disconnect
Quality Assurance/ Sustainability
Enhance Quality Assurance Process
Quarterly Quality Assurance Self Audit
Quarterly Report of Self Audit (mirror Performance standard)
Internal Training and Communication
Prior Obligation Communications
Frequent Refresher Training
Testing and coaching
Metrics and Reporting
Develop Prior Obligation Scorecard
Develop Method to monitor Pledge application workload
Review Deposit Standard
OCT |  | Nov |  | Dec |  | Jan
3
Completed
On-Going
On-Going
Began 12/3/10
On-Going
On-Going
In Progress
Completed
Completed
Completed
Completed
Denotes change in original timeline.
Completed

## Slide 4: Key Deliverables
4
Process Improvement
Revised Prior Obligation processes.
Training
Trained all agents and Customer Care leadership on new processes.
Curriculum development is in process for training and on-going training.
Quality Assurance
Established Quality Assurance criteria to examine end to end Prior Obligation handling.
Established reporting format for monthly and quarterly QA results.
Established VRU menu option for disconnected customers.
Implemented a specialized team to handle all calls from disconnected customers.
Updated scripting for agents.
Initiated QA reviews on updated processes on 12/3/10.
Focused training for specialized disconnect team.

## Slide 5: Updated Scripting
Scripting was revised through collaborative feedback and testing
Current version of script provides clarity and consistency
Delivery time improved 2-3 minutes from previous versions
5
Let me revi
ew your account and then I can advise you on action
s that are available
to you…
Thank you for holding…
It looks like
this
account was disconnected for:
·
Usage charges (and/or a deposit), for a total disconnect amount of $________
We can:
·
Recon
nect
the service
for the disconnection amount of $____ + a $37
reconnection fee, which totals $_________;
·
If
you are unable (it isn’t possible)
to pay the full disconnect amount, we can
reconnect
your
service
for a new deposit & a reconnection fee, which
appears
to
total $_______;
and
/or but
I
need
to explain a few details to you about this prior
obligation
process
(if total exceeds disconnection amount, quote ½ deposit + reconnect
fee)
·
We will be closing your account and re
-
opening it right away so th
at your
reconnect can be processed as soon as the payment is received.
·
When we do this, it allows
your service
to
be
reconnect
ed
for a deposit
and
a
reconnection fee
·
If you choose to have your service reconnected by paying a new deposit and
reconnect f
ee then this
provides
PSE
the opportunity for us to offer you a payment
plan
on the prior charges
. The charges in the payment arrangement would be for
usage of $XXX and is called prior obligation. What would you be able to pay
each month in addition to you
r current charges? ($XXX)
(Based on customer
response process payment arrangement.)
·
Okay, the
prior obligation arrangement is $XX/month spread out over the next X
months starting with your next bill. Is this ok? (Yes) I’ve noted the arrangement
on your ac
count and you will see this arrangement on your next statement in
addition to the current charges.
·
I
f
you are unable
(
isn’t possible
)
to pay these arrangements on time,
PSE cannot
disconnect
the service
for those charges
of $XXX.XX
included in
the prior
o
bligation
arrangement.
However,
PSE will send the prior obligation balance
owing directly to a collection agency, so it is
very
important to keep this
arrangement.
·
Please
ensure to continue to pay the
current charges to avoid a
possible
disconnect
ion of
service
in the future.

## Slide 6: Prior Obligation Calculation Scenario
6

## Slide 7: Next Steps
Continue work with agencies on pledge process improvement.
Perform Quality Assurance against new process and continue to refine.
Continue to monitor and mitigate all complaint scenarios.
Maintain training curriculum for Pledges and Prior Obligation.
Provide quarterly report beginning April 2011.
7