## Slide 1: Smart Investment Grant Update
May 24, 2011 WUTC Update
Smart Circuit Project – Spokane, WA

## Slide 2: Overview
Substation Construction
6 Substations Complete
Distribution Construction
Smart Switches & Capacitors being Installed
Reporting
Project Performance
Build Metrics
Impact Metrics
4 Stations 100% Complete with Overhead Construction
Project Funding
$42MM Total
$22MM Avista
$20MM DOE
2011 Budget Summary
Actual YTD Spend through March 2011 - $22MM
DOE Reimbursement through March 2011 - $10MM
2
Notes: To date we have completed 24 miles of reconductor with 6.5 left. (Numbers are rough as I have not updated from completions last week.)
We have installed 219 devices with 159 left to install.
33 Vipers installed with 54 left to install
124 ScadaMates installed with 46 left to install
62 Switched banks installed with 59 left to install
4 stations are 100% complete with OH construction. North East, Lyons and Standard, Francis and Cedar, and Fort Wright.

## Slide 3: Substation Construction
Construction Complete
Construction Almost Complete
Construction In Progress
Beacon
Francis & Cedar
Ross Park
Fort Wright
Lyons & Standard
College & Walnut
Northeast
Northwest
Ready for Construction
Post Street
Prints to Transmit June 30th
Third and Hatch
Glenrose
Planning
Southeast
Ninth and Central
Sunset
3

## Slide 4: Distribution Construction
Chart: 
| Reconductor | Switches | Capacitors
Installed | 21.68 | 156 | 62
To Install | 8.56 | 101 | 59
4
Notes: 4 stations are 100% complete with OH construction. North East, Lyons and Standard, Francis and Cedar, and Fort Wright.
-initially planned on installing 59 vipers and scadamates on the rest, but decided to install 87 vipers and reduce scadamates because we learned they were less expensive to install and provided more functionality

## Slide 5
Reporting Requirements
Monthly:
  Monthly Spend
  Project Performance
Quarterly:
  Federal Reporting
  Build Metrics
5

## Slide 6
Project Performance
6

## Slide 7
Chart: 
Build & Impact Metrics
How did the system operate differently?
7
DEVICE

## Slide 8: Smart Grid Update
May 24, 2011 WUTC Update
Smart Grid Demonstration Project – Pullman, WA
8

## Slide 9: Smart Grid Demonstration Project Overview
Communications
Radio Network Complete
Bidding Port of Whitman Fiber Construction Documents
Distribution Management System
Designing Integration into Outage Management Tool
Substation Construction
Reconstructed Pullman Substation Site Finalized
Distribution Construction
Smart Switches & Capacitors being Installed
Smart Transformer Prototypes Scheduled to Deliver in May
75% of 1.6Mile Reconductor Complete
Advanced Metering Infrastructure
Meter Installation 87% Complete
Project Funding
$38MM Total
$15MM Avista
$4MM Partners
$19MM DOE
2011 Budget Summary
Actual YTD Spend through April 2011 - $9.7MM
DOE Reimbursement through March 2011 - $1.6MM
9

## Slide 10: Substation Construction Progress
Pullman Temporary Substation (PTS)
  Grading Complete
  Fencing and Foundation Work Underway
  Grounding Work Began May 11th
New Turner Substation (Replacing Pullman Substation)
  Distribution Poles Removed in Preparation for Grading
  Grading Began May 9th
10
Notes: Help with Spacing and title format

## Slide 11
Advanced Meter Infrastructure Installation
11
  Scope Services Contract Installer
  May 2011 Completion On Schedule
OpenWay Meter Install Statics |  |  | 
Item | Albion | Pullman | Totals
Gas Completed | 197 | 4,596 | 4,793
Electric Completed | 340 | 11,541 | 11,881
Total Completed | 537 | 16,137 | 16,674
Gas Remaining | 0 | 511 | 511
Electric Remaining | 0 | 811 | 811
Total Remaining | 0 | 1,322 | 1,322
Job Total Sent To Scope | 537 | 17,459 | 17,996
Percentage Complete | 92.65% |  | 

## Slide 12: Common Questions being asked by Customers in Pullman
Will my landscaping be disrupted during the meter work?
I have tropical turtles that are kept heated, how long will the power be out?
I have multiple properties, how will the tenants be notified?
Do I really need to be home for the new meter?
My clock on the stove/oven doesn’t work anymore….
Can you tell me more about the Electro Magnetic Field issues with the meter?
12

## Slide 13: Avista Electrical Distribution Dispatch Training
  Device Installation and Field Commissioning
  Simulation Testing with Test Cases to Prove Functionality
  Fault Detection Isolation Restoration Running in Supervised Mode
  Operate the System in Automatic Mode as the Final Outcome
Schedule
Roles & Responsibilities
Certification Requirements
Training Modules
13
Notes: As the Distribution Management System Software is implemented, Distribution Dispatch will require training.

## Slide 14: Customer Experience Update
May 24, 2011 WUTC Update
Smart Grid Demonstration Project – Pullman, WA
14

## Slide 15: Battelle Requirements
15

## Slide 16: The Demonstration Project - Customer Experience
Web-Portal
  Display interval energy usage data
  Energy Management Tools
Demand Response/Home Area Network
  Respond to Battelle’s Transactive Signal
  Home-Area-Network
16

## Slide 17: Web Portal Process
Progress to Date
  Business Requirements Defined
  Use Cases Developed
  Issued Request For Proposal
  Evaluated and Selected Vendor
In Progress
  Integration
  Additional Design – Mobile Applications & Behavior Study
  Determining Tracking Requirements
17
My Smart Meter

## Slide 18: Customer Experience and Web Portal
  Define Customer Experience-
    Access to Data and Energy Tools
  Web Portal
    Sept 2011
  Vendor Selection
    Aclara
    Contract Negotiations Underway
You may be able to improve your score by telling us a bit more about your home.
Draft
For Illustrative Purposes Only
18
Notes: Title and bullet format

## Slide 19
Web Portal + Demand Response + Full Analytics
19

## Slide 20: Customer Communications Update
May 24, 2011 WUTC Update
Smart Grid Demonstration Project – Pullman, WA
Smart Circuit Project – Spokane, WA
20

## Slide 21: Key Communication Tactics - Pullman
  Open House – January
    Provide customers and Pullman community status update on project
  Pre-Installation Notification Letter to Customers -February
  Successful or Unsuccessful installation door hangers left following meter replacement (March/April/May)
  Numerous speaking engagements in the Pullman community (Ongoing)
  Last Meter Installation Event (late May)
  Customer Meeting June 2 in Pullman and Spokane (grid modernization is one of topics)
  Conduct post installation survey to measure the following: (Early June)
    Awareness of communication received
    Awareness of new meter installed
    Satisfaction with meter installation
  Web Portal Introduction and Outreach (Fall)
  Enhance advanced grid content on avistautilities.com (ongoing)
  Demand Response Pilot – Participant Recruitment slated for Q1 2012
21

## Slide 22: Key 2011 Communications Tactics – All Avista Customers
Customer Meetings featuring grid modernization education and project updates (June 2 & 3 in Pullman and Spokane)
Feature stories on Avista’s smart grid projects in the monthly customer newsletter
Content on smart grid projects on avistautilities.com
Various Public speaking engagements
22

## Slide 23: Cyber Security Overview
23
May 24, 2011 WUTC Update
Smart Grid Demonstration Project – Pullman, WA
Smart Circuit Project – Spokane, WA

## Slide 24: Smart Grid Security Goals
Goals
  Identify Risk from new investments and capabilities
  Measure Risk for impact and probability
  Manage Risk as appropriate to the organization and its customers
  Apply Best Practice Controls per industry baselines
24

## Slide 25: Security Risk Management Lifecycle
Categorize
Systems
Select
Controls
Implement
Controls
Assess
Controls
Authorize
Systems
Continuous Monitoring
Complete
Complete
In Progress
25

## Slide 26: High Risk Mandatory Action Areas
Security Governance
Security Policy
Risk Management
Security Program
Identity & Access Management
Configuration Management
Incident Management
Vulnerability Management
Phase 3 - Implement Controls
Security Event Management
26

## Slide 27: Questions………..
27