## 2010-11 Eval Plan Detail
2010 - 2011 Evaluation Projects Plan Rev 10-27-10
Customer Sector | Project Name | Schedule | Study Type | Lead Analyst | Program Manager | Contractor (3rd Party) | Estimated Contract Cost (ELECTRIC) | Estimated Contract Cost (GAS) | Complt Date | Status | Notes | Lists
Pilots
Res | Home Energy Reports - 12 Month PSE Evaluation | E249/G249 | Impact | Wilhelm | Simcox | NA | 0 | 0 | 2010-04-30 | Complete | First year energy savings confirmed | Study Type | Status
C&I | Commercial Demand Response1 | E249A | Impact & Process | Brateng | McCormick | Navigant | 87250 | 0 | 2010-09-30 | Complete | Draft report under review | Impact & Process | Pending
Res | Home Energy Reports - 18 Month 3rd Party Evaluation | E249/G249 | Persistence & Impact | Wilhelm | Simcox | KEMA | 61152 | 26208 | 2010-10-31 | In Progress | Analysis Underway | Persistence & Impact | Ongoing
Res | Residential Demand Response1 | E249 | Impact & Process | Brateng | Chamberlain | TBD | 90000 | 0 | 2011-09-30 | In Progress | Examining interval data for potential use in impact evalaution. | Process | Complete
Res | Ductless Heat Pumps | E249 | Impact & Process | Feinstein | Rominger | Ecotope | (NEEA) | 0 | 2011-11-01 | In Progress | Project Underway: Meter data collected; Lab testing completed; Surveys underway | Impact | Annual
Res, C&I | Other Pilots / Contingency | E249/G249 | Impact & Process | Various | Various | TBD | 110000 |  | 2011-12-30 | Pending | Emphasis on Process
Existing Programs & Measures
C&I | VFD Market Assessment Study | E250 | Process | Feinstein | Dickson | Summit Blue | 16757 | 0 | 2010-03-26 | Complete | Contract costs split between current and prior biennium.
Res | Project Porchlight Follow-up | E214 | Impact | Wilhelm | Simcox | Innovative Research | 4250 | 0 | 2010-05-10 | Complete | Energy savings confirmed
Res | Gas Water Heaters | G214 | Impact | Wilhelm | Rominger | KEMA |  | 37068.88 | 2010-06-30 | Complete | Final report to be completed this month
C&I | Commercial Sprayhead Metering | E262/G262 | Impact | Wilhelm | Dickson | SBW | 44800 | 0 | 2010-12-01 | In Progress
C&I | PC Power Management (Software) | E250 | Impact | Feinstein | Dickson | Cadmus | 170000 | 0 | 2011-01-31 | In Progress | NEEA is leading separate Process Eval of same measure.
Res | MF Weatherization - Retrofit | E217/G217 | Impact & Process | Wilhelm | Forde | SBW | 107086 | 45984 | 2011-03-01 | In Progress | Analysis Underway
Res | Residential Duct Sealing | E214/G215 | Impact & Process | Wilhelm | Taylor | Navigant | 67855.9 | 126018.1 | 2011-07-31 | In Progress | Field Collection Started
C&I | C&I Retrofit | E250/G205 | Impact & Process | Feinstein | Landers | TBD | 300000 | 100000 | 2011-12-30 | Pending | Emphasis on lighting, refrigeration, boilers and HVAC
C&I | Large Power/Self Directed | E258 | Impact & Process | Feinstein | Montgomery | TBD | 150000 | 0 | 2011-12-30 | Pending | Emphasis on lighting and process measures
C&I | LED Traffic Lights | E257 | Impact & Process | Feinstein | Schmutzler | TBD | 20000 | 0 | 2011-12-30 | Pending | Emphasis on market penetration
Res | Low Income Program | E201/G203 | Impact & Process | Wilhelm | Sieg | TBD | 300000 | 100000 | 2011-12-30 | Pending | Emphasis on Impact and Process
Res, C&I | Regional Technical Forum (RTF) | All | Impact | Brateng | Various | Various | 260000 |  | 2011-12-11 | Annual | 2011 RTF Funding Support Allocation
Res, C&I | Independent 3rd-Party 2010-2011 Portfolio Review; K. 6 (g) | All | Impact & Process | Hopkins | Various | TBD | 250000 |  | 2012-06-30 | Pending | I-937 Conditions Agreement K. 6 (g)
Totals: | [6 empty] | 2039150.9 | 435278.98
| 1 - Demand Response Pilot Evaluation costs, total |  | 177250 | budgeted and tracked in DR cost accounting, are shown in this total, but not included in Evaluation budget.

## 2011 Eval Plan Detail
2011 Evaluation Plan / Summary - Annual Conservation Plan Rev 10-27-2010
Cust. Sector | Schedule | Project Name | Study Type | Lead Analyst | Program Manager | Contractor (3rd Party) | Estimated Contract $ (ELECTRIC) | Estimated Contract $ (GAS) | Start Date | Estimated Completion Date | Status | Notes
Res | E249a | Residential Demand Response1 | Impact & Process | Brateng | Chamberlain | TBD | 90000 | 0 |  | 2011-09-30 | In Progress | Examining interval data for potential use in impact evalaution.
Res | E249 | Ductless Heat Pumps | Impact & Process | Feinstein | Rominger | Ecotope / NEEA | (NEEA) | 0 |  | 2011-11-01 | In Progress | Project Underway: Meter data collected; Lab testing completed; Surveys underway
C&I | E250 | PC Power Management (Software) | Impact | Feinstein | Dickson | Cadmus | 10000 | 0 | 2010-07-31 | 2011-01-31 | In Progress | NEEA is leading separate Process Eval of same measure.
Res | E217/G217 | MF Weatherization | Impact & Process | Wilhelm | Forde | SBW | 96726 | 41454 | 2010-05-30 | 2011-03-01 | In Progress | Analysis underway
Res | E214/G215 | Residential Duct Sealing | Impact & Process | Wilhelm | McCulloch | Navigant | 45238 | 84012 | 2010-06-30 | 2011-07-31 | In Progress | Field Collection underway
C&I | E250/G205 | C&I Retrofit | Impact & Process | Feinstein | Landers | TBD | 300000 | 100000 | 2011-01-30 | 2011-12-30 | Pending | Emphasis on lighting, refrigeration, boilers and HVAC
C&I | E258 | Large Power/Self Directed | Impact & Process | Feinstein | Montgomery | TBD | 150000 | 0 | 2011-01-30 | 2011-12-30 | Pending | Emphasis on lighting and process measures
C&I | E257 | LED Traffic Lights | Impact & Process | Feinstein | Schmutzler | TBD | 20000 | 0 | 2011-01-30 | 2011-12-30 | Pending | Emphasis on market penetration
Res | E201/G203 | Low Income Programs | Impact & Process | Wilhelm | Sieg | TBD | 300000 | 100000 | 2011-01-30 | 2011-12-30 | Pending | Emphasis on Impact and Process
Res, C&I | E249/G249 | Pilots / Contingency | Impact & Process | Various | Various | TBD | 110000 |  | 2011-01-30 | 2011-12-30 | Pending | Emphasis on Process
Res, C&I | All | Regional Technical Forum (RTF) | Impact | Brateng | Various | Various | 260000 |  |  | 2011-12-11 | Annual | 2011 RTF Funding Support Allocation
Res, C&I | All | Independent 3rd-Party 2010-2011 3rd-Party Portfolio Review; K.6(g) | Impact & Process | Hopkins | Various | TBD | 250000 |  | 2010-11-01 | 2012-06-30 | Pending | I-937 Conditions Agreement K. 6 (g)
Totals: | [6 empty] | 1631964 | 325466
|  | 1 - Residential DRP Evaluation cost of |  | 90000 | shows in this total, but is budgeted and tracked separately in DRP order # for Tariff 249a

## ACP Past Evals; 8-06 to 3-10
PSE Past Evaluation Projects; August, 2006 thru March, 2010
Project Name | Fuel Type | Study Type | PSE Lead Analyst | Analyst (PSE) or Contractor (3rd Party) | Completion Date | Partners & Regional Interest Notes
VFD Market in PSE Service Territory | E | Market Assessment | Feinstein | Navigant (3rd Party) | 2010-03-01
Premium Service HVAC Impact Evaluation | E | Impact & Process | Feinstein | Feinstein (PSE) | 2010-01-14
Rock the Bulb Awareness Study | E | Participant Survey | Haechrel | Haechrel (PSE) | 2010-01-08
2008 Low-Flow Showerhead Installation Rate Survey | EG | Participant Survey | Wilhelm | McCallum Print Group (3rd Party) | 2009-10-20 | Joint Study: PSE, SCL, SPU, and CWA
Understanding Barriers to Residential Customer Adoption of Energy Efficiency Programs | EG | Market Assessment | Nusser | Definitive Insights (3rd Party) | 2009-10-09
Commercial New Construction Measure Cost Assessment | EG | Measure Cost Assessment | Wilhelm | Summit Blue (3rd Party) | 2009-09-25 | Joint Study: PSE, SCL
Mid Year OPower Billing Analysis | EG | Impact/Persistence | Wilhelm | Wilhelm (PSE) | 2009-09-02
Field Evaluation of an Updated Duct Sealing Protocol | EG | Impact | Wilhelm | Delta T & Ecotope (3rd Party) | 2009-09-01
Characterization and Energy Efficiency Opportunities in Vending Machines for the Pacific Northwest-Phase II | E | Market Assessment | Brateng / NEEA | NEEA / Cadmus (3rd Party) | 2009-04-17 | Regional study managed by NEEA
Gas Boiler Tune-up Evaluation | G | Impact & Process | Feinstein | Feinstein (PSE) | 2009-03-20
CFL Energy Savings Adjustment | E | Impact | Wilhelm | Wilhelm & Brateng (PSE) | 2009-02-05 | Led to regional change in Retail CFL deemed savings from 33 to 24 kWh/yr
Residential Measure Cost Assessment | EG | Measure Cost Assessment | Wilhelm | Summit Blue (3rd Party)
Resource Conservation Manager Impact Study | EG | Impact & Process | Feinstein | Feinstein (PSE) | 2008-11-14
Residential Energy Efficient Furnace Program Impact Evaluation | G | Impact | Wilhelm | Kema (3rd Party) | 2008-11-05
Residential Weatherization Study | EG | SEEM Modeling | Wilhelm | Ecotope (3rd Party) | 2008-10-15
LIW Duct Insulation Savings | EG | Savings Calulation Review | Feinstein | Feinstein (PSE) | 2008-06-17
LIW Door Sweeps and Weatherstripping | EG | Savings Calulation Review | Feinstein | Feinstein (PSE) | 2008-06-04
Clothes Washer Savings Alignment | EG | Savings Calulation Review | Wilhelm | Wilhelm (PSE) | 2008-06-03
CFL Saturation Study | E | Impact, Saturation | Brateng | EMI (3rd Party) | 2007-11-20 | Joint Study: PSE, SCL, SnoPUD; Contributed to regional change in Retail CFL deemed savings from 33 to 24 kWh/yr
Commercial & Industrial Lighting Savings Verification Study | E | Impact | Brateng | RLW Analytics (3rd Party) | 2007-07-20
Compressor Savings Verification | E | Impact | Wilhelm | Wilhelm (PSE) | 2006-08-23

## CRAG PPT Slide - 2011 Eval Plan
2011 Evaluation Plan / Summary - Annual Conservation Plan 11-4-2010
Project Name | Fuel Type | Study Type | Contractor (3rd-Party) | Estimated Contract $ (ELECTRIC) | Estimated Contract $ (GAS) | Estimated Completion Date
PC Power Management (Software) | E | Impact | Cadmus | 10000 | 0 | 2011-01-31
Multi-Family Retrofit | E & G | Impact & Process | SBW | 97000 | 41000 | 2011-03-01
Residential Duct Sealing | E & G | Impact & Process | Navigant | 45000 | 84000 | 2011-07-31
Residential Demand Response1 | E | Impact & Process | TBD | 90000 | 0 | 2011-09-30
Ductless Heat Pumps | E | Impact & Process | Ecotope | (NEEA) | 0 | 2011-11-01
C&I Retrofit | E & G | Impact & Process | TBD | 300000 | 100000 | 2011-12-30
Large Power/Self Directed | E | Impact & Process | TBD | 150000 | 0 | 2011-12-30
LED Traffic Lights | E | Impact & Process | TBD | 20000 | 0 | 2011-12-30
Low Income Programs | E & G | Impact & Process | TBD | 300000 | 100000 | 2011-12-30
Pilots / Contingency | E & G | Impact & Process | TBD | 110000 |  | 2011-12-30
Regional Technical Forum (RTF) | E | Impact | Various | 260000 |  | 2011-12-30
Independent 3rd-Party 2010 - 2011 Portfolio Review; K.6 (g) | E | Impact & Process | TBD | 250000 |  | 2012-06-30
|  |  | Totals: | 1632000 | 325000
1 - Estimated DRP Evaluation cost | 90000 | is budgeted and tracked separately with Residential DRP program costs

## 2010-11 Elec Eval Proj Detail
2010 - 2011 Electric Evaluation Project Details Rev 11-17-10 per 11-4-2010 CRAG Mtg
Customer Sector | Project Name | Schedule | 20091 Program Savings (kWh) | % of Total 2009 Program Savings | 2009 Program Expenditures | Percent of Overall 2009 Electric Budget | Study Type | Lead Analyst | Program Manager | Contractor (3rd Party) | Est Contractor Cost | Est PSE Analyst Cost | Est Total Cost5 | Complt Date | Status | Notes | Lists
69742000
Pilots
Res | Home Energy Reports - 12 Month PSE Evaluation | E249 | N/A | N/A | 109798 | 0.1574% | Impact | Wilhelm | Simcox | NA | 0 | 4400 | 4400 | 2010-04-30 | Complete | First year energy savings confirmed | Study Type | Status
C&I | Commercial Demand Response4 | E249A | N/A | N/A | 407953 | 0.5849% | Impact & Process | Brateng | McCormick | Navigant | 87250 | 2585 | 89835 | 2010-09-30 | Complete | Draft report under review | Impact & Process | Pending
Res | Home Energy Reports - 18 Month 3rd Party Evaluation | E249 | N/A | N/A | same as HER/12 mo. (in 2009) |  | Persistence & Impact | Wilhelm | Simcox | KEMA | 61152 | 1100 | 62252 | 2010-10-31 | Complete | Analysis Underway | Persistence & Impact | Annual
Res | Residential Demand Response4 | E249 | N/A | N/A | 933413 | 1.338% | Impact & Process | Brateng | Chamberlain | TBD | 90000 | 2695 | 92695 | 2011-09-30 | In Progress | Examining interval data for potential use in impact evalaution. | Process | Complete
Res | Ductless Heat Pumps | E249 | 1389500 | 0.49% | 765991 | 1.098% | Impact & Process | Feinstein | Rominger | Ecotope | (NEEA) | 1000 | 1000 | 2011-11-01 | In Progress | Project Underway: Meter data collected; Lab testing completed; Surveys underway | Impact
Res, C&I | Other Pilots / Contingency | E249 | N/A | N/A | 1990869 | 2.855% | Impact & Process | Various | Various | TBD | 110000 | 0 | 110000 | 2011-12-30 | Pending | Emphasis on Process
Existing Programs & Measures
C&I | VFD Market Assessment Study | E250 | 1041678 | 0.3674% | VFD not a specific budget item; P/O CI Retro |  | Process | Feinstein | Dickson | Summit Blue | 16757 | 18000 | 34757 | 2010-03-26 | Complete | Contract costs split between current and prior biennium.
Res | Project Porchlight Follow-up | E214 | 4300000 | 1.516% | 2211276 | 3.171% | Impact | Wilhelm | Simcox | Innovative Research | 4250 | 2200 | 6450 | 2010-05-10 | Complete | Energy savings confirmed
C&I | Commercial Sprayhead Metering | E262 | 6055000 | 2.135% | 174488 | 0.2502% | Impact | Wilhelm | Dickson | SBW | 44800 | 4400 | 49200 | 2010-12-01 | In Progress
C&I | PC Power Management (Software) | E250 | 3700000 | 1.305% | 1488970 | 2.135% | Impact | Feinstein | Dickson | Cadmus | 170000 | 5500 | 175500 | 2011-01-31 | In Progress | NEEA is leading separate Process Eval of same measure.
Res | MF Weatherization - Retrofit | E217 | 4193000 | 1.479% | 2700000 | 3.871% | Impact & Process | Wilhelm | Forde | SBW | 107086 | 7700 | 114786 | 2011-03-01 | In Progress | Analysis Underway
Res | Residential Duct Sealing | E214 | 17580 | 0.0062% | 10000 | 0.01434% | Impact & Process | Wilhelm | Taylor | Navigant | 67855.9 | 11550 | 79405.9 | 2011-07-31 | In Progress | Field Collection Started
C&I | C&I Retrofit | E250 | 51700000 | 18.23% | 16817001 | 24.11% | Impact & Process | Feinstein | Landers | TBD | 300000 | 30000 | 330000 | 2011-12-30 | Pending | Emphasis on lighting, refrigeration, boilers and HVAC
C&I | Large Power/Self Directed | E258 | 16240000 | 5.727% | 3192731 | 4.578% | Impact & Process | Feinstein | Montgomery | TBD | 150000 | 14000 | 164000 | 2011-12-30 | Pending | Emphasis on lighting and process measures
C&I | LED Traffic Lights | E257 | 590000 | 0.2081% | 19057 | 0.02732% | Impact & Process | Feinstein | Schmutzler | TBD | 20000 | 1000 | 21000 | 2011-12-30 | Pending | Emphasis on market penetration
Res | Low Income Program | E201 | 1890000 | 0.6665% | 2143410 | 3.073% | Impact & Process | Wilhelm | Sieg | TBD | 300000 | 11550 | 311550 | 2011-12-30 | Pending | Emphasis on Impact and Process
Res, C&I | Regional Technical Forum (RTF) | All | N/A | N/A | 250000 | 0.3585% | Impact | Brateng | Various | Various | 260000 | 6050 | 266050 |  | Annual | 2011 RTF Funding Support Allocation
Res, C&I | 2010-11 3rd Party Portfolio Review (Jan - Aug 2010 kWh Savings2) | All | 189280000 | N/A |  |  | Impact & Process | Hopkins | Various | TBD | 250000 |  | 250000 | 2012-06-30 | Pending | I-937 Conditions Agreement K. 6 (g)
| Total 2009 Electric Savings, all Programs3: |  | 283560000 | [6 empty] | Totals: | 2039150.9 | 123730 | 2162880.9
1 2009 savings figures were used for consistency with our normal selection/prioritization process, as well as reflecting a full year of data.
2 January through August 2010 savings included for reference only.
3 neither of the Program Savings totals at the bottom reflect the column total above since the evaluation study line items reflect only a portion of the full portfolio
4 Demand Response Pilot Evaluation costs, totaling $177,250, budgeted and tracked in DR cost accounting, are shown in this total, but not included in Evaluation budget.
5 Although some evaluation projects are scheduled to be completed in 2011, the costs may be spread between 2010 and 2011.
Note on F10: Andy Hemstreet: Cool School Challenge: $144,872 Ecos Home Energy Audit: $1,514,663 Home Energy Analyzer: $13,914 In-home Display: $150,259 SF Prescr. Duct Sealing: $152,039 HomePrint: $15,121
Note on F13: Andy Hemstreet: The entire residential retail lighting expenditure: $11,751,982.
Note on F14: Andy Hemstreet: Total C/I electric sprayhead expenditures
Note on F15: Andy Hemstreet: Total C/I rebates expenditures, less: Spray heads--$187,197
Note on F16: Andy Hemstreet: This is an estimate of shell insulation and windows. MFE total 2009 expenditures were $4.97 million. Much of that was CFL and other deemed measures.
Note on F17: Andy Hemstreet: An estimate, based on approximately 10 duct sealing jobs. Total electric weatherization expenditures of $664,840

## 2010-11 Gas Eval Proj Detail
2010 - 2011 Gas Evaluation Project Details Rev 11-17-10 per 11-4-2010 CRAG Mtg
Customer Sector | Project Name | Schedule | 20091 Program Savings (Therms) | % of Total 2009 Program Savings | 2009 Program Expenditures | Percent of Overall 2009 Gas Budget | Study Type | Lead Analyst | Program Manager | Contractor (3rd Party) | Est Contractor Cost | Est PSE Analyst Cost | Est Total Cost3 | Complt Date | Status | Notes | Lists
16353000
Pilots
Res | Home Energy Reports - 12 Month PSE Evaluation | G249 | N/A | N/A | 47556 | 0.2908% | Impact | Wilhelm | Simcox | NA | 0 | 4400 | 4400 | 2010-04-30 | Complete | First year energy savings confirmed | Study Type | Status
Res | Home Energy Reports - 18 Month 3rd Party Evaluation | G249 | N/A | N/A | same as HER/12 mo. (in 2009) |  | Persistence & Impact | Wilhelm | Simcox | KEMA | 26208 | 1100 | 27308 | 2010-10-31 | Complete | Results showed persistence consistent with 12-month study | Persistence & Impact
Res, C&I | Other Pilots / Contingency | G249 | N/A | N/A | 1031577 | 6.308% | Impact & Process | Various | Various | TBD |  | 0 | 0 | 2011-12-30 | Pending | Emphasis on Process
Existing Programs & Measures
Res | Gas Water Heaters | G214 | 70200 | 1.369% | 238852 | 1.461% | Impact | Wilhelm | Rominger | KEMA | 37068.88 | 2200 | 39268.88 | 2010-06-30 | Complete
C&I | Commercial Sprayhead Metering | G262 | 1756000 | 34.25% | 187942 | 1.149% | Impact | Wilhelm | Dickson | SBW | 0 | 2200 | 2200 | 2010-12-01 | In Progress
Res | MF Weatherization - Retrofit | G217 | 24350 | 0.4749% | 150000 | 0.9173% | Impact & Process | Wilhelm | Forde | SBW | 45984 | 3300 | 49284 | 2011-03-01 | In Progress | Analysis Underway
Res | Residential Duct Sealing | G215 | 7030 | 0.1371% | 40000 | 0.2446% | Impact & Process | Wilhelm | Taylor | Navigant | 126018.1 | 4950 | 130968.1 | 2011-07-31 | In Progress | Field Collection Started
C&I | C&I Retrofit | G205 | 602000 | 11.74% | 3425815 | 20.95% | Impact & Process | Feinstein | Landers | TBD | 100000 | 10000 | 110000 | 2011-12-30 | Pending | Emphasis on boiler and process measures
Res | Low Income Program | G203 | 25000 | 0.4876% | 530272 | 3.243% | Impact & Process | Wilhelm | Sieg | TBD | 100000 | 4950 | 104950 | 2011-12-30 | Pending | Emphasis on Impact and Process
Res, C&I | Total 2009 Gas Savings, all Programs2: |  | 5127546 | [6 empty] | Totals: | 435278.98 | 33100 | 468378.98
1 2009 savings figures were used for consistency with our normal selection/prioritization process, as well as reflecting a full year of data.
2 neither of the Program Savings totals at the bottom reflect the column total above since the evaluation study line items reflect only a portion of the full portfolio
3 Although some evaluation projects are scheduled to be completed in 2011, the costs may be spread between 2010 and 2011.
Note on F7: Andy Hemstreet: Cool School Challenge: $66,230 SF Prescr Duct Seal'g: $741,315 Ecos Home Energy Aud: $219,860 HomePrint: $5,173
Note on F11: Andy Hemstreet: This is an approximation of shell insulation and window measures. Total expenditures of $333,493 also included other deemed measures.
Note on F12: Andy Hemstreet: An approximate figure, based on 109 duct sealing jobs. Total gas weatherization expenditures of $2.409 million included shell insulation.