## 2021_Proposed Colstrip Outage
Colstrip Units 3&4 |  |  |  | Colstrip Approved 2021 Capital Items | [5 empty] | Rev: 2/4/21
2021 Proposed Capital - DRAFT
Avista
[5 empty] | (000's) |  | 15%
Location | Status | Project ID | Index | DESCRIPTION | Total | Note | Avista share | O&M or Capital | Avista Capital (Adjusted O&M) | Estimated Date in Service
|  | TBD | 1 | Auxiliary Turbine Overhaul | 128 |  | 19.2 |  | 19.2 | 2021-06-01
|  | 10026978 | 32 | Boiler Economizer Tube Replacement | 0 | High | 0 |  | 0
|  | 10026975 | 28 | Boiler Water Wall Replacement/Maintenance | 647 | High | 97.05 |  | 97.05 | 2021-06-01
|  | 10026962 | 18 | Boiler Coutant Bottom-3 | 641 | Medium | 96.15 |  | 96.15 | 2021-06-01
| Must Do | TBD | 59 | Capital Project Support | 1998 | N/A | 299.7 |  | 299.7 | 2021-06-01
Turbine | Partially Approved | 10026949 | 4 | Turbine/Generator Base Overhaul (Partially Approved) - Unit 3 | 4677 | Medium | 701.55 | 60/40 | 280.62 | 2021-06-01
|  | TBD | 6 | LP Turbine Overhaul * | 1868 | Medium | 280.2 | 60/40 | 112.08 | 2021-06-01
|  | TBD | 7 | Generator Inspection/Repair * | 1728 | Medium | 259.2 | O&M | 0 | 2021-06-01
Boiler | Approved | 10026972 | 26 | Air Preheater Basket Replacement | 2122 | High | 318.3 |  | 318.3 | 2021-06-01
|  | 10026967 | 21 | Boiler Bucket Burner and Aux Air Replacement * | 2350 | High | 352.5 |  | 352.5 | 2021-06-01
|  | 10026968 | 22 | Hot Air Gate Replacement-3 | 1100 | Medium | 165 |  | 165 | 2021-06-01
|  | 10026976 | 29 | Separate Over Fire Air Bucket Replacement-3 * | 376 |  | 56.4 |  | 56.4 | 2021-06-01
|  | 10026977 | 30 | Top Over Fire Air (TOFA)Bucket Replacement-3 * | 268 |  | 40.2 |  | 40.2 | 2021-06-01
|  | TBD | 15 | Burner Management System Replacement-BMS | 155 |  | 23.25 |  | 23.25 | 2021-06-01
| Recommended | TBD | 19 | Boiler Capital Scaffolding * | 938 | N/A | 140.7 | O&M | 0 | 2021-06-01
|  | TBD | 31 | Air Preheater Seal Replacement | 515 | High | 77.25 |  | 77.25 | 2021-06-01
| Must Do | TBD | 36 | Cooling Tower Fill * | 3500 | Medium | 525 |  | 525 | 2021-06-01
|  | TBD | 42 | Cathodic Protection - River Station/Pipe Lines | 32.7818 |  | 4.9173 |  | 4.9173 | 2021-06-01
|  | TBD | 21 | Scrubber 3-7 Mist Eliminator replacement | 550 | Medium | 82.5 |  | 82.5 | 2021-06-01
|  | TBD | 52 | Scrubber Lime Slaker Replacement | 337 |  | 50.55 |  | 50.55 | 2021-06-01
Other | Approved | 10027099 | 13 | 4-5 Feedwater Heater Replacement | 1800 | High | 270 |  | 270 | 2021-06-01
|  | 10026598 | 17 | Aux Transformer-3 | 250 |  | 37.5 |  | 37.5 | 2021-06-01
|  | TBD | 10 | DCS PC/Communication Replacement | 530 | High | 79.5 |  | 79.5 | 2021-06-01
|  | TBD | 3 | Boiler Feed Pump Rebuild-3 | 414 |  | 62.1 |  | 62.1 | 2021-06-01
|  | TBD | 2 | Boiler Feed Booster Pump Rebuild-3 | 334 |  | 50.1 |  | 50.1 | 2021-06-01
|  | TBD | 11 | PLC to DCS retrofits | 275 |  | 41.25 |  | 41.25 | 2021-06-01
|  | TBD | 9 | Condenser Expansion Joint Replacement | 180 |  | 27 |  | 27 | 2021-06-01
|  |  | 41 | Fire Pump Addition | 250 |  | 37.5 |  | 37.5 | 2021-03-01
|  |  | 49 | Design/Build Dry Waste Disposal System | 37900 |  |  |  |  | 2022-07-01
|  |  |  | Building Steel | 3500
|  |  |  | Conveyor/Chutes/Hopper Steel | 500
|  |  |  | Amount Approved | 4000 |  | 600 |  | 600
|  |  |  | Total | 31963.7818 |  | 4794.5673 |  | 3805.6173
See Staff-DR-107 - 3.19 Attachment B
|  |  |  | 2022 Addition | 33900 |  | 5085 | WA Share / Moved to 7/1/2022
See Staff-DR-107 - 3.19 Attachment B

## Sheet1
Sum of Avista Capital (Adjusted O&M)
Estimated Date in Service | Total
2021-03-01 | 37.5
2021-06-01 | 3168.1173
(blank) | 0
Grand Total | 3205.6173