## MCP-6 - 2020 Plant Additions
Cascade Natural Gas
Proposed Plant Additions
12 Months ended December 31, 2019
NOTE: Projects with note code 27 or 28 (column 'H') are blanket projects that keep accruing costs and close to 'Plant in Service' every month; Cascade is reflecting the current balance in the Funding Project as of 9/30/2020. In addition, these projects are on pace to be more than Cascade originally filed for by yearend.
| (A) | (B) | (C) | (D) | ( E ) | (F)=(D)*( E ) | (G) | (H) | (I) |  | Filed
Line No. | Function | Funding Project - Description | Account No. | 2020 Total Company's Plant | WA Alloc | WA | Proposed Adjustment as of 9/30/20 | Notes | Estimated In-Service Date |  | Proposed Adjustment as of 12/31/20 | Estimated In-Service Date | Proposed Adjustment Difference to be Installed in the next 3 mo.
1 | Gas Intangible | FP-101480 UG Implement Maximo Ph 1 CNG Direct | 303 | 205921.33 |  | 205921.33 |  |  | 2020-12-31 |  |  | 2020-12-31 | 0
2 | Gas Intangible | FP-200663 UG-GIS Enhancements CNGC | 303 | 87032.79 | 75.17% | 65422.5482 |  |  | 2020-12-01 |  |  | 2020-12-01 | 0 | 66105637.285 | Filed
3 | Gas Intangible | FP-302596 WALLULA GATE; GTN | 303 | 5648475 |  | 5648475 | 5648475 | 2 | 2020-10-30 |  | 5648475 | 2020-08-31 | 0 | 0 | ck
4 | Gas Intangible | FP-302621 LV CUSTOMER WEB SITE - DIRECT | 303 | 50930.43 | 75.17% | 38284.4042 |  |  | 2020-12-31 |  |  | 2020-12-31 | 0
5 | Gas Intangible | FP-306998 SOUTH WALLA GATE-WILLIAMS COSTS | 303 | 746233 |  | 746233 | 746233 | 4 | 2020-11-25 |  | 746233 | 2020-11-20 | 0 | 15537544.115 | Amount yet to be installed/spent.
6 | Gas Intangible | FP-316019 UG GIS ESRI UPGRADE - CNG DIRECT | 303 | 346857.72 | 75.17% | 260732.9481 |  |  | 2022-12-31 |  |  | 2022-12-31 | 0
7 | Gas Intangible | FP-316047 UG GIS LANDBASE - CNG DIRECT COST | 303 | 35994.87 | 75.17% | 27057.3438 |  |  | 2020-02-15 |  |  | 2020-02-15 | 0 | 5983376 | Actual reduction amount to Proposed Plant Additions, due to delayed in-service date. Projects note code 5 & 26.
8 | Gas Intangible | FP-316102 UG-GIS Pipeline Inspection System | 303 | 158747.54 | 75.17% | 119330.5258 |  |  | 2020-06-30 |  |  | 2020-06-30 | 0
9 | Gas Intangible | FP-316182 UG 2018 CC&B UPGRADE - CNG DIRECT | 303 | 670450.44 | 75.17% | 503977.5957 |  |  | 2019-01-31 |  |  | 2019-01-31 | 0 | 9554168.115 | Amount expected to be spent and installed within the next 3 months by 12/31/20.
10 | Gas Intangible | FP-316269 UG WEBLOGIC FOR JDE - CNG DIRE | 303 | 21082.9 |  | 21082.9 |  |  | 2020-08-30 |  |  | 2020-08-30 | 0
11 | Gas Intangible | FP-316284 GIS High Acc Trans Line Surv Enhanc | 303 | 155972.76 | 75.17% | 117244.7237 |  |  | 2020-12-31 |  |  | 2020-12-31 | 0 | 60122261.285 | Proposed Plant Additions to be spent and installed by 12/31/20.
12 | Gas Intangible | FP-316289 PowerPlan Lease CNG | 303 | -450.01 |  | -450.01 |  |  | 2020-04-30 |  |  | 2020-04-30 | 0
13 | Gas Intangible | FP-316361 UG 2018 SCADA ENHANCE-CNG DIRECT | 303 | 69223.05 | 75.17% | 52034.9667 |  |  | 2023-12-31 |  |  | 2023-12-31 | 0
14 | Gas Intangible | FP-316451 UG Purch RabMQ Software CNG Direct | 303 | 15422.61 |  | 15422.61 |  |  | 2020-04-30 |  |  | 2020-04-30 | 0
15 | Gas Intangible | FP-317101 UG-JDEdwards AS400 to Oracle DB | 303 | 63738.72 | 75.17% | 47912.3958 |  |  | 2020-09-30 |  |  | 2020-09-30 | 0
16 | Gas Intangible | FP-317322 ARLINGTON GATE UPGR; WILLIAMS COSTS | 303 | 882417.45 |  | 882417.45 | 805597 | 11 | 2020-09-03 |  | 882417.45 | 2020-06-30 | 76820.45
17 | Gas Intangible | FP-317617 UG-Migrate Aligne CNG Direct | 303 | 8476.31 | 75.17% | 6371.6422 |  |  | 2020-01-12 |  |  | 2020-01-12 | 0
18 | Gas Intangible | FP-318808 GR-OTHELLO-GT-OTHELLO GATE NWP | 303 | 858122 |  | 858122 | 858122 | 21 | 2020-09-18 |  | 858122 | 2020-11-30 | 0
19 | Gas Intangible | FP-318822 Impl myWorld Leak Survey at CNGC | 303 | 136867.86 |  | 136867.86 |  |  | 2020-05-31 |  |  | 2020-05-31 | 0
20 | Gas Intangible | FP-318846 UG-Impl 2Ring Dashboard for CSC-CNG | 303 | 26509.6 | 75.17% | 19927.2663 |  |  | 2020-05-01 |  |  | 2020-05-01 | 0
21 | Gas Intangible | FP-318893 UG-Impl GIS Offline Mobile Maps-CNG | 303 | 27529.2 | 75.17% | 20693.6996 |  |  | 2020-10-15 |  |  | 2020-10-15 | 0
22 | Gas Intangible | FP-318987 GR-OTHELLO-NWP LAT FA COSTS | 303 | 4731395 |  | 4731395 | 2628782 | 23 | 2020-08-28 |  | 4731395 | 2020-11-30 | 2102613
23 |  | Total Intangible Plant |  | 14946950.57 |  | 14524477.2003 | 10687209 |  |  |  | 12866642.45
24 | RESULTS OF OPERATIONS SUMMARY SHEET
25 | Gas Distribution | FP-101163 Gas Work Equipment-CNGC | 396.2 | 481087.24 | 75.17% | 361633.2783 |  |  | 2020-12-31 |  |  | 2020-12-31 | 0
26 | Gas Distribution | FP-101164 IT Network Equipment-CNG | 397.2 | 290586.04 | 75.17% | 218433.5263 |  |  | 2020-12-31 |  |  | 2020-12-31 | 0
27 | Gas Distribution | FP-101191 - MAIN-REINFORCE-WASHINGTON | 376.2 | 36096.4 |  | 36096.4 |  |  | 2020-04-25 |  |  | 2020-04-25 | 0
28 | Gas Distribution | FP-101192 - MAIN-RELO-REPL-WASHINGTON | 376 | 55032.54 |  | 55032.54 |  |  | 2020-09-01 |  |  | 2020-09-01 | 0
29 | Gas Distribution | FP-101194-Reg Station Growth Washingotn | 378 | 611717 |  | 16553.18 | 16553.18 | 27 | 2020-12-31 |  | 611717 | 2020-12-31 | 595163.82
30 | Gas Distribution | FP-101196 - R STA-RELO-REPL-WASHINGTON | 378 | 650533.54 |  | 650533.54 |  |  | 2020-10-15 |  |  | 2020-10-15 | 0
31 | Gas Distribution | FP-101197 - SERV-GROWTH-WASHINGTON | 380 | 62.76 |  | 62.76 |  |  | 2020-11-01 |  |  | 2020-11-01 | 0
32 | Gas Distribution | FP-101200 - IND M&R-GROWTH-WASHINGTON | 385 | 40010.83 |  | 40010.83 |  |  | 2020-12-16 |  |  | 2020-12-16 | 0
33 | Gas Distribution | FP-101201 - IND M&R-REMOVE&REPL-WASHINGTON | 385 | 21467.7 |  | 21467.7 |  |  | 2020-05-30 |  |  | 2020-05-30 | 0
34 | Gas Distribution | FP-101210 Gas Meters-Total Company CNGC | 381 | 3919185.28 | 75.17% | 5961143.85 | 5961143.85 | 28 | 2020-12-31 |  | 2946051.575 | 2020-12-31 | -3015092.275
35 | Gas Distribution | FP-101215 Gas Vehicles-CNGC | 392.2 | 2180374.04 | 75.17% | 1638987.1659 |  |  | 2020-12-31 |  |  | 2020-12-31 | 0
36 | Gas Distribution | FP-101259 Gas Regulators-Total Company CNGC | 383 | 1320143.48 | 75.17% | 992351.8539 |  |  | 2020-12-31 |  |  | 2020-12-31 | 0
37 | Gas Distribution | FP-101275 - SERV-RELO-REPL-WASHINGTON | 380 | 31924.36 |  | 31924.36 |  |  | 2020-11-01 |  |  | 2020-11-01 | 0
38 | Gas Distribution | FP-101413GP BUILDINGS - WALLAWALLA | 375.1 | 124289.24 |  | 124289.24 |  |  | 2020-12-31 |  |  | 2020-12-31 | 0
39 | Gas Distribution | FP-101416GP TOOLS - WALLAWALLA | 394.1 | 4282.32 |  | 4282.32 |  |  | 2020-12-31 |  |  | 2020-12-31 | 0
40 | Gas Distribution | FP-200043 RPL 8" TRANSMISSION BELFAIR | 367.1 | 7616.94 |  | 7616.94 |  |  | 2020-12-31 |  |  | 2020-12-31 | 0
41 | Gas Distribution | FP-200662 Personal Computers & Peripherals | 391.3 | 54854.48 | 75.17% | 41234.1126 |  |  | 2020-12-31 |  |  | 2020-12-31 | 0
42 | Gas Distribution | FP-300233 - ARLINGTON 6" HP REINFORCEMENT | 376.2 | 2757265.26 |  | 2757265.26 | 2834085.71 | 1 | 2020-01-27 |  | 2757265.26 | 2020-06-30 | -76820.45
43 | Gas Distribution | FP-302369 - GB - GROUNDBED WASHINGTON | 376.1 | 747641.35 |  | 747641.35 |  |  | 2020-03-01 |  |  | 2020-03-01 | 0
45 | Gas Distribution | FP-306980 ERT Replacement 2020 | 381 | 363466.8 | 75.17% | 273217.9936 |  |  | 2020-12-31 |  |  | 2020-12-31 | 0
46 | Gas Distribution | FP-306988 - Walla Walla Mains High Press Steel | 376.2 | 3360413 |  | 3360413 | 4618317.11 | 3 | 2020-11-25 |  | 3360413 | 2020-11-30 | -1257904.11
47 | Gas Distribution | FP-309960 Anacortes Upgrade | 367.1 | 2363557.25 |  | 2363557.25 |  |  | 2022-11-30 |  |  | 2022-11-30 | 0
48 | Gas Distribution | FP-312009 - RP;R-130 (R-25) BURBANK | 378 | 20008.89 |  | 20008.89 |  |  | 2020-01-31 |  |  | 2020-01-31 | 0
49 | Gas Distribution | FP-316027 C/M RPL; 2" HP; NOOKSACK; 732' | 376.2 | 179168.59 |  | 179168.59 |  | C | 2020-12-31 |  |  | 2020-12-31 | 0
50 | Gas Distribution | FP-316033 C/M RPL; 3" HP; ZILLAH; 873' | 376.2 | 239545.87 |  | 239545.87 |  | C | 2020-12-31 |  |  | 2020-12-31 | 0
51 | Gas Distribution | FP-316034 - MAOP; 8" HP; OTHE; 11,500' W LEE RD | 376.2 | 112657.85 |  | 112657.85 |  |  | 2020-11-30 |  |  | 2020-11-30 | 0
52 | Gas Distribution | FP-316035 C/M RPL; 4" HP; ARLINGTON; 4,700' | 376.2 | 1321132.35 |  | 1321132.35 |  | C | 2020-12-31 |  |  | 2020-12-31 | 0
53 | Gas Distribution | FP-316043 MAOP; 8" HP; BELLINGHAM; 1,800' | 376.2 | 588710.21 |  | 588710.21 |  |  | 2020-12-01 |  |  | 2020-12-01 | 0
54 | Gas Distribution | FP-316044 C/M RPL; 8" HP; BREMERTON; 7,373' | 376.2 | 1714110.95 |  | 1714110.95 |  | C | 2020-12-31 |  |  | 2020-12-31 | 0
55 | Gas Distribution | FP-316046 - MAOP; 8" HP; YAKI; 4,500' YAKIMA RI | 376.2 | 490462.48 |  | 490462.48 |  |  | 2020-07-30 |  |  | 2020-07-30 | 0
56 | Gas Distribution | FP-316146 RP; R-178 (R-137) FERNDALE | 378 | 17894.23 |  | 17894.23 |  |  | 2020-04-30 |  |  | 2020-04-30 | 0
57 | Gas Distribution | FP-316403 CRM; 6" ST; TOPPENISH, 800' | 376.1 | 517249.44 |  | 517249.44 |  | C | 2020-12-01 |  |  | 2020-12-01 | 0
58 | Gas Distribution | FP-316429 - RF; 6" HP; ABER; 12,500' BASICH BLV | 376.2 | 4257740 |  | 4257740 | 0 | 5 | 2021-08-31 |  | 4257740 | 2020-07-30 | 4257740
59 | Gas Distribution | FP-316570 C/M RPL; 12" STL HP, LONG/KELSO PH4 | 376.2 | 3462856.75 |  | 3462856.75 |  | C | 2020-11-30 |  |  | 2020-11-30 | 0
60 | Gas Distribution | FP-316580 C/M RPL; 2,6,8" HP; ANACORTES; PH3 | 376.2 | 1079817.45 |  | 1079817.45 |  | C | 2020-12-31 |  |  | 2020-12-31 | 0
61 | Gas Distribution | FP-316586 - RP; R-187 ARLINGTON GATE | 378 | 1015615.47 |  | 1015615.47 | 1005786.24 | 6 | 2020-07-31 |  | 1015615.47 | 2020-06-30 | 9829.23
62 | Gas Distribution | FP-316587 - RF; WALLULA GATE; R-127 & O-14 | 378 | 1308260.44 |  | 1308260.44 | 1308260.44 | 7 | 2020-10-30 |  | 1308260.44 | 2020-08-31 | 0
63 | Gas Distribution | FP-316589 RF; S WALLA GATE; R-4 & O-2 | 378 | 1160244.89 |  | 1160244.89 | 1160244.89 | 8 | 2020-11-25 |  | 1160244.89 | 2020-11-30 | 0
64 | Gas Distribution | FP-316670 - RF; 12" HP; KENN; WALLULA HP LINE | 376.2 | 9795152 |  | 9795152 | 9795152 | 9 | 2020-10-30 |  | 9795152 | 2020-08-31 | 0
65 | Gas Distribution | FP-316822 - RP; O-4(O-4) LAWR; DIRINJECT | 378 | 77932.33 |  | 77932.33 |  |  | 2020-01-30 |  |  | 2020-01-30 | 0
66 | Gas Distribution | FP-316823 - RP; O-12(O-5) DEMI; DIRINJECT | 378 | 77959.74 |  | 77959.74 |  |  | 2020-01-30 |  |  | 2020-01-30 | 0
67 | Gas Distribution | FP-316923 -C/M RPL 8" MARCH POINT LINE PHASE 2 | 367.1 | 2438636.93 |  | 2438636.93 |  | C | 2020-11-30 |  |  | 2020-11-30 | 0
68 | Gas Distribution | FP-317060 - FRL; 10" HP; BELL; 2900' STATEBRIDG | 376.2 | 1526471.05 |  | 1526471.05 | 1512200.81 | 10 | 2020-01-23 |  | 1526471.05 | 2020-01-20 | 14270.24
69 | Gas Distribution | FP-317519 RP; 2" ST; SHELTON; 7,034' PH 3 SEC | 376.3 | 441993.69 |  | 441993.69 |  | C | 2020-03-30 |  |  | 2020-03-30 | 0
70 | Gas Distribution | FP-317528 RP; 3/4" SL; SHELTON; PH 3 SEC 1 SE | 380.3 | 100949.38 |  | 100949.38 |  | C | 2020-03-30 |  |  | 2020-03-30 | 0
71 | Gas Distribution | FP-317535 GR; R-128 BURB;TIE-IN TO ATTAL | 378 | 136928 |  | 136928 | 136928 | 12 | 2020-10-30 |  | 136928 | 2020-08-31 | 0
72 | Gas Distribution | FP-317609 GR; R-80 ABER; BASICH BLV | 378 | 324.69 |  | 324.69 |  |  | 2020-06-30 |  |  | 2020-06-30 | 0
73 | Gas Distribution | FP-317628 MAIN-GROWTH-WALLA WALLA DISTRICT | 376.3 | 639913.04 |  | 133326.96 | 133326.96 | 27 | 2020-12-31 |  | 639913.04 | 2020-12-31 | 506586.08
74 | Gas Distribution | FP-317629 MAIN-REPLACE-WALLA WALLA DISTRICT | 376 | 122698.76 |  | 122698.76 |  |  | 2020-12-31 |  |  | 2020-12-31 | 0
75 | Gas Distribution | FP-317630 SERV-GROWTH-WALLA WALLA DISTRICT | 380.3 | 951862.52 |  | 410276.59 | 410276.59 | 27 | 2020-12-31 |  | 951862.52 | 2020-12-31 | 541585.93
76 | Gas Distribution | FP-317631 SERV-REPLACE-WALLA WALLA DISTRICT | 380 | 72198.24 |  | 72198.24 |  |  | 2020-12-31 |  |  | 2020-12-31 | 0
77 | Gas Distribution | FP-317632 MAIN-GROWTH-WENATCHEE DISTRICT | 376.3 | 79311 |  | 5329.72 | 5329.72 | 27 | 2020-12-31 |  | 79311 | 2020-12-31 | 73981.28
78 | Gas Distribution | FP-317633 MAIN-REPLACE-WENATCHEE DISTRICT | 376 | 35499.24 |  | 35499.24 |  |  | 2020-12-31 |  |  | 2020-12-31 | 0
79 | Gas Distribution | FP-317634 SERV-GROWTH-WENATCHEE DISTRICT | 380.3 | 133027.99 |  | 64681.2 | 64681.2 | 27 | 2020-12-31 |  | 133027.99 | 2020-12-31 | 68346.79
80 | Gas Distribution | FP-317635 SERV-REPLACE-WENATCHEE DISTRICT | 380 | 75135.57 |  | 75135.57 |  |  | 2020-12-31 |  |  | 2020-12-31 | 0
81 | Gas Distribution | FP-317636 MAIN-GROWTH-YAKIMA DISTRICT | 376.3 | 800173.4 |  | 58159.6 | 58159.6 | 27 | 2020-12-31 |  | 800173.4 | 2020-12-31 | 742013.8
82 | Gas Distribution | FP-317637 MAIN-REPLACE-YAKIMA DISTRICT | 376 | 270033.86 |  | 270033.86 |  |  | 2020-12-31 |  |  | 2020-12-31 | 0
83 | Gas Distribution | FP-317638 SERV-GROWTH-YAKIMA DISTRICT | 380.3 | 1330260 |  | 903580.47 | 903580.47 | 27 | 2020-12-31 |  | 1330260 | 2020-12-31 | 426679.53
84 | Gas Distribution | FP-317639 SERV-REPLACE-YAKIMA DISTRICT | 380 | 65462.16 |  | 65462.16 |  |  | 2020-12-31 |  |  | 2020-12-31 | 0
85 | Gas Distribution | FP-317640 MAIN-GROWTH-ABERDEEN DISTRICT | 376.3 | 484622.4 |  | 17518.11 | 17518.11 | 27 | 2020-12-31 |  | 484622.4 | 2020-12-31 | 467104.29
86 | Gas Distribution | FP-317641 MAIN-REPLACE-ABERDEEN DISTRICT | 376 | 149164.2 |  | 149164.2 |  |  | 2020-12-31 |  |  | 2020-12-31 | 0
87 | Gas Distribution | FP-317642 SERV-GROWTH-ABERDEEN DISTRICT | 380.3 | 447800.6 |  | 212871.49 | 212871.49 | 27 | 2020-12-31 |  | 447800.6 | 2020-12-31 | 234929.11
88 | Gas Distribution | FP-317643 SERV-REPLACE-ABERDEEN DISTRICT | 380 | 74578.68 |  | 74578.68 |  |  | 2020-12-31 |  |  | 2020-12-31 | 0
89 | Gas Distribution | FP-317644-MAIN-GROWTH-BELLINGHAM DISTRICT | 376.3 | 1294473.18 |  | 177982.99 | 177982.99 | 27 | 2020-12-31 |  | 1294473.18 | 2020-12-31 | 1116490.19
90 | Gas Distribution | FP-317645 MAIN-REPLACE-BELLINGHAM DISTRICT | 376 | 126071.52 |  | 126071.52 |  |  | 2020-12-31 |  |  | 2020-12-31 | 0
91 | Gas Distribution | FP-317646 SERV-GROWTH-BELLINGHAM DISTRICT | 380.3 | 1568619.36 |  | 1035068.99 | 1035068.99 | 27 | 2020-12-31 |  | 1568619.36 | 2020-12-31 | 533550.37
92 | Gas Distribution | FP-317647 SERV-REPLACE-BELLINGHAM DISTRICT | 380 | 74578.68 |  | 74578.68 |  |  | 2020-12-31 |  |  | 2020-12-31 | 0
93 | Gas Distribution | FP-317648-MAIN-GROWTH-BREMERTON DISTRICT | 376.3 | 1396510.12 |  | 120941.31 | 120941.31 | 27 | 2020-12-31 |  | 1396510.12 | 2020-12-31 | 1275568.81
94 | Gas Distribution | FP-317649 MAIN-REPLACE-BREMERTON DISTRICT | 376 | 54857.76 |  | 54857.76 |  |  | 2020-12-31 |  |  | 2020-12-31 | 0
95 | Gas Distribution | FP-317650 SERV-GROWTH-BREMERTON DISTRICT | 380.3 | 2118035.96 |  | 1069805.37 | 1069805.37 | 27 | 2020-12-31 |  | 2118035.96 | 2020-12-31 | 1048230.59
96 | Gas Distribution | FP-317651 SERV-REPLACE-BREMERTON DISTRICT | 380 | 74578.68 |  | 74578.68 |  |  | 2020-12-31 |  |  | 2020-12-31 | 0
97 | Gas Distribution | FP-317652 MAIN-GROWTH-LONGVIEW DISTRICT | 376.3 | 255366.68 |  | 47892.42 | 47892.42 | 27 | 2020-12-31 |  | 255366.68 | 2020-12-31 | 207474.26
98 | Gas Distribution | FP-317653 MAIN-REPLACE-LONGVIEW DISTRICT | 376 | 100812.24 |  | 100812.24 |  |  | 2020-12-31 |  |  | 2020-12-31 | 0
99 | Gas Distribution | FP-317654 SERV-GROWTH-LONGVIEW DISTRICT | 380.3 | 884722.06 |  | 255247.63 | 255247.63 | 27 | 2020-12-31 |  | 884722.06 | 2020-12-31 | 629474.43
100 | Gas Distribution | FP-317655 SERV-REPLACE-LONGVIEW DISTRICT | 380 | 74578.68 |  | 74578.68 |  |  | 2020-12-31 |  |  | 2020-12-31 | 0
101 | Gas Distribution | FP-317656 MAIN-GROWTH-MT VERNON DISTRICT | 376.3 | 613354.97 |  | 158285.08 | 158285.08 | 27 | 2020-12-31 |  | 613354.97 | 2020-12-31 | 455069.89
102 | Gas Distribution | FP-317657 MAIN-REPLACE-MT VERNON DISTRICT | 376 | 97392.48 |  | 97392.48 |  |  | 2020-12-31 |  |  | 2020-12-31 | 0
103 | Gas Distribution | FP-317658 SERV-GROWTH-MT VERNON DISTRICT | 380.3 | 1801553.41 |  | 986255.43 | 986255.43 | 27 | 2020-12-31 |  | 1801553.41 | 2020-12-31 | 815297.98
104 | Gas Distribution | FP-317659 SERV-REPLACE-MT VERNON DISTRICT | 380 | 74578.68 |  | 74578.68 |  |  | 2020-12-31 |  |  | 2020-12-31 | 0
105 | Gas Distribution | FP-317744 Tools & Minor Work Equip CNG WA | 394 | 88997.82 |  | 88997.82 |  |  | 2020-12-31 |  |  | 2020-12-31 | 0
106 | Gas Distribution | FP-317750 MAIN-GROWTH-KENNEWICK DISTRICT | 376.3 | 1417842.72 |  | 856065.48 | 856065.48 | 27 | 2020-12-31 |  | 1417842.72 | 2020-12-31 | 561777.24
107 | Gas Distribution | FP-317751 MAIN-REPLACE-KENNEWICK DISTRICT | 376 | 145471.8 |  | 145471.8 |  |  | 2020-12-31 |  |  | 2020-12-31 | 0
108 | Gas Distribution | FP-317752 SERV-GROWTH-KENNEWICK DISTRICT | 380.3 | 2952964.66 |  | 1772812.73 | 1772812.73 | 27 | 2020-12-31 |  | 2952964.66 | 2020-12-31 | 1180151.93
109 | Gas Distribution | FP-317753 SERV-REPLACE-KENNEWICK DISTRICT | 380 | 72740.76 |  | 72740.76 |  |  | 2020-12-31 |  |  | 2020-12-31 | 0
110 | Gas Distribution | FP-318092 HPSS Replacements CNG WA | 376 | 296950 |  | 296950 |  |  | 2020-12-31 |  |  | 2020-12-31 | 0
111 | Gas Distribution | FP-318186 Sys Safety & Integ Main Repl CNG WA | 376.3 | 5004463.92 |  | 5004463.92 |  |  | 2020-12-31 |  |  | 2020-12-31 | 0
112 | Gas Distribution | FP-318187 Sys Safety & Integ Svcs Rpl CNG WA | 380 | 4410563.92 |  | 4410563.92 |  |  | 2020-12-31 |  |  | 2020-12-31 | 0
113 | Gas Distribution | FP-318325 CRM, RP; 3/4" SL; ANACORT; PH 7 S 2 | 380.3 | 71392.82 |  | 71392.82 |  | C | 2020-01-01 |  |  | 2020-01-01 | 0
114 | Gas Distribution | FP-318482 RF; 4"; PE; Moses Lake 1,800' | 376.3 | 433146.02 |  | 433146.02 | 212170.31 | 14 | 2020-03-10 |  | 433146.02 | 2020-07-30 | 220975.71
115 | Gas Distribution | FP-318566 RP-Brem-R-Werener&Twin View R-21 | 378 | 177166.29 |  | 177166.29 | 177166.29 | 15 | 2020-11-20 |  | 177166.29 | 2020-09-30 | 0
116 | Gas Distribution | FP-318588 RP-GIBRALT-4"PE2125' | 376.3 | 125671.29 |  | 125671.29 | 125671.29 | 16 | 2020-10-15 |  | 125671.29 | 2020-07-31 | 0
117 | Gas Distribution | FP-318690 RF-Walla-1800' 6"S/6"PE Larch Ave | 376.1 | 312625 |  | 312625 | 312625 | 17 | 2020-11-30 |  | 312625 | 2020-11-30 | 0
118 | Gas Distribution | FP-318742 RP-MTVE-R-N TEXAS RD R-47 | 378 | 352513.6 |  | 352513.6 | 352513.6 | 18 | 2020-10-31 |  | 352513.6 | 2020-10-31 | 0
119 | Gas Distribution | FP-318746 RF-WALLA-R-OLD MILTON HWY-2" STD | 378 | 124719 |  | 124719 | 124719 | 19 | 2020-11-25 |  | 124719 | 2020-11-20 | 0
120 | Gas Distribution | FP-318747 RF-WALLA-R-PLAZA WAY-2" STD | 378 | 124719 |  | 124719 | 124719 | 20 | 2020-11-25 |  | 124719 | 2020-11-20 | 0
121 | Gas Distribution | FP-318829 GR-OTHELLO-GT-OTHELLO GATE RS | 378 | 464483 |  | 464483 | 464483 | 22 | 2020-09-18 |  | 464483 | 2020-11-30 | 0
122 | Gas Distribution | FP-319029 RP-MTVE-MTR-N TEXAS RD | 385 | 58451 |  | 58451 |  |  | 2020-09-30 |  |  | 2020-09-30 | 0
123 | Gas Distribution | FP-319056 RP; O-TBD (O-08); RICH | 378 | 143033.6 |  | 143033.6 | 143033.6 | 24 | 2020-12-30 |  | 143033.6 | 2020-08-30 | 0
124 | Gas Distribution | FP-319063 RP; O-TBD (O-03); KENN | 378 | 144470.2 |  | 144470.2 | 144470.2 | 25 | 2020-10-30 |  | 144470.2 | 2020-08-30 | 0
125 | Gas Distribution | FP-319072 GR; 6" HP&PE;W.RICH; 1.7mi KEENE RD | 376.2 | 1725636 |  | 1725636 | 0 | 26 | 2021-07-30 |  | 1725636 | 2021-07-30 | 1725636
126 | Gas Distribution | FP-319086 GR; 4"; PE; WRIC; 2946; PARA | 376.3 | 19400.1 |  | 19400.1 |  |  | 2020-02-28 |  |  | 2020-02-28 | 0
127 | Gas Distribution | FP-319095 Odorizer site imprvmts Walla Walla | 378 | 5607.8 |  | 5607.8 |  |  | 2020-10-20 |  |  | 2020-10-20 | 0
128 | Gas Distribution | FP-319099 Repl Fence R-1 Reg Stn Walla Walla | 378 | 5845.1 |  | 5845.1 |  |  | 2020-09-20 |  |  | 2020-09-20 | 0
129 | Gas Distribution | FP-319106 C/M RPL; 8" HP; YAKIMA; PH2 | 376.2 | 1196019 |  | 1196019 |  | C | 2020-12-30 |  |  | 2020-12-30 | 0
130 | Gas Distribution | FP-319111 MAOP MAIN RPL CNG WA | 376 | 1178410 |  | 1178410 |  |  | 2020-12-31 |  |  | 2020-12-31 | 0
131 | Gas Distribution | FP-319112 MAOP SERV RPL CNG WA | 380 | 128780 |  | 128780 |  |  | 2020-12-31 |  |  | 2020-12-31 | 0
132 | Gas Distribution | FP-319168 Ext Main Noll Rd Poulsbo | 376.3 | 121015.44 |  | 121015.44 |  |  | 2020-04-15 |  |  | 2020-04-15 | 0
133 | Gas Distribution | FP-319180 GR; 4" PE; LONG; 4,600' KELSO SCHOO | 376.3 | 169486.67 |  | 169486.67 |  |  | 2020-05-01 |  |  | 2020-05-01 | 0
134 | Gas Distribution | FP-319193 MN,ILLAHEE PRESERVE,BREMERTON,WA | 376.3 | 10487.23 |  | 10487.23 |  |  | 2020-05-30 |  |  | 2020-05-30 | 0
135 | Gas Distribution | FP-319209 GR; 4" HP; KALA; 2,500' SPENCER CRE | 376.2 | 16510.17 |  | 16510.17 |  |  | 2020-12-30 |  |  | 2020-12-30 | 0
136 | Gas Distribution | FP-319238 MN,13559' SOUND VIEW,BREMERTON,WA | 376.3 | 52336.62 |  | 52336.62 |  |  | 2020-05-30 |  |  | 2020-05-30 | 0
137 | Gas Distribution | FP-319247 RL;2"ST;YAKI;2,000' | 376.1 | 1145.58 |  | 1145.58 |  |  | 2020-02-01 |  |  | 2020-02-01 | 0
138 | Gas Distribution | FP-319256 GR; 2" PE; PROS; 2,500' | 376.3 | -87097.05 |  | -87097.05 |  |  | 2020-11-20 |  |  | 2020-11-20 | 0
139 | Gas Distribution | FP-319257 GR;4" SL; PROS; 1500 PATERSON RD | 380.3 | -21795.91 |  | -21795.91 |  |  | 2020-11-20 |  |  | 2020-11-20 | 0
140 |  |  |  | 88517757.53 |  | 78687258.9105 | 38816345.09
141 | Gas General | FP-101204 - GP TRAN. VEHICLE - WASHINGTO | 392.2 | 219131.38 |  | 219131.38 |  |  | 2020-06-30 |  |  | 2020-06-30 | 0
142 | Gas General | FP-101288 Purchase calibration field kit | 394.1 | 1359.54 |  | 1359.54 |  |  | 2020-03-31 |  |  | 2020-03-31 | 0
143 | Gas General | FP-101413 REPLACE WAREHOUSE FENCE WALLA WALLA | 390.1 | 36245.61 |  | 36245.61 |  |  | 2020-01-30 |  |  | 2020-01-30 | 0
144 | Gas General | FP-306967 District Office Access Control Sys | 391.3 | 27223.01 | 75.17% | 27223.01 |  |  | 2020-05-01 |  |  | 2020-05-01 | 0
146 | Gas General | FP-316445 Toughbook Replacements-CNG | 391.1 | 176798.64 | 75.17% | 176798.64 |  |  | 2020-12-31 |  |  | 2020-12-31 | 0
147 | Gas General | FP-316832 Office Structure & Eq-Kennewick GO | 391.5 | 50980 | 75.17% | 50980 |  |  | 2020-12-31 |  |  | 2020-12-31 | 0
148 | Gas General | FP-316915 Pur replacement display devices | 391.3 | 17333.2 | 75.17% | 17333.2 |  |  | 2020-05-01 |  |  | 2020-05-01 | 0
149 | Gas General | FP-317290 Building remodel for Bellingham Dis | 390.1 | 316076 |  | 316076 |  |  | 2020-07-01 |  |  | 2020-07-01 | 0
150 | Gas General | FP-317291 - Roof replacement/Parking lot - Bell | 390.1 | 15243.69 |  | 15243.69 |  |  | 2020-11-20 |  |  | 2020-11-20 | 0
151 | Gas General | FP-317387 MGP site restoration | 390 | 20392 |  | 20392 |  |  | 2020-06-05 |  |  | 2020-06-05 | 0
152 | Gas General | FP-318192 Fixed Network Equipment-CNG | 397 | 509800 | 75.17% | 509800 |  |  | 2020-12-31 |  |  | 2020-12-31 | 0
153 | Gas General | FP-318197 Gas SCADA Equipment-CNG | 397 | 1223.52 | 75.17% | 1223.52 |  |  | 2020-12-31 |  |  | 2020-12-31 | 0
154 | Gas General | FP-318317 Sensit PMD Trainer | 394.1 | 14274.4 |  | 14274.4 |  |  | 2020-02-01 |  |  | 2020-02-01 | 0
155 | Gas General | FP-318319 Sensit GLT Trainer | 394.1 | 6627.4 |  | 6627.4 |  |  | 2020-02-01 |  |  | 2020-02-01 | 0
156 | Gas General | FP-318352 Bremerton District Office Remodel | 390.1 | 1064539.08 |  | 1064539.08 | 1064539.08 | 13 | 2020-10-30 |  | 1064539.08 | 2020-10-30 | 0
157 | Gas General | FP-318706 Repl Cisco VoIP Telephone-CNG | 397 | 158321.16 | 75.17% | 158321.16 |  |  | 2020-11-15 |  |  | 2020-11-15 | 0
158 | Gas General | FP-318797 Instl District Strge Fclty Kelso | 390.1 | 620912.7 |  | 620912.7 |  |  | 2020-11-01 |  |  | 2020-11-01 | 0
159 | Gas General | FP-318801 Instl Asphalt in Storage Area Kelso | 390.1 | 76470 |  | 76470 |  |  | 2020-07-31 |  |  | 2020-07-31 | 0
160 | Gas General | FP-318889 New Transfer Prover | 394.1 | 33646.8 |  | 33646.8 |  |  | 2020-04-30 |  |  | 2020-04-30 | 0
161 | Gas General | FP-318904 Transfer Prover Upgrade Bellingham | 394.1 | 23450.8 |  | 23450.8 |  |  | 2020-04-30 |  |  | 2020-04-30 | 0
162 | Gas General | FP-318914 Transfer Prover upgrade Longview | 394.1 | 23450.8 |  | 23450.8 |  |  | 2020-06-06 |  |  | 2020-06-06 | 0
163 | Gas General | FP-318918 Transfer Prover Upgrade Kennewick | 394.1 | 23450.8 |  | 23450.8 |  |  | 2020-10-31 |  |  | 2020-10-31 | 0
164 | Gas General | FP-318957 Two Meter Shop Table Lifts | 394.1 | 8156.8 |  | 8156.8 |  |  | 2020-05-31 |  |  | 2020-05-31 | 0
165 | Gas General | FP-318958 Meter Shop Leak Tester | 394.1 | 25490 |  | 25490 |  |  | 2020-04-30 |  |  | 2020-04-30 | 0
166 | Gas General | FP-318959 Clamp on Check Meter | 394.1 | 20392 |  | 20392 |  |  | 2020-10-31 |  |  | 2020-10-31 | 0
167 | Gas General | FP-319025 Auto Floor Scrubber | 394.1 | 7137.2 |  | 7137.2 |  |  | 2020-04-04 |  |  | 2020-04-04 | 0
168 | Gas General | FP-319043 Mueller Equipment | 394 | 76238.35 | 75.17% | 76238.35 |  |  | 2020-06-30 |  |  | 2020-06-30 | 0
169 | Gas General | FP-319044 CONST SERV - NEW BLDG ADD - MT VERN | 390.1 | 195305.21 |  | 195305.21 |  |  | 2020-09-30 |  |  | 2020-09-30 | 0
170 | Gas General | FP-319045 TAP TRUCK HYDRAULIC SYSTEM | 394 | 11422.98 | 75.17% | 11422.98 |  |  | 2020-03-30 |  |  | 2020-03-30 | 0
171 | Gas General | FP-319048 Mueller Equipment | 394 | 13240.14 | 75.17% | 13240.14 |  |  | 2020-06-30 |  |  | 2020-06-30 | 0
172 | Gas General | FP-319052 BUILDING UPGARDES | 390 | 67673.91 | 75.17% | 67673.91 |  |  | 2020-03-10 |  |  | 2020-03-10 | 0
173 | Gas General | FP-319053 NEW WELDER YAK FAB SHOP | 394 | 5955.01 | 75.17% | 5955.01 |  |  | 2020-03-01 |  |  | 2020-03-01 | 0
174 | Gas General | FP-319090 Replace Shop Roof Walla Walla | 390.1 | 23392 |  | 23392 |  |  | 2020-03-30 |  |  | 2020-03-30 | 0
175 | Gas General | FP-319091 Repl Asphalt Park Lot Walla Walla | 390.1 | 46705.6 |  | 46705.6 |  |  | 2020-09-20 |  |  | 2020-09-20 | 0
176 | Gas General | FP-319092 Replace Roof Old Barn Walla Walla | 390.1 | 18294 |  | 18294 |  |  | 2020-12-20 |  |  | 2020-12-20 | 0
177 | Gas General | FP-319093 Rplc Fence 324 Rose St Walla Walla | 390.1 | 13196 |  | 13196 |  |  | 2020-07-02 |  |  | 2020-07-02 | 0
178 | Gas General | FP-319094 Instl Electronic Gate Walla Walla | 390.1 | 5607.8 |  | 5607.8 |  |  | 2020-10-20 |  |  | 2020-10-20 | 0
179 | Gas General | FP-319098 Rplc Ovrhd Shop Door Walla Walla | 390.1 | 3958.8 |  | 3958.8 |  |  | 2020-11-06 |  |  | 2020-11-06 | 0
180 | Gas General | FP-319100 Purch Threading Machine Walla Walla | 394.1 | 4282.32 |  | 4282.32 |  |  | 2020-05-05 |  |  | 2020-05-05 | 0
181 | Gas General | FP-319101 Pur Xtndble Squze Tool Walla Walla | 394.1 | 3059.82 |  | 3059.82 |  |  | 2020-05-05 |  |  | 2020-05-05 | 0
182 | Gas General | FP-319102 Purch Storage Cabinet Walla Walla | 391.5 | 2447.04 |  | 2447.04 |  |  | 2020-04-10 |  |  | 2020-04-10 | 0
183 | Gas General | FP-319120 Instl Cement Floor Barn Walla Walla | 390.1 | 2039.2 |  | 2039.2 |  |  | 2020-11-20 |  |  | 2020-11-20 | 0
184 | Gas General | FP-319132 Purch Swamp Cooler Wld Shp Wla Wla | 398 | 2039.2 |  | 2039.2 |  |  | 2020-06-15 |  |  | 2020-06-15 | 0
185 | Gas General | FP-319143 Purch 2 Squeeze Tools Walla Walla | 394.1 | 15905.76 |  | 15905.76 |  |  | 2020-11-05 |  |  | 2020-11-05 | 0
186 | Gas General | FP-319146 OFFICE REMODEL | 390.1 | 100372.18 |  | 100372.18 |  |  | 2020-02-18 |  |  | 2020-02-18 | 0
187 | Gas General | FP-319147 Purchase Air Compressor Walla Walla | 394.1 | 2039.2 |  | 2039.2 |  |  | 2020-05-15 |  |  | 2020-05-15 | 0
188 | Gas General | FP-319284 12" Mueller Shell Cutter and Stoppe | 394.1 | 5534.02 | 75.17% | 5534.02 |  |  | 2020-01-15 |  |  | 2020-01-15 | 0
189 | Gas General | FP-319289 PURCHASE FUME EXTRACTOR BREMERTON | 394.1 | 6159.1 |  | 6159.1 |  |  | 2020-02-29 |  |  | 2020-02-29 | 0
190 |  | Total Distribution Plant |  | 4122994.17 |  | 4122994.17 | 1064539.08
191 |  | Total |  | 107587702.27 |  | 97334730.2809 | 50568093.17
192 | Notes:
193 | [5 empty] | FERC | Budgeted 2020 | Depr. Rate | Depreciation
194 | C | CRM | 12762873.22 |  |  | Acct | Investment | UG-200278 | Expense
195 | [5 empty] | 303 | 10687209 | 12.81% | 1369031.4729
196 | [5 empty] | 367.1 | 0 | 1.5% | 0
197 | [5 empty] | 374.2 | 0 | 1.64% | 0
198 | [5 empty] | 376.1 | 312625 | 3.56% | 11129.45
199 | [5 empty] | 376.2 | 18759755.63 | 1.52% | 285148.2856
200 | [5 empty] | 376.3 | 1913343.27 | 2.81% | 53764.9459
201 | [5 empty] | 378 | 5158877.44 | 1.97% | 101629.8856
202 | [5 empty] | 380.1 | 0 | 3.47% | 0
203 | [5 empty] | 380.3 | 6710599.9 | 3.36% | 225476.1566
204 | [5 empty] | 381 | 5961143.85 | 2.61% | 155585.8545
205 | [5 empty] | 383 | 0 | 2.16% | 0
206 | [5 empty] | 385 | 0 | 1.7% | 0
207 | [5 empty] | 390.1 | 1064539.08 | 1.44% | 15329.3628
208 | [5 empty] | 394.1 | 0 | 10.66% | 0
209 | [5 empty] | 396.2 | 0 | 9.63% | 0
210 | [5 empty] | 397.2 | 0 | 5.53% | 0
211 |  |  |  |  | Totals |  | 50568093.17 | 3.571% | 2217095.4138 | 0.043844
212
213 | [6 empty] | 0