## Source Data - Act v Plan by WBS
Actual CWIP Closings vs GRC Forecast CWIP Closings | [6 empty] | -1174390719.3527 | -910885102.0654 | -263505617.2873
GAP Year 2022 | [8 empty] | - = Over Forecast
+ = Under Forecast
WBS | PB - WBS Level 3 | Energy | Project | U&U Category | Explanation | Area | 2023 EOP Total Actual CWIP Closings | JAK5 SEF16 Forecast CWIP Closings | Variance | Notes
C.10002.02.02.02 | W_C.10002.02.02.02: CLSD PSE HQ Refresh Phase 2 | Common |  |  |  | Facilities | -1136.89 | 0 | -1136.89
C.10002.02.02.04 | W_C.10002.02.02.04: CLSD Remodel Bellevue 9th Floor | Common |  |  |  | Facilities | -3137460.19 | 0 | -3137460.19
C.10002.02.04.01 | W_C.10002.02.04.01: Facility Optimizatn Bothell G Lease Exit | Common |  |  |  | Facilities | -1454822.02 | 0 | -1454822.02
C.10002.07.01.01 | W_C.10002.07.01.01: CLSD Puyallup Service Center Rebuild | Common |  |  |  | Facilities | -3163.14 | 0 | -3163.14
C.10002.08.02.01 | W_C.10002.08.02.01: CLSD Operational Training Center | Common |  |  |  | Facilities | -957996.11 | 0 | -957996.11
C.10003.01.01.01 | W_C.10003.01.01.01: CLSD Furniture and Fixture Installation | Common |  |  |  | Facilities | -299505.27 | -3000000 | 2700494.73
C.10003.01.03.01 | W_C.10003.01.03.01: Unplanned Facility Improvements | Electric |  |  |  | Facilities | -22263.42 | 0 | -22263.42
C.10005.01.02.01 | W_C.10005.01.02.01: Security System Installations Electric | Electric |  |  |  | IT | -28851.06 | -4150542.924 | 4121691.864
C.10005.01.02.02 | W_C.10005.01.02.02: WECC Mitigation Security Installations | Electric |  |  |  | IT | -14028826.31 | -7015753.7989 | -7013072.5111
C.10006.01.01.01 | W_C.10006.01.01.01: Fleet Capital Purchase | Electric |  |  |  | Other | -1679811.81 | -1000000 | -679811.81
C.10006.01.01.03 | W_C.10006.01.01.03: Fleet Radio Upgrade | Common |  |  |  | Other | -213317.6 | -300000 | 86682.4
C.10009.01.01.01 | W_C.10009.01.01.01: Storm OH Replacement Dist | Electric | Not Ops | Not Ops |  | Storm | -3338732.2713 | -2712513.0792 | -626219.1921
C.10009.01.01.02 | W_C.10009.01.01.02: Storm OH Replacement Trans | Electric | Not Ops | Not Ops |  | Storm | -1038901.71 | -1056886.4311 | 17984.7211
C.10010.02.01.01 | W_C.10010.02.01.01: Shuffleton Reloc at Kent Serv Center | Common |  |  |  | Facilities | -730.16 | 0 | -730.16
C.40001.01.01.01 | W_C.40001.01.01.01: Success Factors Application | Common |  |  |  | IT | -31187.46 | 0 | -31187.46
F.10002.01.14.01 | W_F.10002.01.14.01: Data Governance Foundation | Common |  |  |  | IT | -2813318.35 | -3510776.5 | 697458.15
F.10002.01.17.01 | W_F.10002.01.17.01: iDOT Replacement | Common |  |  |  | IT | 2178.68 | 0 | 2178.68
F.10002.01.18.01 | W_F.10002.01.18.01: Cap and Invest Billing | Common |  |  |  | IT | -3262565.93 | 0 | -3262565.93
F.10002.01.23.01 | W_F.10002.01.23.01: Complex Billing CEIP | Common |  |  |  | IT | -1906500.52 | -975493.8351 | -931006.6849
F.10002.03.02.01 | W_F.10002.03.02.01: Field Resources Call Out Tool | Electric |  |  |  | IT | 8597.42 | 0 | 8597.42
F.10002.03.03.01 | W_F.10002.03.03.01: Multi-Channel Workforce Management | Common |  |  |  | IT | -1269752.14 | -4469507.276 | 3199755.136
F.10002.04.01.01 | W_F.10002.04.01.01: Travel mgmt.-Exp Rpting and Elect pmt | Common |  |  |  | IT | -1281.01 | 0 | -1281.01
F.10002.05.02.01 | W_F.10002.05.02.01: Check Payment Processing | Common |  |  |  | IT | -1294.48 | 0 | -1294.48
F.10002.06.01.01 | W_F.10002.06.01.01: eGain Replacement | Common |  |  |  | IT | 478.33 | 0 | 478.33
F.10002.06.02.01 | W_F.10002.06.02.01: Customer Experience Enhancement Program | Common |  |  |  | IT | -2149992.82 | 0 | -2149992.82
F.10002.06.06.01 | W_F.10002.06.06.01: Bill Discount Rate | Common |  |  |  | IT | -2714622 | 0 | -2714622
F.10002.07.06.01 | W_F.10002.07.06.01: Time Varying Rates Pilot | Electric |  |  |  | IT | -4294742.08 | -6226556.3942 | 1931814.3142
F.10002.09.02.01 | W_F.10002.09.02.01: Enterprise PPM Tool | Common |  |  |  | IT | -3016387.93 | -2130526.2728 | -885861.6572
F.10003.02.01.07 | W_F.10003.02.01.07: Data Center Hardware Refresh | Common |  |  |  | IT | -11719941.2 | -19898747.4741 | 8178806.2741
F.10003.03.02.01 | W_F.10003.03.02.01: Transport Network Modernization | Common |  |  |  | IT | -768647.57 | 0 | -768647.57
F.10013.09.01.03 | W_F.10013.09.01.03: PSE ITSR | Common |  |  |  | IT | -1662783.67 | -2004756.4599 | 341972.7899
F.10015.02.06.02 | W_F.10015.02.06.02: Gas Control Upgrade 2022 | Gas |  |  |  | IT | -6651845 | -3510776.5 | -3141068.5
F.10015.02.14.02 | W_F.10015.02.14.02: OSI Soft PI Historian | Electric |  |  |  | IT | -142.27 | 0 | -142.27
F.10015.02.17.03 | W_F.10015.02.17.03: CLSD ADMS Advanced Apps | Electric | Projected | Projected | 9 - Projected | Operations | -32603.37 | 0 | -32603.37
F.10015.02.20.01 | W_F.10015.02.20.01: Annual Market Changes to Support CAISO | Common |  |  |  | IT | -78559.51 | 0 | -78559.51
F.10015.02.23.01 | W_F.10015.02.23.01: ERX Migration | Common | Projected | Projected | 9 - Projected | Operations | -86238.4 | 0 | -86238.4
F.10015.04.02.04 | W_F.10015.04.02.04: MDMS License Extension 2022-2026 | Common |  |  |  | IT | -215968.57 | 0 | -215968.57
F.10015.05.04.01 | W_F.10015.05.04.01: Quality Framework | Common |  |  |  | IT | -26817.3 | 0 | -26817.3
F.10015.06.05.02 | W_F.10015.06.05.02: SAP HR Support Packs 2022-2026 | Common |  |  |  | IT | -328596.66 | 0 | -328596.66
F.10015.06.23.02 | W_F.10015.06.23.02: SAP BW 7.5 Functional Upgrade | Common |  |  |  | IT | -16812.05 | 0 | -16812.05
F.10015.06.25.01 | W_F.10015.06.25.01: SAP Annual Upgrades 2022-2026 | Common |  |  |  | IT | -501758.07 | 0 | -501758.07
F.10015.06.26.01 | W_F.10015.06.26.01: Enhanced SAP Monitoring Alerting BPM | Common |  |  |  | IT | -752.48 | 0 | -752.48
F.10015.06.27.01 | W_F.10015.06.27.01: Cloud Connector SLS11 to SLS15 Upgrade | Common |  |  |  | IT | -212438.2 | 0 | -212438.2
F.10015.08.11.06 | W_F.10015.08.11.06: ServiceNow Improvements 2022-2026 | Common |  |  |  | IT | -1687241.67 | 0 | -1687241.67
F.10015.08.14.03 | W_F.10015.08.14.03: Sitecore 9.3 to 10.2 Upgrade | Common |  |  |  | IT | -1356429.56 | 0 | -1356429.56
F.10015.08.18.01 | W_F.10015.08.18.01: Microservices NET Core Upgrade | Common |  |  |  | IT | 176.26 | 0 | 176.26
F.10015.08.19.01 | W_F.10015.08.19.01: Terraform Upgrade | Common |  |  |  | IT | 7583.27 | 0 | 7583.27
F.10015.08.23.01 | W_F.10015.08.23.01: Xamarin Forms Migration to MAUI | Common |  |  |  | IT | -748465.54 | 0 | -748465.54
F.10015.11.04.01 | W_F.10015.11.04.01: Windows Server 2012 Upgrade | Common |  |  |  | IT | -3579613.96 | 0 | -3579613.96
F.10015.11.06.01 | W_F.10015.11.06.01: Migration to Dynatrace SaaS | Common |  |  |  | IT | -2868.41 | 0 | -2868.41
F.10016.01.01.03 | W_F.10016.01.01.03: IT Enterprise Architecture Tool 2022 | Common |  |  |  | IT | -162419.6 | 0 | -162419.6
F.10017.02.01.03 | W_F.10017.02.01.03: CLSD Annual Comm Room Tech Refresh 2022 | Common |  |  |  | IT | 1371.58 | 0 | 1371.58
F.10017.02.02.03 | W_F.10017.02.02.03: Annual Data Center Tech Refresh 2022-26 | Common |  |  |  | IT | 35140.99 | 0 | 35140.99
F.10017.03.05.02 | W_F.10017.03.05.02: Annual End User PC Refresh 2022-2026 | Common |  |  |  | IT | -5155266.6 | 0 | -5155266.6
F.10017.05.03.02 | W_F.10017.05.03.02: Annual MS Enterprise Agreement Growth | Common |  |  |  | IT | -215501.25 | 0 | -215501.25
F.10017.05.07.01 | W_F.10017.05.07.01: DC Battery Management | Common |  |  |  | IT | -2505.86 | 0 | -2505.86
F.10017.07.01.03 | W_F.10017.07.01.03: IPP SharePoint Upgrade NERC | Common |  |  |  | IT | 32784.7 | 0 | 32784.7
F.10017.08.02.03 | W_F.10017.08.02.03: Annual Telecom SCADA Refresh 2022-26 | Electric |  |  |  | IT | -92479 | 0 | -92479
F.10017.08.03.01 | W_F.10017.08.03.01: Enhanced Substation Communications | Electric |  |  |  | IT | -2659583.03 | 0 | -2659583.03
F.10017.08.07.01 | W_F.10017.08.07.01: 700MHz Spectrum | Electric |  |  |  | IT | -10201.11 | 0 | -10201.11
F.10017.08.08.01 | W_F.10017.08.08.01: ASAT to RTAC Replacement | Electric |  |  |  | IT | -294545.07 | 0 | -294545.07
F.10017.10.06.04 | W_F.10017.10.06.04: Annual Server Growth 2022-2026 | Common |  |  |  | IT | -205120.47 | 0 | -205120.47
F.10017.10.09.02 | W_F.10017.10.09.02: Hyper Converged Infra Refresh | Common |  |  |  | IT | -1560297.85 | 0 | -1560297.85
F.10017.10.18.01 | W_F.10017.10.18.01: Directory Services Optimization | Common |  |  |  | IT | -115491.54 | 0 | -115491.54
F.10017.11.01.04 | W_F.10017.11.01.04: Annual Storage Growth 2022-2026 | Common |  |  |  | IT | -121.9 | 0 | -121.9
F.10017.12.01.03 | W_F.10017.12.01.03: Annual Fiber Refresh Repair 2022-26 | Electric |  |  |  | IT | -489415.45 | 0 | -489415.45
F.10017.12.05.03 | W_F.10017.12.05.03: Annual Telecom RF Refresh 2022-26 | Electric |  |  |  | IT | -222361.2 | 0 | -222361.2
F.10017.12.06.03 | W_F.10017.12.06.03: Annual Telecom Equip Growth Tool 2022-26 | Electric |  |  |  | IT | -148786.75 | 0 | -148786.75
F.10017.12.08.04 | W_F.10017.12.08.04: Annual Telecom Network Refresh 2022-2026 | Electric |  |  |  | IT | -411865.72 | 0 | -411865.72
F.10017.12.23.04 | W_F.10017.12.23.04: Annual Network Tech Refresh 2022-2026 | Common |  |  |  | IT | -460673.31 | 0 | -460673.31
F.10017.12.25.02 | W_F.10017.12.25.02: Annual Audio Visual Tech Refresh 2022-26 | Common |  |  |  | IT | -2073.23 | 0 | -2073.23
F.10017.12.26.01 | W_F.10017.12.26.01: Generation Sites | Electric |  |  |  | IT | -447.47 | 0 | -447.47
F.10017.12.26.02 | W_F.10017.12.26.02: Generation Infrastructure Prgrm 2022-26 | Electric |  |  |  | IT | -2356558.71 | 0 | -2356558.71
F.10017.13.01.03 | W_F.10017.13.01.03: CLSD Annual Voice Equipment Refresh New | Common |  |  |  | IT | -11682.27 | 0 | -11682.27
F.10017.13.05.01 | W_F.10017.13.05.01: ACTR 2021 | Common |  |  |  | IT | -1036876.43 | 0 | -1036876.43
F.10017.13.06.01 | W_F.10017.13.06.01: Voice Recording Tech Refresh | Common |  |  |  | IT | -580285.51 | 0 | -580285.51
F.10017.15.01.04 | W_F.10017.15.01.04: Cloud Cost Optimization Tooling Refresh | Common |  |  |  | IT | -46884.63 | 0 | -46884.63
F.10018.02.03.02 | W_F.10018.02.03.02: Opex to Capital Maint 2022-2026 | Common |  |  |  | IT | -23098678.97 | 0 | -23098678.97
F.10018.02.04.01 | W_F.10018.02.04.01: Annual Enterprise App Growth 2022-2026 | Common |  |  |  | IT | -453856.89 | 0 | -453856.89
F.10025.01.04.01 | W_F.10025.01.04.01: Physical Security Roadmap | Electric |  |  |  | IT | -3162412.83 | 0 | -3162412.83
F.10025.01.04.02 | W_F.10025.01.04.02: Cyber Audit Web Server Upgrade | Common |  |  |  | IT | -2.16 | 0 | -2.16
F.10025.02.01.07 | W_F.10025.02.01.07: Transportation Security Admin TSA | Common |  |  |  | IT | -243997.36 | 0 | -243997.36 | Part of W_F.10007.02.01.02: IT Operational Program in the GRC
F.10025.02.01.08 | W_F.10025.02.01.08: Cyber Security Roadmap | Common |  |  |  | IT | -875253.88 | -2006158 | 1130904.12
F.10026.01.01.01 | W_F.10026.01.01.01: Robotic Process Automation | Common |  |  |  | IT | -32828.84 | -1002452.993 | 969624.153
K.10001.01.01.01 | W_K.10001.01.01.01: LBK Hydro Plant Work | Electric |  |  |  | Generation | -333967.66 | 0 | -333967.66
K.10001.01.01.02 | W_K.10001.01.01.02: LBK Small Tools | Electric |  |  |  | Generation | -28404.17 | -519.3026 | -27884.8674
K.10001.01.02.01 | W_K.10001.01.02.01: UBK Hydro Plant Work | Electric |  |  |  | Generation | -692849.32 | -520556.1995 | -172293.1205
K.10001.01.02.02 | W_K.10001.01.02.02: UBK Small Tools | Electric |  |  |  | Generation | -38015.09 | 0 | -38015.09
K.10002.01.02.06 | W_K.10002.01.02.06: UBK U2 Runner Replacement | Electric |  |  |  | Generation | -8661.96 | 0 | -8661.96
K.10003.01.01.01 | W_K.10003.01.01.01: LBK Crest Improvement and Floodwall | Electric |  |  |  | Generation | -12166.64 | 0 | -12166.64
K.10003.01.01.03 | W_K.10003.01.01.03: LBK Hatchery Raceway Project | Electric |  |  |  | Generation | -10290041.15 | -9245928.5269 | -1044112.6231
K.10003.02.01.01 | W_K.10003.02.01.01: UBK Phase II Spillway Stabilization | Electric |  |  |  | Generation | -5144336.99 | -4501342.2194 | -642994.7706
K.10004.01.01.01 | W_K.10004.01.01.01: COL 500Kv Trans Line | Electric |  |  |  | Generation | -334796.18 | -966780 | 631983.82
K.10006.01.01.02 | W_K.10006.01.01.02: ENC Thermal Plant Work | Electric |  |  |  | Generation | -1456724.73 | -195278.327 | -1261446.403
K.10007.01.01.02 | W_K.10007.01.01.02: FERN Thermal Plant Work | Electric |  |  |  | Generation | -4161827.87 | -315571.1489 | -3846256.7211
K.10007.01.01.03 | W_K.10007.01.01.03: FERN Major Maintenance Activity | Electric |  |  |  | Generation | -26306575.3 | 0 | -26306575.3
K.10008.01.01.03 | W_K.10008.01.01.03: FREDDY 1 Thermal Plant Work | Electric |  |  |  | Generation | -766151.29 | -4455701.362 | 3689550.072
K.10009.01.01.03 | W_K.10009.01.01.03: FRA Small Tools | Electric |  |  |  | Generation | -1423.39 | -27.9947 | -1395.3953
K.10009.01.01.04 | W_K.10009.01.01.04: FRA Thermal Plant Work | Electric |  |  |  | Generation | -4466532.14 | 0 | -4466532.14
K.10010.01.01.04 | W_K.10010.01.01.04: FRE Thermal Plant Work | Electric |  |  |  | Generation | -481105.61 | 0 | -481105.61
K.10013.01.01.01 | W_K.10013.01.01.01: GLD Small Tools | Electric |  |  |  | Generation | -75472.11 | 0 | -75472.11
K.10013.01.01.02 | W_K.10013.01.01.02: GLD Thermal Plant Work | Electric |  |  |  | Generation | -619258.31 | 0 | -619258.31
K.10015.01.01.01 | W_K.10015.01.01.01: HPK Ongoing UOP Replacements | Electric |  |  |  | Generation | -2194459.17 | -2039804.765 | -154654.405
K.10015.01.01.02 | W_K.10015.01.01.02: HPK Small Tools | Electric |  |  |  | Generation | -27766.22 | -47.1501 | -27719.0699
K.10015.01.01.03 | W_K.10015.01.01.03: HPK Wind Plant Work | Electric |  |  |  | Generation | -2406.35 | -8.2209 | -2398.1291
K.10016.01.01.01 | W_K.10016.01.01.01: JP Operational Capital | Gas |  |  |  | Generation | -1462705.48 | -2612889.5491 | 1150184.0691
K.10017.01.01.01 | W_K.10017.01.01.01: BKR Aquatic Riparian Habitat | Electric |  |  |  | Generation | -76346.58 | 0 | -76346.58
K.10018.01.01.01 | W_K.10018.01.01.01: LSR1 Ongoing Uop Replacements | Electric |  |  |  | Generation | -9827167.83 | -4646610.8246 | -5180557.0054
K.10018.01.01.02 | W_K.10018.01.01.02: LSR1 Small Tools | Electric |  |  |  | Generation | -12479.72 | 0 | -12479.72
K.10018.01.01.03 | W_K.10018.01.01.03: LSR1 Wind Plant Work | Electric |  |  |  | Generation | -84891.27 | 0 | -84891.27
K.10019.01.01.01 | W_K.10019.01.01.01: MTF Small Tools | Electric |  |  |  | Generation | -108514.34 | -361.502 | -108152.838
K.10019.01.01.02 | W_K.10019.01.01.02: MTF Thermal Plant Work | Electric |  |  |  | Generation | -2603299.02 | -1306704.4823 | -1296594.5377
K.10021.01.01.01 | W_K.10021.01.01.01: SNO Hydro Plant Work | Electric |  |  |  | Generation | -272266.4 | 0 | -272266.4
K.10021.01.01.02 | W_K.10021.01.01.02: SNO Small Tools | Electric |  |  |  | Generation | -7085.23 | 0 | -7085.23
K.10023.01.01.02 | W_K.10023.01.01.02: SMS Thermal Plant Work | Electric |  |  |  | Generation | -1555245.8742 | 0 | -1555245.8742
K.10025.01.02.01 | W_K.10025.01.02.01: LNG 1 Mile Pipe Connector | Gas |  |  |  | Generation | -480.01 | 0 | -480.01
K.10025.01.02.02 | W_K.10025.01.02.02: LNG 4 Mile Pipe To Plant | Gas |  |  |  | Generation | -267.83 | 0 | -267.83
K.10025.02.01.01 | W_K.10025.02.01.01: TLNG Operational Plant | Gas |  |  |  | Generation | -440382.15 | 0 | -440382.15
K.10026.01.01.03 | W_K.10026.01.01.03: WHH Small Tools | Electric |  |  |  | Generation | -28240.09 | -291.3408 | -27948.7492
K.10026.01.01.04 | W_K.10026.01.01.04: WHH Thermal Plant Work | Electric |  |  |  | Generation | -226808.65 | 0 | -226808.65
K.10028.01.01.01 | W_K.10028.01.01.01: WLD Small Tools | Electric |  |  |  | Generation | -1386.5 | -12794.2581 | 11407.7581
K.10028.01.01.03 | W_K.10028.01.01.03: WLD Wind Plant Work | Electric |  |  |  | Generation | -36492.78 | 0 | -36492.78 | Part of W_F.10007.02.01.02: IT Operational Program in the GRC
K.10028.01.01.04 | W_K.10028.01.01.04: WLD Ongoing UOP Replacements | Electric |  |  |  | Generation | -3485416.27 | -3095100.5624 | -390315.7076
R.10005.01.01.01 | W_R.10005.01.01.01: E Eastside 230Kv Subs Richards Creek | Electric | Energize Eastside | Specific: Specific |  | Operations | -44509897.4 | -37051853.9392 | -7458043.4608
R.10005.01.01.02 | W_R.10005.01.01.02: E Eastside 230Kv Subs Talbot Hill | Electric | Projected | Projected | 9 - Projected | Operations | -423.68 | -1007314.4742 | 1006890.7942
R.10005.01.01.07 | W_R.10005.01.01.07: E Eastside 230Kv Tlines | Electric | Energize Eastside | Specific: Specific |  | Operations | -158815791.08 | -3067957.5151 | -155747833.5649
R.10006.01.01.03 | W_R.10006.01.01.03: E Substation SCADA CEIP | Electric | Grid Modernization | Programmatic: Programmatic | 6E - Grid Mod | Operations | -5194074.5276 | -10122925.1792 | 4928850.6516
R.10006.01.01.04 | W_R.10006.01.01.04: E Trans Automation | Electric | Grid Modernization | Programmatic: Programmatic | 6E - Grid Mod | Operations | -499538.91 | -1434359.934 | 934821.024
R.10006.01.01.07 | W_R.10006.01.01.07: E Electric System Modeling | Electric | Grid Modernization | Programmatic: Programmatic | 6E - Grid Mod | Operations | -155913.93 | 0 | -155913.93
R.10007.06.01.01 | W_R.10007.06.01.01: E 5 Yr Electric Refundable CIAC | Electric | CIAC - Electric | Programmatic Customer Driven | 3E - CIAC, NCC, PI | Operations | 14562652.3 | 6382400 | 8180252.3
R.10007.07.01.01 | W_R.10007.07.01.01: E Customer Reimbursed | Electric | Customer Construction Electric | Programmatic Customer Driven | 3E - CIAC, NCC, PI | Operations | -8041.65 | -3258429.2382 | 3250387.5882
R.10007.08.01.01 | W_R.10007.08.01.01: E OH UG Commercial Services | Electric | Customer Construction Electric | Programmatic Customer Driven | 3E - CIAC, NCC, PI | Operations | -5512507.0854 | -3452.753 | -5509054.3324
R.10007.08.02.01 | W_R.10007.08.02.01: E OH UG Residential Services | Electric | Customer Construction Electric | Programmatic Customer Driven | 3E - CIAC, NCC, PI | Operations | -7582881.0732 | -17543.8189 | -7565337.2543
R.10007.08.02.02 | W_R.10007.08.02.02: E UG Residential Services In Plats | Gas | Customer Construction Electric | Programmatic Customer Driven | 3G - CIAC, NCC, PI | Operations | -646283.887 | 0 | -646283.887
R.10007.09.01.01 | W_R.10007.09.01.01: E Commercial Line Extension | Electric | Customer Construction Electric | Programmatic Customer Driven | 3E - CIAC, NCC, PI | Operations | -30083911.4376 | -328048.1002 | -29755863.3374
R.10007.09.02.01 | W_R.10007.09.02.01: E Multi Family Line Extension | Electric | Customer Construction Electric | Programmatic Customer Driven | 3E - CIAC, NCC, PI | Operations | -7266526.9215 | -449542.0357 | -6816984.8858
R.10007.09.03.02 | W_R.10007.09.03.02: E Plats Line Extension | Electric | Customer Construction Electric | Programmatic Customer Driven | 3E - CIAC, NCC, PI | Operations | -16922789.3279 | -251838.0017 | -16670951.3262
R.10007.09.04.01 | W_R.10007.09.04.01: E Single Family Line Extension | Electric | Customer Construction Electric | Programmatic Customer Driven | 3E - CIAC, NCC, PI | Operations | -15356014.4904 | -194567.0475 | -15161447.4429
R.10007.12.01.01 | W_R.10007.12.01.01: E Microsoft Campus Rebuild | Electric | Projected | Projected | 9 - Projected | Operations | 779464.2825 | 0 | 779464.2825
R.10007.12.03.01 | W_R.10007.12.03.01: E Customer Reimbursed Major Projects | Electric | Major Projects Electric | Programmatic: Programmatic | 7E - Maj Proj | Operations | 734743.4 | 0 | 734743.4
R.10008.01.01.01 | W_R.10008.01.01.01: E Conversions Sched 73 Cust Driven | Electric | PI Electric | Programmatic Customer Driven | 3E - CIAC, NCC, PI | Operations | -810990.7594 | -1757174.0095 | 946183.2501
R.10008.01.01.02 | W_R.10008.01.01.02: E OH UG Reloc - Removal Cust Driven Dist | Electric | PI Electric | Programmatic Customer Driven | 3E - CIAC, NCC, PI | Operations | -1131792.8495 | -2096.785 | -1129696.0644
R.10008.03.01.01 | W_R.10008.03.01.01: E Conversions Sched 74 PI Driven | Electric | PI Electric | Programmatic Customer Driven | 3E - CIAC, NCC, PI | Operations | -3259646.2076 | -129512.6362 | -3130133.5714
R.10008.03.01.03 | W_R.10008.03.01.03: E OH UG Rel PI Driven NonReimb Dist | Electric | PI Electric | Programmatic Customer Driven | 3E - CIAC, NCC, PI | Operations | -13148591.7277 | -939758.4966 | -12208833.2311
R.10008.03.01.04 | W_R.10008.03.01.04: E OH UG Rel PI Driven Reimburse Dist | Electric | PI Electric | Programmatic Customer Driven | 3E - CIAC, NCC, PI | Operations | -2124295.23 | -1273712.1873 | -850583.0427
R.10008.03.01.05 | W_R.10008.03.01.05: E PI Driven Relocations Trans | Electric | PI Electric | Programmatic Customer Driven | 3E - CIAC, NCC, PI | Operations | -1637663 | -42777.4164 | -1594885.5836
R.10008.03.01.14 | W_R.10008.03.01.14: E Sound Transit Reimburse | Electric | Projected | Projected | 9 - Projected | Operations | -757576.1236 | -197094.479 | -560481.6446
R.10008.03.01.18 | W_R.10008.03.01.18: E WSDOT Fish Passage Relocation | Electric | Projected | Projected | 9 - Projected | Operations | -1292404.7968 | 0 | -1292404.7968
R.10008.05.01.01 | W_R.10008.05.01.01: E Sound Transit Dist | Electric | Projected | Projected | 9 - Projected | Operations | -472148.33 | 0 | -472148.33
R.10008.05.01.02 | W_R.10008.05.01.02: E Sound Transit East Link Dist | Electric | Projected | Projected | 9 - Projected | Operations | -7722.89 | 0 | -7722.89
R.10008.07.01.01 | W_R.10008.07.01.01: E WSDOT Clr Zone Pole Prog Dist | Electric | PI Electric | Programmatic Customer Driven | 3E - CIAC, NCC, PI | Operations | -54192.09 | -2601507.4276 | 2547315.3376
R.10009.01.01.01 | W_R.10009.01.01.01: E BPA 3rd AC Transmission Intertie Work | Electric | Projected | Projected | 9 - Projected | Operations | -5735.34 | -1303933.4286 | 1298198.0886
R.10009.02.01.03 | W_R.10009.02.01.03: E Central Bellevue Dist Rel Feeder | Electric | Grid Modernization | Programmatic: Programmatic | 6E - Grid Mod | Operations | -267380.52 | -2498008.7604 | 2230628.2404
R.10009.04.01.02 | W_R.10009.04.01.02: E Damage Claims Cap Writeoff | Electric |  |  |  | Other | -2517619.42 | 0 | -2517619.42
R.10009.05.01.01 | W_R.10009.05.01.01: E Emergency NonOutage OH Repl Dist | Electric | Emergent Electric | Programmatic: Programmatic | 4 - Emergent Work | Operations | -2406256.4756 | -3642840.7176 | 1236584.2421
R.10009.05.01.02 | W_R.10009.05.01.02: E Emergency NonOutage OH Repl Trans | Electric | Emergent Electric | Programmatic: Programmatic | 4 - Emergent Work | Operations | -2372040.15 | -1756507.0784 | -615533.0716
R.10009.05.01.03 | W_R.10009.05.01.03: E Emergency NonOutage UG Repl Dist | Electric | Emergent Electric | Programmatic: Programmatic | 4 - Emergent Work | Operations | -2139720.5425 | -1606939.8125 | -532780.7301
R.10009.05.02.01 | W_R.10009.05.02.01: E Emergency OH Replacement Trans | Electric | Emergent Electric | Programmatic: Programmatic | 4 - Emergent Work | Operations | -6318232.3242 | -1189417.4402 | -5128814.884
R.10009.05.02.02 | W_R.10009.05.02.02: E Emergency Outage OH Replacement Dist | Electric | Emergent Electric | Programmatic: Programmatic | 4 - Emergent Work | Operations | -25478963.85 | -16869284.0575 | -8609679.7925
R.10009.05.02.03 | W_R.10009.05.02.03: E Emergency Outage UG Replacement Dist | Electric | Emergent Electric | Programmatic: Programmatic | 4 - Emergent Work | Operations | -30365295.7753 | -18644248.9137 | -11721046.8616
R.10009.05.02.04 | W_R.10009.05.02.04: E Unplanned OH Distribution Abnormals | Electric | Emergent Electric | Programmatic: Programmatic | 4 - Emergent Work | Operations | -4177086.3413 | -5064605.6706 | 887519.3293
R.10009.05.02.05 | W_R.10009.05.02.05: E Unplanned UG Distribution Abnormals | Electric | Emergent Electric | Programmatic: Programmatic | 4 - Emergent Work | Operations | -6532201.7106 | -77270.4087 | -6454931.3019
R.10009.07.01.01 | W_R.10009.07.01.01: E OH System Capacity New Dist | Electric | Capacity Electric | Programmatic: Programmatic |  | Operations | 5362.99 | 0 | 5362.99
R.10009.07.01.03 | W_R.10009.07.01.03: E UG System Capacity New Dist | Electric | Capacity Electric | Programmatic: Programmatic |  | Operations | -2746811.24 | -534307.1978 | -2212504.0422
R.10009.07.01.07 | W_R.10009.07.01.07: E System Planning Software | Electric | Projected | Projected | 9 - Projected | Operations | -43840.73 | 0 | -43840.73
R.10009.07.03.01 | W_R.10009.07.03.01: E OH UG System Improv Opport New Dist | Electric | PI Electric | Programmatic Customer Driven | 3E - CIAC, NCC, PI | Operations | -289356.6065 | -23122.4962 | -266234.1104
R.10009.08.01.02 | W_R.10009.08.01.02: E UG Cable Remediation Dist | Electric | Grid Modernization | Programmatic: Programmatic | 6E - Grid Mod | Operations | -13184031.8736 | -13489572.6176 | 305540.7439
R.10009.08.01.07 | W_R.10009.08.01.07: E UG Cable Remediation Progr IPM | Electric | Grid Modernization | Programmatic: Programmatic | 6E - Grid Mod | Operations | -26591228.1663 | 0 | -26591228.1663
R.10009.08.02.05 | W_R.10009.08.02.05: E OH Clearance Alley Syst Dist | Electric | Grid Modernization | Programmatic: Programmatic | 6E - Grid Mod | Operations | -8130037.1593 | -46177442.5088 | 38047405.3495
R.10009.08.02.07 | W_R.10009.08.02.07: E OH Sys Rel Upgrades Outage Dist | Electric | Grid Modernization | Programmatic: Programmatic | 6E - Grid Mod | Operations | -1991093.3701 | -12358911.5378 | 10367818.1677
R.10009.08.02.09 | W_R.10009.08.02.09: E OH Syst Rel Upgrades Rebuild Dist | Electric | Grid Modernization | Programmatic: Programmatic | 6E - Grid Mod | Operations | -4644157.8319 | -3468753.4409 | -1175404.3909
R.10009.08.02.10 | W_R.10009.08.02.10: E OH Syst Rel Upgrades UG Convers Dist | Electric | Grid Modernization | Programmatic: Programmatic | 6E - Grid Mod | Operations | -13874827.5994 | -2743343.3117 | -11131484.2877
R.10009.08.02.11 | W_R.10009.08.02.11: E OH Syst Rel Upgr Gang OP Switches Dist | Electric | Projected | Projected | 9 - Projected | Operations | -135145.17 | 0 | -135145.17
R.10009.08.02.12 | W_R.10009.08.02.12: E OH Syst Rel Upgr Reclosers Dist | Electric | Projected | Projected | 9 - Projected | Operations | -3089040.79 | -2883351.1758 | -205689.6142
R.10009.08.02.14 | W_R.10009.08.02.14: E OH Syst Rel Upgr Tree WirE Dist | Electric | Grid Modernization | Programmatic: Programmatic | 6E - Grid Mod | Operations | -19054204.9779 | -11728176.8471 | -7326028.1308
R.10009.08.02.15 | W_R.10009.08.02.15: E OH Syst Rel Upgr Fusesaver Dist | Electric | Grid Modernization | Programmatic: Programmatic | 6E - Grid Mod | Operations | -1311998.2015 | -2842255.0084 | 1530256.8069
R.10009.08.02.17 | W_R.10009.08.02.17: E OH System Capacity Upgrade Dist | Electric | Grid Modernization | Programmatic: Programmatic | 6E - Grid Mod | Operations | -11013199.7598 | -598051.2745 | -10415148.4853
R.10009.08.02.19 | W_R.10009.08.02.19: E OH System Reliability Upgrades Trans | Electric | Projected | Projected | 9 - Projected | Operations | -140467.14 | -343.5899 | -140123.5501
R.10009.08.02.22 | W_R.10009.08.02.22: E 6 Copper Open Wire 2nd Repl Dist | Electric | Grid Modernization | Programmatic: Programmatic | 6E - Grid Mod | Operations | -963883.7798 | 0 | -963883.7798
R.10009.08.02.24 | W_R.10009.08.02.24: E Sedro Mar Pt 230 Remediate Underbuild | Electric | Projected | Projected | 9 - Projected | Operations | -20759.32 | 0 | -20759.32
R.10009.08.02.25 | W_R.10009.08.02.25: E UG Syst Rel Upgrades Dist | Electric | Grid Modernization | Programmatic: Programmatic | 6E - Grid Mod | Operations | -15526234.392 | -161747.6434 | -15364486.7486
R.10009.08.02.28 | W_R.10009.08.02.28: E UG System Capacity Upgrade Dist | Electric | Projected | Projected | 9 - Projected | Operations | -944312.6497 | -2439.4245 | -941873.2253
R.10009.08.03.01 | W_R.10009.08.03.01: E Fish And Wildlife Program Dist | Electric |  |  |  | Other | -277293.5874 | 0 | -277293.5874
R.10009.08.05.02 | W_R.10009.08.05.02: E Emergent Pole Replacement Dist | Electric | Emergent Electric | Programmatic: Programmatic | 4 - Emergent Work | Operations | -4360134.8087 | -1208886.2842 | -3151248.5245
R.10009.08.05.03 | W_R.10009.08.05.03: E Emergent Pole Replacement Trans | Electric | Emergent Electric | Programmatic: Programmatic | 4 - Emergent Work | Operations | -38573.47 | -219797.8814 | 181224.4114
R.10009.08.05.05 | W_R.10009.08.05.05: E Pole Replacement Plan Dist | Electric | Grid Modernization | Programmatic: Programmatic | 6E - Grid Mod | Operations | -6867195.116 | -27730275.613 | 20863080.4969
R.10009.08.05.07 | W_R.10009.08.05.07: E Pole Replacement Plan Trans | Electric | Grid Modernization | Programmatic: Programmatic | 6E - Grid Mod | Operations | -11986074.2261 | -5896473.0105 | -6089601.2156
R.10009.08.05.16 | W_R.10009.08.05.16: E Pole Inspection and Restoration Dist | Electric | Grid Modernization | Programmatic: Programmatic | 6E - Grid Mod | Operations | -1037790.98 | -132602.5847 | -905188.3953
R.10009.08.05.17 | W_R.10009.08.05.17: E Pole Inspection and Restoration Trans | Electric | Grid Modernization | Programmatic: Programmatic | 6E - Grid Mod | Operations | -115430.08 | -8484.2529 | -106945.8271
R.10009.12.01.01 | W_R.10009.12.01.01: C AMI Network Installations Gen Plant | Common | AMI Meters and Modules Deployment | Programmatic: Programmatic | 1 - AMI | AMI | -80813.69 | 0 | -80813.69
R.10009.12.01.03 | W_R.10009.12.01.03: E AMI Netwrk Installtion TransDist | Electric | AMI Meters and Modules Deployment | Programmatic: Programmatic | 1 - AMI | AMI | -100838.31 | 0 | -100838.31
R.10009.12.01.04 | W_R.10009.12.01.04: E AMI Electric Meter Deployment | Electric | AMI Meters and Modules Deployment | Programmatic: Programmatic | 1 - AMI | AMI | -27840619.7719 | -104544526.2965 | 76703906.5246
R.10009.12.01.05 | W_R.10009.12.01.05: G AMI Gas Module Deployment | Gas | AMI Meters and Modules Deployment | Programmatic: Programmatic | 1 - AMI | AMI | -6439970.9736 | -62537804.7206 | 56097833.747
R.10009.12.01.08 | W_R.10009.12.01.08: E Opt Out AMR to NCM Capital Exch | Electric | Projected | Projected | 9 - Projected | Operations | -7171.48 | 61120.2968 | -68291.7768
R.10009.12.01.09 | W_R.10009.12.01.09: G Opt Out AMI to NCM Capital Exch | Gas | Projected | Projected | 9 - Projected | Operations | -270.4364 | -2400 | 2129.5636
R.10009.12.03.01 | W_R.10009.12.03.01: E Distribution Automation Dist | Electric | Grid Modernization | Programmatic: Programmatic | 6E - Grid Mod | Operations | -4055737.6486 | -9717623.2223 | 5661885.5737
R.10009.14.04.01 | W_R.10009.14.04.01: E Substation Replacement SpcC Dist | Electric | Grid Modernization | Programmatic: Programmatic | 6E - Grid Mod | Operations | -23434.89 | 0 | -23434.89
R.10009.14.05.02 | W_R.10009.14.05.02: E Emergent Substation Replacement Dist | Electric | Emergent Electric | Programmatic: Programmatic | 4 - Emergent Work | Operations | -6192262.18 | -6277278.1563 | 85015.9763
R.10009.14.05.03 | W_R.10009.14.05.03: E Emergent Substation Replacement Trans | Electric | Emergent Electric | Programmatic: Programmatic | 4 - Emergent Work | Operations | -2189643.1 | -2472772.7424 | 283129.6424
R.10009.14.05.06 | W_R.10009.14.05.06: E Substation Reliability Dist | Electric | Grid Modernization | Programmatic: Programmatic | 6E - Grid Mod | Operations | -10412305.5072 | -14286949.0973 | 3874643.5901
R.10009.14.05.07 | W_R.10009.14.05.07: E Subs Replacement Fuses Dist | Electric | Grid Modernization | Programmatic: Programmatic | 6E - Grid Mod | Operations | -15464.2492 | -12557.4554 | -2906.7937
R.10009.14.05.09 | W_R.10009.14.05.09: E Substation Reliability Trans | Electric | Projected | Projected | 9 - Projected | Operations | -1854282.261 | 0 | -1854282.261
R.10009.14.07.01 | W_R.10009.14.07.01: E Subs Replacement Breaker Replcmt Trans | Electric | Grid Modernization | Programmatic: Programmatic | 6E - Grid Mod | Operations | -8155.22 | -282885.4511 | 274730.2311
R.10009.17.01.01 | W_R.10009.17.01.01: E Mazama Pcket Gopher Habitat Mitigation | Electric | Projected | Projected | 9 - Projected | Operations | -106259.76 | -350000 | 243740.24
R.10011.01.01.03 | W_R.10011.01.01.03: G Gas System Monitoring Equip Replc | Gas | Gas Modernization | Programmatic: Programmatic | 6G - Gas Mod | Operations | -453596.06 | -1187215.4834 | 733619.4234
R.10011.01.01.04 | W_R.10011.01.01.04: G Gauges Sems Dist | Gas | Gas Modernization | Programmatic: Programmatic | 6G - Gas Mod | Operations | -142381.01 | -188614.8299 | 46233.8199
R.10011.01.01.06 | W_R.10011.01.01.06: G Remote Telemetry Units Dist | Gas | Projected | Projected | 9 - Projected | Operations | -122749.41 | 0 | -122749.41
R.10011.01.01.07 | W_R.10011.01.01.07: G Williams Pipeline Equipment Upgrades | Gas | Major Projects Gas | Programmatic: Programmatic | 7G - Maj Proj | Operations | -320771.7 | -576037.5545 | 255265.8545
R.10012.01.01.01 | W_R.10012.01.01.01: G Altered Modified Comm Ind Mains | Gas | Customer Construction Gas | Programmatic Customer Driven | 3G - CIAC, NCC, PI | Operations | -1472992.01 | 0 | -1472992.01
R.10012.01.01.02 | W_R.10012.01.01.02: G Altered Modified Comm Ind Service | Gas | Customer Construction Gas | Programmatic Customer Driven | 3G - CIAC, NCC, PI | Operations | -2093679.8505 | -19817.8377 | -2073862.0128
R.10012.01.02.01 | W_R.10012.01.02.01: G Altered Modified Residential Mains | Gas | Customer Construction Gas | Programmatic Customer Driven | 3G - CIAC, NCC, PI | Operations | -322903.4242 | -34389.0369 | -288514.3873
R.10012.01.02.02 | W_R.10012.01.02.02: G Altered Modified Residential Services | Gas | Customer Construction Gas | Programmatic Customer Driven | 3G - CIAC, NCC, PI | Operations | -11895177.7803 | -17159.5113 | -11878018.269
R.10012.02.01.01 | W_R.10012.02.01.01: G 5 Yr Gas Refundable CIAC | Gas | CIAC - Gas | Programmatic Customer Driven | 3G - CIAC, NCC, PI | Operations | 198563.8 | 3005100 | -2806536.2
R.10012.03.01.01 | W_R.10012.03.01.01: G Commercial Industrial Mains | Gas | Customer Construction Gas | Programmatic Customer Driven | 3G - CIAC, NCC, PI | Operations | -10504158.7278 | -177108.115 | -10327050.6128
R.10012.03.02.01 | W_R.10012.03.02.01: G Multi Family Mains | Gas | Customer Construction Gas | Programmatic Customer Driven | 3G - CIAC, NCC, PI | Operations | -2768771.4624 | -35940.9556 | -2732830.5068
R.10012.03.03.01 | W_R.10012.03.03.01: G Plats Mains | Gas | Customer Construction Gas | Programmatic Customer Driven | 3G - CIAC, NCC, PI | Operations | -8307148.06 | -337792.2525 | -7969355.8075
R.10012.03.03.02 | W_R.10012.03.03.02: G Residential Mains | Gas | Customer Construction Gas | Programmatic Customer Driven | 3G - CIAC, NCC, PI | Operations | -3109124.8302 | -26571.9159 | -3082552.9142
R.10012.04.01.01 | W_R.10012.04.01.01: G Commercial Industrial Service | Gas | Customer Construction Gas | Programmatic Customer Driven | 3G - CIAC, NCC, PI | Operations | -7672221.6546 | -7135.7059 | -7665085.9487
R.10012.04.02.01 | W_R.10012.04.02.01: G Multi Family Service | Gas | Customer Construction Gas | Programmatic Customer Driven | 3G - CIAC, NCC, PI | Operations | -3195490.048 | -497.0836 | -3194992.9644
R.10012.04.03.02 | W_R.10012.04.03.02: G Residential Services | Gas | Customer Construction Gas | Programmatic Customer Driven | 3G - CIAC, NCC, PI | Operations | -23735597.6994 | -335.9715 | -23735261.7279
R.10012.04.03.03 | W_R.10012.04.03.03: G Residential Services In Plat Dev | Gas | Customer Construction Gas | Programmatic Customer Driven | 3G - CIAC, NCC, PI | Operations | -7990777.4569 | 0 | -7990777.4569
R.10012.06.01.01 | W_R.10012.06.01.01: G Gas Retire Only No Additions | Gas | Customer Construction Gas | Programmatic Customer Driven | 3G - CIAC, NCC, PI | Operations | -1650613.8911 | 0 | -1650613.8911
R.10013.01.01.01 | W_R.10013.01.01.01: G Cust Driven Relocate Reimburse Dist | Gas | Customer Construction Gas | Programmatic Customer Driven | 3G - CIAC, NCC, PI | Operations | -121043.49 | -15613608.8795 | 15492565.3895
R.10013.04.01.01 | W_R.10013.04.01.01: G PI Driven Relocate NonReimb Dist | Gas | PI Gas | Programmatic Customer Driven | 3G - CIAC, NCC, PI | Operations | -35901727.9023 | -111550.1045 | -35790177.7978
R.10013.04.01.02 | W_R.10013.04.01.02: G PI Driven Relocate Reimb Dist | Gas | PI Gas | Programmatic Customer Driven | 3G - CIAC, NCC, PI | Operations | -1060031.0369 | -22867.5443 | -1037163.4926
R.10013.04.01.04 | W_R.10013.04.01.04: G Sound Transit Reimburse | Gas | Projected | Projected | 9 - Projected | Operations | -1333382.66 | 0 | -1333382.66
R.10013.04.01.06 | W_R.10013.04.01.06: G WSDOT Fish Passage Relocation | Gas | Projected | Projected | 9 - Projected | Operations | -619359.33 | 0 | -619359.33
R.10013.05.01.01 | W_R.10013.05.01.01: G Seattle Core Alaskan Way Viaduct | Gas | PI Gas | Programmatic Customer Driven | 3G - CIAC, NCC, PI | Operations | 9426.9 | 0 | 9426.9
R.10013.05.01.02 | W_R.10013.05.01.02: G Seattle Core IP Main | Gas | Projected | Projected | 9 - Projected | Operations | -794.06 | 0 | -794.06
R.10013.06.01.01 | W_R.10013.06.01.01: G Sound Transit Dist | Gas | Projected | Projected | 9 - Projected | Operations | -336.5 | 0 | -336.5
R.10013.07.01.01 | W_R.10013.07.01.01: G Relocate Bulk Dist Like Kind Dist | Gas | PI Gas | Programmatic Customer Driven | 3G - CIAC, NCC, PI | Operations | -391890.3642 | -6744.3421 | -385146.0221
R.10013.07.01.02 | W_R.10013.07.01.02: G System Improv Opport Dist | Gas | PI Gas | Programmatic Customer Driven | 3G - CIAC, NCC, PI | Operations | -69817.07 | -2770.3444 | -67046.7256
R.10014.01.01.01 | W_R.10014.01.01.01: G Swarr Propane Air Plant Upgrades | Gas | Major Projects Gas | Programmatic: Programmatic | 7G - Maj Proj | Operations | -2876519.46 | 0 | -2876519.46
R.10015.01.01.01 | W_R.10015.01.01.01: G CP System Improv Main With Serv Dist | Gas | Emergent Gas | Programmatic: Programmatic | 4 - Emergent Work | Operations | -184180.97 | -429333.6507 | 245152.6807
R.10015.01.01.02 | W_R.10015.01.01.02: G CP System Improv Service Dist | Gas | Emergent Gas | Programmatic: Programmatic | 4 - Emergent Work | Operations | -2767569.487 | -3578145.4171 | 810575.9301
R.10015.01.01.03 | W_R.10015.01.01.03: G CP System Improv Dist | Gas | Emergent Gas | Programmatic: Programmatic | 4 - Emergent Work | Operations | -924204.17 | -1307244.2242 | 383040.0542
R.10015.01.01.05 | W_R.10015.01.01.05: G Emergent CP System Improv Dist | Gas | Emergent Gas | Programmatic: Programmatic | 4 - Emergent Work | Operations | -2180001.2442 | -1506973.3175 | -673027.9267
R.10015.02.01.02 | W_R.10015.02.01.02: G Damage Claims Cap Writeoff | Gas |  |  |  | Other | -123834.79 | 0 | -123834.79
R.10015.03.01.01 | W_R.10015.03.01.01: G DIMP Brdg Sld Dist Unmaintain Facil | Gas | Gas Modernization | Programmatic: Programmatic | 6G - Gas Mod | Operations | -352107.1729 | -625050.2662 | 272943.0934
R.10015.03.02.01 | W_R.10015.03.02.01: G DIMP Mobile Home Encroachment Program | Gas | Gas Modernization | Programmatic: Programmatic | 6G - Gas Mod | Operations | -752419.5402 | -624510.634 | -127908.9062
R.10015.03.04.01 | W_R.10015.03.04.01: G DIMP Dupont Pipe Repl Main With Serv | Gas | Pipe Replacement | Programmatic: Programmatic | 8 - Pipe Replacement | Operations | -49271824.5099 | -44009686.2226 | -5262138.2873
R.10015.03.04.02 | W_R.10015.03.04.02: G DIMP Older Stw Repl Main With Service | Gas | Gas Modernization | Programmatic: Programmatic | 6G - Gas Mod | Operations | -1430500.63 | -3749768.582 | 2319267.952
R.10015.03.04.03 | W_R.10015.03.04.03: G DIMP Older Stw Repl Service Only | Gas | Gas Modernization | Programmatic: Programmatic | 6G - Gas Mod | Operations | -651433.8309 | -1449293.4231 | 797859.5922
R.10015.03.06.01 | W_R.10015.03.06.01: G DIMP Legacy Cross Bore Inspection Dist | Gas | Pipe Replacement | Programmatic: Programmatic | 8 - Pipe Replacement | Operations | -95795.2 | 0 | -95795.2
R.10015.03.07.01 | W_R.10015.03.07.01: G DIMP Continuing Surveillance Other | Gas | Gas Modernization | Programmatic: Programmatic | 6G - Gas Mod | Operations | -62919.4371 | -531422.5829 | 468503.1458
R.10015.03.07.03 | W_R.10015.03.07.03: G DIMP Shallow Serv and Main Repl | Gas | Gas Modernization | Programmatic: Programmatic | 6G - Gas Mod | Operations | -2695663.9241 | -2702523.93 | 6860.0059
R.10015.03.08.01 | W_R.10015.03.08.01: G DIMP Buried MSA Serv Or Riser Repl Opp | Gas | Gas Modernization | Programmatic: Programmatic | 6G - Gas Mod | Operations | -824.92 | -2025.3927 | 1200.4727
R.10015.03.09.01 | W_R.10015.03.09.01: G DIMP Preventative Maint Facilities | Gas | Gas Modernization | Programmatic: Programmatic | 6G - Gas Mod | Operations | -1967967.6142 | -3267068.2415 | 1299100.6272
R.10015.03.09.03 | W_R.10015.03.09.03: G DIMP Preventive Maint Dist Reg Dist | Gas | Gas Modernization | Programmatic: Programmatic | 6G - Gas Mod | Operations | -3935224.7 | -3683508.9904 | -251715.7096
R.10015.03.09.07 | W_R.10015.03.09.07: G DIMP Preventive Maint Farm Taps Dist | Gas | Gas Modernization | Programmatic: Programmatic | 6G - Gas Mod | Operations | -201883.58 | -429745.2302 | 227861.6502
R.10015.03.09.14 | W_R.10015.03.09.14: G Idle Riser Remediation | Gas | Gas Modernization | Programmatic: Programmatic | 6G - Gas Mod | Operations | -712659.3502 | -4103148.8046 | 3390489.4545
R.10015.03.09.15 | W_R.10015.03.09.15: G Buried Meter Riser Replacement | Gas | Pipe Replacement | Programmatic: Programmatic | 8 - Pipe Replacement | Operations | -6038892.2231 | -5653600.1325 | -385292.0905
R.10015.03.10.02 | W_R.10015.03.10.02: G-DIMP Unmaintainable STW Main in Casing | Gas | Projected | Projected | 9 - Projected | Operations | -148211.1512 | 0 | -148211.1512
R.10015.03.11.01 | W_R.10015.03.11.01: G DIMP Guard Posts | Gas | Gas Modernization | Programmatic: Programmatic | 6G - Gas Mod | Operations | -42149.3642 | -180175.3019 | 138025.9376
R.10015.04.01.02 | W_R.10015.04.01.02: G Leak Repair Main | Gas | Projected | Projected | 9 - Projected | Operations | -2315739.2356 | -3754567.2705 | 1438828.0349
R.10015.04.01.03 | W_R.10015.04.01.03: G Leak Repair Service | Gas | Emergent Gas | Programmatic: Programmatic | 4 - Emergent Work | Operations | -352751.5893 | -1026506.76 | 673755.1707
R.10015.04.01.04 | W_R.10015.04.01.04: G Scattered Short Main Rehab | Gas | Emergent Gas | Programmatic: Programmatic | 4 - Emergent Work | Operations | -1279814.0942 | -2029436.6605 | 749622.5662
R.10015.04.01.05 | W_R.10015.04.01.05: G Service Replacement Misc | Gas | Emergent Gas | Programmatic: Programmatic | 4 - Emergent Work | Operations | -10043107.2995 | -9056163.8388 | -986943.4607
R.10015.04.01.06 | W_R.10015.04.01.06: G Sewer Cross Bore Repair Main | Gas | Emergent Gas | Programmatic: Programmatic | 4 - Emergent Work | Operations | -240389.55 | -297924.5009 | 57534.9509
R.10015.04.01.07 | W_R.10015.04.01.07: G Sewer Cross Bore Repair Service | Gas | Emergent Gas | Programmatic: Programmatic | 4 - Emergent Work | Operations | -4787.19 | -148439.5139 | 143652.3239
R.10015.04.01.09 | W_R.10015.04.01.09: G Gas Work Release Service | Gas | Emergent Gas | Programmatic: Programmatic | 4 - Emergent Work | Operations | -248141.6942 | -1205412.4115 | 957270.7172
R.10015.04.01.12 | W_R.10015.04.01.12: G Nonhaz Main Repair Methane PRP | Gas | Pipe Replacement | Programmatic: Programmatic | 8 - Pipe Replacement | Operations | -3825169.73 | 0 | -3825169.73
R.10015.04.01.13 | W_R.10015.04.01.13: G Nonhaz Service Repair Methane PRP | Gas | Pipe Replacement | Programmatic: Programmatic | 8 - Pipe Replacement | Operations | -661462.4956 | 0 | -661462.4956
R.10015.05.01.01 | W_R.10015.05.01.01: G System Capacity New Dist | Gas | Projected | Projected | 9 - Projected | Operations | -1530.8 | -1176.159 | -354.641
R.10015.06.01.02 | W_R.10015.06.01.02: G Odorizer Componant Repl Bulk Dist | Gas | Gas Modernization | Programmatic: Programmatic | 6G - Gas Mod | Operations | -30357.3 | -192004.5623 | 161647.2623
R.10015.06.01.04 | W_R.10015.06.01.04: G System Capacity Upgrade Bulk Dist | Gas | Capacity Gas | Programmatic: Programmatic |  | Operations | -2580429.9736 | -8824690.6818 | 6244260.7081
R.10015.06.01.05 | W_R.10015.06.01.05: G System Capacity Upgrade Dist | Gas | Capacity Gas | Programmatic: Programmatic |  | Operations | -3239929.69 | -4989828.6342 | 1749898.9442
R.10015.07.01.01 | W_R.10015.07.01.01: G Gas Lightups Clearing | Gas | Projected | Projected | 9 - Projected | Operations | -346.0264 | 0 | -346.0264
R.10015.08.02.02 | W_R.10015.08.02.02: G Alternative Fuels | Gas | Projected | Projected | 9 - Projected | Operations | -161561.24 | -6458825.681 | 6297264.441
R.10019.01.01.01 | W_R.10019.01.01.01: E Port Madison Subs | Electric | Projected | Projected | 9 - Projected | Operations | -380747.7738 | 0 | -380747.7738
R.10019.01.01.02 | W_R.10019.01.01.02: Bainbridge Trans WIN-MUR Loop | Electric | Bainbridge Tlines Trans | Specific: Specific | 2 - Bainbridge | Operations | -617924.7517 | -1131175.8881 | 513251.1364
R.10024.01.01.04 | W_R.10024.01.01.04: G AMR Operations | Gas | Projected | Projected | 9 - Projected | Operations | -17769.7636 | -1504618.5 | 1486848.7364
R.10024.01.01.05 | W_R.10024.01.01.05: E AMR Operations | Electric | Projected | Projected | 9 - Projected | Operations | -62851.0438 | 0 | -62851.0438
R.10024.01.01.07 | W_R.10024.01.01.07: E Opt Out AMR to NCM Capital Exch | Electric | Projected | Projected | 9 - Projected | Operations | -323491.5812 | -5483.3922 | -318008.189
R.10024.01.01.09 | W_R.10024.01.01.09: G AMI Operations | Gas | Projected | Projected | 9 - Projected | Operations | -453634.8738 | -974194.6208 | 520559.747
R.10024.02.01.01 | W_R.10024.02.01.01: G NonRegistering Meters Dist | Gas | Emergent Gas | Programmatic: Programmatic | 4 - Emergent Work | Operations | -453746.5811 | -189383.4311 | -264363.1499
R.10024.02.01.03 | W_R.10024.02.01.03: G Periodic Meter Changeout IMO Dist | Gas | Gas Modernization | Programmatic: Programmatic | 6G - Gas Mod | Operations | -848270.2687 | -1331904.7345 | 483634.4658
R.10031.01.01.02 | W_R.10031.01.01.02: E Lake Hills Phantom Lake 115Kv Tline | Electric | Major Projects Electric | Programmatic: Programmatic | 7E - Maj Proj | Operations | -624116.57 | 0 | -624116.57
R.10031.03.01.01 | W_R.10031.03.01.01: E Sammamish Juanita 115Kv Tline | Electric | Sammamish Juanita 115Kv Tline | Specific: Specific | 10 - Sammamish | Operations | -44028432.8917 | -9047247.237 | -34981185.6547
R.10033.01.01.03 | W_R.10033.01.01.03: E Small Tool Electric Operations Tool | Electric | Projected | Projected | 9 - Projected | Operations | -4173800.7 | -2044207 | -2129593.7
R.10033.01.01.09 | W_R.10033.01.01.09: G Small Tool Gas Operations Tool | Gas | Projected | Projected | 9 - Projected | Operations | -1748850.52 | -1370746 | -378104.52
R.10033.02.01.01 | W_R.10033.02.01.01: C Operational Training ISR Program | Common | Projected | Projected | 9 - Projected | Operations | -2278.79 | -500000 | 497721.21
R.10036.02.01.01 | W_R.10036.02.01.01: C Capitalization of Real Estate Permits | Electric | Projected | Projected | 9 - Projected | Operations | -413845.28 | -800000 | 386154.72
R.10036.03.01.01 | W_R.10036.03.01.01: C Transient Deterrent | Common | Projected | Projected | 9 - Projected | Operations | -14588.58 | -600000 | 585411.42
R.10039.02.01.01 | W_R.10039.02.01.01: E Buckley Substation Feeder | Electric | Major Projects Electric | Programmatic: Programmatic | 7E - Maj Proj | Operations | -8740.1427 | -33464.0427 | 24723.9
R.10039.02.01.02 | W_R.10039.02.01.02: E Buckley Substation Sub | Electric | Major Projects Electric | Programmatic: Programmatic | 7E - Maj Proj | Operations | -589047.8021 | -348759.9182 | -240287.8839
R.10039.02.01.06 | W_R.10039.02.01.06: E Electr Enum 55Kv To 115Kv Fiber | Electric | Major Projects Electric | Programmatic: Programmatic | 7E - Maj Proj | Operations | -332803.5 | 0 | -332803.5
R.10045.01.01.01 | W_R.10045.01.01.01: E Talbot Asbury Ug 115Kv Repl Tline | Electric | Major Projects Electric | Programmatic: Programmatic | 7E - Maj Proj | Operations | -2275718.28 | 0 | -2275718.28
R.10051.02.01.01 | W_R.10051.02.01.01: E Thurston Transmission Capacity | Electric | Thurston Transmission Capacity | Specific: Specific | 11 - Thurston | Operations | -19661839.26 | -10173066.6069 | -9488772.6531
R.10054.01.01.01 | W_R.10054.01.01.01: E Bellingham Sedro 4 115Kv Recond Tline | Electric | Major Projects Electric | Programmatic: Programmatic | 7E - Maj Proj | Operations | -4427.79 | -1243996.6522 | 1239568.8622
R.10059.02.01.02 | W_R.10059.02.01.02: E Circuit Enablement EV | Electric | EV Circuit | Programmatic: Programmatic |  | Operations | -1442703.394 | -7165996.376 | 5723292.982
R.10059.03.01.01 | W_R.10059.03.01.01: E Resilience Enhancement Substation | Electric | Resilience Enhancement | Programmatic: Programmatic |  | Operations | -1258562.329 | -4266596.5265 | 3008034.1975
R.10059.04.01.01 | W_R.10059.04.01.01: E Wildfire Resilience | Electric | Projected | Projected | 9 - Projected | Operations | -3266.9764 | -1885788.52 | 1882521.5436
R.10060.01.01.01 | W_R.10060.01.01.01: G Vashon Marine Crossing | Gas | Projected | Projected | 9 - Projected | Operations | -1024585.86 | 0 | -1024585.86
R.10060.01.01.02 | W_R.10060.01.01.02: G Vashon Interim Supply at Gig Harbor | Gas | Marine Crossing | Specific: Specific |  | Operations | -110540.056 | 0 | -110540.056
X.10003.01.01.01 | W_X.10003.01.01.01: Street and Area Lighting Services | Electric |  |  |  | NP&S | -2774952.2052 | -4757737.4334 | 1982785.2283
X.10003.01.03.01 | W_X.10003.01.03.01: Street Light Replacement | Electric |  |  |  | NP&S | -1813298.1 | -1610902.4702 | -202395.6298
X.10003.01.03.02 | W_X.10003.01.03.02: Smart Street Lighting | Electric |  |  |  | NP&S | -2995082.71 | -229013.2765 | -2766069.4335
X.10005.01.01.01 | W_X.10005.01.01.01: Wireless and Wireline Construction | Electric |  |  |  | NP&S | -1026939.635 | -945078.6899 | -81860.9451
X.10006.01.01.01 | W_X.10006.01.01.01: Customer Sited Energy Storage Pilot | Electric |  |  |  | NP&S | 140154.2 | 0 | 140154.2
X.10006.02.02.02 | W_X.10006.02.02.02: EV Charging Program Infrastructure | Electric |  |  |  | NP&S | -2297632.6732 | -6022703.3382 | 3725070.665
X.10006.03.01.05 | W_X.10006.03.01.05: Community Solar Program 2022-25 | Electric |  |  |  | NP&S | -1829357.09 | 0 | -1829357.09
X.10007.01.01.01 | W_X.10007.01.01.01: Covid 19 Work for WUTC Order | Common |  |  |  | NP&S | -744122.07 | 0 | -744122.07
F.10002.01.16.01 | Placeholder WBS 53b: DER Circuit Enablemnt Virtual Power Plan | Electric |  |  |  | IT |  | -12011.9488 | 12011.9488
X.10006.05.01.01 | W_K.10038.02.01.01: Rooftop Solar Program:DER Solar Project and Programs CEIP | Electric |  |  |  | NP&S |  | -3380000 | 3380000
R.10059.02.01.03 | PLACEHOLDER WBS 38b: E Volt/Var Optimization | Electric |  |  |  | Operations |  | -779493.8976 | 779493.8976
F.10002.01.30.01 | PLACEHOLDER WBS 31b: Hosting Capacity and Customer Portal | Electric |  |  |  | IT |  | -194225.0976 | 194225.0976
PLACEHOLDER WBS 24 | PLACEHOLDER WBS 7b: Demand Response transferred to Placeholder WBS 24 | Electric |  |  |  | NP&S |  | -321149.785 | 321149.785
F.10002.01.28.01 | PLACEHOLDER WBS 88b: DER Innovation Process CEIP | Electric |  |  |  | NP&S |  | -409619 | 409619
K.10038.01.01.01 | W_K.10038.01.01.01: Cust Sited Energy Storage Demos CEIP | Electric |  |  |  | NP&S |  | -1040000 | 1040000
C.10002.12.01.01 | W_C.10002.12.01.01: Hybrid Working Transition to 50 Percent | Common |  |  |  | Facilities | -1045825.58 | 0 | -1045825.58
C.10003.01.01.03 | W_C.10003.01.01.03: Furniture Fixtures HVAC Refresh | Common |  |  |  | Facilities | -3014945.66 | 0 | -3014945.66
C.10006.01.01.04 | W_C.10006.01.01.04: EEI Fleet Electrical Commitment | Electric |  |  |  | Facilities | -348942.11 | 0 | -348942.11
F.10002.01.20.01 | W_F.10002.01.20.01: Front Office Enhancements | Electric |  |  |  | IT | -2216233.57 | 0 | -2216233.57
F.10002.01.26.01 | W_F.10002.01.26.01: Urbint Enhancement | Gas |  |  |  | IT | -259777.62 | -1556639.0986 | 1296861.4786
F.10002.01.31.01 | W_F.10002.01.31.01: Sendout Replacement | Gas |  |  |  | IT | -211064.18 | 0 | -211064.18
F.10002.06.05.02 | W_F.10002.06.05.02: PSE 2030 Digital Experience Non CEIP | Common |  |  |  | IT | -278769.55 | -2075710.4702 | 1796940.9202
F.10002.06.08.04 | W_F.10002.06.08.04: Billing Correction Automation | Common |  |  |  | IT | -3229430.16 | 0 | -3229430.16
F.10002.07.03.01 | W_F.10002.07.03.01: GIS Upgrade Smallworld | Common |  |  |  | IT | -1534151.84 | 0 | -1534151.84
F.10002.07.04.01 | W_F.10002.07.04.01: Streetlight New Business DB SAP Conversn | Electric |  |  |  | IT | -143896.11 | 0 | -143896.11
F.10002.07.08.01 | W_F.10002.07.08.01: eGRC Archer | Common |  |  |  | IT | -944878.86 | 0 | -944878.86
F.10003.04.01.01 | W_F.10003.04.01.01: Digital Workplace Transformation | Common |  |  |  | IT | -957357.45 | 0 | -957357.45
F.10015.01.03.02 | W_F.10015.01.03.02: Oracle Upgrades 2023 | Common |  |  |  | IT | -53665.39 | 0 | -53665.39
F.10015.02.24.01 | W_F.10015.02.24.01: PI Vision Suite Migration | Common |  |  |  | IT | -647845.66 | 0 | -647845.66
F.10015.04.07.01 | W_F.10015.04.07.01: LoadSEER Non-production Environmnt Purch | Electric |  |  |  | IT | -175823.08 | 0 | -175823.08
F.10015.05.04.02 | W_F.10015.05.04.02: Annual Quality Framework Enhancemnt 2023 | Common |  |  |  | IT | -175716.3 | 0 | -175716.3
F.10015.05.10.01 | W_F.10015.05.10.01: Work Manager Upgrade | Common |  |  |  | IT | -270244.25 | 0 | -270244.25
F.10015.06.24.03 | W_F.10015.06.24.03: POI - HANA DR Enablement | Common |  |  |  | IT | -156400.57 | 0 | -156400.57
F.10015.06.26.02 | W_F.10015.06.26.02: SAP Business Process Monitoring | Common |  |  |  | IT | -49287.6 | 0 | -49287.6
F.10015.06.28.01 | W_F.10015.06.28.01: Annual SQL Server Patches | Common |  |  |  | IT | -137262.08 | 0 | -137262.08
F.10015.08.11.07 | W_F.10015.08.11.07: Annual ServiceNow Platform Upgrades | Common |  |  |  | IT | -35417.21 | 0 | -35417.21
F.10015.08.14.04 | W_F.10015.08.14.04: Sitecore Autoscaling 2023 | Common |  |  |  | IT | -485772.88 | 0 | -485772.88
F.10015.08.14.05 | W_F.10015.08.14.05: Consolidate Web Platforms | Common |  |  |  | IT | -482646.76 | 0 | -482646.76
F.10015.08.18.02 | W_F.10015.08.18.02: Microservices Refactoring with Cassandra | Common |  |  |  | IT | -390708.48 | 0 | -390708.48
F.10015.08.20.01 | W_F.10015.08.20.01: Annual Splunk Growth (2023-27) | Common |  |  |  | IT | -84038.26 | 0 | -84038.26
F.10015.08.20.02 | W_F.10015.08.20.02: Splunk Version Upgrades 2023 | Common |  |  |  | IT | -175404.75 | 0 | -175404.75
F.10015.08.20.03 | W_F.10015.08.20.03: Annual Splunk Security Improvements | Common |  |  |  | IT | -68963.76 | 0 | -68963.76
F.10015.08.21.01 | W_F.10015.08.21.01: DataStax Astra Migration | Common |  |  |  | IT | -471605 | 0 | -471605
F.10015.08.24.01 | W_F.10015.08.24.01: Twilio/SendGrid Replacement | Common |  |  |  | IT | -772496.25 | 0 | -772496.25
F.10016.01.01.04 | W_F.10016.01.01.04: IT Enterprise Architecture 2023-27 | Common |  |  |  | IT | -184143.81 | 0 | -184143.81
F.10017.02.02.04 | W_F.10017.02.02.04: Annual Data Center Tech Refresh (2023+) | Common |  |  |  | IT | -428200.25 | 0 | -428200.25
F.10017.03.08.01 | W_F.10017.03.08.01: Annual AV/Conf Room Tech Refresh | Common |  |  |  | IT | -139126.7 | 0 | -139126.7
F.10017.05.07.02 | W_F.10017.05.07.02: DC Battery Management 2022-26 | Common |  |  |  | IT | -186899.48 | 0 | -186899.48
F.10017.07.01.04 | W_F.10017.07.01.04: OpenText ECM Upgrade | Common |  |  |  | IT | -522840.7 | 0 | -522840.7
F.10017.09.11.01 | W_F.10017.09.11.01: Annual Network&Voice Tech Refresh/Growth | Common |  |  |  | IT | -799360.76 | 0 | -799360.76
F.10017.10.20.01 | W_F.10017.10.20.01: Annual Corporate Comm Room Tech Refresh | Common |  |  |  | IT | -129316.09 | 0 | -129316.09
F.10017.10.21.01 | W_F.10017.10.21.01: Purch & Implmnt Syst Orchestration Tool | Common |  |  |  | IT | -126827.98 | 0 | -126827.98
F.10017.12.29.01 | W_F.10017.12.29.01: Annual Telecom Comm Sites Tech Refresh | Common |  |  |  | IT | -335795.19 | 0 | -335795.19
F.10025.01.04.05 | W_F.10025.01.04.05: Reconeyez Wireless Video | Common |  |  |  | IT | -616432.77 | 0 | -616432.77
F.10025.01.05.01 | W_F.10025.01.05.01: Zero Trust Strategy for TSA Gas Pipeline | Gas |  |  |  | IT | -1372689.31 | 0 | -1372689.31
F.10025.01.05.03 | W_F.10025.01.05.03: Jackson Prairie IT Infrastructure | Gas |  |  |  | IT | -213097.9 | 0 | -213097.9
F.10026.01.01.03 | W_F.10026.01.01.03: Robotic Process Automation (2023-27) | Common |  |  |  | IT | -415822.3 | 0 | -415822.3
K.10008.01.01.05 | W_K.10008.01.01.05: FREDDY 1 Major Maintenance Activity | Electric |  |  |  | Generation | -3892596.55 | 0 | -3892596.55
K.10011.01.03.01 | W_K.10011.01.03.01: FRE Major Maintenance Activity | Electric |  |  |  | Generation | -3436991.01 | 0 | -3436991.01
K.10020.01.01.07 | W_K.10020.01.01.07: MTF Major Maintenance | Electric |  |  |  | Generation | -24497000.53 | 0 | -24497000.53
R.10006.01.01.08 | W_R.10006.01.01.08: E Substation SCADA (Non-CEIP) | Electric | Grid Modernization | Programmatic: Programmatic | 6E - Grid Mod | Operations | -1735036.5213 | 0 | -1735036.5213
R.10009.08.07.01 | W_R.10009.08.07.01: E Fault Location | Electric | Projected | Projected | 9 - Projected | Operations | -45509.87 | 0 | -45509.87
R.10015.03.09.16 | W_R.10015.03.09.16: G NRF Retirement Program | Gas | Projected | Projected | 9 - Projected | Operations | -17267.64 | 0 | -17267.64
R.10015.08.01.02 | W_R.10015.08.01.02: G Enhanced Methane Emissions Reduction | Gas | Pipe Replacement | Programmatic: Programmatic | 8 - Pipe Replacement | Operations | -3890525.25 | 0 | -3890525.25
R.10034.01.01.03 | W_R.10034.01.01.03: E Pierce Co 230Kv Alderton Tline | Electric | Projected | Projected | 9 - Projected | Operations | -16426.06 | 0 | -16426.06
R.10035.01.01.01 | W_R.10035.01.01.01: E Alderton Electron Hgts 115Kv Ph2 Tline | Electric | Projected | Specific: Specific |  | Operations | -1635.29 | 0 | -1635.29
R.10059.06.01.01 | W_R.10059.06.01.01: E Conservation Voltage Reduction | Electric | Grid Modernization | Programmatic: Programmatic | 6E - Grid Mod | Operations | -10674.04 | 0 | -10674.04
X.10006.02.03.02 | W_X.10006.02.03.02: Transprtatn Electrificatn Plan General | Electric |  |  |  | NP&S | -396715.91 | 0 | -396715.91
C.10002.02.02.01 | W_C.10002.02.02.01: CLSD East Building Retirement | Common |  |  |  | Facilities | 0 | -12462842.5786 | 12462842.5786
C.10002.04.03.01 | W_C.10002.04.03.01: CLSD New Headquarters TI | Common |  |  |  | Facilities | 0 | -14472.17 | 14472.17
C.10002.09.01.01 | W_C.10002.09.01.01: CLSD BUCC relocation | Common |  |  |  | Facilities | 0 | -707.8972 | 707.8972
PLACEHOLDER WBS 34 | PLACEHOLDER WBS 34: Crystal Mountain | Electric |  |  |  | Generation | 0 | -13040.027 | 13040.027
F.10002.01.34.01 | W_F.10002.01.34.01: IWM Enhancements | Common |  |  |  | IT | 0 | -752309.25 | 752309.25
K.10012.01.01.10 | W_K.10012.01.01.10: BPCC Faster Pmt Posting | Common |  |  |  | IT | 0 | -4834241.3077 | 4834241.3077
R.10059.02.01.09 | W_R.10059.02.01.09: E Property Acquisition Cir Enablement | Electric | Grid Modernization | Programmatic: Programmatic | 6E - Grid Mod | Operations | 0 | -5600000 | 5600000
C.10002.02.03.01 | W_C.10002.02.03.01: RedWest Vacate and SKC Buildout | Common |  |  |  | Facilities | 0 | -5000000 | 5000000
C.20001.01.01.01 | W_C.20001.01.01.01: Transformer Retirement and Disposal | Electric |  |  |  | Other | 0 | -1658458.92 | 1658458.92
C.20001.02.01.01 | W_C.20001.02.01.01: Treated Wood Disposal | Electric |  |  |  | Other | 0 | -431725.08 | 431725.08
F.10015.04.04.01 | W_F.10015.04.04.01: GIS SmallWorld Upgrade | Common |  |  |  | IT | 0 | -2000000 | 2000000
F.10017.05.04.02 | W_F.10017.05.04.02: AV Updates | Common |  |  |  | IT | 0 | -1003079 | 1003079
F.10017.07.01.02 | W_F.10017.07.01.02: OpenText Migrations | Common |  |  |  | IT | 0 | -852336.8181 | 852336.8181
F.10017.13.02.02 | W_F.10017.13.02.02: Annual VOIP Deployment and Refresh | Common |  |  |  | IT | 0 | -0.043577 | 0.043577
K.10035.01.01.02 | W_K.10035.01.01.02: FRA Unit 2 to 4 Hot Gas Path | Electric |  |  |  | Generation | 0 | -1447.5462 | 1447.5462
R.10009.12.04.01 | W_R.10009.12.04.01: E Trans Automation Placeholder | Electric | Projected | Projected | 9 - Projected | Operations | 0 | -524.703 | 524.703
R.10009.14.05.15 | W_R.10009.14.05.15: E Subs CAP Transient Security Issues Dis | Electric | Projected | Projected | 9 - Projected | Operations | 0 | -25677.8394 | 25677.8394
R.10037.01.01.07 | W_R.10037.01.01.07: G Scrap Sale Plt Meters Dist | Gas |  |  |  | Other | 0 | -1920 | 1920
R.10044.01.01.03 | W_R.10044.01.01.03: E Lake Holm Substation Subs | Electric | Projected | Projected | 9 - Projected | Operations | 0 | -385505.8286 | 385505.8286
R.10009.07.03.02 | W_R.10009.07.03.02: E OH UG System Improv Opport New Trans | Electric | PI Electric | Programmatic Customer Driven | 3E - CIAC, NCC, PI | Operations | 0 | -366.1517 | 366.1517
R.10039.03.01.01 | W_R.10039.03.01.01: E White River Krain Substation | Electric | Major Projects Electric | Programmatic: Programmatic | 7E - Maj Proj | Operations | 0 | -9072.57 | 9072.57
F.10007.02.01.02 | W_F.10007.02.01.02: IT Operational Funding | Common |  |  |  | IT | 0 | -31095449 | 31095449
R.10003.01.01.01 | W_R.10003.01.01.01: E Lake Tradition 230Kv Development | Electric | Projected | Projected | 9 - Projected | Operations | 0 | -27570.89 | 27570.89
R.10037.01.01.06 | W_R.10037.01.01.06: G Removal Cost Meters | Gas |  |  |  | Other | 0 | -127819.2 | 127819.2
R.10037.01.01.01 | W_R.10037.01.01.01: E Removal Cost Meters | Electric |  |  |  | Other | 0 | -456998.86 | 456998.86
R.10015.06.01.11 | W_R.10015.06.01.11: G Project Initiation | Gas | Capacity Gas | Programmatic: Programmatic |  | Operations | 0 | -2830389.3666 | 2830389.3666
R.10009.08.02.23 | W_R.10009.08.02.23: E Project Initiation | Electric | Capacity Electric | Programmatic: Programmatic |  | Operations | 0 | -31978133.108 | 31978133.108
R.99999.99.99.99 | W_R.99999.99.99.99: General Transmission Project (Offest to Energize Eastside) | Electric | Projected | Projected | 9 - Projected | Operations | 0 | 40119811.4543 | -40119811.4543
C.10004.01.01.02 | W_C.10004.01.01.02: Wireless PCS Construction | Electric | Projected | Projected | 9 - Projected | Operations | 0 | -59235.8288 | 59235.8288
F.10002.01.22.01 | W_F.10002.01.22.01: Click Schedule Replacement | Common |  |  |  | IT | 0 | -7264315.7932 | 7264315.7932
F.10002.01.25.01 | W_F.10002.01.25.01: Transmission & Generation Facilities DB | Electric |  |  |  | IT | 0 | -3293534.9292 | 3293534.9292
F.10015.02.17.01 | W_F.10015.02.17.01: Distribution Management System | Electric |  |  |  | IT | 0 | -13682163.113 | 13682163.113
F.10015.08.13.03 | W_F.10015.08.13.03: UI Enhancements Phase 3 | Common |  |  |  | IT | 0 | -951662.0614 | 951662.0614
F.10017.05.04.01 | W_F.10017.05.04.01: Workplace Mobility Program | Common |  |  |  | IT | 0 | -1002546.1425 | 1002546.1425
F.10017.13.03.02 | W_F.10017.13.03.02: VOIP Deployment and Refresh | Electric |  |  |  | IT | 0 | -421.6669 | 421.6669
K.10006.01.01.01 | W_K.10006.01.01.01: ENC Small Tools | Electric |  |  |  | Generation | 0 | -247.01 | 247.01
K.10010.01.01.03 | W_K.10010.01.01.03: FRE Small Tools | Electric |  |  |  | Generation | 0 | -1030.8043 | 1030.8043
K.10020.01.01.03 | W_K.10020.01.01.03: MTF CT Major Maintenance | Electric |  |  |  | Generation | 0 | 4193238.35 | -4193238.35
K.10023.01.01.01 | W_K.10023.01.01.01: SMS Small Tools | Electric |  |  |  | Generation | 0 | -1057.889 | 1057.889
R.10004.01.01.01 | W_R.10004.01.01.01: C Franchises | Common | Projected | Projected | 9 - Projected | Operations | 0 | -146624 | 146624
R.10005.01.01.04 | W_R.10005.01.01.04: E Eastside 230Kv Subs Rose Hill | Electric | Projected | Projected | 9 - Projected | Operations | 0 | -8529285.6655 | 8529285.6655
R.10008.02.01.01 | W_R.10008.02.01.01: E Franchises | Electric | Projected | Projected | 9 - Projected | Operations | 0 | -2433475 | 2433475
R.10008.07.02.01 | W_R.10008.07.02.01: E King County Clr Zone Pole Prog Dist | Electric | PI Electric | Programmatic Customer Driven | 3E - CIAC, NCC, PI | Operations | 0 | -3027511.3667 | 3027511.3667
R.10009.03.01.01 | W_R.10009.03.01.01: E Clyde Hill Switching Station | Electric | Major Projects Electric | Programmatic: Programmatic | 7E - Maj Proj | Operations | 0 | -293524.86 | 293524.86
R.10009.08.02.18 | W_R.10009.08.02.18: E OH Sys Capacity Upgrades Uprates Trans | Electric | Projected | Projected | 9 - Projected | Operations | 0 | -809.5737 | 809.5737
R.10009.08.02.20 | W_R.10009.08.02.20: E OH Transformer PCB Remediation | Electric | Projected | Projected | 9 - Projected | Operations | 0 | -3019.2287 | 3019.2287
R.10009.08.05.04 | W_R.10009.08.05.04: E Pole Replacement Due To Joint Use | Electric |  |  |  | NP&S | 0 | -1548118.764 | 1548118.764
R.10009.08.06.01 | W_R.10009.08.06.01: E Root Cause Analysis | Electric | Major Projects Electric | Programmatic: Programmatic | 7E - Maj Proj | Operations | 0 | -896569.744 | 896569.744
R.10009.09.01.02 | W_R.10009.09.01.02: E Emergent Major Projects Trans | Electric | Projected | Projected | 9 - Projected | Operations | 0 | -1168.2136 | 1168.2136
R.10009.10.01.01 | W_R.10009.10.01.01: E Issaquah Highland Substation | Electric | Major Projects Electric | Programmatic: Programmatic | 7E - Maj Proj | Operations | 0 | -131192.4 | 131192.4
R.10009.12.02.04 | W_R.10009.12.02.04: E Conservation Voltage Reduction | Electric | Grid Modernization | Programmatic: Programmatic | 6E - Grid Mod | Operations | 0 | -19619.7438 | 19619.7438
R.10009.12.03.04 | W_R.10009.12.03.04: E Network and Automate Grid | Electric | Grid Modernization | Programmatic: Programmatic | 6E - Grid Mod | Operations | 0 | -235723.565 | 235723.565
R.10009.14.05.01 | W_R.10009.14.05.01: E Digital Fault Recorders Replacement | Electric | Projected | Projected | 9 - Projected | Operations | 0 | -27319.3194 | 27319.3194
R.10009.14.05.05 | W_R.10009.14.05.05: E Subs Replacement Circuit Switcher Dist | Electric | Grid Modernization | Programmatic: Programmatic | 6E - Grid Mod | Operations | 0 | -11481.874 | 11481.874
R.10009.14.05.11 | W_R.10009.14.05.11: E Subs Replacement Vegetation Management | Electric | Projected | Projected | 9 - Projected | Operations | 0 | -197744.8422 | 197744.8422
R.10009.14.06.01 | W_R.10009.14.06.01: E Subs Replacement Transformers Dist | Electric | Grid Modernization | Programmatic: Programmatic | 6E - Grid Mod | Operations | 0 | -27477.0595 | 27477.0595
R.10011.01.01.10 | W_R.10011.01.01.10: G Service Replacements CBP | Gas | Projected | Projected | 9 - Projected | Operations | 0 | -59.5624 | 59.5624
R.10013.02.01.01 | W_R.10013.02.01.01: G Franchises | Gas | Projected | Projected | 9 - Projected | Operations | 0 | -1810156 | 1810156
R.10015.03.05.04 | W_R.10015.03.05.04: G DIMP Regulator Station Sidewalk Regs | Gas | Projected | Projected | 9 - Projected | Operations | 0 | -49.7039 | 49.7039
R.10015.03.06.02 | W_R.10015.03.06.02: G DIMP Legacy Crss Bore Replacement Dist | Gas | Pipe Replacement | Programmatic: Programmatic | 8 - Pipe Replacement | Operations | 0 | -1085.1389 | 1085.1389
R.10015.03.09.05 | W_R.10015.03.09.05: G DIMP Preventive Maintenance MSA Dist | Gas | Gas Modernization | Programmatic: Programmatic | 6G - Gas Mod | Operations | 0 | -227997.054 | 227997.054
R.10015.04.01.08 | W_R.10015.04.01.08: G Gas Work Release Main | Gas | Emergent Gas | Programmatic: Programmatic | 4 - Emergent Work | Operations | 0 | -148843.1356 | 148843.1356
R.10015.06.01.01 | W_R.10015.06.01.01: G Cold Weather Action Reinforcement | Gas | Capacity Gas | Programmatic: Programmatic |  | Operations | 0 | -28888.6752 | 28888.6752
R.10018.01.01.01 | W_R.10018.01.01.01: E Covington Area Capacity Project | Electric | Projected | Projected | 9 - Projected | Operations | 0 | -680074.44 | 680074.44
R.10019.01.01.03 | W_R.10019.01.01.03: E Rebuild Winslow Tap | Electric | Projected | Projected | 9 - Projected | Operations | 0 | -11263990.0435 | 11263990.0435
R.10019.01.01.04 | W_R.10019.01.01.04: E Murden Cove Subs | Electric | Bainbridge Tlines Trans | Specific: Specific | 2 - Bainbridge | Operations | 0 | -11427708.0128 | 11427708.0128
R.10019.03.01.01 | W_R.10019.03.01.01: E So Brm Bngr 115Kv 230Kv Prprty Purch | Electric | Projected | Projected | 9 - Projected | Operations | 0 | -1457506.97 | 1457506.97
R.10020.02.01.01 | W_R.10020.02.01.01: E Wind RidgE Kittitas 115Kv Tline | Electric | Major Projects Electric | Programmatic: Programmatic | 7E - Maj Proj | Operations | 0 | -336742.26 | 336742.26
R.10039.02.01.03 | W_R.10039.02.01.03: E Electr Enum 55Kv 115Kv Sub Electr Hght | Electric | Major Projects Electric | Programmatic: Programmatic | 7E - Maj Proj | Operations | 0 | -32985.9339 | 32985.9339
R.10039.02.01.05 | W_R.10039.02.01.05: E Electr Enum 55Kv To 115Kv Sub Enum | Electric | Major Projects Electric | Programmatic: Programmatic | 7E - Maj Proj | Operations | 0 | -23091.1144 | 23091.1144
R.10052.01.01.01 | W_R.10052.01.01.01: E Kent-Tukwila Area Capacity Project | Electric | Major Projects Electric | Programmatic: Programmatic | 7E - Maj Proj | Operations | 0 | -725216.849 | 725216.849
R.10052.01.01.02 | W_R.10052.01.01.02: E Briscoe Park Substation Tline | Electric | Major Projects Electric | Programmatic: Programmatic | 7E - Maj Proj | Operations | 0 | -24582.46 | 24582.46
R.10054.03.01.01 | W_R.10054.03.01.01: E Lynden Substation Expansion | Electric | Major Projects Electric | Programmatic: Programmatic | 7E - Maj Proj | Operations | 0 | -7233886.9231 | 7233886.9231
R.10056.01.01.01 | W_R.10056.01.01.01: E Wilkeson Substation Sub | Electric | Major Projects Electric | Programmatic: Programmatic | 7E - Maj Proj | Operations | 0 | -1883740.9732 | 1883740.9732
R.10059.01.01.01 | W_R.10059.01.01.01: E Smart Grid Living Lab | Electric | Grid Modernization | Programmatic: Programmatic | 6E - Grid Mod | Operations | 0 | -900000 | 900000
R.10059.02.01.01 | W_R.10059.02.01.01: E ADMS Circuit Enablement | Electric | Grid Modernization | Programmatic: Programmatic | 6E - Grid Mod | Operations | 0 | -1154777.0333 | 1154777.0333
R.10059.05.01.01 | W_R.10059.05.01.01: E Submarine Cable - Mercer Island | Electric | Grid Modernization | Programmatic: Programmatic | 6E - Grid Mod | Operations | 0 | -3771577.04 | 3771577.04
X.10006.03.01.02 | W_X.10006.03.01.02: Community Solar Program | Electric |  |  |  | NP&S | 0 | -9453083.701 | 9453083.701
F.10002.01.27.01 | W_F.10002.01.27.01: Asset Change Work Management | Electric |  |  |  | IT | 0 | -1504618.5 | 1504618.5
F.10002.05.03.01 | W_F.10002.05.03.01: EA and Magic Access DB Replacement | Electric |  |  |  | IT | 0 | -2849402.9637 | 2849402.9637
R.10006.01.01.02 | PLACEHOLDER WBS 21: IP Scada | Electric |  |  |  | IT | 0 | -2250000 | 2250000
F.10002.06.04.01 | W_F.10002.06.04.01: Arrearage Management Plan | Common |  |  |  | IT | 0 | -3113278.1971 | 3113278.1971
F.10002.06.07.01 | W_F.10002.06.07.01: Cust Usage Disaggregation and Presentmnt | Electric |  |  |  | IT | 0 | -2000000 | 2000000
F.10002.07.05.01 | W_F.10002.07.05.01: Third Party Risk | Common |  |  |  | IT | 0 | -3009237 | 3009237
F.10002.07.07.01 | W_F.10002.07.07.01: Multi-Family Solar | Electric |  |  |  | IT | 0 | -942894.26 | 942894.26
F.10002.07.09.01 | W_F.10002.07.09.01: Supply Chain Stabilization Phase 3 | Common |  |  |  | IT | 0 | -539634.8875 | 539634.8875
Total All Items Considered in 2023 Rate Year 1 CWIP Closings | [6 empty] | -1174390719.3527 | -910885102.0654 | -263505617.2873
[6 empty] | From reconciliation ----> | 1174455208.46 | 910885102
[6 empty] | Reconciled (Difference Immaterial) | 64489.1073 | -0.065351

## STR RR Recalc (Table 1)
2023 STR Calculation (in millions) |  |  | Electric |  |  | Natural Gas
[5 empty] | Act > Fcst |  |  | Act > Fcst
Description |  |  | Approved | Actual | (Fcst> Act) | Approved | Actual | (Fcst> Act)
| a |  | b | c | d | e | f | g
1 | Rate Base |  | 682.0364 | 731.9805 | 49.9441 | 334.4934 | 327.3799 | -7.1135
2 | Autorized Rate of Return |  | 7.16% | 7.16% | 0% | 7.16% | 7.16% | 0%
3 | Grossed up Rate of Return |  | 48.8338 | 52.4098 | 3.576 | 23.9497 | 23.4404 | -0.50933
4 | Depreciation |  | 30.0225 | 39.6944 | 9.6719 | 15.8252 | 16.4692 | 0.64396
5 | Taxes |  | -9.858 | -15.5485 | -5.6905 | -5.4364 | -5.8905 | -0.45411
6 | Total Expenses |  | 20.1645 | 24.1459 | 3.9814 | 10.3888 | 10.5787 | 0.18985
7 | Operating Income Requirement |  | 68.9983 | 76.5557 | 7.5574 | 34.3386 | 34.0191 | -0.31948
8 | Approved Conversion Factor |  | 0.75235 | 0.75235 | 0 | 0.7548 | 0.7548 | 0
9 | Revenue Requirement STR |  | 91.7098 | 101.7548 | 10.045 | 45.5 | 45.0703 | -0.42972
10 | If line 9<0, then threshold |  |  |  | n/a |  |  | -2.2158
11 | Exceeds threshold |  |  |  | n/a |  |  | Below threshold
12
13 | Threshold Calculation:
14 | 2023 Approved Rate Base |  |  |  | 682.0364 |  |  | 334.4934
15 | Fifty Basis Point Threshold |  |  |  | 0.5% |  |  | 0.5%
16 | Line 9 should not be less than |  |  |  | -4.5327 |  |  | -2.2158
|  | Check | 0 | 0 | 0 | -0.0064613 | 0 | 0.0064613

## Gross Plant Compare (Table 2)
(cumulative
|  | 2022-2023) | 2023
(in millions) |  | Gross Plant | Plant
Line | Description | Balance | Closings
(AMA)
1 | Electric
2 | Approved | 728.9523 | 659.2516
3 | Actual | 796.0971 | 886.412
4 | Over / (Under) | 67.1448 | 227.1604
5
6 | Natural Gas
7 | Approved | 358.8749 | 251.6335
8 | Actual | 365.4887 | 287.9787
9 | Over / (Under) | 6.6138 | 36.3453
10
11 | Combined
12 | Approved | 1087.8272 | 910.8851
13 | Actual | 1161.5859 | 1174.3907
14 | Over / (Under) | 73.7586 | 263.5056

## Variance Summary (Table 3)
(in miillions) |  |  | Deficiency (Surplus)
Line | Description |  | Electric | Gas | Combined
1 | Rate Base Higher (Lower) than Approved |  | 6.39 | 0.62738 | 7.0174
2 | Accumulated Depreciation (Higher) Lower than Approved |  | -0.68403 | -0.015923 | -0.69995
3 | Accumulated Deferred Income Taxes (Higher) Lower than Approved |  | -0.95292 | -1.2862 | -2.2392
4 | Net Depreciation and Amortization Higher (Lower) than Approved |  | 5.6474 | 0.20106 | 5.8485
5 | Tax Benefit of Interest (Higher) Lower than Approved |  | -0.35548 | 0.050468 | -0.30502
6 | Total Deficiency (Surplus) vs. Approved |  | 10.045 | -0.42326 | 9.6218 | 0.070128
|  | Check | 0 |  | 0

## Electric Closings Summary
Actual CWIP Closings 2023 - End of Period
Line
No. | Program | Gross Plant | Accum Depr | DFIT | Depr Exp
1 | AMI Meters and Modules Deployment | 17674943.04 | 668168.2433 | 1141185.4514 | 933763.5918
2 | Bainbridge Tlines Trans | 163258.2433 | 1713.3319 | 7953.1627 | 14509.2103
3 | Capacity Electric | 5006137.7654 | 89858.4513 | 107382.3825 | 169609.7565
4 | CIAC - Electric | -14236237.5342 | -414628.3221 | -60662.9838 | -631668.0808
5 | Customer Construction Electric | 79257830.2254 | 2261286.2438 | 799870.0238 | 3262097.4906
6 | Customer Construction Gas | 2832.6888 | 285.5777 | 65.394 | 204.8003
7 | Customer Sited Energy Storage | 9261.405 | 1067.5246 | 6830.9921 | 770.0789
8 | Data Center Hardware Refresh | 5179821.9019 | 1015983.7057 | 379675.0758 | 1133177.3872
9 | Emergent Electric | 105587700.8337 | 2790029.4704 | 1400751.5094 | 3739639.292
10 | Energize Eastside | 54183824.5017 | 177488.0275 | 1055058.266 | 1229545.278
11 | EV Circuit | 277146.5392 | 1991.4333 | -20644.5712 | 9665.3952
12 | Goldendale MM | -3595.86 | -328.5268 | -16.7042 | -265.5543
13 | Grid Modernization | 160280782.9967 | 4536779.9115 | 1655045.2759 | 6109532.7677
14 | GTZ | -29641.09 | -8031.0405 | -756.9488 | -6422.2362
15 | IT Operational Program | 6755776.7903 | 1683700.2803 | 215405.8353 | 1287180.9077
16 | Lower Baker Dam Grouting Program | 0 | 0 | 0 | 0
17 | Major Projects Electric | 2677726.1862 | 79875.9193 | 126527.7078 | 111013.6966
18 | Mint Farm MM | 14435849.02 | 1378362.374 | -12983.6954 | 1788962.5898
19 | Misc Additions | 57027650.5489 | 3049232.5408 | 1946357.8381 | 7221749.7544
20 | PI Electric | 34271524.095 | 942974.8829 | 686173.009 | 1633228.3674
21 | Pre-Capitalized Plant | 71143812.6592 | 2529677.1644 | 2619136.8857 | 3424141.0999
22 | Projected | 184845384.8688 | 11306219.5269 | 5317526.0436 | 12907250.8811
23 | Resilience Enhancement | 2061746.6196 | 23249.9067 | 34077.9863 | 49182.1048
24 | Sammamish Juanita 115Kv Tline | 1834414.8975 | 2068.037 | 262480.7924 | 49632.8881
25 | SAP S/4 Hana | 0 | 0 | 0 | 0
26 | Thurston Transmission Capacity | 6530908.23 | 36730.1385 | 109217.7963 | 168872.8117
27 | Transport Network Modernization | 1158287.9412 | 199416.3006 | 96472.8385 | 241726.8724
28 | Grand Total | 796097147.5136 | 32353171.1028 | 17872129.363 | 44847101.1512
0

## Gas Closings Summary
Actual CWIP Closings 2023 - End of Period
Line
No. | Program | Gross Plant | Accum Depr | DFIT | Depr Exp
1 | AMI Meters and Modules Deployment | 12375459.04 | 422752.5092 | 1034127.9507 | 732113.1237
2 | Capacity Gas | 5736257.5908 | 127484.8242 | 264050.6579 | 181980.8994
3 | CIAC - Gas | -1568587.6817 | -52607.404 | -31370.6997 | -53328.0327
4 | Customer Construction Electric | 20101.6513 | 634.7029 | 615.7925 | 833.4495
5 | Customer Construction Gas | 118640878.0504 | 3263642.438 | 4462663.8954 | 4530169.9028
6 | Data Center Hardware Refresh | 2675534.3339 | 524786.2453 | 196113.6348 | 585320.3186
7 | Emergent Gas | 23739315.7321 | 627814.9393 | 949428.7536 | 943299.3207
8 | Gas Modernization | 19090948.8704 | 471735.1164 | 729457.3914 | 656078.7005
9 | IT Operational Program | 3523713.828 | 894532.6494 | 107561.0848 | 681578.4361
10 | Major Projects Gas | 1560532.325 | 2530.2506 | 16464.0862 | 9050.9312
11 | Marine Crossing | 506294.4121 | 20370.7903 | 10175.0628 | 15917.2545
12 | Misc Additions | 17892030.6815 | 1271514.4225 | 925235.3143 | 2562103.0115
13 | PI Gas | 48534662.1208 | 819483.8991 | 1890061.7372 | 1326797.8208
14 | Pipe Replacement | 60557014.2583 | 1303797.243 | 2815729.3854 | 1884037.7668
15 | Pre-Capitalized Plant | 21865008.7858 | 950232.7654 | 1073249.3371 | 1025279.735
16 | Projected | 29741262.7883 | 2742667.0233 | 1218647.5288 | 3001779.9753
17 | SAP S/4 Hana | 0 | 0 | 0 | 0
18 | Transport Network Modernization | 598290.6775 | 103004.5374 | 49831.1326 | 124859.2247
19 | Total Gas | 365488717.4647 | 13494376.9524 | 15712042.0459 | 18207871.8384
0

## Rev Req Comparison
| ELECTRIC REVENUE REQUIREMENT |  |  |  |  | GAS REVENUE REQUIREMENT
|  | SEF 23-24 Compliance | 2023 Year End |  |  |  | SEF 23-24 Compliance | 2023 Year End
Line |  | Subject to Refund | Subject to Refund | Deficiency |  |  | Subject to Refund | Subject to Refund | Deficiency
No. |  | RY 1 In Rates | RY 1 Actuals | (Surplus) |  |  | RY 1 In Rates | RY 1 Actuals | (Surplus)
1 | Rate Base Increase (Decrease): |  |  |  |  | Rate Base Increase (Decrease):
2 | Gross Plant CWIP Closings | 728952322.5972 | 796097147.5136 | 6390027.931 |  | Gross Plant CWIP Closings | 358874908.1328 | 365488717.4647 | 627382.248 |  | 1161585864.9783 | <------ reconciled ------> | 1161585864.9783
3 | Accum Depr and Amort CWIP Closings | -27237621.2285 | -32353171.1028 | -486835.8302 |  | Accum Depr and Amort CWIP Closings | -13228601.6415 | -13494376.9524 | -25211.2971
4 | DFIT CWIP Closings | -12669342.3063 | -17872129.363 | -495138.0043 |  | DFIT CWIP Closings | -5569572.8037 | -15712042.0459 | -962108.9502
5 | Gross Plant Retirements | 0 | 0 | 0 |  | Gross Plant Retirements | 0 | 0 | 0
6 | Accum Depr and Amort Retirements | 7224733.012 | 5152670.5945 | -197193.7039 |  | Accum Depr and Amort Retirements | 1640749.178 | 1738668.6732 | 9288.5885
7 | ADIT + EDIT Retirements | -14233687.9981 | -19043982.5112 | -457785.3369 |  | ADIT + EDIT Retirements | -7224079.5247 | -10641099.7796 | -324136.6271
8 | Total Inc (Dec) Rate Base | 682036404.0763 | 731980535.1312 | 4753075.0557 | 0 | Total Inc (Dec) Rate Base | 334493403.3409 | 327379867.3599 | -674786.038 | 5.8208e-09
9
10 | Net Operating Income Increase (Decrease): |  |  |  |  | Net Operating Income Increase (Decrease):
11 | Deprec and Amort Exp CWIP Closings | -39430019.8214 | -44847101.1512 | -7200166.5833 |  | Deprec and Amort Exp CWIP Closings | -17881280.8986 | -18207871.8384 | -432684.8266
12 | FIT CWIP Closings | 8280304.1625 | 9417891.2418 | 1512034.9825 |  | FIT CWIP Closings | 3755068.9887 | 3823653.0861 | 90863.8136
13 | Deprec and Amort Exp Retirements | 9407514.2827 | 5152670.5945 | -5655367.065 |  | Deprec and Amort Exp Retirements | 2056035.8973 | 1738668.6732 | -420464.7638
14 | FIT/EDIT/FT Retirements | -2074592.6 | 2210870.6329 | 5696065.332 |  | FIT/EDIT/FT Retirements | -109876.9497 | 313739.1543 | 561228.8591
15 | Sub-Total Increase (Decrease) NOI | -23816793.9762 | -28065668.6821 | -5647433.3338 |  | Sub-Total Increase (Decrease) NOI | -12180052.9623 | -12331810.9248 | -201056.9177
16
17 | Plus: Tax Benefit of Proforma Interest | 3652304.9438 | 3919755.7656 | 355484.8732 |  | Plus: Tax Benefit of Proforma Interest | 1791212.1749 | 1753119.1897 | -50467.5871
18 | Total Increase (Decrease) NOI | -20164489.0324 | -24145912.9165 | -5291948.4606 |  | Total Increase (Decrease) NOI | -10388840.7874 | -10578691.7351 | -251524.5048
19
20 | Plus: Return on Rate Base | 48833806.5319 | 52409806.3154 |  | 0 | Plus: Return on Rate Base | 23949727.6792 | 23440398.503 |  | 7.567e-09
21 | Net Operating Income Deficiency | 68998295.5643 | 76555719.2319 |  | 0 | Net Operating Income Deficiency | 34338568.4666 | 34019090.2381 |  | 0
22
23 | Grossed Up Deficiency | 91709758.7765 | 101754782.2928 | 10045023.5163 | -2.0489e-08 | Grossed Up Deficiency | 45493538.65 | 45070277.1168 | -423261.5332 | 1.1758e-08
24
25 | Cost of Debt | 2.55% |  |  |  | Cost of Debt | 2.55%
26 | ROR per Settlement | 7.16% |  |  |  | ROR per Settlement | 7.16%
27 | Statutory Federal Income Tax Rate | 21% |  |  |  | Statutory Federal Income Tax Rate | 21%
28 | Conversion Factor | 75.24% |  |  |  | Conversion Factor | 75.48%

## 2022 GRC SEF-23 Adds
| DETERMINATION OF DEFICIENCY ASSOCIATED WITH | [7 empty] | UE-__________
| PROVISIONAL PROFORMA ADJUSTMENTS - FOR RATES | [7 empty] | Exh. SEF-23 pages 2 of 3
SUBJECT TO REFUND
Note: Amounts in bold and italics are different from the June 27, 2022 revised filing.
|  |  |  | EOP |  | EOP |  | AMA |  | AMA
ELECTRIC
|  |  |  | DEC 2021 | 2022 | ADJUSTED | 2023 | ADJUSTED | 2024 | ADJUSTED
|  |  | TRADITIONAL | ADJUSTED | GAP YEAR | RESULTS | RATE YEAR 1 | RESULTS | RATE YEAR 2 | RESULTS
LINE |  |  | PROFORMA | RESULTS OF | PROVISIONAL | START OF | PROVISIONAL | END OF | PROVISIONAL | END OF
NO. | DESCRIPTION |  | ADJUSTMENTS | OPERATIONS | ADJUSTMENTS | RATE YEAR 1 | ADJUSTMENTS | RATE YEAR 1 | ADJUSTMENTS | RATE YEAR 2
1 | Programmatic | (less Colstrip)
2 | 403 ELEC. DEPRECIATION EXPENSE |  | 0 | 0 | 3273093.55 | 3273093.55 | 9840603.22 | 13113696.77 | 18030677.91 | 31144374.68
3 | 403 ELEC. PORTION OF COMMON |  | 0 | 0 | 1623965.1965 | 1623965.1965 | 578426.5768 | 2202391.7732 | 2489754.139 | 4692145.9123
4 | 404 ELEC. AMORTIZATION EXPENSE |  | 0 | 0 | 190269.56 | 190269.56 | 588293.76 | 778563.32 | 2170084.36 | 2948647.68
5 | 404 ELEC. PORTION OF COMMON |  | 0 | 0 | 1796060.6375 | 1796060.6375 | 3837403.166 | 5633463.8035 | 4340981.5389 | 9974445.3424
6 | TOTAL DEPRECIATION AND AMORTIZATION EXPENSE |  | 0 | 0 | 6883388.944 | 6883388.944 | 14844726.7228 | 21728115.6667 | 27031497.9479 | 48759613.6146
7
8 | INCREASE (DECREASE) EXPENSE |  | 0 | 0 | 6883388.944 | 6883388.944 | 14844726.7228 | 21728115.6667 | 27031497.9479 | 48759613.6146
9
10 | INCREASE (DECREASE) FIT | 21% | 0 | 0 | -1445511.6782 | -1445511.6782 | -3117392.6118 | -4562904.29 | -5676614.5691 | -10239518.8591
11
12 | INCREASE (DECREASE) NOI |  | 0 | 0 | -5437877.2657 | -5437877.2657 | -11727334.111 | -17165211.3767 | -21354883.3789 | -38520094.7556
13
14 | GROSS PLANT |  | 0 | 0 | 275144876.5406 | 275144876.5406 | 156248807.7366 | 431393684.2772 | 519951689.8028 | 951345374.08
15 | ACCUM. DEPRECIATION & AMORTIZATION |  | 0 | 0 | -6883388.944 | -6883388.944 | -9398218.0489 | -16281606.9929 | -35005245.8045 | -51286852.7974
16 | DFIT |  | 0 | 0 | -2634322.4649 | -2634322.4649 | -5049179.8292 | -7683502.2941 | -12452260.1632 | -20135762.4573
17 | TOTAL ADJUSTMENT TO RATE BASE |  | 0 | 0 | 265627165.1318 | 265627165.1318 | 141801409.8584 | 407428574.9902 | 472494183.8351 | 879922758.8253
18
19 | Programmatic Customer Drive
20 | 403 ELEC. DEPRECIATION EXPENSE |  | 0 | 0 | 124018.32 | 124018.32 | 97835.56 | 221853.88 | 241632.78 | 463486.66
21 | 403 ELEC. PORTION OF COMMON |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | 404 ELEC. AMORTIZATION EXPENSE |  | 0 | 0 | 7346.88 | 7346.88 | 40307.04 | 47653.92 | 71876.82 | 119530.74
23 | 404 ELEC. PORTION OF COMMON |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | TOTAL DEPRECIATION AND AMORTIZATION EXPENSE |  | 0 | 0 | 131365.2 | 131365.2 | 138142.6 | 269507.8 | 313509.6 | 583017.4
25
26 | INCREASE (DECREASE) EXPENSE |  | 0 | 0 | 131365.2 | 131365.2 | 138142.6 | 269507.8 | 313509.6 | 583017.4
27
28 | INCREASE (DECREASE) FIT | 21% | 0 | 0 | -27586.692 | -27586.692 | -29009.946 | -56596.638 | -65837.016 | -122433.654
29
30 | INCREASE (DECREASE) NOI |  | 0 | 0 | -103778.508 | -103778.508 | -109132.654 | -212911.162 | -247672.584 | -460583.746
31
32 | GROSS PLANT |  | 0 | 0 | 4064845.85 | 4064845.85 | 4047296.68 | 8112142.53 | 8832345.36 | 16944487.89
33 | ACCUM. DEPRECIATION & AMORTIZATION |  | 0 | 0 | -131365.2 | -131365.2 | -111605.5 | -242970.7 | -419360.21 | -662330.91
34 | DFIT |  | 0 | 0 | -12153.7 | -12153.7 | -50860.45 | -63014.15 | -150990.09 | -214004.24
35 | TOTAL ADJUSTMENT TO RATE BASE |  | 0 | 0 | 3921326.95 | 3921326.95 | 3884830.73 | 7806157.68 | 8261995.06 | 16068152.74
36
37 | Specific
38 | 403 ELEC. DEPRECIATION EXPENSE |  | 0 | 0 | 305733.2 | 305733.2 | 2603562.16 | 2909295.36 | 2487783.11 | 5397078.47
39 | 403 ELEC. PORTION OF COMMON |  | 0 | 0 | 0 | 0 | 0 | 0 | 8266.4296 | 8266.4296
40 | 404 ELEC. AMORTIZATION EXPENSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | 404 ELEC. PORTION OF COMMON |  | 0 | 0 | 0 | 0 | 0 | 0 | 384929.9461 | 384929.9461
42 | TOTAL DEPRECIATION AND AMORTIZATION EXPENSE |  | 0 | 0 | 305733.2 | 305733.2 | 2603562.16 | 2909295.36 | 2880979.4857 | 5790274.8457
43
44 | INCREASE (DECREASE) EXPENSE |  | 0 | 0 | 305733.2 | 305733.2 | 2603562.16 | 2909295.36 | 2880979.4857 | 5790274.8457
45
46 | INCREASE (DECREASE) FIT | 21% | 0 | 0 | -64203.972 | -64203.972 | -546748.0536 | -610952.0256 | -605005.692 | -1215957.7176
47
48 | INCREASE (DECREASE) NOI |  | 0 | 0 | -241529.228 | -241529.228 | -2056814.1064 | -2298343.3344 | -2275973.7937 | -4574317.1281
49
50 | GROSS PLANT |  | 0 | 0 | 52149803.8 | 52149803.8 | 24986915.77 | 77136719.57 | 113711032.4133 | 190847751.9833
51 | ACCUM. DEPRECIATION & AMORTIZATION |  | 0 | 0 | -305733.2 | -305733.2 | -1322746.54 | -1628479.74 | -3862878.1017 | -5491357.8417
52 | DFIT |  | 0 | 0 | -483369.39 | -483369.39 | -725942.25 | -1209311.64 | -3246538.5509 | -4455850.1909
53 | TOTAL ADJUSTMENT TO RATE BASE |  | 0 | 0 | 51360701.21 | 51360701.21 | 22938226.98 | 74298928.19 | 106601615.7607 | 180900543.9507
54
55 | Projected
56 | 403 ELEC. DEPRECIATION EXPENSE |  | 0 | 0 | 856213.49 | 856213.49 | 4000634.07 | 4856847.56 | 3367889.57 | 8224737.13
57 | 403 ELEC. PORTION OF COMMON |  | 0 | 0 | 37040.74 | 37040.74 | 268195.0057 | 305235.7457 | 388831.8467 | 694067.5923
58 | 404 ELEC. AMORTIZATION EXPENSE |  | 0 | 0 | 856872.86 | 856872.86 | 2010015.41 | 2866888.27 | 3447073.45 | 6313961.72
59 | 404 ELEC. PORTION OF COMMON |  | 0 | 0 | 959799.3434 | 959799.3434 | 5534330.0757 | 6494129.419 | 8775367.556 | 15269496.975
60 | TOTAL DEPRECIATION AND AMORTIZATION EXPENSE |  | 0 | 0 | 2709926.4334 | 2709926.4334 | 11813174.5614 | 14523100.9947 | 15979162.4226 | 30502263.4173
61
62 | INCREASE (DECREASE) EXPENSE |  | 0 | 0 | 2709926.4334 | 2709926.4334 | 11813174.5614 | 14523100.9947 | 15979162.4226 | 30502263.4173
63 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
64 | INCREASE (DECREASE) FIT | 21% | 0 | 0 | -569084.551 | -569084.551 | -2480766.6579 | -3049851.2089 | -3355624.1088 | -6405475.3176
65
66 | INCREASE (DECREASE) NOI |  | 0 | 0 | -2140841.8824 | -2140841.8824 | -9332407.9035 | -11473249.7858 | -12623538.3139 | -24096788.0997
67
68 | GROSS PLANT |  | 0 | 0 | 156886692.0653 | 156886692.0653 | 55423084.1548 | 212309776.22 | 144501948.0529 | 356811724.2729
69 | ACCUM. DEPRECIATION & AMORTIZATION |  | 0 | 0 | -2709926.4334 | -2709926.4334 | -6374637.3623 | -9084563.7956 | -22358467.7865 | -31443031.5822
70 | DFIT |  | 0 | 0 | -1612462.0257 | -1612462.0257 | -2101052.1966 | -3713514.2222 | -5394091.8467 | -9107606.0689
71 | TOTAL ADJUSTMENT TO RATE BASE |  | 0 | 0 | 152564303.6062 | 152564303.6062 | 46947394.5959 | 199511698.2022 | 116749388.4196 | 316261086.6218
72
73 | Total All Provisional Proformas
74 | 403 ELEC. DEPRECIATION EXPENSE |  | 0 | 0 | 4559058.56 | 4559058.56 | 16542635.01 | 21101693.57 | 24127983.37 | 45229676.94
75 | 403 ELEC. PORTION OF COMMON |  | 0 | 0 | 1661005.9364 | 1661005.9364 | 846621.5825 | 2507627.5189 | 2886852.4153 | 5394479.9342
76 | 404 ELEC. AMORTIZATION EXPENSE |  | 0 | 0 | 1054489.3 | 1054489.3 | 2638616.21 | 3693105.51 | 5689034.63 | 9382140.14
77 | 404 ELEC. PORTION OF COMMON |  | 0 | 0 | 2755859.9809 | 2755859.9809 | 9371733.2416 | 12127593.2225 | 13501279.0409 | 25628872.2635
78 | TOTAL DEPRECIATION AND AMORTIZATION EXPENSE |  | 0 | 0 | 10030413.7773 | 10030413.7773 | 29399606.0441 | 39430019.8214 | 46205149.4562 | 85635169.2777
79
80 | INCREASE (DECREASE) EXPENSE |  | 0 | 0 | 10030413.7773 | 10030413.7773 | 29399606.0441 | 39430019.8214 | 46205149.4562 | 85635169.2777
81
82 | INCREASE (DECREASE) FIT | 21% | 0 | 0 | -2106386.8932 | -2106386.8932 | -6173917.2693 | -8280304.1625 | -9703081.3858 | -17983385.5483
83
84 | INCREASE (DECREASE) NOI |  | 0 | 0 | -7924026.8841 | -7924026.8841 | -23225688.7749 | -31149715.6589 | -36502068.0704 | -67651783.7294
85
86 | GROSS PLANT |  | 0 | 0 | 488246218.2559 | 488246218.2559 | 240706104.3414 | 728952322.5972 | 786997015.6289 | 1515949338.2262
87 | ACCUM. DEPRECIATION & AMORTIZATION |  | 0 | 0 | -10030413.7773 | -10030413.7773 | -17207207.4512 | -27237621.2285 | -61645951.9027 | -88883573.1312
88 | DFIT |  | 0 | 0 | -4742307.5806 | -4742307.5806 | -7927034.7258 | -12669342.3063 | -21243880.6508 | -33913222.9571
89 | TOTAL ADJUSTMENT TO RATE BASE |  | 0 | 0 | 473473496.898 | 473473496.898 | 215571862.1644 | 689045359.0624 | 704107183.0755 | 1393152542.1378

## 2022 GRC SEF-23 Retires
DETERMINATION OF DEFICIENCY ASSOCIATED WITH | [10 empty] | UE-__________
PROVISIONAL PROFORMA ADJUSTMENTS - FOR RATES | [10 empty] | Exh. SEF-23 page 3 of 3
SUBJECT TO REFUND
ELECTRIC
|  |  |  | EOP |  | EOP |  | AMA |  | AMA
|  |  |  | DEC 2021 | DEC 2021 | 2022 | ADJUSTED | 2023 | ADJUSTED | 2024 | ADJUSTED
|  |  |  | TRADITIONAL | ADJUSTED | GAP YEAR | RESULTS | RATE YEAR 1 | RESULTS | RATE YEAR 2 | RESULTS
LINE |  |  |  | PROFORMA | RESULTS OF | PROVISIONAL | START OF | PROVISIONAL | END OF | PROVISIONAL | END OF
NO. | DESCRIPTION |  |  | ADJUSTMENTS | OPERATIONS | ADJUSTMENTS | RATE YEAR 1 | ADJUSTMENTS | RATE YEAR 1 | ADJUSTMENTS | RATE YEAR 2
1
2 | 403 ELEC. DEPRECIATION EXPENSE |  | 0 | 0 | 0 | -2916126.09 | -2916126.09 | -6221238.26 | -9137364.35 | -3602864.9 | -12740229.25
3 | 403 ELEC. PORTION OF COMMON |  | 0 | 0 | 0 | -27499.0769 | -27499.0769 | -169791.7216 | -197290.7985 | -147196.1212 | -344486.9197
4 | 404 ELEC. AMORTIZATION EXPENSE |  | 0 | 0 | 0 | -30109.61 | -30109.61 | -42469.2 | -72578.81 | -42469.2 | -115048.01
5 | 404 ELEC. PORTION OF COMMON |  | 0 | 0 | 0 | -137.1816 | -137.1816 | -143.1426 | -280.3241 | -143.1426 | -423.4667
6 | SUBTOTAL DEPRECIATION EXPENSE 403 |  | 0 | 0 | 0 | -2973871.9585 | -2973871.9585 | -6433642.3242 | -9407514.2827 | -3792673.3637 | -13200187.6464
7 | 403.1 ELEC. ASSET RETIREMENT COST DEPRECIATION |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 403.1 ELEC. PORTION OF COMMON |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 411.10 ELEC. ASSET RETIREMENT OBLIGATION ACCRETION |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | TOTAL DEPRECIATION AND ACCRETION |  | 0 | 0 | 0 | -2973871.9585 | -2973871.9585 | -6433642.3242 | -9407514.2827 | -3792673.3637 | -13200187.6464
11
12 | INCREASE (DECREASE) EXPENSE |  | 0 | 0 | 0 | -2973871.9585 | -2973871.9585 | -6433642.3242 | -9407514.2827 | -3792673.3637 | -13200187.6464
13
14 | INCREASE (DECREASE) FIT | 21% | 0 | 0 | 0 | 624513.1113 | 624513.1113 | 1351064.8881 | 1975577.9994 | 796461.4064 | 2772039.4057
15 | INCREASE (DECREASE) EDIT |  | 0 | 0 | 0 | 399107.5784 | 399107.5784 | 426432.459 | 825540.0374 | 116933.3847 | 942473.4221
16 | INCREASE (DECREASE) FLOW-THROUGH |  | 0 | 0 | 0 | -648388.0739 | -648388.0739 | -78137.3629 | -726525.4368 | -656931.5864 | -1383457.0232
17 | INCREASE (DECREASE) TAX EXPENSE |  | 0 | 0 | 0 | 375232.6157 | 375232.6157 | 1699359.9842 | 2074592.6 | 256463.2047 | 2331055.8047
18
19 | INCREASE (DECREASE) NOI |  | 0 | 0 | 0 | 2598639.3427 | 2598639.3427 | 4734282.34 | 7332921.6827 | 3536210.159 | 10869131.8417
20
21 | ADJUSTMENT TO RATE BASE:
22 | ADJUSTMENT TO ACCUM. DEPREC. AT 100% DEPREC. EXP. LINE 12 |  | 0 | 0 | 0 | 2973871.9585 | 2973871.9585 | 4250861.0535 | 7224733.012 | 11531408.0779 | 18756141.0899
23 | ADIT |  | 0 | 0 | 0 | -9204702.5529 | -9204702.5529 | -4247453.0412 | -13452155.5942 | -8769988.9624 | -22222144.5565
24 | EDIT |  | 0 | 0 | 0 | -399107.5784 | -399107.5784 | -382424.8255 | -781532.4039 | -878515.6156 | -1660048.0195
25 | TOTAL ADJUSTMENT TO RATEBASE |  | 0 | 0 | 0 | -6629938.1728 | -6629938.1728 | -379016.8132 | -7008954.9861 | 1882903.4999 | -5126051.4861
26
27
28 | Four Factor Allocation Percentages: | Gas: |  | 34.06%
29 |  | Electric: |  | 65.94%

## 2022 GRC SEF-24 Adds
DETERMINATION OF DEFICIENCY ASSOCIATED WITH | [9 empty] | UG-__________
PROVISIONAL PROFORMA ADJUSTMENTS - FOR RATES | [9 empty] | Exh. SEF-24 page 2 of 3
SUBJECT TO REFUND
Note: Amounts in bold and italics are different from the June 27, 2022 revised filing.
NATURAL GAS |  |  |  | EOP |  | EOP |  | AMA |  | AMA
|  |  |  | DEC 2021 | 2022 | ADJUSTED | 2023 | ADJUSTED | 2024 | ADJUSTED
|  |  | TRADITIONAL | ADJUSTED | GAP YEAR | RESULTS | RATE YEAR 1 | RESULTS | RATE YEAR 2 | RESULTS
LINE |  |  | PROFORMA | RESULTS OF | PROVISIONAL | START OF | PROVISIONAL | END OF | PROVISIONAL | END OF
NO. | DESCRIPTION |  | ADJUSTMENTS | OPERATIONS | ADJUSTMENTS | RATE YEAR 1 | ADJUSTMENTS | RATE YEAR 1 | ADJUSTMENTS | RATE YEAR 2
1 | Programmatic
2 | 403 GAS DEPRECIATION EXPENSE |  | 0 | 0 | 1447082.16 | 1447082.16 | 3938648.67 | 5385730.83 | 8049741.32 | 13435472.15
3 | 403 GAS PORTION OF COMMON |  | 0 | 0 | 838827.0335 | 838827.0335 | 298774.7832 | 1137601.8168 | 1286033.151 | 2423634.9677
4 | 404 GAS AMORTIZATION EXPENSE |  | 0 | 0 | 1295.34 | 1295.34 | 2628.66 | 3924 | 2706.42 | 6630.42
5 | 404 GAS PORTION OF COMMON |  | 0 | 0 | 927719.5225 | 927719.5225 | 1982134.544 | 2909854.0665 | 2242247.9711 | 5152102.0376
6 | TOTAL DEPRECIATION AND AMORTIZATION EXPENSE |  | 0 | 0 | 3214924.056 | 3214924.056 | 6222186.6572 | 9437110.7133 | 11580728.8621 | 21017839.5754
7
8 | INCREASE (DECREASE) EXPENSE |  | 0 | 0 | 3214924.056 | 3214924.056 | 6222186.6572 | 9437110.7133 | 11580728.8621 | 21017839.5754
9 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | INCREASE (DECREASE) FIT | 21% | 0 | 0 | -675134.0518 | -675134.0518 | -1306659.198 | -1981793.2498 | -2431953.061 | -4413746.3108
11
12 | INCREASE (DECREASE) NOI |  | 0 | 0 | -2539790.0043 | -2539790.0043 | -4915527.4592 | -7455317.4635 | -9148775.801 | -16604093.2645
13
14 | INCREASE TO RATE BASE |  | 0 | 0 | 123742113.2694 | 123742113.2694 | 58558976.4934 | 182301089.7628 | 213051242.6772 | 395352332.44
15 | ACCUM. DEPRECIATION & AMORTIZATION |  | 0 | 0 | -3214924.056 | -3214924.056 | -4147223.9911 | -7362148.0471 | -15191827.6955 | -22553975.7426
16 | DFIT |  | 0 | 0 | -1026111.8451 | -1026111.8451 | -2552947.7108 | -3579059.5559 | -5979722.9368 | -9558782.4927
17 | TOTAL ADJUSTMENT TO RATE BASE |  | 0 | 0 | 119501077.3682 | 119501077.3682 | 51858804.7916 | 171359882.1598 | 191879692.0449 | 363239574.2047
18
19 | Programmatic Customer Drive
20 | 403 GAS DEPRECIATION EXPENSE |  | 0 | 0 | 1340113.04 | 1340113.04 | 2078844.55 | 3418957.59 | 2327081.96 | 5746039.55
21 | 403 GAS PORTION OF COMMON |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | 404 GAS AMORTIZATION EXPENSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | 404 GAS PORTION OF COMMON |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | TOTAL DEPRECIATION AND AMORTIZATION EXPENSE |  | 0 | 0 | 1340113.04 | 1340113.04 | 2078844.55 | 3418957.59 | 2327081.96 | 5746039.55
25
26 | INCREASE (DECREASE) EXPENSE |  | 0 | 0 | 1340113.04 | 1340113.04 | 2078844.55 | 3418957.59 | 2327081.96 | 5746039.55
27
28 | INCREASE (DECREASE) FIT | 21% | 0 | 0 | -281423.7384 | -281423.7384 | -436557.3555 | -717981.0939 | -488687.2116 | -1206668.3055
29
30 | INCREASE (DECREASE) NOI |  | 0 | 0 | -1058689.3016 | -1058689.3016 | -1642287.1945 | -2700976.4961 | -1838394.7484 | -4539371.2445
31
32 | INCREASE TO RATE BASE |  | 0 | 0 | 120233571.84 | 120233571.84 | 6769603.14 | 127003174.98 | 85663988.11 | 212667163.09
33 | ACCUM. DEPRECIATION & AMORTIZATION |  | 0 | 0 | -1340113.04 | -1340113.04 | -1679780.67 | -3019893.71 | -4258615.85 | -7278509.56
34 | DFIT |  | 0 | 0 | -665426.31 | -665426.31 | -566950.44 | -1232376.75 | -1606280.42 | -2838657.17
35 | TOTAL ADJUSTMENT TO RATE BASE |  | 0 | 0 | 118228032.49 | 118228032.49 | 4522872.03 | 122750904.52 | 79799091.84 | 202549996.36
36
37 | Specific
38 | 403 GAS DEPRECIATION EXPENSE |  | 0 | 0 | 16135.4 | 16135.4 | 16618.12 | 32753.52 | 0 | 32753.52
39 | 403 GAS PORTION OF COMMON |  | 0 | 0 | 0 | 0 | 0 | 0 | 4269.8604 | 4269.8604
40 | 404 GAS AMORTIZATION EXPENSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | 404 GAS PORTION OF COMMON |  | 0 | 0 | 0 | 0 | 0 | 0 | 198827.9339 | 198827.9339
42 | TOTAL DEPRECIATION AND AMORTIZATION EXPENSE |  | 0 | 0 | 16135.4 | 16135.4 | 16618.12 | 32753.52 | 203097.7943 | 235851.3143
43
44 | INCREASE (DECREASE) EXPENSE |  | 0 | 0 | 16135.4 | 16135.4 | 16618.12 | 32753.52 | 203097.7943 | 235851.3143
45
46 | INCREASE (DECREASE) FIT | 21% | 0 | 0 | -3388.434 | -3388.434 | -3489.8052 | -6878.2392 | -42650.5368 | -49528.776
47
48 | INCREASE (DECREASE) NOI |  | 0 | 0 | -12746.966 | -12746.966 | -13128.3148 | -25875.2808 | -160447.2575 | -186322.5383
49
50 | INCREASE TO RATE BASE |  | 0 | 0 | 1256366.2 | 1256366.2 | 0 | 1256366.2 | 2055930.3467 | 3312296.5467
51 | ACCUM. DEPRECIATION & AMORTIZATION |  | 0 | 0 | -16135.4 | -16135.4 | -16376.76 | -32512.16 | -91237.4183 | -123749.5783
52 | DFIT |  | 0 | 0 | -6505.43 | -6505.43 | -5636.8 | -12142.23 | -74473.4391 | -86615.6691
53 | TOTAL ADJUSTMENT TO RATE BASE |  | 0 | 0 | 1233725.37 | 1233725.37 | -22013.56 | 1211711.81 | 1890219.4893 | 3101931.2993
54
55 | Projected
56 | 403 GAS DEPRECIATION EXPENSE |  | 0 | 0 | 152201.17 | 152201.17 | 651335.6 | 803536.77 | 547635.71 | 1351172.48
57 | 403 GAS PORTION OF COMMON |  | 0 | 0 | 19132.66 | 19132.66 | 138530.8143 | 157663.4743 | 200843.3833 | 358506.8577
58 | 404 GAS AMORTIZATION EXPENSE |  | 0 | 0 | 15725.45 | 15725.45 | 661119.55 | 676845 | 487562.72 | 1164407.72
59 | 404 GAS PORTION OF COMMON |  | 0 | 0 | 495765.3266 | 495765.3266 | 2858648.5043 | 3354413.8309 | 4532742.174 | 7887156.005
60 | TOTAL DEPRECIATION AND AMORTIZATION EXPENSE |  | 0 | 0 | 682824.6066 | 682824.6066 | 4309634.4686 | 4992459.0753 | 5768783.9874 | 10761243.0627
61
62 | INCREASE (DECREASE) EXPENSE |  | 0 | 0 | 682824.6066 | 682824.6066 | 4309634.4686 | 4992459.0753 | 5768783.9874 | 10761243.0627
63
64 | INCREASE (DECREASE) FIT | 21% | 0 | 0 | -143393.1674 | -143393.1674 | -905023.2384 | -1048416.4058 | -1211444.6373 | -2259861.0432
65
66 | INCREASE (DECREASE) NOI |  | 0 | 0 | -539431.4392 | -539431.4392 | -3404611.2302 | -3944042.6695 | -4557339.35 | -8501382.0195
67
68 | INCREASE TO RATE BASE |  | 0 | 0 | 29948655.4947 | 29948655.4947 | 18365621.6952 | 48314277.19 | 48559199.7871 | 96873476.9771
69 | ACCUM. DEPRECIATION & AMORTIZATION |  | 0 | 0 | -682824.6066 | -682824.6066 | -2131223.1177 | -2814047.7244 | -7944094.2735 | -10758141.9978
70 | DFIT |  | 0 | 0 | -253046.6343 | -253046.6343 | -492947.6334 | -745994.2678 | -1323038.6733 | -2069032.9411
71 | TOTAL ADJUSTMENT TO RATE BASE |  | 0 | 0 | 29012784.2538 | 29012784.2538 | 15741450.9441 | 44754235.1978 | 39292066.8404 | 84046302.0382
72
73 | Total All Provisional Proformas
74 | 403 GAS DEPRECIATION EXPENSE |  | 0 | 0 | 2955531.77 | 2955531.77 | 6685446.94 | 9640978.71 | 10924458.99 | 20565437.7
75 | 403 GAS PORTION OF COMMON |  | 0 | 0 | 857959.6936 | 857959.6936 | 437305.5975 | 1295265.2911 | 1491146.3947 | 2786411.6858
76 | 404 GAS AMORTIZATION EXPENSE |  | 0 | 0 | 17020.79 | 17020.79 | 663748.21 | 680769 | 490269.14 | 1171038.14
77 | 404 GAS PORTION OF COMMON |  | 0 | 0 | 1423484.8491 | 1423484.8491 | 4840783.0484 | 6264267.8975 | 6973818.0791 | 13238085.9765
78 | TOTAL DEPRECIATION AND AMORTIZATION EXPENSE |  | 0 | 0 | 5253997.1027 | 5253997.1027 | 12627283.7959 | 17881280.8986 | 19879692.6038 | 37760973.5023
79
80 | INCREASE (DECREASE) EXPENSE |  | 0 | 0 | 5253997.1027 | 5253997.1027 | 12627283.7959 | 17881280.8986 | 19879692.6038 | 37760973.5023
81
82 | INCREASE (DECREASE) FIT | 21% | 0 | 0 | -1103339.3916 | -1103339.3916 | -2651729.5971 | -3755068.9887 | -4174735.4468 | -7929804.4355
83
84 | INCREASE (DECREASE) NOI |  | 0 | 0 | -4150657.7111 | -4150657.7111 | -9975554.1987 | -14126211.9099 | -15704957.157 | -29831169.0668
85
86 | INCREASE TO RATE BASE |  | 0 | 0 | 275180706.8041 | 275180706.8041 | 83694201.3286 | 358874908.1328 | 349330360.9211 | 708205269.0538
87 | ACCUM. DEPRECIATION & AMORTIZATION |  | 0 | 0 | -5253997.1027 | -5253997.1027 | -7974604.5388 | -13228601.6415 | -27485775.2373 | -40714376.8788
88 | DFIT |  | 0 | 0 | -1951090.2194 | -1951090.2194 | -3618482.5842 | -5569572.8037 | -8983515.4692 | -14553088.2729
89 | TOTAL ADJUSTMENT TO RATE BASE |  | 0 | 0 | 267975619.482 | 267975619.482 | 72101114.2056 | 340076733.6876 | 312861070.2145 | 652937803.9022

## 2022 GRC SEF-24 Retires
DETERMINATION OF DEFICIENCY ASSOCIATED WITH | [10 empty] | UG-__________
PROVISIONAL PROFORMA ADJUSTMENTS - FOR RATES | [10 empty] | Exh. SEF-24 page 3 of 3
SUBJECT TO REFUND
NATURAL GAS
|  |  |  | DEC 2021 | DEC 2021 | 2022 | ADJUSTED | 2023 | ADJUSTED | 2024 | ADJUSTED
|  |  |  | TRADITIONAL | ADJUSTED | GAP YEAR | RESULTS | RATE YEAR 1 | RESULTS | RATE YEAR 2 | RESULTS
LINE |  |  |  | PROFORMA | RESULTS OF | PROVISIONAL | START OF | PROVISIONAL | END OF | PROVISIONAL | END OF
NO. | DESCRIPTION |  |  | ADJUSTMENTS | OPERATIONS | ADJUSTMENTS | RATE YEAR 1 | ADJUSTMENTS | RATE YEAR 1 | ADJUSTMENTS | RATE YEAR 2
1
2 | 403 GAS DEPRECIATION EXPENSE |  | 0 | 0 | 0 | -675312.61 | -675312.61 | -1275355.7 | -1950668.31 | -517188.25 | -2467856.56
3 | 403 GAS PORTION OF COMMON |  | 0 | 0 | 0 | -14204.1031 | -14204.1031 | -87702.5484 | -101906.6515 | -76031.2388 | -177937.8903
4 | 404 GAS AMORTIZATION EXPENSE |  | 0 | 0 | 0 | -1563.3 | -1563.3 | -1752.84 | -3316.14 | -1752.84 | -5068.98
5 | 404 GAS PORTION OF COMMON |  | 0 | 0 | 0 | -70.8584 | -70.8584 | -73.9374 | -144.7959 | -73.9374 | -218.7333
6 | SUBTOTAL DEPRECIATION EXPENSE 403 |  | 0 | 0 | 0 | -691150.8715 | -691150.8715 | -1364885.0258 | -2056035.8973 | -595046.2663 | -2651082.1636
7 | 403.1 GAS ASSET RETIREMENT COST DEPRECIATION |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 403.1 GAS PORTION OF COMMON |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 411.10 GAS ASSET RETIREMENT OBLIGATION ACCRETION |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | TOTAL DEPRECIATION AND ACCRETION |  | 0 | 0 | 0 | -691150.8715 | -691150.8715 | -1364885.0258 | -2056035.8973 | -595046.2663 | -2651082.1636
11
12 | INCREASE (DECREASE) EXPENSE |  | 0 | 0 | 0 | -691150.8715 | -691150.8715 | -1364885.0258 | -2056035.8973 | -595046.2663 | -2651082.1636
13
14 | INCREASE (DECREASE) FIT | 21% | 0 | 0 | 0 | 145141.683 | 145141.683 | 286625.8554 | 431767.5384 | 124959.7159 | 556727.2544
15 | INCREASE (DECREASE) EDIT |  | 0 | 0 | 0 | -155774.1837 | -155774.1837 | 157558.8216 | 1784.6379 | 166216.8542 | 168001.4921
16 | INCREASE (DECREASE) FLOW-THROUGH |  | 0 | 0 | 0 | -182698.6546 | -182698.6546 | -140976.572 | -323675.2266 | -237981.322 | -561656.5486
17 | INCREASE (DECREASE) TAX EXPENSE |  | 0 | 0 | 0 | -193331.1552 | -193331.1552 | 303208.105 | 109876.9497 | 53195.2481 | 163072.1978
18
19 | INCREASE (DECREASE) NOI |  | 0 | 0 | 0 | 884482.0268 | 884482.0268 | 1061676.9208 | 1946158.9476 | 541851.0182 | 2488009.9658
20
21 | ADJUSTMENT TO RATE BASE: |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | ADJUSTMENT TO ACCUM. DEPREC. AT 100% DEPREC. EXP. LINE 12 |  | 0 | 0 | 0 | 691150.8715 | 691150.8715 | 949598.3065 | 1640749.178 | 2398429.3021 | 4039178.4801
23 | ADIT |  | 0 | 0 | 0 | -4750426.2987 | -4750426.2987 | -2473653.226 | -7224079.5247 | -4942310.3221 | -12166389.8468
24 | EDIT |  | 0 | 0 | 0 | 155774.1837 | 155774.1837 | -826.7193 | 154947.4644 | -78570.6299 | 76376.8346
25 | TOTAL ADJUSTMENT TO RATEBASE |  | 0 | 0 | 0 | -4059275.4271 | -4059275.4271 | -1524054.9195 | -5583330.3467 | -2543881.0201 | -8127211.3668
26
27
28 | Four Factor Allocation Percentages: | Gas: |  | 34.06%
29 |  | Electric: |  | 65.94%

## Att D Table
|  |  |  | Combined |  |  |  | Electric |  |  |  | Gas |  |  |  | Common |  |  |  | Electric Portion of Common |  |  |  | Gas Portion of Common |  |  |  | Electric |  |  |  | Gas
Row Labels | Actual CWIP Closings | Forecast CWIP Closings | Sum of Variance | Electric and Gas Combined | Actual CWIP Closings | Forecast CWIP Closings | Forecast < Actual (Forecast > Actual) | Row Labels | Actual CWIP Closings | Forecast CWIP Closings | Forecast < Actual (Forecast > Actual) | Row Labels | Actual CWIP Closings | Forecast CWIP Closings | Forecast < Actual (Forecast > Actual) | Row Labels | Actual CWIP Closings | Forecast CWIP Closings | Forecast < Actual (Forecast > Actual) | Row Labels | Actual CWIP Closings | Forecast CWIP Closings | Forecast < Actual (Forecast > Actual) | Row Labels | Actual CWIP Closings | Forecast CWIP Closings | Forecast < Actual (Forecast > Actual) | Electric + Allocated Common | Actual CWIP Closings | Forecast CWIP Closings | Forecast < Actual (Forecast > Actual) | Gas + Allocated Common | Actual CWIP Closings | Forecast CWIP Closings | Forecast < Actual (Forecast > Actual) | check actual | check forecast | check variance
AMI | -34462242.7455 | -167082331.0171 | 132620088.2716 | Facilities | 10286790.55 | 20478022.6457 | -10191232.0957 | Facilities | 371205.53 | 0 | 371205.53 | Facilities | 0 | 0 | 0 | Facilities | 9915585.02 | 20478022.6457 | -10562437.6257 | Facilities | 6538336.7622 | 13503208.1326 | -6964871.3704 | Facilities | 3377248.2578 | 6974814.5131 | -3597566.2553 | Facilities | 6909542.2922 | 13503208.1326 | -6593665.8404 | Facilities | 3377248.2578 | 6974814.5131 | -3597566.2553 | 0 | 0 | 0
Facilities | -10286790.55 | -20478022.6457 | 10191232.0957 | Generation | 109499005.7642 | 29739902.6627 | 79759103.1015 | Generation | 107595170.2942 | 27127013.1136 | 80468157.1806 | Generation | 1903835.47 | 2612889.5491 | -709054.0791 | Generation | 0 | 0 | 0 | Generation | 0 | 0 | 0 | Generation | 0 | 0 | 0 | Generation | 107595170.2942 | 27127013.1136 | 80468157.1806 | Generation | 1903835.47 | 2612889.5491 | -709054.0791 | 0 | 0 | 0
Generation | -109499005.7642 | -29739902.6627 | -79759103.1015 | IT | 128978578.3 | 143681759.977 | -14703181.677 | IT | 30728573.4 | 44122125.5962 | -13393552.1962 | IT | 8708474.01 | 5067415.5986 | 3641058.4114 | IT | 89541530.89 | 94492218.7822 | -4950687.8922 | IT | 59043685.4689 | 62308169.065 | -3264483.5961 | IT | 30497845.4211 | 32184049.7172 | -1686204.2961 | IT | 89772258.8689 | 106430294.6612 | -16658035.7924 | IT | 39206319.4311 | 37251465.3158 | 1954854.1154 | 0 | 0 | -1.4901e-08
IT | -128978578.3 | -143681759.977 | 14703181.677 | NP&S | 13737946.1934 | 29717406.4581 | -15979460.2647 | NP&S | 12993824.1234 | 29717406.4581 | -16723582.3347 | NP&S | 0 | 0 | 0 | NP&S | 744122.07 | 0 | 744122.07 | NP&S | 490674.093 | 0 | 490674.093 | NP&S | 253447.977 | 0 | 253447.977 | NP&S | 13484498.2164 | 29717406.4581 | -16232908.2418 | NP&S | 253447.977 | 0 | 253447.977 | 0 | 0 | 0
NP&S | -13737946.1934 | -29717406.4581 | 15979460.2647 | Operations | 902698887.3563 | 679521688.7515 | 223177198.6048 | Operations | 659536234.6094 | 474137285.6208 | 185398948.9886 | Operations | 242978733.287 | 204137779.1307 | 38840954.1563 | Operations | 183919.46 | 1246624 | -1062704.54 | Operations | 121276.4919 | 822023.8656 | -700747.3737 | Operations | 62642.9681 | 424600.1344 | -361957.1663 | Operations | 659657511.1013 | 474959309.4864 | 184698201.6149 | Operations | 243041376.255 | 204562379.2651 | 38478996.9899 | 0 | 0 | 0
W_K.10038.01.01.01: Cust Sited Energy Storage Demos CEIP |  | -1040000 | 1040000 | Storm | 4377633.9813 | 3769399.5103 | 608234.471 | Storm | 4377633.9813 | 3769399.5103 | 608234.471 | Storm | 0 | 0 | 0 | Storm | 0 | 0 | 0 | Storm | 0 | 0 | 0 | Storm | 0 | 0 | 0 | Storm | 4377633.9813 | 3769399.5103 | 608234.471 | Storm | 0 | 0 | 0 | 0 | 0 | 0
W_R.10009.08.05.04: E Pole Replacement Due To Joint Use | 0 | -1548118.764 | 1548118.764 | Other | 4811877.2074 | 3976922.06 | 834955.1474 | Other | 4474724.8174 | 3547182.86 | 927541.9574 | Other | 123834.79 | 129739.2 | -5904.41 | Other | 213317.6 | 300000 | -86682.4 | Other | 140661.6254 | 197820 | -57158.3746 | Other | 72655.9746 | 102180 | -29524.0254 | Other | 4615386.4429 | 3745002.86 | 870383.5829 | Other | 196490.7646 | 231919.2 | -35428.4354 | 0 | 0 | 0
W_X.10003.01.01.01: Street and Area Lighting Services | -2774952.2052 | -4757737.4334 | 1982785.2283 | Grand Total | 1174390719.3527 | 910885102.0654 | 263505617.2873 | Grand Total | 820077366.7557 | 582420413.1591 | 237656953.5966 | Grand Total | 253714877.557 | 211947823.4784 | 41767054.0786 | Grand Total | 100598475.04 | 116516865.4279 | -15918390.3879 | Grand Total | 66334634.4414 | 76831221.0632 | -10496586.6218 | Grand Total | 34263840.5986 | 39685644.3648 | -5421803.7661 | Grand Total | 886412001.1971 | 659251634.2222 | 227160366.9748 | Grand Total | 287978718.1556 | 251633467.8431 | 36345250.3125 | 0 | 0 | 2.3842e-07
W_X.10003.01.03.01: Street Light Replacement | -1813298.1 | -1610902.4702 | -202395.6298
W_X.10003.01.03.02: Smart Street Lighting | -2995082.71 | -229013.2765 | -2766069.4335
W_X.10005.01.01.01: Wireless and Wireline Construction | -1026939.635 | -945078.6899 | -81860.9451 |  | 0 | 0 | 0
W_X.10006.01.01.01: Customer Sited Energy Storage Pilot | 140154.2 | 0 | 140154.2 |  | 0 | 0 | -3.5763e-07 | [12 empty] | Electric | 65.94% |  |  | Gas | 34.06%
W_X.10006.02.02.02: EV Charging Program Infrastructure | -2297632.6732 | -6022703.3382 | 3725070.665
W_X.10006.03.01.02: Community Solar Program | 0 | -9453083.701 | 9453083.701
W_X.10006.03.01.05: Community Solar Program 2022-25 | -1829357.09 | 0 | -1829357.09
W_X.10007.01.01.01: Covid 19 Work for WUTC Order | -744122.07 | 0 | -744122.07
W_X.10006.02.03.02: Transprtatn Electrificatn Plan General | -396715.91 | 0 | -396715.91
W_K.10038.02.01.01: Rooftop Solar Program:DER Solar Project and Programs CEIP |  | -3380000 | 3380000
PLACEHOLDER WBS 7b: Demand Response transferred to Placeholder WBS 24 |  | -321149.785 | 321149.785
PLACEHOLDER WBS 88b: DER Innovation Process CEIP |  | -409619 | 409619
Operations | -868236644.6108 | -512439357.7344 | -355797286.8764
Other | -4811877.2074 | -3976922.06 | -834955.1474
Storm | -4377633.9813 | -3769399.5103 | -608234.471
W_C.10009.01.01.01: Storm OH Replacement Dist | -3338732.2713 | -2712513.0792 | -626219.1921
W_C.10009.01.01.02: Storm OH Replacement Trans | -1038901.71 | -1056886.4311 | 17984.7211
Grand Total | -1174390719.3527 | -910885102.0654 | -263505617.2873

## Reconcile JAK-5 22 GRC
JAK-5 from 2022 GRC Compliance Filing
Total included in MYRP | 915044782
Remove Colstrip to separate Tracker (not part of STR review) | -4159680
Total in rates for MYRYP STR Review | 910885102
|  |  | 4159680 | Colstrip
|  |  | 915044782 | Included in MYRP

## Reconcile 2023 Actual GP&Adds
|  | PT - Company | 1000: Puget Sound Energy
Colstrip, TEP, CEIP |  | ST Item: Summary Item for Rate Base Report of ST - Item | Gross Plant
& LNG Removed |  | ST - Item | Plant Book Ending Balance
12/31/2023 AMA |  | Row Labels | Sum of Dec-2022 | Sum of Jan-2023 | Sum of Feb-2023 | Sum of Mar-2023 | Sum of Apr-2023 | Sum of May-2023 | Sum of Jun-2023 | Sum of Jul-2023 | Sum of Aug-2023 | Sum of Sep-2023 | Sum of Oct-2023 | Sum of Nov-2023 | Sum of Dec-2023
0 |  | N/A: Not Applicable | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4226582.16 |  | W_C.10002.02.02.01: CLSD East Building Retirement | 4226582.16 | 4226582.16 | 4226582.16 | 4226582.16 | 4226582.16 | 4226582.16 | 4226582.16 | 4226582.16 | 4226582.16 | 4226582.16 | 4226582.16 | 4226582.16 | 4226582.16
3013238.1946 |  | W_C.10002.02.02.02: CLSD PSE HQ Refresh Phase 2 | 3012717.12 | 3012717.12 | 3012717.12 | 3012717.12 | 3012717.12 | 3012717.12 | 3012717.12 | 3013854.01 | 3013854.01 | 3013854.01 | 3013854.01 | 3013854.01 | 3013854.01
2491616.1396 |  | W_C.10002.02.02.04: CLSD Remodel Bellevue 9th Floor | 0 | 0 | 166889.99 | 3088398.75 | 3115242.02 | 3136764.02 | 3136764.02 | 3136764.02 | 3137460.19 | 3137460.19 | 3137460.19 | 3137460.19 | 3137460.19
0 |  | W_C.10002.02.03.02: Redmond South King Lease Exit | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
996568.2792 |  | W_C.10002.02.04.01: Facility Optimizatn Bothell G Lease Exit | 0 | 0 | 0 | 827951.9 | 854393.31 | 854393.31 | 1442959.51 | 1443037.52 | 1449734 | 1449734 | 1454382.77 | 1454822.02 | 1454822.02
1885.74 |  | W_C.10002.03.01.03: CLSD South King Complex Reno | 1885.74 | 1885.74 | 1885.74 | 1885.74 | 1885.74 | 1885.74 | 1885.74 | 1885.74 | 1885.74 | 1885.74 | 1885.74 | 1885.74 | 1885.74
25402.97 |  | W_C.10002.04.03.01: CLSD New Headquarters TI | 25402.97 | 25402.97 | 25402.97 | 25402.97 | 25402.97 | 25402.97 | 25402.97 | 25402.97 | 25402.97 | 25402.97 | 25402.97 | 25402.97 | 25402.97
138.87 |  | W_C.10002.06.01.01: CLSD Snoq Tech Center | 138.87 | 138.87 | 138.87 | 138.87 | 138.87 | 138.87 | 138.87 | 138.87 | 138.87 | 138.87 | 138.87 | 138.87 | 138.87
753075.5325 |  | W_C.10002.07.01.01: CLSD Puyallup Service Center Rebuild | 750044.19 | 753207.33 | 753207.33 | 753207.33 | 753207.33 | 753207.33 | 753207.33 | 753207.33 | 753207.33 | 753207.33 | 753207.33 | 753207.33 | 753207.33
909683.2404 |  | W_C.10002.08.02.01: CLSD Operational Training Center | 0 | 932523.6 | 937574.58 | 948452.93 | 942776.33 | 942776.33 | 949428.38 | 955733.8 | 955733.8 | 956825.46 | 957379.51 | 957996.11 | 957996.11
0 |  | W_C.10002.08.02.02: Operational Training Center CC 1507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5081733.1 |  | W_C.10002.09.01.01: CLSD BUCC relocation | 5081733.1 | 5081733.1 | 5081733.1 | 5081733.1 | 5081733.1 | 5081733.1 | 5081733.1 | 5081733.1 | 5081733.1 | 5081733.1 | 5081733.1 | 5081733.1 | 5081733.1
77736.9 |  | W_C.10002.10.01.01: CLSD - Site Feas and Master Plan | 77736.9 | 77736.9 | 77736.9 | 77736.9 | 77736.9 | 77736.9 | 77736.9 | 77736.9 | 77736.9 | 77736.9 | 77736.9 | 77736.9 | 77736.9
0 |  | W_C.10002.11.01.01: Lake Tapps Improvements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43576.0658 |  | W_C.10002.12.01.01: Hybrid Working Transition to 50 Percent | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1045825.58
0 |  | W_C.10002.14.01.01: NOB Security Fence | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_C.10002.15.01.01: New Primary Control Center | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_C.10002.16.01.01: Fac Fleet & Supply Chain Expan or Reloc | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1028176.6888 |  | W_C.10003.01.01.01: CLSD Furniture and Fixture Installation | 931984.88 | 931984.88 | 1010308.82 | 1010308.82 | 1010308.82 | 1010308.82 | 1010308.82 | 1010308.82 | 1010308.82 | 1010308.82 | 1010437.16 | 1231490.15 | 1231490.15
125622.7358 |  | W_C.10003.01.01.03: Furniture Fixtures HVAC Refresh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3014945.66
2500672.7317 |  | W_C.10003.01.03.01: Unplanned Facility Improvements | 2482679.01 | 2482679.01 | 2497351.29 | 2499125.49 | 2500509.26 | 2504942.43 | 2504942.43 | 2504942.43 | 2504942.43 | 2504942.43 | 2504942.43 | 2504942.43 | 2504942.43
-319620.77 |  | W_C.10004.01.01.02: Wireless PCS Construction | -319620.77 | -319620.77 | -319620.77 | -319620.77 | -319620.77 | -319620.77 | -319620.77 | -319620.77 | -319620.77 | -319620.77 | -319620.77 | -319620.77 | -319620.77
2798621.3708 |  | W_C.10005.01.02.01: Security System Installations Electric | 2777267.29 | 2777267.29 | 2777267.29 | 2785594.14 | 2785594.14 | 2829330.67 | 2806118.35 | 2806118.35 | 2806118.35 | 2806118.35 | 2806118.35 | 2806118.35 | 2806118.35
3583504.0129 |  | W_C.10005.01.02.02: WECC Mitigation Security Installations | 2360340.17 | 2297848 | 2297928.97 | 2297928.97 | 2297928.97 | 2297928.97 | 2297928.97 | 2297928.97 | 2297928.97 | 2297928.97 | 2297928.97 | 10648086.1 | 16389166.48
3157402.3438 |  | W_C.10006.01.01.01: Fleet Capital Purchase | 3087362.15 | 3087362.15 | 3087362.15 | 3087362.15 | 3087362.15 | 3087362.15 | 3087458.22 | 3087458.22 | 3087458.22 | 3087458.22 | 3087458.22 | 3087458.22 | 4767173.96
390454.1942 |  | W_C.10006.01.01.03: Fleet Radio Upgrade | 187123.94 | 388024.72 | 399669.01 | 400441.54 | 400441.54 | 400441.54 | 400441.54 | 400441.54 | 400441.54 | 400441.54 | 400441.54 | 400441.54 | 400441.54
14539.2546 |  | W_C.10006.01.01.04: EEI Fleet Electrical Commitment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 348942.11
9739131.8075 |  | W_C.10009.01.01.01: Storm OH Replacement Dist | 7446610.81 | 8225115.68 | 9047978.51 | 10011785.19 | 10036150.85 | 10059982.56 | 10074207.13 | 10072490.17 | 10073826.15 | 10074882.2 | 10075277.21 | 10075458.26 | 10638244.75
1135708.9338 |  | W_C.10009.01.01.02: Storm OH Replacement Trans | 324036.53 | 684692.27 | 683803.21 | 1267969.96 | 1268188.34 | 1268188.34 | 1268244.87 | 1268244.87 | 1268691.57 | 1268691.57 | 1269152.41 | 1269152.41 | 1362938.24
85626.81 |  | W_C.10010.02.01.01: Shuffleton Reloc at Kent Serv Center | 84987.92 | 84987.92 | 85718.08 | 85718.08 | 85718.08 | 85718.08 | 85718.08 | 85718.08 | 85718.08 | 85718.08 | 85718.08 | 85718.08 | 85718.08
0 |  | W_C.10010.03.01.01: Shuffleton Relocation at SKC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40637.3 |  | W_C.10010.06.01.01: Shuffleton Reloc at Todd Road | 40637.3 | 40637.3 | 40637.3 | 40637.3 | 40637.3 | 40637.3 | 40637.3 | 40637.3 | 40637.3 | 40637.3 | 40637.3 | 40637.3 | 40637.3
73775.2625 |  | W_C.40001.01.01.01: Success Factors Application | 49085.19 | 49085.19 | 49085.19 | 80272.65 | 80272.65 | 80272.65 | 80272.65 | 80272.65 | 80272.65 | 80272.65 | 80272.65 | 80272.65 | 80272.65
0 |  | W_C.40001.01.02.01: SuccessFactors Application Sustainment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
71143812.6592 |  | W_ELEC PRECAP: Elec precap | 43525431.6 | 47541154.69 | 50004644.16 | 56970612.37 | 63637292.6 | 68749859.08 | 76852929.72 | 79470263.84 | 81869319.85 | 84773576.73 | 88518710.45 | 88021438.82 | 91106467.6
174136.85 |  | W_F.10002.01.02.04: PCI Upgrade for EIM Changes | 174136.85 | 174136.85 | 174136.85 | 174136.85 | 174136.85 | 174136.85 | 174136.85 | 174136.85 | 174136.85 | 174136.85 | 174136.85 | 174136.85 | 174136.85
0 |  | W_F.10002.01.02.06: PCI Transmission Billing Module | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_F.10002.01.05.02: Transmission GIS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_F.10002.01.05.03: Enterprise GIS Product Enhancements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_F.10002.01.05.04: GIS Technology Rationalization | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_F.10002.01.06.02: SAP SuccessFactor Onboarding 2.0 Upgrade | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3810257.0521 |  | W_F.10002.01.14.01: Data Governance Foundation | 3234899.89 | 3241912.6 | 3305803.73 | 3493998.41 | 3559147.46 | 3654209.46 | 3663011.81 | 3675312.03 | 3976435.94 | 4025402.06 | 4032233.67 | 4454058.39 | 6048218.24
0 |  | W_F.10002.01.16.02: Virtual Power Plant 2024 & Beyond | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
734527.8583 |  | W_F.10002.01.17.01: iDOT Replacement | 736615.76 | 734437.08 | 734437.08 | 734437.08 | 734437.08 | 734437.08 | 734437.08 | 734437.08 | 734437.08 | 734437.08 | 734437.08 | 734437.08 | 734437.08
672098.5704 |  | W_F.10002.01.18.01: Cap and Invest Billing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3137728.33 | 3296171.55 | 3262565.93
0 |  | W_F.10002.01.19.01: Data Lake and Data Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_F.10002.01.19.02: Data Lake and Data Analytics NonCEIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
218120.6604 |  | W_F.10002.01.20.01: Front Office Enhancements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1509331.14 | 2216233.57
0 |  | W_F.10002.01.21.01: EMS Platform Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_F.10002.01.22.01: Click Schedule Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
79437.5217 |  | W_F.10002.01.23.01: Complex Billing CEIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1906500.52
0 |  | W_F.10002.01.24.01: Cust Relationship Mgmt (CRM) CEIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_F.10002.01.24.02: Cust Relationship Mgmnt (CRM) NonCEIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_F.10002.01.25.01: Transmission & Generation Facilities DB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30022.0767 |  | W_F.10002.01.26.01: Urbint Enhancement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 230376.11 | 259777.62
0 |  | W_F.10002.01.27.01: Asset Change Work Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_F.10002.01.28.03: Dist Energy Resource Mgmnt Systs (DERMS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_F.10002.01.29.01: Enh Day Ahead Mkt for CAISO or SPP+ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_F.10002.01.30.01: Hosting Capacity Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8794.3408 |  | W_F.10002.01.31.01: Sendout Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 211064.18
0 |  | W_F.10002.01.32.01: PM Tool for C&SP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_F.10002.01.33.01: Substation Forms Automation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_F.10002.01.35.01: Advanced Leak Detection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_F.10002.01.35.02: Leak Management System Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_F.10002.01.36.01: DIMP Predictive Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2675060.2458 |  | W_F.10002.03.02.01: Field Resources Call Out Tool | 2682734.14 | 2672875.93 | 2673105.67 | 2672736.56 | 2667716.08 | 2694126.85 | 2673143.63 | 2673214.54 | 2673171.67 | 2673781.77 | 2674278.1 | 2674136.72 | 2674136.72
52906.3392 |  | W_F.10002.03.03.01: Multi-Channel Workforce Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1269752.14
71229.4446 |  | W_F.10002.04.01.01: Travel mgmt.-Exp Rpting and Elect pmt | 70001.81 | 71282.82 | 71282.82 | 71282.82 | 71282.82 | 71282.82 | 71282.82 | 71282.82 | 71282.82 | 71282.82 | 71282.82 | 71282.82 | 71282.82
362316.2683 |  | W_F.10002.05.02.01: Check Payment Processing | 361022.92 | 362951.06 | 362317.4 | 362317.4 | 362317.4 | 362317.4 | 362317.4 | 362317.4 | 362317.4 | 362317.4 | 362317.4 | 362317.4 | 362317.4
0 |  | W_F.10002.05.03.01: EA and Magic Access DB Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_F.10002.05.04.01: Treasury & Risk Management Enhancement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_F.10002.05.05.01: ETRMS Consolidate - Endur Replace | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_F.10002.05.05.02: ETRMS Consolidate - OATI WebTrader Repl | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5151276.1263 |  | W_F.10002.06.01.01: eGain Replacement | 5151685.43 | 5151685.43 | 5151317.92 | 5151207.1 | 5151207.1 | 5151207.1 | 5151207.1 | 5151207.1 | 5151207.1 | 5151207.1 | 5151207.1 | 5151207.1 | 5151207.1
2962704.6842 |  | W_F.10002.06.02.01: Customer Experience Enhancement Program | 1802364.33 | 1802364.33 | 1802364.33 | 1802364.33 | 1802364.33 | 1802364.33 | 3933620.86 | 3938626.29 | 3939110.2 | 3947426.53 | 3952481.53 | 3952008.41 | 3952357.15
0 |  | W_F.10002.06.04.01: Arrearage Management Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11615.3979 |  | W_F.10002.06.05.02: PSE 2030 Digital Experience NonCEIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 278769.55
113109.25 |  | W_F.10002.06.06.01: Bill Discount Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2714622
0 |  | W_F.10002.06.07.01: Cust Usage Disaggregation and Presentmnt | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_F.10002.06.08.01: Budget Billing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_F.10002.06.08.02: Interactive Bill | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_F.10002.06.08.03: Billing and Pymnt Opertional Enhancemnts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
134559.59 |  | W_F.10002.06.08.04: Billing Correction Automation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3229430.16
539823.54 |  | W_F.10002.07.01.01: IMPACT | 539823.54 | 539823.54 | 539823.54 | 539823.54 | 539823.54 | 539823.54 | 539823.54 | 539823.54 | 539823.54 | 539823.54 | 539823.54 | 539823.54 | 539823.54
0 |  | W_F.10002.07.02.01: Safety Incident Management Tool | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
63922.9933 |  | W_F.10002.07.03.01: GIS Upgrade Smallworld | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1534151.84
17850.4504 |  | W_F.10002.07.04.01: Streetlight New Business DB SAP Conversn | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142257.35 | 143896.11
0 |  | W_F.10002.07.05.01: Third Party Risk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
178947.5867 |  | W_F.10002.07.06.01: Time Varying Rates Pilot | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4294742.08
0 |  | W_F.10002.07.07.01: Multi-Family Solar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39369.9525 |  | W_F.10002.07.08.01: eGRC Archer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 944878.86
0 |  | W_F.10002.07.09.01: Supply Chain Stabilization Phase 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_F.10002.07.10.01: SAP S/4 Hana | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_F.10002.07.11.01: Learning Management System (LMS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_F.10002.07.12.01: Vendor DEI/Green | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_F.10002.07.13.01: Enterprise Application Integration | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_F.10002.07.14.01: Legal Hold Management System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_F.10002.08.01.01: Material TrackTrace Pipeline Safety Comp | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2283675.26 |  | W_F.10002.09.01.01: Power Plan Upgrade | 2283675.26 | 2283675.26 | 2283675.26 | 2283675.26 | 2283675.26 | 2283675.26 | 2283675.26 | 2283675.26 | 2283675.26 | 2283675.26 | 2283675.26 | 2283675.26 | 2283675.26
2582576.8654 |  | W_F.10002.09.02.01: Enterprise PPM Tool | 0 | 0 | 2994637.14 | 3771664.57 | 2832653.61 | 2848020.03 | 2863058.52 | 2835858.91 | 2829258.91 | 2835858.91 | 2835858.91 | 2835858.91 | 3016387.93
0 |  | W_F.10002.09.02.02: EPPM Tool Phase 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_F.10002.09.03.01: Facilities and Workplace Mgmt System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_F.10002.09.04.01: FERC 881 Mitigation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7855356.2358 |  | W_F.10003.02.01.07: Data Center Hardware Refresh | 7470171.56 | 7852452.19 | 7341274.38 | 7351497.9 | 7351497.9 | 7351497.9 | 7280985.4 | 7280985.4 | 7280985.4 | 7280985.4 | 7280985.4 | 7280985.4 | 19190112.76
0 |  | W_F.10003.02.02.01: CLSD FTIP Hardware Upgrade | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1756578.6188 |  | W_F.10003.03.02.01: Transport Network Modernization | 1583401.51 | 1596068.16 | 1591351.99 | 1719449.2 | 1737227.6 | 1739595.57 | 1741424.27 | 1796547.22 | 1797388.53 | 1797388.53 | 1797388.53 | 1797388.53 | 2352049.08
39889.8937 |  | W_F.10003.04.01.01: Digital Workplace Transformation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 957357.45
0 |  | W_F.10003.04.02.01: AV (Audio/Video) Upgrades | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_F.10003.04.03.01: Network Substation Hardware Refresh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_F.10003.04.04.01: Microsoft 365 Enablement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_F.10003.04.05.01: Critical Access Database Remediation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_F.10013.09.01.01: PSE ITSR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_F.10013.09.01.02: PSE ITSR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1019768.6079 |  | W_F.10013.09.01.03: PSE ITSR | 626303.57 | 660389.22 | 658171.42 | 685401.8 | 848332 | 837751.99 | 928910.94 | 1084653.15 | 1166061.43 | 1181440.61 | 1257361.49 | 1471053.84 | 2289087.24
2236.0579 |  | W_F.10015.01.03.02: Oracle Upgrades 2023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53665.39
0 |  | W_F.10015.01.04.01: Annual Informatica Upgrades | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_F.10015.02.02.03: EMS Point Growth (2024+) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_F.10015.02.03.01: EMS 3X Upgrade | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
277160.2083 |  | W_F.10015.02.06.02: Gas Control Upgrade 2022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6651845
0 |  | W_F.10015.02.14.01: OSI Soft PI Historian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1191666.6013 |  | W_F.10015.02.14.02: OSI Soft PI Historian | 1191411.69 | 1192976.79 | 1191553.96 | 1191553.96 | 1191553.96 | 1191553.96 | 1191553.96 | 1191553.96 | 1191553.96 | 1191553.96 | 1191553.96 | 1191553.96 | 1191553.96
157967.89 |  | W_F.10015.02.14.03: Elec OSI PI Asst Framewrk PI Vision Migr | 157967.89 | 157967.89 | 157967.89 | 157967.89 | 157967.89 | 157967.89 | 157967.89 | 157967.89 | 157967.89 | 157967.89 | 157967.89 | 157967.89 | 157967.89
0 |  | W_F.10015.02.14.04: OSISoft PI Historian Data Visualization | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
-2845922.97 |  | W_F.10015.02.17.01: Distribution Management System | -2845922.97 | -2845922.97 | -2845922.97 | -2845922.97 | -2845922.97 | -2845922.97 | -2845922.97 | -2845922.97 | -2845922.97 | -2845922.97 | -2845922.97 | -2845922.97 | -2845922.97
2845922.97 |  | W_F.10015.02.17.02: ADMS SCADA | 2845922.97 | 2845922.97 | 2845922.97 | 2845922.97 | 2845922.97 | 2845922.97 | 2845922.97 | 2845922.97 | 2845922.97 | 2845922.97 | 2845922.97 | 2845922.97 | 2845922.97
23094.0538 |  | W_F.10015.02.17.03: CLSD ADMS Advanced Apps | 0 | 0 | 0 | 0 | 32603.37 | 32603.37 | 32603.37 | 32603.37 | 32603.37 | 32603.37 | 32603.37 | 32603.37 | 32603.37
1956354.69 |  | W_F.10015.02.18.02: Geospacial Load Forecasting | 1956354.69 | 1956354.69 | 1956354.69 | 1956354.69 | 1956354.69 | 1956354.69 | 1956354.69 | 1956354.69 | 1956354.69 | 1956354.69 | 1956354.69 | 1956354.69 | 1956354.69
0 |  | W_F.10015.02.19.02: SSIS Version 2019 Upgrade | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
131274.2687 |  | W_F.10015.02.20.01: Annual Market Changes to Support CAISO | 118095.05 | 118163.32 | 117730.91 | 117730.91 | 117730.91 | 135222.91 | 135222.91 | 135222.91 | 135222.91 | 135222.91 | 135222.91 | 135222.91 | 196654.56
386246.23 |  | W_F.10015.02.22.01: ESO Video Wall Replacement | 386246.23 | 386246.23 | 386246.23 | 386246.23 | 386246.23 | 386246.23 | 386246.23 | 386246.23 | 386246.23 | 386246.23 | 386246.23 | 386246.23 | 386246.23
81555.3558 |  | W_F.10015.02.23.01: ERX Migration | 0 | 79400.6 | 82392.16 | 84357.97 | 85725.54 | 86238.4 | 86238.4 | 86238.4 | 86238.4 | 86238.4 | 86238.4 | 86238.4 | 86238.4
26993.5692 |  | W_F.10015.02.24.01: PI Vision Suite Migration | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 647845.66
0 |  | W_F.10015.02.25.01: Task Factory Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_F.10015.02.26.01: Annual SmallWorld Upgrade | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100132.16 |  | W_F.10015.04.02.03: MDMS 7.5 Upgrade | 100132.16 | 100132.16 | 100132.16 | 100132.16 | 100132.16 | 100132.16 | 100132.16 | 100132.16 | 100132.16 | 100132.16 | 100132.16 | 100132.16 | 100132.16
43678.6012 |  | W_F.10015.04.02.04: MDMS License Extension 2022-2026 | 0 | 37832.63 | 37832.63 | 37832.63 | 37832.63 | 37832.63 | 37832.63 | 37832.63 | 37832.63 | 37832.63 | 37832.63 | 37832.63 | 215968.57
256985.73 |  | W_F.10015.04.02.05: MDMS DB Partitioning Truncation | 256985.73 | 256985.73 | 256985.73 | 256985.73 | 256985.73 | 256985.73 | 256985.73 | 256985.73 | 256985.73 | 256985.73 | 256985.73 | 256985.73 | 256985.73
0 |  | W_F.10015.04.06.01: Annual Smart Community Center Upgrade | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7325.9617 |  | W_F.10015.04.07.01: LoadSEER Non-production Environmnt Purch | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175823.08
0 |  | W_F.10015.04.07.02: Annual LoadSEER Upgrade | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_F.10015.04.08.01: AMI Command Center Upgrade | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_F.10015.04.09.01: MV90 Upgrade | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
614491.21 |  | W_F.10015.05.04.01: Quality Framework | 590208.93 | 602436.7 | 615926.03 | 615704.37 | 617026.23 | 617026.23 | 617026.23 | 617026.23 | 617026.23 | 617026.23 | 617026.23 | 617026.23 | 617026.23
7321.5125 |  | W_F.10015.05.04.02: Annual Quality Framework Enhancemnt 2023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175716.3
0 |  | W_F.10015.05.09.01: ESRI Enterprise Platform Prep Work | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11260.1771 |  | W_F.10015.05.10.01: Work Manager Upgrade | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270244.25
447725.04 |  | W_F.10015.06.05.01: SAP HR Support Packs | 447725.04 | 447725.04 | 447725.04 | 447725.04 | 447725.04 | 447725.04 | 447725.04 | 447725.04 | 447725.04 | 447725.04 | 447725.04 | 447725.04 | 447725.04
371131.9508 |  | W_F.10015.06.05.02: SAP HR Support Packs 2022-2026 | 253010.78 | 239947.22 | 249046.14 | 251033.53 | 256071.15 | 256071.15 | 256071.15 | 256071.15 | 544976.5 | 572285.42 | 576308.02 | 578392.87 | 581607.44
14710.5437 |  | W_F.10015.06.23.02: SAP BW 7.5 Functional Upgrade | 0 | 0 | 16812.05 | 16812.05 | 16812.05 | 16812.05 | 16812.05 | 16812.05 | 16812.05 | 16812.05 | 16812.05 | 16812.05 | 16812.05
0 |  | W_F.10015.06.24.02: POI HANA Sizing & Optimization | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6516.6904 |  | W_F.10015.06.24.03: POI - HANA DR Enablement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156400.57
1802093.5896 |  | W_F.10015.06.25.01: SAP Annual Upgrades 2022-2026 | 1776208.42 | 1817768.1 | 1777968.84 | 1777968.84 | 1777968.84 | 1777968.84 | 1777968.84 | 1777968.84 | 1777968.84 | 1777968.84 | 1777968.84 | 1778547.96 | 2277966.49
589455.7008 |  | W_F.10015.06.26.01: Enhanced SAP Monitoring Alerting BPM | 588672.33 | 590171.74 | 589424.81 | 589424.81 | 589424.81 | 589424.81 | 589424.81 | 589424.81 | 589424.81 | 589424.81 | 589424.81 | 589424.81 | 589424.81
2053.65 |  | W_F.10015.06.26.02: SAP Business Process Monitoring | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49287.6
203586.6083 |  | W_F.10015.06.27.01: Cloud Connector SLS11 to SLS15 Upgrade | 0 | 212438.2 | 212438.2 | 212438.2 | 212438.2 | 212438.2 | 212438.2 | 212438.2 | 212438.2 | 212438.2 | 212438.2 | 212438.2 | 212438.2
5719.2533 |  | W_F.10015.06.28.01: Annual SQL Server Patches | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137262.08
0 |  | W_F.10015.06.29.01: SAP Systems Data Archiving (2024-26) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2029399.2 |  | W_F.10015.08.03.05: IAM Stability and Enhancement | 2029399.2 | 2029399.2 | 2029399.2 | 2029399.2 | 2029399.2 | 2029399.2 | 2029399.2 | 2029399.2 | 2029399.2 | 2029399.2 | 2029399.2 | 2029399.2 | 2029399.2
0 |  | W_F.10015.08.11.04: ServiceNow New York Upgrade | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
877485.0221 |  | W_F.10015.08.11.06: ServiceNow Improvements 2022-2026 | 240888.25 | 240888.25 | 240888.25 | 240888.25 | 1115326.67 | 1091521.84 | 1092660.07 | 1093627.57 | 1048627.57 | 1093627.57 | 1093627.57 | 1093627.57 | 1928129.92
16232.8879 |  | W_F.10015.08.11.07: Annual ServiceNow Platform Upgrades | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35417.21 | 35417.21 | 35417.21 | 35417.21 | 35417.21 | 35417.21
0 |  | W_F.10015.08.13.01: UI Enhancements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3614400.62 |  | W_F.10015.08.13.03: UI Enhancements Phase 3 | 3614400.62 | 3614400.62 | 3614400.62 | 3614400.62 | 3614400.62 | 3614400.62 | 3614400.62 | 3614400.62 | 3614400.62 | 3614400.62 | 3614400.62 | 3614400.62 | 3614400.62
0 |  | W_F.10015.08.13.04: Annual UI Planner Upgrade | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
842222.64 |  | W_F.10015.08.14.03: Sitecore 9.3 to 10.2 Upgrade | 0 | 0 | 0 | 0 | 0 | 1284042.39 | 1375828.38 | 1349976.41 | 1352712.85 | 1354705.84 | 1355317.49 | 1355873.54 | 1356429.56
20240.5367 |  | W_F.10015.08.14.04: Sitecore Autoscaling 2023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485772.88
20110.2817 |  | W_F.10015.08.14.05: Consolidate Web Platforms | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 482646.76
0 |  | W_F.10015.08.16.02: Cassandra (Astra) Data Reconciliation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_F.10015.08.16.03: PI/PO Notifications Migration to CPI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
102832.7008 |  | W_F.10015.08.18.01: Microservices NET Core Upgrade | 102980.74 | 102857.01 | 102949.67 | 102857.28 | 102804.48 | 102804.48 | 102804.48 | 102804.48 | 102804.48 | 102804.48 | 102804.48 | 102804.48 | 102804.48
16279.52 |  | W_F.10015.08.18.02: Microservices Refactoring with Cassandra | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 390708.48
0 |  | W_F.10015.08.18.03: AWS Container Stabilization | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_F.10015.08.18.04: Service Health Dashboard for API Gateway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45624.7863 |  | W_F.10015.08.19.01: Terraform Upgrade | 52869.98 | 45557.92 | 45280.78 | 45286.71 | 45286.71 | 45286.71 | 45286.71 | 45286.71 | 45286.71 | 45286.71 | 45286.71 | 45286.71 | 45286.71
0 |  | W_F.10015.08.19.02: Terraform Build Improvements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3501.5942 |  | W_F.10015.08.20.01: Annual Splunk Growth (2023-27) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84038.26
7308.5312 |  | W_F.10015.08.20.02: Splunk Version Upgrades 2023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175404.75
2873.49 |  | W_F.10015.08.20.03: Annual Splunk Security Improvements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68963.76
19650.2083 |  | W_F.10015.08.21.01: DataStax Astra Migration | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 471605
31186.0642 |  | W_F.10015.08.23.01: Xamarin Forms Migration to MAUI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 748465.54
289311.6454 |  | W_F.10015.08.24.01: Twilio/SendGrid Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 767132.93 | 773597.86 | 772322.51 | 772438.32 | 772496.25
0 |  | W_F.10015.08.25.01: eGain Improvements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_F.10015.08.26.01: Azure Dev Ops (ADO) Upgrade | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_F.10015.08.27.01: Optimization of VDI Instance for Web | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_F.10015.08.28.01: Monitor and Alert Sys for Extrnl Compnnt | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
139490.2 |  | W_F.10015.11.02.01: Command Center Upgrade 2021 | 139490.2 | 139490.2 | 139490.2 | 139490.2 | 139490.2 | 139490.2 | 139490.2 | 139490.2 | 139490.2 | 139490.2 | 139490.2 | 139490.2 | 139490.2
154464.01 |  | W_F.10015.11.03.01: Gas Control Workstations Upgrade | 154464.01 | 154464.01 | 154464.01 | 154464.01 | 154464.01 | 154464.01 | 154464.01 | 154464.01 | 154464.01 | 154464.01 | 154464.01 | 154464.01 | 154464.01
149150.5817 |  | W_F.10015.11.04.01: Windows Server 2012 Upgrade | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3579613.96
66577.0546 |  | W_F.10015.11.06.01: Migration to Dynatrace SaaS | 63848.45 | 66595.13 | 66595.13 | 66716.86 | 66716.86 | 66716.86 | 66716.86 | 66716.86 | 66716.86 | 66716.86 | 66716.86 | 66716.86 | 66716.86
0 |  | W_F.10015.11.08.01: Annual Everbridge Upgrade | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_F.10015.11.09.01: Archer Enhancements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
312301.53 |  | W_F.10015.12.01.01: MIGRATE FROM TABLEAU TO POWER BI | 312301.53 | 312301.53 | 312301.53 | 312301.53 | 312301.53 | 312301.53 | 312301.53 | 312301.53 | 312301.53 | 312301.53 | 312301.53 | 312301.53 | 312301.53
0 |  | W_F.10015.12.01.02: Annual Power BI Upgrades | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_F.10015.12.02.01: SQL Server Audit Compliance Tool | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_F.10015.12.02.02: SQL Server Lab Environment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
305888.91 |  | W_F.10016.01.01.02: CLSD IT Enterprise Architecture System | 305888.91 | 305888.91 | 305888.91 | 305888.91 | 305888.91 | 305888.91 | 305888.91 | 305888.91 | 305888.91 | 305888.91 | 305888.91 | 305888.91 | 305888.91
42946.4667 |  | W_F.10016.01.01.03: IT Enterprise Architecture Tool 2022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143900.2 | 145038.43 | 145209.17 | 162419.6
50745.9987 |  | W_F.10016.01.01.04: IT Enterprise Architecture 2023-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163835.6 | 172694.93 | 180349.55 | 184143.81
27004.17 |  | W_F.10017.02.01.02: CLSD Annual Comm Room Refresh | 27004.17 | 27004.17 | 27004.17 | 27004.17 | 27004.17 | 27004.17 | 27004.17 | 27004.17 | 27004.17 | 27004.17 | 27004.17 | 27004.17 | 27004.17
249640.0192 |  | W_F.10017.02.01.03: CLSD Annual Comm Room Tech Refresh 2022 | 250954.45 | 249582.87 | 249582.87 | 249582.87 | 249582.87 | 249582.87 | 249582.87 | 249582.87 | 249582.87 | 249582.87 | 249582.87 | 249582.87 | 249582.87
425.05 |  | W_F.10017.02.02.02: Annual Data Center Refresh and Growth | 425.05 | 425.05 | 425.05 | 425.05 | 425.05 | 425.05 | 425.05 | 425.05 | 425.05 | 425.05 | 425.05 | 425.05 | 425.05
299819.3962 |  | W_F.10017.02.02.03: Annual Data Center Tech Refresh 2022-26 | 327695.64 | 327357.88 | 327357.88 | 292554.65 | 292554.65 | 292554.65 | 292554.65 | 292554.65 | 292554.65 | 292554.65 | 292554.65 | 292554.65 | 292554.65
17841.6771 |  | W_F.10017.02.02.04: Annual Data Center Tech Refresh (2023+) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 428200.25
1961451.91 |  | W_F.10017.02.04.02: Enterpr Monitoring Standardization 2022 | 1961451.91 | 1961451.91 | 1961451.91 | 1961451.91 | 1961451.91 | 1961451.91 | 1961451.91 | 1961451.91 | 1961451.91 | 1961451.91 | 1961451.91 | 1961451.91 | 1961451.91
19981.15 |  | W_F.10017.03.01.03: PC and TB Refresh New | 19981.15 | 19981.15 | 19981.15 | 19981.15 | 19981.15 | 19981.15 | 19981.15 | 19981.15 | 19981.15 | 19981.15 | 19981.15 | 19981.15 | 19981.15
3346674.6608 |  | W_F.10017.03.05.02: Annual End User PC Refresh 2022-2026 | 3157927.13 | 3182103.33 | 3227011.39 | 3259549.36 | 3292087.33 | 3292087.33 | 3287378.37 | 3287378.37 | 3287729.47 | 2769736.85 | 2769736.85 | 2769736.85 | 8313193.73
5796.9458 |  | W_F.10017.03.08.01: Annual AV/Conf Room Tech Refresh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 139126.7
0 |  | W_F.10017.03.08.02: Annual AV/Conf Room Tech Refrsh (2024+) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_F.10017.03.09.01: InTune Migration | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_F.10017.03.10.01: Digital Experience Monitoring Tool | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_F.10017.03.11.01: Hardware Asset Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_F.10017.04.03.02: eWFM Back Office Component | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
116729.8438 |  | W_F.10017.05.03.02: Annual MS Enterprise Agreement Growth | 0 | 0 | 0 | 0 | 0 | 0 | 215501.25 | 215501.25 | 215501.25 | 215501.25 | 215501.25 | 215501.25 | 215501.25
425238.88 |  | W_F.10017.05.04.01: Workplace Mobility Program | 425238.88 | 425238.88 | 425238.88 | 425238.88 | 425238.88 | 425238.88 | 425238.88 | 425238.88 | 425238.88 | 425238.88 | 425238.88 | 425238.88 | 425238.88
115602.2992 |  | W_F.10017.05.07.01: DC Battery Management | 113200.85 | 115706.71 | 115706.71 | 115706.71 | 115706.71 | 115706.71 | 115706.71 | 115706.71 | 115706.71 | 115706.71 | 115706.71 | 115706.71 | 115706.71
38937.3917 |  | W_F.10017.05.07.02: DC Battery Management 2022-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186899.48 | 186899.48 | 186899.48
299332.45 |  | W_F.10017.05.08.01: Underground Fuel Tank Removal | 299332.45 | 299332.45 | 299332.45 | 299332.45 | 299332.45 | 299332.45 | 299332.45 | 299332.45 | 299332.45 | 299332.45 | 299332.45 | 299332.45 | 299332.45
0 |  | W_F.10017.05.09.01: IT Enterprise Architecture (2024+) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
277977.2075 |  | W_F.10017.07.01.03: IPP SharePoint Upgrade NERC | 306484.38 | 308637.66 | 273699.68 | 273699.68 | 273699.68 | 273699.68 | 273699.68 | 273699.68 | 273699.68 | 273699.68 | 273699.68 | 273699.68 | 273699.68
21785.0292 |  | W_F.10017.07.01.04: OpenText ECM Upgrade | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 522840.7
0 |  | W_F.10017.07.01.05: EDRMS Phase 2 (OpenText) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
73787.27 |  | W_F.10017.08.02.02: CLSD Annual Scada Refresh New | 73787.27 | 73787.27 | 73787.27 | 73787.27 | 73787.27 | 73787.27 | 73787.27 | 73787.27 | 73787.27 | 73787.27 | 73787.27 | 73787.27 | 73787.27
50274.3325 |  | W_F.10017.08.02.03: Annual Telecom SCADA Refresh 2022-26 | 0 | 0 | 0 | 55161.39 | 54615.66 | 54617.24 | 57531.27 | 58191.93 | 59470.02 | 62492.99 | 62492.99 | 92479 | 92479
4764444.6179 |  | W_F.10017.08.03.01: Enhanced Substation Communications | 3356315.07 | 3384459.51 | 3650220.15 | 3681268.24 | 3720769.4 | 3993881.8 | 5588202.92 | 5600693.91 | 5614960.75 | 5617728.95 | 5622683.71 | 6012359.49 | 6015898.1
1437719.2871 |  | W_F.10017.08.07.01: 700MHz Spectrum | 1428860.64 | 1433407.72 | 1433706.78 | 1439061.75 | 1439061.75 | 1439061.75 | 1439061.75 | 1439061.75 | 1439061.75 | 1439061.75 | 1439061.75 | 1439061.75 | 1439061.75
156192.5104 |  | W_F.10017.08.08.01: ASAT to RTAC Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 263831.33 | 285234.24 | 294440.94 | 294440.94 | 294545.07 | 294545.07 | 294545.07
524957.73 |  | W_F.10017.09.04.07: SAP Security Roles Optimization | 524957.73 | 524957.73 | 524957.73 | 524957.73 | 524957.73 | 524957.73 | 524957.73 | 524957.73 | 524957.73 | 524957.73 | 524957.73 | 524957.73 | 524957.73
33306.6983 |  | W_F.10017.09.11.01: Annual Network&Voice Tech Refresh/Growth | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 799360.76
181562.6663 |  | W_F.10017.10.06.04: Annual Server Growth 2022-2026 | 173015.98 | 173015.98 | 173015.98 | 173015.98 | 173015.98 | 173015.98 | 173015.98 | 173015.98 | 173015.98 | 173015.98 | 173015.98 | 173015.98 | 378136.45
496454.1504 |  | W_F.10017.10.09.02: Hyper Converged Infra Refresh | 247721.98 | 247721.98 | 247730.05 | 251810.18 | 251848.15 | 258739.01 | 258860.91 | 646687.36 | 687529.98 | 687773.81 | 694561.97 | 696315.5 | 1808019.83
68394.5233 |  | W_F.10017.10.18.01: Directory Services Optimization | 0 | 0 | 0 | 0 | 0 | 106156.73 | 106156.73 | 108241.58 | 106035.64 | 105414.75 | 115491.54 | 115491.54 | 115491.54
882038.44 |  | W_F.10017.10.19.01: Data Center UPS Battery Replacement | 882038.44 | 882038.44 | 882038.44 | 882038.44 | 882038.44 | 882038.44 | 882038.44 | 882038.44 | 882038.44 | 882038.44 | 882038.44 | 882038.44 | 882038.44
5388.1704 |  | W_F.10017.10.20.01: Annual Corporate Comm Room Tech Refresh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 129316.09
5284.4992 |  | W_F.10017.10.21.01: Purch & Implmnt Syst Orchestration Tool | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126827.98
0 |  | W_F.10017.10.22.01: Annual Server and Storage Growth (2024+) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
470084.62 |  | W_F.10017.11.01.03: Annual Strge Bckup Growth Refresh New | 470084.62 | 470084.62 | 470084.62 | 470084.62 | 470084.62 | 470084.62 | 470084.62 | 470084.62 | 470084.62 | 470084.62 | 470084.62 | 470084.62 | 470084.62
576230.9425 |  | W_F.10017.11.01.04: Annual Storage Growth 2022-2026 | 576124.28 | 576124.28 | 576246.18 | 576246.18 | 576246.18 | 576246.18 | 576246.18 | 576246.18 | 576246.18 | 576246.18 | 576246.18 | 576246.18 | 576246.18
33539.71 |  | W_F.10017.12.01.02: CLSD Annual Fiber Refresh New | 33539.71 | 33539.71 | 33539.71 | 33539.71 | 33539.71 | 33539.71 | 33539.71 | 33539.71 | 33539.71 | 33539.71 | 33539.71 | 33539.71 | 33539.71
509616.8854 |  | W_F.10017.12.01.03: Annual Fiber Refresh Repair 2022-26 | 476264.6 | 478222.42 | 481055.04 | 484151.46 | 491474.43 | 481808.45 | 481808.45 | 481808.45 | 481808.45 | 481808.45 | 525242.35 | 525242.35 | 965680.05
0 |  | W_F.10017.12.03.01: Annual Microwave Radio Refresh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
93040.03 |  | W_F.10017.12.05.02: CLSD Annual RF Refresh New | 93040.03 | 93040.03 | 93040.03 | 93040.03 | 93040.03 | 93040.03 | 93040.03 | 93040.03 | 93040.03 | 93040.03 | 93040.03 | 93040.03 | 93040.03
224597.535 |  | W_F.10017.12.05.03: Annual Telecom RF Refresh 2022-26 | 148811.33 | 149032.47 | 163363.41 | 180144.45 | 180144.45 | 180144.45 | 180144.45 | 180144.45 | 596633.41 | 206707.07 | 207366.91 | 211352.97 | 371172.53
0 |  | W_F.10017.12.06.02: CLSD Telecom Equipment Refresh and Grwth | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
64189.1804 |  | W_F.10017.12.06.03: Annual Telecom Equip Growth Tool 2022-26 | 57991.95 | 57408.14 | 58047.67 | 58047.67 | 58047.67 | 58047.67 | 58047.67 | 58047.67 | 58047.67 | 58047.67 | 58047.67 | 58047.67 | 206778.7
68093.81 |  | W_F.10017.12.08.01: CLSD Annual Telecom Netwrk Refrh n Grwth | 68093.81 | 68093.81 | 68093.81 | 68093.81 | 68093.81 | 68093.81 | 68093.81 | 68093.81 | 68093.81 | 68093.81 | 68093.81 | 68093.81 | 68093.81
0 |  | W_F.10017.12.08.02: Transport Refresh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
225526.3108 |  | W_F.10017.12.08.04: Annual Telecom Network Refresh 2022-2026 | 146553.17 | 174982.86 | 177533.72 | 211074.36 | 212354.47 | 213061.95 | 215596.78 | 229000.09 | 229359.82 | 230288.55 | 230288.55 | 230288.55 | 558418.89
0 |  | W_F.10017.12.17.02: Upper Baker Glover Tower Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
405774.37 |  | W_F.10017.12.23.03: CLSD Network Refresh n Growth New | 405774.37 | 405774.37 | 405774.37 | 405774.37 | 405774.37 | 405774.37 | 405774.37 | 405774.37 | 405774.37 | 405774.37 | 405774.37 | 405774.37 | 405774.37
832388.7712 |  | W_F.10017.12.23.04: Annual Network Tech Refresh 2022-2026 | 508126.07 | 626968.87 | 637936.83 | 637936.83 | 637936.83 | 896626.89 | 968799.38 | 968799.38 | 968799.38 | 968799.38 | 968799.38 | 968799.38 | 968799.38
77748.9754 |  | W_F.10017.12.25.02: Annual Audio Visual Tech Refresh 2022-26 | 75762.13 | 77835.36 | 77835.36 | 77835.36 | 77835.36 | 77835.36 | 77835.36 | 77835.36 | 77835.36 | 77835.36 | 77835.36 | 77835.36 | 77835.36
1319265.1554 |  | W_F.10017.12.26.01: Generation Sites | 1318800.55 | 1319677.38 | 1319248.02 | 1319248.02 | 1319248.02 | 1319248.02 | 1319248.02 | 1319248.02 | 1319248.02 | 1319248.02 | 1319248.02 | 1319248.02 | 1319248.02
581778.4796 |  | W_F.10017.12.26.02: Generation Infrastructure Prgrm 2022-26 | 321365.08 | 327355.63 | 328808.76 | 356917.62 | 357347.14 | 358566.27 | 362760.61 | 362882.51 | 363392.2 | 368287.43 | 371347.06 | 1924032.09 | 2677923.79
1244576.51 |  | W_F.10017.12.27.01: Move of Telecom Core | 1244576.51 | 1244576.51 | 1244576.51 | 1244576.51 | 1244576.51 | 1244576.51 | 1244576.51 | 1244576.51 | 1244576.51 | 1244576.51 | 1244576.51 | 1244576.51 | 1244576.51
0 |  | W_F.10017.12.28.01: GIS Fiber Mapping | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18530.5379 |  | W_F.10017.12.29.01: Annual Telecom Comm Sites Tech Refresh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27234.43 | 27234.43 | 335795.19
10221.9863 |  | W_F.10017.13.01.03: CLSD Annual Voice Equipment Refresh New | 0 | 0 | 11682.27 | 11682.27 | 11682.27 | 11682.27 | 11682.27 | 11682.27 | 11682.27 | 11682.27 | 11682.27 | 11682.27 | 11682.27
139346.36 |  | W_F.10017.13.03.02: VOIP Deployment and Refresh | 139346.36 | 139346.36 | 139346.36 | 139346.36 | 139346.36 | 139346.36 | 139346.36 | 139346.36 | 139346.36 | 139346.36 | 139346.36 | 139346.36 | 139346.36
596672.58 |  | W_F.10017.13.04.01: CLSD Corp SIP Trunking Expansion | 596672.58 | 596672.58 | 596672.58 | 596672.58 | 596672.58 | 596672.58 | 596672.58 | 596672.58 | 596672.58 | 596672.58 | 596672.58 | 596672.58 | 596672.58
292458.5338 |  | W_F.10017.13.05.01: ACTR 2021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 989908.12 | 997954.03 | 1003202.04 | 1036876.43
160713.3154 |  | W_F.10017.13.06.01: Voice Recording Tech Refresh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 506886.56 | 508994.63 | 622535.84 | 580285.51
0 |  | W_F.10017.15.01.03: Automation API Platform | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25395.8412 |  | W_F.10017.15.01.04: Cloud Cost Optimization Tooling Refresh | 0 | 0 | 0 | 0 | 0 | 0 | 46884.63 | 46884.63 | 46884.63 | 46884.63 | 46884.63 | 46884.63 | 46884.63
402444.1 |  | W_F.10018.02.02.01: IT Client Software Growth | 402444.1 | 402444.1 | 402444.1 | 402444.1 | 402444.1 | 402444.1 | 402444.1 | 402444.1 | 402444.1 | 402444.1 | 402444.1 | 402444.1 | 402444.1
4803143 |  | W_F.10018.02.03.01: Opex to Capex Maint | 4803143 | 4803143 | 4803143 | 4803143 | 4803143 | 4803143 | 4803143 | 4803143 | 4803143 | 4803143 | 4803143 | 4803143 | 4803143
13513539.7771 |  | W_F.10018.02.03.02: Opex to Capital Maint 2022-2026 | 13890829.82 | 13890829.82 | 12283147.82 | 12283147.82 | 12283147.82 | 12283147.82 | 12283147.82 | 12283147.82 | 12283147.82 | 12283147.82 | 12283147.82 | 12283147.82 | 36989508.79
94392.6588 |  | W_F.10018.02.04.01: Annual Enterprise App Growth 2022-2026 | 0 | 38647.5 | 38647.5 | 62236.84 | 62236.84 | 100573.54 | 100573.54 | 100573.54 | 100573.54 | 100573.54 | 100573.54 | 100573.54 | 453856.89
3774788.5771 |  | W_F.10025.01.04.01: Physical Security Roadmap | 3464827.47 | 3655305.36 | 3655814.33 | 3659523.57 | 3659974.83 | 3660115.85 | 3660115.85 | 3660115.85 | 3660115.85 | 3660115.85 | 3660115.85 | 3660115.85 | 6627240.3
92102.4608 |  | W_F.10025.01.04.02: Cyber Audit Web Server Upgrade | 92038.92 | 92778.73 | 92041.08 | 92041.08 | 92041.08 | 92041.08 | 92041.08 | 92041.08 | 92041.08 | 92041.08 | 92041.08 | 92041.08 | 92041.08
0 |  | W_F.10025.01.04.03: DNA Fusion Upgrade | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_F.10025.01.04.04: Threat Vulnerability Assessment (TVA) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25684.6987 |  | W_F.10025.01.04.05: Reconeyez Wireless Video | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 616432.77
0 |  | W_F.10025.01.04.06: Phys Sec Imprvmts-High-Risk Sites & Sys | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_F.10025.01.04.07: O'Brien Sub Phys Security Enhancements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_F.10025.01.04.09: ESO Physical Security Enhancements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_F.10025.01.04.10: SKC SVC Physical Security Enhancements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_F.10025.01.04.11: TAC SVC Physical Security Enhancements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
57195.3879 |  | W_F.10025.01.05.01: Zero Trust Strategy for TSA Gas Pipeline | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1372689.31
0 |  | W_F.10025.01.05.02: Physical Security Gas Facility Improv | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31392.8267 |  | W_F.10025.01.05.03: Jackson Prairie IT Infrastructure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110733.27 | 159431.7 | 213097.9
0 |  | W_F.10025.01.05.04: Zero Trust Strategy - Enterprise | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12718.16 |  | W_F.10025.02.01.06: CDC Extension & Efficiency | 12718.16 | 12718.16 | 12718.16 | 12718.16 | 12718.16 | 12718.16 | 12718.16 | 12718.16 | 12718.16 | 12718.16 | 12718.16 | 12718.16 | 12718.16
183047.7692 |  | W_F.10025.02.01.07: Transportation Security Admin TSA | 0 | 0 | 0 | 122595.67 | 243997.36 | 243997.36 | 243997.36 | 243997.36 | 243997.36 | 243997.36 | 243997.36 | 243997.36 | 243997.36
1102222.7667 |  | W_F.10025.02.01.08: Cyber Security Roadmap | 0 | 1118328.55 | 828246.08 | 1253596.07 | 1283632.08 | 1319203.41 | 1353868.81 | 1365249.41 | 1155922.34 | 1014568.26 | 1044290.89 | 1052140.36 | 875253.88
867363.13 |  | W_F.10026.01.01.01: Robotic Process Automation | 836483.47 | 864144.95 | 863683.03 | 863683.03 | 872617.17 | 872617.17 | 872152.77 | 869312.31 | 869312.31 | 869312.31 | 869312.31 | 869312.31 | 869312.31
59322.22 |  | W_F.10026.01.01.02: Workspace Reservation System | 59322.22 | 59322.22 | 59322.22 | 59322.22 | 59322.22 | 59322.22 | 59322.22 | 59322.22 | 59322.22 | 59322.22 | 59322.22 | 59322.22 | 59322.22
17325.9292 |  | W_F.10026.01.01.03: Robotic Process Automation (2023-27) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 415822.3
0 |  | W_F.10028.01.01.01: Performance Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_F.10028.01.02.01: Activity Based Forecasting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21865008.7858 |  | W_GAS PRECAP: Gas precap | 17791726.73 | 18767713.27 | 20308869.61 | 20382749.61 | 20969579.44 | 21047867.15 | 22454813.67 | 23476649.19 | 24679057.27 | 24590088.97 | 21754238.02 | 22933378.21 | 24238475.31
340465.4475 |  | W_K.10001.01.01.01: LBK Hydro Plant Work | 148152.47 | 148152.47 | 289061.13 | 289061.13 | 289061.13 | 289061.13 | 411008.68 | 411008.68 | 411008.68 | 411008.68 | 411008.68 | 411008.68 | 482120.13
124877.8221 |  | W_K.10001.01.01.02: LBK Small Tools | 117661.39 | 117661.39 | 124900.9 | 124900.9 | 124900.9 | 124900.9 | 124900.9 | 124900.9 | 124900.9 | 124900.9 | 124900.9 | 124900.9 | 146065.56
3417065.5008 |  | W_K.10001.01.02.01: UBK Hydro Plant Work | 3271155.48 | 3273244.03 | 3273244.03 | 3273244.03 | 3273244.03 | 3273244.03 | 3273244.03 | 3273244.03 | 3273244.03 | 3273244.03 | 3964004.8 | 3964004.8 | 3964004.8
14040.6871 |  | W_K.10001.01.02.02: UBK Small Tools | 4351.9 | 4351.9 | 14077.69 | 14077.69 | 14077.69 | 14077.69 | 14077.69 | 14077.69 | 14077.69 | 14077.69 | 14077.69 | 14077.69 | 42366.99
6855945.35 |  | W_K.10002.01.01.01: LBK Clubhouse Remodel Visitor Center | 6855945.35 | 6855945.35 | 6855945.35 | 6855945.35 | 6855945.35 | 6855945.35 | 6855945.35 | 6855945.35 | 6855945.35 | 6855945.35 | 6855945.35 | 6855945.35 | 6855945.35
1624.43 |  | W_K.10002.01.01.06: LBK FSC Guide Net Replacement | 1624.43 | 1624.43 | 1624.43 | 1624.43 | 1624.43 | 1624.43 | 1624.43 | 1624.43 | 1624.43 | 1624.43 | 1624.43 | 1624.43 | 1624.43
0 |  | W_K.10002.01.01.07: LBK Equipment Storage Building | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17743207.135 |  | W_K.10002.01.02.06: UBK U2 Runner Replacement | 17735305.92 | 17742122.5 | 17742491.59 | 17742491.59 | 17743967.88 | 17743967.88 | 17743967.88 | 17743967.88 | 17743967.88 | 17743967.88 | 17743967.88 | 17743967.88 | 17743967.88
905880.25 |  | W_K.10003.01.01.01: LBK Crest Improvement and Floodwall | 900406.27 | 900406.27 | 900406.27 | 900406.27 | 900406.27 | 900406.27 | 902030.42 | 909834.5 | 912515.66 | 912515.66 | 912572.91 | 912572.91 | 912572.91
0 |  | W_K.10003.01.01.02: LBK Dam Grouting Program | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
501793.9746 |  | W_K.10003.01.01.03: LBK Hatchery Raceway Project | 73042.26 | 73042.26 | 73042.26 | 73042.26 | 73042.26 | 73042.26 | 73042.26 | 73042.26 | 73042.26 | 73042.26 | 73042.26 | 73042.26 | 10363083.41
214347.3746 |  | W_K.10003.02.01.01: UBK Phase II Spillway Stabilization | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5144336.99
17153.78 |  | W_K.10003.02.01.02: UBK W Pass Dike Instrmt n Stability Eval | 17153.78 | 17153.78 | 17153.78 | 17153.78 | 17153.78 | 17153.78 | 17153.78 | 17153.78 | 17153.78 | 17153.78 | 17153.78 | 17153.78 | 17153.78
2674907.135 |  | W_K.10004.01.01.01: COL 500Kv Trans Line | 2630258.21 | 2663748.12 | 2663748.12 | 2663748.12 | 2663748.12 | 2663748.12 | 2663748.12 | 2663748.12 | 2663748.12 | 2663748.12 | 2663748.12 | 2663748.12 | 2965054.39
8759.55 |  | W_K.10006.01.01.01: ENC Small Tools | 8759.55 | 8759.55 | 8759.55 | 8759.55 | 8759.55 | 8759.55 | 8759.55 | 8759.55 | 8759.55 | 8759.55 | 8759.55 | 8759.55 | 8759.55
2049858.7621 |  | W_K.10006.01.01.02: ENC Thermal Plant Work | 1198744.01 | 1238885.88 | 2031209.43 | 2031209.43 | 2031209.43 | 2031209.43 | 2031209.43 | 2031209.43 | 2207661.75 | 2207661.75 | 2207661.75 | 2622071.06 | 2655468.74
0 |  | W_K.10006.01.01.03: ENC Major Maintenance Activity | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_K.10007.01.01.01: FERN Small Tools | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2335924.5388 |  | W_K.10007.01.01.02: FERN Thermal Plant Work | 584026.15 | 584026.15 | 1276944.15 | 1276944.15 | 1276944.15 | 1276944.15 | 1512813.92 | 1517141.88 | 4013108.8 | 4037567.42 | 4255234.32 | 4338485.29 | 4745854.02
9646604.8058 |  | W_K.10007.01.01.03: FERN Major Maintenance Activity | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12878325.96 | 19862517.9 | 21589064.7 | 22265817.07 | 26010244.39 | 26306575.3
439798.5721 |  | W_K.10008.01.01.03: FREDDY 1 Thermal Plant Work | 137200.89 | 137200.89 | 137200.89 | 137200.89 | 137200.89 | 215629.02 | 215629.02 | 480618.39 | 803679.07 | 803679.07 | 844634.1 | 844634.1 | 903352.18
1809814.6013 |  | W_K.10008.01.01.05: FREDDY 1 Major Maintenance Activity | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3981023.18 | 3947613.44 | 3947613.44 | 3947613.44 | 3947613.44 | 3892596.55
22237.3679 |  | W_K.10009.01.01.03: FRA Small Tools | 22178.06 | 22178.06 | 22178.06 | 22178.06 | 22178.06 | 22178.06 | 22178.06 | 22178.06 | 22178.06 | 22178.06 | 22178.06 | 22178.06 | 23601.45
4214670.3 |  | W_K.10009.01.01.04: FRA Thermal Plant Work | 655845.82 | 1940175.36 | 4306615.37 | 4312885.52 | 4343388.54 | 4408784.7 | 4642147.1 | 4667751.71 | 4682631.55 | 4688342.73 | 4718637.84 | 4975571.29 | 5122377.96
0 |  | W_K.10009.01.01.06: FRA Major Maintenance Activity | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_K.10010.01.01.02: CLSD FRE Thermal Plant Work | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8998.53 |  | W_K.10010.01.01.03: FRE Small Tools | 8998.53 | 8998.53 | 8998.53 | 8998.53 | 8998.53 | 8998.53 | 8998.53 | 8998.53 | 8998.53 | 8998.53 | 8998.53 | 8998.53 | 8998.53
2572960.1654 |  | W_K.10010.01.01.04: FRE Thermal Plant Work | 2139214.87 | 2503725.09 | 2557717.87 | 2558985.86 | 2558985.86 | 2599901.08 | 2618655.45 | 2618697.56 | 2618697.56 | 2619873.34 | 2620194.16 | 2620320.48 | 2620320.48
2146746.1979 |  | W_K.10011.01.03.01: FRE Major Maintenance Activity | 0 | 0 | 0 | 0 | 0 | 3431697.77 | 3431398.53 | 3431398.53 | 3436991.01 | 3436991.01 | 3436991.01 | 3436991.01 | 3436991.01
0 |  | W_K.10011.01.03.02: FRE Electrolyzer Pilot Program | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_K.10012.01.02.06: CLSD CI IVR Enhan Predct n Natural Voice | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
126005.22 |  | W_K.10012.01.05.04: CLSD IWM Work Management System | 126005.22 | 126005.22 | 126005.22 | 126005.22 | 126005.22 | 126005.22 | 126005.22 | 126005.22 | 126005.22 | 126005.22 | 126005.22 | 126005.22 | 126005.22
-29641.09 |  | W_K.10012.01.05.11: IWM EFR Electric First Response | -29641.09 | -29641.09 | -29641.09 | -29641.09 | -29641.09 | -29641.09 | -29641.09 | -29641.09 | -29641.09 | -29641.09 | -29641.09 | -29641.09 | -29641.09
47666.2412 |  | W_K.10013.01.01.01: GLD Small Tools | 44521.57 | 44521.57 | 44521.57 | 44521.57 | 44521.57 | 44521.57 | 44521.57 | 44521.57 | 44521.57 | 44521.57 | 44521.57 | 44521.57 | 119993.68
1862032.3746 |  | W_K.10013.01.01.02: GLD Thermal Plant Work | 1669853.09 | 1679281.9 | 1679281.9 | 1680174.97 | 1681492.39 | 1681098.32 | 1681493.57 | 2003098.34 | 2037737.09 | 2037082.11 | 2037082.11 | 2167083.55 | 2289111.4
-3595.86 |  | W_K.10014.01.01.02: GLD CT Major Maintenance | -3595.86 | -3595.86 | -3595.86 | -3595.86 | -3595.86 | -3595.86 | -3595.86 | -3595.86 | -3595.86 | -3595.86 | -3595.86 | -3595.86 | -3595.86
0 |  | W_K.10014.01.01.07: GLD Major Maintenance Activity | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2404839.2146 |  | W_K.10015.01.01.01: HPK Ongoing UOP Replacements | 1701868.57 | 1731467.72 | 1763817.09 | 1791936.42 | 1817434.97 | 1834150.78 | 1868282.76 | 2786450.25 | 2801439.8 | 3038639.74 | 3282502 | 3342850.89 | 3896327.74
6937.3758 |  | W_K.10015.01.01.02: HPK Small Tools | 5780.45 | 5780.45 | 5780.45 | 5780.45 | 5780.45 | 5780.45 | 5780.45 | 5780.45 | 5780.45 | 5780.45 | 5780.45 | 5780.45 | 33546.67
17926.7946 |  | W_K.10015.01.01.03: HPK Wind Plant Work | 17826.53 | 17826.53 | 17826.53 | 17826.53 | 17826.53 | 17826.53 | 17826.53 | 17826.53 | 17826.53 | 17826.53 | 17826.53 | 17826.53 | 20232.88
2334918.4658 |  | W_K.10016.01.01.01: JP Operational Capital | 1972210.1 | 1987829 | 2238347.22 | 2267810.68 | 2287390.02 | 2313528.49 | 2338250.16 | 2338250.16 | 2385995.76 | 2386024.36 | 2386024.36 | 2386008.54 | 3434915.58
334163.3117 |  | W_K.10017.01.01.01: BKR Aquatic Riparian Habitat | 297080.39 | 297080.39 | 297080.39 | 297080.39 | 301466.65 | 301466.65 | 348853.62 | 361608.01 | 361608.01 | 361608.01 | 373426.97 | 373426.97 | 373426.97
3054790.9 |  | W_K.10017.01.01.02: BKR Develop Recreation Capital | 3054790.9 | 3054790.9 | 3054790.9 | 3054790.9 | 3054790.9 | 3054790.9 | 3054790.9 | 3054790.9 | 3054790.9 | 3054790.9 | 3054790.9 | 3054790.9 | 3054790.9
0 |  | W_K.10017.01.01.03: BKR Elk Habitat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_K.10017.01.02.01: HPK Eagle Conservation Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_K.10017.01.03.01: LSR1 Eagle Conservation Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5926039.5804 |  | W_K.10018.01.01.01: LSR1 Ongoing Uop Replacements | 2366622.33 | 2548559.81 | 2900868.49 | 3174979.03 | 3299582.11 | 3739620.07 | 3779639.54 | 5778241.61 | 7462914.43 | 9019780.99 | 10558865.25 | 11569217.39 | 12193790.16
9314.6883 |  | W_K.10018.01.01.02: LSR1 Small Tools | 8794.7 | 8794.7 | 8794.7 | 8794.7 | 8794.7 | 8794.7 | 8794.7 | 8794.7 | 8794.7 | 8794.7 | 8794.7 | 8794.7 | 21274.42
28702.4571 |  | W_K.10018.01.01.03: LSR1 Wind Plant Work | 0 | 0 | 0 | 0 | 0 | 43140.55 | 43140.55 | 43140.55 | 43140.55 | 43140.55 | 43140.55 | 43140.55 | 84891.27
57901.1842 |  | W_K.10019.01.01.01: MTF Small Tools | 0 | 0 | 82292.93 | 82292.93 | 82292.93 | 56239.75 | 56239.75 | 56239.75 | 56239.75 | 56239.75 | 56239.75 | 56239.75 | 108514.34
2308874.5892 |  | W_K.10019.01.01.02: MTF Thermal Plant Work | 1658913.78 | 1988183.65 | 1988183.65 | 2006108.48 | 2008881.35 | 2052830.8 | 2145593.41 | 2145593.41 | 2354766.46 | 2547152.11 | 2726960.64 | 2781677.82 | 4262212.8
14435849.02 |  | W_K.10020.01.01.03: MTF CT Major Maintenance | 14435849.02 | 14435849.02 | 14435849.02 | 14435849.02 | 14435849.02 | 14435849.02 | 14435849.02 | 14435849.02 | 14435849.02 | 14435849.02 | 14435849.02 | 14435849.02 | 14435849.02
11252071.7821 |  | W_K.10020.01.01.07: MTF Major Maintenance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24640635.29 | 24643737.27 | 24497987.5 | 24497000.53 | 24497000.53 | 24497000.53
301710.2533 |  | W_K.10021.01.01.01: SNO Hydro Plant Work | 86166.02 | 86166.02 | 86166.02 | 358432.42 | 358432.42 | 358432.42 | 358432.42 | 358432.42 | 358432.42 | 358432.42 | 358432.42 | 358432.42 | 358432.42
3849.1562 |  | W_K.10021.01.01.02: SNO Small Tools | 1338.08 | 1338.08 | 3997.11 | 3997.11 | 3997.11 | 3997.11 | 3997.11 | 3997.11 | 3997.11 | 3997.11 | 3997.11 | 3997.11 | 8423.31
0 |  | W_K.10022.01.01.02: SNO Park Bathroom Rebuild | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1796843.84 |  | W_K.10022.01.01.04: SNO U5 Erosion Repair | 1796843.84 | 1796843.84 | 1796843.84 | 1796843.84 | 1796843.84 | 1796843.84 | 1796843.84 | 1796843.84 | 1796843.84 | 1796843.84 | 1796843.84 | 1796843.84 | 1796843.84
4469.62 |  | W_K.10023.01.01.01: SMS Small Tools | 4469.62 | 4469.62 | 4469.62 | 4469.62 | 4469.62 | 4469.62 | 4469.62 | 4469.62 | 4469.62 | 4469.62 | 4469.62 | 4469.62 | 4469.62
4677457.0117 |  | W_K.10023.01.01.02: SMS Thermal Plant Work | 3891601.2 | 3891458.27 | 3987441.93 | 3987441.93 | 4023877.96 | 4031677.77 | 4057854.97 | 5807274.22 | 5421479.22 | 5421479.22 | 5421479.22 | 5421479.22 | 5421479.22
0 |  | W_K.10023.01.01.03: SMS Major Maintenance Activity | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37532.8254 |  | W_K.10025.01.02.01: LNG 1 Mile Pipe Connector | 37404.86 | 37522.64 | 37522.64 | 37522.64 | 37522.64 | 37522.64 | 37522.64 | 37522.64 | 37522.64 | 37522.64 | 37522.64 | 37522.64 | 37884.87
13631.9387 |  | W_K.10025.01.02.02: LNG 4 Mile Pipe To Plant | 13591.18 | 11268.07 | 13859.01 | 13859.01 | 13859.01 | 13859.01 | 13859.01 | 13859.01 | 13859.01 | 13859.01 | 13859.01 | 13859.01 | 13859.01
0 |  | W_K.10025.01.02.03: LNG Clover Creek Limit Station Modi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
684.16 |  | W_K.10025.01.02.06: LNG Golden Givens New Limit Station | 684.16 | 684.16 | 684.16 | 684.16 | 684.16 | 684.16 | 684.16 | 684.16 | 684.16 | 684.16 | 684.16 | 684.16 | 684.16
275238.8438 |  | W_K.10025.02.01.01: TLNG Operational Plant | 0 | 0 | 0 | 0 | 0 | 440382.15 | 440382.15 | 440382.15 | 440382.15 | 440382.15 | 440382.15 | 440382.15 | 440382.15
24710.0788 |  | W_K.10026.01.01.03: WHH Small Tools | 0 | 0 | 28240.09 | 28240.09 | 28240.09 | 28240.09 | 28240.09 | 28240.09 | 28240.09 | 28240.09 | 28240.09 | 28240.09 | 28240.09
1612640.6896 |  | W_K.10026.01.01.04: WHH Thermal Plant Work | 1432511.26 | 1610100.35 | 1610100.35 | 1610100.35 | 1610100.35 | 1610100.35 | 1625878.49 | 1625878.49 | 1625878.49 | 1625878.49 | 1625878.49 | 1625878.49 | 1659319.91
0 |  | W_K.10026.01.01.05: WHH Major Maintenance Activity | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
866.5625 |  | W_K.10028.01.01.01: WLD Small Tools | 0 | 0 | 0 | 0 | 0 | 1386.5 | 1386.5 | 1386.5 | 1386.5 | 1386.5 | 1386.5 | 1386.5 | 1386.5
46326.6175 |  | W_K.10028.01.01.03: WLD Wind Plant Work | 21598.04 | 27359.81 | 27359.81 | 27359.81 | 27359.81 | 58090.82 | 58090.82 | 58090.82 | 58090.82 | 58090.82 | 58090.82 | 58090.82 | 58090.82
3868942.0613 |  | W_K.10028.01.01.04: WLD Ongoing UOP Replacements | 2341537.37 | 2352023.98 | 2362367.1 | 2576197.77 | 3286698.77 | 3305864.73 | 3716770.57 | 4327877.78 | 4358074.6 | 4861366.45 | 5387653.82 | 5808163.66 | 5826953.64
0 |  | W_K.10037.01.01.01: Generation Engineering Small Tools | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_K.10040.01.01.01: Gordon Butte Hydro Pump Storage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_K.10041.01.01.01: CMN Thermal Plant Work | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_K.10042.01.01.01: Appaloosa Solar Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_K.10043.01.01.01: Beaver Creek Plant Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_K.10043.01.01.02: Beaver Creek IT Infrastructure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_PLACEHOLDER_06: Alternative Fuels Supply Procurement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_PLACEHOLDER_116: Energy Efficiency for Facilities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_PLACEHOLDER_118: Facilities Opt - Facility Modernization | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_PLACEHOLDER_142: Cash Payment Transformation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_PLACEHOLDER_143: ADMS Enhancements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_PLACEHOLDER_144: Electric Distribution Digital As Builting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_PLACEHOLDER_145: ETRMS Consolidate - Endur Replace | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_PLACEHOLDER_146: Digital Radio Upgrade | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_PLACEHOLDER_147: Call Center Technology Platform Modernization | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_PLACEHOLDER_148: IWM R5 Customer and Project Enhancement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_PLACEHOLDER_149: IT Ops - Running the Business of IT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_PLACEHOLDER_150: IT Ops - Technology Reliability Hardware | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_PLACEHOLDER_151: IT Ops - Technology Reliability Software | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_PLACEHOLDER_152: IT Ops - Telecom | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_PLACEHOLDER_153: IT Ops - Capitalized Cloud Services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_PLACEHOLDER_154: IT Ops - Capitalized IT Support Agreements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_PLACEHOLDER_155: Advanced Leak Detection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_PLACEHOLDER_156: Bellevue HQ Lease Exit | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_PLACEHOLDER_158: Sewer Cross Bore Predictive Model | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_PLACEHOLDER_159: Appaloosa Solar Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_PLACEHOLDER_160: Virtual Power Plant 2024 and Beyond | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_PLACEHOLDER_163: Rewind/Recore UBK Unit 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_PLACEHOLDER_166: Data Center Hardware Refresh 2026+ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_PLACEHOLDER_167: Data & Analytics Platform Uplift BW BOBJ POI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_PLACEHOLDER_168: SAP Work Manager Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_PLACEHOLDER_169: CEF5 Kittitas BESS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_PLACEHOLDER_170: Data Lake Phase 2 (Operations) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_PLACEHOLDER_171: Potential Transactional Bill Print Vendor Move | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_PLACEHOLDER_175: Supply Chain Warehouse Improvements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_PLACEHOLDER_177: Vernell Building Retirement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_PLACEHOLDER_179: Implement GIS Strategy | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_PLACEHOLDER_180: Click Replacement Enhancements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_PLACEHOLDER_181: ETRMS Consolidate - OATI WebTrader Replace | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_PLACEHOLDER_182: Front Office Data Enablement Phase 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_PLACEHOLDER_183: Enterprise GIS Product Enhancements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_PLACEHOLDER_184: Physical Security Improvements for High-Risk Sites & Systems | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_PLACEHOLDER_185: Tensing Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_PLACEHOLDER_186: Centralia 100MW Hydrogen Peaker | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_PLACEHOLDER_188: Long Duration Storage Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_PLACEHOLDER_189: CEF4 Tenino Alternative Renewable Backup Generator | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_PLACEHOLDER_190: Network Substation Hardware Refresh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_PLACEHOLDER_191: Beaver Creek Wind | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_PLACEHOLDER_192: FRA CT Rotor Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_PLACEHOLDER_193: LSR New Tower | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_PLACEHOLDER_194: GLD CT Rotor Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_PLACEHOLDER_195: DER Demonstrations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_PLACEHOLDER_196: E Transformers Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_PLACEHOLDER_199: Lineage Algona Solar CEIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_PLACEHOLDER_200: Lineage Algona Storage CEIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_PLACEHOLDER_54: New Primary Control Center | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_PLACEHOLDER_63: E King County Franchise Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_PLACEHOLDER_64: G King County Franchise Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_PLACEHOLDER_67: Misc Business Enablement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_PLACEHOLDER_69: Facility Fleet and Supply Chain-Todd Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_PLACEHOLDER_90: Hopkins Ridge DSTATCOM Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_PLACEHOLDER_92: Misc Technology Reliability | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_PLACEHOLDER_99: Replace Service Centers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_R.10002.02.01.01: G Bonney Lake HP Supply Reliability | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_R.10004.01.01.01: C Franchises | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13023623.0933 |  | W_R.10005.01.01.01: E Eastside 230Kv Subs Richards Creek | 79903.81 | 79954.29 | 50825.24 | 77430.03 | 80136.17 | 77438.02 | 77438.02 | 77438.02 | 77438.02 | 44334145.72 | 44452783.12 | 44563597.96 | 44589801.21
2217.57 |  | W_R.10005.01.01.02: E Eastside 230Kv Subs Talbot Hill | 1952.77 | 1952.77 | 1952.77 | 1952.77 | 1952.77 | 2376.45 | 2376.45 | 2376.45 | 2376.45 | 2376.45 | 2376.45 | 2376.45 | 2376.45
0 |  | W_R.10005.01.01.04: E Eastside 230Kv Subs Rose Hill | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_R.10005.01.01.05: E Eastside 230Kv Subs Sammamish | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_R.10005.01.01.06: E Eastside 230Kv Subs Somerset | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41160201.4083 |  | W_R.10005.01.01.07: E Eastside 230Kv Tlines | 275434.16 | 275487.56 | 275569.74 | 275445.74 | 275426.75 | 268854.42 | 269160.51 | 269149.7 | 269147.8 | 95810922.82 | 157866849.33 | 158383072.83 | 159091225.24
61310.67 |  | W_R.10005.01.01.08: E Talbot Hill Paccar Reconductor | 61310.67 | 61310.67 | 61310.67 | 61310.67 | 61310.67 | 61310.67 | 61310.67 | 61310.67 | 61310.67 | 61310.67 | 61310.67 | 61310.67 | 61310.67
6739036.0538 |  | W_R.10006.01.01.03: E Substation SCADA CEIP | 5099694.42 | 5114942.13 | 5126009.72 | 5137259.15 | 5253547.68 | 6093622.91 | 6818462.9 | 6835519.95 | 6857500.86 | 7846530.59 | 7889909.46 | 10212889.12 | 10264781.93
1650120.3388 |  | W_R.10006.01.01.04: E Trans Automation | 1544834.15 | 1555529.44 | 1562295.28 | 1573310.32 | 1603629.12 | 1610708.8 | 1608574.55 | 1616939.03 | 1649413.96 | 1657735.47 | 1664177.66 | 1904526.83 | 2044373.06
621031.1063 |  | W_R.10006.01.01.07: E Electric System Modeling | 475541.9 | 618250.49 | 620331.29 | 622492 | 624572.82 | 626653.76 | 629294.9 | 631455.83 | 631455.83 | 631455.83 | 631455.83 | 631455.83 | 631455.83
2098930.8129 |  | W_R.10006.01.01.08: E Substation SCADA (Non-CEIP) | 1308320.66 | 1315650.5 | 1317153.17 | 1318891.77 | 1319667.21 | 1320724.99 | 1670421.05 | 2864879.57 | 2914845.34 | 2958573.69 | 2966772.25 | 3042254.81 | 3046350.15
174.46 |  | W_R.10007.02.01.02: E Bellingham Substation Rebuild Sub | 174.46 | 174.46 | 174.46 | 174.46 | 174.46 | 174.46 | 174.46 | 174.46 | 174.46 | 174.46 | 174.46 | 174.46 | 174.46
-14236237.5342 |  | W_R.10007.06.01.01: E 5 Yr Electric Refundable CIAC | -8593299.5 | -8593299.5 | -8593299.5 | -11833343.34 | -11833343.34 | -11833343.34 | -15071155.71 | -15071155.71 | -15071155.71 | -19020042.87 | -19020042.87 | -19020042.87 | -23155951.8
-85122.2354 |  | W_R.10007.07.01.01: E Customer Reimbursed | -89137.56 | -88961.56 | -88812.62 | -88636.61 | -88480.15 | -86761.26 | -85662.12 | -82439.27 | -82067.94 | -81794.56 | -81638.09 | -81095.91 | -81095.91
5749455.7404 |  | W_R.10007.08.01.01: E OH UG Commercial Services | 3521762.81 | 3786931.61 | 4155667.88 | 4576308.3 | 4889027.63 | 5272729.43 | 5746395.6 | 6132682.15 | 6547585.55 | 6867079.02 | 7350688.1 | 7824932.12 | 8165120.18
6411287.4467 |  | W_R.10007.08.02.01: E OH UG Residential Services | 4542952.8 | 4042139.9 | 4415189.41 | 5686151 | 5300989.23 | 5655383.43 | 7371400.9 | 6454050.45 | 6906107.89 | 8192658.19 | 7668464.92 | 8133997.86 | 9674879.56
891190.1113 |  | W_R.10007.08.02.02: E UG Residential Services In Plats | 600383.66 | 658070.77 | 687620.05 | 736956.76 | 774572.31 | 805828.44 | 896136.3 | 911416.8 | 974058.85 | 1041932.29 | 1099987.43 | 1185077.28 | 1244864.45
21929471.6546 |  | W_R.10007.09.01.01: E Commercial Line Extension | 10989968.02 | 12051934.19 | 14355034.17 | 14305061.98 | 16585121.96 | 20136917.34 | 21639731.84 | 23426354.22 | 26356828.15 | 28192347.05 | 30687676.7 | 32649490.29 | 34544355.91
4767219.0637 |  | W_R.10007.09.02.01: E Multi Family Line Extension | 3462240.88 | 2100667.1 | 2499467.74 | 4342113.79 | 3108917.82 | 3525590.95 | 5800954.77 | 4762741.96 | 4882195.59 | 7437296.92 | 6272634.48 | 6310309.22 | 8865235.97
22676895.4771 |  | W_R.10007.09.03.02: E Plats Line Extension | 16940601.85 | 16765973.56 | 17118756.69 | 17868279.38 | 18009227.55 | 21116572.74 | 24072428.43 | 23877708.73 | 24960574.33 | 27136349.12 | 27731710.44 | 29128030.16 | 31733667.34
16937534.6183 |  | W_R.10007.09.04.01: E Single Family Line Extension | 11437921.84 | 12248053.42 | 13012835.88 | 14074548.27 | 14677652.92 | 16026360.3 | 17137827.45 | 17318197.51 | 18622642.79 | 19760979.53 | 20929730.36 | 22037006.39 | 23371239.36
6083045.17 |  | W_R.10007.12.01.01: E Microsoft Campus Rebuild | 6310739.7 | 6472117.49 | 6475217.18 | 6456228.08 | 6458921.2 | 6821112.31 | 5786309.35 | 5790865.95 | 5723202.82 | 5699560.01 | 5711205.58 | 5703723.3 | 5485417.84
435418.29 |  | W_R.10007.12.03.01: E Customer Reimbursed Major Projects | 679501.54 | 679597.65 | 872286.49 | 870676.65 | 870676.65 | 446348.75 | 446348.75 | 446348.75 | 446348.75 | -55259.08 | -55241.86 | -55241.86 | -55241.86
0 |  | W_R.10007.12.04.01: Shuffleton Switchyard SECO Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
304051.1754 |  | W_R.10008.01.01.01: E Conversions Sched 73 Cust Driven | -184634.01 | -121167.57 | 314368.01 | 190225.35 | 90565.09 | 157053.28 | 380659.58 | 334430.98 | 623356.28 | 467232.79 | 677771.75 | 417628.46 | 417614.22
1971526.1788 |  | W_R.10008.01.01.02: E OH UG Reloc - Removal Cust Driven Dist | 1538250.08 | 1589462.1 | 2001584.99 | 2090996.55 | 1756975.07 | 1850326.11 | 1898863.93 | 1999091.58 | 2126385.7 | 1951548.56 | 2142289.66 | 2229325.45 | 2504678.81
0 |  | W_R.10008.02.01.01: E Franchises | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3985308.5417 |  | W_R.10008.03.01.01: E Conversions Sched 74 PI Driven | 2683766.63 | 2749322 | 2913354.2 | 2867095.36 | 3092524.44 | 3484866.56 | 4237975.4 | 4217682.2 | 4189323.33 | 4113249 | 5626550.31 | 6044293.75 | 5891165.27
20998268.4879 |  | W_R.10008.03.01.03: E OH UG Rel PI Driven NonReimb Dist | 15215794.22 | 16233981.15 | 16474050.78 | 17684706.42 | 17856959.97 | 18048245.78 | 20331125.32 | 22162345.33 | 24034086.77 | 24659197.38 | 25948916.07 | 26829422.59 | 28216574.37
5067975.2454 |  | W_R.10008.03.01.04: E OH UG Rel PI Driven Reimburse Dist | 4656066.87 | 3842856.75 | 3943441.21 | 4060162.4 | 4403074.79 | 5190078.22 | 5306303.83 | 5377797.43 | 5619863.13 | 5692717.35 | 5698555.3 | 5981516.01 | 6742606.18
1169811.8542 |  | W_R.10008.03.01.05: E PI Driven Relocations Trans | 423517.23 | 470428.77 | 694904.24 | 703167.6 | 813722.73 | 845251.41 | 1105081.37 | 1099762.26 | 1142081.29 | 1828602.28 | 2020152.18 | 2072239.39 | 2061180.23
-156956.6 |  | W_R.10008.03.01.13: E Elec Facility Replacement Trans | -156956.6 | -156956.6 | -156956.6 | -156956.6 | -156956.6 | -156956.6 | -156956.6 | -156956.6 | -156956.6 | -156956.6 | -156956.6 | -156956.6 | -156956.6
212239.2425 |  | W_R.10008.03.01.14: E Sound Transit Reimburse | -101800.39 | -73986.7 | -68701.18 | 235163.37 | 215597.15 | 223900.15 | 237284.65 | 57332.81 | 112580.64 | 515834.87 | 416251.43 | 460283.76 | 532460.31
371733.4883 |  | W_R.10008.03.01.18: E WSDOT Fish Passage Relocation | 0 | 0 | 0 | 0 | 0 | 0 | 201288.27 | 190357.82 | 190357.35 | 649227.58 | 1284550.78 | 1301055.76 | 1287928.6
-1316917.0829 |  | W_R.10008.05.01.01: E Sound Transit Dist | -1336589.93 | -1336589.93 | -1336589.93 | -1336589.93 | -1336589.93 | -1336589.93 | -1336589.93 | -1336589.93 | -1336589.93 | -1336589.93 | -1336589.93 | -1336589.93 | -864441.6
1996182.0521 |  | W_R.10008.05.01.02: E Sound Transit East Link Dist | 1989317.78 | 1992270.23 | 1993802.46 | 1994570.69 | 1994568.54 | 2000578.96 | 2000576.94 | 1996852.08 | 1996852.08 | 1996852.08 | 1997040.67 | 1997040.67 | 1997040.67
235785.4946 |  | W_R.10008.07.01.01: E WSDOT Clr Zone Pole Prog Dist | 208574.06 | 210243.92 | 218910.21 | 224706.19 | 226754.73 | 228045.96 | 230571.6 | 235579.02 | 244248.11 | 254367.96 | 259382.26 | 260945.87 | 262766.15
0 |  | W_R.10008.07.02.01: E King County Clr Zone Pole Prog Dist | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_R.10008.07.02.02: E King County Clr Zone Pole Prog Trans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
311287.8575 |  | W_R.10009.01.01.01: E BPA 3rd AC Transmission Intertie Work | 327481.64 | 287900.54 | 287900.54 | 287900.54 | 287900.54 | 287900.54 | 327600.38 | 327600.38 | 327600.38 | 327600.38 | 327600.38 | 327600.38 | 333216.98
92371.97 |  | W_R.10009.02.01.02: E Central Bellevue Dist Growth Feeder | 92371.97 | 92371.97 | 92371.97 | 92371.97 | 92371.97 | 92371.97 | 92371.97 | 92371.97 | 92371.97 | 92371.97 | 92371.97 | 92371.97 | 92371.97
649406.9483 |  | W_R.10009.02.01.03: E Central Bellevue Dist Rel Feeder | 541599.3 | 578339.63 | 578339.63 | 579128.52 | 580356.5 | 581669.3 | 589564.66 | 596016.76 | 693632.99 | 747487.04 | 790195.73 | 802863.06 | 808979.82
0 |  | W_R.10009.03.01.01: E Clyde Hill Switching Station | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3076216.75 |  | W_R.10009.04.01.02: E Damage Claims Cap Writeoff | 1922547.65 | 2081623.78 | 2224017.63 | 2423273.41 | 2803390.67 | 2935276.76 | 3074393.96 | 3284383.92 | 3385475.74 | 3458933.9 | 3896558.89 | 4165914.98 | 4440167.07
3341514.3892 |  | W_R.10009.05.01.01: E Emergency NonOutage OH Repl Dist | 2181621.01 | 2366196.25 | 2476739.46 | 2663498.95 | 2980918.36 | 3204900.13 | 3424811.84 | 3569311.44 | 3812760.59 | 3904939.42 | 4076135.43 | 4285886.39 | 4482527.81
3391591.0188 |  | W_R.10009.05.01.02: E Emergency NonOutage OH Repl Trans | 2289164.5 | 2555604.54 | 2554173.32 | 2745098.06 | 2818648.41 | 2895339.01 | 3602066.33 | 3728689.19 | 3753701.79 | 4017566.26 | 4216509.87 | 4336510.87 | 4661204.65
2175332.3042 |  | W_R.10009.05.01.03: E Emergency NonOutage UG Repl Dist | 1349699.9 | 1386455.12 | 1499395.55 | 1655606.42 | 1791946.02 | 1880471.78 | 2250442.53 | 2324086.01 | 2370886.91 | 2729514.13 | 2778826.68 | 3055626.9 | 3411759.3
3628635.1688 |  | W_R.10009.05.02.01: E Emergency OH Replacement Trans | 2592100.8 | 2648785.55 | 2650432.78 | 2830741.71 | 2852507.67 | 2876701.72 | 2879571.79 | 2880120.15 | 2880795.58 | 3319438.43 | 3429474.98 | 8546252.5 | 8905497.53
32843694.6383 |  | W_R.10009.05.02.02: E Emergency Outage OH Replacement Dist | 21769469.1 | 24347858.77 | 26179402.89 | 28292311.59 | 29900918.36 | 31284454.89 | 32901796.23 | 33803713.05 | 35635051.2 | 37185374.21 | 39679682.19 | 41812835.56 | 44432404.34
35245985.8887 |  | W_R.10009.05.02.03: E Emergency Outage UG Replacement Dist | 23428162.73 | 24880566.21 | 26038463.62 | 27740386.29 | 29407329.37 | 31508632.54 | 33740899.04 | 35757710.79 | 39321787.53 | 42503970.81 | 46570615.4 | 48565391.57 | 50403992.26
4117382.3358 |  | W_R.10009.05.02.04: E Unplanned OH Distribution Abnormals | 2425364.87 | 2679923.95 | 2749706.62 | 3017571.67 | 3613243.37 | 4017433.82 | 4174599.29 | 4386376.92 | 4514102.21 | 4765738.7 | 5158290.92 | 5951249.89 | 6335336.47
8999290.3588 |  | W_R.10009.05.02.05: E Unplanned UG Distribution Abnormals | 5670839.31 | 6125256.38 | 6676426.52 | 7231670.17 | 7670067.39 | 8344565.68 | 8978784.23 | 9243989.72 | 10375040.09 | 11108346.18 | 11537652.36 | 11849971.59 | 12028588.68
-25407.8638 |  | W_R.10009.07.01.01: E OH System Capacity New Dist | -20729.98 | -20503.8 | -20503.8 | -28016.37 | -28016.37 | -26540.91 | -26540.91 | -26540.91 | -26540.91 | -26092.97 | -26092.97 | -26092.97 | -26092.97
5031545.6292 |  | W_R.10009.07.01.03: E UG System Capacity New Dist | 3939999.06 | 3753426.39 | 4157377.8 | 4193683.7 | 4307122.42 | 4364542.42 | 4521514.67 | 4550836.46 | 5897997.61 | 5991626.15 | 6658414.47 | 6668600.78 | 6686810.3
9133.4854 |  | W_R.10009.07.01.07: E System Planning Software | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43840.73 | 43840.73 | 43840.73
538797.1171 |  | W_R.10009.07.03.01: E OH UG System Improv Opport New Dist | 431779.33 | 431779.33 | 431779.33 | 431779.33 | 446492.39 | 479527.38 | 505799.11 | 578301.53 | 579398.63 | 603468.24 | 688406.55 | 714843.18 | 716201.48
29832678.2675 |  | W_R.10009.08.01.02: E UG Cable Remediation Dist | 22024212.32 | 23888362.82 | 25609582.7 | 26310374.8 | 26829581.32 | 28095543.55 | 30648380.25 | 31770341.2 | 32918146.38 | 34236439.27 | 34381209.03 | 34698734.34 | 35186674.78
14841293.4708 |  | W_R.10009.08.01.07: E UG Cable Remediation Progr IPM | 5476195.09 | 5572626.39 | 6450975.28 | 7250636.78 | 9061552.67 | 11590022.22 | 14106704.25 | 15416342.49 | 18803162.49 | 20081159.6 | 24291752.71 | 26770103.36 | 31924771.73
57.85 |  | W_R.10009.08.02.01: E Bellingham Subs | 57.85 | 57.85 | 57.85 | 57.85 | 57.85 | 57.85 | 57.85 | 57.85 | 57.85 | 57.85 | 57.85 | 57.85 | 57.85
336479.6725 |  | W_R.10009.08.02.05: E OH Clearance Alley Syst Dist | 0 | 0 | 9529.97 | 9529.97 | 9529.97 | 9529.97 | 9529.97 | 9529.97 | 9529.97 | 9529.97 | 9529.97 | 9529.97 | 7884912.74
7371382.0796 |  | W_R.10009.08.02.07: E OH Sys Rel Upgrades Outage Dist | 6293675.33 | 6335199.43 | 6337038.03 | 6330998.36 | 6332191.88 | 6303662.95 | 8268515.36 | 8244191.22 | 8243239.63 | 8246328.43 | 8246360.71 | 8298997.29 | 8246048
12973705.2475 |  | W_R.10009.08.02.09: E OH Syst Rel Upgrades Rebuild Dist | 10545496.86 | 10772629.15 | 10831818.38 | 11043327.05 | 12419463.62 | 12475967.73 | 12481938.39 | 12484230.3 | 15019825.47 | 15099894.34 | 15120308.7 | 15103545.02 | 15117532.78
10707822.5312 |  | W_R.10009.08.02.10: E OH Syst Rel Upgrades UG Convers Dist | 8456216.17 | 8587689.8 | 9007644.16 | 8866929.9 | 8827432.91 | 8847858.29 | 8853668.32 | 8872821.55 | 12714292.51 | 12835565.63 | 12860469.26 | 12870878.68 | 22241022.56
16604.3404 |  | W_R.10009.08.02.11: E OH Syst Rel Upgr Gang OP Switches Dist | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131679.5 | 135145.17
4599754.2796 |  | W_R.10009.08.02.12: E OH Syst Rel Upgr Reclosers Dist | 2853195.32 | 3031565.79 | 3160644.81 | 4015792.99 | 4232842.16 | 4409013.06 | 4822674.12 | 4879085.12 | 5061938.94 | 5537549.07 | 5727084.53 | 5921145.05 | 5942236.11
155988.56 |  | W_R.10009.08.02.13: E UG Sys Rel Upgr Pm Switch Dist | 155988.56 | 155988.56 | 155988.56 | 155988.56 | 155988.56 | 155988.56 | 155988.56 | 155988.56 | 155988.56 | 155988.56 | 155988.56 | 155988.56 | 155988.56
17481134.5208 |  | W_R.10009.08.02.14: E OH Syst Rel Upgr Tree WirE Dist | 12084798.3 | 12448380.44 | 12667930.9 | 12892784.02 | 13010712.07 | 13143254.87 | 13879109.4 | 14600686.14 | 17819373.79 | 24115029.2 | 26533107.91 | 27189972.92 | 30861746.88
1932615.1454 |  | W_R.10009.08.02.15: E OH Syst Rel Upgr Fusesaver Dist | 1448819.9 | 1542068.69 | 1585192.71 | 1695417.93 | 1726079.11 | 1842718.17 | 1837222.28 | 1896607.05 | 1991377.01 | 2152708.27 | 2357892.3 | 2460149.59 | 2759077.37
2685698.6767 |  | W_R.10009.08.02.17: E OH System Capacity Upgrade Dist | 1518266.3 | 1595294.5 | 1666552.61 | 1759222.26 | 1859849.61 | 1948828.32 | 1995325.93 | 2062077.11 | 2183268.32 | 2421355.5 | 3812161.76 | 4127055.96 | 12076518.18
892.18 |  | W_R.10009.08.02.18: E OH Sys Capacity Upgrades Uprates Trans | 892.18 | 892.18 | 892.18 | 892.18 | 892.18 | 892.18 | 892.18 | 892.18 | 892.18 | 892.18 | 892.18 | 892.18 | 892.18
151128.6675 |  | W_R.10009.08.02.19: E OH System Reliability Upgrades Trans | 28219.92 | 28219.92 | 168687.06 | 168687.06 | 168687.06 | 168687.06 | 168687.06 | 168687.06 | 168687.06 | 168687.06 | 168687.06 | 168687.06 | 168687.06
0 |  | W_R.10009.08.02.20: E OH Transformer PCB Remediation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
655494.6429 |  | W_R.10009.08.02.22: E 6 Copper Open Wire 2nd Repl Dist | 524.01 | 593.42 | 348362.36 | 655311.63 | 672863.03 | 613567.07 | 616537.81 | 616830.37 | 1015861.04 | 950876.75 | 941779.83 | 954720.91 | 956738.98
1341948.1083 |  | W_R.10009.08.02.24: E Sedro Mar Pt 230 Remediate Underbuild | 1321999.83 | 1322060.14 | 1327396.92 | 1364255.56 | 1374219.23 | 1374863.09 | 1334550.62 | 1334684.17 | 1335344.55 | 1339763.75 | 1331929.89 | 1331929.89 | 1342759.15
8700909.3138 |  | W_R.10009.08.02.25: E UG Syst Rel Upgrades Dist | 2591543.22 | 5930487.44 | 5923698.6 | 9102539.88 | 9128934.25 | 9128397.61 | 9128691.09 | 9155670.31 | 9148310.86 | 9148323.56 | 9148417.3 | 9148823.97 | 18045690.57
589402.8021 |  | W_R.10009.08.02.28: E UG System Capacity Upgrade Dist | 147919.03 | 147892.19 | 155021.28 | 194389.06 | 213168.96 | 755967.85 | 772714.9 | 796326.19 | 816627.84 | 858138.91 | 889591.69 | 922949.33 | 952171.82
787818.55 |  | W_R.10009.08.03.01: E Fish And Wildlife Program Dist | 620338.9 | 676342.26 | 666457.05 | 720527.18 | 785537.52 | 797280.94 | 808803.23 | 827926.25 | 814641.07 | 860029.13 | 861202.36 | 877252.07 | 895308.18
0 |  | W_R.10009.08.03.03: Avian Protection Program | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5980651.0092 |  | W_R.10009.08.05.02: E Emergent Pole Replacement Dist | 3985067.64 | 4362273.96 | 4500729 | 4875600.78 | 5302791.26 | 5615411.34 | 5912590.56 | 6151125.01 | 6537326.26 | 6998414.35 | 7554826.43 | 7862219.39 | 8203939.9
20474.3413 |  | W_R.10009.08.05.03: E Emergent Pole Replacement Trans | 6439.62 | 16252.53 | 17638.15 | 17638.15 | 20830.08 | 21086.69 | 21086.69 | 21086.69 | 21086.69 | 21086.69 | 21086.69 | 21086.69 | 45013.09
10254.73 |  | W_R.10009.08.05.04: E Pole Replacement Due To Joint Use | 10254.73 | 10254.73 | 10254.73 | 10254.73 | 10254.73 | 10254.73 | 10254.73 | 10254.73 | 10254.73 | 10254.73 | 10254.73 | 10254.73 | 10254.73
6853356.6196 |  | W_R.10009.08.05.05: E Pole Replacement Plan Dist | 4453627.45 | 4531733.13 | 4632161 | 4933633.03 | 5669863.31 | 5790686.48 | 6204722.13 | 6605232.36 | 7509288.88 | 8674395.47 | 9569220.82 | 10373052.35 | 11038953.5
11452599.3567 |  | W_R.10009.08.05.07: E Pole Replacement Plan Trans | 5863709.62 | 7824778.63 | 9527918.23 | 10983004.55 | 11408559.03 | 11476881.03 | 11599993.87 | 11653003.47 | 12037066.38 | 12537676.31 | 12706125.83 | 13842244.61 | 17804171.06
7033122.5792 |  | W_R.10009.08.05.16: E Pole Inspection and Restoration Dist | 6160077.07 | 6972829.71 | 6972927.79 | 6984586.08 | 6984586.08 | 6984586.08 | 7124222.92 | 7124222.92 | 7124222.92 | 7124222.92 | 7124222.92 | 7197868.05 | 7197868.05
146151.6067 |  | W_R.10009.08.05.17: E Pole Inspection and Restoration Trans | 46436.77 | 46436.77 | 160323.07 | 160323.07 | 160323.07 | 160323.07 | 160323.07 | 160323.07 | 160323.07 | 160323.07 | 160323.07 | 160323.07 | 161866.85
0 |  | W_R.10009.08.06.01: E Root Cause Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9386.6879 |  | W_R.10009.08.07.01: E Fault Location | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44881.71 | 45003.61 | 45509.87
0 |  | W_R.10009.09.01.02: E Emergent Major Projects Trans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_R.10009.10.01.01: E Issaquah Highland Substation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3929625.9388 |  | W_R.10009.12.01.01: C AMI Network Installations Gen Plant | 3826724.85 | 3900865.54 | 3777605.79 | 4349379.84 | 3853281.45 | 3896097.34 | 3893094.05 | 3893895.36 | 3896552.27 | 3898310.92 | 3998421.81 | 3930875.2 | 3907538.54
202622.4812 |  | W_R.10009.12.01.03: E AMI Netwrk Installtion TransDist | 131730.64 | 132128.08 | 132128.08 | 132128.08 | 231541.98 | 231541.98 | 231541.98 | 231541.98 | 231541.98 | 231541.98 | 231541.98 | 232141.88 | 232568.95
14877999.4733 |  | W_R.10009.12.01.04: E AMI Electric Meter Deployment | 12758718.42 | 13968999.81 | 15100306.84 | 15142740.7 | 14117166.32 | 14540052.34 | 13575205.76 | 13997720.2 | 13134257 | 13571810.51 | 13637832.33 | 20829338.87 | 21082407.58
11040154.1867 |  | W_R.10009.12.01.05: G AMI Gas Module Deployment | 8909147.43 | 9985933.23 | 10666718.99 | 9417529.89 | 9891331.08 | 9923363.56 | 12433820.84 | 12240791.87 | 11633014.01 | 11839733.52 | 11912938.64 | 11975696.48 | 12212808.83
0 |  | W_R.10009.12.01.06: C AMI System Integration | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3884.5517 |  | W_R.10009.12.01.08: E Opt Out AMR to NCM Capital Exch | 0 | 0 | 0 | 0 | 0 | 0 | 7171.48 | 7171.48 | 7171.48 | 7171.48 | 7171.48 | 7171.48 | 7171.48
-0.023333 |  | W_R.10009.12.01.09: G Opt Out AMI to NCM Capital Exch | -2.1684e-18 | -0.02 | -0.03 | -0.04 | -0.04 | -0.02 | -0.03 | -0.02 | -0.02 | -0.03 | -0.02 | -5.421e-18 | -0.02
28.81 |  | W_R.10009.12.02.04: E Conservation Voltage Reduction | 28.81 | 28.81 | 28.81 | 28.81 | 28.81 | 28.81 | 28.81 | 28.81 | 28.81 | 28.81 | 28.81 | 28.81 | 28.81
8788643.375 |  | W_R.10009.12.03.01: E Distribution Automation Dist | 6967685.64 | 7235861.02 | 7248748.02 | 7518416.18 | 7981885.58 | 7890526.4 | 8123603.46 | 9436190.29 | 10015820.44 | 10029944.64 | 10072221.27 | 10920646.42 | 11012027.92
-392 |  | W_R.10009.12.03.04: E Network and Automate Grid | -392 | -392 | -392 | -392 | -392 | -392 | -392 | -392 | -392 | -392 | -392 | -392 | -392
85204.13 |  | W_R.10009.14.01.01: E Substation Replacement Battery Dist | 85204.13 | 85204.13 | 85204.13 | 85204.13 | 85204.13 | 85204.13 | 85204.13 | 85204.13 | 85204.13 | 85204.13 | 85204.13 | 85204.13 | 85204.13
84371.79 |  | W_R.10009.14.01.02: E Substation Replacement Battery Trans | 84371.79 | 84371.79 | 84371.79 | 84371.79 | 84371.79 | 84371.79 | 84371.79 | 84371.79 | 84371.79 | 84371.79 | 84371.79 | 84371.79 | 84371.79
0 |  | W_R.10009.14.03.01: E Subs Repl Electron Mech Relays Dist | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
117021.46 |  | W_R.10009.14.03.03: E Purchase PAC Engineering Software | 117021.46 | 117021.46 | 117021.46 | 117021.46 | 117021.46 | 117021.46 | 117021.46 | 117021.46 | 117021.46 | 117021.46 | 117021.46 | 117021.46 | 117021.46
460266.0079 |  | W_R.10009.14.04.01: E Substation Replacement SpcC Dist | 440331 | 440435.75 | 456814.89 | 463765.89 | 463765.89 | 463765.89 | 463765.89 | 463765.89 | 463765.89 | 463765.89 | 463765.89 | 463765.89 | 463765.89
0 |  | W_R.10009.14.05.01: E Digital Fault Recorders Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3451812.3583 |  | W_R.10009.14.05.02: E Emergent Substation Replacement Dist | 747626.17 | 737095.58 | 763604.23 | 1100729.89 | 1101270.86 | 1175294.29 | 4493812.35 | 4494468.9 | 5567187.48 | 5606774.22 | 5608238.12 | 6929515.12 | 6939888.35
2391337.0225 |  | W_R.10009.14.05.03: E Emergent Substation Replacement Trans | 1316165.77 | 1317553 | 2228317.23 | 2246884.93 | 2151036.47 | 2516212.14 | 2519489.2 | 2520180.46 | 2589692.22 | 2589748.31 | 2595748.59 | 3010194.4 | 3505808.87
3853.58 |  | W_R.10009.14.05.05: E Subs Replacement Circuit Switcher Dist | 3853.58 | 3853.58 | 3853.58 | 3853.58 | 3853.58 | 3853.58 | 3853.58 | 3853.58 | 3853.58 | 3853.58 | 3853.58 | 3853.58 | 3853.58
7434839.0704 |  | W_R.10009.14.05.06: E Substation Reliability Dist | 3614657.18 | 3621151.92 | 3688078.62 | 3695981.98 | 4037124.64 | 4073664.66 | 6921794.61 | 8465634.29 | 10636403.56 | 10683635.98 | 11077349.65 | 13498701.95 | 14022436.79
2730.6912 |  | W_R.10009.14.05.07: E Subs Replacement Fuses Dist | 2539.17 | 2539.17 | 2539.17 | 2539.17 | 2539.17 | 2539.17 | 2539.17 | 2539.17 | 2539.17 | 2539.17 | 2539.17 | 4071.34 | 4071.34
7017400.88 |  | W_R.10009.14.05.09: E Substation Reliability Trans | 6440227.49 | 6481628.31 | 6507439.22 | 6530869.32 | 6579738.42 | 6603443.92 | 6613240.06 | 7327288.33 | 7343830.5 | 7309934.53 | 7324050.17 | 8232932.74 | 8268602.59
11883.58 |  | W_R.10009.14.05.10: E Subs Replacement Transfer Trip Dist | 11883.58 | 11883.58 | 11883.58 | 11883.58 | 11883.58 | 11883.58 | 11883.58 | 11883.58 | 11883.58 | 11883.58 | 11883.58 | 11883.58 | 11883.58
0 |  | W_R.10009.14.05.11: E Subs Replacement Vegetation Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31273.5 |  | W_R.10009.14.06.01: E Subs Replacement Transformers Dist | 31273.5 | 31273.5 | 31273.5 | 31273.5 | 31273.5 | 31273.5 | 31273.5 | 31273.5 | 31273.5 | 31273.5 | 31273.5 | 31273.5 | 31273.5
225496.8742 |  | W_R.10009.14.07.01: E Subs Replacement Breaker Replcmt Trans | 219720.26 | 219720.26 | 219720.26 | 219720.26 | 227875.48 | 227875.48 | 227875.48 | 227875.48 | 227875.48 | 227875.48 | 227875.48 | 227875.48 | 227875.48
0 |  | W_R.10009.15.02.01: E Cherry Point Substation Tline Reimb | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_R.10009.15.02.03: E Cherry Point Substation Reimbursable | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_R.10009.16.01.01: E Whidbey Subs 1115Kv Bus Upgrade Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
207877.4883 |  | W_R.10009.17.01.01: E Mazama Pcket Gopher Habitat Mitigation | 106054.75 | 212200.13 | 212314.51 | 212314.51 | 212314.51 | 212314.51 | 212314.51 | 212314.51 | 212314.51 | 212314.51 | 212314.51 | 212314.51 | 212314.51
0 |  | W_R.10009.18.01.01: E OH Syst Upgr Tree Wire WF Tracker | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_R.10009.18.01.14: E PSPS Notification Softwr (ACT Now) WF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19052.23 |  | W_R.10011.01.01.02: G ERX Pilot Dist | 19052.23 | 19052.23 | 19052.23 | 19052.23 | 19052.23 | 19052.23 | 19052.23 | 19052.23 | 19052.23 | 19052.23 | 19052.23 | 19052.23 | 19052.23
696792.8642 |  | W_R.10011.01.01.03: G Gas System Monitoring Equip Replc | 379628.87 | 380019.57 | 380100.21 | 648813.42 | 664892.48 | 792444.67 | 794828.25 | 795128.08 | 816934.78 | 819255.59 | 831335.21 | 831335.21 | 833224.93
108490.5771 |  | W_R.10011.01.01.04: G Gauges Sems Dist | 31367.53 | 31367.53 | 31367.53 | 31367.53 | 31367.53 | 31367.53 | 173748.54 | 173748.54 | 173748.54 | 173748.54 | 173748.54 | 173748.54 | 173748.54
97176.6163 |  | W_R.10011.01.01.06: G Remote Telemetry Units Dist | 0 | 0 | 0 | 122749.41 | 122749.41 | 122749.41 | 122749.41 | 122749.41 | 122749.41 | 122749.41 | 122749.41 | 122749.41 | 122749.41
191471.5658 |  | W_R.10011.01.01.07: G Williams Pipeline Equipment Upgrades | 0 | 0 | 0 | 0 | 0 | 0 | 427093.07 | 427093.07 | 320771.7 | 320771.7 | 320771.7 | 320771.7 | 320771.7
2920.42 |  | W_R.10011.01.01.10: G Service Replacements CBP | 2920.42 | 2920.42 | 2920.42 | 2920.42 | 2920.42 | 2920.42 | 2920.42 | 2920.42 | 2920.42 | 2920.42 | 2920.42 | 2920.42 | 2920.42
0 |  | W_R.10011.01.01.11: G Gas Monitoring | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2111675.3104 |  | W_R.10012.01.01.01: G Altered Modified Comm Ind Mains | 1421152.25 | 1411303.21 | 1475011.05 | 1566403.74 | 1595610.65 | 1593723.32 | 2172496.86 | 2180208.56 | 2700379.92 | 2732253.67 | 2872990.67 | 2882073.82 | 2894144.26
3582814.1329 |  | W_R.10012.01.01.02: G Altered Modified Comm Ind Service | 2422708.39 | 2781733.45 | 2920201.66 | 3117351.7 | 3267878.66 | 3441268.98 | 3625314.2 | 3729592.59 | 3992094.16 | 4118139.82 | 4208909.69 | 4339404.42 | 4481052.14
1215235.5304 |  | W_R.10012.01.02.01: G Altered Modified Residential Mains | 1020888.4 | 1046441.11 | 1093819.13 | 1146665.06 | 1153515.1 | 1162747.22 | 1271117.42 | 1302735.46 | 1303854.57 | 1306695.66 | 1306740.07 | 1306165.31 | 1343772.11
14152011.8213 |  | W_R.10012.01.02.02: G Altered Modified Residential Services | 8426793.38 | 8995966.3 | 9786849.34 | 11232308.95 | 12182351.44 | 13302698.98 | 14510102.17 | 15033365.87 | 15995181.95 | 17348907.97 | 18110003.61 | 19044625.68 | 20136765.81
-1568587.6817 |  | W_R.10012.02.01.01: G 5 Yr Gas Refundable CIAC | -1411391.34 | -1411391.34 | -1411391.34 | -1609955.14 | -1609955.14 | -1609955.14 | -1609955.14 | -1609955.14 | -1609955.14 | -1609955.14 | -1609955.14 | -1609955.14 | -1609955.14
10356100.8067 |  | W_R.10012.03.01.01: G Commercial Industrial Mains | 5356578.43 | 6508542.52 | 6688316.65 | 6865982.86 | 7785649.84 | 8459161.92 | 9589083.51 | 12165848.96 | 13111050.46 | 13514656.15 | 13918633.79 | 15058070.65 | 15859846.31
4109315.1875 |  | W_R.10012.03.02.01: G Multi Family Mains | 2507512.11 | 2850737.57 | 3154800.75 | 3696807.84 | 3915944.07 | 4117978.3 | 4269515.22 | 4434382.39 | 4548379.05 | 4708297.21 | 4787456.8 | 4935668.04 | 5276117.91
10255633.8675 |  | W_R.10012.03.03.01: G Plats Mains | 6131634.38 | 6740987.43 | 7550262.23 | 8062555.21 | 8459564.7 | 9344891.63 | 10125547.22 | 10945631.84 | 11487030.55 | 12354252.41 | 13572510.04 | 14139164.74 | 14438782.44
4545091.125 |  | W_R.10012.03.03.02: G Residential Mains | 3092574.73 | 3305393.77 | 3572950.71 | 3931283.32 | 4111487.3 | 4270551.57 | 4373273.26 | 4488224.5 | 4892039.58 | 5359773.99 | 5613921.43 | 5975067.08 | 6201679.25
12281175.35 |  | W_R.10012.04.01.01: G Commercial Industrial Service | 8586390.8 | 9024275.03 | 9978796.65 | 10635475.03 | 11461240.76 | 12030165 | 12564100.53 | 13099999.88 | 13080765.37 | 13574792.7 | 14289125.02 | 15259766.25 | 16164813.16
5666313.7158 |  | W_R.10012.04.02.01: G Multi Family Service | 4087102.71 | 4303359.98 | 4597162.86 | 4958020.34 | 5325958.42 | 5570990.54 | 5812733.92 | 5950080.99 | 6129367.32 | 6318250.87 | 6457651.64 | 6927405.09 | 7202462.53
38273322.3517 |  | W_R.10012.04.03.02: G Residential Services | 26037113.77 | 27925746.15 | 30060883.02 | 32815688.24 | 34839219.7 | 37172509.61 | 38829899.53 | 40198239.18 | 42425641.08 | 43870957.3 | 45559777.5 | 47882384.49 | 49360731.07
11908333.1271 |  | W_R.10012.04.03.03: G Residential Services In Plat Dev | 8310815.3 | 8861316.09 | 9386635.74 | 9891838.74 | 10398088.03 | 10973529.88 | 11729863.19 | 12417369.11 | 13299814.63 | 13909185.7 | 14637089.81 | 15290301.97 | 15899113.97
8463.8733 |  | W_R.10012.06.01.01: G Gas Retire Only No Additions | 7292.1 | 7292.1 | 7292.1 | 7292.1 | 8941.07 | 8946.79 | 8946.79 | 8946.79 | 8946.79 | 8947.4 | 8947.4 | 8947.4 | 8947.4
178224.5396 |  | W_R.10013.01.01.01: G Cust Driven Relocate Reimburse Dist | 97687.62 | 137671.16 | 161657.62 | 161626.28 | 162503.46 | 162536.36 | 162536.36 | 162536.36 | 215965.53 | 216711.92 | 218008.95 | 218731.11 | 218731.11
0 |  | W_R.10013.02.01.01: G Franchises | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_R.10013.03.01.01: G I405 Relocate Like Kind Dist | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2642.54 |  | W_R.10013.03.01.02: G I5 Tacoma Hov Relocate | 2642.54 | 2642.54 | 2642.54 | 2642.54 | 2642.54 | 2642.54 | 2642.54 | 2642.54 | 2642.54 | 2642.54 | 2642.54 | 2642.54 | 2642.54
41524861.1058 |  | W_R.10013.04.01.01: G PI Driven Relocate NonReimb Dist | 19388324.97 | 27263677.44 | 33903862.91 | 37064006.06 | 39341723.88 | 40285545.87 | 44558287.22 | 44284448.7 | 45639921 | 46689808.28 | 49913787.01 | 52015187.95 | 55287828.93
734937.55 |  | W_R.10013.04.01.02: G PI Driven Relocate Reimb Dist | 621092.22 | 579617.29 | 625310.04 | 623352.27 | 629076.62 | 643109.65 | 643218.7 | 648497.38 | 820519.56 | 454181.56 | 826653.47 | 1174645.75 | 1681044.4
1979456.1958 |  | W_R.10013.04.01.04: G Sound Transit Reimburse | 1482069.74 | 1490585.27 | 1420514.23 | 1433646.82 | 1432134.84 | 1456584.14 | 685809.07 | 2639042.17 | 2753276.77 | 2748986.12 | 2749373.29 | 2794760.56 | 2815452.4
323101.2988 |  | W_R.10013.04.01.06: G WSDOT Fish Passage Relocation | 0 | 0 | 0 | 0 | 0 | 0 | 547669.56 | 581571.35 | 605301.22 | 605301.22 | 608333.24 | 619359.33 | 619359.33
5289774.8492 |  | W_R.10013.05.01.01: G Seattle Core Alaskan Way Viaduct | 5310891.51 | 5284138.55 | 5285272.83 | 5286569.43 | 5287406.14 | 5286266.05 | 5286574.5 | 5286574.5 | 5280904.88 | 5294113.85 | 5293911.61 | 5299387.79 | 5301464.61
1367.825 |  | W_R.10013.05.01.02: G Seattle Core IP Main | 1090.33 | 1090.33 | 1090.33 | 1090.33 | 1090.33 | 1090.33 | 1518.1 | 1518.1 | 1518.1 | 1518.1 | 1518.1 | 1884.39 | 1884.39
156.16 |  | W_R.10013.05.01.03: G Seattle Core Other Projects | 156.16 | 156.16 | 156.16 | 156.16 | 156.16 | 156.16 | 156.16 | 156.16 | 156.16 | 156.16 | 156.16 | 156.16 | 156.16
326.96 |  | W_R.10013.05.01.05: G Seattle Core Services | 326.96 | 326.96 | 326.96 | 326.96 | 326.96 | 326.96 | 326.96 | 326.96 | 326.96 | 326.96 | 326.96 | 326.96 | 326.96
44592.7575 |  | W_R.10013.06.01.01: G Sound Transit Dist | 44298.32 | 44298.32 | 44634.82 | 44634.82 | 44634.82 | 44634.82 | 44634.82 | 44634.82 | 44634.82 | 44634.82 | 44634.82 | 44634.82 | 44634.82
293557.7212 |  | W_R.10013.07.01.01: G Relocate Bulk Dist Like Kind Dist | 6025.51 | -26821.94 | 122556.99 | 134412.84 | 368465.93 | 380831.67 | 380447.27 | 385163.58 | 389434.17 | 392904.85 | 395487.7 | 397848.76 | 397896.16
691530.8946 |  | W_R.10013.07.01.02: G System Improv Opport Dist | 643645.32 | 652123.43 | 652198.36 | 653193.78 | 700829.1 | 705675.13 | 705675.13 | 705675.13 | 710168.42 | 710168.42 | 710707.44 | 713402.54 | 713462.39
1369060.7592 |  | W_R.10014.01.01.01: G Swarr Propane Air Plant Upgrades | 0 | 0 | 0 | 0 | 0 | 0 | 2121274.3 | 2122672.93 | 2125542.69 | 2872230 | 2872230 | 2876519.46 | 2876519.46
475328.8971 |  | W_R.10015.01.01.01: G CP System Improv Main With Serv Dist | 335462.67 | 453812.03 | 454012.79 | 461794.15 | 469181.84 | 469761.05 | 469806.74 | 489716.26 | 494138.83 | 499252.29 | 506447.47 | 508470.16 | 519643.64
4121127.7171 |  | W_R.10015.01.01.02: G CP System Improv Service Dist | 2774796.86 | 2986457.87 | 3100828.54 | 3401413.01 | 3592488.33 | 3853050.69 | 4096989.02 | 4301901.88 | 4521101.78 | 4849210.59 | 5195043.24 | 5398108.53 | 5539081.39
334033.6037 |  | W_R.10015.01.01.03: G CP System Improv Dist | 125166.12 | 125173.7 | 218458.98 | 223200.31 | 223421.74 | 271457.9 | 389773.21 | 391776.45 | 392684.33 | 393946.34 | 394090.47 | 397151.61 | 1049370.29
2320107.5321 |  | W_R.10015.01.01.05: G Emergent CP System Improv Dist | 1201271.01 | 1521406.65 | 1658351.11 | 1847701.23 | 2017621.81 | 2093576.24 | 2259422.71 | 2476363.33 | 2703650.81 | 2765416.21 | 2904268.43 | 3302250.08 | 3381252.54
0 |  | W_R.10015.02.01.01: G Damage Claims Dist | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
277188.8496 |  | W_R.10015.02.01.02: G Damage Claims Cap Writeoff | 237260.96 | 243665 | 243665 | 243946.05 | 249619.91 | 253627.34 | 259518.45 | 275153.05 | 275153.05 | 288798.63 | 338617.87 | 355323.49 | 361095.75
87300.4288 |  | W_R.10015.03.01.01: G DIMP Brdg Sld Dist Unmaintain Facil | 342.99 | 342.99 | 342.99 | 342.99 | 64922.28 | 66469.31 | 74000.78 | 76354.24 | 79449.34 | 79568.06 | 82038.46 | 347552.16 | 352100.1
122768.83 |  | W_R.10015.03.02.01: G DIMP Mobile Home Encroachment Program | 16783.73 | 20273.91 | 30274.55 | 32630.67 | 32630.67 | 32630.67 | 32630.67 | 32630.67 | 32630.67 | 32630.67 | 32630.67 | 768747.07 | 768986.41
0 |  | W_R.10015.03.03.02: PE Pipe Recall 1-inch | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
52931511.7958 |  | W_R.10015.03.04.01: G DIMP Dupont Pipe Repl Main With Serv | 35125246.08 | 38069653.8 | 39247864.31 | 40674544.38 | 42267184 | 47236423.36 | 50828983.86 | 55060261.16 | 60109731.23 | 61936397.82 | 68208887.4 | 71780479.74 | 84390214.9
2688264.8021 |  | W_R.10015.03.04.02: G DIMP Older Stw Repl Main With Service | 2078617.53 | 2081970.49 | 2086089.88 | 2187184.29 | 2188730.94 | 2263781.57 | 2281925.17 | 3022870.42 | 3051493.69 | 3401611.22 | 3401726.58 | 3497925.53 | 3509118.16
679585.9396 |  | W_R.10015.03.04.03: G DIMP Older Stw Repl Service Only | 286650.79 | 293536.15 | 349017.53 | 514571.55 | 576989.16 | 691594.65 | 781151.33 | 802264.35 | 844978.98 | 880235.75 | 883633.2 | 924897.27 | 937671.92
0 |  | W_R.10015.03.04.11: G DIMP Low Pressure Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_R.10015.03.05.04: G DIMP Regulator Station Sidewalk Regs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
127387.8817 |  | W_R.10015.03.06.01: G DIMP Legacy Cross Bore Inspection Dist | 75462.75 | 78517.2 | 87176.07 | 94314.8 | 99118.65 | 129116.82 | 130635.15 | 134059.19 | 149069.48 | 156913.01 | 168207.81 | 178166.05 | 171257.95
0 |  | W_R.10015.03.06.02: G DIMP Legacy Crss Bore Replacement Dist | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23789.4646 |  | W_R.10015.03.07.01: G DIMP Continuing Surveillance Other | 11233.5 | 11342.02 | 11342.02 | 11495.37 | 11495.37 | 11495.37 | 11520.92 | 11520.92 | 12679.36 | 12679.36 | 63439.19 | 73897.95 | 73897.95
2517404.1054 |  | W_R.10015.03.07.03: G DIMP Shallow Serv and Main Repl | 1066157.58 | 1208709.3 | 1570842.77 | 1951218.54 | 2211080.48 | 2350786.33 | 2577212.46 | 2665878.43 | 2898484.06 | 3108971.67 | 3522335.17 | 3729622.81 | 3761256.91
3727.8675 |  | W_R.10015.03.08.01: G DIMP Buried MSA Serv Or Riser Repl Opp | 3422.13 | 3422.13 | 3422.13 | 3422.13 | 3422.13 | 3575.48 | 3575.48 | 3575.48 | 3926.87 | 4155.47 | 4155.47 | 4247.05 | 4247.05
1863863.7608 |  | W_R.10015.03.09.01: G DIMP Preventative Maint Facilities | 834037.45 | 835109.86 | 834692.46 | 996200.92 | 1008463.55 | 2129759.97 | 2301706.31 | 2311804.08 | 2427222.87 | 2501107.46 | 2521715.48 | 2680570.77 | 2801985.35
7246574.9342 |  | W_R.10015.03.09.03: G DIMP Preventive Maint Dist Reg Dist | 4567643.07 | 4583492.68 | 6327724.41 | 6372185.44 | 6440506.18 | 6682403.94 | 8208443.94 | 8293699.43 | 8318923.74 | 8379666.56 | 8396208.39 | 8420389.08 | 8502867.77
0 |  | W_R.10015.03.09.05: G DIMP Preventive Maintenance MSA Dist | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1768720.9333 |  | W_R.10015.03.09.07: G DIMP Preventive Maint Farm Taps Dist | 1638335.99 | 1726627.92 | 1729672.03 | 1729689.14 | 1731548.05 | 1731554.24 | 1792019.03 | 1792974.74 | 1794954.87 | 1794982.53 | 1821407.18 | 1839943.69 | 1840219.57
359750.8763 |  | W_R.10015.03.09.14: G Idle Riser Remediation | 158406.9 | 160945.78 | 175822.05 | 182202.57 | 227577.95 | 266026.83 | 357044.68 | 373637.45 | 400758.39 | 427304.24 | 480754.96 | 750403.48 | 870657.37
7498114.5808 |  | W_R.10015.03.09.15: G Buried Meter Riser Replacement | 4571446.48 | 4773527.76 | 5045073.28 | 5537936.3 | 5993057.39 | 7038093.42 | 7566484.38 | 8058531.21 | 8790340.82 | 9377618.71 | 9894769.01 | 10315137.33 | 10602164.24
10784.1242 |  | W_R.10015.03.09.16: G NRF Retirement Program | 0 | 0 | 0 | 0 | 0 | 17169.83 | 17267.64 | 17267.64 | 17267.64 | 17267.64 | 17267.64 | 17267.64 | 17267.64
108705.3875 |  | W_R.10015.03.10.02: G-DIMP Unmaintainable STW Main in Casing | 0 | 0 | 0 | 107679.12 | 108004.28 | 140605.7 | 141319.96 | 144268.4 | 146995.37 | 147178.51 | 147178.51 | 147178.51 | 148112.58
18897.0237 |  | W_R.10015.03.11.01: G DIMP Guard Posts | 1454.2 | 1454.2 | 1454.2 | 1454.2 | 1454.2 | 1454.2 | 30120.28 | 31025.65 | 31025.64 | 31870.84 | 31870.84 | 41061.01 | 43583.85
2651215.5154 |  | W_R.10015.04.01.02: G Leak Repair Main | 1441519.09 | 1662646.55 | 1755870.39 | 1925825.18 | 2353466.59 | 2521589.55 | 2661810.29 | 2775079.96 | 3183044.93 | 3256175.5 | 3457349.22 | 3662506.89 | 3756923.18
648641.9033 |  | W_R.10015.04.01.03: G Leak Repair Service | 524097 | 530108.56 | 534777.86 | 549233.1 | 564445.08 | 575902.93 | 640755.23 | 645057.94 | 653507.53 | 720152.9 | 816871.34 | 852589.85 | 876504.04
2579244.9958 |  | W_R.10015.04.01.04: G Scattered Short Main Rehab | 1916701.54 | 1952813.61 | 2094072 | 2175221.13 | 2328262.31 | 2383142.17 | 2642784.2 | 2725282.1 | 2850602.33 | 2982624.71 | 3078466.53 | 3181070.13 | 3196495.92
12535198.8825 |  | W_R.10015.04.01.05: G Service Replacement Misc | 7461843.2 | 8042685.97 | 8491598.65 | 9666471.31 | 10623025.01 | 11655105.51 | 12945153.45 | 13683225.62 | 14299031.35 | 15304663.65 | 16221684.31 | 17015745.97 | 17486148.38
135185.0054 |  | W_R.10015.04.01.06: G Sewer Cross Bore Repair Main | 25226.21 | 56730.27 | 56802.6 | 77154.26 | 82396.42 | 82555.66 | 82555.66 | 82555.66 | 214175.96 | 214175.96 | 258790.19 | 268906.44 | 265615.76
123801.3288 |  | W_R.10015.04.01.07: G Sewer Cross Bore Repair Service | 121197.09 | 121197.09 | 121197.09 | 121197.09 | 122233.57 | 124217.54 | 124217.54 | 124906.25 | 124906.25 | 125984.28 | 125984.28 | 125984.28 | 125984.28
0 |  | W_R.10015.04.01.08: G Gas Work Release Main | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
202053.8408 |  | W_R.10015.04.01.09: G Gas Work Release Service | 21466.56 | 21466.56 | 212037.13 | 213569.61 | 206025.05 | 218634.36 | 219517.53 | 220135.36 | 222077.14 | 224674.82 | 251455.24 | 269525.74 | 269588.54
2682326.1504 |  | W_R.10015.04.01.12: G Nonhaz Main Repair Methane PRP | 431900.9 | 653284.92 | 1323335.3 | 1728623.27 | 2191941.03 | 2772554.12 | 3069786.99 | 3144170.39 | 3327844.4 | 3682716.56 | 3722506.01 | 4226665.05 | 4257070.63
463050.5537 |  | W_R.10015.04.01.13: G Nonhaz Service Repair Methane PRP | 135889.44 | 182147.49 | 218561.57 | 281035.22 | 403820.31 | 468061.93 | 548123.27 | 556315.96 | 570546.44 | 588821.81 | 604345.09 | 668408.79 | 796948.09
1985.4533 |  | W_R.10015.05.01.01: G System Capacity New Dist | 773.57 | 773.57 | 773.57 | 2304.37 | 2304.37 | 2304.37 | 2304.37 | 2304.37 | 2304.37 | 2304.37 | 2304.37 | 2304.37 | 2304.37
0 |  | W_R.10015.06.01.01: G Cold Weather Action Reinforcement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
231365.5525 |  | W_R.10015.06.01.02: G Odorizer Componant Repl Bulk Dist | 207188.27 | 207525.52 | 207540.45 | 237809.05 | 237837.73 | 237826.01 | 237753.1 | 237545.57 | 237545.57 | 237545.57 | 237545.57 | 237545.57 | 237545.57
929981.0046 |  | W_R.10015.06.01.04: G System Capacity Upgrade Bulk Dist | 286260.26 | 292676.19 | 296315.87 | 296315.87 | 296439.23 | 296592.58 | 1069394.56 | 1069394.56 | 1069394.56 | 1069394.56 | 1069394.56 | 2758538.89 | 2865580.99
4806276.5863 |  | W_R.10015.06.01.05: G System Capacity Upgrade Dist | 3562079.61 | 3590782.77 | 3614721.55 | 3660152.4 | 3705202.57 | 3707263.58 | 5463899.64 | 5507844.47 | 5514303.51 | 5515238.77 | 5515836.68 | 6698028.64 | 6802009.3
-0.03 |  | W_R.10015.07.01.01: G Gas Lightups Clearing | -0.03 | -0.03 | -0.03 | -0.03 | -0.03 | -0.03 | -0.03 | -0.03 | -0.03 | -0.03 | -0.03 | -0.03 | -0.03
162105.2188 |  | W_R.10015.08.01.02: G Enhanced Methane Emissions Reduction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3890525.25
0 |  | W_R.10015.08.02.01: G TSA RTU/ERX Replacemnt/Retiremnt Progr | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6731.7183 |  | W_R.10015.08.02.02: G Alternative Fuels | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161561.24
0 |  | W_R.10015.09.01.01: G Gas Mega Rule Compliance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_R.10017.01.01.02: E Greenwater Tap Subs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_R.10018.01.01.01: E Covington Area Capacity Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
111742.9421 |  | W_R.10019.01.01.01: E Port Madison Subs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111812.48 | 113177.8 | 322841.75 | 317975.01 | 316714.06 | 316788.41
163258.2433 |  | W_R.10019.01.01.02: Bainbridge Trans WIN-MUR Loop | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78328.87 | 78328.15 | 304795.96 | 570477.81 | 618205.76 | 617924.74
0 |  | W_R.10019.01.01.03: E Rebuild Winslow Tap | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_R.10019.01.01.04: E Murden Cove Subs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_R.10019.03.01.01: E So Brm Bngr 115Kv 230Kv Prprty Purch | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_R.10019.03.01.03: E West Kitsap Reliability Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_R.10019.03.01.04: E Keyport Switch Station Transm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_R.10020.02.01.01: E Wind RidgE Kittitas 115Kv Tline | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_R.10021.01.01.01: G N Lacey Supply 8inche Reinf Bulk Dist | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_R.10021.02.01.01: G N Lacey HP Supply Reliability | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_R.10022.01.01.01: E Sumner Valley Area Capacity | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_R.10023.01.01.01: E Lakemont Substation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_R.10024.01.01.01: C AMR Operations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
238237.655 |  | W_R.10024.01.01.04: G AMR Operations | 229410.95 | 238034.17 | 238065.32 | 238118.07 | 238118.07 | 238398.91 | 238398.91 | 238543.72 | 238869.23 | 239200.09 | 239226.15 | 239449.16 | 239449.17
95415.1958 |  | W_R.10024.01.01.05: E AMR Operations | 67031.71 | 73458.43 | 79251.87 | 85921.29 | 90390.63 | 93496.5 | 94937.61 | 96612.86 | 101907.25 | 106580.3 | 110924.12 | 116520.84 | 122929.59
132343.6433 |  | W_R.10024.01.01.07: E Opt Out AMR to NCM Capital Exch | 7192.55 | 7192.55 | 7192.55 | 7391.94 | 156627.69 | 156627.69 | 157258.82 | 157258.82 | 157258.82 | 157258.82 | 157258.82 | 308703.14 | 308995.57
540058.3938 |  | W_R.10024.01.01.09: G AMI Operations | 399838.62 | 514175.74 | 533249.7 | 537287.63 | 542320.25 | 547367.16 | 548451.77 | 554701.09 | 555046.23 | 555561.2 | 555566.02 | 556723.9 | 560661.45
264592.0254 |  | W_R.10024.02.01.01: G NonRegistering Meters Dist | 68792.42 | 78560.69 | 87045.05 | 98513.7 | 188672.55 | 236648.51 | 276782.62 | 318512.96 | 355114.57 | 382516.43 | 413101.76 | 453087.7 | 504303.11
673650.9104 |  | W_R.10024.02.01.03: G Periodic Meter Changeout IMO Dist | 282695.96 | 294443.59 | 301604.42 | 308925.27 | 335640.31 | 358151.96 | 921001.87 | 943897.92 | 959998.33 | 971495.23 | 999410.45 | 1016844.73 | 1062097.73
0 |  | W_R.10024.02.01.04: Meter Change SS FF PM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100516.68 |  | W_R.10024.04.01.01: Click Enhancements | 100516.68 | 100516.68 | 100516.68 | 100516.68 | 100516.68 | 100516.68 | 100516.68 | 100516.68 | 100516.68 | 100516.68 | 100516.68 | 100516.68 | 100516.68
660.52 |  | W_R.10027.01.01.01: E Moorlnds Vitulli 115Kv Reconduc Trans | 660.52 | 660.52 | 660.52 | 660.52 | 660.52 | 660.52 | 660.52 | 660.52 | 660.52 | 660.52 | 660.52 | 660.52 | 660.52
38883.85 |  | W_R.10027.02.01.01: E Vernell Substation Feeder | 38883.85 | 38883.85 | 38883.85 | 38883.85 | 38883.85 | 38883.85 | 38883.85 | 38883.85 | 38883.85 | 38883.85 | 38883.85 | 38883.85 | 38883.85
0 |  | W_R.10027.02.01.02: E BelRed Area Capacity Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_R.10027.03.01.01: E Redmond Inititation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
192.66 |  | W_R.10029.01.01.01: G Tolt Hp 16in Phase 1 Main | 192.66 | 192.66 | 192.66 | 192.66 | 192.66 | 192.66 | 192.66 | 192.66 | 192.66 | 192.66 | 192.66 | 192.66 | 192.66
1532955.4688 |  | W_R.10031.01.01.02: E Lake Hills Phantom Lake 115Kv Tline | 1327181.2 | 1334312.7 | 1356118.73 | 1139347.2 | 1163993.69 | 1191767.06 | 1645333.64 | 1729996.04 | 1750245.53 | 1780701.81 | 1820452.81 | 1843956.93 | 1951297.77
0 |  | W_R.10031.02.01.04: E Lakeside 115 Kv Sub Tran Longlines Ph1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1834414.8975 |  | W_R.10031.03.01.01: E Sammamish Juanita 115Kv Tline | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44025957.54
4965385.6742 |  | W_R.10033.01.01.03: E Small Tool Electric Operations Tool | 4653891.33 | 4838598.44 | 4838629.66 | 4840902.7 | 4841124.68 | 4841124.68 | 4841124.68 | 4841124.68 | 4841124.68 | 4706694.07 | 4706694.07 | 4706694.07 | 8827692.03
2768311.4758 |  | W_R.10033.01.01.09: G Small Tool Gas Operations Tool | 2605045.36 | 2611176.02 | 2661074.88 | 2670511.09 | 2695887.68 | 2714957.27 | 2714957.27 | 2714957.27 | 2714957.27 | 2714957.27 | 2745526.14 | 2781304.93 | 4353895.88
28410.69 |  | W_R.10033.01.01.19: E Small Tools PTS on CC4587 | 28410.69 | 28410.69 | 28410.69 | 28410.69 | 28410.69 | 28410.69 | 28410.69 | 28410.69 | 28410.69 | 28410.69 | 28410.69 | 28410.69 | 28410.69
195708.8813 |  | W_R.10033.02.01.01: C Operational Training ISR Program | 193714.94 | 193714.94 | 195993.73 | 195993.73 | 195993.73 | 195993.73 | 195993.73 | 195993.73 | 195993.73 | 195993.73 | 195993.73 | 195993.73 | 195993.73
6161.1 |  | W_R.10034.01.01.03: E Pierce Co 230Kv Alderton Tline | 0 | 0 | 0 | 117.81 | 352.84 | 352.84 | 352.84 | 2931.74 | 12333.92 | 16426.06 | 16426.06 | 16426.06 | 16426.06
1246.0738 |  | W_R.10035.01.01.01: E Alderton Electron Hgts 115Kv Ph2 Tline | 0 | 0 | 468.74 | 819.59 | 1399.88 | 1635.29 | 1635.29 | 1635.29 | 1635.29 | 1635.29 | 1635.29 | 1635.29 | 1635.29
0 |  | W_R.10035.02.01.01: E Greenwater Tap 55 155Kv Conversion | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_R.10036.01.01.04: C Transmission Land | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
539116.2117 |  | W_R.10036.02.01.01: C Capitalization of Real Estate Permits | 274689.5 | 274689.5 | 571309.29 | 571309.29 | 571309.29 | 571309.29 | 571309.29 | 571309.29 | 571309.29 | 571309.29 | 571309.29 | 571309.29 | 688534.78
178273.6325 |  | W_R.10036.03.01.01: C Transient Deterrent | 169784.5 | 170131.33 | 170131.33 | 170131.33 | 170131.33 | 175596.44 | 184217.64 | 184373.08 | 184373.08 | 184373.08 | 184373.08 | 184373.08 | 184373.08
0 |  | W_R.10038.01.01.01: E Issaquah Area Capacity Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_R.10039.01.01.01: E Christopher Sub 230Kv Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_R.10039.02.01.01: E Buckley Substation Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
73281.8288 |  | W_R.10039.02.01.02: E Buckley Substation Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 586254.63 | 586254.63
0 |  | W_R.10039.02.01.03: E Electr Enum 55Kv 115Kv Sub Electr Hght | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_R.10039.02.01.04: E Electr Enum 55Kv To 115Kv Sub Krain | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_R.10039.02.01.05: E Electr Enum 55Kv To 115Kv Sub Enum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
234842.7808 |  | W_R.10039.02.01.06: E Electr Enum 55Kv To 115Kv Fiber | 51191.23 | 51191.23 | 51191.23 | 62257.03 | 62257.03 | 62257.03 | 374893.92 | 400523.08 | 383965.65 | 383994.73 | 383994.73 | 383994.73 | 383994.73
0 |  | W_R.10039.02.01.07: E Electr Enum 55Kv To 115Kv Tline | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_R.10040.01.01.01: E Seabeck Area Reliability Improvement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_R.10043.02.01.01: E Skagit Swtchng Station Prprty Purchase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
94821.595 |  | W_R.10045.01.01.01: E Talbot Asbury Ug 115Kv Repl Tline | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2275718.28
0 |  | W_R.10047.02.01.02: G SP Alignment Trans and Dist | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_R.10048.01.01.01: E St Clair Yelm 115Kv Trans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_R.10050.02.01.01: E Carpenter Substation Feeder Dist | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_R.10050.02.01.02: E Carpenter Substation Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_R.10050.03.01.01: E Hoffman Switching Station | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6530908.23 |  | W_R.10051.02.01.01: E Thurston Transmission Capacity | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13314473.35 | 13488616.84 | 13514827.52 | 13553752.45 | 14668308.97 | 19661839.26
0 |  | W_R.10052.01.01.01: E Kent-Tukwila Area Capacity Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_R.10052.01.01.02: E Briscoe Park Substation Tline | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23388.2529 |  | W_R.10054.01.01.01: E Bellingham Sedro 4 115Kv Recond Tline | 19880.83 | 21037.57 | 21563.67 | 22446.97 | 23355.76 | 24308.62 | 24308.62 | 24308.62 | 24308.62 | 24308.62 | 24308.62 | 24308.62 | 24308.62
0 |  | W_R.10054.02.01.01: E Glacier Energy Storage Project Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_R.10054.03.01.01: E Lynden Substation Expansion | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
127.28 |  | W_R.10055.01.01.01: E Maxwelton Substation Feeders | 127.28 | 127.28 | 127.28 | 127.28 | 127.28 | 127.28 | 127.28 | 127.28 | 127.28 | 127.28 | 127.28 | 127.28 | 127.28
1456.58 |  | W_R.10055.01.01.03: E Maxwelton Substation Trans | 1456.58 | 1456.58 | 1456.58 | 1456.58 | 1456.58 | 1456.58 | 1456.58 | 1456.58 | 1456.58 | 1456.58 | 1456.58 | 1456.58 | 1456.58
283017.97 |  | W_R.10055.02.01.01: E Whidbey Island 115Kv Row | 283017.97 | 283017.97 | 283017.97 | 283017.97 | 283017.97 | 283017.97 | 283017.97 | 283017.97 | 283017.97 | 283017.97 | 283017.97 | 283017.97 | 283017.97
0 |  | W_R.10055.03.01.01: E Whidbey Transmission Improvement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_R.10056.01.01.01: E Wilkeson Substation Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8279.99 |  | W_R.10058.01.01.01: E Skookumchuck Wind Farm | 8279.99 | 8279.99 | 8279.99 | 8279.99 | 8279.99 | 8279.99 | 8279.99 | 8279.99 | 8279.99 | 8279.99 | 8279.99 | 8279.99 | 8279.99
105740.5 |  | W_R.10059.01.01.01: E Smart Grid Living Lab | 105740.5 | 105740.5 | 105740.5 | 105740.5 | 105740.5 | 105740.5 | 105740.5 | 105740.5 | 105740.5 | 105740.5 | 105740.5 | 105740.5 | 105740.5
0 |  | W_R.10059.01.01.03: CEF4 Living Lab Generator | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
382804.91 |  | W_R.10059.02.01.01: E ADMS Circuit Enablement | 382804.91 | 382804.91 | 382804.91 | 382804.91 | 382804.91 | 382804.91 | 382804.91 | 382804.91 | 382804.91 | 382804.91 | 382804.91 | 382804.91 | 382804.91
277146.5392 |  | W_R.10059.02.01.02: E Circuit Enablement EV | 0 | 0 | 0 | 0 | 11651.21 | 24415.46 | 187457.24 | 280511.38 | 433390.77 | 500640.78 | 607720.55 | 781840.14 | 996261.88
2061746.6196 |  | W_R.10059.03.01.01: E Resilience Enhancement Substation | 1294239.24 | 1317613.37 | 1331579.37 | 1461063.68 | 1932031.29 | 1939093.86 | 2157262.46 | 2530179.73 | 2534783.58 | 2537250.77 | 2539516.87 | 2540377.76 | 2546174.15
0 |  | W_R.10059.03.01.03: E Resilience Enhancement (Non-CEIP) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_R.10059.04.01.01: E Wildfire Resilience | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_R.10059.05.01.01: E Submarine Cable - Mercer Island | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7396.5558 |  | W_R.10059.06.01.01: E Conservation Voltage Reduction | 0 | 0 | 0 | 851.63 | 9646.31 | 9646.31 | 10290.62 | 10290.62 | 10674.04 | 10674.04 | 10674.04 | 10674.04 | 10674.04
0 |  | W_R.10059.07.01.01: ADMS Advanced Apps | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43706.5108 |  | W_R.10060.01.01.01: G Vashon Marine Crossing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3046.3 | 3046.3 | 3046.3 | 3046.3 | 1024585.86
506294.4121 |  | W_R.10060.01.01.02: G Vashon Interim Supply at Gig Harbor | 458640.09 | 467422.1 | 467893.18 | 479366.39 | 488196.74 | 489190 | 489190 | 519311.09 | 534149.29 | 545076.2 | 545076.2 | 546327.39 | 550028.64
0 |  | W_R.10062.01.01.01: Midlakes Substation Transmission | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_R.10062.01.01.02: Midlakes Substation Distribution | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_R.10062.02.01.02: Totem Lake Capacity Increase Dist | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_R.10062.03.01.02: Berthusen Capacity Increase Dist | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_R.10062.04.01.02: Sunrise Capacity Increase Dist | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_R.10062.05.01.02: Maplewood Capacity Increase Dist | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_R.10062.06.01.02: Southwick Capacity Increase Dist | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_R.10062.07.01.02: Rose Hill Capacity Increase Dist | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_R.10062.08.01.02: Rhodes Lake Capacity Increase Dist | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_R.10062.11.01.02: Cedarhurst Capacity Increase Dist | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_R.10062.12.01.02: Grady Subs Capacity Increase Dist | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_X.10002.01.01.01: Water Heater Commerical Gas | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_X.10002.01.01.02: Water Heater Residential Gas | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3767378.2733 |  | W_X.10003.01.01.01: Street and Area Lighting Services | 2296489.86 | 2352050.7 | 2951865.53 | 2984045.3 | 3287597.08 | 4016902.73 | 3850723.41 | 3795630.18 | 3997751.29 | 4625776.39 | 4661190.06 | 5002854.56 | 5067814.24
1499830.2242 |  | W_X.10003.01.03.01: Street Light Replacement | 1336724.9 | 1359015.32 | 1387051.18 | 1392918.77 | 1408128.16 | 1420512.5 | 1435589.02 | 1443873.07 | 1467330.6 | 1473053.19 | 1482191.16 | 1484925.77 | 3150023
3346338.7329 |  | W_X.10003.01.03.02: Smart Street Lighting | 1617272.27 | 2483014.17 | 2706420.96 | 2800688.88 | 3084403.28 | 3141807.42 | 3325259.35 | 3463423.87 | 3738606.07 | 4024670.76 | 4112295.05 | 4160661.36 | 4612354.98
3624502.8592 |  | W_X.10005.01.01.01: Wireless and Wireline Construction | 2702727.89 | 2516158.09 | 1606136.17 | 1557137.93 | 2728763.02 | 3523088.73 | 4341408.62 | 4452167.84 | 4720549.89 | 4681190.37 | 5217587.38 | 5035755.79 | 3525453.07
9261.405 |  | W_X.10006.01.01.01: Customer Sited Energy Storage Pilot | 144034.18 | 3329.98 | 3329.98 | 3329.98 | 3329.98 | 3329.98 | 3329.98 | 3329.98 | 3329.98 | 3329.98 | 3329.98 | 3879.98 | 3879.98
0 |  | W_X.10006.02.01.01: EV Charging Program PSE Internal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2878547.9121 |  | W_X.10006.02.02.02: EV Charging Program Infrastructure | 2093226.55 | 2645460.37 | 2645460.37 | 2672839.68 | 2704778.07 | 2715410.82 | 2715433.31 | 2760616.76 | 2764422.43 | 2764424.79 | 3447000.46 | 3488070.97 | 4344087.28
186784.5288 |  | W_X.10006.02.03.02: Transprtatn Electrificatn Plan General | 0 | 0 | 0 | 0 | 0 | 249046.18 | 250065.38 | 250899.25 | 250899.25 | 250899.25 | 395623.54 | 395623.54 | 396715.91
2032922.06 |  | W_X.10006.03.01.02: Community Solar Program | 2032922.06 | 2032922.06 | 2032922.06 | 2032922.06 | 2032922.06 | 2032922.06 | 2032922.06 | 2032922.06 | 2032922.06 | 2032922.06 | 2032922.06 | 2032922.06 | 2032922.06
1753853.1379 |  | W_X.10006.03.01.05: Community Solar Program 2022-25 | 1357.49 | 1823937.58 | 1830567.62 | 1830567.62 | 1830567.62 | 1830567.62 | 1830567.62 | 1830567.62 | 1830714.58 | 1830714.58 | 1830714.58 | 1830714.58 | 1830714.58
0 |  | W_X.10006.05.01.01: DER Solar Projects and Programs CEIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | W_X.10006.05.01.02: DER Storage Projects and Programs CEIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
711016.6038 |  | W_X.10007.01.01.01: Covid 19 Work for WUTC Order | 0 | 718917.51 | 744122.07 | 744122.07 | 744122.07 | 744122.07 | 744122.07 | 744122.07 | 744122.07 | 744122.07 | 744122.07 | 744122.07 | 744122.07
1161585864.9783 |  | Grand Total | 747773979.55 | 802080974.54 | 851971780.31 | 901538332.86 | 940560542.25 | 995857562.09 | 1074374584.41 | 1171692024.93 | 1243225996.1 | 1432829355.92 | 1552284722 | 1637612920.55 | 1922229188.01
1161585864.9783 | From Report File | [13 empty] | 747773979.55 | 2022-12-31
0 | Reconciled | [13 empty] | 1174455208.46 | 2023 Net Additions
[15 empty] | 1174390719.3527 | From Report File
[15 empty] | 64489.1073 | Reconciled (Difference is immaterial)

## Ops Detail for Rpt
Area | (Multiple Items)
| 0 | 779493.8976 | -779493.8976
Row Labels | Sum of 2023 EOP Total Actual CWIP Closings | Sum of JAK5 SEF16 Forecast CWIP Closings | Sum of Variance | Project | Actual Plant Closings | Forecast Used to Set Rates | Forecast < Actual (Forecast > Actual)
AMI Meters and Modules Deployment | -34462242.7455 | -167082331.0171 | 132620088.2716 | AMI Meters and Modules Deployment | 34462242.7455 | 167082331.0171 | -132620088.2716
Bainbridge Tlines Trans | -617924.7517 | -12558883.9009 | 11940959.1492 | Bainbridge Tlines Trans | 617924.7517 | 12558883.9009 | -11940959.1492
Capacity Electric | -2741448.25 | -32512440.3059 | 29770992.0559 | Capacity Electric | 2741448.25 | 32512440.3059 | -29770992.0559
Capacity Gas | -5820359.6636 | -16673797.3577 | 10853437.6941 | Capacity Gas | 5820359.6636 | 16673797.3577 | -10853437.6941
CIAC - Electric | 14562652.3 | 6382400 | 8180252.3 | CIAC - Electric | -14562652.3 | -6382400 | -8180252.3
CIAC - Gas | 198563.8 | 3005100 | -2806536.2 | CIAC - Gas | -198563.8 | -3005100 | 2806536.2
Customer Construction Electric | -83378955.8729 | -4503420.9951 | -78875534.8778 | Customer Construction Electric | 83378955.8729 | 4503420.9951 | 78875534.8778
Customer Construction Gas | -84839700.3855 | -16270357.2655 | -68569343.12 | Customer Construction Gas | 84839700.3855 | 16270357.2655 | 68569343.12
Emergent Electric | -92570410.7281 | -59029849.1636 | -33540561.5645 | Emergent Electric | 92570410.7281 | 59029849.1636 | 33540561.5645
Emergent Gas | -18678693.8696 | -20923806.8619 | 2245112.9924 | Emergent Gas | 18678693.8696 | 20923806.8619 | -2245112.9924
Energize Eastside | -203325688.48 | -40119811.4543 | -163205877.0257 | Energize Eastside | 203325688.48 | 40119811.4543 | 163205877.0257
EV Circuit | -1442703.394 | -7165996.376 | 5723292.982 | EV Circuit | 1442703.394 | 7165996.376 | -5723292.982
Gas Modernization | -14280358.7025 | -24475978.0435 | 10195619.3409 | Gas Modernization | 14280358.7025 | 24475978.0435 | -10195619.3409
Grid Modernization | -158669103.4777 | -177412055.0667 | 18742951.589 | Grid Modernization | 158669103.4777 | 177412055.0667 | -18742951.589
Major Projects Electric | -3100110.6848 | -13216826.7009 | 10116716.0161 | Major Projects Electric | 3100110.6848 | 13216826.7009 | -10116716.0161
Major Projects Gas | -3197291.16 | -576037.5545 | -2621253.6055 | Major Projects Gas | 3197291.16 | 576037.5545 | 2621253.6055
Marine Crossing | -110540.056 | 0 | -110540.056 | Marine Crossing | 110540.056 | 0 | 110540.056
PI Electric | -22456528.4708 | -9797538.9733 | -12658989.4974 | Pipe Replacement | 63783669.4086 | 49664371.494 | 14119297.9146
PI Gas | -37414039.4735 | -143932.3353 | -37270107.1381 | Projected | 21621499.4009 | 12515349.6173 | 9106149.7836
Pipe Replacement | -63783669.4086 | -49664371.494 | -14119297.9146 | PI Electric | 22456528.4708 | 9797538.9733 | 12658989.4974
Projected | -21621499.4009 | -12515349.6173 | -9106149.7836 | PI Gas | 37414039.4735 | 143932.3353 | 37270107.1381
Resilience Enhancement | -1258562.329 | -4266596.5265 | 3008034.1975 | Resilience Enhancement | 1258562.329 | 4266596.5265 | -3008034.1975
Sammamish Juanita 115Kv Tline | -44028432.8917 | -9047247.237 | -34981185.6547 | Sammamish Juanita 115Kv Tline | 44028432.8917 | 9047247.237 | 34981185.6547
Thurston Transmission Capacity | -19661839.26 | -10173066.6069 | -9488772.6531 | Thurston Transmission Capacity | 19661839.26 | 10173066.6069 | 9488772.6531
Grand Total | -902698887.3563 | -678742194.8539 | -223956692.5024 | Over (Under) Closed | 902698887.3563 | 678742194.8539 | 223956692.5024
0

## Ops Detail
Area | (Multiple Items)
| 0 | 779493.8976 | -779493.8976
Row Labels | Sum of 2023 EOP Total Actual CWIP Closings | Sum of JAK5 SEF16 Forecast CWIP Closings | Sum of Variance
Common | -183919.46 | -1246624 | 1062704.54
Projected
Projected | -103105.77 | -1246624 | 1143518.23
Programmatic: Programmatic
AMI Meters and Modules Deployment | -80813.69 | 0 | -80813.69
Electric | -659536234.6094 | -473357791.7232 | -186178442.8862
Programmatic Customer Driven
CIAC - Electric | 14562652.3 | 6382400 | 8180252.3
Customer Construction Electric | -82732671.986 | -4503420.9951 | -78229250.9909
PI Electric | -22456528.4708 | -9797538.9733 | -12658989.4974
Projected
Projected | -13550368.8338 | 4608067.8804 | -18158436.7142
Specific: Specific
Bainbridge Tlines Trans | -617924.7517 | -12558883.9009 | 11940959.1492
Energize Eastside | -203325688.48 | -40119811.4543 | -163205877.0257
Projected | -1635.29 | 0 | -1635.29
Thurston Transmission Capacity | -19661839.26 | -10173066.6069 | -9488772.6531
Sammamish Juanita 115Kv Tline | -44028432.8917 | -9047247.237 | -34981185.6547
Programmatic: Programmatic
Emergent Electric | -92570410.7281 | -59029849.1636 | -33540561.5645
EV Circuit | -1442703.394 | -7165996.376 | 5723292.982
Grid Modernization | -158669103.4777 | -177412055.0667 | 18742951.589
Major Projects Electric | -3100110.6848 | -13216826.7009 | 10116716.0161
Resilience Enhancement | -1258562.329 | -4266596.5265 | 3008034.1975
Capacity Electric | -2741448.25 | -32512440.3059 | 29770992.0559
AMI Meters and Modules Deployment | -27941458.0819 | -104544526.2965 | 76603068.2146
Gas | -242978733.287 | -204137779.1307 | -38840954.1563
Programmatic Customer Driven
CIAC - Gas | 198563.8 | 3005100 | -2806536.2
Customer Construction Electric | -646283.887 | 0 | -646283.887
Customer Construction Gas | -84839700.3855 | -16270357.2655 | -68569343.12
PI Gas | -37414039.4735 | -143932.3353 | -37270107.1381
Projected
Projected | -7966389.5071 | -15876793.4977 | 7910403.9906
Specific: Specific
Marine Crossing | -110540.056 | 0 | -110540.056
Programmatic: Programmatic
Emergent Gas | -18678693.8696 | -20923806.8619 | 2245112.9924
Gas Modernization | -14280358.7025 | -24475978.0435 | 10195619.3409
Major Projects Gas | -3197291.16 | -576037.5545 | -2621253.6055
AMI Meters and Modules Deployment | -6439970.9736 | -62537804.7206 | 56097833.747
Pipe Replacement | -63783669.4086 | -49664371.494 | -14119297.9146
Capacity Gas | -5820359.6636 | -16673797.3577 | 10853437.6941
Grand Total | -902698887.3563 | -678742194.8539 | -223956692.5024

## Ops Explain Table
Area | (Multiple Items)
Row Labels | Sum of 2023 EOP Total Actual CWIP Closings | Sum of JAK5 SEF16 Forecast CWIP Closings | Sum of Variance
(blank) | -214700937.4626 | -101518135.918 | -113182801.5446
Capacity Electric | -2741448.25 | -32512440.3059 | 29770992.0559
Capacity Gas | -5820359.6636 | -16673797.3577 | 10853437.6941
Energize Eastside | -203325688.48 | -40119811.4543 | -163205877.0257
EV Circuit | -1442703.394 | -7165996.376 | 5723292.982
Marine Crossing | -110540.056 | 0 | -110540.056
Projected | -1635.29 | 0 | -1635.29
Resilience Enhancement | -1258562.329 | -4266596.5265 | 3008034.1975
(blank) |  | -779493.8976 | 779493.8976
9 - Projected | -21619864.1109 | -12515349.6173 | -9104514.4936
Projected | -21619864.1109 | -12515349.6173 | -9104514.4936
6E - Grid Mod | -158669103.4777 | -177412055.0667 | 18742951.589
Grid Modernization | -158669103.4777 | -177412055.0667 | 18742951.589
3E - CIAC, NCC, PI | -90626548.1567 | -7918559.9684 | -82707988.1883
CIAC - Electric | 14562652.3 | 6382400 | 8180252.3
Customer Construction Electric | -82732671.986 | -4503420.9951 | -78229250.9909
PI Electric | -22456528.4708 | -9797538.9733 | -12658989.4974
3G - CIAC, NCC, PI | -122701459.9459 | -13409189.6008 | -109292270.3451
CIAC - Gas | 198563.8 | 3005100 | -2806536.2
Customer Construction Electric | -646283.887 | 0 | -646283.887
Customer Construction Gas | -84839700.3855 | -16270357.2655 | -68569343.12
PI Gas | -37414039.4735 | -143932.3353 | -37270107.1381
7E - Maj Proj | -3100110.6848 | -13216826.7009 | 10116716.0161
Major Projects Electric | -3100110.6848 | -13216826.7009 | 10116716.0161
4 - Emergent Work | -111249104.5976 | -79953656.0255 | -31295448.5722
Emergent Electric | -92570410.7281 | -59029849.1636 | -33540561.5645
Emergent Gas | -18678693.8696 | -20923806.8619 | 2245112.9924
1 - AMI | -34462242.7455 | -167082331.0171 | 132620088.2716
AMI Meters and Modules Deployment | -34462242.7455 | -167082331.0171 | 132620088.2716
6G - Gas Mod | -14280358.7025 | -24475978.0435 | 10195619.3409
Gas Modernization | -14280358.7025 | -24475978.0435 | 10195619.3409
7G - Maj Proj | -3197291.16 | -576037.5545 | -2621253.6055
Major Projects Gas | -3197291.16 | -576037.5545 | -2621253.6055
8 - Pipe Replacement | -63783669.4086 | -49664371.494 | -14119297.9146
Pipe Replacement | -63783669.4086 | -49664371.494 | -14119297.9146
2 - Bainbridge | -617924.7517 | -12558883.9009 | 11940959.1492
Bainbridge Tlines Trans | -617924.7517 | -12558883.9009 | 11940959.1492
10 - Sammamish | -44028432.8917 | -9047247.237 | -34981185.6547
Sammamish Juanita 115Kv Tline | -44028432.8917 | -9047247.237 | -34981185.6547
11 - Thurston | -19661839.26 | -10173066.6069 | -9488772.6531
Thurston Transmission Capacity | -19661839.26 | -10173066.6069 | -9488772.6531
Grand Total | -902698887.3563 | -679521688.7515 | -223177198.6048

## Eng ES Stlmt Chg
Energize Eastside Settlement Change
JAK-5 Filing Date | Jul - Dec 2021 | 2022 | 2023 | 2024 | 2025 | Total
Original Filing | 0 | -40119811.4543 | 0 | -256428722.3774 | -254417.0502 | -296802950.882
Compliance Filing | 0 | 0 | -40119811.4543 | -256683139.4277 |  | -296802950.882
Change | 0 | -40119811.4543 | 40119811.4543 | 254417.0502 | -254417.0502 | 0
|  | Assumed the |  |  |  |  | Depreciation Rate
reduction due to
EE delayed in-
|  | service date was |  |  |  |  | 2.51%
|  | redeployed to |  |  |  |  | 1.54%
same depr
groups as EE
See Tab "Eng ES Stlmt Chg"

## SEF-23
DETERMINATION OF DEFICIENCY ASSOCIATED WITH |  |  |  | From 220066 1/9/2023 Compliance Filing
PROVISIONAL PROFORMA ADJUSTMENTS - FOR RATES
SUBJECT TO REFUND
ELECTRIC
LINE | PLANT RELATED COSTS | 2022 | 2023 | 2024
9 | Cost of Debt | 2.62% | 2.55% | 2.55%
10 | ROR per Settlement | 7.23% | 7.16% | 7.16%
11 | Statutory Federal Income Tax Rate | 21% | 21% | 21%
12 | Conversion Factor | 75.24% | 75.24% | 75.24%
13 | Rate Base | 466843558.7252 | 682036404.0763 | 1388026490.6517
14
15 | Impact on Operating Income for Depreciation/Amortization Expense | -7056541.8189 | -30022505.5388 | -72434981.6313
16 | Income Tax Expense | 1731154.2775 | 6205711.5625 | 15652329.7437
17 | Impact on NOI for Depreciation/Amortization Expense | -5325387.5414 | -23816793.9762 | -56782651.8876
18 | Tax Benefit of Proforma Interest | 2568573.2601 | 3652304.9438 | 7432881.8574
19 | Net Operating Income | -2756814.2813 | -20164489.0324 | -49349770.0302
20 | Net Operating Income Requirement (Return on Rate Base) | 33752789.2958 | 48833806.5319 | 99382696.7307
21 | Net Operating Income Deficiency | 36509603.5771 | 68998295.5643 | 148732466.7609
22 | Grossed Up Deficiency - Cumulative | 48527096.3536 | 91709758.7765 | 197689211.5568
23 | Grossed Up Deficiency - Cumulative In Rates | 0 | 91709758.7765 | 197689211.5568
24
25 | Grossed Up Deficiency - By Year | 0 | 91709758.7765 | 105979452.7804
| Annual Deficiency | 48527096.3536 | 43182662.4229 | 105979452.7804 | 197689211.5568 | 0
| Threshold | 0.5% | 0.5% | 0.5%
| Annual Threshold | 4532676.7555 | 4532676.7555 | 9224544.8668
|  | 9.341% | 10.5% | 8.704%

## SEF-24
DETERMINATION OF DEFICIENCY ASSOCIATED WITH |  |  |  | From 220066 1/9/2023 Compliance Filing
PROVISIONAL PROFORMA ADJUSTMENTS - FOR RATES
SUBJECT TO REFUND
NATURAL GAS
LINE | PLANT RELATED COSTS | 2022 | 2023 | 2024
9 | Cost of Debt | 2.62% | 2.55% | 2.55%
10 | ROR per Settlement | 7.23% | 7.16% | 7.16%
11 | Statutory Federal Income Tax Rate | 21% | 21% | 21%
12 | Conversion Factor | 75.48% | 75.48% | 75.48%
13 | Rate Base | 263916344.0549 | 334493403.3409 | 644810592.5354
14
15 | Impact on Operating Income for Depreciation/Amortization Expense | -4562846.2311 | -15825245.0012 | -35109891.3387
16 | Income Tax Expense | 1296670.5468 | 3645192.039 | 7766732.2376
17 | Impact on NOI for Depreciation/Amortization Expense | -3266175.6843 | -12180052.9623 | -27343159.1011
18 | Tax Benefit of Proforma Interest | 1452067.725 | 1791212.1749 | 3452960.723
19 | Net Operating Income | -1814107.9593 | -10388840.7874 | -23890198.378
20 | Net Operating Income Requirement (Return on Rate Base) | 19081151.6752 | 23949727.6792 | 46168438.4255
21 | Net Operating Income Deficiency | 20895259.6345 | 34338568.4666 | 70058636.8036
22 | Grossed Up Deficiency - Cumulative | 27683137.1905 | 45493538.65 | 92817360.872
23 | Grossed Up Deficiency - Cumulative In Rates | 0 | 45493538.65 | 92817360.872
24
25 | Grossed Up Deficiency - By Year | 0 | 45493538.65 | 47323822.222
| Annual Deficiency | 27683137.1905 | 17810401.4596 | 47323822.222 | 92817360.872 | 0
| Threshold | 0.5% | 0.5% | 0.5%
| Annual Threshold | 2215772.1263 | 2215772.1263 | 4271394.6625
|  | 8.004% | 12.44% | 9.026%

## 2023 YE Gross Plant Detail
| Electric with Common Allocation: |  |  |  | Gas with Common Allocation:
Line
No. | Program Name | U&U Category | Company | YE 2023 Additions | Program Name | U&U Category | Company | YE 2023 Additions
1 | AMI Meters and Modules Deployment | Programmatic: Programmatic | C | 2585143.9233 | AMI Meters and Modules Deployment | Programmatic: Programmatic | C | 1335304.8533
2 | AMI Meters and Modules Deployment | Programmatic: Programmatic | E | 15089799.1167 | AMI Meters and Modules Deployment | Programmatic: Programmatic | E | 0
3 | AMI Meters and Modules Deployment | Programmatic: Programmatic | G | 0 | AMI Meters and Modules Deployment | Programmatic: Programmatic | G | 11040154.1867
4 | Bainbridge Tlines Trans | Specific: Specific | E | 163258.2433 | Bainbridge Tlines Trans | Specific: Specific | E | 0
5 | Capacity Electric | Programmatic: Programmatic | E | 5006137.7654 | Capacity Electric | Programmatic: Programmatic | E | 0
6 | Capacity Gas | Programmatic: Programmatic | G | 0 | Capacity Gas | Programmatic: Programmatic | G | 5736257.5908
7 | CIAC - Electric | Projected: Projected | E | -14236237.5342 | CIAC - Electric | Projected: Projected | E | 0
8 | CIAC - Gas | Projected: Projected | G | 0 | CIAC - Gas | Projected: Projected | G | -1568587.6817
9 | Customer Construction Electric | Projected: Projected | E | 79257830.2254 | Customer Construction Electric | Projected: Projected | E | 0
10 | Customer Construction Electric | Projected: Projected | G | 0 | Customer Construction Electric | Projected: Projected | G | 20101.6513
11 | Customer Construction Gas | Projected: Projected | E | 2832.6888 | Customer Construction Gas | Projected: Projected | E | 0
12 | Customer Construction Gas | Projected: Projected | G | 0 | Customer Construction Gas | Projected: Projected | G | 118640878.0504
13 | Customer Sited Energy Storage | Programmatic: Programmatic | E | 9261.405 | Customer Sited Energy Storage | Programmatic: Programmatic | E | 0
14 | Data Center Hardware Refresh | Programmatic: Programmatic | C | 5179821.9019 | Data Center Hardware Refresh | Programmatic: Programmatic | C | 2675534.3339
15 | Emergent Electric | Programmatic: Programmatic | E | 105587700.8337 | Emergent Electric | Programmatic: Programmatic | E | 0
16 | Emergent Gas | Programmatic: Programmatic | G | 0 | Emergent Gas | Programmatic: Programmatic | G | 23739315.7321
17 | Energize Eastside | Specific: Specific | E | 54183824.5017 | Energize Eastside | Specific: Specific | E | 0
18 | EV Circuit | Programmatic: Programmatic | E | 277146.5392 | EV Circuit | Programmatic: Programmatic | E | 0
19 | Gas Modernization | Programmatic: Programmatic | G | 0 | Gas Modernization | Programmatic: Programmatic | G | 19090948.8704
20 | Goldendale MM | Specific: Specific | E | -3595.86 | Goldendale MM | Specific: Specific | E | 0
21 | Grid Modernization | Programmatic: Programmatic | E | 160280782.9967 | Grid Modernization | Programmatic: Programmatic | E | 0
22 | GTZ | Programmatic: Programmatic | E | -29641.09 | GTZ | Programmatic: Programmatic | E | 0
23 | IT Operational Program | Programmatic: Programmatic | C | 6522851.8203 | IT Operational Program | Programmatic: Programmatic | C | 3369249.818
24 | IT Operational Program | Programmatic: Programmatic | E | 232924.97 | IT Operational Program | Programmatic: Programmatic | E | 0
25 | IT Operational Program | Programmatic: Programmatic | G | 0 | IT Operational Program | Programmatic: Programmatic | G | 154464.01
26 | Lower Baker Dam Grouting Program | Specific: Specific | E | 0 | Lower Baker Dam Grouting Program | Specific: Specific | E | 0
27 | Major Projects Electric | Programmatic: Programmatic | E | 2677726.1862 | Major Projects Electric | Programmatic: Programmatic | E | 0
28 | Major Projects Gas | Programmatic: Programmatic | G | 0 | Major Projects Gas | Programmatic: Programmatic | G | 1560532.325
29 | Marine Crossing | Specific: Specific | G | 0 | Marine Crossing | Specific: Specific | G | 506294.4121
30 | Mint Farm MM | Specific: Specific | E | 14435849.02 | Mint Farm MM | Specific: Specific | E | 0
31 | Misc Additions | Misc Additions | C | 26095020.6573 | Misc Additions | Misc Additions | C | 13478865.6898
32 | Misc Additions | Misc Additions | E | 30932629.8917 | Misc Additions | Misc Additions | E | 0
33 | Misc Additions | Misc Additions | G | 0 | Misc Additions | Misc Additions | G | 4413164.9917
34 | PI Electric | Projected: Projected | E | 34271524.095 | PI Electric | Projected: Projected | E | 0
35 | PI Gas | Projected: Projected | G | 0 | PI Gas | Projected: Projected | G | 48534662.1208
36 | Pipe Replacement | Programmatic: Programmatic | G | 0 | Pipe Replacement | Programmatic: Programmatic | G | 60557014.2583
37 | Pre-Capitalized Plant | Pre-Capitalized Plant | E | 71143812.6592 | Pre-Capitalized Plant | Pre-Capitalized Plant | E | 0
38 | Pre-Capitalized Plant | Pre-Capitalized Plant | G | 0 | Pre-Capitalized Plant | Pre-Capitalized Plant | G | 21865008.7858
39 | Projected | Specific: Specific | C | 16843979.2794 | Projected | Specific: Specific | C | 8700423.6314
40 | Projected | Specific: Specific | E | 19188087.7346 | Projected | Specific: Specific | E | 0
41 | Projected | Specific: Specific | G | 0 | Projected | Specific: Specific | G | 1541876.3087
42 | Projected | Programmatic: Programmatic | C | 13985814.2177 | Projected | Programmatic: Programmatic | C | 7224095.1206
43 | Projected | Programmatic: Programmatic | E | 117039704.0442 | Projected | Programmatic: Programmatic | E | 0
44 | Projected | Programmatic: Programmatic | G | 0 | Projected | Programmatic: Programmatic | G | 9432203.7058
45 | Projected | Projected: Projected | E | 17787799.5929 | Projected | Projected: Projected | E | 0
46 | Projected | Projected: Projected | G | 0 | Projected | Projected: Projected | G | 2842664.0217
47 | Remove | Specific: Specific | E | 0 | Remove | Specific: Specific | E | 0
48 | Remove | Specific: Specific | G | 0 | Remove | Specific: Specific | G | 0
49 | Remove | Programmatic: Programmatic | C | 0 | Remove | Programmatic: Programmatic | C | 0
50 | Remove | Programmatic: Programmatic | E | 0 | Remove | Programmatic: Programmatic | E | 0
51 | Remove | Programmatic: Programmatic | G | 0 | Remove | Programmatic: Programmatic | G | 0
52 | Resilience Enhancement | Programmatic: Programmatic | E | 2061746.6196 | Resilience Enhancement | Programmatic: Programmatic | E | 0
53 | Sammamish Juanita 115Kv Tline | Specific: Specific | E | 1834414.8975 | Sammamish Juanita 115Kv Tline | Specific: Specific | E | 0
54 | SAP S/4 Hana | Specific: Specific | C | 0 | SAP S/4 Hana | Specific: Specific | C | 0
55 | Thurston Transmission Capacity | Specific: Specific | E | 6530908.23 | Thurston Transmission Capacity | Specific: Specific | E | 0
56 | Transport Network Modernization | Specific: Specific | C | 1158287.9412 | Transport Network Modernization | Specific: Specific | C | 598290.6775
57 | Grand Total |  |  | 796097147.5136 | Grand Total |  |  | 365488717.4647

## 2023 YE Accum Depr Detail
| Electric with Common Allocation: |  |  |  | Gas with Common Allocation:
Line
No. | Program Name | U&U Category | Company | 2023 Accum Depr | Program Name | U&U Category | Company | 2023 Accum Depr
1 | AMI Meters and Modules Deployment | Programmatic: Programmatic | C | 188944.7083 | AMI Meters and Modules Deployment | Programmatic: Programmatic | C | 97595.644
2 | AMI Meters and Modules Deployment | Programmatic: Programmatic | E | 479223.535 | AMI Meters and Modules Deployment | Programmatic: Programmatic | E | 0
3 | AMI Meters and Modules Deployment | Programmatic: Programmatic | G | 0 | AMI Meters and Modules Deployment | Programmatic: Programmatic | G | 325156.8653
4 | Bainbridge Tlines Trans | Specific: Specific | E | 1713.3319 | Bainbridge Tlines Trans | Specific: Specific | E | 0
5 | Capacity Electric | Programmatic: Programmatic | E | 89858.4513 | Capacity Electric | Programmatic: Programmatic | E | 0
6 | Capacity Gas | Programmatic: Programmatic | G | 0 | Capacity Gas | Programmatic: Programmatic | G | 127484.8242
7 | CIAC - Electric | Projected: Projected | E | -414628.3221 | CIAC - Electric | Projected: Projected | E | 0
8 | CIAC - Gas | Projected: Projected | G | 0 | CIAC - Gas | Projected: Projected | G | -52607.404
9 | Customer Construction Electric | Projected: Projected | E | 2261286.2438 | Customer Construction Electric | Projected: Projected | E | 0
10 | Customer Construction Electric | Projected: Projected | G | 0 | Customer Construction Electric | Projected: Projected | G | 634.7029
11 | Customer Construction Gas | Projected: Projected | E | 285.5777 | Customer Construction Gas | Projected: Projected | E | 0
12 | Customer Construction Gas | Projected: Projected | G | 0 | Customer Construction Gas | Projected: Projected | G | 3263642.438
13 | Customer Sited Energy Storage | Programmatic: Programmatic | E | 1067.5246 | Customer Sited Energy Storage | Programmatic: Programmatic | E | 0
14 | Data Center Hardware Refresh | Programmatic: Programmatic | C | 1015983.7057 | Data Center Hardware Refresh | Programmatic: Programmatic | C | 524786.2453
15 | Emergent Electric | Programmatic: Programmatic | E | 2790029.4704 | Emergent Electric | Programmatic: Programmatic | E | 0
16 | Emergent Gas | Programmatic: Programmatic | G | 0 | Emergent Gas | Programmatic: Programmatic | G | 627814.9393
17 | Energize Eastside | Specific: Specific | E | 177488.0275 | Energize Eastside | Specific: Specific | E | 0
18 | EV Circuit | Programmatic: Programmatic | E | 1991.4333 | EV Circuit | Programmatic: Programmatic | E | 0
19 | Gas Modernization | Programmatic: Programmatic | G | 0 | Gas Modernization | Programmatic: Programmatic | G | 471735.1164
20 | Goldendale MM | Specific: Specific | E | -328.5268 | Goldendale MM | Specific: Specific | E | 0
21 | Grid Modernization | Programmatic: Programmatic | E | 4536779.9115 | Grid Modernization | Programmatic: Programmatic | E | 0
22 | GTZ | Programmatic: Programmatic | E | -8031.0405 | GTZ | Programmatic: Programmatic | E | 0
23 | IT Operational Program | Programmatic: Programmatic | C | 1625896.3801 | IT Operational Program | Programmatic: Programmatic | C | 839824.5482
24 | IT Operational Program | Programmatic: Programmatic | E | 57803.9001 | IT Operational Program | Programmatic: Programmatic | E | 0
25 | IT Operational Program | Programmatic: Programmatic | G | 0 | IT Operational Program | Programmatic: Programmatic | G | 54708.1012
26 | Lower Baker Dam Grouting Program | Specific: Specific | E | 0 | Lower Baker Dam Grouting Program | Specific: Specific | E | 0
27 | Major Projects Electric | Programmatic: Programmatic | E | 79875.9193 | Major Projects Electric | Programmatic: Programmatic | E | 0
28 | Major Projects Gas | Programmatic: Programmatic | G | 0 | Major Projects Gas | Programmatic: Programmatic | G | 2530.2506
29 | Marine Crossing | Specific: Specific | G | 0 | Marine Crossing | Specific: Specific | G | 20370.7903
30 | Mint Farm MM | Specific: Specific | E | 1378362.374 | Mint Farm MM | Specific: Specific | E | 0
31 | Misc Additions | Misc Additions | C | 2367588.9134 | Misc Additions | Misc Additions | C | 1222931.1251
32 | Misc Additions | Misc Additions | E | 681643.6274 | Misc Additions | Misc Additions | E | 0
33 | Misc Additions | Misc Additions | G | 0 | Misc Additions | Misc Additions | G | 48583.2974
34 | PI Electric | Projected: Projected | E | 942974.8829 | PI Electric | Projected: Projected | E | 0
35 | PI Gas | Projected: Projected | G | 0 | PI Gas | Projected: Projected | G | 819483.8991
36 | Pipe Replacement | Programmatic: Programmatic | G | 0 | Pipe Replacement | Programmatic: Programmatic | G | 1303797.243
37 | Pre-Capitalized Plant | Pre-Capitalized Plant | E | 2529677.1644 | Pre-Capitalized Plant | Pre-Capitalized Plant | E | 0
38 | Pre-Capitalized Plant | Pre-Capitalized Plant | G | 0 | Pre-Capitalized Plant | Pre-Capitalized Plant | G | 950232.7654
39 | Projected | Specific: Specific | C | 2253405.2481 | Projected | Specific: Specific | C | 1163951.816
40 | Projected | Specific: Specific | E | 1501951.657 | Projected | Specific: Specific | E | 0
41 | Projected | Specific: Specific | G | 0 | Projected | Specific: Specific | G | 80787.153
42 | Projected | Programmatic: Programmatic | C | 2139622.153 | Projected | Programmatic: Programmatic | C | 1105179.4136
43 | Projected | Programmatic: Programmatic | E | 4852789.2262 | Projected | Programmatic: Programmatic | E | 0
44 | Projected | Programmatic: Programmatic | G | 0 | Projected | Programmatic: Programmatic | G | 332860.858
45 | Projected | Projected: Projected | E | 558451.2426 | Projected | Projected: Projected | E | 0
46 | Projected | Projected: Projected | G | 0 | Projected | Projected: Projected | G | 59887.7827
47 | Remove | Specific: Specific | E | 0 | Remove | Specific: Specific | E | 0
48 | Remove | Specific: Specific | G | 0 | Remove | Specific: Specific | G | 0
49 | Remove | Programmatic: Programmatic | C | 0 | Remove | Programmatic: Programmatic | C | 0
50 | Remove | Programmatic: Programmatic | E | 0 | Remove | Programmatic: Programmatic | E | 0
51 | Remove | Programmatic: Programmatic | G | 0 | Remove | Programmatic: Programmatic | G | 0
52 | Resilience Enhancement | Programmatic: Programmatic | E | 23249.9067 | Resilience Enhancement | Programmatic: Programmatic | E | 0
53 | Sammamish Juanita 115Kv Tline | Specific: Specific | E | 2068.037 | Sammamish Juanita 115Kv Tline | Specific: Specific | E | 0
54 | SAP S/4 Hana | Specific: Specific | C | 0 | SAP S/4 Hana | Specific: Specific | C | 0
55 | Thurston Transmission Capacity | Specific: Specific | E | 36730.1385 | Thurston Transmission Capacity | Specific: Specific | E | 0
56 | Transport Network Modernization | Specific: Specific | C | 199416.3006 | Transport Network Modernization | Specific: Specific | C | 103004.5374
57 | Grand Total |  |  | 32353171.1028 | Grand Total |  |  | 13494376.9524

## 2023 YE Def Tax Detail
| Electric with Common Allocation: |  |  |  | Gas with Common Allocation:
Line
No. | Program Name | U&U Category | Company | Deferred Tax | Program Name | U&U Category | Company | Deferred Tax
1 | AMI Meters and Modules Deployment | Programmatic: Programmatic | C | 454726.9859 | AMI Meters and Modules Deployment | Programmatic: Programmatic | C | 234880.2114
2 | AMI Meters and Modules Deployment | Programmatic: Programmatic | E | 686458.4655 | AMI Meters and Modules Deployment | Programmatic: Programmatic | E | 0
3 | AMI Meters and Modules Deployment | Programmatic: Programmatic | G | 0 | AMI Meters and Modules Deployment | Programmatic: Programmatic | G | 799247.7393
4 | Bainbridge Tlines Trans | Specific: Specific | E | 7953.1627 | Bainbridge Tlines Trans | Specific: Specific | E | 0
5 | Capacity Electric | Programmatic: Programmatic | E | 107382.3825 | Capacity Electric | Programmatic: Programmatic | E | 0
6 | Capacity Gas | Programmatic: Programmatic | G | 0 | Capacity Gas | Programmatic: Programmatic | G | 264050.6579
7 | CIAC - Electric | Projected: Projected | E | -60662.9838 | CIAC - Electric | Projected: Projected | E | 0
8 | CIAC - Gas | Projected: Projected | G | 0 | CIAC - Gas | Projected: Projected | G | -31370.6997
9 | Customer Construction Electric | Projected: Projected | E | 799870.0238 | Customer Construction Electric | Projected: Projected | E | 0
10 | Customer Construction Electric | Projected: Projected | G | 0 | Customer Construction Electric | Projected: Projected | G | 615.7925
11 | Customer Construction Gas | Projected: Projected | E | 65.394 | Customer Construction Gas | Projected: Projected | E | 0
12 | Customer Construction Gas | Projected: Projected | G | 0 | Customer Construction Gas | Projected: Projected | G | 4462663.8954
13 | Customer Sited Energy Storage | Programmatic: Programmatic | E | 6830.9921 | Customer Sited Energy Storage | Programmatic: Programmatic | E | 0
14 | Data Center Hardware Refresh | Programmatic: Programmatic | C | 379675.0758 | Data Center Hardware Refresh | Programmatic: Programmatic | C | 196113.6348
15 | Emergent Electric | Programmatic: Programmatic | E | 1400751.5094 | Emergent Electric | Programmatic: Programmatic | E | 0
16 | Emergent Gas | Programmatic: Programmatic | G | 0 | Emergent Gas | Programmatic: Programmatic | G | 949428.7536
17 | Energize Eastside | Specific: Specific | E | 1055058.266 | Energize Eastside | Specific: Specific | E | 0
18 | EV Circuit | Programmatic: Programmatic | E | -20644.5712 | EV Circuit | Programmatic: Programmatic | E | 0
19 | Gas Modernization | Programmatic: Programmatic | G | 0 | Gas Modernization | Programmatic: Programmatic | G | 729457.3914
20 | Goldendale MM | Specific: Specific | E | -16.7042 | Goldendale MM | Specific: Specific | E | 0
21 | Grid Modernization | Programmatic: Programmatic | E | 1655045.2759 | Grid Modernization | Programmatic: Programmatic | E | 0
22 | GTZ | Programmatic: Programmatic | E | -756.9488 | GTZ | Programmatic: Programmatic | E | 0
23 | IT Operational Program | Programmatic: Programmatic | C | 208436.0406 | IT Operational Program | Programmatic: Programmatic | C | 107663.5053
24 | IT Operational Program | Programmatic: Programmatic | E | 6969.7947 | IT Operational Program | Programmatic: Programmatic | E | 0
25 | IT Operational Program | Programmatic: Programmatic | G | 0 | IT Operational Program | Programmatic: Programmatic | G | -102.4205
26 | Lower Baker Dam Grouting Program | Specific: Specific | E | 0 | Lower Baker Dam Grouting Program | Specific: Specific | E | 0
27 | Major Projects Electric | Programmatic: Programmatic | E | 126527.7078 | Major Projects Electric | Programmatic: Programmatic | E | 0
28 | Major Projects Gas | Programmatic: Programmatic | G | 0 | Major Projects Gas | Programmatic: Programmatic | G | 16464.0862
29 | Marine Crossing | Specific: Specific | G | 0 | Marine Crossing | Specific: Specific | G | 10175.0628
30 | Mint Farm MM | Specific: Specific | E | -12983.6954 | Mint Farm MM | Specific: Specific | E | 0
31 | Misc Additions | Misc Additions | C | 2472789.0015 | Misc Additions | Misc Additions | C | 1277270.1454
32 | Misc Additions | Misc Additions | E | -526431.1633 | Misc Additions | Misc Additions | E | 0
33 | Misc Additions | Misc Additions | G | 0 | Misc Additions | Misc Additions | G | -352034.8311
34 | PI Electric | Projected: Projected | E | 686173.009 | PI Electric | Projected: Projected | E | 0
35 | PI Gas | Projected: Projected | G | 0 | PI Gas | Projected: Projected | G | 1890061.7372
36 | Pipe Replacement | Programmatic: Programmatic | G | 0 | Pipe Replacement | Programmatic: Programmatic | G | 2815729.3854
37 | Pre-Capitalized Plant | Pre-Capitalized Plant | E | 2619136.8857 | Pre-Capitalized Plant | Pre-Capitalized Plant | E | 0
38 | Pre-Capitalized Plant | Pre-Capitalized Plant | G | 0 | Pre-Capitalized Plant | Pre-Capitalized Plant | G | 1073249.3371
39 | Projected | Specific: Specific | C | 784066.4216 | Projected | Specific: Specific | C | 404993.9691
40 | Projected | Specific: Specific | E | 794756.554 | Projected | Specific: Specific | E | 0
41 | Projected | Specific: Specific | G | 0 | Projected | Specific: Specific | G | 117642.9639
42 | Projected | Programmatic: Programmatic | C | 274664.7693 | Projected | Programmatic: Programmatic | C | 141872.6424
43 | Projected | Programmatic: Programmatic | E | 3064190.2691 | Projected | Programmatic: Programmatic | E | 0
44 | Projected | Programmatic: Programmatic | G | 0 | Projected | Programmatic: Programmatic | G | 453855.0661
45 | Projected | Projected: Projected | E | 399848.0295 | Projected | Projected: Projected | E | 0
46 | Projected | Projected: Projected | G | 0 | Projected | Projected: Projected | G | 100282.8873
47 | Remove | Specific: Specific | E | 0 | Remove | Specific: Specific | E | 0
48 | Remove | Specific: Specific | G | 0 | Remove | Specific: Specific | G | 0
49 | Remove | Programmatic: Programmatic | C | 0 | Remove | Programmatic: Programmatic | C | 0
50 | Remove | Programmatic: Programmatic | E | 0 | Remove | Programmatic: Programmatic | E | 0
51 | Remove | Programmatic: Programmatic | G | 0 | Remove | Programmatic: Programmatic | G | 0
52 | Resilience Enhancement | Programmatic: Programmatic | E | 34077.9863 | Resilience Enhancement | Programmatic: Programmatic | E | 0
53 | Sammamish Juanita 115Kv Tline | Specific: Specific | E | 262480.7924 | Sammamish Juanita 115Kv Tline | Specific: Specific | E | 0
54 | SAP S/4 Hana | Specific: Specific | C | 0 | SAP S/4 Hana | Specific: Specific | C | 0
55 | Thurston Transmission Capacity | Specific: Specific | E | 109217.7963 | Thurston Transmission Capacity | Specific: Specific | E | 0
56 | Transport Network Modernization | Specific: Specific | C | 96472.8385 | Transport Network Modernization | Specific: Specific | C | 49831.1326
57 | Grand Total |  |  | 17872129.363 | Grand Total |  |  | 15712042.0459

## 2023 YE Depr Expense
| Electric with Common Allocation: |  |  |  | Gas with Common Allocation:
Line
No. | Program Name | U&U Category | Company | Depr Expense | Program Name | U&U Category | Company | Depr Expense
1 | AMI Meters and Modules Deployment | Programmatic: Programmatic | C | 184822.5372 | AMI Meters and Modules Deployment | Programmatic: Programmatic | C | 95466.4182
2 | AMI Meters and Modules Deployment | Programmatic: Programmatic | E | 748941.0545 | AMI Meters and Modules Deployment | Programmatic: Programmatic | E | 0
3 | AMI Meters and Modules Deployment | Programmatic: Programmatic | G | 0 | AMI Meters and Modules Deployment | Programmatic: Programmatic | G | 636646.7054
4 | Bainbridge Tlines Trans | Specific: Specific | E | 14509.2103 | Bainbridge Tlines Trans | Specific: Specific | E | 0
5 | Capacity Electric | Programmatic: Programmatic | E | 169609.7565 | Capacity Electric | Programmatic: Programmatic | E | 0
6 | Capacity Gas | Programmatic: Programmatic | G | 0 | Capacity Gas | Programmatic: Programmatic | G | 181980.8994
7 | CIAC - Electric | Projected: Projected | E | -631668.0808 | CIAC - Electric | Projected: Projected | E | 0
8 | CIAC - Gas | Projected: Projected | G | 0 | CIAC - Gas | Projected: Projected | G | -53328.0327
9 | Customer Construction Electric | Projected: Projected | E | 3262097.4906 | Customer Construction Electric | Projected: Projected | E | 0
10 | Customer Construction Electric | Projected: Projected | G | 0 | Customer Construction Electric | Projected: Projected | G | 833.4495
11 | Customer Construction Gas | Projected: Projected | E | 204.8003 | Customer Construction Gas | Projected: Projected | E | 0
12 | Customer Construction Gas | Projected: Projected | G | 0 | Customer Construction Gas | Projected: Projected | G | 4530169.9028
13 | Customer Sited Energy Storage | Programmatic: Programmatic | E | 770.0789 | Customer Sited Energy Storage | Programmatic: Programmatic | E | 0
14 | Data Center Hardware Refresh | Programmatic: Programmatic | C | 1133177.3872 | Data Center Hardware Refresh | Programmatic: Programmatic | C | 585320.3186
15 | Emergent Electric | Programmatic: Programmatic | E | 3739639.292 | Emergent Electric | Programmatic: Programmatic | E | 0
16 | Emergent Gas | Programmatic: Programmatic | G | 0 | Emergent Gas | Programmatic: Programmatic | G | 943299.3207
17 | Energize Eastside | Specific: Specific | E | 1229545.278 | Energize Eastside | Specific: Specific | E | 0
18 | EV Circuit | Programmatic: Programmatic | E | 9665.3952 | EV Circuit | Programmatic: Programmatic | E | 0
19 | Gas Modernization | Programmatic: Programmatic | G | 0 | Gas Modernization | Programmatic: Programmatic | G | 656078.7005
20 | Goldendale MM | Specific: Specific | E | -265.5543 | Goldendale MM | Specific: Specific | E | 0
21 | Grid Modernization | Programmatic: Programmatic | E | 6109532.7677 | Grid Modernization | Programmatic: Programmatic | E | 0
22 | GTZ | Programmatic: Programmatic | E | -6422.2362 | GTZ | Programmatic: Programmatic | E | 0
23 | IT Operational Program | Programmatic: Programmatic | C | 1249098.8131 | IT Operational Program | Programmatic: Programmatic | C | 645197.2334
24 | IT Operational Program | Programmatic: Programmatic | E | 38082.0946 | IT Operational Program | Programmatic: Programmatic | E | 0
25 | IT Operational Program | Programmatic: Programmatic | G | 0 | IT Operational Program | Programmatic: Programmatic | G | 36381.2027
26 | Lower Baker Dam Grouting Program | Specific: Specific | E | 0 | Lower Baker Dam Grouting Program | Specific: Specific | E | 0
27 | Major Projects Electric | Programmatic: Programmatic | E | 111013.6966 | Major Projects Electric | Programmatic: Programmatic | E | 0
28 | Major Projects Gas | Programmatic: Programmatic | G | 0 | Major Projects Gas | Programmatic: Programmatic | G | 9050.9312
29 | Marine Crossing | Specific: Specific | G | 0 | Marine Crossing | Specific: Specific | G | 15917.2545
30 | Mint Farm MM | Specific: Specific | E | 1788962.5898 | Mint Farm MM | Specific: Specific | E | 0
31 | Misc Additions | Misc Additions | C | 4592681.6548 | Misc Additions | Misc Additions | C | 2372258.677
32 | Misc Additions | Misc Additions | E | 2629068.0996 | Misc Additions | Misc Additions | E | 0
33 | Misc Additions | Misc Additions | G | 0 | Misc Additions | Misc Additions | G | 189844.3345
34 | PI Electric | Projected: Projected | E | 1633228.3674 | PI Electric | Projected: Projected | E | 0
35 | PI Gas | Projected: Projected | G | 0 | PI Gas | Projected: Projected | G | 1326797.8208
36 | Pipe Replacement | Programmatic: Programmatic | G | 0 | Pipe Replacement | Programmatic: Programmatic | G | 1884037.7668
37 | Pre-Capitalized Plant | Pre-Capitalized Plant | E | 3424141.0999 | Pre-Capitalized Plant | Pre-Capitalized Plant | E | 0
38 | Pre-Capitalized Plant | Pre-Capitalized Plant | G | 0 | Pre-Capitalized Plant | Pre-Capitalized Plant | G | 1025279.735
39 | Projected | Specific: Specific | C | 2411041.2972 | Projected | Specific: Specific | C | 1245375.5927
40 | Projected | Specific: Specific | E | 1754983.0134 | Projected | Specific: Specific | E | 0
41 | Projected | Specific: Specific | G | 0 | Projected | Specific: Specific | G | 111473.3976
42 | Projected | Programmatic: Programmatic | C | 2209168.5682 | Projected | Programmatic: Programmatic | C | 1141102.2358
43 | Projected | Programmatic: Programmatic | E | 5869773.7732 | Projected | Programmatic: Programmatic | E | 0
44 | Projected | Programmatic: Programmatic | G | 0 | Projected | Programmatic: Programmatic | G | 424467.4094
45 | Projected | Projected: Projected | E | 662284.2291 | Projected | Projected: Projected | E | 0
46 | Projected | Projected: Projected | G | 0 | Projected | Projected: Projected | G | 79361.3397
47 | Remove | Specific: Specific | E | 0 | Remove | Specific: Specific | E | 0
48 | Remove | Specific: Specific | G | 0 | Remove | Specific: Specific | G | 0
49 | Remove | Programmatic: Programmatic | C | 0 | Remove | Programmatic: Programmatic | C | 0
50 | Remove | Programmatic: Programmatic | E | 0 | Remove | Programmatic: Programmatic | E | 0
51 | Remove | Programmatic: Programmatic | G | 0 | Remove | Programmatic: Programmatic | G | 0
52 | Resilience Enhancement | Programmatic: Programmatic | E | 49182.1048 | Resilience Enhancement | Programmatic: Programmatic | E | 0
53 | Sammamish Juanita 115Kv Tline | Specific: Specific | E | 49632.8881 | Sammamish Juanita 115Kv Tline | Specific: Specific | E | 0
54 | SAP S/4 Hana | Specific: Specific | C | 0 | SAP S/4 Hana | Specific: Specific | C | 0
55 | Thurston Transmission Capacity | Specific: Specific | E | 168872.8117 | Thurston Transmission Capacity | Specific: Specific | E | 0
56 | Transport Network Modernization | Specific: Specific | C | 241726.8724 | Transport Network Modernization | Specific: Specific | C | 124859.2247
57 | Grand Total |  |  | 44847101.1512 | Grand Total |  |  | 18207871.8384

## 2023 Retirement Depr Adj
| Depreciation Impact of Actual Retirements: |  | Four Factor Allocation Percentages: | Gas: | 34.06%
| 2023, Rate Year 1 |  |  | Electric: | 65.94%
Line
No. |  | Inc (Dec) Expense |  | Inc (Dec) Rate Base
1 | Common: |  | Common:
2 | Common Depr/Amort Expense | -3978749.354 | Common Accum Depr/Amort | 3978749.354
3
4
5 | Electric: |  | Electric:
6 | Electric Depr/Amort Expense | -3386251.9836 | Electric Accum Depr/Amort | 3386251.9836
7 | Less: Colstrip Depr/Amort | 857168.7132 | Less: Colstrip Depr/Amort | -857168.7132
8 | Plus: Elec portion of Common | -2623587.324 | Plus: Elec portion of Common | 2623587.324
9 | Increase (Decrease) Expense | -5152670.5945 | Increase (Decrease) Rate Base | 5152670.5945
10
11 | Increase (Decrease) FIT | 1082060.8248 | ADIT | -17870599.5459
12 | EDIT | 1173382.9652 | EDIT | -1173382.9652
13 | Flow-Through | -44573.1572 | Inc(Dec) Electric Rate Base | -13891311.9167
14 | Inc(Dec) Electric Expense | -2941799.9616
15
16 | Gas: |  | Gas:
17 | Gas Depr/Amort Expense | -383506.6432 | Gas Accum Depr/Amort | 383506.6432
18 | Plus: Gas portion of Common | -1355162.03 | Plus: Gas portion of Common | 1355162.03
19 | Increase (Decrease) Expense | -1738668.6732 | Increase (Decrease) Rate Base | 1738668.6732
20
21 | Increase (Decrease) FIT | 365120.4214 | ADIT | -10697927.1905
22 | EDIT | 34611.0283 | EDIT | 56827.4108
23 | Flow-Through | -85992.2953 | Inc(Dec) Gas Rate Base | -8902431.1065
24 | Inc(Dec) Gas Expense | -1424929.5189

## RB Act v Rates
AMA 2023
Description | Electric | Gas
(in billions)
Adjusted CBR | 5.52 | 2.7055
GRC (excludes AMI and TLNG Facility) | 5.44 | 2.56
Act > GRC | 0.08 | 0.14553
Test Year EOP | 5.7 | 3
Remove AMI | -0.18 | -0.09
Remove Tacoma LNG Facility | 0 | -0.20447
Adjusted CBR | 5.52 | 2.7055
204465073.75
0.20447
AMI
Gross Plant | 0.25 | 0.11
Accumulated Depreciation | -0.04 | -0.01
Accumulated Deferred Income Taxes | -0.03 | -0.01
Total AMI | 0.18 | 0.09