## Sheet1
ESCHELON DATA FROM BJJ-6 | [13 empty] | QWEST REVIEW
PON | LSR ID | Reason for Invalid Customer Not Ready Jeopardy | Eschelon Requested Due Date | Did Qwest Complete Order on Eschelon Requested Due Date (DDD) Yes/No | Date Qwest Sent K Jeopardy | Date and Time Qwest called to Deliver Circuit in K Jeopardy Status | Date Qwest sent Releasing FOC for K Jeopardy | New Due Date on Releasing FOC for K Jeopardy | Date Eschelon Received Classification of CNR Jeopardy | Actual Completion Date | Number of Days between Requested Due Date and the actual Completion date | ST | Order # | Qwest Tech Notes | CNR Jeopardy in Error? | FOC Sent after original Jeopardy?
OR462897T1FAC | 12971352 | Releasing FOC for K 1 jep never sent. Qwest applied invalid CNR jeopardy | 2005-01-11 17:00 | No | 2005-01-06 19:04 | Not Recorded | NOT SENT | NOT SENT | 2005-01-11 | 2005-01-12 | 1 | OR | N10835043 | Although Qwest did not send a FOC prior to the DD of 1/11/05; Qwest started working with Adam at Eschelon prior to 5 p.m. End result is that Eschlon was having wiring problems and Adam at Eschelon indicated that he needed to dispatch a technician to the cage and Adam said he would supp the order. Qwest subsequently received the supplement as indicated by Eschelon and Adam at Eschelon accepted the service on 1/12 (Qwest installed the service prior to the supp'd due date of 1/17) | NO | NO
UT474484T1FAC | 13275636 | Releasing FOC not sent the day prior to DD Qwest applied an invalid CNR jeopardy | 2005-02-09 17:00 | No | 2005-02-08 13:44 | Not Recorded | 2005-02-09 | 2005-02-09 | 2005-02-08 | 2005-02-14 | 5 | UT | N13197574 | DD 2/9/05 missed due to Qwest reasons and a jeopardy of K45 was shown on the order in Qwest's systems as the original due date miss. Qwest contacted Mark at Eschelon at 7:36 am on the DD to advise of possible miss. 2/10 at 7:18 called Eschelon and left Voice Mail that Qwest was ready to test and due date rescheduled for today. Eschelon never called back and a second DD jeopardy of C01 was posted against the order. C01 jeopardy notice was sent to CLEC on the 10th. 2/14 supp to chg DD to 2/17; however Qwest still installed on the 14th. | NO | NO
CO477191T1FAC | 13337990 | Releasing FOC not sent 24 hours prior to DD Qwest applied an invalid CNR Jeopardy | 2005-02-17 17:00 | Yes | 2005-02-17 12:28 | 2005-02-17 12:28 | 2005-02-17 | 2005-02-17 | 2005-02-17 | 2005-02-17 | 0 | CO | N14415724 | CLEC received jeopardy notice at 1:41 and Qwest immediately followed with a FOC at 1:52 re-acknowledging the DD of 2/17/05; 2/17 referred to CLEC but no CLEC callback at 17:16 so C01 jeop; 2/17 18:21 CLEC cld bk & accepted, tester removed C01 jeop | NO | YES
OR477412T1FAC | 13349048 | Releasing FOC for K 1 jep never sent. Qwest applied invalid CNR jeopardy | 2005-02-23 17:00 | No | 2006-02-22 19:00 | Not Recorded | NOT SENT | NOT SENT | 2005-02-23 | 2005-02-24 | 1 | OR | N14485305 | Orig K17 jeop sent 2/22 at 6:02 pm. Jeopardy condition cleared on the DD. Contacted Eschelon to attempt to turn up the circuit. Eschelon indicated they would be avail after 5P Pac, CLEC had equipment problems and C01 jeop posted; 2/24 supp to chg DD to 3/1; Qwest did install and Eschelon accepted on 2/24 instead of waiting until new DD of 3/1 | NO | NO
AZ485850T1FAC | 13789261 | Releasing FOC for K 1 jep never sent. Qwest applied invalid CNR jeopardy | 2005-03-17 17:00 | No | 2005-03-16 20:07 | Not Recorded | NOT SENT | NOT SENT | 2005-03-17 | 2005-03-18 | 1 | AZ | N17311757 | Jeopardy notice was sent 3/16 and later cleared. No FOC resent. Talked to Tracy at Eschelon on the PTD 3/16/05 at 13:59, he was going to test and call back. 3/17 no callback from CLEC. C01 jeop posted. 3/18 supp to chg DD to 3/23; Qwest installed the circuit on 3/18 with the CLEC instead of waiting for new 3/23 date. | NO | NO
WA494646T1FAC | 14216585 | Releasing FOC for K 1 jep never sent. Qwest applied invalid CNR jeopardy | 2005-04-14 17:00 | No | 2005-04-13 15:38 | Not Recorded | NOT SENT | NOT SENT | 2005-04-14 | 2005-04-15 | 1 | WA | N21366533 | K17 jeop sent 4/13 and K43 on DD 4/14/05. Contacted Jeff at Eschelon at 16:58 he said he would test and call back. Jeff called back at 17:23 can't see signal. Problem originally thought to be on CLEC side. 4/15 found trbl to be in Qwest wiring, fixed & CLEC accepted | NO | NO
AZ510194T1FAC | 14657841 | Releasing FOC for K 1 jep never sent. Qwest applied invalid CNR jeopardy | 2005-06-03 17:00 | No | 2005-05-31 19:01 | Not Recorded | NOT SENT | NOT SENT | 2005-06-06 | 2005-06-07 | 4 | AZ | N26053835 | Sent K17 jeop on 5/31 and a K18 on 6/3. DD 6/3/05 missed due to Qwest reasons and coded as such in Qwest internal systems. No FOC sent. 6/6 refd to CLEC who will test & call back C01 jeop; CLEC can't loop NIU; Originally problem thought to be on the CLEC side. 6/7 found trbl to be in Qwest wiring, fixed & CLEC accepted | NO | NO
CO528230T1FAC | 15276469 | Releasing FOC not sent the day prior to DD Qwest applied an invalid CNR jeopardy | 2005-08-05 17:00 | No | 2005-08-01 12:54 | Not Recorded | 2005-08-05 07:33 | 2005-08-05 | 2005-08-05 | 2005-08-08 | 3 | CO | N30873460 | Sent K17 jeoparrdy on 8/1. Sent K18 jeopardy on 8/4. Sent FOC 8/5 at 7:33 DD 8/5/05; 8/5 16:34 refd to CLEC; 19:23 no CLEC callback C01 jeop; 8/8 supp to chg DD to 8/11; 8/8 CLEC called to accept | NO | YES
WA535799T1FAC | 15508546 | Releasing FOC not sent the day prior to DD Qwest applied an invalid CNR jeopardy | 2005-09-02 17:00 | No | 2005-08-29 15:08 | Not Recorded | 2005-09-02 15:05 | 2005-09-02 | 2005-09-02 | 2005-09-07 | 5 | WA | N33388590 | Initial jeop sent K17 on 8/29. Jeop K08 on 8/31. 9/2 sent FOC with DD 9/2/05 at 3:05. 9/2 refd to Joe at Eschelon at 16:13, Joe advised to C01 jeop.C01 jeop; 9/6 supp to chg DD to 9/9; 9/7 CLEC accepted the circuit | NO | YES
AZ591886T1FAC | 16172421 | Releasing FOC for K 1 jep never sent. Qwest applied invalid CNR jeopardy | 2005-11-22 17:00 | No | 2005-11-21 14:37 | Not Recorded | NOT SENT | NOT SENT | 2005-11-22 | 2005-12-02 | 5 | AZ | N40299259 | Sent K17 on 11/21. K45 jeop sent also on 11/21at 6pm. Sent FOC 11/21 5:49pm with 11/22 DD. 11/22 1658 refd to CLEC; 1729 no CLEC callback C01 jeop; 11/29 supp to chg DD to 12/2; 11/29 CLEC can't loop NIU will dispatch CLEC tech to cage; 12/2 CLEC accepted | NO | YES
WA609209T1FAC | 16594320 | Releasing FOC for K 1 jep never sent. Qwest applied invalid CNR jeopardy | 2006-01-13 17:00 | No | 2006-01-11 19:38 | Not Recorded | NOT SENT | NOT SENT | 2006-01-13 | 2006-01-18 | 5 | WA | N44115166 | Initial jeop 1/11 K17 jeop. 1/12 K17 jeop. No FOC. DD 1/13/06; 1/13 referred to CLEC Jeff at Eschelon at 16:49 left message. 17:29 on 1/13 worked with CLEC to try to turn up CKT. CLEC unable to accept. C01 jeop; 1/17 supp to chg DD to 1/20; 1/18 refd to CLEC & CLEC (Joe) accepted | NO | NO Qwest Error
AZ610571T1FAC | 16615282 | Releasing FOC not sent the day prior to DD Qwest applied an invalid end user customer no access C02 jeopardy | 2006-01-16 17:00 | No | 2006-01-11 17:14 | 2006-01-16 16:42 | 2006-01-16 15:42 | 2006-01-16 | 2006-01-16 | 2006-01-23 | 7 | AZ | N43700628 | Initial jeop K17 on 1/11. Sent FOC 1/16 at 3:42 with 1/16 DD. 1/16 15:51 received call from outside tech, advised NoAccess to prem Called CLEC and advised no access. C02 jeopardy posted. 1/20 supp to chg DD to 1/25, cld CLEC advsd ckt rdy; 1/23 CLEC accepted (prior to 1/25 supped due date) | NO | YES
AZ610687T1FAC | 16615986 | Releasing FOC for K 1 jep never sent. Qwest applied invalid CNR jeopardy | 2006-01-16 17:00 | No | 2006-01-13 13:52 | Not Recorded | NOT SENT | NOT SENT | 2006-01-16 | 2006-01-18 | 2 | AZ | N45042996 | K17 jeop 1/13. No FOC. 1/16 C01 jeop posted. DD 1/16/06; 1/16 15:43 advsd Lex at Eschelon order was released from held. He said would test and call back. 16:39 CLEC cannot loop NIU, still trying to meet DD. CLEC wl stay til 1800, unable to resolve before CLEC left, C01 jeop'd in error (should have been K jeop); 1/18 supp to chg DD to 1/23; 1/18 CLEC accepted | YES | NO
AZ602905T1FAC | 16798946 | Releasing FOC for K 1 jep never sent. Qwest applied invalid CNR jeopardy | 2006-02-07 17:00 | No | 2006-01-31 13:39 | Not Recorded | NOT SENT | NOT SENT | 2006-02-07 | 2006-02-09 | 2 | AZ | N46302319 | Initial K17 jeop sent on 1/31. FOC send 2/2 with DD 2/7; 2/6 K18 jeop was issued. No subsequent FOC. 2/7 10:08 referred order to CLEC to test but no CLEC callback (as of 17:34); C01 jeop posted. 2/8 supp to chg DD to 2/13; 2/9 CLEC accepted service and order completed. | NO | YES
AZ624356T1FAC | 16886232 | Releasing FOC for K 1 jep never sent. Qwest applied invalid CNR jeopardy | 2006-02-16 17:00 | No | 2006-02-13 19:00 | Not Recorded | NOT SENT | NOT SENT | 2006-02-16 | 2006-02-20 | 4 | AZ | N47011517 | Sent K17 jeops on 2/13. No FOC. Sent K18 jeop at 16:02 on 2/16. DD 2/16, jeop was cleared in the field. 2/16 16:04 talked to CLEC who was going to test and call back, but no CLEC callback (as of 17:58) C01 jeop; 2/17 supp to chg DD to 2/22; 2/20 CLEC accepted | NO | NO
MN660526T1FAC | 17197449 | Releasing FOC for K 1 jep never sent. Qwest applied invalid CNR jeopardy | 2006-03-24 17:00 | No | 2006-03-24 19:00 | 2006-03-24 13:46 | NOT SENT | NOT SENT | 2006-03-27 18:00 | 2006-03-30 | 6 | MN | N49735347 | Sent K17 on 3/24 at 13:10. Then at 18:01 B33 jeop sent followed by a C01 jeop on 3/24/06; 3/24 13:35. Talked to Stan at Eschelon advised end user needs to provide ground. C01 jeop EU needs to provide ground; K18 jeop to recover prs; CNR jeopardy posted in error due to pair recovery issue. 3/30 CLEC accepted | YES | NO
MN659573T1FAC | 17223262 | Releasing FOC for K 1 jep never sent. Qwest applied invalid CNR jeopardy | 2006-03-28 17:00 | No | 2006-03-27 14:18 | 2006-03-28 13:49 | NOT SENT | NOT SENT | 2006-03-28 18:01 | 2006-03-31 | 3 | MN | N50018967 - 70 | 3/27 sent K17 jeopardy for 2 orders. 3/27 K18 jeop on another order. No FOC. 3/28 C01 jeop. 3/28 13:44 called CLEC, referred to Dave. 13:53 said to jeop back to Escelon they are not ready. 3/29 supp to chg DD to 4/3; 3/30 refd to CLEC; 3/31 CLEC accepted | NO | NO
OR668544T1FAC | 17301788 | Releasing FOC for K 1 jep never sent. Qwest applied invalid CNR jeopardy | 2006-04-14 17:00 | No | 2006-04-14 16:01 | Not Recorded | NOT SENT | NOT SENT | 2006-04-14 18:03 | 2006-04-21 | 7 | OR | N50692388 | 4/14 sent K17 jeop 3pm. No FOC. DD 4/14/06; 4/14 refd 15:30 referred to Surge at Eschelon, but no callback; C01 posted. 4/21 supp to chg DD to 4/26; 4/24 refd to CLEC & CLEC accepted | NO | NO
WA696462T1FAC | 17804830 | Releasing FOC for K 1 jep never sent. Qwest applied invalid CNR jeopardy | 2006-06-07 17:00 | No | 2006-06-07 09:56 | Not Recorded | NOT SENT | NOT SENT | 2006-06-07 18:02 | 2006-06-08 | 1 | WA | N55399841 | 6/7 sent K18 jeop at 8:55. Jeopardy resolved later in the day on due date (6/7) DD 6/7/06. 6/7 16:45 tried to ref CLEC 206-346-3806 but Ring No Answer. C01 jeop; 6/8 DD chg to 6/13; 6/8 CLEC accepted | NO | NO
CO689077T1FAC | 17705435 | Releasing FOC not sent the day prior to DD Qwest applied an invalid CNR jeopardy | 2006-05-26 17:00 | No | 2006-05-25 17:15 | Not Recorded | 2006-05-26 12:36 | 2006-05-26 | 2006-05-26 18:03 | 2006-05-30 | 4 | CO | N55328894 | 5/25 17:18 K18 jeop was sent. K17 also sent at 18:01. 5/26 FOC sent at 12:36 pm with DD 5/26/06. 5/25 19:12 called CLEC left voice mail was ready to test (day before the DD) 5/26 16:47 no CLEC callback jeop C01; 5/30 supp to chg DD to 6/2; 5/20 refd to CLEC & CLEC accepted | NO | YES
CO702280T1FAC | 17929677 | Releasing FOC not sent the day prior to DD Qwest applied an invalid CNR jeopardy | 2006-06-22 17:00 | No | 2006-06-20 | Not Recorded | 2006-06-22 13:13 | 2006-06-22 | 2006-06-26 13:43 | 2006-06-28 | 6 | CO | N57492344 | 6/20 at 15:48 K17 jeop issued. 6/22 13:00 send FOC with DD 6/22/06. 6/22 K43 discovered and missed due to Qwest reasons; 6/23 13:04 called Jeff at Eschelon, talked to Jeff advised ready to test and accept. 6/26 9:17 no response from CLEC. 6/26 9:20 pending acceptance Pete. 6/27 supp to chg DD to 6/29; 6/28 CLEC accepted | NO | YES
AZ716331T1FAC | 18253036 | Releasing FOC not sent the day prior to DD Qwest applied an invalid CNR jeopardy | 2006-07-27 17:00 | No | 2006-07-24 11:13 | Not Recorded | 2006-07-27 13:06 | 2006-07-27 | 2006-07-28 18:02 | 2006-08-02 | 6 | AZ | N59678376 | Sent K17 jeop 7/24. FOC 7/27 13:00 for a DD of 7/27/06. 7/27 V25 jeop sent. Missed the due to Qwest reasons on 7/27 and coded original due date miss to Qwest. No FOC. 7/28 12:44 refd to Lex but no CLEC callback and a subsequent C01 jeop posted on 7/28. 7/31 supp to cng DD to 8/3; 8/2 refd to CLEC & CLEC accepted | NO | NO Qwest Error
AZ719081T1FAC | 18386264 | Releasing FOC for K 1 jep never sent. Qwest applied invalid CNR jeopardy | 2006-08-09 17:00 | No | 2006-08-04 12:26 | Not Recorded | 2006-08-11 09:52 | 2006-08-10 | 2006-08-09 18:26 | 2006-08-10 | 1 | AZ | N61499633 | 8/4 11:26 K17 jeop issued. 8/8 18:04 K17 jeop issued. 8/9 11:36 K17 jeop issued. 8/9 two more jeopardies issued. DD 8/9/06. jeopardy issue resolved on the due date. 8/9 tried to call CLEC 17:22. C01 jeopardy posted in error. | YES | NO Possible Qwest Error