## Plant Additions
PacifiCorp
Washington Expedited Rate Filing - June 2015
Major Plant Additions
Project Description | In-Service Date | Plant Additions | PIS as of 12/31/2015 | Removal as of 12/3/2015 | Total as of 12/31/2015 | Variance | Explanation
Jim Bridger Unit 3 Overhaul
Replace Cooling Tower | 2015-11-05 | [5 empty] | Costs for fire system and cold water basin refurbishment were less than estimated. Performance testing is yet to be completed.
APH Baskets/Reinforcement | 2015-11-30 | [5 empty] | Cash flow timing on project completion costs
Replace Finishing Superheater | 2015-11-30 | [5 empty] | Reduced costs for under run in structural reinforcement and reduction in post-construction testing.
Burners - Major | 2015-11-30
SCR System - Pollution Control | 2015-11-05 | [5 empty] | Reduced costs for: flue gas system, boiler and air preheater reinforcing; economizer replacement installation; capitalized spare parts; company labor; hazardous materials handling and disposal; and contingency.
Jim Bridger Unit 3 Overhaul Project Total |  | 127544646 | 117233290.19 | 1992383.09 | 119225673.28 | -8318972.72
PacifiCorp
Washington Expedited Rate Filing - June 2015
Major Plant Additions
Project Description | In-Service Date | Total Company 2016 Additions | CWIP at 12/31/2015 | Forecast 2016 | Total Forecast | Variance | Explanation
Jim Bridger U4 Overhaul Project
Jim Bridger U4 Replace Finishing Superheater 16 | 2016-11-30
Jim Bridger U4 Replace Hot Reheat Pipe 16 | 2016-11-30
Jim Bridger U4 Burners - Major 16 | 2016-11-30
Jim Bridger U4 Steam-Cooled Floor Replacement 16 | 2016-11-30
Jim Bridger U4 Absorber Reline 16 | 2016-11-30
Jim Bridger U4 SCR System | 2016-11-30 | [5 empty] | Reduced cost for contingency.
Jim Bridger U4 Overhaul Project Total |  | 143656688.11 | 82194333.03 | 60633361.53 | 142827694.56 | -828993.55