Exhibit No. ___CT (JMW-1CT)

Docket UE-130043

Witness:  Juliana Williams

Redacted Version

BEFORE THE WASHINGTON

UTILITIES AND TRANSPORTATION COMMISSION

| WASHINGTON UTILITIES AND TRANSPORTATION COMMISSION, Complainant, v. PACIFIC POWER & LIGHT COMPANY, Respondent. | DOCKET UE-130043 |
| --- | --- |

TESTIMONY OF

JULIANA WILLIAMS

STAFF OF

WASHINGTON UTILITIES AND

TRANSPORTATION COMMISSION

Prudence of Major Hydroelectric Plant Additions and Low Income Bill Assistance (LIBA)

June 21, 2013

CONFIDENTIAL PER PROTECTIVE ORDER

Redacted Version

TABLE OF CONTENTS

I.	INTRODUCTION 	1

II.	SCOPE AND SUMMARY OF TESTIMONY 	2

III.	PRUDENCE OF MAJOR HYDROELECTRIC PLANT ADDITIONS	3

III.	PRUDENCE OF MAJOR HYDROELECTRIC PLANT ADDITIONS	3

- Description of the Hydroelectric Plant Additions 	3

- Used and Useful for Service 	6

- Prudence of PacifiCorp’s Acquisition of Swift Fish Collector, Soda Springs Fish Passage and Prospect In-Stream Flow and Automation projects 		7

1.	Prudence Standard 	7

2.	Application of the Prudence Standard – Swift Fish Collector 	9

- The Need for the Resource; Evaluation of Alternatives;

Cost 	9

b.	Participation of the Company’s Board of Directors 	12

- Documentation of the Company’s Decision-Making

Process 	13

- Conclusion on Swift Fish Collector Acquisition

Prudence 	13

- Application of the Prudence Standard – Soda Springs Fish

Passage 	14

- The Need for the Resource; Evaluation of Alternatives;

Cost 	14

b.	Participation of the Company’s Board of Directors 	16

- Documentation of the Company’s Decision-Making

Process 	17

d.	Conclusion on Soda Springs Fish Passage Acquisition Prudence	17

- Application of the Prudence Standard – Prospect In-Stream Flow/Automation project 	18

- The Need for the Resource; Evaluation of Alternatives;

Cost 	18

b.	Participation of the Company’s Board of Directors 	20

- Documentation of the Company’s Decision-Making

Process 	20

- Conclusion on Prospect In-Stream Flow and Automation Acquisition Prudence 	21

IV. LOW INCOME BILL ASSISTANCE (LIBA) 	21

I.	INTRODUCTION

Q.	Please state your name and business address.

A.	My name is Juliana M. Williams.  My business address is The Richard Hemstad Building, 1300 S. Evergreen Park Drive S.W., Olympia, Washington 98504.

Q.	By whom are you employed and in what capacity?

A.	I am employed by the Washington Utilities and Transportation Commission (“Commission”) as a Regulatory Analyst in the Conservation and Energy Planning Section of the Regulatory Services Division.

Q.	How long have you been employed by the Commission?

A.	I have been employed by the Commission since May 2012.

Q.	Would you please state your educational and professional background?

A.	I graduated from Whitman College in 2007 with a Bachelor of Arts degree in Geology.  I graduated from the University of Maryland in 2011 with a Master of Public Policy degree, with a concentration in Energy Policy.

Prior to my employment with the Commission, I held various policy research and analysis positions with a clean energy developer, multiple think tanks and environmental non-profit organizations.  In 2012, I attended the New Mexico State University’s “The Basics – Practical Regulatory Training,” as well as other sector specific trainings.

Q.	What are your responsibilities at the Commission?

A.	My responsibilities at the Commission include the review and analysis of resource acquisition prudence, electric utility compliance filings regarding integrated resource planning and the energy conservation and renewable portfolio standards of the Energy Independence Act, energy conservation program implementation and evaluation, and low-income and reliability issues.

Q.	Have you previously testified before the Commission?

A.	No.  However, I have presented Staff recommendations to the Commission at open public meetings.  I have also participated in Commission rulemakings and supported Staff testimony in other cases before the Commission.

II.	SCOPE AND SUMMARY OF TESTIMONY

Q.	Please explain the purpose of your testimony.

A.	My testimony addresses the prudence of significant capital improvements to various hydroelectric projects owned by PacifiCorp d/b/a Pacific Power & Light (“PacifiCorp” or “Company”).  These major plant additions to rate base are the Swift Fish Collector, Soda Springs Fish Passage, Prospect In-Stream Flow and Automation, and Merwin Fish Collector projects.  The relevant Company witnesses on this subject matter are Mark R. Tallman and Steven R. McDougal.

I also respond to PacifiCorp witness Joelle R. Steward regarding proposed changes to the Low Income Bill Assistance (“LIBA”) Program and the impact of these changes on the Company’s five-year plan for the LIBA Program.

Q.	Please summarize your conclusions on the issues addressed in your testimony.

A.	I conclude that the Company’s acquisitions of the Swift Fish Collector, Soda Springs Fish Passage, and Prospect In-Stream Flow and Automation projects are prudent under Commission-established standards.  Staff witness Christopher R. McGuire presents the specific ratemaking treatment recommended for these projects.  Based on Mr. McGuire’s recommendation, I do not address the prudence of the Merwin Fish Collector project at this time.

I also conclude that the Company’s proposed changes to the LIBA program are reasonable in principle, and that the percentage increase in LIBA participant benefits should remain twice the final percentage increase in residential general rates that result from this case, in accordance with Commission Order 07 in Docket UE-111190.

III.	PRUDENCE OF MAJOR HYDRO ELECTRIC PLANT ADDITIONS

- Description of the Hydroelectric Plant Additions

Q.	Please briefly describe the Swift Fish Collector.

A.	The Swift Fish Collector is a facility designed to collect, sort and provide downstream transportation to juvenile and adult fish at the Swift Hydroelectric Project No. 1 (“Swift No. 1”) on the Lewis River in Skamania County, Washington.  The Company pursued the addition of this facility to fulfill conditions in the Lewis River Settlement Agreement, as part of the new operating license ordered by the Federal Energy Regulatory Commission (“FERC”).

There are three primary phases of this project.  Phase 1 consists of a trestle to provide access for two-way traffic to the floating barge and collection systems, and was completed in December, 2011.  Phase 2 is a barge moored to the trestle, which was completed in September 2012.  Phase 3 includes the collection, sorting and guidance systems, which were completed in November 2012.  Final project closeout costs were expected to be completed by May 2013.

Q.	Please briefly describe the Soda Springs Fish Passage.

A.	The Soda Springs Fish Passage consists of an upstream fish ladder, spillway improvement, downstream fish screen, and evaluation facility at the Soda Springs dam on the North Umpqua River in Douglas County, Oregon.  The Company pursued the addition of this facility to fulfill the conditions of North Umpqua Settlement, as part of the operating license for the North Umpqua Hydroelectric Project (“North Umpqua”) ordered by FERC.  The facility was placed into service in October 2012, but final closeout costs were expected to be completed in May 2013.

Q.	Please briefly describe the Prospect In-Stream Flow and Automation project.

A.	The Prospect In-Stream Flow and Automation addition consists of water flow measuring devices, flow release structures, and an automation and communication system for the Prospect No. 1, 2, and 4 hydroelectric projects (“Prospect”) on the Rogue River and two tributary streams in Jackson County, Oregon.  Prospect consists of three concrete diversion dams located on the Middle Fork Rogue River (Middle Fork dam), Red Blanket Creek (Red Blanket dam), and the Rogue River (North Fork dam).  The dams divert water through approximately 9.25 miles of water conveyance system to a fore-bay, which supplies water to three powerhouses.

The Company pursued the addition of the Prospect In-Stream Flow and Automation facilities to fulfill conditions of the FERC license issued for Prospect.  These conditions include controlling in-stream flow and meeting ramp rate requirements established by the Oregon Department of Environmental Quality as part of the 401 certification process of the Clean Water Act.  The facilities were placed into service in December 2012.  Final closeout costs are expected to be completed in June 2013.

Q.	Please briefly discuss the Merwin Fish Collector.

A.	The Merwin Fish Collector was not placed into service prior to the filing of this rate case in January 2013, and therefore the expenditures on the project are not known and measurable, as discussed in the testimony of Staff witness McGuire.  Therefore, my testimony does not discuss the prudence of the acquisition of the Merwin Fish Collector because such a determination would be premature and unnecessary at this time.  It should be addressed only once the facility is complete and the final expenditures can be fully assessed.  Staff witness Deborah J. Reynolds presents the concept of an expedited rate filing that will allow timely consideration of the Merwin Fish Collector by the Commission.

Q.	What information did you evaluate in conducting your analyses in this case?

A.	I reviewed the direct testimony and exhibits of PacifiCorp witnesses McDougal and Tallman, and PacifiCorp’s responses to data requests from Staff.  These documents included FERC licenses, applicable settlement agreements and orders, approvals of parties to the settlement agreements, economic analyses, request for proposal criteria and analyses, proof of project in-service dates, and other related documents.

- Used and Useful for Service

Q.	What is the importance of the “used and useful for service” issue?

A.	In order for a capital investment to be included in rate base for ratemaking purposes, the resource must be “used and useful for service” in Washington State.

Q.	Are the Swift Fish Collector, Soda Springs Fish Passage and Prospect In-Stream Flow and Automation projects used and useful for service in Washington?

A.	Yes.  The Swift Fish Collector began operation in December 2012.  The Soda Springs Fish Passage was placed into service in October 2012.  The Prospect In-Stream Flow and Automation project was placed into service in December 2012.  All three capital improvements were required by FERC license.  The underlying generation projects for all three improvements are used to provide electric service to customers in Washington State.

All three projects also indirectly reduce costs to Washington customers by enabling the Company to continue to operate the Swift No. 1, North Umpqua Hydroelectric Project and Prospect facilities, instead of acquiring more costly replacement resources.

- Prudence of PacifiCorp’s Acquisition of Swift Fish Collector, Soda Springs Fish Passage and Prospect In-Stream Flow and Automation projects

1.	Prudence Standard

Q.	What is the relevant standard to assess the Company’s acquisition of the Swift Fish Collector, Soda Springs Fish Passage and Prospect In-Stream Flow and Automation additions?

A.	The Commission applies a “prudence” standard when it determines whether a specific resource acquisition decision by a utility was appropriate, and that ratepayers can be required to support that resource through rates.  Overall, the prudence standard is a reasonableness standard:

The Commission has consistently applied a reasonableness standard when reviewing the prudence of decisions relating to power costs, including those arising from power generation asset acquisitions.  The test the Commission applies to measure prudence is what would a reasonable board of directors and company management have decided given what they knew or reasonably should have known to be true at the time they made a decision.  This test applies both to the question of need and the appropriateness of the expenditures.  The company must establish that it adequately studied the question of whether to purchase these resources and made a reasonable decision, using the data and methods that a reasonable management would have used at the time the decisions were made.

Q.	What factors does the Commission use to evaluate the prudence of a utility’s electric resource acquisition?

A.	There is no single set of factors.   However, the Commission has generally focused on the following four factors:

- The Need for the Resource - The utility must first determine whether new resources are necessary.  Once a need has been identified, the utility must determine how to fill that need in a cost-effective manner.  When a utility is considering the purchase of a resource, it must evaluate that resource against the standards of what other purchases are available, and against the standard of what it would cost to build the resource itself.

- Evaluation of Alternatives - The utility must analyze the resource alternatives using current information that adjusts for such factors as end effects, capital costs, dispatchability, transmission costs, and whatever other factors need specific analysis at the time of a purchase decision.  The acquisition process should be appropriate.

- Communication With and Involvement of the Company’s Board of Directors - The utility should inform its board of directors about the purchase decision and its costs.  The utility should also involve the board in the decision process as appropriate.

- Adequate Documentation - The utility must keep adequate contemporaneous records that will allow the Commission to evaluate the Company’s decision-making process.  The Commission should be able to follow the utility’s decision process; understand the elements that the utility used; and determine the manner in which the utility valued these elements.

Although these factors have been typically applied to the acquisition of new major resources, in my opinion, it is likewise appropriate to consider these factors when evaluating the prudence of major upgrades to existing resources.

2.	Application of the Prudence Standard – Swift Fish Collector

- The Need for the Resource; Evaluation of Alternatives; Cost

Q.	Did the Company adequately support the need for the Swift Fish Collector, and show that it was an appropriate investment to acquire to meet that need?

A.	Yes.  The testimony of Company witnesses McDougal and Tallman supports the need for the Swift Fish Collector, as does Section 4.4.1 of the Lewis River Settlement Agreement, adopted by FERC in the new operating license for Swift No. 1, which states,

By six months after the fourth anniversary of the Issuance of the New License for the Swift No. 1 Project or the Swift No. 2 Project, whichever is later, PacifiCorp shall construct and provide for the operation of a passage facility at the Swift No. 1 Dam, including a modular surface collector, to collect, sort, tag, and transport downstream-migrating Transported Species.

The ongoing need for Swift No. 1 as a generating resource is also recognized by the FERC license and PacifiCorp’s 2007 Integrated Resource Plan, which includes Swift No. 1 as part of the existing resource portfolio.  Thus, the fish collector is required for the Swift No. 1 to continue to generate electricity in compliance with the FERC license.

Q.	How did PacifiCorp evaluate the Swift Fish Collector project?

A.	First, the Company conducted a Relicensing Cost Analysis to compare the economics of relicensing the Lewis River Hydroelectric Projects to decommissioning.  This analysis showed that relicensing was the lower cost option.

Once FERC issued the new license for Swift No. 1, PacifiCorp consulted with parties to the Lewis River Settlement Agreement on the design of all three phases of the Swift Fish Collector, as described below:

The Licensee shall coordinate with and shall provide 30% and 60% completed preliminary designs for review and comment to the Services and WDFW.

The Company considered 22 design alternatives to evaluate configuration options for the facility under a range of reservoir conditions.  These alternatives included options for accessing the collection facility by boat, rail or motor vehicle.  The Company determined that the trestle option, which allows for two-way vehicle

traffic to the collection facility, was the only option that could perform in the full range of operational conditions.

The final design of the Swift Fish Collector was reviewed and approved by the National Oceanic and Atmospheric Administration (“NOAA”) and the U.S. Fish and Wildlife Service (“FWS”).  The Washington State Department of Fish and Wildlife (“WDFW”) provided informal review in support of the project.

PacifiCorp issued a Request for Proposals (“RFP”) for the Swift Fish Collector and invited 29 bidders to submit proposals.  Five proposals were received in June 2010, and two were selected as short-list contractors.  The Company conducted an evaluation of the two proposals that included review of construction plans and schedules, experience constructing similar facilities and documentation of key personnel.  The winning proposal scored the highest on PacifiCorp’s evaluation matrix in addition to providing the lowest cost bid.

Q.	Was the cost of the Swift Fish Collector project reasonable?

A.	Yes.  The cost through December 2012 was $60,608,221.  This excludes final project closeout costs which were incurred after the filing of this case.  The Company initially estimated that all three phases of the project would cost $xxx xxxxxx, including engineering costs and other miscellaneous costs.  This estimate was based on the first stage of design consultation with NOAA, FWS and WDFW, as well as a comparison with the only other project of similar design and scale that was under construction at the time.  The final project came in significantly under budget, due to lower material costs than originally estimated.

Construction of the Swift Fish Collector occurred both during and after the test year for this rate case.  PacifiCorp included in rate base $xxxxxxxx incurred during the test year.  PacifiCorp spent $38,935,266 after the end of the test period and before the rate case was filed.  This after test period amount is included by Staff as a pro forma adjustment to rate base, as discussed by Mr. McGuire.

b.	Participation of the Company’s Board of Directors

Q.	Did PacifiCorp’s Board of Directors make the final decision to build Swift Fish Collector?

A.	No.  However, it may be reasonable for upper management to be the decision-makers for these types of projects, rather than the Board of Directors, as would be required for significant new resource acquisitions.

Here, PacifiCorp’s Board of Directors “delegates operating decisions such as approval of major capital projects to PacifiCorp’s executive management.” Following receipt of detailed analysis of the project proposal, Greg Abel, PacifiCorp Chief Executive Officer, gave final approval of the project.  The Lewis River Settlement Agreement was signed by Judith Johansen, PacifiCorp Chief Executive Officer at the time, on November 30, 2004.  Staff reviewed the Schedule of

Authorities and accepts that the final approval for the Swift Fish Collector was made at the appropriate level for this type of project, pursuant to Company policy.

- Documentation of the Company’s Decision-Making Process

Q.	Did PacifiCorp meet the documentation requirement for the acquisition of the Swift Fish Collector project?

A.	Yes.  PacifiCorp provided adequate contemporaneous records of its decision-making process and supporting analysis in this case, as cited above.

- Conclusion on Swift Fish Collector Acquisition Prudence

Q.	What is your conclusion regarding the prudence of PacifiCorp’s acquisition of the Swift Fish Collector?

A.	Based on the documentation provided by the Company, I conclude that the Swift Fish Collector is “used and useful” and that acquisition of the project by PacifiCorp was prudent.  Staff recommends that the total $60,608,221 of project costs incurred through December 2012 be included in rate base, including $38,935,266 as a pro forma adjustment.  Inclusion of final closeout expenditures in rate base should occur in a later proceeding after the final totals are known and measurable.

- Application of the Prudence Standard – Soda Springs Fish Passage

- The Need for the Resource; Evaluation of Alternatives; Cost

Q.	Did the Company adequately support the need for the Soda Springs Fish Passage, and show that it was an appropriate resource to acquire to meet that need?

A.	Yes.  The testimony of Company witnesses McDougal and Mr. Tallman supports the need for the Soda Springs Fish Passage, as does the North Umpqua Settlement Agreement, adopted by FERC in the new operating license for North Umpqua, which became final October 18, 2005.  The North Umpqua Settlement Agreement states,

PacifiCorp shall provide volitional upstream fish passage at Soda Springs Dam by means of a vertical-slot fish ladder that meets design criteria established by NMFS, USFWS, and ODFW for passage of adult salmonids and lamprey. These fish passage facilities shall be tested and functioning by the seventh anniversary of the New License.

and,

PacifiCorp shall provide downstream fish passage at Soda Springs Dam by the seventh anniversary of the New License.

The ongoing need for generation from the North Umpqua Hydroelectric Project is recognized by the FERC license.  Continued operation is dependent on the construction of the fish passage facilities.

Q.	How did PacifiCorp evaluate the Soda Springs Fish Passage?

A.	As for the Swift Fish Collector project, the Company conducted a Relicensing Cost Analysis to compare the economics of relicensing North Umpqua to decommissioning, and determined that relicensing was the lower cost option.  Once FERC issued the new license for North Umpqua, PacifiCorp consulted with the U.S. Forest Service, National Marine Fisheries Service, the U.S. Fish and Wildlife Service and the Oregon Department of Fish and Wildlife when 30, 60 and 90 percent of the design of the Soda Springs Fish Passage was completed.

The Company considered multiple design alternatives for the fish screens based on survival performance criteria and technical feasibility at the site.  In consultation with agencies party to the North Umpqua Settlement Agreement, the Company determined that the initial design was unfeasible at the site, and that a criteria fish screen constructed on the spillway was the best design option.  The final design was approved by the agencies in March, 2009.

Once the design was complete, PacifiCorp issued an RFP for the Soda Springs Fish Passage and invited 20 bidders to submit proposals.  Five proposals were received for the project.  The Company conducted an evaluation of the proposals that included review of the technical specifications of the project, construction plan and schedules, and experience constructing similar facilities.  The winning proposal was the highest evaluated bidder and provided the lowest cost bid.

Q.	Was the cost of the Soda Springs Fish Passage reasonable?

A.	Yes.  The cost through December 2012 was $73,422,320.  This excludes final project closeout costs which were incurred after the filing of this case.  The Company initially estimated a project cost of $xxxxxxxxx, based on a design utilizing an Eicher screen and comparison with a similarly scaled facility.  However, after preliminary analysis, the Company and consulted agencies concluded that the initial design would not meet the requirements of the project.  The revised design was estimated to cost $xxxxxxxxx, based on similar facilities.  Final project expenditures were, therefore, about $xxxxxxxx or xxx percent above the revised design estimate.  The increased cost of the project was due to a one-year delay for regulatory approval and the associated Allowance of Funds Used During Construction (“AFUDC”).  Staff does not consider the amount over budget to be unreasonable.

b.	Participation of the Company’s Board of Directors

Q.	Did PacifiCorp’s Board of Directors make the final decision to build Soda Springs Fish Passage?

A.	No.  Following receipt of detailed analysis of the project proposal, Greg Abel, PacifiCorp Chief Executive Officer, formally delegated final approval of the project

to Robert Lasich, President of PacifiCorp Energy.  Staff reviewed the Schedule of Authorities and accepts that the final approval for the Soda Springs Fish Passage was made at the appropriate level for this type of project, again, pursuant to Company policy that allows the Board to delegate decisions on major capital projects to executive management.

- Documentation of the Company’s Decision-Making Process

Q.	Did PacifiCorp meet the documentation requirement for the acquisition of the Soda Springs Fish Passage?

A.	Yes.  PacifiCorp provided adequate contemporaneous records of its decision-making process and supporting analysis in this case, as cited above.

- Conclusion on Soda Springs Fish Passage Acquisition Prudence

Q.	What is your conclusion regarding the prudence of PacifiCorp’s acquisition of the Soda Springs Fish Passage?

A.	Based on the documentation provided by the Company, I conclude that Soda Springs Fish Passage is “used and useful” and that the acquisition of the project by PacifiCorp was prudent.  Staff recommends that the $73,422,320 of project costs incurred through December 2012 be placed into rate base as a pro forma adjustment.  Inclusion of final closeout expenditures in rate base should occur in a later proceeding after the final totals are known and measurable.

- Application of the Prudence Standard – Prospect In-Stream Flow/Automation project

- The Need for the Resource; Evaluation of Alternatives; Cost

Q.	Does the Company adequately support the need for the Prospect In-Stream Flow and Automation project, and show that it was an appropriate resource to acquire to meet that need?

A.	Yes.  The testimony of Company witnesses McDougal and Mr. Tallman supports the need for the Prospect In-Stream Flow and Automation project, as does the Section 401 Certification requirements issued by the Oregon Department of Environmental Quality,  and the conditions to the operating license for Prospect Nos. 1, 2 and 4 issued by FERC.  The FERC license requires PacifiCorp to:

[R]elease minimum flows in the project’s bypassed reaches…, install gages with telemetry at the head of the project’s bypassed reaches…, operate the project run-of-river…, [and] maintain specific ramping rates in river reaches affected by the project…

Compliance with these water management requirements necessitates constant monitoring, data storage and reporting.  Manual operation was determined by the Company to be an infeasible long-term solution as it would not allow for real-time compliance measurement and response capabilities.  Therefore, an automated flow management system was deemed necessary.

The ongoing need for generation from the North Umpqua Hydroelectric Project is recognized by the FERC license.  Continued operation is dependent on the construction of the automated flow management system.

Q.	How did PacifiCorp evaluate the Prospect In-Stream Flow and Automation project?

A.	Again, the Company conducted a Relicensing Cost Analysis to compare the economics of relicensing Prospect to decommissioning, and determined that relicensing was the lower cost option.  The FERC License did not require the Company to consult with Settlement parties on the final design of the Prospect In-Stream Flow and Automation project.

On June 1, 2011, PacifiCorp issued an RFP for this project and invited 14 bidders to submit proposals.  Eight bidders attended the pre-bid meeting and two submitted proposals.  The Company’s evaluation of the proposals included review of construction plans and schedules, experience constructing similar facilities and qualifications of key personnel.  The winning proposal scored the highest on PacifiCorp’s evaluation matrix and provided the lowest cost bid.

Q.	Was the cost of the Prospect In-Stream Flow/Automation project reasonable?

A.	Yes.  The cost through December 2012 was $10,090,905.  This excludes final project closeout costs incurred after the filing of this case.  The final cost of the project through June 2013 is projected to be $xxxxxxxx.  The Company initially estimated that the project would cost $xxxxxxxxx, so the final project is expected to come in roughly $xxxxxxxxx, or xxxxxxxxx, above that estimate.

b.	Participation of the Company’s Board of Directors

Q.	Did PacifiCorp’s Board of Directors make the final decision to build the Prospect In-Stream Flow and Automation project?

A.	No.  Following receipt of detailed analysis of the project proposal, Michael Dunn, President of PacifiCorp Energy, gave final approval of the project.  Staff reviewed the Schedule of Authorities and accepts that the final approval for the Prospect In-Stream Flow and Automation project was made at the appropriate level for this type of project, pursuant to Company policy.

- Documentation of the Company’s Decision-Making Process

Q.	Did PacifiCorp meet the documentation requirement for the acquisition of the Prospect In-Stream Flow and Automation project?

A.	Yes.  PacifiCorp provided adequate contemporaneous records of its decision-making process and supporting analysis in this case, as cited above.

- Conclusion on Prospect In-Stream Flow and Automation Acquisition Prudence

Q.	What is your conclusion regarding the prudence of PacifiCorp’s acquisition of the Prospect In-Stream Flow/Automation project?

A.	Based on the documentation provided by the Company, I conclude that the Prospect In-Stream Flow/Automation project is “used and useful” and that the acquisition of the project by PacifiCorp was prudent.  Staff recommends that the $10,090,905 of project costs incurred through December 2012 be placed into rate base as a pro forma adjustment.  Inclusion of final closeout expenditures in rate base should occur in a later proceeding after the final totals are known and measurable.

Q.	Does that complete your testimony regarding the Company’s investment in hydroelectric project improvements?

A.	Yes.

IV. LOW INCOME BILL ASSISTANCE (LIBA)

Q.	What is the current framework for the Company’s LIBA Program?

A.	A five-year plan for LIBA funding for 2012 through 2016 was agreed to by the parties in the Settlement Stipulation that was approved by the Commission in Order 07 in Docket UE-111190.  The key provisions of that plan are described by Company witness Steward, and, for the 2013-2014 program year (the rate year for this case), are summarized as follows:

- Increase the number of program participants to approximately 5,192 customers, through implementation of two-year certification.

- Increase agency funding to $67.50 per certification, with a maximum of 4,720 certifications for the 2013-2014 program year.

- Increase benefits to each program participant by two times the percentage increase of any future residential general rate increase.

- File for an annual increase to the Schedule 91 surcharge, which funds the LIBA program, by May 1, 2013.

Q.	Please explain the changes proposed by PacifiCorp to the LIBA Program.

A.	As instructed by Order 07 in Docket UE-111190, the Company proposes to:

- Increase the number of program participants to approximately 5,192 customers, through two-year certification.

- Increase agency funding to $67.50 per certification, with a maximum of 4,720 certifications, which increases program costs by $11,800.

- Increase benefits per participant by $86.90, or 30 percent, which is twice the percentage increase of the Company’s proposed residential general rate increase.  To provide program benefits to 5,192 participants, this increases program costs by $597,046.

The total impact of these changes increases LIBA funding by 36 percent, from $1.7 million to $2.3 million, for the 2013-2014 program year.

Q.	Are the proposed changes to the Company’s LIBA Program consistent with the five-year plan approved in Docket UE-111190?

A.	Yes.  The proposed changes will allow the number of LIBA participants and Agency funding for certification to increase, as required by Order 07 in Docket UE-111190. The average benefit to LIBA participants will increase by $86.90, or 30 percent, which is two times the Company proposed residential rate increase of 15 percent.  The proposed changes reflect the annual update to funding levels, as well as the increase in benefits to participants in response to the proposed residential rate increases.

The Company filed annual changes to the Schedule 91 surcharge on May 6, 2013 in Docket UE-130694, which includes the annual increase in certification funding and number of participants.  Appropriately, the filing did not include an increase in the benefit per customer due to proposed rate increases in this case.

Q.	Does Staff support the proposed changes to the LIBA Program?

A.	In principle, yes.  The scope of the changes is appropriate and consistent with the provisions of the five-year plan approved in Docket UE-111190.  However, as discussed in the testimony of Staff witness Christopher T. Mickelson, Staff’s proposed increase in residential general rates is 5.54 percent, versus the Company’s 15 percent. Therefore, Staff recommends an increase in LIBA benefits per participant of $32.11, which is an increase of 11.08 percent, or two times Staff’s proposed residential general rate increase.

Although the proposed changes to LIBA will have no impact on the overall revenue requirement requested in this case, the Company will make a separate Schedule 91 filing to reflect the increase in benefits to program participants that results from the final residential general rate increase approved by the Commission in this case.

Q.	Does this conclude your testimony?

A.	Yes.

Tallman, Exhibit No.__ (MRT-1T) at 3:4-12.

FERC Project No. 2111 License, Ordering Paragraphs F and G and Article 401.

Tallman, Exhibit No.__ (MRT-1T) at 7:4-13.

FERC Project No. 1927-008, License Ordering Paragraph 47 and Article 401.

Tallman, Exhibit No.__ (MRT-1T) at 8:8-17.

FERC Project No. 2630, License Ordering Paragraph D, Articles 401 and 403, and Appendix A.

PacifiCorp 2nd Supplemental Response to Staff Data Request 194, Confidential Attachment.

RCW 80.04.250.

PacifiCorp Response to Staff Data Request 251, Confidential Attachment.

WUTC v. Puget Sound Energy, Inc., Docket UE-031725, Order 12 at ¶19 (April 7, 2004) (footnotes and related citations omitted).

WUTC v. Puget Sound Power & Light Co., Docket UE-921262, et al., Nineteenth Supplemental Order at 11 (September 27, 1994).

WUTC v. Puget Sound Energy, Inc., Docket UE-031725, Order 12 at ¶20 (April 7, 2004).

Id.

Id. at ¶20.

Lewis River Settlement Agreement, Section 4.4.1.  See also PacifiCorp Response to Staff Data Request 61.

FERC Project No. 2111 License, paragraphs 137-141; PacifiCorp 2007 Integrate Resource Plan, page 47.

PacifiCorp Response to WUTC Staff Data Request 197, Confidential Attachment.

Lewis River Settlement Agreement, Section 4.1.2.  See also, PacifiCorp Response to Staff Data Request 111, Attachment 111-2.

PacifiCorp Response to Staff Data Request 157, Confidential Attachment.

PacifiCorp Response to Staff Data Request 157, Confidential Attachment.

PacifiCorp Response to Staff Data Request 196.

PacifiCorp Response to Staff Data Request 250, Attachment.

PacifiCorp Response to Staff Data Request 157, Confidential Attachment.

PacifiCorp Response to Staff Data Request 157, Confidential Attachment.

PacifiCorp Response to Staff Data Request 250, Confidential Attachment.

Costs incurred from July 2012 through December 2012.

PacifiCorp Response to Staff Data Request 157.

PacifiCorp Response to Staff Data Request 157, Confidential Attachment.

PacifiCorp Response to Staff Data Request 231.

North Umpqua Settlement Agreement, Section 4.1.1.  See also, PacifiCorp Response to Staff Data Request 61.

North Umpqua Settlement Agreement, Section 4.1.2.  See also, PacifiCorp Response to Staff Data Request 61.

FERC Project No. 1927-008, paragraphs 97-100.

PacifiCorp Response to Staff Data Request 197, Confidential Attachment.

North Umpqua Settlement Agreement, Sections 4.1.1 and 4.1.2.  See also, PacifiCorp Response to Staff Data Request 114.

PacifiCorp Response to Staff Data Request 157 Confidential Attachment.

PacifiCorp Response to Staff Data Request 196.

PacifiCorp Response to Staff Data Request 262.

PacifiCorp Response to Staff Data Request 157, Confidential Attachment.

PacifiCorp Response to Staff Data Request 157, Confidential Attachment.

PacifiCorp 1st Supplemental Response to Staff Data Request 157.

PacifiCorp Response to Staff Data Request 254.

PacifiCorp Response to Staff Data Request 231.

Submitted by the Oregon Department of Environmental Quality (filed by PacifiCorp on April 5, 2007) under Section 401(a)(1) of the Clean Water Act, 33 U.S.C. § 1431(a)(1) (2000).

The Section 401 Certification Requirements were adopted by FERC as a condition in the operating license for Prospect Nos. 1, 2 and 4 (FERC Project No. 2630, issued April 8, 2008).

FERC, Order Issuing New License, Project No. 2630-004, April 8, 2008.

Id., Appendix A – Condition 1(a).

Id., Appendix A – Condition 2(d)(1), and Article 401(b).

Id., Article 403.

Id., Appendix A – Condition 1(b).

FERC Project No. 2630, paragraphs 93-97.

PacifiCorp Response to Staff Data Request 197, Confidential Attachment.

PacifiCorp Response to Staff Data Request 161.

PacifiCorp Response to Staff Data Request 262, Attachment.

PacifiCorp Response to Staff Data Request 194, Second Supplemental Confidential Attachment.

PacifiCorp Response to Staff Data Request 157, Confidential Attachment.

PacifiCorp Response to Staff Data Request 157, Confidential Attachment.

PacifiCorp Response to Staff Data Request 231.

WUTC v. PacifiCorp, Docket UE-111190, Order 07 at ¶¶17-18 and Settlement Stipulation at ¶¶25-26 (March 30, 2012).  Parties to the Settlement Agreement are PacifiCorp, Staff, Public Counsel, the Industrial Customers of Northwest Utilities and The Energy Project.

Steward, Exhibit No.__(JRS-1T) at 8:3-20.

Steward, Exhibit No.__ (JRS-1T) at 9:22 and Exhibit No.__ (JRS-6).

Steward, Exhibit No.__(JRS-1T), at 3.

PacifiCorp Response to WUTC Staff Data Request 59.