## Hydro Summary Update
#1 - Removed Cost Occurring after April 25, 2013
Hydro Projects
Timing & Capital | In Service | Budget
| Date | Closings
Baker
Lower Baker Powerhouse | 7.24.13 | 95194976.9116
Lower Baker FSC | 2013-02-14 | 56867149.2009
Sub-Total |  | 152062126.1125
U4 powerhouse AFUDC Split
| Project Cost at Completion | 86364534.8183
| AFUDC | 8830442.0933
| Total | 95194976.9116
FSC AFUDC Split
| Project Cost at Completion | 53066481.8609
| AFUDC | 3800667.34
| Total | 56867149.2009

## FSC
[81 empty] | Within last 20% of Agreement Value | Exceeds Agreement Value
LB FSC - S.10774.01.01.05.02, S000774.01.01.05.03 | [8 empty] | Agreement # | Target Value | Status | Original Budget | Current Budget | Inception through 2009 | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | 2010 | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | 2011 | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | 2012 | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | 2013 | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | 2014 | 2015 | Cost to Date | Forecast to Completion | Current Forecast at Completion | Current Budget Variance | Previous month forecast | Forecast Variance - Current to previous |  | 5-Year Capital Plan
[14 empty] | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual |  | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual |  | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual |  | Actual | Actual | Actual | Actual | Actual | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast |  | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | [9 empty] | Plan Title | excl AFUDC | 2011 | 2012 | 2013 | 2014 | 2015 | Total
A. | 510 |  |  | ACQUISITIONS / EASEMENTS | [7 empty] | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | LB Dwnstrm Fish Passage Cap | Current forecast | 18975118.31 | 27104924.4159 | 1920333.845 | 0 | 0 | 48000376.5709
| 510.1 |  |  | PURCHASE / LEASE | [7 empty] | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Current plan
|  | 510.11 |  |  | Cal Portland Purchase | [6 empty] | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 510.111 |  |  | Commission | [6 empty] | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
| 510.2 |  |  | CAL-PORTLAND EASEMENT | [7 empty] | 100000 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
| 510.3 |  |  | Demolition | [7 empty] | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
| 510.4 |  |  | LEGAL (Acquisitions) | [7 empty] | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 510.41 |  |  | Contract | [21 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 510.42 |  |  | Negotiations | [6 empty] | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
| 510.5 |  |  | Other | [7 empty] | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
B. | 100 |  |  | PSE INTERNAL | [7 empty] | 3650465.6639 | 3571766 | 468949 | 25344.85 | 26141.25 | 33241.32 | 21549.76 | 27957.75 | 29523.99 | 20140.29 | 30536.5 | 38776.08 | 37983.15 | 55056.57 | 56154.69 | 402406.2 | 45104.18 | 35832 | 45857.62 | 50893.98 | 21369.41 | 41885.28 | 54409.8 | 60261.98 | 41286.99 | 40074.79 | 52451.87 | 52177.97 | 541605.87 | 60006.74 | 63014.41 | 69998.08 | 71421.58 | 53380.33 | 61105.74 | 65741.69 | 47233.43 | 37424.94 | 54295.08 | 85833.44 | 67300.47 | 736755.93 | 109427.9 | 137451.14 | 98962.92 | 61614.2333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 407456.1933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2557173.1933 | 0 | 2557173.1933 | -1014592.8067 | 2632320.04 | -75146.8467
| 101 |  |  | PSE LABOR & MISC EXPENSE & OH | [7 empty] | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 101.01 |  |  | Inception through 12/31/2009 | [6 empty] | 468949 | 468949 | 468949 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 468949 | 0 | 468949 | 0 | 468949 | 0
|  | 101.02 |  |  | 2010 Through Completion 6/1/2013 | [6 empty] | 0 | 0 |  | 25344.85 | 26141.25 | 33241.32 | 21549.76 | 27957.75 | 29523.99 | 20140.29 | 30536.5 | 38776.08 | 37983.15 | 55056.57 | 56154.69 | 402406.2 | 45104.18 | 35832 | 45857.62 | 50893.98 | 21369.41 | 41885.28 | 54409.8 | 60261.98 | 41286.99 | 40074.79 | 52451.87 | 52177.97 | 541605.87 | 60006.74 | 63014.41 | 69998.08 | 71421.58 | 53380.33 | 61105.74 | 65741.69 | 47233.43 | 37424.94 | 54295.08 | 85833.44 | 67300.47 | 736755.93 | 109427.9 | 137451.14 | 98962.92 | 61614.2333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 407456.1933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2088224.1933 | 0 | 2088224.1933 | -386603.8067 | 2163371.04 | -75146.8467
|  |  | 101.021 |  |  | Project Management and Project Engineering | [5 empty] | 1275064.89 | 1453953 |  | 25344.85 | 26141.25 | 33241.32 | 21549.76 | 27957.75 | 29523.99 | 20140.29 | 30536.5 | 38776.08 | 37983.15 | 55056.57 | 56154.69 | 402406.2 | 45104.18 | 35832 | 45857.62 | 50893.98 | 21369.41 | 41885.28 | 54409.8 | 60261.98 | 41286.99 | 40074.79 | 52451.87 | 52177.97 | 541605.87 | 60006.74 | 63014.41 | 69998.08 | 71421.58 | 53380.33 | 61105.74 | 65741.69 | 47233.43 | 37424.94 | 54295.08 | 85833.44 | 67300.47 | 736755.93 | 109427.9 | 137451.14 | 98962.92 | 61614.2333 | [8 empty] | 407456.1933 | [12 empty] | 0 |  | 2088224.1933 | 0 | 2088224.1933 | 634271.1933 | 2163371.04 | -75146.8467
|  |  | 101.022 |  |  | Construction Management | [5 empty] | 300000 | 275000 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | -275000 | 0 | 0
|  |  | 101.023 |  |  | PTS Support - Design | [5 empty] | 350000 | 225000 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | -225000 | 0 | 0
|  |  | 101.024 |  |  | PTS Support - Construction | [5 empty] | 250000 | 225000 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | -225000 | 0 | 0
|  |  | 101.025 |  |  | Plant Support | [5 empty] | 250000 | 250000 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | -250000 | 0 | 0
|  |  | 101.026 |  |  | Permitting Staff | [5 empty] | 20000 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 101.027 |  |  | IT | [5 empty] | 9000 | 21875 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | -21875 | 0 | 0
|  |  | 101.028 |  |  | Corporate Security | [5 empty] | 13500 | 13500 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | -13500 | 0 | 0
|  |  | 101.029 |  |  | Cultural / Archeology | [5 empty] | 10500 | 10500 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | -10500 | 0 | 0
|  |  | 101.03 |  |  | To be awarded | [20 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
| 102 |  |  | TEMP. FACILITIES | [7 empty] | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
| 103 |  |  | ALLOCATIONS | [7 empty] | 703451.7739 | 627989 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | -627989 | 0 | 0
| 104 |  |  | OTHER | [7 empty] | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
C. | 300 |  |  | CONSULTANT SERVICES | [7 empty] | 5765600 | 7385189 | 641916 | 20590.52 | 20147.92 | 38789.26 | 436372.39 | 12582.34 | 481412.15 | 229272.55 | 36056.86 | 70796.74 | 216499.33 | 253243.13 | 795310.06 | 2611073.25 | -208401.5 | 140300.25 | 558056.4 | 51822.26 | 199403.85 | 217462.66 | 507880.5 | -173769.02 | 146474.73 | 89723.09 | 19600.65 | 94236.57 | 1642790.44 | 75778.43 | 140298.05 | 136432.51 | 300731.89 | 100073.59 | 159006.72 | 65048.43 | 59084.25 | 71487.69 | 21797.16 | -12385.09 | 23393.47 | 1140747.1 | 86004.76 | 13609.26 | 140495.84 | 57733.0417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 297842.9017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6334369.6917 | 0 | 6334369.6917 | -1050819.3083 | 6503746.77 | -169377.0783
| 301 |  |  | PRE-DESIGN | [7 empty] | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 |  | 0
|  | 301.01 |  |  | Services Through 2009 | [6 empty] | 641916 | 641916 | 641916 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 641916 | 0 | 641916 | 0 | 641916 | 0
[12 empty] | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
| 302 |  |  | DESIGN PHASE |  |  |  | 01/2010 to 02/2011 |  |  |  | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 302.01 |  |  | Engineering - MWH |  |  |  | 6400002256 | 4250898 | Active | 2075047 | 2307960 |  |  |  |  | 430425.67 |  | 294622.08 | 213509 | -0.47 | 44618.58 | 196389.08 | 236567.89 | 752989.91 | 2169121.74 | -211212 | 130607.94 | 271471.92 | 55042.62 | 68991.78 |  | 257092.26 | [5 empty] | 571994.52 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 2741116.26 | 0 | 2741116.26 | 433156.26 | 2741116.26 | 0 |  | 4250898 | 1509781.74 | 233831
[7 empty] | Accruals | [19 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 302.02 |  |  | Geotechnical - Shannon and Wilson |  |  |  | 6400002823 | 460671 | Active | 198827 | 298827 |  |  |  | 27550.59 |  |  | 142546.4 |  | 17988.35 |  | 10741.97 |  |  | 198827.31 |  |  |  | 17888.01 | 81547.84 |  |  |  |  | 7500 |  |  | 106935.85 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 305763.16 | 0 | 305763.16 | 6936.16 | 305763.16 | 0
|  | 302.03 |  |  | Project Controls |  |  |  | 4600004599 | 2199000 | Blanket agreement | 37813 | 49207 |  | 2654.32 |  | 1165.88 | 3893.88 |  | 7986.81 | 1369.19 |  | 5742.89 | 6731.89 |  | 17383.25 | 46928.11 | -2762.7 | 2510.75 | 2530.77 | [9 empty] | 2278.82 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 49206.93 | 0 | 49206.93 | -0.07 | 49206.93 | 0
|  | 302.04 |  |  | Project Engineering (Wescorp) |  |  |  | 4600003776 | 1370000 | Active | 47089 | 47089 |  | 2881.92 | 2638.72 | 4158.72 |  | 9938.27 | 3712 |  | 12961.28 | 10798 |  |  |  | 47088.91 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 47088.91 | 0 | 47088.91 | -0.09 | 47088.91 | 0
|  | 302.05 |  |  | Structural | [6 empty] | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 302.06 |  |  | Cultural / Archeology (Northwest Archaeological) |  |  |  | 6400001807 | 1000000 | Active | 8392 | 29500 | [11 empty] | 8391.79 | 15751.11 | 24142.9 |  | 5356.75 | [10 empty] | 5356.75 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 29499.65 | 0 | 29499.65 | -0.35 | 29499.65 | 0
|  | 302.07 |  |  | Environmental | [6 empty] | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 302.08 |  |  | Fish and Wildlife (Fisheries Design Review) - Kozmo |  |  |  | 6400001762 | 80000 | Active | 14658 | 14658 |  | 14657.8 | [11 empty] | 14657.8 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 14657.8 | 0 | 14657.8 | -0.2 | 14657.8 | 0
|  | 302.09 |  |  | Permitting Assistance (Geoengineers) |  |  |  | 4600005167 | 11636100 | Blanket agreement | 8673 | 10198 | [6 empty] | 1418.75 | 2028.75 | 1517.75 |  | 1129.25 | 1840.25 | 738 | 8672.75 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 8672.75 | 0 | 8672.75 | -1525.25 | 8672.75 | 0
|  | 302.1 |  |  | Other | [21 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 302.101 |  |  | Cost Estimate | [20 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 302.102 |  |  | Value Engineering | [5 empty] | 35759 | 38000 | [6 empty] | 21623.5 | 11071.48 | 675 | 729 | 498 | 1162 | 2158 | 37916.98 |  | 83 | [10 empty] | 83 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 37999.98 | 0 | 37999.98 | -0.02 | 37999.98 | 0
|  |  | 302.103 |  |  | GC Design Assist | [20 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 302.104 |  |  | Acoustic (195K study completed in pre-design) | [20 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 302.105 |  |  | Drafting Support - Autoscan |  |  | 6400003484 | 20000 | Agreement expired | 5186 | 5186 | [9 empty] | 5186 |  |  |  | 5186 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 5186 | 0 | 5186 | 0 | 5186 | 0
|  |  | 302.106 |  |  | Prelimary Design Scoping and Development - R2 |  |  | 6400001827 | 800000 | Blanket agreement | 22022 | 22022 |  |  | 11548.46 | 4817.64 |  | 2465.8 |  |  | 2666.95 |  |  | 523.33 | 0 | 22022.18 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 22022.18 | 0 | 22022.18 | 0.18 | 22022.18 | 0
|  |  | 302.107 |  |  | Meeting Facilitator - PDSA |  |  | 6400002433 | 210000 | Blanket agreement | 2040 | 2040 |  |  |  |  | 2040 | [8 empty] | 2040 |  |  |  | 1700 | [8 empty] | 1700 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 3740 | 0 | 3740 | 1700 | 3740 | 0
|  |  | 302.108 |  |  | Sogetti |  |  | 4600004941 | 1034770 | Blanket agreement | 7329 | 14839 |  |  | 5294 | 1000 | [6 empty] | 1035 |  | 4980 | 12309 |  | 920 | 1610 | [9 empty] | 2530 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 14839 | 0 | 14839 | 0 | 14839 | 0
|  |  | 302.109 |  |  | Document Control - URS | [5 empty] | 15957 | 19852 | [6 empty] | 9379.1 | 1135.03 |  | 3510.17 |  | 1932.44 |  | 15956.74 | 3895.12 | [11 empty] | 3895.12 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 19851.86 | 0 | 19851.86 | -0.14 | 19851.86 | 0
|  |  | 302.11 |  |  | Volt | [5 empty] | 190 | 190 |  |  |  | 190.12 | [9 empty] | 190.12 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 190.12 | 0 | 190.12 | 0.12 | 190.12 | 0
|  |  | 302.111 |  |  | Aerotek |  |  |  |  | Blanket agreement | 437 | 1010 | [11 empty] | 436.8 | 673.4 | 1110.2 | -72.8 | -27.3 | [10 empty] | -100.1 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 1010.1 | 0 | 1010.1 | 0.1 | 1010.1 | 0
|  |  | 302.112 |  |  | Leonard Boudinot & Skodje Inc | [6 empty] | 176 | [13 empty] | 0 |  | 176.25 | [10 empty] | 176.25 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 176.25 | 0 | 176.25 | 0.25 | 176.25 | 0
|  |  | 302.113 |  |  | Applied Professional Services Inc. | [6 empty] | 325 | [13 empty] | 0 |  |  | 325 | [9 empty] | 325 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 325 | 0 | 325 | 0 | 325 | 0
|  |  | 302.114 |  |  | URS Corporation | [6 empty] | 8953 | [13 empty] | 0 |  |  | 8952.77 | [9 empty] | 8952.77 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 8952.77 | 0 | 8952.77 | -0.23 | 8952.77 | 0
|  |  | 302.115 |  |  | Hill International | [6 empty] | 2680 | [13 empty] | 0 |  |  | 2680 | [9 empty] | 2680 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 2680 | 0 | 2680 | 0 | 2680 | 0
[12 empty] | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
| 303 |  |  | CONSTRUCTION PHASE |  |  |  | 03/2011 to 06/2013 |  |  |  | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 303.01 |  |  | AECOM/ENSR - Screen Balancing (Alden Research Laboratory Inc) |  |  |  | 4600006084 | 225000 | Active | 240000 | 240000 | [13 empty] | 0 | [12 empty] | 0 | [7 empty] | 1380.75 | 945 |  |  |  | 2325.75 | 33023.15 |  | 112900.64 | 42746.2833 | [8 empty] | 188670.0733 | [12 empty] | 0 |  | 190995.8233 | 0 | 190995.8233 | -49004.1767 | 340000.15 | -149004.3267
|  | 303.02 |  |  |  | AECOM/ENSR - Baffle Tests |  |  | 6400000687 | 5067998 | Active | [15 empty] | 0 | [5 empty] | 16170.53 |  | 9184.26 |  |  |  |  | 25354.79 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 25354.79 | 0 | 25354.79 | 25354.79 | 25354.79 | 0
|  | 303.03 |  |  | AECOM - start-up support | [21 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 303.04 |  |  | Aerotek | [21 empty] | 0 |  |  |  |  | 420.9 | -173.85 | -18.3 |  |  | 122 | -97.6 | 12.2 | 265.35 | -6.1 | 2087.76 | 1216.02 | 1550.61 | 1711.05 | -347.7 | 0 | -273.28 | -156.16 |  |  |  | 5782.2 | 0 | [11 empty] | 0 | [12 empty] | 0 |  | 6047.55 | 0 | 6047.55 | 6047.55 | 6047.55 | 0
|  | 303.05 |  |  | Alden Research Laboratory Inc (see 303.010) | [21 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 303.06 |  |  | Applied Professional Services Inc |  |  |  | 4600004978 | 1402484 | Active | [15 empty] | 0 | [12 empty] | 0 |  | 360 | [10 empty] | 360 | [12 empty] | 0 | [12 empty] | 0 |  | 360 | 0 | 360 | 360 | 360 | 0
|  | 303.07 |  |  | Bradson Technology Professionals |  |  |  | 6400004047 | 101400 | Blanket agreement | [15 empty] | 0 |  |  |  |  | 1107.22 | [7 empty] | 1107.22 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 1107.22 | 0 | 1107.22 | 1107.22 | 1107.22 | 0
|  | 303.08 |  |  | Claims Consultant | [6 empty] | 100000 | 100000 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | -100000 | 0 | 0
|  | 303.09 |  |  | Construction Administration (Hayre McElroy) |  |  |  | 6400004230 | 452000 | Active | 500000 | 500000 | [13 empty] | 0 | [7 empty] | 19223.5 | 22948.8 | 20979.42 | 19876.92 |  | 83028.64 | 38086.44 | 47877.69 | -748.44 | 19209.75 | 17115 | 21635.25 | 19209.75 | 15571.5 | 16453.5 |  |  |  | 194410.44 | [12 empty] | 0 | [12 empty] | 0 |  | 277439.08 | 0 | 277439.08 | -222560.92 | 277439.08 | 0 | 468000 | 190560.92
[7 empty] | Accruals | [19 empty] | 0 | [6 empty] | 10000 | -10000 | 20000 | 0 | 0 | 22714 | 42714 | -22714 | 0 | 2000 | -2000 | 0 | 0 | 0 | 0 | -20000 |  |  |  | -42714 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 303.1 |  |  | Custom Coatings Consultants |  |  |  | 4600005922 | 25000 | Active | [15 empty] | 0 | [12 empty] | 0 |  |  |  | 9989.2 | 4824.6 | [7 empty] | 14813.8 | [12 empty] | 0 | [12 empty] | 0 |  | 14813.8 | 0 | 14813.8 | 14813.8 | 14813.8 | 0
|  | 303.11 |  |  | Project Controls |  |  |  |  | 225000 |  | 500000 | 479167 | [13 empty] | 0 |  |  |  | 3974.57 | 3803.8 | 5821.81 | 7314.84 |  | 7663.48 |  |  | 7755 | 36333.5 | 20645 | 3602 | 3199.5 | 4715 | 8841 | 3300 | 360.14 | 6050 | 10581.24 | 3850 | 7205 | 9350 | 81698.88 | 6210 | 7645 | 9625 | [9 empty] | 23480 | [12 empty] | 0 |  | 141512.38 | 0 | 141512.38 | -337654.62 | 158887.78 | -17375.4
|  | 303.12 |  |  | Direct Connect Group West |  |  |  | 6400003686 | 1000000 | Blanket agreement | [15 empty] | 0 |  |  |  |  | 139.88 | [7 empty] | 139.88 | [11 empty] | 468.19 | 468.19 | 0 | [11 empty] | 0 | [12 empty] | 0 |  | 608.07 | 0 | 608.07 | 608.07 | 608.07 | 0
|  | 303.13 |  |  | Evans E-Z Dock Inc | [21 empty] | 0 | [12 empty] | 0 |  |  |  | 28374.37 | [5 empty] | 22085.78 |  |  | 50460.15 | [12 empty] | 0 | [12 empty] | 0 |  | 50460.15 | 0 | 50460.15 | 50460.15 | 50460.15 | 0
|  | 303.14 |  |  | Hill International |  |  |  | 6400002843 | 417500 | Blanket agreement | [15 empty] | 0 |  |  |  | 2389.5 | 1500 | [7 empty] | 3889.5 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 3889.5 | 0 | 3889.5 | 3889.5 | 3889.5 | 0
|  | 303.15 |  |  | Historical Research Associates Inc |  |  |  | 6400001837 | 300000 | Active | [15 empty] | 0 | [12 empty] | 0 |  |  |  | 594 | [8 empty] | 594 | [12 empty] | 0 | [12 empty] | 0 |  | 594 | 0 | 594 | 594 | 594 | 0
|  | 303.16 |  |  | Kozmo Ken Bates |  |  |  | 6400001762 | 80000 | Active | [15 empty] | 0 | [12 empty] | 0 |  | 9882.1 | [8 empty] | 7667.5 |  | 17549.6 |  |  |  | 2149.125 | [8 empty] | 2149.125 | [12 empty] | 0 |  | 19698.725 | 0 | 19698.725 | 19698.725 | 20128.55 | -429.825
|  | 303.17 |  |  | MWH (Engineering) |  |  |  | 6400002256 | 4250898 | Active |  | 1620508 | [13 empty] | 0 |  |  |  | 54137.78 | 58389.91 | 0 | 158095.18 | 70481.09 | 84204.9 | 31914.2 | 23860.63 |  | 481083.69 | 87373.43 | 52305.93 | 64376.62 | 115140.41 | 67155.03 | 126825.14 | 34616.33 | 31010.02 |  | 42075.18 | 19056.85 | 7968.72 | 647903.66 | 41731.39 | 1835.77 | 7248.81 | 8718.125 | [8 empty] | 59534.095 | [12 empty] | 0 |  | 1188521.445 | 0 | 1188521.445 | -431986.555 | 1190265.07 | -1743.625 | 1509781.74 | 321260.295
|  | 303.18 |  |  |  |  | Accruals | [19 empty] | 0 |  |  | 270400 | -120400 | -20000 | 183188 | 48812 | -302000 | 0 | -10000 | -25000 | 58491 | 83491 | -58491 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 50000 | -50000 | -50000 |  | -83491 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 303.19 |  |  | NRC Environmental Services |  |  |  | 4600002765 | 2699000 | Active | [15 empty] | 0 | [12 empty] | 0 |  |  |  | 2007.8 | [8 empty] | 2007.8 | [12 empty] | 0 | [12 empty] | 0 |  | 2007.8 | 0 | 2007.8 | 2007.8 | 2007.8 | 0
|  | 303.2 |  |  | North Shore Maintenance |  |  |  | 4600005832 | 20000 | Active | [15 empty] | 0 | [12 empty] | 0 | [6 empty] | 10472.63 | [5 empty] | 10472.63 | [12 empty] | 0 | [12 empty] | 0 |  | 10472.63 | 0 | 10472.63 | 10472.63 | 10472.63 | 0
|  | 303.21 |  |  | North Sky Engineering |  |  |  | 4600005348 | 923286 | Active | [15 empty] | 0 | [7 empty] | 126.12 |  | 126.12 |  |  | 252.24 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 252.24 | 0 | 252.24 | 252.24 | 252.24 | 0
|  | 303.22 |  |  | Northwest Cascade (Honey Buckett) |  |  |  | 4600001697 | 1287500 | Active | [15 empty] | 0 | [12 empty] | 0 |  | 103 | [10 empty] | 103 | [12 empty] | 0 | [12 empty] | 0 |  | 103 | 0 | 103 | 103 | 103 | 0
|  | 303.23 |  |  | NW Utility Services LLC |  |  |  | 4600001697 | 1287500 | Active | [15 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 303.24 |  |  | Open Text Inc |  |  |  | 6400003906 | 385250 | Blanket agreement | [15 empty] | 0 |  |  |  | 5306.69 | 3374.64 | [7 empty] | 8681.33 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 8681.33 | 0 | 8681.33 | 8681.33 | 8681.33 | 0
|  | 303.25 |  |  | Pacific Geomatic Services Inc. |  |  |  | 6400001495 | 70000 | Blanket agreement | [15 empty] | 0 |  |  |  | 3877 | [8 empty] | 3877 |  | 1925.5 | -1925.5 | [9 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 3877 | 0 | 3877 | 3877 | 3877 | 0
|  | 303.26 |  |  | Pacific Rim Environmental Inc |  |  |  | 6400001495 | 70000 | Blanket agreement | [15 empty] | 0 | [12 empty] | 0 |  | 1925.5 | -1925.5 | [9 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 303.27 |  |  | Project Engineering (Wescorp) | [6 empty] | 300000 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 303.28 |  |  | QA/QC Inspection (Mayes Testing) |  |  |  | 6400004278 | 50000 | Active | 1000000 | 925000 | [13 empty] | 0 | [11 empty] | 330 | 330 | 2342 | 310 | [10 empty] | 2652 | [12 empty] | 0 | [12 empty] | 0 |  | 2982 | 0 | 2982 | -922018 | 2982 | 0
|  | 303.29 |  |  | Quanta |  |  |  | 4600002102 | 65000000 | Blanket agreement | [15 empty] | 0 | [7 empty] | 502.87 | 442.52 | 61512.9 |  |  | 62458.29 |  |  | 341.94 | 9600.75 |  |  |  |  | 14587.12 |  |  |  | 24529.81 | [12 empty] | 0 | [12 empty] | 0 |  | 86988.1 | 0 | 86988.1 | 86988.1 | 86988.1 | 0
[7 empty] | Accruals | [19 empty] | 0 | [6 empty] | 22541.89 | 28939.98 | 10518.67 | -61999.94 |  | 2446.72 | 2447.32 | -2.86 | 5204.66 | 2009.48 | -9658.5 |  |  |  | 1335.6 | -1335.6 |  |  |  | -2447.22 | [12 empty] | 0 | [12 empty] | 0 |  | 0.1 | 0 | 0.1 | 0.1 | 0.1 | 0
|  | 303.3 |  |  | Shannon & Wilson ( Pier Construction Observation/Support) |  |  |  | 6400002823 | 460671 | Active | [15 empty] | 0 | [9 empty] | 2550 |  | 842 | 3392 |  | 5957.5 | 42389.39 | 99783.22 | [8 empty] | 148130.11 | [12 empty] | 0 | [12 empty] | 0 |  | 151522.11 | 0 | 151522.11 | 151522.11 | 151522.11 | 0
|  | 303.31 |  |  | Turbo Trucking |  |  |  | LPO403408 | 400 | Complete | [15 empty] | 0 | [12 empty] | 0 |  |  |  | 400 |  | 2400.75 | -1001.11 | [5 empty] | 1799.64 | [12 empty] | 0 | [12 empty] | 0 |  | 1799.64 | 0 | 1799.64 | 1799.64 | 1799.64 | 0
|  | 303.32 |  |  | URS Corporation |  |  |  | 6400002523 | 1450000 | Blanket agreement | [15 empty] | 0 |  |  |  | 27749.88 |  | 6716.39 | 3877.94 | 8009.2 |  |  |  |  | 46353.41 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 46353.41 | 0 | 46353.41 | 46353.41 | 46353.41 | 0
|  | 303.33 |  |  | Van De Vanter Group | [21 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 680 | [11 empty] | 680 | [12 empty] | 0 |  | 680 | 0 | 680 | 680 | 680 | 0
|  | 303.34 |  |  | WQPP - Geoengineers |  |  |  | 4600005167 | 11636100 | Blanket agreement |  | 737 | [13 empty] | 0 | 1866 | 397 |  |  |  | 5932.75 |  | 1753.5 |  | 36939.4 |  | 1391.6 | 48280.25 | 8411.75 | 7614.5 |  | 20166.15 |  | 5163.8 |  | 3359.25 |  | 3496 |  | 1707.45 | 49918.9 | 1828.25 | 2690.25 | 3691.5 | 2200.8333 | [8 empty] | 10410.8333 | [12 empty] | 0 |  | 108609.9833 | 0 | 108609.9833 | 107872.9833 | 109050.15 | -440.1667 | 100000 | -8609.9833
[12 empty] | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
| 304 |  |  | ASSESSMENTS | [7 empty] | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 304.01 |  |  | 69990120 - Transfer - P/P/C | [6 empty] | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 304.02 |  |  | 84200012 - Legal Assessment | [6 empty] | 581 | 633 |  |  | 13.32 |  | 3.89 | 5.15 |  | 32.35 | 8.59 | 41.33 | 48.85 | 427.15 | 13.64 | 594.27 |  | 15.77 | 22.58 | 6.16 |  | -262.58 |  | -27.35 |  |  |  |  | -245.42 | [12 empty] | 0 |  | 1286.08 | 2101.51 | 1495.8583 | [8 empty] | 4883.4483 | [12 empty] | 0 |  | 5232.2983 | 0 | 5232.2983 | 4599.2983 | 5531.47 | -299.1717
|  | 304.03 |  |  | 84200013 - Other Assessment | [6 empty] | 888 | 1224 |  | 2.27 | 0.16 | 4.31 | 0.06 | 176.44 | 123.32 | 126.75 | 239.41 | 170.77 | -74.71 | 118.87 | 156.57 | 1044.22 | -115.75 | 257.72 | 38.08 | 150.05 | 120.09 | 44.63 | 160.49 | 35.78 | 642.22 | 55 | 959.65 | 236.09 | 2584.05 | 133.77 | 1117.14 | 492.26 | 849.93 | 423.77 | 29.48 | 1388.43 | 297.03 | 408.91 | 290.2 | 3683.58 | 3892.24 | 13006.74 | 2531.97 | 150.98 | 4888.06 | 422.8167 | [8 empty] | 7993.8267 | [12 empty] | 0 |  | 24628.8367 | 0 | 24628.8367 | 23404.8367 | 24713.4 | -84.5633
|  | 304.04 |  |  | 84200078 - Field Assessment | [6 empty] | 2796 | 3292 |  | 394.21 | 653.26 | -98 | 8.89 | -3.32 | 0.19 |  |  |  |  | 1842.61 | 466.18 | 3264.02 | 0.63 | 2.37 | 25.28 |  | 7.79 | 24.98 | 4.2 | 2.03 | 54.14 | 23.99 | 1.05 | 17.96 | 164.42 |  | 24.77 | 6.74 | 9.2 | 3.14 |  | 2.26 | 353.38 | 3.68 |  | 1.98 | 6.87 | 412.02 |  | 1.18 | 40.32 | [9 empty] | 41.5 | [12 empty] | 0 |  | 3881.96 | 0 | 3881.96 | 589.96 | 3881.96 | 0
[12 empty] | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
| 370 |  |  | DESIGN CONTINGENCY (10% +/-) (see 1000.100) | [22 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
D. | 400 |  |  | CONSTRUCTION |  |  |  | 04/2011 to 06/2013 |  |  |  | 33155692.58 | 37331238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73612.5 | 12412.5 | 401975.93 | 488000.93 | -2631.01 | 0 | 0 | 876169 | 1720772.91 | 947664.87 | 1530786.9 | 1628565.28 | 1379774.9 | 1811137.95 | 2749345.16 | 3455447.32 | 16097033.28 | 1742149.55 | 4561089.74 | 1720976.962 | 1268609.33 | 1655894.454 | 2706580.48 | 2812004.8519 | 1296941.068 | 2354062.98 | 1943531.75 | 1039334.59 | 1097607.2 | 24198782.9559 | 415096.21 | 5244.1 | 469333.49 | 18659.025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 908332.825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41692149.9909 | 0 | 41692149.9909 | 4360911.9909 | 41986221.7959 | -294071.805
| 401 |  |  | PRE-CONSTRUCTION | [7 empty] | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 401.01 |  |  | Reservoir Logging - Triton |  |  |  | 6400003511 | 510125 | Completed | 531375 | 485370 | [10 empty] | 73612.5 | 12412.5 | 401975.93 | 488000.93 | -2631.01 | [11 empty] | -2631.01 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 485369.92 | 0 | 485369.92 | -0.08 | 485369.92 | 0
[12 empty] | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
| 402 |  |  | MAIN CONSTRUCTION EFFORT (SKANSKA CIVIL NW) |  |  |  |  | 6400003979 | 30300000 | Active | 25953596 | 30300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 874753 | 1637337.5 | 828317.4 | 1442875.9 | 1503635.2 | 1131807.25 | 1810447.95 | 2593353.33 | 3226282.17 | 15048809.7 | 1561798.5 | 4347873.09 | 1454199 | 981280.65 | 1570012 | 2579366.5 | 2357798.95 | 1085752.7 | 2270973.6 | 1572877.76 | 911768.55 | 1004514.75 | 21698216.05 | 378386.85 | -77015.3 | 304097 | 0.30833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 605468.8583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37352494.6083 | 0 | 37352494.6083 | 7052494.6083 | 37352494.67 | -0.061667
|  | 402.01 |  |  | General |  |  |  | 6400003979 | 38705006 | Active | 1937000 | 30300000 | [13 empty] | 0 |  |  |  | 132705 | 783049.5 | 1355353.4 | 816309.9 | 1406366.2 | 2759862.25 | -6899.05 | 1789611.33 | 2508396.17 | 11544754.7 | 1955894.5 | 2104961.09 | 3225341 | 1336389.65 | 1034622 | 975250.5 | 2401371.95 | 2562724 | 1691324.61 | 1919578.45 | 1372285.55 | 702696.75 | 21282440.05 | 84427.85 | 1108194.7 | 304097 | 459765.8083 | [8 empty] | 1956485.3583 | [12 empty] | 0 |  | 34783680.1083 | 0 | 34783680.1083 | 4483680.1083 | 34875633.27 | -91953.1617 | 30300000 | -4483680.1083 | 9983773.71 | [5 empty] | 1412590.7851
[7 empty] | Accruals- work complete | [19 empty] | 0 |  |  |  | 742048 | 854288 | -527036 | 461486 | 97269 | -1628055 | 1817347 | 926969 | -580210 | 2164106 | -759566 | 2085279 | -1771142 | -596809 | 497809 | 1079681 | -136634 | -702287 | 492820.99 | -622380.99 | -693152 | 42813 | -1083568 | -38962 | -1041576 |  | -273180 | [8 empty] | -1353718 | [12 empty] | 0 |  | -273180 | 0 | -273180 | -273180 | -327816 | 54636 | 0 | 273180
[7 empty] | Accruals - retention earned | [19 empty] | 0 | [11 empty] | 1298096 | 1298096 | 337609 | -150430 | 0 | 0 | 35356 | 4653 | 0 | -774684.3 | 0 | 23384.3 | 0 | 0 | -524112 | 49918 | -600000 | 0 | -186585.5 | [8 empty] | -736667.5 | [12 empty] | 0 |  | 37316.5 | 0 | 37316.5 | 37316.5 | -0.6 | 37317.1 | 0 | -37316.5
|  | 402.02 |  |  | Mooring Anchorages | [6 empty] | 1600000 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 402.03 |  |  | Guide Net Systems | [6 empty] | 2180298 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 402.04 |  |  | Net Transition Structure | [6 empty] | 2550000 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 402.05 |  |  | Floating Surface Collector | [6 empty] | 17686298 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 402.06 |  |  | Shore side facilities | [21 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 402.07 |  |  | CO 3 - Escalation on Steel | [21 empty] | 0 | [6 empty] | 165080 | [5 empty] | 165080 |  | -7552 | [10 empty] | -7552 | [12 empty] | 0 | [12 empty] | 0 |  | 157528 | 0 | 157528 | 157528 | 157528 | 0
|  | 402.08 |  |  | CO 5 - Temporary power credit | [21 empty] | 0 | [10 empty] | -123227 |  | -123227 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | -123227 | 0 | -123227 | -123227 | -123227 | 0
|  | 402.09 |  |  | CO 6 - Pier design and construction, misc. items | [21 empty] | 0 | [12 empty] | 0 |  | 56926 |  | 26597 | [8 empty] | 83523 | [12 empty] | 0 | [12 empty] | 0 |  | 83523 | 0 | 83523 | 83523 | 83523 | 0
|  | 402.1 |  |  | CO 7 - Pit Tag Detector Shield, etc | [21 empty] | 0 | [12 empty] | 0 |  | 157434 |  | 29983 | [8 empty] | 187417 | [12 empty] | 0 | [12 empty] | 0 |  | 187417 | 0 | 187417 | 187417 | 187417 | 0
|  | 402.11 |  |  | CO 8 - 16" Bulkhead Knife Gate, etc | [21 empty] | 0 | [12 empty] | 0 | 27861 | 24743 | [10 empty] | 52604 | [12 empty] | 0 | [12 empty] | 0 |  | 52604 | 0 | 52604 | 52604 | 52604 | 0
|  | 402.12 |  |  | CCD 7 - Revised Guide Nets | [21 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 402.13 |  |  | CP 6 - Mooring Line Length Addition | [21 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 402.14 |  |  | CO 9 - Baffle Modifications 8/16 Drawings | [21 empty] | 0 | [12 empty] | 0 |  | 76512 | [10 empty] | 76512 | [12 empty] | 0 | [12 empty] | 0 |  | 76512 | 0 | 76512 | 76512 | 76512 | 0
|  | 402.15 |  |  | CO 10 - T&M for access road bank slope removal, etc | [21 empty] | 0 | [12 empty] | 0 |  |  |  | 185120 | 2225 | 19383 | [6 empty] | 206728 | [12 empty] | 0 | [12 empty] | 0 |  | 206728 | 0 | 206728 | 206728 | 206728 | 0
|  | 402.16 |  |  | CO 11 - DBM Pile splicing and subsurface variations, Blast quantity differences (CP45 - CP49) | [21 empty] | 0 | [12 empty] | 0 | [5 empty] | 188603 | [6 empty] | 188603 | [12 empty] | 0 | [12 empty] | 0 |  | 188603 | 0 | 188603 | 188603 | 188603 | 0
|  | 402.17 |  |  | CO 12 - DBM subsurface variations, DBM higher strength bedrock impact | [21 empty] | 0 | [12 empty] | 0 | [5 empty] | 311796 | [6 empty] | 311796 | [12 empty] | 0 | [12 empty] | 0 |  | 311796 | 0 | 311796 | 311796 | 311796 | 0
|  | 402.18 |  |  | CO 13 - Various changes | [21 empty] | 0 | [12 empty] | 0 | [6 empty] | 93061 | [5 empty] | 93061 | [12 empty] | 0 | [12 empty] | 0 |  | 93061 | 0 | 93061 | 93061 | 93061 | 0
|  | 402.19 |  |  | CO 14 | [21 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 402.2 |  |  | CP 0053 - Adding float switches in pontoons. | [21 empty] | 0 | [12 empty] | 0 | [8 empty] | 17906 |  |  |  | 17906 | [12 empty] | 0 | [12 empty] | 0 |  | 17906 | 0 | 17906 | 17906 | 17906 | 0
|  | 402.21 |  |  | CP 0057 - Pier Security | [21 empty] | 0 | [12 empty] | 0 | [8 empty] | 68922 | 17230 |  |  | 86152 | [12 empty] | 0 | [12 empty] | 0 |  | 86152 | 0 | 86152 | 86152 | 86152 | 0
|  | 402.22 |  |  | CP 0067 - Design-Build CMU building | [21 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 |  | 0
|  | 402.23 |  |  | CO 15 - Monorail hoist support structure changes (CP-0063) | [21 empty] | 0 | [12 empty] | 0 | [9 empty] | 120064 |  |  | 120064 | [12 empty] | 0 | [12 empty] | 0 |  | 120064 | 0 | 120064 | 120064 | 120064 | 0
|  | 402.24 |  |  | CP 066 - FSC Security | [21 empty] | 0 | [12 empty] | 0 | [9 empty] | 72047 |  |  | 72047 | [12 empty] | 0 | [12 empty] | 0 |  | 72047 | 0 | 72047 | 72047 | 72047 | 0
|  | 402.25 |  |  | CP 0013R3 - Added load cell monitoring line 8 | [21 empty] | 0 | [12 empty] | 0 | [9 empty] | 2919 |  |  | 2919 | [12 empty] | 0 | [12 empty] | 0 |  | 2919 | 0 | 2919 | 2919 | 2919 | 0
|  | 402.26 |  |  | CP 0068 - Jib crane manufacturer & model changes | [21 empty] | 0 | [12 empty] | 0 | [10 empty] | 34605 |  | 34605 | [12 empty] | 0 | [12 empty] | 0 |  | 34605 | 0 | 34605 | 34605 | 34605 | 0
|  | 402.27 |  |  | CP 0069 - PIT Tagg Electrical | [21 empty] | 0 | [12 empty] | 0 | [9 empty] | 12511 |  |  | 12511 | [12 empty] | 0 | [12 empty] | 0 |  | 12511 | 0 | 12511 | 12511 | 12511 | 0
|  | 402.28 |  |  | CP 0065A - Sliding gate operator | [21 empty] | 0 | [12 empty] | 0 | [9 empty] | 18462 |  |  | 18462 | [12 empty] | 0 | [12 empty] | 0 |  | 18462 | 0 | 18462 | 18462 | 18462 | 0
|  | 402.29 |  |  | CP 0070 - Monorail hoist changes | [21 empty] | 0 | [12 empty] | 0 | [9 empty] | 9063 |  |  | 9063 | [12 empty] | 0 | [12 empty] | 0 |  | 9063 | 0 | 9063 | 9063 | 9063 | 0
|  | 402.3 |  |  | CO 16 - Various Changes | [21 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 402.31 |  |  | CP 0079 - Modifications to Operating Deck Railing. | [21 empty] | 0 | [12 empty] | 0 | [10 empty] | 11413 |  | 11413 | [12 empty] | 0 | [12 empty] | 0 |  | 11413 | 0 | 11413 | 11413 | 11413 | 0
|  | 402.32 |  |  | CP 0081 - Pump Base modifications. | [21 empty] | 0 | [12 empty] | 0 | [10 empty] | 15280 |  | 15280 | [12 empty] | 0 | [12 empty] | 0 |  | 15280 | 0 | 15280 | 15280 | 15280 | 0
|  | 402.33 |  |  | CP 0073 - RFI 308 308.1 Holding tank and vertical crowder conflict. | [21 empty] | 0 | [12 empty] | 0 | [10 empty] | 26669 |  | 26669 | [12 empty] | 0 | [12 empty] | 0 |  | 26669 | 0 | 26669 | 26669 | 26669 | 0
|  | 402.34 |  |  | CP 0080 - Semi-circle decking plates added to floating dock | [21 empty] | 0 | [12 empty] | 0 | [10 empty] | 2429 |  | 2429 | [12 empty] | 0 | [12 empty] | 0 |  | 2429 | 0 | 2429 | 2429 | 2429 | 0
|  | 402.35 |  |  | CP 0071 - Haul material from quarry to FSC location and grade | [21 empty] | 0 | [12 empty] | 0 | [10 empty] | 116550 |  | 116550 | [12 empty] | 0 | [12 empty] | 0 |  | 116550 | 0 | 116550 | 116550 | 116550 | 0
|  | 402.36 |  |  | CP 0075 - Added pump room pedestals | [21 empty] | 0 | [12 empty] | 0 | [10 empty] | 8626 |  | 8626 | [12 empty] | 0 | [12 empty] | 0 |  | 8626 | 0 | 8626 | 8626 | 8626 | 0
|  | 402.37 |  |  | CP 0076 - Added holding pond weir gate cover | [21 empty] | 0 | [12 empty] | 0 | [10 empty] | 10408 |  | 10408 | [12 empty] | 0 | [12 empty] | 0 |  | 10408 | 0 | 10408 | 10408 | 10408 | 0
|  | 402.38 |  |  | CP 0078 - RFI-0383 Added 3 lights in evaluation station | [21 empty] | 0 | [12 empty] | 0 | [10 empty] | 6655 |  | 6655 | [12 empty] | 0 | [12 empty] | 0 |  | 6655 | 0 | 6655 | 6655 | 6655 | 0
|  | 402.39 |  |  | Forecast allowance for Skanska changes (tbd) | [21 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 402.4 |  |  | CO 17 - Various Changes | [21 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 402.41 |  |  |  | CP-0090 Operating Deck Hatch Replacement | [20 empty] | 0 | [12 empty] | 0 | [11 empty] | 94315 | 94315 | [12 empty] | 0 | [12 empty] | 0 |  | 94315 | 0 | 94315 | 94315 | 94315 | 0
|  | 402.42 |  |  |  | CP-0072 Revisions from SKA-SUB-0083 | [20 empty] | 0 | [12 empty] | 0 | [11 empty] | 28948 | 28948 | [12 empty] | 0 | [12 empty] | 0 |  | 28948 | 0 | 28948 | 28948 | 28948 | 0
|  | 402.43 |  |  |  | CP-0051 Reduced Quantity Sinker Weights | [20 empty] | 0 | [12 empty] | 0 | [11 empty] | -2088 | -2088 | [12 empty] | 0 | [12 empty] | 0 |  | -2088 | 0 | -2088 | -2088 | -2088 | 0
|  | 402.44 |  |  |  | CP-0092 RFI-266 Fishway Tolerances | [20 empty] | 0 | [12 empty] | 0 | [11 empty] | 10791 | 10791 | [12 empty] | 0 | [12 empty] | 0 |  | 10791 | 0 | 10791 | 10791 | 10791 | 0
|  | 402.45 |  |  |  | CP-0074 Docking Station Bridge Plate Material Change | [20 empty] | 0 | [12 empty] | 0 | [11 empty] | 5485 | 5485 | [12 empty] | 0 | [12 empty] | 0 |  | 5485 | 0 | 5485 | 5485 | 5485 | 0
|  | 402.46 |  |  |  | CP-0087 Added BFV Drain for Holding Pond | [20 empty] | 0 | [12 empty] | 0 | [11 empty] | 14001 | 14001 | [12 empty] | 0 | [12 empty] | 0 |  | 14001 | 0 | 14001 | 14001 | 14001 | 0
|  | 402.47 |  |  |  | CP-0077 Revised Monorail Catwalk Extension | [20 empty] | 0 | [12 empty] | 0 | [11 empty] | 37142 | 37142 | [12 empty] | 0 | [12 empty] | 0 |  | 37142 | 0 | 37142 | 37142 | 37142 | 0
|  | 402.48 |  |  |  | CP-0095 Vent Header Cut-Out on Pre-Engineered Metal Building | [20 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 402.49 |  |  |  | CP-0098 Revised NTS Lighting per NTS-401 | [20 empty] | 0 | [12 empty] | 0 | [11 empty] | 9903 | 9903 | [12 empty] | 0 | [12 empty] | 0 |  | 9903 | 0 | 9903 | 9903 | 9903 | 0
|  | 402.5 |  |  |  | CP-0094 NTS Winches Connection Upgrade | [20 empty] | 0 | [12 empty] | 0 | [11 empty] | 16291 | 16291 | [12 empty] | 0 | [12 empty] | 0 |  | 16291 | 0 | 16291 | 16291 | 16291 | 0
|  | 402.51 |  |  |  | CP-0105 Fish Crowder Conflicts | [20 empty] | 0 | [12 empty] | 0 | [11 empty] | 6089 | 6089 | [12 empty] | 0 | [12 empty] | 0 |  | 6089 | 0 | 6089 | 6089 | 6089 | 0
|  | 402.52 |  |  |  | CP-0082 Added Standpipe for Level Transmitters | [20 empty] | 0 | [12 empty] | 0 | [11 empty] | 8496 | 8496 | [12 empty] | 0 | [12 empty] | 0 |  | 8496 | 0 | 8496 | 8496 | 8496 | 0
|  | 402.53 |  |  |  | CP-0083 RFI-384 Added Power & Controls for NTS Water Separator | [20 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 402.54 |  |  |  | CP-0084 Add Switch and Receptacle for Recirc Pump | [20 empty] | 0 | [12 empty] | 0 | [11 empty] | 1158 | 1158 | [12 empty] | 0 | [12 empty] | 0 |  | 1158 | 0 | 1158 | 1158 | 1158 | 0
|  | 402.55 |  |  |  | CP-0099 Medium Voltage Conduit Revisions | [20 empty] | 0 | [12 empty] | 0 | [11 empty] | 11058 | 11058 | [12 empty] | 0 | [12 empty] | 0 |  | 11058 | 0 | 11058 | 11058 | 11058 | 0
|  | 402.56 |  |  |  | CP-0085 Disconnect at the Monorail Hoist | [20 empty] | 0 | [12 empty] | 0 | [11 empty] | 1766 | 1766 | [12 empty] | 0 | [12 empty] | 0 |  | 1766 | 0 | 1766 | 1766 | 1766 | 0
|  | 402.57 |  |  |  | CP-0101 Secondary and Holding Pond Pump Flap Gates Rework | [20 empty] | 0 | [12 empty] | 0 | [11 empty] | 4958 | 4958 | [12 empty] | 0 | [12 empty] | 0 |  | 4958 | 0 | 4958 | 4958 | 4958 | 0
|  | 402.58 |  |  |  | CP-0102 Relocate Vent 6C due to Conflict with Pump | [20 empty] | 0 | [12 empty] | 0 | [11 empty] | 7736 | 7736 | [12 empty] | 0 | [12 empty] | 0 |  | 7736 | 0 | 7736 | 7736 | 7736 | 0
|  | 402.59 |  |  |  | CP-0100 Revised Drawing M-418-1 Transport Tank | [20 empty] | 0 | [12 empty] | 0 | [11 empty] | 2956 | 2956 | [12 empty] | 0 | [12 empty] | 0 |  | 2956 | 0 | 2956 | 2956 | 2956 | 0
|  | 402.6 |  |  | CO 18 - Various Changes | [21 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 283003 | [11 empty] | 283003 | [12 empty] | 0 |  | 283003 | 0 | 283003 | 283003 | 283003 | 0
|  | 402.61 |  |  | CO 19 - Various Changes | [21 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 456366 | [10 empty] | 456366 | [12 empty] | 0 |  | 456366 | 0 | 456366 | 456366 | 456366 | 0
|  | 402.62 |  |  | Credit - CP 0067 (Design-Build CMU Building). Item charged to order 103005057. | [21 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 |  | 0
[12 empty] | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
| 403 |  |  | MAIN CONSTRUCTION - OTHERS | [7 empty] | 3530000 | 3430000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143450 | 0 | 0 | 223000 | 0 | 0 | 182827.46 | 0 | 0 | 549277.46 | 0 | 0 | 96848.38 | 1301.6333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98150.0133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 647427.4733 | 0 | 647427.4733 | -2782572.5267 | 647687.8 | -260.3267
|  | 403.01 |  |  | Transport Vessels - Kvichak |  |  |  | 6400004490 | 562900 | Active | 230000 | 230000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143450 | 0 | 0 | 223000 | 0 | 0 | 182827.46 | 0 | 0 | 549277.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 549277.46 | 0 | 549277.46 | 319277.46 | 549277.46 | 0
[6 empty] | Development | [20 empty] | 0 | [12 empty] | 0 |  |  |  | 12000 | [8 empty] | 12000 | [12 empty] | 0 | [12 empty] | 0 |  | 12000 | 0 | 12000 | 12000 | 12000 | 0
[6 empty] | Construction | [5 empty] | 230000 | 230000 | [13 empty] | 0 | [12 empty] | 0 |  |  |  | 111500 |  |  | 223000 |  |  | 135499.06 |  |  | 469999.06 |  |  |  | 0 | [8 empty] | 0 | [12 empty] | 0 |  | 469999.06 | 0 | 469999.06 | 239999.06 | 469999.06 | 0
[6 empty] | Option 4 - modifications to beam and overall length | [20 empty] | 0 | [12 empty] | 0 |  |  |  | 19950 | [8 empty] | 19950 | [12 empty] | 0 | [12 empty] | 0 |  | 19950 | 0 | 19950 | 19950 | 19950 | 0
[6 empty] | Change orders 003 - 010 | [20 empty] | 0 | [12 empty] | 0 | [9 empty] | 47328.4 |  |  | 47328.4 | [12 empty] | 0 | [12 empty] | 0 |  | 47328.4 | 0 | 47328.4 | 47328.4 | 47328.4 | 0
|  | 403.02 |  |  | Pier and Docks | [6 empty] | 3200000 | 3200000 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | -3200000 | 0 | 0
|  | 403.03 |  |  | Temporary Boat Launch | [6 empty] | 100000 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 403.04 |  |  | Asplundh Tree Experts | [21 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  |  |  | 1301.6333 | [8 empty] | 1301.6333 | [12 empty] | 0 |  | 1301.6333 | 0 | 1301.6333 | 1301.6333 | 1561.96 | -260.3267
|  | 403.04 |  |  | Jesse Engineering | [21 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  |  | 58465.88 | [9 empty] | 58465.88 | [12 empty] | 0 |  | 58465.88 | 0 | 58465.88 | 58465.88 | 58465.88 | 0
|  | 403.05 |  |  | Mike Hawkins Trucking LLC | [21 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  |  | 382.5 | [9 empty] | 382.5 | [12 empty] | 0 |  | 382.5 | 0 | 382.5 | 382.5 | 382.5 | 0
|  | 403.06 |  |  | Technical Systems Inc | [21 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 403.07 |  |  | Western Refinery Services | [21 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  |  | 38000 | [9 empty] | 38000 | [12 empty] | 0 |  | 38000 | 0 | 38000 | 38000 | 38000 | 0
[12 empty] | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
| 404 |  |  | CONTROL BUILDING | [7 empty] | 141000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 404.01 |  |  | Allowance in MWH 30% Estimate | [6 empty] | 141000 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
| 405 |  |  | COMMUNICATIONS BUILDING | [7 empty] | 0 | 323482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1416 | 0 | 2106 | 0 | 510 | 460 | 690 | 1523.76 | 850.42 | 7556.18 | 0 | 0 | 2300 | 0 | 861 | 2569.31 | 1610 | 1045 | 805 | 0 | 1610 | 17069.59 | 27869.9 | 6946.04 | 5243.84 | 2491.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14681.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50107.67 | 0 | 50107.67 | -273374.33 | 210938.67 | -160831
|  | 405.01 |  |  | Wiring | [6 empty] | 0 | 22883 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | -22883 | 0 | 0
|  | 405.02 |  |  | Network | [6 empty] | 0 | 72874 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | -72874 | 0 | 0
|  | 405.03 |  |  | Voice | [6 empty] | 0 | 14656 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | -14656 | 0 | 0
|  | 405.04 |  |  | Audio Visual | [6 empty] | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 405.05 |  |  | Desktop | [6 empty] | 0 | 6714 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | -6714 | 0 | 0
|  | 405.06 |  |  | TDM Network | [6 empty] | 0 | 96725 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | -96725 | 0 | 0
|  | 405.07 |  |  | Microwave | [6 empty] | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 405.08 |  |  | Power | [6 empty] | 0 | 74825 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | -74825 | 0 | 0
|  | 405.09 |  |  | Fiber | [6 empty] | 0 | 9657 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | -9657 | 0 | 0
|  | 405.1 |  |  | Contingency | [6 empty] | 0 | 25148 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | -25148 | 160831 | -160831
|  | 405.11 |  |  | Aerotek | [21 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 643.84 | -1267.68 | [9 empty] | -623.84 | [12 empty] | 0 |  | -623.84 | 0 | -623.84 | -623.84 | -623.84 | 0
|  | 405.12 |  |  | Dimension Data | [21 empty] | 0 | [12 empty] | 0 | [11 empty] | 10579.59 | 10579.59 | [12 empty] | 0 | [12 empty] | 0 |  | 10579.59 | 0 | 10579.59 | 10579.59 | 10579.59 | 0
|  | 405.13 |  |  | tbd | [21 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 405.14 |  |  | Sogetti |  |  |  | 4600004941 | 1034770 | Blanket agreement | [15 empty] | 0 |  |  |  | 1416 |  | 2106 |  | 510 | 460 | 690 | 1523.76 | 850.42 | 7556.18 |  |  | 2300 |  | 861 | 2569.31 | 1610 | 1045 | 805 |  | 1610 | 6490 | 17290.31 |  | 4600 | 3759.39 | [9 empty] | 8359.39 | [12 empty] | 0 |  | 33205.88 | 0 | 33205.88 | 33205.88 | 33205.88 | 0
|  | 405.15 |  |  | Tessco | [21 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 6946.04 | [11 empty] | 6946.04 | [12 empty] | 0 |  | 6946.04 | 0 | 6946.04 | 6946.04 | 6946.04 | 0
[12 empty] | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 |  | 0
[12 empty] | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
| 406 |  |  | SECURITY | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3485.85 | 0 | 0 | 0 | 0 | 0 | 3485.85 | 0 | 0 | 42176.83 | 17357.0833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59533.9133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63019.7633 | 0 | 63019.7633 | 63019.7633 | 196000.18 | -132980.4167
|  | 406.01 |  |  | As per email 3/13/2012 from Corporate Security | [6 empty] | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 129509 | -129509
|  | 406.02 |  |  | Revised estimate from IT as per Jim Hogan 6/19/2012 | [6 empty] | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 406.03 |  |  |  | Limited Energy Services Inc | [5 empty] | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  |  | 34043.08 | 17357.0833 | [8 empty] | 51400.1633 | [12 empty] | 0 |  | 51400.1633 | 0 | 51400.1633 | 51400.1633 | 54871.58 | -3471.4167
|  | 406.04 |  |  |  | Trinity Gate and Door | [5 empty] | 0 | [14 empty] | 0 | [12 empty] | 0 | [6 empty] | 3485.85 | [5 empty] | 3485.85 |  |  | 8133.75 | [9 empty] | 8133.75 | [12 empty] | 0 |  | 11619.6 | 0 | 11619.6 | 11619.6 | 11619.6 | 0
[12 empty] | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
| 409.01 |  |  | CONTINGENCY (25%) (See 1000.200) | [22 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
| 409.02 |  |  | WSST (8.2%) | [7 empty] | 2999721.58 | 2792386 | [13 empty] | 0 |  |  |  | 0 | 83435.41 | 117241.47 | 87911 | 124420.08 | 247507.65 |  | 154468.07 | 228314.73 | 1043298.41 | 180351.05 | 213216.65 | 264477.962 | 142013.83 | 85021.454 | 124644.67 | 223211.0519 | 210143.368 | 82284.38 | 187826.53 | 125956.04 | 76022.86 | 1915169.8459 | 29763.32 | 77015.56 | 23719.57 |  | 0 | [7 empty] | 130498.45 | [12 empty] | 0 |  | 3088966.7059 | 0 | 3088966.7059 | 296580.7059 | 3088966.7059 | 0 | 3062904.5579 | -26062.148
[5 empty] | WSST Adjustments | [21 empty] | 0 | [12 empty] | 0 |  |  |  | 1864.85 |  |  | 2899 | [5 empty] | 4763.85 | [12 empty] | 0 | [12 empty] | 0 |  | 4763.85 | 0 | 4763.85 | 4763.85 | 4763.85 | 0
| 409.03 |  |  | ESCALATION (See 402.070) | [7 empty] | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
E. | 200 |  |  | PSE PURCHASED EQUIPMENT & MATERIAL | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 201 |  |  | BELLY TANKS / STEEL (contained in const. cost above) | [7 empty] | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
| 202 |  |  | WSST | [7 empty] | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
| 203 |  |  | SPARE PARTS | [7 empty] | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 203.01 |  |  | Primary pump | [6 empty] | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 203.02 |  |  | Transformer | [6 empty] | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 203.03 |  |  | Other | [6 empty] | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
F. | 500 |  |  | OTHER PROJECT COSTS | [7 empty] | 1206161.93 | 992142 | 0 | 3710 | 8148.75 | 18269.85 | 429 | 10712.5 | 1365 | 5952 | 0 | 3244.5 | 7016 | 18314.58 | 32872.99 | 110035.17 | 0 | -19915 | 1194.91 | 5981.83 | 25253.27 | 7166.09 | 3008.36 | 2064.67 | 0 | 3787.92 | 0 | 16562.31 | 45104.36 | 1908.2 | 27406.69 | -21.93 | 38548.07 | 20946.79 | 14606.3 | 0 | 13170.09 | 0 | 3699.76 | 2693.47 | 65648.49 | 188605.93 | 3889.86 | 13944.34 | 3203.73 | 6551.325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27589.255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 371334.715 | 0 | 371334.715 | -620807.285 | 838117.47 | -466782.755
| 501 |  |  | MISC PROJECT COSTS | [7 empty] | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 501.01 |  |  | Permit Fees | [6 empty] | 30000 | 30000 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | -30000 | 0 | 0
|  | 501.02 |  |  | GIS Data and Storage | [6 empty] | 100000 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 501.03 |  |  | Sharepoint - (Building Information Systems LLC) | [6 empty] | 182359 | 37659 |  | 3710 | 7686.75 | 4950 |  | 10712.5 |  |  |  |  | 5300 |  | 5300 | 37659.25 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 37659.25 | 0 | 37659.25 | 0.25 | 37659.25 | 0
|  | 501.04 |  |  | Builders Risk Insurance | [7 empty] | 41827 | [13 empty] | 0 |  |  |  |  | 22476 | [7 empty] | 22476 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 22476 | 0 | 22476 | -19351 | 22476 | 0
[12 empty] | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
| 502 |  |  | LEGAL | [7 empty] | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 502.01 |  |  | Contract Review-Consulting - Riddell Williams | [6 empty] | 67408.35 | 68453 |  |  | 462 | 13319.85 | 429 |  | 1365 | 5952 |  | 3244.5 | 1716 | 920 | 960 | 28368.35 |  | 85 | [10 empty] | 85 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 28453.35 | 0 | 28453.35 | -39999.65 | 28453.35 | 0
|  | 502.02 |  |  | Contract Review - Construction | [6 empty] | 100000 | 100000 | [13 empty] | 0 |  | 0 | [10 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | -100000 | 0 | 0
|  | 502.03 |  |  | Dewey & Leboeuf LLP | [6 empty] | 37394.58 | 24013 | [11 empty] | 17394.58 | 26617.95 | 44012.53 | 0 | -20000 | [10 empty] | -20000 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 24012.53 | 0 | 24012.53 | -0.47 | 24012.53 | 0
|  | 502.04 |  |  | Perkins Coie LLP | [6 empty] | 0 | 1190 | [12 empty] | -4.96 | -4.96 |  |  | 1194.91 | [8 empty] | 6202.28 | 7397.19 | 1908.2 |  | -21.93 | [9 empty] | 1886.27 | [12 empty] | 0 | [12 empty] | 0 |  | 9278.5 | 0 | 9278.5 | 8088.5 | 9278.5 | 0
[12 empty] | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
| 503 |  |  | FISHERIES | [7 empty] | 689000 | 689000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5981.83 | 2777.27 | 7166.09 | 3008.36 | 2064.67 | 0 | 3787.92 | 0 | 10360.03 | 35146.17 | 0 | 27406.69 | 0 | 38548.07 | 20946.79 | 14606.3 | 0 | 13170.09 | 0 | 3699.76 | 2693.47 | 65648.49 | 186719.66 | 3889.86 | 13944.34 | 3203.73 | 6551.325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27589.255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 249455.085 | 0 | 249455.085 | -439544.915 | 716237.84 | -466782.755
|  | 503.01 |  |  | First Year Performance Study | [6 empty] | 430000 | 430000 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | -430000 | 380000 | -380000
|  | 503.02 |  |  | Biomark System Start Up Testing | [6 empty] | 20000 | 20000 | [13 empty] | 0 | [12 empty] | 0 | [11 empty] | 48712.17 | 48712.17 | [12 empty] | 0 | [12 empty] | 0 |  | 48712.17 | 0 | 48712.17 | 28712.17 | 48712.17 | 0
|  | 503.03 |  |  | Onset Weather Station | [6 empty] | 3000 | 3000 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | -3000 | 3000 | -3000
|  | 503.04 |  |  | PIT Tag Equipment (Biomark) | [6 empty] | 24000 | 24000 | [13 empty] | 0 | [12 empty] | 0 |  | 22525.25 | [10 empty] | 22525.25 | [12 empty] | 0 | [12 empty] | 0 |  | 22525.25 | 0 | 22525.25 | -1474.75 | 22525.25 | 0
|  | 503.05 |  |  | Small transport tank for study holding/release (AquaEngineering) | [6 empty] | 8000 | 8000 | [13 empty] | 0 | [12 empty] | 0 |  |  |  |  | 7211.53 | [7 empty] | 7211.53 | [12 empty] | 0 | [12 empty] | 0 |  | 7211.53 | 0 | 7211.53 | -788.47 | 7999.53 | -788
|  | 503.06 |  |  | 5 Net pens | [6 empty] | 20000 | 20000 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | -20000 | 20000 | -20000
|  | 503.07 |  |  | Pen brackets and hardware | [6 empty] | 2000 | 2000 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | -2000 | 2000 | -2000
|  | 503.08 |  |  | Nets for pens | [6 empty] | 12000 | 12000 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | -12000 | 12000 | -12000
|  | 503.09 |  |  | Fish evaluation station setup | [6 empty] | 10000 | 10000 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | -10000 | 10000 | -10000
|  | 503.1 |  |  | Fish office setup | [6 empty] | 10000 | 10000 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | -10000 | 0 | 0
|  | 503.11 |  |  | FERC Plans - R2 |  |  |  | 6400001827 | 800000 | Blanket agreement | 150000 | 150000 | [13 empty] | 0 |  |  |  | 5981.83 | 2777.27 | 7166.09 | 3008.36 | 2064.67 |  | 3787.92 |  | 10360.03 | 35146.17 |  | 4881.44 |  | 38548.07 | 13735.26 | 14606.3 |  | 13170.09 |  | 3699.76 | 2693.47 | 16936.32 | 108270.71 | 3889.86 | 13944.34 | 3203.73 | 6551.325 | [8 empty] | 27589.255 | [12 empty] | 0 |  | 171006.135 | 0 | 171006.135 | 21006.135 | 210000.89 | -38994.755
[12 empty] | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
G. | 900 |  |  | PSE PROJECT COSTS | [7 empty] | 588243.6069 | 637939 | 0 | 19041.74 | 19792.31 | 14923.84 | 16464.51 | 17910.37 | 24983.83 | 17745.36 | 26407.9 | 30690.42 | 38841.65 | 57011.45 | 59911.36 | 343724.74 | 34368.95 | 30180.64 | 43684.29 | 55660.72 | 74088.39 | 47087.36 | 60891.85 | 61205.68 | 50647.69 | 49327.71 | 63244.02 | 78197.06 | 648584.36 | 67662.88 | 95054.38 | 70807.68 | 74588.03 | 65570.15 | 78718.93 | 80641.24 | 55644.32 | 57305.42 | 62580.81 | 69899.4 | 61559.26 | 840032.5 | 85617.76 | 69545.11 | 78289.15 | 45660.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 279112.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2111454.27 | 0 | 2111454.27 | 1473515.27 | 2185636.1896 | -74181.9196
| 901 |  |  | AFUDC - FERC - 8.1% Compounded anually | [22 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
| 902 |  |  | INDIRECTS - OH Construction | [7 empty] | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 902.01 |  |  | Corporate Indirects through 2009 | [6 empty] | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 902.02 |  |  | Corporate Indirects 2010 through completion | [6 empty] | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 902.02 |  |  | Labor overhead | [5 empty] | 261750 | 224050 |  | 14292.11 | 13326.22 | 9309.5 | 8764.37 | 11800.34 | 14855.9 | 11652.49 | 18025.95 | 20486.13 | 21727.21 | 30297.83 | 30625.11 | 205163.16 | 23533.47 | 19071.68 | 24261.07 | 26849.59 | 22136.24 | 22028.73 | 22717.81 | 26181.37 | 21952.6 | 20772.96 | 25890.88 | 26746.95 | 282143.35 | 30413.63 | 29314.77 | 33270.28 | 36618.01 | 29359.21 | 27160.6 | 30441.28 | 25746.66 | 19254.87 | 27915.15 | 38464.35 | 31987.26 | 359946.07 | 54380.73 | 39151.09 | 42092.58 | 31957.5372 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 167581.9372 | [12 empty] | 0 |  | 1014834.5172 | 0 | 1014834.5172 | 790784.5172 | 1063318.1046 | -48483.5874
|  |  | 902.02 |  |  | Construction overhead | [5 empty] | 326493.6069 | 413889 |  | 4749.63 | 6466.09 | 5614.34 | 7700.14 | 6110.03 | 10127.93 | 6092.87 | 8381.95 | 10204.29 | 17114.44 | 26713.62 | 29286.25 | 138561.58 | 10835.48 | 11108.96 | 19423.22 | 28811.13 | 51952.15 | 25058.63 | 38174.04 | 35024.31 | 28695.09 | 28554.75 | 37353.14 | 51450.11 | 366441.01 | 37249.25 | 65739.61 | 37537.4 | 37970.02 | 36210.94 | 51558.33 | 50199.96 | 29897.66 | 38050.55 | 34665.66 | 31435.05 | 29572 | 480086.43 | 31237.03 | 30394.02 | 36196.57 | 13703.1128 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 111530.7328 | [12 empty] | 0 |  | 1096619.7528 | 0 | 1096619.7528 | 682730.7528 | 1122318.085 | -25698.3322
[12 empty] | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
H. | 1000 |  |  | CONTINGENCY (PSE) | [7 empty] | 8677426.909 | 3225317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3225317 | 347548.1 | -347548.1
| 1000.1 |  |  | Design Contingency | [7 empty] | 1456731 | 1250387 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | -1250387 | 0 | 0
| 1000.2 |  |  | Construction Contingency | [7 empty] | 7220695.909 | 1974930 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | -1974930 | 347548.1 | -347548.1
[12 empty] | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [25 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
I. | 530 |  |  | RELATED PROJECTS | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 530.1 | [10 empty] | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
| 530.2 | [10 empty] | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
[27 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [27 empty] | 0 |  | 0 |  | 0 | 0
|  |  |  | TOTAL PROJECT (A-I) excluding AFUDC | [7 empty] | 53143590.6899 | 53143591 | 1110865 | 68687.11 | 74230.23 | 105224.27 | 474815.66 | 69162.96 | 537284.97 | 273110.2 | 93001.26 | 143507.74 | 373952.63 | 396038.23 | 1346225.03 | 3955240.29 | -131559.38 | 186397.89 | 648793.22 | 1040527.79 | 2040887.83 | 1261266.26 | 2156977.41 | 1578328.59 | 1618184.31 | 1994051.46 | 2884641.7 | 3696621.23 | 18975118.31 | 1947505.8 | 4886863.27 | 1998193.302 | 1753898.9 | 1895865.314 | 3020018.17 | 3023436.2119 | 1472073.158 | 2520281.03 | 2085904.56 | 1185375.81 | 1315508.89 | 27104924.4159 | 700036.49 | 239793.95 | 790285.13 | 190218.275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1920333.845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53066481.8609 | 0 | 53066481.8609 | -77109.1391 | 54493590.3655 | -1427108.5046 |  | 55743592.0703 | Total
-2677110.2094
|  |  |  | AFUDC | [7 empty] | 2329692.0361 | 3420757 | 19175 | 6625.92 | 4617.38 | 8225.52 | 10882.62 | 10576.35 | 9961.05 | 16883.37 | 18118.99 | 19637.8 | 16196.82 | 17082.9 | 17188.9 | 155997.62 | 17828.71 | 13839.12 | 18778.69 | 28447.11 | 34921.67 | 43884.32 | 54142.33 | 64939.16 | 79720.56 | 85302.46 | 97440.15 | 117637.03 | 656881.31 | 134976.72 | 146774.32 | 170687.53 | 185302.66 | 197837.45 | 207900.78 | 223680.78 | 242637.09 | 255421.17 | 253582.63 | 248713.98 | 254597.51 | 2522112.62 | 297296.34 | 149404.24 | -199.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 446500.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3800667.34 | 0 | 3800667.34 | 379910.34 | 3800867.34 | 0 |  | 53066481.8609
|  |  |  | AFUDC | [7 empty] | 2329692.0361 | 3420757 | 19175 | 6625.92 | 4617.38 | 8225.52 | 10882.62 | 10576.35 | 9961.05 | 16883.37 | 18118.99 | 19637.8 | 16196.82 | 17082.9 | 17188.9 | 155997.62 | 17828.71 | 13839.12 | 18778.69 | 28447.11 | 34921.67 | 43884.32 | 54142.33 | 64939.16 | 79720.56 | 85302.46 | 97440.15 | 117637.03 | 656881.31 | 134976.72 | 146774.32 | 170687.53 | 185302.66 | 197837.45 | 207900.78 | 223680.78 | 242637.09 | 255421.17 | 253582.63 | 248713.98 | 254597.51 | 2522112.62 | 297296.34 | 149404.24 | -199.79 | [9 empty] | 446500.79 | [12 empty] | 0 |  | 3800667.34 | 0 | 3800667.34 | 379910.34 | 3800667.34 | 0
0
|  |  |  | PROJECT INCLUDING AFUDC | [7 empty] | 55473282.726 | 56564348 | 1130040 | 75313.03 | 78847.61 | 113449.79 | 485698.28 | 79739.31 | 547246.02 | 289993.57 | 111120.25 | 163145.54 | 390149.45 | 413121.13 | 1363413.93 | 4111237.91 | -113730.67 | 200237.01 | 667571.91 | 1068974.9 | 2075809.5 | 1305150.58 | 2211119.74 | 1643267.75 | 1697904.87 | 2079353.92 | 2982081.85 | 3814258.26 | 19631999.62 | 2082482.52 | 5033637.59 | 2168880.832 | 1939201.56 | 2093702.764 | 3227918.95 | 3247116.9919 | 1714710.248 | 2775702.2 | 2339487.19 | 1434089.79 | 1570106.4 | 29627037.0359 | 997332.83 | 389198.19 | 790085.34 | 190218.275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2366834.635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56867149.2009 | 0 | 56867149.2009 | 302801.2009 | 58294457.7055 | -1427108.5046
228261.93
[52 empty] | 2012 Budget | 20419591
[52 empty] | Forecast variance | 6685333.4159
CLX/C.A.R.S. System | [19 empty] | 0.11 | [6 empty] | 0.11 |  | 0.28 |  | 0.59 |  |  |  | 2.47 | 1.86 | 318.03 |  | 2.81 | 326.04 |  |  |  | 40.38 |  |  |  |  | 87.33 | 5.3 |  |  | 133.01 | 26.8
Labor | [14 empty] | 22943.81 | 21225.05 | 14847.42 | 14037.45 | 18800.5 | 26380.32 | 18584.5 | 28827.88 | 34251.35 | 34618.55 | 48476.9 | 50936.5 | 333930.23 | 39992.09 | 32449.54 | 41279.92 | 45970.22 | 38026.35 | 37876.11 | 39090.71 | 45216.56 | 37811.72 | 35526.68 | 44240.51 | 45891.89 | 483372.3 | 46397.05 | 44030.3 | 50621.06 | 57764.07 | 44259.03 | 41719.8 | 46279.46 | 39494.28 | 29259.97 | 42480.68 | 58905.77 | 50644.54 | 551856.01 | 78490.16 | 56974.75 | 64492.36 | 57237.38 | 42575.24
Employee Expense | [14 empty] | 193.66 | 2435.12 | 113.22 | 44.38 | 289.12 | 1530.22 | 220.1 | 91.31 | 624.32 | 659.01 | 1136.68 | 1749.5 | 9086.64 | 1017.19 | 258.85 | 651.63 | 734.8 | 937.47 | 847.6 | 1970.16 | 1354.69 | 728.38 | 1158.16 | 2763.23 | 3207.3 | 15629.46 | 2223.39 | 19220.47 | 2588.93 | 4856.18 | 3178.52 | 3879.57 | 2750.64 | 2904.39 | 3578.28 | 4052.42 | 4239.9 | 3192.91 | 56665.6 | 6019.74 | 3229.3 | 5164.74 | 3348.86 | 2442.01
Material | [14 empty] | 67.29 | 86.96 | 18429.44 | -10.79 | 259.22 | 11.1 | 155.67 | 136.6 | 705.4 | -12.16 | 2161.11 | 72.15 | 22061.99 | 18.81 | 10.96 | 216.57 | 445.14 | 66.66 | 50.57 | 10569.25 | 13174.75 | 691.33 | 380.59 | 106.15 | 1158.89 | 26889.67 | 6551.29 |  | 12277.1 | 2504.84 | 1898.18 | 24781.84 | 10965.11 | 1592.25 | 232.33 | 47.12 | 8984 | 4351.22 | 74185.28 | 15007.95 | 68117.65 | 21732.03 | 9329.39 | 12586.05
Miscellaneous Expense | [14 empty] | 63.77 | 1228.84 | -935.24 | 43.02 | 7517.78 | -7401.58 | 147.07 | 15.6 | 3.44 | 146.84 | 49.74 | 31.5 | 910.78 | 2463.7 | 10.46 | 353.85 | 870.83 | -20224.54 | 427.44 | 6.45 | 116.42 | 24.46 | 42.5 | 83.79 | 65.03 | -15759.61 | 83.52 | 299.84 | 746.77 | -426.46 | 523.78 | 2192.78 | -610.76 | 109.83 | 1863.4 | -1134.53 | 371.62 | 1761.38 | 5781.17 | 50.92 | 1638.45 | 2139.39 | -1394.59 | 140.17
Insurance, Injuries | [26 empty] | 0 |  |  | 22.53 | [8 empty] | 0.31 | 22.84 | [6 empty] | 0.08 | [5 empty] | 0.08 | 1744.67 |  | 15.2
Permit Fees | [26 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
Advertising | [14 empty] | 1 | 65.6 | 3.96 |  | 3.74 |  |  | 29.71 |  |  |  |  | 104.01 | 8.56 | 1.21 | 7.9 | 71.49 | 0.35 | 29.06 | 23.87 | 14.75 | 15.6 | 92.09 |  | 144.69 | 409.57 |  | 79.76 |  |  | 1.52 | 0.24 | 22.97 |  | 35.1 |  |  |  | 139.59 |  |  | 20.48 | 10.63
Membership | [14 empty] | 80 | [11 empty] | 80 | [12 empty] | 0 | [12 empty] | 0
Employee Training | [14 empty] | 20 | 91.4 | 57.43 | 17.67 | 13.45 |  | 10.63 | 62.53 | 69.28 | 35.31 | 38.83 | 381.75 | 798.28 | 39.27 | 308.84 | 145.22 | 863.36 | 431.37 | 17.8 | 330.48 | 77.32 | 183.53 | 82.76 | 11.9 | 107.79 | 2599.64 | 79.79 | 295.56 | 377.9 | 632.7 | 653.05 | 300.52 | 748.15 | 331.54 | 247.77 | 249.52 | 1105.78 | 11.05 | 5033.33 |  | 244.04 | 570.06 | 71.27 | 51.83
Office and Supplies | [14 empty] | 1474.69 | 435.58 | 344.09 | 7180.71 | 600.88 | 8219.6 | 609.24 | 770.42 | 721.06 | 676.88 | 892.73 | 929.64 | 22855.52 | 69.15 | 1488.01 | 443.38 | 596.94 | 316.01 | 131.57 | 119.82 | 497.59 | 247.01 | 751.3 | 560.05 | 252.16 | 5472.99 | 1500.01 | 431.59 | 436.7 | 1266.68 | 525.34 | 465.99 | 586.31 | 402.74 | 322.03 | 1819.82 | 1378.61 | 592.28 | 9728.1 |  | 328.17 | 338.12 | 250.6 | 110.62
Phone Expense | [26 empty] | 0 | 528.3 | 460.6 | 909.35 | 436.22 | 139.16 | 603.83 | 423.76 | 705.86 | 474.85 | 611.19 | 624.2 | 662.4 | 6579.72 | 717.04 | 726.65 | 882.85 | 516.66 | 662.56 | 1173.1 | 433.24 | 475.04 | 534.43 | 515.12 | 800.77 | 526.48 | 7963.94 | 782.23 | 614.15 | 554.02 | 492.62 | 292.2
Regulatory Fees and Permits | [15 empty] | 3.35 | 0.46 | 2.64 | 4.55 | 1.87 | 0.39 | 21.34 | 1.55 | 35.7 | 0.59 | 1.29 | 73.73 | 1 | 7.59 | 2.12 | 0.41 | 680.99 | 5.27 | 1.56 |  | 1.15 | 1.41 | 1487 | 0.16 | 2188.66 | 2.64 | 100 |  | 1169.87 |  |  | 1676 |  |  | 3000.9 |  |  | 5949.41
Software and Hardware | [15 empty] | 53.34 | 32.27 | 3.11 | 55.36 | 18.09 |  | 5.56 | 54.03 | 1366.64 | 85.56 | 52.37 | 1726.33 | 107.05 | 176.53 | 378.3 | 7.43 | 26.76 | 875.32 | 16.4 | 457.11 | 19.58 |  | 1629.18 | 239.35 | 3933.01 | 71.4 | 29.42 | 125.83 |  | 14.28 | 82.01 | 30.68 | 49.26 | 44.87 | 1106.5 | 8108.31 | 2873.74 | 12536.3 | 462.66 | 296.96 | 188.19 | 0.11 | 472.21
Rent/Lease | [14 empty] | 3.07 | 18.26 | 5.27 |  |  | 371.79 |  | 0 | 1984.56 | 21.48 |  |  | 2404.43 | 0.15 |  | 586.19 |  | 5.56 | 22.5 | 27.57 |  | 0.2 | 0.1 |  | 18.2 | 660.47 | 16.25 | 29314.77 |  | 27.95 |  | 3427.77 | 372.85 | 94.35 | 489.62 | 469.11 | 268.11 | 106.4 | 34587.18 |  | 476.24 | 260.71 | 115.22 | 198.92
OH Construction | [14 empty] | 4749.63 | 6466.09 | 5614.34 | 7700.14 | 6110.03 | 10127.93 | 6092.87 | 8381.95 | 10204.29 | 17114.44 | 26713.62 | 29286.25 | 138561.58 | 10835.48 | 11108.96 | 19423.22 | 28811.13 | 51952.15 | 25058.63 | 38174.04 | 35024.31 | 28695.09 | 28554.75 | 37353.14 | 51450.11 | 366441.01 | 37249.25 | 65739.61 | 37537.4 | 37970.02 | 36210.94 | 51558.33 | 50199.96 | 29897.66 | 38050.55 | 34665.66 | 31435.05 | 29572 | 480086.43 | 31237.03 | 30394.02 | 36196.57 | 17286 | 27895.07
OH Labor | [14 empty] | 14292.11 | 13326.22 | 9309.5 | 8764.37 | 11800.34 | 14855.9 | 11652.49 | 18025.95 | 20486.13 | 21727.21 | 30297.83 | 30625.11 | 205163.16 | 23533.47 | 19071.68 | 24261.07 | 26849.59 | 22136.24 | 22028.73 | 22717.81 | 26181.37 | 21952.6 | 20772.96 | 25890.88 | 26746.95 | 282143.35 | 30413.63 |  | 33270.28 | 36618.01 | 29359.21 | 27160.6 | 30441.28 | 25746.66 | 19254.87 | 27915.15 | 38464.35 | 31987.26 | 330631.3 | 54380.73 | 39151.09 | 42092.58 | 38172.67 | 28456.37
OH Material | [16 empty] | 0.02 | 0.01 | 4.47 | 0.1 |  | 0.51 | 0.21 | 0.85 | 2.7 | 0.51 | 9.38 | 3.84 | 0.5 | 0.13 | 46.77 | 0.67 | 0.09 | 946.96 | 1180.44 | 90.35 | 64.74 | 4.89 | 92.05 | 2431.43 | 29.84 | 527.73 | 1.6 | 16.85 |  | 1796.06 | 637.14 | 2.13 | 14.25 | 4.3 | 4.98 | 19.31 | 3054.19 | 638.95 | 284.25 | 25.89 | 30.46 | 4.55
OH Transportation | [14 empty] | 497.56 | 497.75 | 342.98 | 457.09 | 408.68 | 392.37 | 412.62 | 575.03 | 360.88 | 433.81 | 2211.11 | 1999.38 | 8589.26 | 854.02 | 658.63 | 860.53 | 849.29 | 962.46 | 998.12 | 882.81 | 1226.69 | 996.96 | 1042.15 | 940.32 | 1040.82 | 11312.8 | 2334.15 | 1947.08 | 1938.89 | 3051.71 | 1664.07 | 1202.79 | 1849.56 | 1777.62 | 715.02 | 1678.82 | 1665.59 | 3223.62 | 23048.92 | 6206.82 | 5247.17 | 3460.8 | 3607.95 | 2640.76
OH Small Tools | [20 empty] | 0.07 | 0.01 |  | 0.24 | 0.62 | 0.1 | 1.04 | 1.05 |  |  | 0.49 | 0.14 |  |  | 0.02 | 0.01 | 3.09 | 0.65 |  | 5.45 | 0.37 |  | 0.45 | 0.15 |  | 0.4 | 0.26 |  | 0.54 |  |  | 0.54 | 2.71 |  | 0.01 | 0.93 | 0.02
Unassigned Cost Elements | [17 empty] | -225.53 | [8 empty] | -225.53 | [7 empty] | -3762.69 |  |  |  | -705.88 | -4468.57 |  | -4673.99 |  |  |  | -19917.13 | [6 empty] | -24591.12 |  |  |  | 171.27 | -10814.19
TOTAL PSE INTERNAL COSTS | [14 empty] | 44386.59 | 45933.56 | 48165.16 | 38014.27 | 45868.12 | 54507.82 | 37885.65 | 56944.4 | 69466.5 | 76824.8 | 112068.02 | 116066.05 | 746130.94 | 79473.13 | 66012.64 | 89541.91 | 106554.7 | 95457.8 | 88972.64 | 115301.65 | 121467.66 | 91934.68 | 89402.5 | 115695.89 | 130375.03 | 1190190.23 | 127669.62 | 158068.79 | 140805.76 | 146009.61 | 118950.48 | 139824.67 | 146382.93 | 102877.75 | 94730.36 | 116875.89 | 155732.84 | 128862.73 | 1576791.43 | 195048.66 | 206996.25 | 177252.07 | 107274.8833 | 107051.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Employee: | [26 empty] | 0 | [25 empty] | 0
| Employee 1 | [23 empty] | 46.31 | 321.79 | 368.1 | [12 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [14 empty] | 368.1 | 0 | 368.1
| Employee 2 | [23 empty] | 1378.08 | 2339.87 | 3717.95 | 3099.24 | 1740.6 | 436.85 | 89.58 | [5 empty] | 354.6 | 59.1 | 413.7 | 6193.67 |  | 960.38 | 517.13 | 705.64 | 2715.18 | 1779.44 | 383.5 | 245.44 | 2745.86 | 1418.95 | 2555.84 | 2153.4 | 16180.76 | 3273.75 | 1746 | 362.4 | 90.6 | 0 | [7 empty] | 5472.75 | [14 empty] | 31565.13 | 0 | 31565.13
| Employee 3 | [25 empty] | 0 | [12 empty] | 0 |  |  | 69.54 | 168.6 | 32 |  |  |  | 0 | 0 | 0 | 0 | 270.14 | 0 | 0 | 0 | 0 | 59.61 | [7 empty] | 59.61 | [14 empty] | 329.75 | 0 | 329.75
| Employee 4 | [25 empty] | 0 | 1358.3 | 762.08 | 772.16 | 1331.37 | 3155.84 | 5607.01 | 7127.12 | [5 empty] | 20113.88 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3072 | [6 empty] | 3072 | [14 empty] | 20113.88 | 3072 | 23185.88
| Employee 5 | [13 empty] | 6364.8 | 4199 | 2475.2 | [9 empty] | 13039 | [12 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [14 empty] | 13039 | 0 | 13039
| Employee 6 | [23 empty] | 621.2 |  | 621.2 | [12 empty] | 0 | 316.4 |  | 395.5 | 276.85 |  |  |  | 363.96 | 0 | 0 | 0 | 0 | 1352.71 | 814.6 | 0 | 40.74 | 0 | 0 | [7 empty] | 855.34 | [14 empty] | 2829.25 | 0 | 2829.25
| Employee 7 | [6 empty] | IT/Communications | [18 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  |  | 0 | 705.44 | 0 | [7 empty] | 705.44 | [14 empty] | 705.44 | 0 | 705.44
| Employee 8 | [17 empty] | 1033.12 | [7 empty] | 1033.12 | 49 | 142.89 | 144.57 |  |  | 838.19 | 565.46 | [5 empty] | 1740.11 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1568 | [6 empty] | 1568 | [14 empty] | 2773.23 | 1568 | 4341.23
| Employee 9 | [13 empty] | 195.3 | 260.4 |  | 162.75 | 260.4 |  | 130.2 |  |  | 32.55 |  | 32.55 | 1074.15 | 292.95 |  | 67.38 |  |  | 640.11 | 33.69 | 269.52 |  |  |  |  | 1303.65 | 33.69 |  | 439.99 | 520.5 | 277.6 | 277.6 | 277.6 |  | 173.5 | 0 | 69.4 | 138.8 | 2208.68 | 832.8 | 347 | 357.4 | 607.58 | 285.92 | [7 empty] | 2430.7 | [14 empty] | 7017.18 | 0 | 7017.18
| Employee 10 | [6 empty] | IT/Communications | [18 empty] | 0 | [12 empty] | 0 | [11 empty] | 127.02 | 127.02 | 0 | 212.7 | 0 | 0 | 0 | [7 empty] | 212.7 | [14 empty] | 339.72 | 0 | 339.72
| Employee 11 | [6 empty] | IT/Communications | [18 empty] | 0 | [12 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 1017.08 | [7 empty] | 1017.08 | [14 empty] | 1017.08 | 0 | 1017.08
| Employee 12 | [6 empty] | IT/Communications | [7 empty] | 150.48 | 250.8 | 200.64 | 200.64 | 100.32 |  | 100.32 |  | 100.32 |  |  | 1103.52 |  | 100.32 | 200.64 | 211.84 | [8 empty] | 512.8 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 156.18 | 0 | 159.72 | 254 | 558.8 | [7 empty] | 1128.7 | [14 empty] | 2745.02 | 0 | 2745.02
| Employee 13 | [24 empty] | 76.92 | 76.92 | [12 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [14 empty] | 76.92 | 0 | 76.92
| Employee 14 | [16 empty] | 657.44 | 1985.16 | 576.36 | 192.12 |  |  | 774.56 |  |  | 4185.64 | [12 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [14 empty] | 4185.64 | 0 | 4185.64
| Employee 15 | [25 empty] | 0 | 141.85 | 170.22 | [10 empty] | 312.07 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [14 empty] | 312.07 | 0 | 312.07
| Employee 16 | [25 empty] | 0 | [12 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 242.28 | 1453.54 | 3145.64 | 1865.25 | [7 empty] | 6706.71 | [14 empty] | 6706.71 | 0 | 6706.71
| Employee 17 | [13 empty] | 584.35 | 207.35 | [9 empty] | 194.13 | 985.83 | [12 empty] | 0 | 870.1 | 237.33 | 672.35 | 1661.1 | 121.32 |  |  |  | 0 | 0 | 0 | 0 | 3562.2 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [14 empty] | 4548.03 | 0 | 4548.03
| Employee 18 | [23 empty] | 1203.55 |  | 1203.55 | [12 empty] | 0 | 395.5 |  | 791 | 237.3 | 121.32 | 727.92 | 1718.7 | 2749.92 | 0 | 1213.2 | 244.41 | 0 | 8199.27 | 0 | 0 | 0 | 0 | 83.68 | [7 empty] | 83.68 | [14 empty] | 9486.5 | 0 | 9486.5
| Employee 19 | [6 empty] | IT/Communications | [18 empty] | 0 | [12 empty] | 0 |  |  |  |  | 757.44 | 253.98 | 86.02 | 172.04 | 0 | 0 | 343.92 | 730.83 | 2344.23 | 429.9 | 85.98 | 88.18 | 88.18 | 88.18 | [7 empty] | 780.42 | [14 empty] | 3124.65 | 0 | 3124.65
| Employee 20 | [13 empty] | 41.31 | 206.55 | 247.86 |  | 82.62 |  |  | 82.62 | 41.31 |  |  |  | 702.27 | 82.62 | [11 empty] | 82.62 | 87.6 | [7 empty] | 0 | 0 | 0 | 0 | 87.6 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [14 empty] | 872.49 | 0 | 872.49
| Employee 21 | [25 empty] | 0 | [10 empty] | 177.24 | 177.24 | 354.48 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [14 empty] | 354.48 | 0 | 354.48
| Employee 22 | [25 empty] | 0 | [12 empty] | 0 | 287.95 |  | 177.2 | 883.57 | 337.44 | 84.36 |  |  | 0 | 0 | 0 | 0 | 1770.52 | 941.64 | 190.24 | 713.4 | 0 | 0 | [7 empty] | 1845.28 | [14 empty] | 3615.8 | 0 | 3615.8
| Employee 23 | [23 empty] | 1426.83 | 58.23 | 1485.06 | [12 empty] | 0 |  |  |  |  | 80.88 | 323.52 | 202.2 | 80.88 | 0 | 1091.88 | 4704.43 | 5234.06 | 11717.85 | 9449.73 | 9796.17 | 9836.81 | 6074.86 | 3619.1 | [7 empty] | 38776.67 | [14 empty] | 51979.58 | 0 | 51979.58
| Employee 24 | [13 empty] | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | 1296.68 | 2222.98 | 5516.4 | 9036.06 | 459.7 | 1471.04 | [10 empty] | 1930.74 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1472 | [6 empty] | 1472 | [14 empty] | 10966.8 | 1472 | 12438.8
| Employee 25 | [13 empty] | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  |  | 0 | [7 empty] | 7932.8 | 9369.6 | 6154.88 | 7259.52 | 8023.68 | 38740.48 | 7259.52 | 3820.8 | 4584.96 | 6021.2 | 7837.2 | 7677.6 | 7172.88 | 5880 | 1568 | 3185.92 | 2553.2 | 1964 | 59525.28 | 1964 | 1080.2 | 1258.75 | 402.8 | 50.35 | [7 empty] | 4756.1 | [14 empty] | 103021.86 | 0 | 103021.86
| Employee 26 | [13 empty] | 93.16 | [10 empty] | 146.34 | 239.5 | [12 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [14 empty] | 239.5 | 0 | 239.5
| Employee 27 | [13 empty] | 0 | [7 empty] | 48.4 |  |  |  | 48.4 | [12 empty] | 0 | 73.35 |  | 263.88 | 547.89 | 863.84 | 217.8 | 69 |  | 97.12 | 24.28 | 0 | 143.66 | 2300.82 | 679.12 | 757.48 | 313.44 | 977.13 | 1311.73 | [7 empty] | 4038.9 | [14 empty] | 6388.12 | 0 | 6388.12
| Employee 28 | [6 empty] | IT/Communications | [18 empty] | 0 | [12 empty] | 0 |  |  |  | 292.05 |  |  |  |  | 0 | 0 | 0 | 169.36 | 461.41 | 0 | 0 | 0 | 0 | 2834.84 | [7 empty] | 2834.84 | [14 empty] | 3296.25 | 0 | 3296.25
| Employee 29 | [6 empty] | IT/Communications | [18 empty] | 0 | [12 empty] | 0 | [11 empty] | 1455 | 1455 | 1406.5 | 679.56 | 1194.72 | 2364.58 | 2048.77 | [7 empty] | 7694.13 | [14 empty] | 9149.13 | 0 | 9149.13
| Employee 30 | [23 empty] | 65.1 |  | 65.1 | [9 empty] | 33.69 |  |  | 33.69 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71.48 | 0 | 0 | [7 empty] | 71.48 | [14 empty] | 170.27 | 0 | 170.27
| Employee 31 | [25 empty] | 0 | [12 empty] | 0 | [8 empty] | 0 | 76.26 | 101.68 | 25.42 | 203.36 | 0 | 25.42 | 25.42 | 0 | 0 | [7 empty] | 50.84 | [14 empty] | 254.2 | 0 | 254.2
| Employee 32 | [25 empty] | 0 | [12 empty] | 0 | [5 empty] | 226 | 536.75 |  | 0 | 0 | 0 | 0 | 762.75 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [14 empty] | 762.75 | 0 | 762.75
| Employee 33 | [25 empty] | 0 | [12 empty] | 0 | 143.88 | 431.64 | 143.88 |  | 1283.62 | 740.55 | 3011.57 | 2419.13 | 296.22 | 1184.88 | 10318.33 | 4196.45 | 24170.15 | 3752.12 | 2024.17 | 610.68 | 356.23 | 101.78 | [7 empty] | 6844.98 | [14 empty] | 31015.13 | 0 | 31015.13
| Employee 34 | [6 empty] | Security | [18 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  |  | 0 | 35.58 | 0 | [7 empty] | 35.58 | [14 empty] | 35.58 | 0 | 35.58
| Employee 35 | [25 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  |  | 0 | 63.46 | 0 | [7 empty] | 63.46 | [14 empty] | 63.46 | 0 | 63.46
| Employee 36 | [13 empty] | 183.4 | 146.72 | 513.52 | 1173.76 | 623.56 | 330.12 | 440.16 | 330.12 | 476.84 | 513.52 | 1063.72 | 1393.84 | 7189.28 | 843.64 | 623.56 | 794.28 | 765.6 | 1110.12 | 918.72 | 497.64 | 880.44 | 765.6 | 1116.27 | 459.36 | 650.76 | 9425.99 | 153.12 | 229.68 |  |  | 315.76 | 197.35 | 315.76 | 710.46 | 0 | 78.94 | 78.94 | 0 | 2080.01 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [14 empty] | 18695.28 | 0 | 18695.28
| Employee 37 | [13 empty] | 302.78 | [11 empty] | 302.78 | [12 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [14 empty] | 302.78 | 0 | 302.78
| Employee 38 | [25 empty] | 0 | [12 empty] | 0 | [5 empty] | 89.04 | 77.91 | 22.26 | 0 | 0 | 0 | 0 | 189.21 | 0 | 77.91 | 0 | 0 | 0 | [7 empty] | 77.91 | [14 empty] | 267.12 | 0 | 267.12
| Employee 39 | [20 empty] | 289.64 |  |  |  |  | 289.64 | [12 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [14 empty] | 289.64 | 0 | 289.64
| Employee 40 | [22 empty] | 121.85 |  |  | 121.85 | [12 empty] | 0 | [8 empty] | 0 | 0 | 0 | 279.62 | 279.62 | 0 | 88.97 | 0 | 0 | 0 | [7 empty] | 88.97 | [14 empty] | 490.44 | 0 | 490.44
| Employee 41 | [25 empty] | 0 | [10 empty] | 3008.88 | 6017.76 | 9026.64 | 5301.36 | 4680.48 | 3156.08 | 3586.65 | 4338.45 | 3473.2 | 4860.57 | 4900 | 2793 | 6122.94 | 4566.3 | 1178.4 | 48957.43 | 3633.4 | 5008.2 | 3927.3 | 2718.9 | 2366.45 | [7 empty] | 17654.25 | [14 empty] | 75638.32 | 0 | 75638.32
| Employee 42 | [6 empty] | Security | [18 empty] | 0 | [12 empty] | 0 | [6 empty] | 94.9 |  | 0 | 113.88 | 0 | 0 | 208.78 | 0 | 0 | 0 | 0 | 154.96 | [7 empty] | 154.96 | [14 empty] | 363.74 | 0 | 363.74
| Employee 43 | [23 empty] | 670.15 | 163.45 | 833.6 | [12 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [14 empty] | 833.6 | 0 | 833.6
| Employee 44 | [19 empty] | 192.12 | 5120.06 | 6486.94 | 4862.24 | 7105 | 7693 | 31459.36 | 7393.2 | 4953.52 | 9333.12 | 7100.64 | 4142.04 |  |  |  |  | 536.8 | 1289.52 | 1862.64 | 36611.48 | 47.76 | [7 empty] | 0 | 0 | 0 | 0 | 47.76 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [14 empty] | 68118.6 | 0 | 68118.6
| Employee 45 | [19 empty] | 56.95 | [5 empty] | 56.95 | [6 empty] | 117.32 |  |  | 234.64 |  |  | 351.96 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [14 empty] | 408.91 | 0 | 408.91
| Employee 46 | [6 empty] | IT/Communications | [18 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  |  | 0 | 670.84 | 0 | [7 empty] | 670.84 | [14 empty] | 670.84 | 0 | 670.84
| Employee 47 | [14 empty] | 586.88 | 586.88 | 1173.76 |  |  | 403.48 | [5 empty] | 2751 |  |  | 220.08 |  |  |  |  | 306.24 | 76.56 |  | 306.24 | 421.08 | 1330.2 | 1607.76 | 1378.08 | 389.94 |  | 473.64 | 236.82 | 236.82 | 1184.1 | 276.29 | 118.41 | 0 | 118.41 | 6020.27 | 473.64 | 236.82 | 81.42 | 0 | 0 | [7 empty] | 791.88 | [14 empty] | 10893.35 | 0 | 10893.35
| Employee 48 | [6 empty] | IT/Communications | [18 empty] | 0 | [12 empty] | 0 | [11 empty] | 85.98 | 85.98 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [14 empty] | 85.98 | 0 | 85.98
| Employee 49 | [25 empty] | 0 | [7 empty] | 5599.68 | 3904 | 2561.44 | 2817.84 | 955.2 | 15838.16 | 2865.6 | 2483.52 | 2533.8 | 2269.2 | 2379.15 | 1604.46 | 1419.33 | 1591.37 | 860.2 | 946.22 | 688.16 | 687.14 | 20328.15 | 485.04 | 464.83 | 268.71 | 0 | 0 | [7 empty] | 1218.58 | [14 empty] | 37384.89 | 0 | 37384.89
| Employee 50 | [23 empty] | 3327.94 | 1166.94 | 4494.88 | [12 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [14 empty] | 4494.88 | 0 | 4494.88
| Employee 51 | [25 empty] | 0 | [8 empty] | 395 | 632 | 790 | 513.5 | 2330.5 |  | 158 | [6 empty] | 0 | 0 | 0 | 0 | 158 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [14 empty] | 2488.5 | 0 | 2488.5
| Employee 52 | [17 empty] | 3842.4 | 8453.28 | 6147.84 | 8489.76 | 8132.88 | 5445.52 | 7056 | 9016 | 56583.68 | 7393.2 | 5715.6 | 10911.04 | 8284.08 | 8284.08 | 8720.96 | 6379.52 | 9926.4 | 3513.6 | 3472 | 2483.52 | 1910.4 | 76994.4 | 3056.64 | 3438.72 | 3061.12 | 766.4 |  |  |  |  | 0 | 0 | 0 | 0 | 10322.88 | 0 | 0 | 0 | 0 | 0 | 7840 | [6 empty] | 7840 | [14 empty] | 143900.96 | 7840 | 151740.96
| Employee 53 | [25 empty] | 0 | [12 empty] | 0 |  |  | 909.65 | 3045.35 |  |  |  |  | 0 | 0 | 0 | 285.11 | 4240.11 | 0 | 0 | 0 | 208.75 | 0 | [7 empty] | 208.75 | [14 empty] | 4448.86 | 0 | 4448.86
| Employee 54 | [25 empty] | 0 | [12 empty] | 0 | [8 empty] | 0 | 0 | 0 |  | 0 | 373.06 | 0 | 161.52 | 579.46 | 0 | [7 empty] | 1114.04 | [14 empty] | 1114.04 | 0 | 1114.04
| Employee 55 | [25 empty] | 0 | [12 empty] | 0 |  |  |  | 204.12 | 110.72 |  |  |  | 0 | 0 | 0 | 0 | 314.84 | 224.2 | 0 | 0 | 21.28 | 0 | [7 empty] | 245.48 | [14 empty] | 560.32 | 0 | 560.32
| Employee 56 | [25 empty] | 0 | [12 empty] | 0 |  |  | 92.72 | [5 empty] | 0 | 0 | 0 | 0 | 92.72 | 0 | 0 | 0 | 74.48 | 0 | [7 empty] | 74.48 | [14 empty] | 167.2 | 0 | 167.2
| Employee 57 | [20 empty] | 103.76 | 415.04 | 103.76 | 415.04 |  | 1037.6 | 99.12 |  | 49.56 | 103.3 |  | 258.25 | 210.8 | 105.4 |  |  |  |  | 826.43 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [14 empty] | 1864.03 | 0 | 1864.03
| Employee 58 | [25 empty] | 0 | [10 empty] | 310.1 |  | 310.1 | 243.65 |  | 333.55 | 378.76 |  |  | 168.72 | 210.9 | 0 | 0 | 0 | 0 | 1335.58 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [14 empty] | 1645.68 | 0 | 1645.68
| Employee 59 | [6 empty] | IT/Communications | [18 empty] | 0 | [12 empty] | 0 |  |  |  |  | 42.01 |  |  |  | 0 | 0 | 0 | 0 | 42.01 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [14 empty] | 42.01 | 0 | 42.01
| Employee 60 | [25 empty] | 0 | [10 empty] | 291.2 |  | 291.2 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [14 empty] | 291.2 | 0 | 291.2
| Employee 61 | [13 empty] | 192.13 | 186.28 | [9 empty] | 243.9 | 622.31 | [10 empty] | 97.8 |  | 97.8 | 220.05 |  | 278.16 | 1089.56 | 21.33 | 21.78 |  |  | 24.28 | 0 | 50.1 | 0 | 1705.26 | 261.2 | 483.22 | 78.36 | 642.48 | 0 | [7 empty] | 1465.26 | [14 empty] | 3890.63 | 0 | 3890.63
| Employee 62 | [13 empty] | 216.78 | 56.55 | [9 empty] | 737.68 | 1011.01 | [10 empty] | 79.1 |  | 79.1 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 570.22 | 0 | 0 | 0 | [7 empty] | 570.22 | [14 empty] | 1660.33 | 0 | 1660.33
| Employee 63 | [13 empty] | 3143.21 | 3862.74 | 1175.12 | 2247.9 | 2668.92 | 3481.66 | 4820.76 | 5495.76 | 6243.48 | 6310.02 | 5182.71 | 5144.88 | 49777.16 | 5863.65 | 3026.4 | 4597.32 | 2324.01 | 6932.64 | 5173.7 | 7068.25 | 4479.76 | 6658.9 | 5286.94 | 5284.78 | 4410.32 | 61106.67 | 4258.24 | 3193.68 | 7348.64 | 5532.84 | 5101.2 | 4787.28 | 4120.2 | 1648.08 | 6553.08 | 4551.84 | 15570.32 | 2282.56 | 64947.96 | 5543.36 | 1222.8 | 4851.85 | 9155.23 | 2826.73 | 2432 | [6 empty] | 26031.97 | [14 empty] | 199431.76 | 2432 | 201863.76
| Employee 64 | [25 empty] | 0 | [12 empty] | 0 |  |  |  | 254.98 |  |  |  |  | 0 | 0 | 0 | 0 | 254.98 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [14 empty] | 254.98 | 0 | 254.98
| Employee 65 | [25 empty] | 0 | [12 empty] | 0 |  |  | 92.72 | [5 empty] | 0 | 0 | 0 | 0 | 92.72 | 0 | 0 | 59.45 | 21.28 | 0 | [7 empty] | 80.73 | [14 empty] | 173.45 | 0 | 173.45
| Employee 66 | [25 empty] | 0 | [12 empty] | 0 | 237.3 |  |  | 2313.68 |  | 242.64 | 970.56 |  | 0 | 0 | 0 | 0 | 3764.18 | 814.6 | 122.19 | 40.74 | 1002 | 836.8 | [7 empty] | 2816.33 | [14 empty] | 6580.51 | 0 | 6580.51
| Employee 67 | [6 empty] | IT/Communications | [43 empty] | 0 |  |  |  | 189.86 | 779.04 | 1244.3 | [22 empty] | 2213.2 | 0 | 2213.2
| Employee 68 | [25 empty] | 0 | [12 empty] | 0 |  |  |  | 509.98 |  |  |  |  | 0 | 0 | 0 | 0 | 509.98 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [14 empty] | 509.98 | 0 | 509.98
| Employee 69 | [14 empty] | 1672.8 | 557.6 | 280.4 | 420.6 | 1226.75 | 1542.2 | 562.8 | 282 | 703.08 | 558.88 | 628.74 | 8435.85 | 489.02 | 768.46 | 360.7 | 216.42 | 432.84 | 431.4 | 501.62 | 358.3 | 214.98 | 214.98 | 282.08 | 71.1 | 4341.9 | 213.3 | [7 empty] | 0 | 0 | 0 | 0 | 213.3 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [14 empty] | 12991.05 | 0 | 12991.05
| Employee 70 | [13 empty] | 116.45 | [11 empty] | 116.45 | [9 empty] | 111.11 |  |  | 111.11 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [14 empty] | 227.56 | 0 | 227.56
| Employee 71 | [18 empty] | 112.38 | 149.84 |  | 74.92 |  |  |  | 337.14 | 115.89 |  | 40.15 |  |  | 120.45 |  |  | 40.4 |  |  |  | 316.89 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [14 empty] | 654.03 | 0 | 654.03
| Employee 72 | [14 empty] | 23.29 | [10 empty] | 23.29 | [12 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [14 empty] | 23.29 | 0 | 23.29
| Employee 73 | [13 empty] | 155.68 | 155.68 | 973 | 622.72 | 311.36 | 155.64 | 233.46 | 715.68 | 715.68 | 636.16 | 477.12 | 834.96 | 5987.14 | 834.96 | 1073.52 | 932.3 | 1241.4 | 620.7 | 455.18 | 951.74 | 993.12 | 331.04 |  | 575.68 | 493.44 | 8503.08 | 945.76 | 740.16 | 287.84 |  |  |  | 469.7 | 256.2 | 170.8 | 0 | 89.36 | 446.8 | 3406.62 | 0 | 89.36 | 230.3 | 1750.28 | 414.54 | [7 empty] | 2484.48 | [14 empty] | 20381.32 | 0 | 20381.32
| Employee 74 | [6 empty] | IT/Communications | [18 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  |  | 0 | 649.2 | 0 | [7 empty] | 649.2 | [14 empty] | 649.2 | 0 | 649.2
| Employee 75 | [25 empty] | 0 | [12 empty] | 0 |  |  |  | 351.9 | 207.97 |  |  |  | 0 | 0 | 0 | 0 | 559.87 | 0 | 0 | 23.78 | 85.12 | 0 | [7 empty] | 108.9 | [14 empty] | 668.77 | 0 | 668.77
| Employee 76 | [13 empty] | 4544.4 | 2726.64 | 3941.7 | 2705.1 | 2594 | 3137.32 | 1530.4 | 1829.64 | 685.26 | 1521.36 | 151.32 |  | 25367.14 |  | 529.62 | 620.88 | 315.12 |  |  | 323.12 | 1126.04 | 1135.93 | 344.48 | 380.2 | 152.08 | 4927.47 | 684.36 | 608.32 | 575.18 | 1177.2 | 627.84 |  | 627.84 | 156.96 | 39.24 | 0 | 0 | 0 | 4496.94 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [14 empty] | 34791.55 | 0 | 34791.55
| Employee 77 | [50 empty] | 0 |  |  |  | 1312.21 | 3145.64 | 1865.25 | [22 empty] | 6323.1 | 0 | 6323.1
| Employee 78 | [13 empty] | 795.27 | 605.92 | [9 empty] | 151.32 | 1552.51 | [12 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [14 empty] | 1552.51 | 0 | 1552.51
| Employee 79 | [13 empty] | 129.84 | 32.46 | [10 empty] | 162.3 | [12 empty] | 0 | 155.05 |  | 132.9 | 571.34 | 548.28 |  | 158.18 |  | 189.81 | 0 | 0 | 425.97 | 2181.53 | 1434.87 | 310.6 | 190.24 | 42.56 | 149.1 | [7 empty] | 2127.37 | [14 empty] | 4471.2 | 0 | 4471.2
| Employee 80 | [25 empty] | 0 | [12 empty] | 0 | 73.35 | 244.5 | 489 | 185.44 |  | 196.02 | 92.02 |  | 48.56 | 0 | 0 | 0 | 1328.89 | 0 | 0 | 208.96 | 214.16 | 107.08 | [7 empty] | 530.2 | [14 empty] | 1859.09 | 0 | 1859.09
| Employee 81 | [25 empty] | 0 | [6 empty] | 88.51 | [5 empty] | 88.51 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [14 empty] | 88.51 | 0 | 88.51
| Employee 82 | [14 empty] | 227.68 | [10 empty] | 227.68 | [12 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [14 empty] | 227.68 | 0 | 227.68
| Employee 83 | [6 empty] | IT/Communications | [18 empty] | 0 | [12 empty] | 0 |  |  |  |  | 42.01 |  |  |  | 0 | 0 | 0 | 0 | 42.01 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [14 empty] | 42.01 | 0 | 42.01
| Employee 84 | [23 empty] | 356.96 | 446.2 | 803.16 | 44.62 | 44.62 | 44.62 | 185.96 | 232.45 | 46.49 | 139.47 | [5 empty] | 738.23 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [14 empty] | 1541.39 | 0 | 1541.39
| Employee 85 | [13 empty] | 1141.85 | 267.36 | [10 empty] | 1409.21 | [12 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [14 empty] | 1409.21 | 0 | 1409.21
| Employee 86 | [22 empty] | 154.18 |  |  | 154.18 | [12 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [14 empty] | 154.18 | 0 | 154.18
| Employee 87 | [25 empty] | 0 |  |  |  |  | 381.6 | [7 empty] | 381.6 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [14 empty] | 381.6 | 0 | 381.6
| Employee 88 | [6 empty] | IT/Communications | [18 empty] | 0 | [12 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 170.16 | 0 | 0 | 0 | [7 empty] | 170.16 | [14 empty] | 170.16 | 0 | 170.16
| Employee 89 | [13 empty] | 139.74 | [7 empty] | 145.2 |  |  |  | 284.94 | [7 empty] | 246.9 |  |  |  |  | 246.9 |  | 18.34 | 193.07 | 46.36 | 170.61 | 54.45 |  | 194.24 | 72.84 | 0 | 250.5 | 104.48 | 1104.89 | 261.2 | 195.9 | 156.72 | 267.71 | 267.7 | [7 empty] | 1149.23 | [14 empty] | 2785.96 | 0 | 2785.96
| Employee 90 | [14 empty] | 113.1 | [8 empty] | 116.47 |  | 229.57 | [12 empty] | 0 | 2709.21 | 3361.81 | 2570.75 | 835.89 | 323.52 | 363.96 | 485.28 | 1091.88 | 444.84 | 1132.32 | 5620.95 | 5335.79 | 24276.2 | 8431.41 | 9083.27 | 11140.36 | 3882.81 | 3514.5 | [7 empty] | 36052.35 | [14 empty] | 60558.12 | 0 | 60558.12
| Employee 91 | [6 empty] | IT/Communications | [18 empty] | 0 | [12 empty] | 0 | [5 empty] | 498.88 | 757.02 |  | 0 | 0 | 0 | 0 | 1255.9 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [14 empty] | 1255.9 | 0 | 1255.9
| Employee 92 | [25 empty] | 0 | [12 empty] | 0 |  |  |  |  | 323.52 | 121.32 |  |  | 0 | 1294.08 | 0 | 0 | 1738.92 | 0 | 651.75 | 0 | 0 | 0 | [7 empty] | 651.75 | [14 empty] | 2390.67 | 0 | 2390.67
| Employee 93 | [13 empty] | 418.75 | 335 | 586.25 | 335 | 837.5 | 418.75 | 418.75 | 335 | 335 | 586.25 | 418.75 | 251.25 | 5276.25 | 418.75 | 586.25 | [10 empty] | 1005 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [14 empty] | 6281.25 | 0 | 6281.25
| Employee 94 | [13 empty] | 150.8 | [9 empty] | 892.95 | 417.32 | 1461.07 | [9 empty] | 39.55 | 2491.65 | 6169.8 | 8701 | [8 empty] | 0 | 0 | 0 | 285.11 | 285.11 | 0 | 0 | 0 | 83.5 | 167.36 | [7 empty] | 250.86 | [14 empty] | 10698.04 | 0 | 10698.04
| Employee 95 | [25 empty] | 0 | [12 empty] | 0 |  |  |  | 117.01 | 158.15 | 21.09 |  |  | 105.45 | 0 | 67.5 | 22.42 | 491.62 | 381.14 | 770.48 | 297.25 | 85.12 | 168.97 | [7 empty] | 1702.96 | [14 empty] | 2194.58 | 0 | 2194.58
| Employee 96 | [6 empty] | IT/Communications | [18 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  |  | 0 | 757.4 | 324.6 | [7 empty] | 1082 | [14 empty] | 1082 | 0 | 1082
| Employee 97 | [25 empty] | 0 | [5 empty] | 287.6 | [6 empty] | 287.6 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [14 empty] | 287.6 | 0 | 287.6
| Employee 98 | [14 empty] | 42.61 | [8 empty] | 160.6 |  | 203.21 | [12 empty] | 0 | 345.3 |  |  | 1810.4 |  | 980 | 1379.4 | 1488.22 | 0 | 0 | 0 | 0 | 6003.32 | 430.77 | 0 | 0 | 0 | 0 | [7 empty] | 430.77 | [14 empty] | 6637.3 | 0 | 6637.3
| Employee 99 | [6 empty] | IT/Communications | [18 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  |  | 0 | 1084.2 | 1334.4 | [7 empty] | 2418.6 | [14 empty] | 2418.6 | 0 | 2418.6
| Employee 100 | [25 empty] | 0 | [12 empty] | 0 |  |  |  | 541.71 | 115.99 | 10.55 |  |  | 0 | 0 | 0 | 0 | 668.25 | 0 | 0 | 118.9 | 0 | 0 | [7 empty] | 118.9 | [14 empty] | 787.15 | 0 | 787.15
| Employee 101 | [25 empty] | 0 | [10 empty] | 39.55 |  | 39.55 | 158.2 |  |  |  | 323.52 |  |  |  | 40.44 | 0 | 0 | 0 | 522.16 | 0 | 407.3 | 1018.32 | 0 | 251.04 | [7 empty] | 1676.66 | [14 empty] | 2238.37 | 0 | 2238.37
| Employee 102 | [6 empty] | IT/Communications | [18 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  |  | 0 | 573.46 | 0 | [7 empty] | 573.46 | [14 empty] | 573.46 | 0 | 573.46
| Employee 103 | [6 empty] | IT/Communications | [18 empty] | 0 | [12 empty] | 0 | [10 empty] | 320 | 480 | 800 | 161.16 | 283.43 | 167.48 | 84.72 | 84.72 | [7 empty] | 781.51 | [14 empty] | 1581.51 | 0 | 1581.51
| Employee 104 | [20 empty] | 838.49 | 1598.94 | 2278.2 | 1361.88 | 2231.97 | 8309.48 | 302.64 | 529.62 | 2092.74 | 1733.16 | 748.41 | 1231.09 | 1090.53 | 2805.34 | 1331.78 | 2034.61 | 1026.54 | 608.32 | 15534.78 | 646.34 | 1710.9 | 1152.8 | 1883.52 | 1451.88 | 1059.48 | 1294.92 | 1294.92 | 902.52 | 1491.12 | 1915.72 | 3668.4 | 18472.52 | 2445.6 | 3179.28 | 4176.81 | 717.23 | 253.14 | 1216 | [6 empty] | 11988.06 | [14 empty] | 53088.84 | 1216 | 54304.84
| Employee 105 | [25 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  |  | 0 | 127.68 | 0 | [7 empty] | 127.68 | [14 empty] | 127.68 | 0 | 127.68
| Employee 106 | [14 empty] | 398.44 | 170.76 | [7 empty] | 226.56 |  | 795.76 | [12 empty] | 0 | [7 empty] | 367.32 | 0 | 397.93 | 61.22 | 123.04 | 949.51 | 953.56 | 1015.08 | 253.84 | 2348.02 | 2712.92 | [7 empty] | 7283.42 | [14 empty] | 9028.69 | 0 | 9028.69
| Employee 107 | [13 empty] | 2272.05 | 1280.61 | 495.72 | 3304.8 | 1817.64 | 660.96 | 950.13 | 660.96 | 784.89 | 3056.94 | 2395.98 | 2561.22 | 20241.9 | 3841.83 | 1735.02 | 1000.24 | 387.63 | 1679.73 | 2024.29 | 646.05 | 732.19 | 430.7 | 1130.04 | 4423.8 | 3635.4 | 21666.92 | 1095 | 3723 | 6349.7 | 3919.35 | 2612.9 | 3919.35 | 2072.3 | 3739.15 | 765.85 | 1756.95 | 1396.55 | 1494.24 | 32844.34 | 1222.56 | 1267.84 | 2101.05 | 1774.22 | 3781.89 | 1312 | [6 empty] | 11459.56 | [14 empty] | 84900.72 | 1312 | 86212.72
| Employee 108 | [23 empty] | 776.5 | 698.85 | 1475.35 | [12 empty] | 0 | [8 empty] | 808.8 | 1536.72 | 3421.32 | 4521.25 | 10288.09 | 1873.58 | 407.3 | 0 | 250.5 | 0 | [7 empty] | 2531.38 | [14 empty] | 14294.82 | 0 | 14294.82
| Employee 109 | [25 empty] | 0 |  |  | 296.16 | [9 empty] | 296.16 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [14 empty] | 296.16 | 0 | 296.16
| Employee 110 | [23 empty] | 48.4 |  | 48.4 | [12 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [14 empty] | 48.4 | 0 | 48.4
| Employee 111 | [25 empty] | 0 | [12 empty] | 0 |  |  |  | 321.36 |  |  |  |  | 97.12 | 0 | 0 | 156.72 | 575.2 | 600.76 | 52.24 | 430.98 | 0 | 0 | [7 empty] | 1083.98 | [14 empty] | 1659.18 | 0 | 1659.18
| Employee 112 | [25 empty] | 0 | [12 empty] | 0 | 1178.24 | 382.08 | 143.28 | 35.93 |  |  |  |  | 0 | 0 | 0 | 0 | 1739.53 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [14 empty] | 1739.53 | 0 | 1739.53
| Employee 113 | [25 empty] | 0 | [12 empty] | 0 | 287.95 |  |  | 246.18 | 189.79 |  |  |  | 73.82 | 0 | 90 | 269.04 | 1156.78 | 1087.37 | 701.86 | 285.36 | 255.36 | 0 | [7 empty] | 2329.95 | [14 empty] | 3486.73 | 0 | 3486.73
| Employee 114 | [25 empty] | 0 | [12 empty] | 0 | [5 empty] | 89.04 |  |  | 0 | 77.91 | 0 | 0 | 166.95 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [14 empty] | 166.95 | 0 | 166.95
| Employee 115 | [6 empty] | IT/Communications | [18 empty] | 0 | [12 empty] | 0 | [11 empty] | 592.76 | 592.76 | 255.12 | 0 | 0 | 0 | 0 | [7 empty] | 255.12 | [14 empty] | 847.88 | 0 | 847.88
| Employee 116 | [25 empty] | 0 | [12 empty] | 0 | 138.12 |  |  | 1064.9 | 24 |  | 181.5 |  | 0 | 476.97 | 0 | 114.87 | 2000.36 | 1761.34 | 2105.94 | 0 | 0 | 245.28 | [7 empty] | 4112.56 | [14 empty] | 6112.92 | 0 | 6112.92
[27 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  |  | 0 | 0 | 0 | [7 empty] | 0 | [14 empty] | 0 | 0 | 0
[27 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  |  | 0 | 0 | 0 | [7 empty] | 0 | [14 empty] | 0 | 0 | 0
[52 empty] | 0 |  |  |  | 0
| tbd - non assigned forecast | [57 empty] | 5000
Total Employee Charges to Project | [14 empty] | 21182.05 | 17744.54 | 11974.41 | 12864.27 | 16677.92 | 18653.54 | 17208.41 | 24954.61 | 26466.78 | 28497.19 | 39726.98 | 42467.75 | 278418.45 | 33124.18 | 23973.34 | 32914.79 | 24290.11 | 27720.45 | 26753.44 | 25740.84 | 35762.13 | 28168.09 | 24258.03 | 33933.7 | 36486.42 | 353125.52 | 36089.65 | 31801.42 | 38146.33 | 44374.71 | 34330.08 | 30275.48 | 33241.15 | 30767.43 | 19147.64 | 28291.6 | 55078.15 | 39296.11 | 420839.75 | 56809.28 | 46154.15 | 48258.45 | 49218.71 | 36996.82 | 23912 | 0 | 0 | 0 | 0 | 0 | 0 | 247813.11
Direct Labor (Mgt. Allocation) | [14 empty] | 1761.76 | 3476.62 | 2873.01 | 1173.18 | 2122.58 | 4454.77 | 1366.66 | 0 | 5776.21 | 6095.6 | 8750.02 | 6019.04 | 43869.45 | 6867.91 | 8476.2 | 8365.13 | 21639.75 | 10305.9 | 11121.43 | 13349.87 | 9454.43 | 9643.63 | 11268.65 | 10306.81 | 9405.47 | 130205.18 | 10307.4 | 12228.88 | 12474.73 | 13389.36 | 9928.95 | 11444.32 | 13038.31 | 8726.85 | 10112.33 | 14189.08 | 3827.62 | 10494.79 | 130162.62 | 21680.88 | 10562.6 | 16233.91 | 8018.67 | 5578.42 | 5000 | [6 empty] | 67074.48
Other Labor | [15 empty] | 3.89 |  |  |  | 3272.01 | 9.43 | 0 | 2008.36 | 25.76 |  | 2449.71 | 7769.16 |  |  |  | 40.36 |  | 1.24 | [6 empty] | 41.6 | [11 empty] | 853.64 | 853.64 |  | 258 | [10 empty] | 258
Total Labor | [14 empty] | 22943.81 | 21225.05 | 14847.42 | 14037.45 | 18800.5 | 26380.32 | 18584.5 | 24954.61 | 34251.35 | 34618.55 | 48477 | 50936.5 | 330057.06 | 39992.09 | 32449.54 | 41279.92 | 45970.22 | 38026.35 | 37876.11 | 39090.71 | 45216.56 | 37811.72 | 35526.68 | 44240.51 | 45891.89 | 483372.3 | 46397.05 | 44030.3 | 50621.06 | 57764.07 | 44259.03 | 41719.8 | 46279.46 | 39494.28 | 29259.97 | 42480.68 | 58905.77 | 50644.54 | 551856.01 | 78490.16 | 56974.75 | 64492.36 | 57237.38 | 42575.24 | 28912 | 0 | 0 | 0 | 0 | 0 | 0 | 315145.59
Note on BI21: Puget Sound Energy: vs Forecast of $39K
Note on I27: Puget Sound Energy: As per Brad Canady estimate 2/2/2011
Note on S38: Puget Sound Energy: F&G Summary shows $642k not $406k
Note on CH38: Puget Sound Energy: of which $233,831 = MWH
Note on AE41: Puget Sound Energy: Include $541,778 accrual
Note on AG41: Puget Sound Energy: Include ($541,778) Dec accrual reversal and $330,556 Jan re-accrual
Note on AH41: Puget Sound Energy: Include ($330,556) accrual reversal, $270,550 accrual
Note on AI41: Puget Sound Energy: Include ($270,550) accrual reversal and $270,400 re-accrual
Note on CO41: Puget Sound Energy: Contract amount as per May billing
Note on CQ41: Puget Sound Energy: MWH in pre-design
Note on AP43: Puget Sound Energy: Final invoice for "shoreside facilities pier geotechnical explorations and engineering report".
Note on AE44: Puget Sound Energy: Include $8,268 accrual
Note on AG44: Puget Sound Energy: Include $8,268 accrual reversal
Note on AD53: Puget Sound Energy: Bruce Blake
Note on AE53: Puget Sound Energy: Bruce Blake
Note on AH53: Puget Sound Energy: Bruce Blake
Note on AD62: Puget Sound Energy: Include 218 accrual
Note on AG62: Puget Sound Energy: Include -$509.60 accrual reversal and $109.2 re-accrual
Note on AH62: Puget Sound Energy: -$109.2 accrual reversal
Note on AL72: Puget Sound Energy: Include ($210.45) and $18.30 accruals
Note on AP72: Puget Sound Energy: Include $97.60 accrual
Note on AQ72: Puget Sound Energy: Accrual reversal
Note on AR72: Puget Sound Energy: Include $6.10 accrual
Note on AU74: Puget Sound Energy: Location of underground utilities
Note on O82: Puget Sound Energy: No info available
Note on AW84: Puget Sound Energy: FSC Gulper document
Note on CI86: Puget Sound Energy: Potential savings
Note on CN86: Puget Sound Energy: As per monthly MWH report 7/12/2011 - take into account work under Design phase and pre - 2009 spend of $233,831 (cell S35)
Note on AL87: Puget Sound Energy: Include ($130,000) accrual reversal and $163,188 and $150,000 new accruals
Note on AZ89: Puget Sound Energy: Sandblast, prime and paint 60" buoy and 2 ramps
Note on AU94: Puget Sound Energy: Wrongly coded
Note on AU95: Puget Sound Energy: Wrongly coded
Note on BK95: Puget Sound Energy: Work on old gulper
Note on CJ97: Puget Sound Energy: Agreement expires 6/30/2012
Note on H98: Puget Sound Energy: S.00774.01.01.05.03 for T&D work
Note on AR99: Puget Sound Energy: Include $2,447.22 accrual
Note on CJ99: Puget Sound Energy: Add $6K as per D Koch 1/23/2012
Note on AZ101: Puget Sound Energy: JE correction
Note on AN102: Puget Sound Energy: K Meaders June + July 2011
Note on CI109: Puget Sound Energy: Forecast based on historical burn rate
Note on AE116: Puget Sound Energy: Include $161,347 accrual
Note on AG116: Puget Sound Energy: Include -$161,347 accrual reversal
Note on AP119: Puget Sound Energy: 2 Invoices paid in Sept - $6K) adjustment on sept invoices
Note on AL120: Puget Sound Energy: Include ($1,596,336) accrual reversal and $1,069,300 June accrual
Note on H159: Puget Sound Energy: As per D Loreen approval 7/13/2012
Note on BI193: Puget Sound Energy: Conveyor dock segment for NTS debris system
Note on BK195: Puget Sound Energy: Debris conveyor control panel
Note on H199: Puget Sound Energy: Allowance of $141K transferred to Communications Building as per Dan Koch 2/2/2011
Note on AZ223: Puget Sound Energy: 30% down for mob - pedestrian gates and hardware
Note on AK226: Puget Sound Energy: Tax on LNTP (Progress Billing 1) and Billing #2
Note on AL226: Puget Sound Energy: tax on pay app 3
Note on CH226: Puget Sound Energy: 8.2% on pay app before retention as well as on accrued retention
Note on AW227: Puget Sound Energy: Kvichak Marine - overpay on WSST - 9.5% vs 8.2%
Note on AZ227: Puget Sound Energy: Overpay of WSST - 9.5% vs 8.2% on Kvichak marine invoice
Note on AE249: Puget Sound Energy: Include Accrual of $20,000
Note on AG249: Puget Sound Energy: accrual reversal and re-accrual
Note on AH249: Puget Sound Energy: -$20K accrual reversal
Note on AR250: Puget Sound Energy: Include $4,074.78 accrual
Note on BK253: Puget Sound Energy: US Fish and Wildlife Services
Note on AX257: Puget Sound Energy: Aluminum live haul transport tank
Note on AP263: Puget Sound Energy: Prelim Design and Scoping - Aug and Sept
Note on AR263: Puget Sound Energy: Invoice received for Nov work
Note on BK316: Puget Sound Energy: Refund on old gulper - amount captured as N/A under Out SVS other
Note on AV322: Puget Sound Energy: Baker Maintenance EP temp worker for Gerry Kincheloe
Note on AT325: Puget Sound Energy: Baker Maintenance Hydro Mechanic - report to Gerry Kincheloe
Note on BJ326: Puget Sound Energy: IT
Note on BE329: Puget Sound Energy: PSE Employee Communication Techs - Client Svc Sr Comm Tech II
Note on BK330: Puget Sound Energy: IT Installation
Note on BH335: Puget Sound Energy: PSE Employee Electron Generating Station Hydro Mechanic
Note on AT336: Puget Sound Energy: Baker Maintenance Hydro Tech - report to Gerry Kincheloe
Note on AT337: Puget Sound Energy: Baker Maintenance Hydro Mechanic - report to Gerry Kincheloe
Note on AX338: Puget Sound Energy: PSE Employee Telecommunications Engineering I/T Consultant
Note on AT339: Puget Sound Energy: Resource scientists - report to Cary Feldman
Note on AQ340: Puget Sound Energy: New entry
Note on AT341: Puget Sound Energy: Fish and Wildlife specialist report to Douglas Bruland
Note on AT346: Puget Sound Energy: Fish and Wildlife specialist report to Douglas Bruland
Note on AW347: Puget Sound Energy: Communication Techs - Client Svc Sr Comm Tech II
Note on BE348: Puget Sound Energy: PSE Employee Voice Assoc Voice Engineer
Note on AY351: Puget Sound Energy: PSE Employee Creative Services Multi Media Program Manager
Note on AT352: Puget Sound Energy: Consulting Engineer report to Chris Brown
Note on BJ353: Puget Sound Energy: Security
Note on BJ354: Puget Sound Energy: PSE Employee Licensing Resource Scientist - Terrestrial
Note on AQ360: Puget Sound Energy: New entry
Note on AZ361: Puget Sound Energy: PSE Employee Corporate Security Security Project Manager
Note on BJ365: Puget Sound Energy: IT
Note on BE367: Puget Sound Energy: PSE Employee SCADA Sr SCADA Engineer
Note on AV372: Puget Sound Energy: Baker Maintenance Hydro Mechanic - report to Gerry Kincheloe
Note on BG373: Puget Sound Energy: PSE Employee Electron Generating Station Hydro Mechanic
Note on AW374: Puget Sound Energy: Baker Maintenance EP Temp Worker 2nd 6mo
Note on AV375: Puget Sound Energy: Baker Maintenance EP temp worker for Gerry Kincheloe
Note on AQ377: Puget Sound Energy: New entry - Baker Maintenance PTA/EP Helper
Note on AX378: Puget Sound Energy: PSE Employee Communication Techs - Client Svc Comm Tech Foreman
Note on AQ379: Puget Sound Energy: New entry - quality assurance inspector
Note on AT380: Puget Sound Energy: Baker Maintenance EP helper report to Gerry Kincheloe
Note on AW383: Puget Sound Energy: Baker Maintenance EP Temp Worker 1st 6mo
Note on AV384: Puget Sound Energy: Baker Maintenance EP temp worker for Gerry Kincheloe
Note on AT385: Puget Sound Energy: Baker Maintenance Hydro Mechanic - report to Gerry Kincheloe
Note on BI386: Puget Sound Energy: PSE Employee Communication Techs - Client Svc Sr Comm Tech II
Note on AW387: Puget Sound Energy: Baker Maintenance EP Temp Worker 2nd 6mo
Note on BJ393: Puget Sound Energy: IT
Note on AW394: Puget Sound Energy: Baker Maintenance EP Temp Worker 1st 6mo
Note on BI396: Puget Sound Energy: PSE Employee Electron Generating Station Hydro Mechanic
Note on AT398: Puget Sound Energy: Fish and Wildlife specialist report to Douglas Bruland
Note on AT399: Puget Sound Energy: Lower Baker EP helper report John Jensen
Note on AX402: Puget Sound Energy: PSE Employee Communication Techs - Client Svc Comm Tech 1st 2 Years
Note on BH407: Puget Sound Energy: PSE Employee Communication Techs - Client Svc Comm Repairman
Note on AT409: Puget Sound Energy: Baker Maintenance Hydro Mechanic - report to Gerry Kincheloe
Note on AY410: Puget Sound Energy: PSE Employee Creative Services Multimedia Analyst
Note on AX411: Puget Sound Energy: PSE Employee Baker Maintenance Hydro Electrician
Note on AR413: Puget Sound Energy: Hydro mechanic report to Gerry Kincheloe
Note on AW414: Puget Sound Energy: Fisheries Ops Fish & Wildlife Specialist I
Note on BJ415: Puget Sound Energy: IT
Note on AT417: Puget Sound Energy: Baker Maintenance Hydro Apprentice - report to Gerry Kincheloe
Note on BJ418: Puget Sound Energy: IT
Note on AW419: Puget Sound Energy: Baker Maintenance EP Temp Worker 2nd 6mo
Note on AQ420: Puget Sound Energy: New entry - Baker maintenance hydro electrician
Note on BJ421: Puget Sound Energy: IT
Note on BD422: Puget Sound Energy: PSE Employee IT Facilities Infrastructure IT Facilities Infrastruct Engineer
Note on BJ424: Puget Sound Energy: PSE Employee Baker Maintenance EP Temp Worker 1st 6mo
Note on AW430: Puget Sound Energy: Fisheries Ops Fish & Wildlife Specialist III
Note on AT431: Puget Sound Energy: Energy Resources Project manager
Note on AT432: Puget Sound Energy: Fish and Wildlife specialist report to Douglas Bruland
Note on BE434: Puget Sound Energy: PSE Employee SCADA Sr Comm Tech II
Note on AT435: Puget Sound Energy: Baker Maintenance Hydro Apprentice - report to Gerry Kincheloe

## Powerhouse
[11 empty] | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual |  | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual |  | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual |  | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual |  | Actual | Actual | Actual | Actual | Actual | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast
[77 empty] | Within last 20% of Agreement Value | Exceeds Agreement Value
| LOWER BAKER U4 POWERHOUSE S.10774.01.01.06 ($000's) |  |  | Original Budget | Budget changed Nov 2012 | Budget Change May 2013 | Current Budget | Agreement | [68 empty] | SAP Actuals | Forecast to Complete | Current Forecast at Completion | Current Budget Variance | Previous Month Forecast at Completion | Forecast Variance - Current to Previous | To go on Agreement |  |  |  | Forecast at Completion
[8 empty] | # | $ | Comments | 2005 - 2008 | 2009 | [11 empty] | 2009 | 2010 | [11 empty] | 2010 | 2011 | [11 empty] | 2011 | 2012 | [11 empty] | 2012 | 2013 | [11 empty] | 2013 | [10 empty] | rev RB AAB | delta
[9 empty] | (excl TAX) |  |  | J | F | M | A | M | J | J | A | S | O | N | D | Total | J | F | M | A | M | J | J | A | S | O | N | D | Total | J | F | M | A | M | J | J | A | S | O | N | D | Total | J | F | M | A | M | J | J | A | S | O | N | D | Total | J | F | M | A | M | J | J | A | S | O | N | D | Total |  |  |  | Over/(Under)
pre Gate 4 | [11 empty] | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 0 | 0 | 0 | 0 | 0 | 0
| Development Costs | [81 empty] | 0
[12 empty] | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0
|  | PSE Directs |  | 173110 | 173133.56 | 0 | 173133.56 |  |  |  | 173133.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173133.56 | 0 | 173133.56 | 0 | 173133.56 | 0 | -173133.56 |  |  |  | 173133.56 | 0
|  |  | Labor | 173110 | 152609.67 |  | 152609.67 |  |  |  | 152609.67 | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 152609.67 | 0 | 152609.67 | 0 | 152609.67 | 0 | -152609.67 |  |  |  | 152609.67 | 0
|  |  | Employee Expense |  | 8082.31 |  | 8082.31 |  |  |  | 8082.31 | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 8082.31 | 0 | 8082.31 | 0 | 8082.31 | 0 | -8082.31 |  |  |  | 8082.31 | 0
|  |  | Material |  | 3069.1 |  | 3069.1 |  |  |  | 3069.1 | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 3069.1 | 0 | 3069.1 | 0 | 3069.1 | 0 | -3069.1 |  |  |  | 3069.1 | 0
|  |  | Miscellaneous Expense |  | 9139.66 |  | 9139.66 |  |  |  | 9139.66 | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 9139.66 | 0 | 9139.66 | 0 | 9139.66 | 0 | -9139.66 |  |  |  | 9139.66 | 0
|  |  | Insurance, Injuries |  | 0 |  | 0 |  |  |  | 0 | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0
|  |  | Advertising |  | 0 |  | 0 |  |  |  | 0 | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0
|  |  | Employee Training |  | 0 |  | 0 |  |  |  | 0 | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0
|  |  | Office and Supplies |  | 209.67 |  | 209.67 |  |  |  | 209.67 | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 209.67 | 0 | 209.67 | 0 | 209.67 | 0 | -209.67 |  |  |  | 209.67 | 0
|  |  | Phone Expense |  | 0 |  | 0 |  |  |  |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0
|  |  | Regulatory Fees and Permits |  | 0 |  | 0 |  |  |  | 0 | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0
|  |  | Software and Hardware |  | 0 |  | 0 |  |  |  | 0 | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0
|  |  | Rent/Lease |  | 23.15 |  | 23.15 |  |  |  | 23.15 | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 23.15 | 0 | 23.15 | 0 | 23.15 | 0 | -23.15 |  |  |  | 23.15 | 0
|  | Overheads |  | 191965.61 | 191965.61 | 0 | 191965.61 |  |  |  | 191965.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191965.61 | 0 | 191965.61 | 0 | 191965.61 | 0 | -191965.61 |  |  |  | 191965.61 | 0
|  |  | OH Construction | 191965.61 | 92160.76 |  | 92160.76 |  |  |  | 92160.76 | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 92160.76 | 0 | 92160.76 | 0 | 92160.76 | 0 | -92160.76 |  |  |  | 92160.76 | 0
|  |  | OH Labor |  | 96319.96 |  | 96319.96 |  |  |  | 96319.96 | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 96319.96 | 0 | 96319.96 | 0 | 96319.96 | 0 | -96319.96 |  |  |  | 96319.96 | 0
|  |  | OH Material |  | 16.45 |  | 16.45 |  |  |  | 16.45 | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 16.45 | 0 | 16.45 | 0 | 16.45 | 0 | -16.45 |  |  |  | 16.45 | 0
|  |  | OH Transportation |  | 3391.13 |  | 3391.13 |  |  |  | 3391.13 | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 3391.13 | 0 | 3391.13 | 0 | 3391.13 | 0 | -3391.13 |  |  |  | 3391.13 | 0
|  |  | OH Small Tools |  | 1.56 |  | 1.56 |  |  |  | 1.56 | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 1.56 | 0 | 1.56 | 0 | 1.56 | 0 | -1.56 |  |  |  | 1.56 | 0
|  |  | Unassigned Cost Elements |  | 76.34 |  | 76.34 |  |  |  | 76.34 | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 76.34 | 0 | 76.34 | 0 | 76.34 | 0 | -76.34 |  |  |  | 76.34 | 0
|  |  | CLX/C.A.R.S. System |  | -0.59 |  | -0.59 |  |  |  | -0.59 | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | -0.59 | 0 | -0.59 | 0 | -0.59 | 0 | 0.59 |  |  |  | -0.59 | 0
|  |  | Precapatilized (Non-Transfer) |  | 0 |  | 0 |  |  |  |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0
|  | Consultants |  | 595716 | 287507.45 | 0 | 287507.45 |  |  |  | 274044.02 | 28.73 | 0 | 103.61 | 0 | 34.54 | 34.54 | 0 | 0 | 51.81 | 151.2 | 802.5 | 0 | 1206.93 | 0 | 0 | 0 | 0 | 0 | 0 | 4039 | 7452.5 | 0 | 0 | 0 | 765 | 12256.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 287507.45 | 0 | 287507.45 | 0 | 287507.45 | 0 |  |  |  |  | 287507.45 | 0
|  |  | Applied Professional Services |  | 487.5 |  | 487.5 | 4600004978 | 902483.66 | Blanket agreement |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 487.5; 2009 D: 0; 2009 Total: 487.5; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 487.5 | 0 | 487.5 | 0 | 487.5 | 0 | 901996.16 |  |  |  | 487.5 | 0
|  |  | Barnard Construction Company Inc | 595716 | 7863.98 |  | 7863.98 | LPO391069 | 7863.98 | Completed | 7863.98 | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 7863.98 | 0 | 7863.98 | 0 | 7863.98 | 0 | 0 |  |  |  | 7863.98 | 0
|  |  | Bruce Blake Consulting |  | 2700 |  | 2700 | 4600003664 | 457550 | Blanket agreement | 2700 | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 2700 | 0 | 2700 | 0 | 2700 | 0 | 454850 |  |  |  | 2700 | 0
|  |  | David Evans & Associates Inc |  | 14741.5 |  | 14741.5 | 4600001845 | 6208200 | Blanket agreement | 3250 | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 4039; 2010 A: 7452.5; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 11491.5; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 14741.5 | 0 | 14741.5 | 0 | 14741.5 | 0 | 6193458.5 |  |  |  | 14741.5 | 0
|  |  | Donald D Fillis PE |  | 6892.9 |  | 6892.9 | LPO388936 | 6892.9 | Completed | 6892.9 | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 6892.9 | 0 | 6892.9 | 0 | 6892.9 | 0 | 0 |  |  |  | 6892.9 | 0
|  |  | EES Consulting Inc |  | 5235.96 |  | 5235.96 | 4600003760 | 61000 | Agreement expired | 5235.96 | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 5235.96 | 0 | 5235.96 | 0 | 5235.96 | 0 | 55764.04 |  |  |  | 5235.96 | 0
|  |  | Eric B Kollgaard |  | 6123.92 |  | 6123.92 | 4600003759 | 90000 | Blanket agreement | 6123.92 | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 6123.92 | 0 | 6123.92 | 0 | 6123.92 | 0 | 83876.08 |  |  |  | 6123.92 | 0
|  |  | Faithful+Gould |  | 85301.28 |  | 85301.28 | 4600004599 | 2199000 | Blanket agreement | 85301.28 | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 85301.28 | 0 | 85301.28 | 0 | 85301.28 | 0 | 2113698.72 |  |  |  | 85301.28 | 0
|  |  | GE International Inc |  | 45268.38 |  | 45268.38 | 4600004585 | 83522 | Agreement expired | 45268.38 | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 45268.38 | 0 | 45268.38 | 0 | 45268.38 | 0 | 38253.62 |  |  |  | 45268.38 | 0
|  |  | Hydroinsight LLC |  | 19189.8 |  | 19189.8 | 4600002887 | 547805 | Blanket agreement | 19189.8 | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 19189.8 | 0 | 19189.8 | 0 | 19189.8 | 0 | 528615.2 |  |  |  | 19189.8 | 0
|  |  | Jerry D Higgins PH.D PG Inc |  | 8141.22 |  | 8141.22 | 4600003761 | 60000 | Blanket agreement | 8141.22 | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 8141.22 | 0 | 8141.22 | 0 | 8141.22 | 0 | 51858.78 |  |  |  | 8141.22 | 0
|  |  | Kim de Rubertis |  | 11452.92 |  | 11452.92 | 4600003758 | 90000 | Blanket agreement | 11452.92 | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 11452.92 | 0 | 11452.92 | 0 | 11452.92 | 0 | 78547.08 |  |  |  | 11452.92 | 0
|  |  | KJM & Associates LTD |  | 15461.98 |  | 15461.98 | 4600002549 | 4277100 | Agreement expired | 15208.75 | 2009 J: 28.73; 2009 F: 0; 2009 M: 103.61; 2009 A: 0; 2009 M: 34.54; 2009 J: 34.54; 2009 J: 0; 2009 A: 0; 2009 S: 51.81; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 253.23; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 15461.98 | 0 | 15461.98 | 0 | 15461.98 | 0 | 4261638.02 |  |  |  | 15461.98 | 0
|  |  | Leonard Boudinot & Skodje Inc |  | 6758.75 |  | 6758.75 | 4600001798 | 1089998 | Blanket agreement | 6758.75 | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 6758.75 | 0 | 6758.75 | 0 | 6758.75 | 0 | 1083239.25 |  |  |  | 6758.75 | 0
|  |  | Northwest Cascade Inc |  | 151.2 |  | 151.2 | 4600001697 | 1225000 | Blanket agreement |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 151.2; 2009 N: 0; 2009 D: 0; 2009 Total: 151.2; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 151.2 | 0 | 151.2 | 0 | 151.2 | 0 | 1224848.8 |  |  |  | 151.2 | 0
|  |  | Powel Technology Inc |  | 11282.3 |  | 11282.3 | 6400002993 | 50000 | Active | 11282.3 | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 11282.3 | 0 | 11282.3 | 0 | 11282.3 | 0 | 38717.7 |  |  |  | 11282.3 | 0
|  |  | Robert L. Coffell |  | 1080 |  | 1080 | LPO398734 | 315 | Completed |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 315; 2009 D: 0; 2009 Total: 315; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 765; 2010 Total: 765; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 1080 | 0 | 1080 | 0 | 1080 | 0 | -765 |  |  |  | 1080 | 0
|  |  | Tung Van Do |  | 2302.47 |  | 2302.47 |  |  | No info | 2302.47 | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 2302.47 | 0 | 2302.47 | 0 | 2302.47 | 0 | -2302.47 |  |  |  | 2302.47 | 0
|  |  | Wescorp |  | 21071.39 |  | 21071.39 | 4600003776 | 1370000 | Blanket agreement | 21071.39 | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 21071.39 | 0 | 21071.39 | 0 | 21071.39 | 0 | 1348928.61 |  |  |  | 21071.39 | 0
|  |  | Whitewater Engineering Corporation |  | 16000 |  | 16000 | 4600004470 | 400000 | Agreement expired | 16000 | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 16000 | 0 | 16000 | 0 | 16000 | 0 | 384000 |  |  |  | 16000 | 0
|  | Assessments, Transfers, etc |  | 0 | 433983.29 | 0 | 433983.29 |  |  |  | 433983.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 433983.29 | 0 | 433983.29 | 0 | 433983.29 | 0 |  |  |  |  | 433983.29 | 0
|  |  | 69990120 Outside Services Other Transfer - P/P/C | 0 | 428994.88 |  | 428994.88 |  |  |  | 428994.88 | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 428994.88 | 0 | 428994.88 | 0 | 428994.88 | 0 | -428994.88 |  |  |  | 428994.88 | 0
|  |  | 84200013 Outside Services Other - Assessment |  | 4988.41 |  | 4988.41 |  |  |  | 4988.41 | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 4988.41 | 0 | 4988.41 | 0 | 4988.41 | 0 | -4988.41 |  |  |  | 4988.41 | 0
|  | Engineering |  | 1396061 | 1283749.35 | 0 | 1283749.35 |  |  |  | 1283749.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1283749.35 | 0 | 1283749.35 | 0 | 1283749.35 | 0 | -1283749.35 |  |  |  | 1283749.35 | 0
|  |  | URS Energy and Construction | 1396061 | 595716 |  | 595716 | 4600003649 | 1300000 | Agreement expired | 595716 | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 595716 | 0 | 595716 | 0 | 595716 | 0 | 704284 |  |  |  | 595716 | 0
|  |  | MWH Americas Inc |  | 191255.1 |  | 191255.1 | 4600004459 | 245000 | Agreement expired | 191255.1 | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 191255.1 | 0 | 191255.1 | 0 | 191255.1 | 0 | 53744.9 |  |  |  | 191255.1 | 0
|  |  | Shannon & Wilson Inc |  | 496778.25 |  | 496778.25 | 4600004051 | 1700000 | Blanket agreement | 496778.25 | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 496778.25 | 0 | 496778.25 | 0 | 496778.25 | 0 | 1203221.75 |  |  |  | 496778.25 | 0
| Total Development |  |  | 2356852.61 | 2370339.26 | 0 | 2370339.26 |  |  |  | 2356875.83 | 28.73 | 0 | 103.61 | 0 | 34.54 | 34.54 | 0 | 0 | 51.81 | 151.2 | 802.5 | 0 | 1206.93 | 0 | 0 | 0 | 0 | 0 | 0 | 4039 | 7452.5 | 0 | 0 | 0 | 765 | 12256.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2370339.26 | 0 | 2370339.26 | 0 | 2370339.26 | 0 |  |  |  |  | 2370339.26 | 0
[12 empty] | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 0 | 0 | 0 | 0 | 0 | 0
Engineering
[12 empty] | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 0 |  | 0 | 0 | 0 | 0
|  | Jacobs Associates |  | 1231000 | 1509940.38 | 0 | 1509940.38 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54795.42 | 58382.09 | 113177.51 | 0 | 303162.27 | 0 | 194913.87 | 0 | 0 | 349175 | -0.25 | 0 | -49416.07 | 0 | 282457.37 | 1080292.19 | -183528.19 | -1 | 0 | 26332.49 | 200000.1 | -3314.72 | 250000 | 0 | 0 | 0 | 0 | 0.3 | 289488.98 | -26719 | 587.21 | 0 | 0 | 0 | 129677.16 | 0 | 0 | 0 | 0 | 0 | 55178.99 | 158724.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1641683.04 | 0 | 1641683.04 | 131742.66 | 1709941.04 | -68258 |  |  |  |  | 1509940.1 | -131742.94
u |  | Tunnel Design Services |  | 756000 | 747483.38 |  | 747483.38 | 6400002347 | 1058100 | Active | 0 | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 54795.42; 2009 D: 58382.09; 2009 Total: 113177.51; 2010 J: 0; 2010 F: 303162.27; 2010 M: 0; 2010 A: 194913.87; 2010 M: 0; 2010 J: 0; 2010 J: 349175; 2010 A: -0.25; 2010 S: 0; 2010 O: -49416.07; 2010 N: 0; 2010 D: 20000.24; 2010 Total: 817835.06; 2011 J: -183528.19; 2011 F: -1; 2011 Total: -183529.19; 2012 J: 191112.8; 2012 Total: 191112.8; 2013 Total: 0 | 938596.18 | 0 | 938596.18 | 191112.8 | 938596.18 | 0 |  |  |  |  | 747483.38 | -191112.8
|  | DB Specs/Construction Support |  | 475000 | 762457 |  | 762457 | 6400003831 | 900000 | Active | 0 | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 Total: 0; 2010 J: 0; 2010 D: 262457.13; 2010 Total: 262457.13; 2011 A: 26332.49; 2011 M: 200000.1; 2011 J: -3314.72; 2011 J: 250000; 2011 A: 0; 2011 S: 0; 2011 O: 0; 2011 N: 0; 2011 D: 0.3; 2011 Total: 473018.17; 2012 J: -217831.8; 2012 F: 587.21; 2012 J: 129677.16; 2012 D: 55178.99; 2012 Total: -32388.44; 2013 J: 0; 2013 J: 0; 2013 Total: 0 | 703086.86 | 0 | 703086.86 | -59370.14 | 771344.86 | -68258 |  | 403314.72 | forecast to complete as per invoice 06/02/2011 |  | 762456.72 | 59369.86
|  | URS Corporation |  | 2597000 | 2775872.28 | 0 | 2775872.28 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90931.57 | 90931.57 | 0 | 0 | 0 | 189877.37 | 0 | 10415.35 | 1073.68 | 300079.67 | 722.9 | 0 | 1580.5 | 451458 | 955207.47 | 5297.52 | 0 | 175287.48 | -233219.83 | -18379 | -17169.93 | 11749.82 | 104324.18 | 50000 | 42368 | 57624.5 | 45996 | 223878.74 | 40904.5 | 45000 | 45000 | 45000 | 59052 | 82032 | 48223 | 8894.05 | 45000 | 27839.15 | 2541.8 | 48135.35 | 497621.85 | 5396 | 23337.7 | 25000 | 11093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64826.7 | 1832466.33 | 0 | 1832466.33 | -943405.95 | 1949288.93 | -116822.6 |  |  |  |  | 2793504.2535 | 961037.9235
|  | Powerhouse Design |  | 847000 | 933093.19 |  | 933093.19 | 6400003043 | 974848 | Active | 0 | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 189877.37; 2010 M: 0; 2010 A: 300079.67; 2010 O: 0; 2010 D: 451458; 2010 Total: 941415.04; 2011 J: 0; 2011 F: 0; 2011 M: -8321.85; 2011 Total: -8321.85; 2012 Total: 0; 2013 Total: 0 | 933093.19 | 0 | 933093.19 | 0 | 933093.19 | 0 |  |  |  |  | 933093.19 | 0
|  | Project, Record and Construction Project Management |  | 1750000 | 1842779.09 |  | 1842779.09 | 6400002523 | 3200000 | Active | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90931.57 | 90931.57 | 0 | 0 | 0 |  |  | 10415.35 | 1073.68 |  | 722.9 |  | 1580.5 |  | 13792.43 | 5297.52 |  | 183609.33 | -233219.83 | -18379 | -17169.93 | 11749.82 | 104324.18 | 50000 | 42368 | 57624.5 | 45996 | 232200.59 | 40904.5 | 45000 | 45000 | 45000 | 59052 | 82032 | 48223 | 8894.05 | 45000 | 27839.15 | 2541.8 | 48135.35 | 497621.85 | 5396 | 23337.7 | 25000 | 11093 | 0 | 0 | 0 | [5 empty] | 64826.7 | 899373.14 | 0 | 899373.14 | -943405.95 | 1016195.74 | -116822.6 |  | 1701454 | 802080.86 | (contract) | 1860411.0635 | 961037.9235
|  | URS Energy and Construction |  | 0 | 18542.04 | 0 | 18542.04 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18542.04 | 18542.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18542.04 | 0 | 18542.04 | 0 | 18542.04 | 0 |  |  |  |  | 18542.04 | 0
|  | Powerhouse Design |  |  | 0 |  | 0 | 4600003649 | 1300000 | Agreement expired |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
|  | Powerhouse Design |  |  | 18542.04 |  | 18542.04 | 4600005441 | 466349 | Active |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 18542.04; 2010 Total: 18542.04; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 18542.04 | 0 | 18542.04 | 0 | 18542.04 | 0 |  |  |  |  | 18542.04 | 0
|  | MWH Americas Inc |  | 0 | 5237.51 | 0 | 5237.51 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1104.23 | 1476.63 | 2656.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5237.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5237.51 | 0 | 5237.51 | 0 | 5237.51 | 0 |  |  |  |  | 5237.51 | 0
|  |  |  | 0 | 0 |  | 0 | 4600004459 | 245000 | Agreement expired |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
|  |  |  | 0 | 5237.51 |  | 5237.51 | 6400002259 | 783704 | Active |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 M: 1104.23; 2011 A: 1476.63; 2011 M: 2656.65; 2011 Total: 5237.51; 2012 Total: 0; 2013 Total: 0 | 5237.51 | 0 | 5237.51 | 0 | 5237.51 | 0 |  |  |  |  | 5237.51 | 0
|  | Shannon & Wilson Inc |  | 1000000 | 583586.13 |  | 583586.13 | 4600004051 | 2900000 | Blanket agreement |  | 2009 J: 0; 2009 F: 3124.21; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 7328.18; 2009 J: 1469.55; 2009 A: 0; 2009 S: 0; 2009 O: 3107.56; 2009 N: 8140.2; 2009 D: 4376.52; 2009 Total: 27546.22; 2010 J: 0; 2010 F: 3391.22; 2010 M: 0; 2010 A: 3068.94; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 12138.51; 2010 S: 0; 2010 O: 78331.59; 2010 N: 0; 2010 D: 35692.71; 2010 Total: 132622.97; 2011 M: 359929.26; 2011 A: 8404.78; 2011 Total: 368334.04; 2012 Total: 0; 2013 Total: 0 | 528503.23 | 0 | 528503.23 | -55082.9 | 528503.23 | 0 |  | 2403221.75 | 1874718.52 | to be reviewed | 1000000.23 | 471497
|  | Consultants |  | 1174268 | 959595.51 | 0 | 959595.51 |  |  |  | 0 | 0 | 14000 | 3516 | 0 | 0 | 0 | 0 | 6500 | 4000 | 0 | 3059.08 | 0 | 31075.08 | 9033.5 | 3276.75 | 1403 | 6180 | 44398.43 | 84146.04 | 55237.25 | 81270.28 | 97395.36 | 88379.13 | 24550.08 | 172194.88 | 667464.7 | 27744.63 | 16290.85 | 44187.6 | 26731.97 | 44720.12 | 31643.37 | 14108.35 | 17353.31 | 31378.55 | 6896.98 | 70297.85 | 53049.32 | 384402.9 | 2321.5 | 21212.74 | 19041.59 | 4916.2 | 44635.05 | 4103.3 | 9738.5 | 38110.03 | 7782.62 | 18603.97 | 38045.08 | 21449.8 | 229960.38 | 10266.21 | 7952.38 | 13943.84 | 15447.2667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47609.6967 | 1360512.7567 | 0 | 1360512.7567 | 400917.2467 | 1398250.29 | -37737.5333 |  |  |  |  | 1132894.4033 | -227618.3533
|  |  | A-1 Mobile Lock & Key Inc |  | 164.46 |  | 164.46 | LPO 401033 | 164.46 | Completed | 0 | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 Total: 0; 2011 M: 164.46; 2011 Total: 164.46; 2012 Total: 0; 2013 Total: 0 | 164.46 | 0 | 164.46 | 0 | 164.46 | 0 |  |  |  |  | 164.46 | 0
|  |  | AEROTEK | 1174268 | 7174.84 |  | 7174.84 |  |  | Blanket agreement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39.9 | 0 | 758.67 | 1623.82 | 425.92 | 3354.57 | 430.08 | 6632.96 | -58.68 | -26.84 | 443.96 | 61.76 | 259.54 | -256.2 |  | 118.34 |  |  |  |  | 541.88 |  | 4952.59 | 1418.25 | 1609.18 | 1134.6 | 3678.3 | 2635.2 | 5151.28 | 3115.12 | 3305.2 | 5452.91 | 5305.48 | 37758.11 | -369.94 | 1896.48 | -1526.44 | 0 | 0 | [7 empty] | 0.1 | 44933.05 | 0 | 44933.05 | 37758.21 | 44933.05 | 0 |  |  |  |  | 7312.7 | -37620.35
|  |  | ALS USA Corp |  | 19085 |  | 19085 | 6400001990 | 50000 | Active | 0 | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 A: 11510; 2010 O: 7575; 2010 Total: 19085; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 19085 | 0 | 19085 | 0 | 19085 | 0 | 30915 |  |  |  | 19085 | 0
|  |  | Applied Professional Services |  | 3205 |  | 3205 | 4600004978 | 1402483 | Blanket agreement | 0 | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 390; 2010 M: 0; 2010 A: 520; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 440; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 1202.5; 2010 Total: 2552.5; 2011 J: 360; 2011 S: 292.5; 2011 Total: 652.5; 2012 S: 325; 2012 Total: 325; 2013 M: 320; 2013 A: 243.75; 2013 Total: 563.75 | 4093.75 | 0 | 4093.75 | 888.75 | 4142.5 | -48.75 | 1398389.25 |  |  |  | 2552.5 | -1541.25
|  |  | Asplundh Tree Experts |  | 569.68 |  | 569.68 | 4600003358 | 137000000 | Blanket agreement |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 M: 569.68; 2011 Total: 569.68; 2012 Total: 0; 2013 Total: 0 | 569.68 | 0 | 569.68 | 0 | 569.68 | 0 | 136999430.32 |  |  |  | 569.68 | 0
|  |  | Barnard Construction Company Inc |  | 0 |  | 0 | LPO 391069 | 7863.98 | Completed |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7863.98 |  |  |  | 0 | 0
|  |  | Bruce Blake Consulting |  | 7587 |  | 7587 | 4600003664 | 1857550 | Blanket agreement |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 6345; 2010 S: 1242; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 7587; 2011 D: 332; 2011 Total: 332; 2012 J: 1162; 2012 Total: 1162; 2013 Total: 0 | 9081 | 0 | 9081 | 1494 | 9081 | 0 | 1848469 |  |  |  | 7587 | -1494
|  |  | Building Information Systems |  | 66953.5 |  | 66953.5 | 6400002830 | 74720 | Agreement expired |  | 2009 D: 0; 2009 Total: 0; 2010 J: 7122.5; 2010 M: 1403; 2010 A: 0; 2010 J: 21907; 2010 J: 15072.5; 2010 A: 0; 2010 S: 21448.5; 2010 N: 0; 2010 Total: 66953.5; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 66953.5 | 0 | 66953.5 | 0 | 66953.5 | 0 | 7766.5 |  |  |  | 66953.5 | 0
|  |  | Building Information Systems |  | 26901.75 |  | 26901.75 | 6400002386 | 149520 | Agreement expired |  | 2009 D: 0; 2009 Total: 0; 2010 F: 2886.75; 2010 M: 9280; 2010 O: 14735; 2010 N: 0; 2010 D: 10000; 2010 Total: 36901.75; 2011 J: -10000; 2011 Total: -10000; 2012 Total: 0; 2013 Total: 0 | 26901.75 | 0 | 26901.75 | 0 | 26901.75 | 0 | 122618.25 |  |  |  | 26901.75 | 0
|  |  | Canopy Conservation LLC |  | 4927.5 |  | 4927.5 | 6400003320 | 35000 | Active |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 4927.5; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 4927.5; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 4927.5 | 0 | 4927.5 | 0 | 4927.5 | 0 | 30072.5 |  |  |  | 4927.5 | 0
|  |  | Cascade Drilling LP |  | 14315 |  | 14315 | 4600003041 | 250000 | Completed |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 14315; 2010 N: 0; 2010 D: 0; 2010 Total: 14315; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 14315 | 0 | 14315 | 0 | 14315 | 0 | 235685 |  |  |  | 14315 | 0
|  |  | Currents Consulting Inc |  | 20078.77 |  | 20078.77 | 6400003595 | 60000 | Active |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 3485; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 3825; 2010 Total: 7310; 2011 M: 12040; 2011 J: -3225.93; 2011 S: 3954.7; 2011 D: 5093.34; 2011 Total: 17862.11; 2012 M: 3161.57; 2012 Total: 3161.57; 2013 Total: 0 | 28333.68 | 0 | 28333.68 | 8254.91 | 28333.68 | 0 | 31666.32 | 60000 | 31666.32 |  | 19350 | -8983.68
|  |  | Cynthia Conrad |  | 200 |  | 200 | LPO 394521 | 200 | Completed |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 Total: 0; 2011 M: 200; 2011 Total: 200; 2012 Total: 0; 2013 Total: 0 | 200 | 0 | 200 | 0 | 200 | 0 | 0 |  |  |  | 200 | 0
|  |  | David Evans & Associates Inc |  | 6991.67 |  | 6991.67 | 4600001845 | 6298200 | Blanket agreement |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 1780.92 | 629.51 | 538.16 | 649.35 | 1367.01 | 591.87 | 1434.85 | 739.78 | 641.5 | 8372.95 |  | 5162.47 | 10796.97 | [6 empty] | 526.5 |  |  | 16485.94 | [5 empty] | 0 | [6 empty] | 0 | 24858.89 | 0 | 24858.89 | 17867.22 | 27332.39 | -2473.5 | 6273341.11 | 24500 | -358.89 |  | 24501.2533 | -357.6367
|  |  | Dewey & LeBoeuf LLP |  | 177787.88 |  | 177787.88 | 4600002357 | 11850200 | Blanket agreement |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 13921.88; 2010 J: 0; 2010 A: 0; 2010 S: 55627.72; 2010 O: 9289.95; 2010 N: 26301.8; 2010 D: 31782.88; 2010 Total: 136924.23; 2011 J: 16022.11; 2011 M: 13007.61; 2011 A: 10082.6; 2011 M: 1751.33; 2011 Total: 40863.65; 2012 Total: 0; 2013 Total: 0 | 177787.88 | 0 | 177787.88 | 0 | 177787.88 | 0 | 11672412.12 |  |  |  | 177787.88 | 0
|  |  | Direct Connect Group West |  |  |  |  | 6400003686 | 1000000 | Active |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 Total: 0; 2011 Total: 0; 2012 A: 1151.26; 2012 O: 550.52; 2012 D: 470.81; 2012 Total: 2172.59; 2013 J: 749.49; 2013 Total: 749.49 | 2922.08 | 0 | 2922.08 | 2922.08 | 2922.08 | 0 | 997077.92 |  |  |  | 177787.88 | 174865.8
|  |  | Economy Fence Center |  | 14526.93 |  | 14526.93 | 6400003384 | 50000 | Active |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 J: 6670.53; 2011 S: 7856.4; 2011 Total: 14526.93; 2012 Total: 0; 2013 Total: 0 | 14526.93 | 0 | 14526.93 | 0 | 14526.93 | 0 | 35473.07 | 50000 | 35473.07 |  | 0 | -14526.93
|  |  | EES Consulting Inc |  | 0 |  | 0 | 4600003760 | 61000 | Agreement expired |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61000 |  |  |  | 0 | 0
|  |  | Eric B Kollgaard |  | 19065.62 |  | 19065.62 | 4600003759 | 90000 | Blanket agreement |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 12537.9; 2010 Total: 12537.9; 2011 J: 1800; 2011 S: 4727.72; 2011 D: 5675.71; 2011 Total: 12203.43; 2012 M: 7390.05; 2012 M: 4996.33; 2012 O: 1462.5; 2012 Total: 13848.88; 2013 Total: 0 | 38590.21 | 0 | 38590.21 | 19524.59 | 38590.21 | 0 | 51409.79 |  |  |  | 12537.9 | -26052.31
|  |  | Extreme Access Incorporated |  | 0 |  | 0 |  |  |  |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 J: 2814.18; 2013 A: 14364.0167; 2013 J: 0; 2013 Total: 17178.1967 | 17178.1967 | 0 | 17178.1967 | 17178.1967 | 22814.18 | -5635.9833 | -17178.1967 |  |  |  | 0 | -17178.1967
|  |  | Fichtner GmBH |  | 0 |  | 0 | 6400004425 | 100000 | Active |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 N: 38758; 2011 D: -711.37; 2011 Total: 38046.63; 2012 M: 18580.66; 2012 Total: 18580.66; 2013 Total: 0 | 56627.29 | 0 | 56627.29 | 56627.29 | 56627.29 | 0 | 43372.71 |  |  |  | 0 | -56627.29
|  |  | GE International Inc |  | 0 |  | 0 | 4600004585 | 83522 | Agreement expired |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83522 |  |  |  | 0 | 0
|  |  | GeoEngineers Inc |  | 106245.36 |  | 106245.36 | 4600005167 | 13409100 | Blanket agreement |  | 2009 D: 0; 2009 Total: 0; 2010 J: 1911; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 15298.25; 2010 A: 25046.83; 2010 S: 521.02; 2010 O: 20858.26; 2010 N: -15040.11; 2010 D: 12825.33; 2010 Total: 61420.58; 2011 J: 20720.61; 2011 F: 1799.75; 2011 M: 13667.67; 2011 J: 8636.75; 2011 N: 18931.1; 2011 D: 8076.5; 2011 Total: 71832.38; 2012 F: 8694.95; 2012 M: 8872.85; 2012 J: 6853.3; 2012 A: 32958.75; 2012 S: 3747.5; 2012 O: 12359.25; 2012 D: 10487.45; 2012 Total: 83974.05; 2013 J: 4530.55; 2013 F: 6055.9; 2013 M: 13105.3; 2013 A: 839.5; 2013 M: 0; 2013 Total: 24531.25 | 241758.26 | 0 | 241758.26 | 135512.9 | 251739.56 | -9981.3 | 13167341.74 |  |  |  | 110143.86 | -131614.4
|  |  | Henkels & McCoy Inc |  | 2572.13 |  | 2572.13 | 4600004346 | 1806603 | Agreement expired |  | 2009 D: 0; 2009 Total: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 D: 2572.13; 2010 Total: 2572.13; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 2572.13 | 0 | 2572.13 | 0 | 2572.13 | 0 | 1804030.87 |  |  |  | 2572.13 | 0
|  |  | Hill International Inc |  | 2680 |  | 2680 | 6400002843 | 580500 | Blanket agreement |  | 2009 D: 0; 2009 Total: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 Total: 0; 2011 M: 2680; 2011 Total: 2680; 2012 Total: 0; 2013 Total: 0 | 2680 | 0 | 2680 | 0 | 2680 | 0 | 577820 |  |  |  | 2680 | 0
|  |  | Historical Research Associates Inc |  | 0 |  | 0 | 6400001837 | 300000 | Active |  | 2009 D: 0; 2009 Total: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 Total: 0; 2011 Total: 0; 2012 M: 1709.14; 2012 Total: 1709.14; 2013 Total: 0 | 1709.14 | 0 | 1709.14 | 1709.14 | 1709.14 | 0 | 298290.86 |  |  |  | 0 | -1709.14
|  |  | Hydroinsight LLC |  | 111188.12 |  | 111188.12 | 4600002887 | 547805 | Blanket agreement |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5295 | 2118.52 | 16454 | 11285 | 767 | 21180 | 0 | 21146 | 78245.52 | 13925 | 4267.1 | 2271.2 | 7289 | 3390.3 | 600 |  |  | 1200 |  |  | 11990.04 | 44932.64 | 1050 |  | -525 | 300 | 450 | [5 empty] | 5170.26 |  | 6445.26 |  |  |  |  | 0 | [7 empty] | 0 | 129623.42 | 0 | 129623.42 | 18435.3 | 129623.42 | 0 | 418181.58 |  |  |  | 109388.12 | -20235.3
|  |  | Jerry D Higgins PH.D PG Inc |  | 22511.03 |  | 22511.03 | 4600003761 | 100000 | Blanket agreement |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 19499.14; 2010 Total: 19499.14; 2011 J: -10000; 2011 M: 6702.2; 2011 J: 6309.69; 2011 D: 10554.04; 2011 Total: 13565.93; 2012 D: 5186.06; 2012 Total: 5186.06; 2013 Total: 0 | 38251.13 | 0 | 38251.13 | 15740.1 | 38251.13 | 0 | 61748.87 |  |  |  | 16201.34 | -22049.79
|  |  | Kim de Rubertis |  | 51556.46 |  | 51556.46 | 4600003758 | 90000 | Blanket agreement |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3059.08 | 0 | 3059.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5367.78 | 1365.88 | 0 | 0 | 15687.6 | 22421.26 | -3557.33 |  |  | 1600 | 2684.7 | 9321.6 | 3022.25 | 3090 | 9914.9 |  | 400 | 4909.19 | 31385.31 |  |  |  | 1855.76 | 3145.57 |  |  |  |  | 400 |  |  | 5401.33 | [5 empty] | 0 | 0 | [5 empty] | 0 | 62266.98 | 0 | 62266.98 | 10710.52 | 81864.98 | -19598 | 27733.02 |  |  |  | 26207.71 | -36059.27
|  |  | Klohn Crippen Berger Ltd |  | 7291.62 |  | 7291.62 | 4600003716 | 17868747 | Active |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 7291.62; 2010 Total: 7291.62; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 7291.62 | 0 | 7291.62 | 0 | 7291.62 | 0 | 17861455.38 |  |  |  | 7291.62 | 0
|  |  | Klohn Crippen Berger Ltd |  | 4972.86 |  | 4972.86 | 6400003722 | 80000 | Active |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 Total: 0; 2011 J: 4972.86; 2011 Total: 4972.86; 2012 Total: 0; 2013 Total: 0 | 4972.86 | 0 | 4972.86 | 0 | 4972.86 | 0 | 75027.14 |  |  |  | 0 | -4972.86
|  |  | Leonard Boudinot & Skodje Inc |  | 0 |  | 0 | 4600001798 | 1089998 | Blanket agreement |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1089998 |  |  |  |  | 0
|  |  | McMillen Engineering LLC |  | 14000 |  | 14000 | 6400001510 | 14000 | Agreement expired |  | 2009 J: 0; 2009 F: 14000; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 14000; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 14000 | 0 | 14000 | 0 | 14000 | 0 | 0 |  |  |  | 14000 | 0
|  |  | Northwest Cascade Inc |  | 109.5 |  | 109.5 | 4600001697 | 1287500 | Blanket agreement |  | 2009 J: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 S: 109.5; 2011 N: 109.5; 2011 D: 109.5; 2011 Total: 328.5; 2012 J: 109.5; 2012 F: 109.5; 2012 M: -38.68; 2012 Total: 180.32; 2013 Total: 0 | 508.82 | 0 | 508.82 | 399.32 | 508.82 | 0 | 1286991.18 |  |  |  | 0 | -508.82
|  |  | Open Text Inc. |  | 5306.69 |  | 5306.69 | 6400003906 | 385250 | Agreement expired |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 D: 0; 2010 Total: 0; 2011 A: 5306.69; 2011 Total: 5306.69; 2012 Total: 0; 2013 Total: 0 | 5306.69 | 0 | 5306.69 | 0 | 5306.69 | 0 | 379943.31 |  |  |  | 5306.69 | 0
|  |  | Pacific Geomatic Services Inc |  | 55008.5 |  | 55008.5 | 6400001495 | 70000 | Agreement expired |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 6500; 2009 S: 4000; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 10500; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 10500 | 0 | 10500 | -44508.5 | 10500 | 0 | 59500 |  |  |  | 55008.5 | 44508.5
|  |  | Pacific Geomatic Services Inc |  | 20517 |  | 20517 | 6400002966 | 180000 | Active |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 5660; 2010 M: 25742; 2010 A: 20517; 2010 D: 13106.5; 2010 Total: 65025.5; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 65025.5 | 0 | 65025.5 | 44508.5 | 65025.5 | 0 | 114974.5 | 151600 | 86574.5 |  | 34771.5 | -30254
|  |  | Pacific Rim Environmental |  |  |  |  | 4600003376 | 254000 | Active |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 Total: 0; 2011 Total: 0; 2012 J: 250; 2012 Total: 250; 2013 Total: 0 | 250 | 0 | 250 | 250 | 250 | 0 | 253750 | 0 | -250 |  | 0 | -250
|  |  | Powel Technology Inc |  | 29360 |  | 29360 | 6400002993 | 50000 | Agreement expired |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 29360; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 29360; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 29360 | 0 | 29360 | 0 | 29360 | 0 | 20640 |  |  |  | 29360 | 0
|  |  | R2 Resource Consultants Inc |  | 3722.74 |  | 3722.74 | 6400001732 | 950000 | Blanket agreement |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 2336; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 693.82; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 3029.82; 2011 J: 692.92; 2011 Total: 692.92; 2012 Total: 0; 2013 Total: 0 | 3722.74 | 0 | 3722.74 | 0 | 3722.74 | 0 | 946277.26 |  |  |  | 3722.74 | 0
|  |  | Tall Taurus Media LLC |  | 611 |  | 611 | LPO 401044 | 611 | Completed |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 Total: 0; 2011 A: 611; 2011 Total: 611; 2012 Total: 0; 2013 Total: 0 | 611 | 0 | 611 | 0 | 611 | 0 | 0 |  |  |  | 611 | 0
|  |  | Tetra Tech Inc |  | 120698.81 |  | 120698.81 | 6400001434 | 300000 | Agreement expired |  | 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 1745.43; 2010 J: 16798.74; 2010 J: 0; 2010 A: 0; 2010 S: 14105.6; 2010 O: 0; 2010 N: 9933.82; 2010 D: 20288.2; 2010 Total: 62871.79; 2011 F: 10250.84; 2011 M: 11383.02; 2011 M: 17062.54; 2011 J: 6352.66; 2011 A: 12777.96; 2011 D: 710.57; 2011 Total: 58537.59; 2012 Total: 0; 2013 Total: 0 | 121409.38 | 0 | 121409.38 | 710.57 | 121409.38 | 0 | 178590.62 | 149579 | 28169.62 |  | 149579.19 | 28169.81
|  |  | Trinity Gate and Door Company |  | 0 |  | 0 | 4600002127 | 1733624 | Active |  | 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 Total: 0; 2011 N: 10509.47; 2011 Total: 10509.47; 2012 F: 1953.23; 2012 N: 27421.91; 2012 Total: 29375.14; 2013 M: 2044.98; 2013 Total: 2044.98 | 41929.59 | 0 | 41929.59 | 41929.59 | 41929.59 | 0 | 1691694.41 | 0 | -41929.59 |  | 0 | -41929.59
|  |  | Van De Vanter Group |  | 8193.09 |  | 8193.09 | 4600001047 | 803801 | Blanket agreement |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 S: 2730.96; 2011 O: 5462.13; 2011 N: 850; 2011 D: 5668.3; 2011 Total: 14711.39; 2012 F: 340; 2012 M: 2584.33; 2012 J: 425; 2012 S: 595; 2012 Total: 3944.33; 2013 J: 2541.93; 2013 Total: 2541.93 | 21197.65 | 0 | 21197.65 | 13004.56 | 21197.65 | 0 | 782603.35 |  |  |  | 0 | -21197.65
|  |  | Whitewater Engineering Corporation |  | 3516 |  | 3516 | 4600004470 | 400000 | Agreement expired |  | 2009 J: 0; 2009 F: 0; 2009 M: 3516; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 3516; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 3516 | 0 | 3516 | 0 | 3516 | 0 | 396484 |  |  |  | 3516 | 0
| Total Engineering |  |  | 6002268 | 5852773.85 | 0 | 5852773.85 |  |  |  | 0 | 0 | 17124.21 | 3516 | 0 | 0 | 7328.18 | 1469.55 | 6500 | 4000 | 3107.56 | 65994.7 | 153690.18 | 262730.38 | 9033.5 | 309830.24 | 1403 | 394040.18 | 44398.43 | 94561.39 | 405485.93 | 393488.21 | 98118.26 | 117294.65 | 26130.58 | 960345 | 2854129.37 | -150486.04 | 16289.85 | 580508.57 | -170273.96 | 228997.87 | 11158.72 | 275858.17 | 121677.49 | 81378.55 | 49264.98 | 127922.35 | 99045.62 | 1271342.17 | 16507 | 66799.95 | 64041.59 | 49916.2 | 103687.05 | 215812.46 | 57961.5 | 47004.08 | 52782.62 | 46443.12 | 40586.88 | 124764.14 | 886306.59 | 15662.21 | 31290.08 | 38943.84 | 26540.2667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112436.3967 | 5386944.9067 | 0 | 5386944.9067 | -465828.9433 | 5609763.04 | -222818.1333 |  |  |  |  | 6460118.5368 | 1073173.6301
[12 empty] | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction
[12 empty] | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PCL |  | 47788377 | 47989494.493 | 2000000 | 49989494.493 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1637174.41 | 1637174.41 | 4302.19 | 4878171.48 | 3657073.2 | 2811108.57 | 1789404.35 | 1000000.31 | 1400000 | 41401.584 | 545611.39 | 810495.214 | 743459.03 | 4098197.18 | 21779224.498 | 1997445.1226 | 2214217.8618 | 2077474.6574 | 3729792.3953 | 887862.6953 | 1277344.0958 | 1105372.2897 | 457849.1182 | 1338989.9734 | 322941.8429 | 1155454.441 | 334084.9068 | 16898829.4 | 4021944.1699 | 434960.8168 | 1235966.9955 | 1193263.4446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6886135.4268 | 47201363.7348 | 0 | 47201363.7348 | -2788130.7582 | 50622886.6525 | -3421522.9177 |  | 48762605.928 | 1561242.1932 |  | 48235000.0607 | 1033636.3259
|  |  | PCL Construction Services | 46288377 | 46459997.3065 | 2000000 | 48459997.3065 | 6400003681 | 50263958.35 | Active |  | 2009 Total: 0; 2010 D: 679172.41; 2010 Total: 679172.41; 2011 J: 4302.19; 2011 F: 1527908.48; 2011 M: 4308241.2; 2011 A: 3370591.57; 2011 M: 307098.35; 2011 J: 3379841.31; 2011 A: 1828078.326; 2011 S: 1195042.39; 2011 O: 949558.214; 2011 N: 646342.346; 2011 D: 1052579.062; 2011 Total: 18569583.438; 2012 J: 1315201.0646; 2012 F: 1804194.2138; 2012 M: 2372489.9774; 2012 A: 2098136.0753; 2012 M: 3560876.7203; 2012 J: 734184.1068; 2012 J: 1134059.7597; 2012 A: 553949.3002; 2012 S: 758033.8046; 2012 O: 1166685.7641; 2012 N: 566255.3622; 2012 D: 1001335.9668; 2012 Total: 17065402.1156; 2013 J: 853634.1699; 2013 F: 2297058.8168; 2013 M: 913468.27; 2013 A: 1119985.8046; 2013 M: 0; 2013 J: 0; 2013 J: 0; 2013 Total: 5184147.0614 | 41498305.025 | 0 | 41498305.025 | -6961692.2814 | 47963427.0707 | -6465122.0456 |  | 46459998 | 4961692.975 |  | 47235000.0607 | 5736695.0357
|  |  | Accruals - work completed |  | 0 |  | 0 |  |  |  |  | 2009 Total: 0; 2010 D: 958002; 2010 Total: 958002; 2011 J: 0; 2011 F: 3350263; 2011 M: -651168; 2011 A: -559483; 2011 M: 1482306; 2011 J: -2379841; 2011 J: 1400000; 2011 A: -1940720; 2011 S: -649431; 2011 O: -139063; 2011 N: 81577; 2011 D: 587360; 2011 Total: 581800; 2012 J: 583648; 2012 F: 414270; 2012 M: -295015.32; 2012 A: 1631656.32; 2012 M: -2831672; 2012 J: 485998.47; 2012 J: -28687.47; 2012 A: -153782; 2012 S: 575867.09; 2012 O: -848833; 2012 N: 584110; 2012 D: -657362; 2012 Total: -539801.91; 2013 J: 3168310; 2013 F: -1902673; 2013 M: -71777; 2013 A: -166055; 2013 M: 0; 2013 J: 0; 2013 Total: 1027805 | 2027805.09 | 0 | 2027805.09 | 2027805.09 | 0.09 | 2027805 |  |  | -2027805.09 |  | 0 | -2027805.09
|  |  | Accruals - retention |  | 0 |  | 0 |  |  |  |  | 2009 Total: 0; 2010 Total: 0; 2011 J: 0; 2011 D: 2317491; 2011 Total: 2317491; 2012 J: 51238; 2012 F: -8860; 2012 M: 0; 2012 A: 0; 2012 M: 82661; 2012 J: 0; 2012 J: 0; 2012 A: 49081; 2012 S: 0; 2012 O: 0; 2012 N: 0; 2012 D: 0; 2012 Total: 174120; 2013 J: 0; 2013 F: 0; 2013 M: 0; 2013 A: 86489.1667; 2013 M: 0; 2013 J: 0; 2013 J: 0; 2013 Total: 86489.1667 | 2578100.1667 | 0 | 2578100.1667 | 2578100.1667 | 0 | 2578100.1667 |  |  | -2578100.1667 |  | 0 | -2578100.1667
|  |  | CO 1/CCD-002: Allowance for tunnel grouting |  | 432799.9286 |  | 432799.9286 |  |  |  |  | 2009 Total: 0; 2010 Total: 0; 2011 A: 24886; 2011 Total: 24886; 2012 F: 4613.648; 2012 Total: 4613.648; 2013 Total: 0 | 29499.648 | 0 | 29499.648 | -403300.2806 | 29499.648 | 0 |  | 432800 | 403300.352 |  | 0 | -29499.648
|  |  | CO 2/CCD-011: Spoils storage/rehandling/development |  | 129157.258 |  | 129157.258 |  |  |  |  | 2009 Total: 0; 2010 Total: 0; 2011 A: 129157.258; 2011 Total: 129157.258; 2012 Total: 0; 2013 Total: 0 | 129157.258 | 0 | 129157.258 | 0 | 129157.258 | 0 |  | 129157.258 | 0 |  | 0 | -129157.258
|  |  | CCD-009: Office trailer credit/del. computer hardware |  | -32460 |  | -32460 |  |  |  |  | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 J: 0; 2013 Total: 0 | 0 | 0 | 0 | 32460 | -32460 | 32460 |  | -32460 | -32460 |  | 0 | 0
|  |  | CO 5 | [8 empty] | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
|  |  | CCD-017: Additional tunnel seismograph | [8 empty] | 2009 Total: 0; 2010 Total: 0; 2011 N: 6492; 2011 D: 3125.898; 2011 Total: 9617.898; 2012 Total: 0; 2013 Total: 0 | 9617.898 | 0 | 9617.898 | 9617.898 | 9617.898 | 0 |  | 6492 | -3125.898 |  | 0 | -9617.898
|  |  | CCD-018: Hwy 20 Stockpile Hydrospam | [8 empty] | 2009 Total: 0; 2010 Total: 0; 2011 N: 9047.684; 2011 D: 33.542; 2011 Total: 9081.226; 2012 Total: 0; 2013 Total: 0 | 9081.226 | 0 | 9081.226 | 9081.226 | 9081.226 | 0 |  | 9047.684 | -33.542 |  | 0 | -9081.226
|  |  | CPR-008: Remove pier nose | [8 empty] | 2009 Total: 0; 2010 Total: 0; 2011 D: 72589.216; 2011 Total: 72589.216; 2012 Total: 0; 2013 Total: 0 | 72589.216 | 0 | 72589.216 | 72589.216 | 72589.216 | 0 |  | 0 | -72589.216 |  | 0 | -72589.216
|  |  | CPR-011: Landscaping in laydown area | [8 empty] | 2009 Total: 0; 2010 Total: 0; 2011 D: 59771.844; 2011 Total: 59771.844; 2012 Total: 0; 2013 Total: 0 | 59771.844 | 0 | 59771.844 | 59771.844 | 59771.844 | 0 |  | 0 | -59771.844 |  | 0 | -59771.844
|  |  | CP-002: OSENCO breathing aparatus | [8 empty] | 2009 Total: 0; 2010 Total: 0; 2011 D: 5246.618; 2011 Total: 5246.618; 2012 Total: 0; 2013 Total: 0 | 5246.618 | 0 | 5246.618 | 5246.618 | 5246.618 | 0 |  | 0 | -5246.618 |  | 0 | -5246.618
|  |  | CO 6 / CCD-019: Install escape tunnel | [8 empty] | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 J: 33833.058; 2012 Total: 33833.058; 2013 Total: 0 | 33833.058 | 0 | 33833.058 | 33833.058 | 33833.058 | 0 |  |  | -33833.058 |  | 0 | -33833.058
|  |  | CCD-021: Communication room add-ons | [8 empty] | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 J: 13525; 2012 Total: 13525; 2013 Total: 0 | 13525 | 0 | 13525 | 13525 | 13525 | 0 |  |  | -13525 |  | 0 | -13525
|  |  | CP-28: Changes to requirements for transformer area | [8 empty] | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -185086.92 | -185086.92 |  | 0 | 0
|  |  | CO 7/CP 034 - Rock pocket repair scope (MDEC) | 0 | 0 | 0 | 0 |  |  |  |  | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 M: 0; 2012 M: 18835.456; 2012 Total: 18835.456; 2013 Total: 0 | 18835.456 | 0 | 18835.456 | 18835.456 | 18835.456 | 0 |  | 18835.456 | 0 |  | 0 | -18835.456
|  |  | CO 7/CPR-15: Scroll case and Draft Tube Elbow paint | [8 empty] | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 M: 57161.519; 2012 J: 57161.519; 2012 Total: 114323.038; 2013 Total: 0 | 114323.038 | 0 | 114323.038 | 114323.038 | 114323.038 | 0 |  | 114323.038 | 0 |  | 0 | -114323.038
|  |  | CO 010 - Accompanying various CP's | 0 | 0 | 0 | 0 |  |  |  |  | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 M: 0; 2012 Total: 0; 2013 Total: 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
|  |  | CP 045: Additional seismograph for tunnel excavation | [8 empty] | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 A: 3551.124; 2012 Total: 3551.124; 2013 Total: 0 | 3551.124 | 0 | 3551.124 | 3551.124 | 3551.124 | 0 |  | 0 | -3551.124 |  | 0 | -3551.124
|  |  | CP59: Surge tank overflow mitigation - design | [8 empty] | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 A: 5049.694; 2012 Total: 5049.694; 2013 Total: 0 | 5049.694 | 0 | 5049.694 | 5049.694 | 5049.694 | 0 |  | 5049.694 | 0 |  | 0 | -5049.694
|  |  | CPR-19/CP59: Surge tank modifications | [8 empty] | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 5049.694 | 5049.694 |  | 0 | 0
|  |  | Potential Mechanical Claims | [8 empty] | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 5049.694 | 5049.694 |  | 0 | 0
|  |  | CCD 033 - Sprayhood installation and embedment | [8 empty] | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 0 |  | 0 | 0 | 0 | 0 |  | 5049.694 | 5049.694 |  | 0 | 0
|  |  | CO 8 - South Portal repair cost | [8 empty] | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 S: 5089.0788; 2012 O: 5089.0788; 2012 N: 5089.0788; 2012 D: -9889.06; 2012 Total: 5378.1764; 2013 J: 0; 2013 Total: 0 | 5378.1764 | 0 | 5378.1764 | 5378.1764 | 0.1764 | 5378 |  | 5049.694 | -328.4824 |  | 0 | -5378.1764
|  |  | CO 12 | [8 empty] | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 F: 40575; 2013 M: 394275.7254; 2013 A: 152843.4733; 2013 M: 0; 2013 J: 0; 2013 Total: 587694.1987 | 587694.1987 | 0 | 587694.1987 | 587694.1987 | 746459.0854 | -158764.8867 |  | 5049.694 | -582644.5047 |  | 0 | -587694.1987
|  |  | CO 13 - Unit 3 Wiring and Controls upgrade, Unit 3 instrument upgrade, HPU piping modifications, 13.8kV power system protective relays | [8 empty] | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 M: 0; 2013 J: 0; 2013 Total: 0 | 0 | 0 | 0 | 0 | 476768.152 | -476768.152 |  | 5049.694 | 5049.694 |  | 0 | 0
|  |  | Geotechnical Contingency | 500000 | 0 | 0 | 0 |  |  |  |  | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
|  |  | Back charge to PCL for Omega Morgan Rigging charges |  | 0 | 0 | 0 |  |  |  |  | 2009 Total: 0; 2010 Total: 0; 2011 J: 0; 2011 Total: 0; 2012 Total: 0; 2013 J: 0; 2013 Total: 0 | 0 | 0 | 0 | 0 | -35389 | 35389 |  | 774151.554 | 774151.554 |  | 0 | 0
|  |  | Early Completion Bonus | 1000000 | 1000000 |  | 1000000 |  |  |  |  | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 J: 0; 2013 Total: 0 | 0 | 0 | 0 | -1000000 | 1000000 | -1000000 |  | 1000000 | 1000000 |  | 1000000 | 1000000
|  | Other |  | 1300000 | 1884033.69 | 500000 | 2384033.69 |  |  |  | 0 | 720.72 | 0 | 559.36 | 647.68 | 478.72 | 0 | 4224 | 0 | 0 | 0 | 0 | 0 | 6630.48 | 0 | 0 | 0 | 2217.38 | 3253.13 | 4616 | 6266.43 | 9180.34 | 11829.08 | 30688.85 | 5395 | 352811.13 | 426257.34 | 17498.02 | 5334 | 8313.13 | 460 | 0 | 3220 | 0 | 9079 | 17670.48 | 21531.02 | 2070 | -6242.58 | 78933.07 | 20737.89 | 29679.61 | 29212.68 | 31238.42 | 40252.61 | 23850.09 | 24375.25 | 28680.28 | 28635.41 | 91071.96 | 166506.03 | 195502.85 | 709743.08 | 24341.21 | 157923.65 | 156213.2 | 107352.2417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 445830.3017 | 1667394.2717 | 0 | 1667394.2717 | -716639.4183 | 2627714.8306 | -960320.5589 |  |  |  |  | 3135018.57 | 1467624.2983
|  |  | Clubhouse Renovation | 0 | 4302.19 | 0 | 4302.19 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4302.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4302.19 | 0 | 0 | 1343.88 | 551.25 | 791.68 | 0 | 0 | 0 | 9089.39 | 1211.65 | 0 | 25943.39 | 38931.24 | 1399.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1399.95 | 44633.38 | 0 | 44633.38 | 40331.19 | 44633.38 | 0 | -44633.38 |  |  |  | 24912.86 | -19720.52
|  |  | Bola Architecture & Planning |  | 4302.19 |  | 4302.19 | LPO 395033 | 4302.19 | Completed |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 M: 4302.19; 2011 Total: 4302.19; 2012 Total: 0; 2013 Total: 0 | 4302.19 | 0 | 4302.19 | 0 | 4302.19 | 0 | 0 |  |  |  | 4302.19 | 0
|  |  | Bola Architecture & Planning |  |  |  |  | 4600005711 | 62000 | Active |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 M: 1343.88; 2012 A: 551.25; 2012 M: 791.68; 2012 S: 9089.39; 2012 O: 1211.65; 2012 D: -4309.33; 2012 Total: 8678.52; 2013 J: 1399.95; 2013 Total: 1399.95 | 10078.47 | 0 | 10078.47 | 10078.47 | 10078.47 | 0 | 51921.53 |  |  |  | 4302.19 | -5776.28
|  |  | Finishing Touch Masonry | [8 empty] | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 D: 30252.72; 2012 Total: 30252.72; 2013 Total: 0 | 30252.72 | 0 | 30252.72 | 30252.72 | 30252.72 | 0 | -30252.72 |  |  |  | 4302.19 | -25950.53
|  |  | tbd | [8 empty] | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0
|  |  | CEMEX |  | 13742.83 |  | 13742.83 | 4600003202 | 2175000 | Blanket agreement |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 13742.83; 2010 N: 0; 2010 D: 0; 2010 Total: 13742.83; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 13742.83 | 0 | 13742.83 | 0 | 13742.83 | 0 | 2161257.17 |  |  |  | 13742.83 | 0
|  |  | Clearcreek Contractors inc |  | 30958.5 |  | 30958.5 | 6400003561 | 35800 | Agreement expired |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 N: 0; 2010 D: 30958.5; 2010 Total: 30958.5; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 30958.5 | 0 | 30958.5 | 0 | 30958.5 | 0 | 4841.5 |  |  |  | 30958.5 | 0
|  |  | Evergreen Sanitation Inc |  | 1511.1 |  | 1511.1 | 4600004186 | 100000 | Blanket agreement |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 M: 1511.1; 2011 Total: 1511.1; 2012 Total: 0; 2013 Total: 0 | 1511.1 | 0 | 1511.1 | 0 | 1511.1 | 0 | 98488.9 |  |  |  | 1511.1 | 0
|  |  | Everett Engineering |  | 0 |  | 0 | LPO 395884 | 5500.68 |  |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 S: 5500.68; 2012 N: 2730; 2012 Total: 8230.68; 2013 M: 0; 2013 Total: 0 | 8230.68 | 0 | 8230.68 | 8230.68 | 8230.68 | 0 | -2730 |  |  |  | 0 | -8230.68
|  |  | Natt McDougall Company |  | 50000 |  | 50000 |  | 50000 | Bid stipend |  | 2009 J: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 50000; 2010 Total: 50000; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 50000 | 0 | 50000 | 0 | 50000 | 0 | 0 |  |  |  | 50000 | 0
|  |  | Nelson Trucking Co Inc | [8 empty] | 2009 J: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 M: 2865.86; 2013 Total: 2865.86 | 2865.86 | 0 | 2865.86 | 2865.86 | 2865.86 | 0 | -2865.86 |  |  |  | 0 | -2865.86
|  |  | Ness & Campbell Crane Inc |  | 0 |  | 0 | 6400002835 | 1000000 |  |  | 2009 J: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 Total: 0; 2011 Total: 0; 2012 S: 832.2; 2012 Total: 832.2; 2013 M: 9422.48; 2013 Total: 9422.48 | 10254.68 | 0 | 10254.68 | 10254.68 | 10254.68 | 0 | 989745.32 |  |  |  | 0 | -10254.68
|  |  | North Sky Engineering Inc |  | 25956.72 |  | 25956.72 | 4600005348 | 923286 | Blanket agreement |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 4680; 2010 S: 2520; 2010 O: 6240; 2010 N: 1200; 2010 D: 10560; 2010 Total: 25200; 2011 S: 504.48; 2011 O: 252.24; 2011 Total: 756.72; 2012 J: 3279.12; 2012 J: 679.7; 2012 Total: 3958.82; 2013 Total: 0 | 29915.54 | 0 | 29915.54 | 3958.82 | 29915.54 | 0 | 893370.46 |  |  |  | 25200 | -4715.54
|  |  | Northwest Cascade Inc |  | 435.9 |  | 435.9 | 4600001697 | 1287500 | Blanket agreement |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 90; 2010 J: 176.4; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 266.4; 2011 A: 169.5; 2011 Total: 169.5; 2012 Total: 0; 2013 Total: 0 | 435.9 | 0 | 435.9 | 0 | 435.9 | 0 | 1287064.1 |  |  |  | 266.4 | -169.5
|  |  | Northwest Utility Services |  | 24912.86 |  | 24912.86 | 4600002211 | 4650000 | Agreement expired |  | 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 3256.51; 2010 J: 4526; 2010 J: 4250.03; 2010 A: 2925.34; 2010 S: 441.57; 2010 O: 8406.02; 2010 N: 0; 2010 D: 0; 2010 Total: 23805.47; 2011 J: 1107.39; 2011 Total: 1107.39; 2012 J: 1379.16; 2012 Total: 1379.16; 2013 F: 2907.09; 2013 M: 5060.1; 2013 A: 2776.9417; 2013 M: 0; 2013 Total: 10744.1317 | 37036.1517 | 0 | 37036.1517 | 12123.2917 | 37591.54 | -555.3883 | 4612963.8483 |  |  |  | 24912.86 | -12123.2917
|  |  | PSE Security |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | -300000 | 0 |  |  |  | 24912.86 | 24912.86
|  |  | tbd | [8 empty] | 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 J: 0; 2013 J: 0; 2013 Total: 0 | 0 | 0 | 0 | 0 | 300000 | -300000 | 0 |  |  |  | 24912.86 | 24912.86
|  |  | PSE IT (indirects) |  | 0 | 500000 | 500000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1840 | 0 | 4485 | 2300 | 3220 | 3463 | 15308 | 0 | 1150 | 460 | 460 | 0 | 3220 | 0 | 2530 | 2300 | 1526.53 | 2070 | 2134.56 | 15851.09 | 1150 | 0 | 6327.88 | 0 | 1890 | 3949.31 | 2530 | 2310 | 230 | 1965 | 43564.36 | 49168.1 | 113084.65 | 9970.36 | 5018.75 | 49089.98 | 862.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64941.59 | 209185.33 | 0 | 209185.33 | -290814.67 | 317912.83 | -108727.5 | -209185.33 |  |  |  | 24912.86 | -184272.47
|  |  | Sogeti USA LLC |  |  |  |  | 4600004941 | 1034770 | Blanket agreement |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1840 | . | 4485 | 2300 | 3220 | 3463 | 15308 |  | 1150 | 460 | 460 |  | 3220 |  | 2530 | 2300 | 1526.53 | 2070 | 2134.56 | 15851.09 | 1150 |  | 6327.88 |  | 1890 | 3949.31 | 2530 | 2310 | 230 | 1965 | 2645 | 5682.36 | 28679.55 |  | 4898.75 | 10942.37 | 862.5 | 0 | [7 empty] | 16703.62 | 76542.26 | 0 | 76542.26 | 76542.26 | 76714.76 | -172.5 | 958227.74 |  |  |  | 17378 | -59164.26
|  |  | Osisoft | [8 empty] | 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 N: 21394.66; 2012 Total: 21394.66; 2013 Total: 0 | 21394.66 | 0 | 21394.66 | 21394.66 | 21394.66 | 0 | -21394.66 |  |  |  | 24912.86 | 3518.2
|  |  | Dimension Data North American Inc | [8 empty] | 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 N: 19524.7; 2012 Total: 19524.7; 2013 J: 9970.36; 2013 Total: 9970.36 | 29495.06 | 0 | 29495.06 | 29495.06 | 29495.06 | 0 | -29495.06 |  |  |  | 24912.86 | -4582.2
|  |  | Skyler Electric Co Inc | [8 empty] | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 D: 43485.74; 2012 Total: 43485.74; 2013 M: 5612.98; 2013 Total: 5612.98 | 49098.72 | 0 | 49098.72 | 49098.72 | 49098.72 | 0 |  | 757400 | 708301.28 |  | 754600 | 705501.28
|  |  | Easi LLC | [8 empty] | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 F: 120; 2013 M: 60; 2013 Total: 180 | 180 | 0 | 180 | 180 | 180 | 0 |  | 0 | -180 |  | 0 | -180
|  |  | Veca Electric & Technologies | [8 empty] | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 M: 32474.63; 2013 Total: 32474.63 | 32474.63 | 0 | 32474.63 | 32474.63 | 32474.63 | 0 |  | 0 | -32474.63 |  | 0 | -32474.63
|  |  | tbd |  |  | 500000 | 500000 |  |  |  |  | 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 J: 0; 2013 Total: 0 | 0 | 0 | 0 | -500000 | 108555 | -108555 | 0 |  |  |  | 24912.86 | 24912.86
|  |  | P&G Landscaping | [8 empty] | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 Total: 0; 2011 Total: 0; 2012 N: 24817; 2012 D: 38957.3; 2012 Total: 63774.3; 2013 Total: 0 | 63774.3 | 0 | 63774.3 | 63774.3 | 63774.3 | 0 | -63774.3 |  |  |  | 3940 | -59834.3
|  |  | On Site Environmental Inc |  | 3940 |  | 3940 | 4600003281 | 1420000 | Agreement expired |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 1575; 2010 S: 130; 2010 O: 0; 2010 N: 975; 2010 D: 0; 2010 Total: 2680; 2011 F: 1260; 2011 D: 250; 2011 Total: 1510; 2012 Total: 0; 2013 A: 50; 2013 Total: 50 | 4240 | 0 | 4240 | 300 | 4250 | -10 | 1415760 |  |  |  | 3940 | -300
|  |  | Potelco Inc |  | 247855.78 |  | 247855.78 | 4600001197 | 10325000 | Blanket agreement |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 247855.78; 2010 Total: 247855.78; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 247855.78 | 0 | 247855.78 | 0 | 247855.78 | 0 | 10077144.22 |  |  |  | 247855.78 | 0
|  |  | Pottle & Sons Construction Inc |  | 6197.42 |  | 6197.42 | 4600005302 | 655812 | Blanket agreement |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 6197.42; 2010 Total: 6197.42; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 6197.42 | 0 | 6197.42 | 0 | 6197.42 | 0 | 649614.58 |  |  |  | 6197.42 | 0
|  |  | Protec Inc | [8 empty] | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 Total: 0; 2011 Total: 0; 2012 N: 7500; 2012 Total: 7500; 2013 Total: 0 | 7500 | 0 | 7500 | 7500 | 7500 | 0 | -7500 |  |  |  | 0 | -7500
|  |  | Quanta Services Inc |  | 14715.2 |  | 14715.2 | 4600002102 | 65000000 | Blanket agreement |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 J: 14715.2; 2011 Total: 14715.2; 2012 O: 2825.29; 2012 N: 255.95; 2012 D: 18.62; 2012 Total: 3099.86; 2013 M: 0; 2013 Total: 0 | 17815.06 | 0 | 17815.06 | 3099.86 | 17815.06 | 0 | 64982184.94 |  |  |  | 14715.2 | -3099.86
` |  |  | Quality Coatings Inspection |  |  |  |  | 4600005796 | 25000 | Active |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 F: 1397.74; 2012 M: 1057.74; 2012 M: 3796.44; 2012 J: 7562.36; 2012 J: 359.43; 2012 O: 717.74; 2012 D: 5741.92; 2012 Total: 20633.37; 2013 F: 8252.26; 2013 A: 3329.4167; 2013 J: 0; 2013 Total: 11581.6767 | 32215.0467 | 0 | 32215.0467 | 32215.0467 | 32999.29 | -784.2433 | -7215.0467 |  |  |  | 14715.2 | -17499.8467
|  |  | Testing Services | 0 | 142081.77 | 0 | 142081.77 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1675.43 | 2924 | 1489.84 | 0 | 0 | 0 | 0 | 6379.5 | 14866 | 19752.25 | 0 | -9613 | 37474.02 | 14944.91 | 26047.23 | 7999 | 23257.18 | 30646.5 | 8180 | 9449.5 | 10757.25 | 10140 | 10966.5 | 0 | 16155 | 168543.07 | 0 | 17165 | 0 | 10570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27735 | 233752.09 | 0 | 233752.09 | 91670.32 | 256017.09 | -22265 |  |  |  |  | 444923.74 | 211171.65
|  |  | Geotest Services Inc |  | 51675.43 |  | 51675.43 | LPO401028 | 1675.43 | Completed |  | 2009 D: 0; 2009 Total: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 Total: 0; 2011 J: 1675.43; 2011 Total: 1675.43; 2012 Total: 0; 2013 Total: 0 | 1675.43 | 0 | 1675.43 | -50000 | 1675.43 | 0 | 0 |  |  |  | 349586.43 | 347911
|  |  | Geotest Services Inc |  | 923 |  | 923 | LPO401039 | 923 | Completed |  | 2009 D: 0; 2009 Total: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 Total: 0; 2011 M: 923; 2011 Total: 923; 2012 Total: 0; 2013 Total: 0 | 923 | 0 | 923 | 0 | 923 | 0 | 0 |  |  |  | 923 | 0
|  |  | Geotest Services Inc | [8 empty] | 2009 D: 0; 2009 Total: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 923 | 923
|  |  | Materials Testing & Consulting Inc |  | 566.84 |  | 566.84 | 4600003511 | 295000 | Blanket agreement |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 M: 566.84; 2011 Total: 566.84; 2012 Total: 0; 2013 Total: 0 | 566.84 | 0 | 566.84 | 0 | 566.84 | 0 | 294433.16 |  |  |  | 566.84 | 0
|  |  | Mayes Testing Engineers Inc |  | 2924 |  | 2924 | 6400002926 | 5000 | Agreement expired |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 F: 2924; 2011 Total: 2924; 2012 Total: 0; 2013 Total: 0 | 2924 | 0 | 2924 | 0 | 2924 | 0 | 2076 |  |  |  | 2924 | 0
|  |  | Mayes Testing Engineers Inc |  | 85992.5 | 0 | 85992.5 | 6400004008 | 215000 | Active | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6379.5 | 14866 | 19752.25 | 0 | -9613 | 31384.75 | 14944.91 | 26047.23 | 7999 | 23257.18 | 30646.5 | 8180 | 9449.5 | 10757.25 | 10140 | 10966.5 | 0 | 16155 | 168543.07 | 0 | 17165 | 0 | 10570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27735 | 227662.82 | 0 | 227662.82 | 141670.32 | 249927.82 | -22265 | -12662.82 | 90000 | -137662.82 |  | 90000.47 | -137662.35
|  |  | - Work completed |  | 85992.5 |  | 85992.5 |  | 215000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 6379.5 | 14866 | 19752.25 |  | -9613 | 31384.75 | 14944.91 | 26047.23 | 7999 | 22817.18 | 30399.5 | 8180 | 9449.5 | 10757.25 | 10140 | 10966.5 |  | 16155 | 167856.07 |  | 17165 |  | 10570 | 0 | 0 | 0 | [5 empty] | 27735 | 226975.82 | 0 | 226975.82 | 140983.32 | 249240.82 | -22265 | -11975.82
|  |  | - Standby time | [8 empty] | 2009 F: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 A: 440; 2012 M: 247; 2012 Total: 687; 2013 Total: 0 | 687 | 0 | 687 | 687 | 687 | 0 | -687 |  |  |  | 6630.48 | 5943.48
|  |  | LGIA Scope (S.10774.01.01.06) | 1300000 | 1300000 |  | 1300000 |  | 1300000 |  |  | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 D: 5378.18; 2012 Total: 5378.18; 2013 J: 0; 2013 Total: 0 | 5378.18 | 0 | 5378.18 | -1294621.82 | 468105.9306 | -462727.7506 |  |  |  |  | 1300000 | 1294621.82
|  |  | Order # 111020147, 111020148 | [5 empty] | 1300000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 |  | 2234.64 | 12484.18 | 6889.49 | 3127.99 | 4158.42 | 11356.62 | 15613.03 | 2343.14 | 4337.68 | 84943.72 | 805.22 | 148294.13 | 12970.9 | 95320.99 | 89774.78 | 32793.2167 | 0 | [7 empty] | 230859.8867 | 379154.0167 | 0 | 379154.0167 | 379154.0167 | 385712.66 | -6558.6433 | 920845.9833 |  |  |  | 0 | -379154.0167
|  |  | Turbo Trucking |  | 550 |  | 550 |  | 2000 | Completed |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 M: 550; 2011 Total: 550; 2012 A: 540.5; 2012 S: 500; 2012 Total: 1040.5; 2013 Total: 0 | 1590.5 | 0 | 1590.5 | 1040.5 | 1590.5 | 0 | 409.5 |  |  |  | 550 | -1040.5
|  |  | Trucking of spoils - LB & R Logging |  |  |  |  | 4600006282 | 300000 | Active |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 O: 69048.1; 2012 N: 2695; 2012 D: 53335.12; 2012 Total: 125078.22; 2013 F: 29259.56; 2013 A: 56970.1667; 2013 J: 0; 2013 J: 0; 2013 Total: 86229.7267 | 211307.9467 | 0 | 211307.9467 | 211307.9467 | 269999.98 | -58692.0333 | 88692.0533 |  |  |  | 0 | -211307.9467
|  |  | Walker Heavy Construction |  | 2214 |  | 2214 | 4600005305 | 2167397 | Blanket agreement |  | 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 2217.38; 2010 M: -3.38; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 2214; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 2214 | 0 | 2214 | 0 | 2214 | 0 | 2165183 |  |  |  | 2214 | 0
|  |  | Wescorp |  | 6630.48 |  | 6630.48 | 4600003776 | 1370000 | Blanket agreement |  | 2009 J: 720.72; 2009 F: 0; 2009 M: 559.36; 2009 A: 647.68; 2009 M: 478.72; 2009 J: 0; 2009 J: 4224; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 6630.48; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 6630.48 | 0 | 6630.48 | 0 | 6630.48 | 0 | 1363369.52 |  |  |  | 6630.48 | 0
|  |  | Western Refinery Services Inc |  |  |  |  | 4600001411 | 1195825 | Active |  | 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 D: 985.86; 2011 Total: 985.86; 2012 J: -15.3; 2012 Total: -15.3; 2013 Total: 0 | 970.56 | 0 | 970.56 | 970.56 | 970.56 | 0 | 1194854.44 |  |  |  | 6630.48 | 5659.92
|  |  | Williams Scotsman |  | 8028.94 |  | 8028.94 | 6400003383 | 20000 | Agreement expired |  | 2009 J: 0; 2009 F: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 4252.51; 2010 O: 0; 2010 N: 0; 2010 D: 3776.43; 2010 Total: 8028.94; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 8028.94 | 0 | 8028.94 | 0 | 8028.94 | 0 | 11971.06 |  |  |  | 8028.94 | 0
| Total Construction |  |  | 49088377 | 49873528.183 | 2500000 | 52373528.183 |  |  |  | 0 | 720.72 | 0 | 559.36 | 647.68 | 478.72 | 0 | 4224 | 0 | 0 | 0 | 0 | 0 | 6630.48 | 0 | 0 | 0 | 2217.38 | 3253.13 | 4616 | 6266.43 | 9180.34 | 11829.08 | 30688.85 | 5395 | 1989985.54 | 2063431.75 | 21800.21 | 4883505.48 | 3665386.33 | 2811568.57 | 1789404.35 | 1003220.31 | 1400000 | 50480.584 | 563281.87 | 832026.234 | 745529.03 | 4091954.6 | 21858157.568 | 2018183.0126 | 2243897.4718 | 2106687.3374 | 3761030.8153 | 928115.3053 | 1301194.1858 | 1129747.5397 | 486529.3982 | 1367625.3834 | 414013.8029 | 1321960.471 | 529587.7568 | 17608572.48 | 4046285.3799 | 592884.4668 | 1392180.1955 | 1300615.6863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7331965.7284 | 48868758.0065 | 0 | 48868758.0065 | -3504770.1766 | 53250601.4831 | -4381843.4766 |  |  |  |  | 51407838.0607 | 2539080.0542
[12 empty] | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 0 | 0 | 0 | 0 | 0 | 0
Owner Supplied Equipment
[12 empty] | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 0 |  | 0 | 0 | 0 | 0
|  | Litostroj Hydro Inc |  | 11319000 | 11685600.2035 | 0 | 11685600.2035 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000 | 550000 | 0 | -276250 | 3014404.94 | 0 | -6439.53 | 526757.46 | -0.16 | 23749.88 | 0 | 544067.47 | 577805.73 | 577844 | 4981939.79 | 34181.08 | 0 | 627303.06 | 51872.06 | 1632202.41 | 1695627.3736 | 0 | 49353.67 | 160745.28 | 31336.56 | 0 | 121545.35 | 4404166.8436 | 1594066.31 | 0 | 88656.57 | 69546.8833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1752269.7633 | 11688376.3969 | 0 | 11688376.3969 | 2776.1934 | 11732343.5163 | -43967.1194 |  | 11775897.1282 | 87520.7312 |  | 11685600.46 | -2775.9369
|  | Base contract |  | 11319000 | 10881348.76 |  | 10881348.76 | 6400003746 | 10881349.4 |  |  | 2009 Total: 0; 2010 D: 550000; 2010 Total: 550000; 2011 J: 0; 2011 F: -276250; 2011 M: 3014404.94; 2011 A: 0; 2011 M: -6439.53; 2011 J: 526757.46; 2011 J: -0.16; 2011 A: 23749.88; 2011 O: 544067.47; 2011 N: 551273.44; 2011 D: 577844; 2011 Total: 4955407.5; 2012 J: -0.32; 2012 M: 544067; 2012 M: 1632202.41; 2012 J: 1632202.41; 2012 Total: 3808471.5; 2013 M: 0; 2013 J: 0; 2013 Total: 0 | 9313879 | 0 | 9313879 | -1567469.76 | 10855878.21 | -1541999.21 |  | 10881349.4 | 1567470.4 |  | 11685600.46 | 2371721.46
|  |  | CO 1 |  | 30099.0435 |  | 30099.0435 |  |  |  |  | 2009 Total: 0; 2010 Total: 0; 2011 J: 0; 2011 Total: 0; 2012 Total: 0; 2013 J: 0; 2013 Total: 0 | 0 | 0 | 0 | -30099.0435 | 30099.0435 | -30099.0435 |  | 30099.0435 | 30099.0435 |  | 0 | 0
|  |  | CO 2 | [8 empty] | 2009 Total: 0; 2010 Total: 0; 2011 J: 0; 2011 Total: 0; 2012 Total: 0; 2013 J: 0; 2013 Total: 0 | 0 | 0 | 0 | 0 | 1384.2892 | -1384.2892 |  | 30099.0435 | 30099.0435 |  | 0 | 0
|  |  | CO 3 | [8 empty] | 2009 Total: 0; 2010 Total: 0; 2011 J: 0; 2011 Total: 0; 2012 J: 22970.6436; 2012 S: 77058.44; 2012 Total: 100029.0836; 2013 J: 0; 2013 Total: 0 | 100029.0836 | 0 | 100029.0836 | 100029.0836 | 99114.2336 | 914.85 |  | 30099.0435 | -69930.0401 |  | 0 | -100029.0836
|  |  | CO 4 | [8 empty] | 2009 Total: 0; 2010 Total: 0; 2011 J: 0; 2011 Total: 0; 2012 J: 14033.54; 2012 Total: 14033.54; 2013 Total: 0 | 14033.54 | 0 | 14033.54 | 14033.54 | 14033.54 | 0 |  | 30099.0435 | 16065.5035 |  | 0 | -14033.54
|  |  | CO 5 | [8 empty] | 2009 Total: 0; 2010 Total: 0; 2011 J: 0; 2011 Total: 0; 2012 S: 42978.75; 2012 Total: 42978.75; 2013 J: 0; 2013 Total: 0 | 42978.75 | 0 | 42978.75 | 42978.75 | 42468.5 | 510.25 |  | 0 | -42978.75 |  | 0 | -42978.75
|  |  | Corporate accrual | [8 empty] | 2009 Total: 0; 2010 Total: 0; 2011 J: 0; 2011 Total: 0; 2012 Total: 0; 2013 J: 1542000; 2013 F: 0; 2013 M: 0; 2013 A: 0; 2013 M: 0; 2013 J: 0; 2013 Total: 1542000 | 1542000 | 0 | 1542000 | 1542000 | 0.3 | 1541999.7 |  | 0 | -1542000 |  | 0 | -1542000
|  | Technical Field Services |  |  | 774152.4 |  | 774152.4 |  |  |  |  | 2009 Total: 0; 2010 Total: 0; 2011 J: 0; 2011 N: 26532.29; 2011 Total: 26532.29; 2012 J: 34181.4; 2012 M: 83236.06; 2012 A: 51872.06; 2012 J: 26420.78; 2012 A: 49353.67; 2012 S: 40708.09; 2012 O: 31336.56; 2012 D: 121545.35; 2012 Total: 438653.97; 2013 J: 52066.31; 2013 M: 88656.57; 2013 A: 69546.8833; 2013 Total: 210269.7633 | 675456.0233 | 0 | 675456.0233 | -98696.3767 | 689365.4 | -13909.3767 |  | 774151.554 | 98695.5307 |  | 0 | -675456.0233
|  | HTG Controls |  | 1617000 | 5599999.7333 | 0 | 5599999.7333 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 243666.4 | 38952 | 0 | 0 | 282618.4 | 100607.2814 | 206537.6782 | 165230.1426 | 144576.3747 | 162823.2227 | 249486.8242 | 341218.6003 | 228728.1998 | 315442.9366 | 578428.7171 | 501905.769 | 653366.8832 | 3648352.63 | 340028.5301 | 500247.9632 | 252923.0445 | 248217.6887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1341417.2266 | 5272388.2565 | 0 | 5272388.2565 | -327611.4768 | 5789848.947 | -517460.6905 |  | 3273997.89 | -1998390.3665 |  | 4076000 | -1196388.2565
|  |  | CO 6 - Electrical Equipment and Control Engineering (CCD 007/020) | 0 | 1298399.7333 | 0 | 1298399.7333 |  |  |  |  | 2009 Total: 0; 2010 Total: 0; 2011 S: 243666.4; 2011 O: 38952; 2011 D: 0; 2011 Total: 282618.4; 2012 J: 100607.2814; 2012 F: 106128.0782; 2012 M: 165230.1426; 2012 A: 144576.3747; 2012 M: 144576.3747; 2012 J: 144576.3747; 2012 J: 103268.8391; 2012 A: 86367.945; 2012 S: 43183.9725; 2012 O: 43183.9725; 2012 N: 43183.9725; 2012 D: 185577.3365; 2012 Total: 1310460.6645; 2013 J: 108684.9199; 2013 F: 86367.945; 2013 M: 34547.178; 2013 A: 64698.2982; 2013 M: 0; 2013 J: 0; 2013 Total: 294298.3411 | 1887377.4056 | 0 | 1887377.4056 | 588977.6723 | 2031542.8144 | -144165.4088 |  | 2031543.782 | 144166.3764 |  | 0 | -1887377.4056
|  |  | CCD-007: Control/Integration LS Eng LNTP | [8 empty] | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 F: 100409.6; 2012 Total: 100409.6; 2013 Total: 0 | 100409.6 | 0 | 100409.6 | 100409.6 | 100409.6 | 0 |  | 0 | -100409.6 |  | 0 | -100409.6
|  |  | CO 7 - Accompanying various CP's | 0 | 0 | 0 | 0 |  |  |  |  | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 M: 0; 2012 Total: 0; 2013 Total: 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
|  |  | CP 046 - Add Unit #4 Exciter system | 0 | 0 | 0 | 0 |  |  |  |  | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 M: 0; 2012 J: 13906.8919; 2012 J: 27813.7838; 2012 O: 97348.2433; 2012 D: 111255.1352; 2012 Total: 250324.0542; 2013 A: 4635.6306; 2013 J: 0; 2013 Total: 4635.6306 | 254959.6848 | 0 | 254959.6848 | 254959.6848 | 278137.8422 | -23178.1574 |  | 278137.838 | 23178.1532 |  | 0 | -254959.6848
|  |  | CP 051 - Additional Hydraulic Analysis (ST Overflow Lk levels) | 0 | 0 | 0 | 0 |  |  |  |  | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 M: 0; 2012 M: 7952.159; 2012 J: 7952.159; 2012 Total: 15904.318; 2013 Total: 0 | 15904.318 | 0 | 15904.318 | 15904.318 | 15904.318 | 0 |  | 15904.318 | 0 |  | 0 | -15904.318
|  |  | CP 038 - HTG Bearing Cooler Heat Exchanger Type Exchange | 0 | 0 | 0 | 0 |  |  |  |  | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 M: 0; 2012 M: 5147.3445; 2012 J: 1715.7815; 2012 Total: 6863.126; 2013 Total: 0 | 6863.126 | 0 | 6863.126 | 6863.126 | 6863.126 | 0 |  | 6863.126 | 0 |  | 0 | -6863.126
|  |  | CP 039 - HTG Smoothing Air Valve Change | 0 | 0 | 0 | 0 |  |  |  |  | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 M: 0; 2012 M: 5147.3445; 2012 J: 1715.7815; 2012 Total: 6863.126; 2013 Total: 0 | 6863.126 | 0 | 6863.126 | 6863.126 | 6863.126 | 0 |  | 6863.126 | 0 |  | 0 | -6863.126
|  |  | CP 054 - Switchboard to switchgear change and DCN 14 | 0 | 0 | 0 | 0 |  |  |  |  | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 M: 0; 2012 J: 6082.6794; 2012 J: 6082.6794; 2012 A: 4055.1196; 2012 N: 24330.716; 2012 Total: 40551.1944; 2013 Total: 0 | 40551.1944 | 0 | 40551.1944 | 40551.1944 | 40551.1944 | 0 |  | 40551.196 | 0.0016 |  | 0 | -40551.1944
|  |  | CP 042 - Governor and HPU procurement | 0 | 0 | 0 | 0 |  |  |  |  | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 M: 0; 2012 J: 89413.4504; 2012 A: 44706.7252; 2012 S: 107296.1405; 2012 O: 71530.7603; 2012 N: 223533.626; 2012 D: 89413.4504; 2012 Total: 625894.1528; 2013 F: 178826.9008; 2013 M: 0; 2013 J: 0; 2013 Total: 178826.9008 | 804721.0536 | 0 | 804721.0536 | 804721.0536 | 894134.7628 | -89413.7092 |  | 894134.504 | 89413.4504 |  | 0 | -804721.0536
|  |  | CO 7 (CCD-007/CP-25): Supply only of Unit 3 & Unit 4 Control and Protection Panels | [8 empty] | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 J: 73537.1562; 2012 J: 73537.1562; 2012 A: 36768.5781; 2012 S: 161781.7436; 2012 O: 183842.8905; 2012 N: 183842.89; 2012 D: 7353.7156; 2012 Total: 720664.1303; 2013 J: 0; 2013 Total: 0 | 720664.1303 | 0 | 720664.1303 | 720664.1303 | 735371.5486 | -14707.4184 |  | 0 | -720664.1303 |  | 0 | -720664.1303
|  |  | CO 009 (CP 055.2, CP 056.2, CP 067): Machine conditioning monitoring, LBKU4 protection, Gen Line Cubicle and parts discharge system, additional switching, pushbuttons and RM Modules | [8 empty] | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 J: 41102.6914; 2012 S: 9650.0875; 2012 O: 182522.8505; 2012 N: 13510.1225; 2012 D: 13506.065; 2012 Total: 260291.8169; 2013 F: 75080.7915; 2013 M: 100372.3792; 2013 A: 56393.299; 2013 M: 0; 2013 J: 0; 2013 Total: 231846.4697 | 492138.2866 | 0 | 492138.2866 | 492138.2866 | 536492.5027 | -44354.2161 |  |  | -492138.2866 |  | 0 | -492138.2866
|  |  | CO 010 - Accompanying various CP's | 0 | 0 | 0 | 0 |  |  |  |  | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 M: 0; 2012 Total: 0; 2013 Total: 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
|  |  | CP 033.1 - Substation battery credit | [8 empty] | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 S: -45433.18; 2012 Total: -45433.18; 2013 Total: 0 | -45433.18 | 0 | -45433.18 | -45433.18 | -45433.18 | 0 |  |  | 45433.18 |  | 0 | 45433.18
|  |  | CP 063 - Motor control center charges | [8 empty] | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 A: 2700.8884; 2012 N: 13504.442; 2012 D: 10263.3759; 2012 Total: 26468.7063; 2013 A: 450.1481; 2013 Total: 450.1481 | 26918.8544 | 0 | 26918.8544 | 26918.8544 | 27008.8803 | -90.0259 |  |  | -26918.8544 |  | 0 | -26918.8544
|  |  | CP 064 - Unit 3 Governor and HPU installation | [8 empty] | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 M: 5211.8858; 2013 A: 73835.0488; 2013 J: 0; 2013 Total: 79046.9346 | 79046.9346 | 0 | 79046.9346 | 79046.9346 | 104237.7118 | -25190.7772 |  |  | -79046.9346 |  | 0 | -79046.9346
|  |  | CP 066 - Governor & HPU warranty & final equipment cost | [8 empty] | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 A: 12988.0575; 2012 S: 38964.1725; 2012 Total: 51952.23; 2013 Total: 0 | 51952.23 | 0 | 51952.23 | 51952.23 | 51952.23 | 0 |  |  | -51952.23 |  | 0 | -51952.23
|  |  | CP 072 - Change 13.8kV breaker 52/MT4 to Generator rated | [8 empty] | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 A: 44852.146; 2012 Total: 44852.146; 2013 Total: 0 | 44852.146 | 0 | 44852.146 | 44852.146 | 44852.146 | 0 |  |  | -44852.146 |  | 0 | -44852.146
|  |  | CP tbd - Corrections to CO 009 | [8 empty] | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 A: -3711.26; 2012 Total: -3711.26; 2013 J: 0; 2013 Total: 0 | -3711.26 | 0 | -3711.26 | -3711.26 | -4100.78 | 389.52 |  |  | 3711.26 |  | 0 | 3711.26
|  |  | CO 011 - Accompanying various CP's | 0 | 0 | 0 | 0 |  |  |  |  | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 M: 0; 2012 Total: 0; 2013 Total: 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
|  |  | CP 92 - Addition of excitation system watch dig relays | [8 empty] | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 D: 474.998; 2012 Total: 474.998; 2013 Total: 0 | 474.998 | 0 | 474.998 | 474.998 | 474.998 | 0 |  |  | -474.998 |  | 0 | -474.998
|  |  | CP 78 - OSE lifting eyes - turbine runner/runner shaft | [8 empty] | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 D: 663.266; 2012 Total: 663.266; 2013 Total: 0 | 663.266 | 0 | 663.266 | 663.266 | 663.266 | 0 |  |  | -663.266 |  | 0 | -663.266
|  |  | CP 109 - Everett street/Hwy 20 stockpile re-sloping | [8 empty] | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 D: 3882.216; 2012 Total: 3882.216; 2013 Total: 0 | 3882.216 | 0 | 3882.216 | 3882.216 | 3882.216 | 0 |  |  | -3882.216 |  | 0 | -3882.216
|  |  | CP 98 - Control panel supply changes - system interface | [8 empty] | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 D: 4478.398; 2012 Total: 4478.398; 2013 Total: 0 | 4478.398 | 0 | 4478.398 | 4478.398 | 4478.398 | 0 |  |  | -4478.398 |  | 0 | -4478.398
|  |  | CP 95 - Bilco access hatch for Surge Shaft Ltd | [8 empty] | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 D: 1651.132; 2012 Total: 1651.132; 2013 M: 4821.3054; 2013 J: 0; 2013 Total: 4821.3054 | 6472.4374 | 0 | 6472.4374 | 6472.4374 | 6604.6554 | -132.218 |  |  | -6472.4374 |  | 0 | -6472.4374
|  |  | CP 88 - Head cover fabrication & runner shaft seal | [8 empty] | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 D: 8462.322; 2012 Total: 8462.322; 2013 Total: 0 | 8462.322 | 0 | 8462.322 | 8462.322 | 8462.322 | 0 |  |  | -8462.322 |  | 0 | -8462.322
|  |  | CP 73 - Additional hydraulic for the smoothing air vent valve | [8 empty] | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 D: 4768.915; 2012 Total: 4768.915; 2013 J: 4577.942; 2013 J: 0; 2013 Total: 4577.942 | 9346.857 | 0 | 9346.857 | 9346.857 | 9537.6136 | -190.7566 |  |  | -9346.857 |  | 0 | -9346.857
|  |  | CP 107 - Change mount pad to copper windings | [8 empty] | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 D: 8186.953; 2012 Total: 8186.953; 2013 F: 4093.4765; 2013 M: 818.7; 2013 A: 682.2461; 2013 M: 0; 2013 J: 0; 2013 Total: 5594.4226 | 13781.3756 | 0 | 13781.3756 | 13781.3756 | 16373.906 | -2592.5304 |  |  | -13781.3756 |  | 0 | -13781.3756
|  |  | CP 36.1 - Scroll case water circulation and monitoring (partial) | [8 empty] | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 M: 0; 2013 Total: 0 | 0 | 0 | 0 | 0 | 4100.78 | -4100.78 |  |  | 0 |  | 0 | 0
|  |  | CP 90 - Draft tube gate hoist installation | [8 empty] | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 D: 3718.9422; 2012 Total: 3718.9422; 2013 J: 3718.834; 2013 F: 12396.474; 2013 M: 2479.2948; 2013 J: 0; 2013 Total: 18594.6028 | 22313.545 | 0 | 22313.545 | 22313.545 | 24792.791 | -2479.246 |  |  | -22313.545 |  | 0 | -22313.545
|  |  | CP 100 - Painting draft tube elbow | [8 empty] | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 F: 11891.4505; 2013 M: 26161.1911; 2013 A: 7134.8703; 2013 J: 0; 2013 Total: 45187.5119 | 45187.5119 | 0 | 45187.5119 | 45187.5119 | 47565.8031 | -2378.2912 |  |  | -45187.5119 |  | 0 | -45187.5119
|  |  | CP 48 - Standby generator system - design only | [8 empty] | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 D: 26417.03; 2012 Total: 26417.03; 2013 J: 25360.3488; 2013 J: 0; 2013 Total: 25360.3488 | 51777.3788 | 0 | 51777.3788 | 51777.3788 | 52834.09 | -1056.7112 |  |  | -51777.3788 |  | 0 | -51777.3788
|  |  | CP 103 - Installation of SBV hood | [8 empty] | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 D: 64991.412; 2012 Total: 64991.412; 2013 J: 81239.265; 2013 F: 8123.9265; 2013 J: 0; 2013 Total: 89363.1915 | 154354.6035 | 0 | 154354.6035 | 154354.6035 | 162478.942 | -8124.3385 |  |  | -154354.6035 |  | 0 | -154354.6035
|  |  | CP 74.1 - Increased complexity of I/O | [8 empty] | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 D: 16200; 2012 Total: 16200; 2013 J: 24345; 2013 F: 40575; 2013 M: 32460; 2013 A: 13525; 2013 M: 0; 2013 J: 0; 2013 Total: 110905 | 127105 | 0 | 127105 | 127105 | 162300 | -35195 |  |  | -127105 |  | 0 | -127105
|  |  | CP 47.2 - U3/U4 electrical 7 controls management | [8 empty] | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 D: 92102.2204; 2012 Total: 92102.2204; 2013 J: 92102.2204; 2013 F: 82891.9984; 2013 M: 46051.1102; 2013 A: 26863.1476; 2013 M: 0; 2013 J: 0; 2013 Total: 247908.4766 | 340010.697 | 0 | 340010.697 | 340010.697 | 460511.3226 | -120500.6256 |  |  | -340010.697 |  | 0 | -340010.697
[12 empty] | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  | 0 | 0
|  | TBD |  | 1617000 | 4301600 |  | 4301600 |  |  |  |  | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 0 | 0 | 0 | -4301600 | 0 | 0 |  |  | 0 |  | 4076000 | 4076000
|  | GSU Transformer - SPX Transformer Solutions |  | 754600 | 757400 |  | 757400 |  |  |  |  | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 M: 142446; 2012 J: 213669; 2012 S: 419585.49; 2012 Total: 775700.49; 2013 Total: 0 | 775700.49 | 0 | 775700.49 | 18300.49 | 775700.49 | 0 |  | 757400 | -18300.49 |  | 754600 | -21100.49
|  | Omega Morgan Rigging and Industrial | [9 empty] | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 O: 35389; 2012 Total: 35389; 2013 Total: 0 | 35389 | 0 | 35389 | 35389 | 35389 | 0 |  | 0 | -35389 |  | 754600 | 719211
|  | O&M Tools | [9 empty] | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 J: 0; 2013 Total: 0 | 0 | 0 | 0 | 0 | 50000 | -50000 |  | 757400 | 757400 |  | 754600 | 754600
| Total Owner Supplied Equipment |  |  | 13690600 | 18042999.9369 | 0 | 18042999.9369 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000 | 550000 | 0 | -276250 | 3014404.94 | 0 | -6439.53 | 526757.46 | -0.16 | 23749.88 | 243666.4 | 583019.47 | 577805.73 | 577844 | 5264558.19 | 134788.3614 | 206537.6782 | 792533.2026 | 196448.4347 | 1937471.6327 | 2158783.1978 | 341218.6003 | 278081.8698 | 895773.7066 | 645154.2771 | 501905.769 | 774912.2332 | 8863608.9636 | 1934094.8401 | 500247.9632 | 341579.6145 | 317764.5721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3093686.9899 | 17771854.1435 | 0 | 17771854.1435 | -271145.7934 | 18383281.9533 | -611427.8098 |  |  |  |  | 18025400.46 | 253546.3165
[12 empty] | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 |  | 0 | 0 | 0 | 0 | 0
Slope Stability
[12 empty] | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 0 |  | 0 | 0 | 0 | 0
|  | Stabilize Rock Slope - LB Powerhouse Road |  | 0 | 934082.93 | 0 | 934082.93 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8522.5 | 12535.25 | -2500.69 | 0 | 106621.362 | 216400 | 92504.508 | 0 | 0 | 434082.93 | 0 | 0 | 85662.64 | 0 | 16845.572 | 0 | 70330 | 0 | 0 | 131250 | 0 | 0 | 304088.212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 738171.142 | 0 | 738171.142 | -195911.788 | 743171.142 | -5000 |  | 2040258.152 | 1302087.01 |  | 5000000 | 4261828.858
|  |  | CO 2/CCD-003: Access road eco block installation | 0 | 52521.362 |  | 52521.362 |  |  |  |  | 2009 Total: 0; 2010 Total: 0; 2011 A: 52521.362; 2011 Total: 52521.362; 2012 Total: 0; 2013 Total: 0 | 52521.362 | 0 | 52521.362 | 0 | 52521.362 | 0 |  | 52521.362 | 0 |  |  | -52521.362
|  |  | CO 4/CCD-014: Slope scaling area 2 & 4 | 0 | 54100 |  | 54100 |  |  |  |  | 2009 Total: 0; 2010 Total: 0; 2011 A: 54100; 2011 Total: 54100; 2012 Total: 0; 2013 Total: 0 | 54100 | 0 | 54100 | 0 | 54100 | 0 |  | 54100 | 0 |  |  | -54100
|  |  | CO 4/CCD-016: Slope scaling area 5 & 7 | 0 | 308904.508 |  | 308904.508 |  |  |  |  | 2009 Total: 0; 2010 Total: 0; 2011 S: 216400; 2011 O: 92504.508; 2011 Total: 308904.508; 2012 Total: 0; 2013 Total: 0 | 308904.508 | 0 | 308904.508 | 0 | 308904.508 | 0 |  | 308904.508 | 0 |  |  | -308904.508
|  |  | CO 7/CP 040: Clean up area 6 & 7 slide on 2/22/2012 | 0 | 0 |  | 0 |  |  |  |  | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 M: 1732.282; 2012 Total: 1732.282; 2013 Total: 0 | 1732.282 | 0 | 1732.282 | 1732.282 | 1732.282 | 0 |  | 1732.282 | 0 |  |  | -1732.282
|  |  | CO 009 (CP 023): Slope stability mitigation along access road area 5 & 6 |  | 0 |  | 0 |  |  |  |  | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 J: 70330; 2012 Total: 70330; 2013 Total: 0 | 70330 | 0 | 70330 | 70330 | 70330 | 0 |  | 0 | -70330 |  |  | -70330
|  |  | GeoEngineers Inc |  | 10034.56 |  | 10034.56 | 4600005167 | 13409100 | Blanket agreement |  | 2009 Total: 0; 2010 Total: 0; 2011 M: 12535.25; 2011 J: -2500.69; 2011 Total: 10034.56; 2012 M: 85662.64; 2012 M: 15113.29; 2012 Total: 100775.93; 2013 Total: 0 | 110810.49 | 0 | 110810.49 | 100775.93 | 115810.49 | -5000 |  | 0 | -110810.49 |  |  | -110810.49
|  |  | Pacific Geomatic Services Inc | 0 | 8522.5 |  | 8522.5 | 6400002966 | 180000 | Active |  | 2009 Total: 0; 2010 Total: 0; 2011 A: 8522.5; 2011 Total: 8522.5; 2012 Total: 0; 2013 Total: 0 | 8522.5 | 0 | 8522.5 | 0 | 8522.5 | 0 |  | 0 | -8522.5 |  |  | -8522.5
|  |  | Rock monitoring and scaling - Hitec Rockwork | 0 | 125000 |  | 125000 |  |  |  |  | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 O: 131250; 2012 Total: 131250; 2013 M: 0; 2013 Total: 0 | 131250 | 0 | 131250 | 6250 | 131250 | 0 |  | 811500 | 680250 |  | 2500000 | 2368750
|  |  | Contingency - Additional monitoring, scaling, wire mesh | 0 | 375000 |  | 375000 |  |  |  |  | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 0 | 0 | 0 | -375000 | 0 | 0 |  | 811500 | 811500 |  | 2500000 | 2500000
|  | Potential Landslide Mitigation - E Slope |  | 0 | 2295485.272 | 0 | 2295485.272 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3809.51 | 0 | 3809.51 | 0 | 0 | 2947 | 18170.5 | 412242.97 | 10948.2 | -22531.23 | 983884.604 | 130149.34 | 7968.378 | 21724.03 | -803.91 | 1564699.882 | 104171.236 | 17501.58 | 16708.89 | 17411.9 | 21059.82 | 91456.61 | 20927.99 | 335188.402 | 22116.79 | 30066.83 | 8035.34 | 26414.2 | 711059.588 | -6795.11 | 0 | 22057.02 | 15448.2083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30710.1183 | 2310279.0983 | 0 | 2310279.0983 | 14793.8263 | 2529768.74 | -219489.6417 |  | 2416088.688 | 116941.0797 |  | 2503809.51 | 193530.4117
|  |  | CCD-001: Secant Piles/Slurry Wall/FERC/Vault Flip | 0 | 216400 |  | 216400 |  |  |  |  | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 J: 0; 2013 Total: 0 | 0 | 0 | 0 | -216400 | 216400 | -216400 |  | 216400 | 216400 |  |  | 0
|  |  | CO 2/CCD-012: Slope Drainage System Program | 0 | 252088.688 |  | 252088.688 |  |  |  |  | 2009 Total: 0; 2010 Total: 0; 2011 A: 225947.568; 2011 O: 26141.12; 2011 D: -26238.5; 2011 Total: 225850.188; 2012 Total: 0; 2013 Total: 0 | 225850.188 | 0 | 225850.188 | -26238.5 | 225850.188 | 0 |  | 252088.688 | 26238.5 |  |  | -225850.188
|  |  | CO 3/CCD-013: Slope Stabilization System (Buttress wall) | 0 | 734864.104 |  | 734864.104 |  |  |  |  | 2009 Total: 0; 2010 Total: 0; 2011 A: 703140.946; 2011 S: 81150; 2011 O: -49426.842; 2011 Total: 734864.104; 2012 J: 76635.896; 2012 Total: 76635.896; 2013 Total: 0 | 811500 | 0 | 811500 | 76635.896 | 811500 | 0 |  | 811500 | 0 |  |  | -811500
|  |  | CO 10/CCD-015/CP 035.1: Impact time extension - recovery schedule |  | 324600 |  | 324600 |  |  |  |  | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 A: 311443.962; 2012 Total: 311443.962; 2013 Total: 0 | 311443.962 | 0 | 311443.962 | -13156.038 | 311443.962 | 0 |  | 324600 | 13156.038 |  | 0 | -311443.962
|  |  | Shannon & Wilson | 0 | 487910.61 |  | 487910.61 | 4600004051 | 2900000 | Blanket agreement |  | 2009 Total: 0; 2010 Total: 0; 2011 M: 400000; 2011 J: 0; 2011 J: -27687.01; 2011 A: 45499.18; 2011 S: 43054.34; 2011 O: 27044.1; 2011 N: 19775.03; 2011 D: 15613.59; 2011 Total: 523299.23; 2012 J: 24643.84; 2012 F: 17501.58; 2012 M: 12831.39; 2012 A: 15591; 2012 M: 12111.02; 2012 J: 18340.23; 2012 J: 18340.23; 2012 A: 21744.44; 2012 O: 30066.83; 2012 N: 8035.34; 2012 D: 26414.2; 2012 Total: 205620.1; 2013 J: -6795.11; 2013 M: 22057.02; 2013 A: 15448.2083; 2013 M: 0; 2013 Total: 30710.1183 | 759629.4483 | 0 | 759629.4483 | 271718.8383 | 762719.09 | -3089.6417 |  | 0 | -759629.4483 |  |  | -759629.4483
|  |  | Pacific Geomatic Services Inc | 0 | 31772.2 |  | 31772.2 | 6400002966 | 180000 | Active |  | 2009 Total: 0; 2010 Total: 0; 2011 M: 2947; 2011 M: 2785; 2011 J: 3735.2; 2011 J: 3982; 2011 A: 8168; 2011 S: 5945; 2011 O: 4210; 2011 N: 1949; 2011 D: 9821; 2011 Total: 43542.2; 2012 J: 2891.5; 2012 M: 3877.5; 2012 A: 1820.9; 2012 M: 5490.8; 2012 J: 6785.35; 2012 J: 2000; 2012 A: 2000; 2012 Total: 24866.05; 2013 M: 0; 2013 Total: 0 | 68408.25 | 0 | 68408.25 | 36636.05 | 68408.25 | 0 |  | 0 | -68408.25 |  |  | -68408.25
|  |  | Mayes Testing Engineers Inc |  | 34841.47 |  | 34841.47 | 6400004008 | 215000 | Active |  | 2009 Total: 0; 2010 Total: 0; 2011 A: 18170.5; 2011 M: 9457.97; 2011 J: 7213; 2011 Total: 34841.47; 2012 Total: 0; 2013 Total: 0 | 34841.47 | 0 | 34841.47 | 0 | 34841.47 | 0 |  | 0 | -34841.47 |  |  | -34841.47
|  |  | Northwest Trails - access to monitoring points (tbd) |  | 117841 |  | 117841 | 4600005617 | 81000 | Active |  | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 J: 65357.5; 2012 S: 22116.79; 2012 Total: 87474.29; 2013 Total: 0 | 87474.29 | 0 | 87474.29 | -30366.71 | 87474.29 | 0 |  | 0 | -87474.29 |  |  | -87474.29
|  |  | Northwest Archaeological |  | 3809.51 |  | 3809.51 | 6400001807 | 1000000 | Blanket agreement |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 3809.51; 2010 D: 0; 2010 Total: 3809.51; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 3809.51 | 0 | 3809.51 | 0 | 3809.51 | 0 | 996190.49 |  |  |  | 3809.51 | 0
|  |  | SWCA Inc |  | 2302.69 |  | 2302.69 | 4600005512 | 673482 | Active |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 Total: 0; 2011 J: 1173.78; 2011 A: 1128.91; 2011 Total: 2302.69; 2012 M: 3458; 2012 J: 973.53; 2012 J: 587.76; 2012 Total: 5019.29; 2013 Total: 0 | 7321.98 | 0 | 7321.98 | 5019.29 | 7321.98 | 0 | 666160.02 |  |  |  | 0 | -7321.98
|  |  | Contingency Additional monitoring, dewatering, etc | 0 | 89055 |  | 89055 |  |  |  |  | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 0 | 0 | 0 | -89055 | 0 | 0 |  | 811500 | 811500 |  | 2500000 | 2500000
| Total Slope Stability |  |  | 0 | 3229568.202 | 0 | 3229568.202 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3809.51 | 0 | 3809.51 | 0 | 0 | 2947 | 26693 | 424778.22 | 8447.51 | -22531.23 | 1090505.966 | 346549.34 | 100472.886 | 21724.03 | -803.91 | 1998782.812 | 104171.236 | 17501.58 | 102371.53 | 17411.9 | 37905.392 | 91456.61 | 91257.99 | 335188.402 | 22116.79 | 161316.83 | 8035.34 | 26414.2 | 1015147.8 | -6795.11 | 0 | 22057.02 | 15448.2083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30710.1183 | 3048450.2403 | 0 | 3048450.2403 | -181117.9617 | 3272939.882 | -224489.6417 |  |  |  |  | 7503809.51 | 4455359.2697
[12 empty] | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PSE Costs
[12 empty] | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 |  |  | 0 | 0 | 0 | 0
|  | PSE Directs |  | 5669308 | 3886083.108 | 800000 | 4686083.108 |  |  |  | 0 | 2583.83 | 2522.18 | 1401.37 | 1660.96 | 5209.81 | 1766.91 | 9670.73 | 9120.33 | 15952.61 | 25039.51 | 28147.26 | 38118.22 | 141193.72 | 23671.86 | 25068.67 | 32389.72 | 39685.9 | 45948.8 | 77340.58 | 85532.58 | 75742.57 | 101308.21 | 99770.918 | 97745.12 | 100126.99 | 804331.918 | 60308.03 | 75237.89 | 86389.31 | 226161.43 | 152458.05 | 85782.39 | 73560.79 | 90351.04 | 81120.37 | 85432.17 | 103645.24 | 115068.91 | 1235515.62 | 70253.31 | 78950.43 | 95187.14 | 101064.59 | 76026.06 | 115665.16 | 88000.77 | 93685.4 | 92695.83 | 127742.36 | 111881.81 | 142565.61 | 1193718.47 | 165150.79 | 245060.33 | 253294 | 152284.5333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 815789.6533 | 4190549.3813 | 0 | 4190549.3813 | -495533.7267 | 4843799.3894 | -653250.0081 | -4190549.3813 |  |  |  | 3879643.858 | -310905.5233
|  |  | Labor | 5669308 | 3440401.7 | 800000 | 4240401.7 |  |  |  |  | 2471.68 | 2436.93 | 72.03 | 1536.52 | 4943.89 | 1552.42 | 7625.34 | 8579.42 | 13535.53 | 23594.71 | 22441.3 | 33830.39 | 122620.16 | 21934.27 | 22732.8 | 30163.6 | 36103.1 | 40666.86 | 68482.24 | 70932.15 | 68185.64 | 66807.48 | 68251.71 | 73857.3 | 66287.4 | 634404.55 | 55477.67 | 56412.98 | 72707.59 | 165975.27 | 88768.33 | 64493.92 | 59053.51 | 79423.53 | 69270.78 | 67978.41 | 70925.13 | 79612.79 | 930099.91 | 62136.64 | 65862.34 | 75155.71 | 73543.52 | 66330.15 | 84863.73 | 73139.35 | 74834.89 | 71628.22 | 92240.97 | 83862.72 | 95569.55 | 919167.79 | 110576.68 | 127870.15 | 198469.09 | 126425.8833 | 0 | 0 | 0 | [5 empty] | 563341.8033 | 3169634.2133 | 0 | 3169634.2133 | -1070767.4867 | 3782908.39 | -613274.1767 |  |  |  |  | 3527681.55 | 358047.3367
|  |  | Employee Expense |  | 127053.35 |  | 127053.35 |  |  |  |  | 76.32 | 28 | 1326.9 | 2.44 | 228.16 | 179.22 | 1902.57 | 304.86 | 1598.46 | 189.36 | 3891.46 | 2598.27 | 12326.02 | 396.36 | 1132.46 | 971.65 | 1123.26 | 2871.53 | 4331.3 | 12810.62 | 3345.77 | 2428.21 | 4006.36 | 1579.17 | 4588.83 | 39585.52 | 683.21 | 12667.65 | 2149.26 | 5222.88 | 11402.79 | 8571.46 | 7246.74 | 7430.94 | 6198.24 | 13568.64 | 20499.09 | 22657.21 | 118298.11 | 4099.57 | 7125.41 | 11178.93 | 13525.76 | 4149.85 | 11048.21 | 8713.97 | 10570.31 | 7166.57 | 10771.86 | 9750.7 | 8930.36 | 107031.5 | 5221.18 | 12234.43 | 35482.01 | 12180.175 | 0 | [7 empty] | 65117.795 | 342358.945 | 0 | 342358.945 | 215305.595 | 344794.98 | -2436.035 |  |  |  |  | 84037.33 | -258321.615
|  |  | Material |  | 138361.95 |  | 138361.95 |  |  |  |  | -2.63 | 0 | 0.01 | 49.65 | 1.87 | 0.91 | -20.28 | 66.94 | 7.47 | 52.96 | 1345.35 | 248.82 | 1751.07 | 654.17 | 201.22 | 36 | 1612.92 | 467.67 | 12.5 | 849.74 | 945.75 | 26201 | 23011.94 | 17296.8 | 22526.57 | 93816.28 | 4041.01 | 2657.1 | 2809.9 | 3938.76 | 21125.53 | 2879.74 | 3398.6 | 380.8 | 917.28 | 645.88 | 1680.18 | 6384.17 | 50858.95 | 1039.7 | 2069.48 | 3335.62 | 2338.64 | 817.57 | 1767.37 | 11598.33 |  | 7930.74 | 14610.21 | 12570.55 | 28595.3 | 86673.51 | 47713.46 | 100494.15 |  | 8293.3333 | 0 | [7 empty] | 156500.9433 | 389600.7533 | 0 | 389600.7533 | 251238.8033 | 391259.42 | -1658.6667 |  |  |  |  | 130139.65 | -259461.1033
|  |  | Miscellaneous Expense |  | 3878.728 |  | 3878.728 |  |  |  |  | 0 | 0 | 1.67 | 2.94 | 0 | 0.1 | 1.28 | 0 | 40.33 | 73.76 | 15.14 | 137.93 | 273.15 | 58.24 | 272.89 | 325.93 | 170.71 | 227.94 | 1762.21 | -1237.11 | 737.65 | 1291.23 | -609.112 | 789.82 | 2113.88 | 5904.278 | -1277.06 | 562.43 | 3047.71 | 1093.26 | -7584.42 | 167.33 | 662.55 | 123.93 | 811.26 | 94.31 | 998.49 | 920.41 | -379.8 | 303.12 | 967.69 | 984.05 | -511.59 | 727.72 | 12224.35 | -9979.99 |  | 2414.27 | -1101.64 | 667.19 | 2375.2 | 9070.37 | -1481.26 | 1076.18 | 3877.04 | -1882.975 | 0 | [7 empty] | 1588.985 | 16456.983 | 0 | 16456.983 | 12578.255 | 16080.388 | 376.595 |  |  |  |  | 2019.348 | -14437.635
|  |  | Insurance, Injuries |  | 34791.14 |  | 34791.14 |  |  |  |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 Total: 0; 2010 Total: 0; 2011 M: 94.17; 2011 A: 1.97; 2011 M: 34695; 2011 D: 0.92; 2011 Total: 34792.06; 2012 A: 5612; 2012 D: 2.44; 2012 Total: 5614.44; 2013 J: 9.22; 2013 F: 29.41; 2013 M: 36.56; 2013 Total: 75.19 | 40481.69 | 0 | 40481.69 | 5690.55 | 40481.69 | 0 |  |  |  |  | 34791.14 | -5690.55
|  |  | Advertising |  | 865.88 |  | 865.88 |  |  |  |  | 6.39 | 0 | 0 | 8.93 | 0 | 0 | 0.08 | 0 | 0.17 | 0 | 0 | 0 | 15.57 | 0 | 53.86 | 8.57 | 0 | 14.02 | 0 | 0 | 176.41 |  |  |  |  | 252.86 | 29.98 | 1.97 | 73.39 | 156.55 |  | 20.69 | 79.84 | 31.44 | 54.54 | 149.05 | 1.68 | 113.99 | 713.12 | 0.37 | 462.74 |  |  | 1.4 | 3.56 | 38.44 |  | 128.19 | 205.51 |  |  | 840.21 |  | 0.54 | 65.08 | 27.6833 | [8 empty] | 93.3033 | 1915.0633 | 0 | 1915.0633 | 1049.1833 | 1920.6 | -5.5367 |  |  |  |  | 530.32 | -1384.7433
|  |  | Employee Training |  | 14670.44 |  | 14670.44 |  |  |  |  | 0 | 0 | 0 | 0 | 1.59 | 10.17 | 17.35 | 22.29 | 424.8 | 783.5 | 30.81 | 237.88 | 1528.39 | 0 | 127.95 | 97.32 | 65.04 | 27.66 | 1.7 | 54.23 | 203.5 | 292.84 | 138.58 | 57.27 | 459.55 | 1525.64 | 209.93 | 341.82 | 227.49 | 3067.84 | 1926.99 | 3362.06 | 1395.99 | 296.42 | 476.46 | 311.41 | 54.33 | 295.55 | 11966.29 | 207.24 | 941.71 | 508.78 | 1756.19 | 1389.61 | 1462.95 | 1483.63 | 1357.26 | 489.88 | 609.14 | 1298.31 | 160.28 | 11664.98 | 71.79 | 766.07 | 1816.78 | 282.1417 | 0 | [7 empty] | 2936.7817 | 29622.0817 | 0 | 29622.0817 | 14951.6417 | 29678.51 | -56.4283 |  |  |  |  | 8828.1 | -20793.9817
|  |  | Office and Supplies |  | 35149.26 |  | 35149.26 |  |  |  |  | 32.07 | 57.25 | 0.1 | 52.85 | 34.3 | 21.98 | 142.6 | 135.22 | 342.72 | 345.22 | 361.89 | 1021.45 | 2547.65 | 625.2 | 501.41 | 700.97 | 606.65 | 1481.51 | 2259.73 | 2122.95 | 2119.18 | 2823.3 | 1368.89 | 3871.95 | 1883 | 20364.74 | 96.41 | 1034.92 | 1632.47 | 2272.92 | 1073.28 | 962.58 | 597.36 | 842.41 | 2434.54 | 1289.98 | 2053.95 | 1867 | 16157.82 | 1285.37 | 488.33 | 1868.14 | 1966.87 | 1579.56 | 894.84 | 910.19 | 930.1 | 1272.68 | 1747.86 | 1595 | 2367.11 | 16906.05 | 1348.27 | 1272.23 | 1610.84 | 2818.5083 | 0 | [7 empty] | 7049.8483 | 63026.1083 | 0 | 63026.1083 | 27876.8483 | 63589.81 | -563.7017 |  |  |  |  | 29022.39 | -34003.7183
|  |  | Phone Expense |  | 10178.6 |  | 10178.6 |  |  |  |  | 2009 Total: 0; 2010 Total: 0; 2011 J: 827.71; 2011 F: 625.39; 2011 M: 1361.37; 2011 A: 1372.06; 2011 M: 957.94; 2011 J: 862.95; 2011 J: 675.26; 2011 A: 1211.09; 2011 S: 892.25; 2011 O: 1392.58; 2011 N: 1062.86; 2011 D: 1385.66; 2011 Total: 12627.12; 2012 J: 1034.98; 2012 F: 1001.81; 2012 M: 1248.22; 2012 A: 991.41; 2012 M: 1012.95; 2012 J: 2834.16; 2012 J: 500.38; 2012 A: 958.61; 2012 S: 1254; 2012 O: 1073.62; 2012 N: 1101.56; 2012 D: 1135.03; 2012 Total: 14146.73; 2013 J: 999.16; 2013 M: 1647.61; 2013 A: 1315.0583; 2013 M: 0; 2013 Total: 3961.8283 | 30735.6783 | 0 | 30735.6783 | 20557.0783 | 30998.69 | -263.0117 |  |  |  |  | 5144.47 | -25591.2083
|  |  | Regulatory Fees and Permits |  | 46185.3 |  | 46185.3 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1.19 | 240.97 |  | 180 | 25 | 447.16 |  | 518.52 | 1246.45 | 42935.19 |  | 723.16 | 312.34 |  | 1.54 | 0.94 | 520.33 | 28.35 | 46286.82 | 1.76 |  |  |  | 2.19 |  | 519 | 938.5 | -938.5 | 205.24 |  |  | 728.19 | 1.19 | 0.11 | 3.92 | 11.675 | [8 empty] | 16.895 | 47479.065 | 0 | 47479.065 | 1293.765 | 47481.4 | -2.335 |  |  |  |  | 45147.32 | -2331.745
|  |  | Software and Hardware |  | 12202.76 |  | 12202.76 |  |  |  |  | 0 | 0 | 0.66 | 7.63 | 0 | 1.44 | 1.81 | 0.33 | 2.73 | 0 | 59.47 | 2.38 | 76.45 | 0 | 24.69 | 75.08 | 4.22 | 191.61 | 83.52 | 0 | 23.97 | 232.76 | 3602.82 | 109.62 | 1649.01 | 5997.3 | 219.1 | 415.11 | 1038.96 | 0.28 | 58.02 | 3674.89 | 50.34 | 610.48 | 61.83 |  | 5848.64 | 1686.08 | 13663.73 | 75.79 | 29.1 | 907.69 | 1751.96 | 15.06 | 266.82 | 687.47 | 197.54 | 85.66 | 2524.38 |  | 3069.82 | 9611.29 | 690.16 | 377.21 | 618.03 | 2.2167 | 0 | [7 empty] | 1687.6167 | 31036.3867 | 0 | 31036.3867 | 18833.6267 | 31036.83 | -0.44333 |  |  |  |  | 7805.22 | -23231.1667
|  |  | Rent/Lease |  | 2403 |  | 2403 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.67 | -0.02 | 11.27 | 0.4 | 0 | 1.84 | 41.1 | 55.26 | 3.62 | 21.39 | 10.6 | 0 | 0 | 407.38 | 0 | 3.51 | 990.42 | -0.27 | 3.19 | 593.75 | 2033.59 | 0.07 |  | 0.55 | 124.45 | 34.59 | 63.61 | 88.26 |  | 1.65 | 0.97 | 0.56 | 116.78 | 431.49 | 68.77 | 1.82 |  | 89.83 |  | 299.17 | 390 | 3898.19 | 1264.12 | 4855.21 | 1035.78 | 360.52 | 12263.41 | 0.94 | 939.85 | 9667.04 | 2810.8333 | 0 | [7 empty] | 13418.6633 | 28202.4133 | 0 | 28202.4133 | 25799.4133 | 28764.58 | -562.1667 |  |  |  |  | 2248.51 | -25953.9033
|  |  | to be awarded |  | 19941 |  | 19941 |  |  |  |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 J: 0; 2013 J: 0; 2013 Total: 0 | 0 | 0 | 0 | -19941 | 34804.1014 | -34804.1014 |  |  |  |  | 2248.51 | 2248.51
[12 empty] | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
|  | Overheads |  | 1589665 | 3844066.0292 | 700000 | 4544066.0292 |  |  |  | 0 | 2563.1 | 4266.35 | 353.89 | 1635.56 | 4087.35 | 1655.85 | 8235.09 | 8292.91 | 11773.65 | 18930.4 | 19077.99 | 43702.05 | 124574.19 | 18752.85 | 45664.48 | 28331.21 | 36188.22 | 46123.82 | 71167.95 | 82205.91 | 67557.98 | 75511.53 | 102079 | 89146.04 | 104927.26 | 767656.25 | 54552.7 | 99852.41 | 141296.87 | 187586.89 | 132540.46 | 86931.19 | 104533.45 | 84056.1 | 76617.96 | 76547.82 | 76315.21 | 124489.05 | 1245320.11 | 90325.77 | 94919.04 | 112954.58 | 119033.04 | 130194.44 | 184292.02 | 17172.39 | 93612.48 | 174742.75 | 152717.92 | 47263.38 | 128016.78 | 1345244.59 | 176462.04 | 168478.72 | 235203.3 | 149387.975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 729532.035 | 4212327.175 | 0 | 4212327.175 | -331738.8542 | 4787519.5293 | -575192.3543 | 0 | 0 | 0 | 0 | 2419118.8078 | -1793208.3672
|  |  | OH Construction | 751889 | 1826470.6192 |  | 1826470.6192 |  |  |  |  | 1022.99 | 2685 | 309.32 | 667.9 | 1126.9 | 728.07 | 3589.7 | 3146.37 | 3630.58 | 4169.89 | 5178.25 | 23682.77 | 49937.74 | 4737.39 | 31142.05 | 9037.75 | 16534.06 | 20017.36 | 29332.13 | 36519.33 | 27358.53 | 29979.84 | 55459.14 | 41609.36 | 74767.81 | 376494.75 | 20871.43 | 65880.88 | 97268.1 | 89787.35 | 79943.67 | 48595.73 | 40215.1 | 36968.06 | 35511.33 | 35432.66 | 33833.88 | 76858.28 | 661166.47 | 48026.96 | 49236.43 | 61272.92 | 68505.73 | 84621.7 | 126879.6 | -33055.1 | 42435.34 | 125991.74 | 85302.29 | -11757.18 | 61294.47 | 708754.9 | 95593.52 | 69583.19 | 95484.83 | 59285.7917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 319947.3317 | 2116301.1917 | 0 | 2116301.1917 | 289830.5724 | 2318481.0415 | -202179.8498 |  |  |  |  | 1341545.7078 | -774755.4839
|  |  | OH Labor | 837776 | 1972153.02 | 700000 | 2672153.02 |  |  |  |  | 1479.81 | 1581.35 | 44.57 | 915.75 | 2955.33 | 924.35 | 4550.96 | 5126.93 | 8101.32 | 14043.71 | 13337.04 | 19929.12 | 72990.24 | 13816.66 | 14291.3 | 18991.44 | 22711.57 | 25574.4 | 40967.48 | 44566.59 | 42036 | 41468.63 | 42578.59 | 44988.53 | 40802.03 | 392793.22 | 32601.32 | 33062.38 | 42367.78 | 94117.56 | 50753.97 | 37130.08 | 33809.73 | 45452.66 | 39716.88 | 39601.28 | 41340.82 | 46317.8 | 536272.26 | 40581.41 | 43970.09 | 50152.04 | 49138.74 | 44232.28 | 54765.71 | 48470.04 | 48885.01 | 46648.44 | 60437.02 | 55239.3 | 61536.84 | 604056.92 | 77125.91 | 86467.67 | 129423.19 | 83442.3833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 376459.1533 | 1982571.7933 | 0 | 1982571.7933 | -689581.2267 | 2354252.3378 | -371680.5445 |  |  |  |  | 1068383.72 | -914188.0733
|  |  | OH Material |  | 8386.06 |  | 8386.06 |  |  |  |  | 0 | 0 | 0 | 0.05 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.06 | 0 | 0 | 0.01 | 0.01 | 0.03 | 0.01 | 0.01 | 2.19 | 2267.34 | 2615.21 | 1264.44 | 1801.87 | 7951.12 | 16.44 | 2.47 | 0.38 | 72.71 | 210.75 | 86.46 | 31.02 |  | 0.3 | 14.35 | 80.78 | 536.63 | 1052.29 | 19.87 | 17.66 | 14.41 | 10.92 | 45 | 12.94 | 0.16 | 9.15 | 38.97 | 1230.52 | 61.04 | 1281.79 | 2742.43 | 190.11 | 4797.95 | 344.1 | 259.45 | 0 | [7 empty] | 5591.61 | 17337.51 | 0 | 17337.51 | 8951.45 | 17389.4 | -51.89 |  |  |  |  | 8253.93 | -9083.58
|  |  | OH Transportation |  | 29076.33 |  | 29076.33 |  |  |  |  | 60.3 | 0 | 0 | 51.86 | 5.11 | 3.42 | 90.24 | 19.61 | 41.75 | 716.8 | 562.7 | 90.16 | 1641.95 | 198.8 | 231.13 | 302.01 | 516.3 | 532.03 | 867.97 | 1136.02 | 1646.22 | 1793.96 | 1424.2 | 1282.57 | 2160.1 | 12091.31 | 1058.57 | 905.28 | 1660.61 | 3586.17 | 1631.45 | 1118.91 | 857.72 | 1635.38 | 1389.45 | 1499.53 | 1057.47 | 774.88 | 17175.42 | 1696.99 | 1694.84 | 1514.73 | 1377.65 | 1897.21 | 2632.46 | 1757.29 | 2282.82 | 2063.6 | 5737.39 | 3717.31 | 3884.31 | 30256.6 | 5418.75 | 7626.44 | 9936.77 | 5954.1667 | 0 | [7 empty] | 28936.1267 | 90101.4067 | 0 | 90101.4067 | 61025.0767 | 91292.24 | -1190.8333 |  |  |  |  | 22575.34 | -67526.0667
|  |  | OH Small Tools |  | 12.9 |  | 12.9 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15 | 0.04 | 0.7 | 1.86 | 1.14 | 0.01 | 3.9 | 4.94 | 0.01 |  | 3.41 | 0.62 | 0.01 |  |  |  |  | 2.26 |  | 11.25 | 0.54 | 0.02 | 0.48 |  |  | 1.31 |  | 0.05 |  |  | 2.91 | 3.24 | 8.55 | 4.37 | 3.47 | 12.71 |  | 0 | [7 empty] | 20.55 | 44.26 | 0 | 44.26 | 31.36 | 44.26 | 0 |  |  |  |  | 12.89 | -31.37
|  |  | Unassigned Cost Elements |  | 26050.35 |  | 26050.35 |  |  |  |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 4.19; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 4.19; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: -3573.72; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 Total: -3573.72; 2011 J: 29619.88; 2011 Total: 29619.88; 2012 Total: 0; 2013 M: 1.41; 2013 A: 446.1833; 2013 Total: 447.5933 | 26497.9433 | 0 | 26497.9433 | 447.5933 | 26587.18 | -89.2367 |  |  |  |  | -3569.53 | -30067.4733
|  |  | CLX/C.A.R.S. System |  | -3478.69 |  | -3478.69 |  |  |  |  | 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0.36; 2010 J: -16.19; 2010 A: -3485; 2010 S: 1.06; 2010 Total: -3499.77; 2011 F: 1.39; 2011 A: 19.69; 2011 D: 1.46; 2011 Total: 22.54; 2012 M: -601.75; 2012 A: 0.11; 2012 O: 10.7; 2012 D: 16.13; 2012 Total: -574.81; 2013 J: -1870.62; 2013 M: 0.29; 2013 M: 0; 2013 Total: -1870.33 | -5922.37 | 0 | -5922.37 | -2443.68 | -5922.37 | 0 |  |  |  |  | -3478.69 | 2443.68
|  |  | Precapatilized (Non-Transfer) |  | -14604.56 |  | -14604.56 |  |  |  |  | 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 D: -14604.56; 2010 Total: -14604.56; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | -14604.56 | 0 | -14604.56 | 0 | -14604.56 | 0 |  |  |  |  | -14604.56 | 0
[12 empty] | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
|  | Consultants |  | 0 | 196499.69 | 0 | 196499.69 |  |  |  | 0 | 1520 | 2310 | 0 | 1855 | 2725 | 1615 | 3800 | 0 | 2324.03 | 0 | 0 | 0 | 16149.03 | 637.04 | 0 | 8970.68 | 7587.8 | 8604.01 | 2375.7 | 1110.15 | 0 | 4736.4 | 4373.58 | 0 | 8150.34 | 46545.7 | 4941.27 | 2359.5 | 5693.38 | 23842.57 | 12444.85 | 4976.57 | 5547.28 | 0 | 6235.54 | 0 | 252.5 | 9570 | 75863.46 | 26375 | 5436.63 | 5203.9 | 3904 | 8134 | 5663.6 | 0 | 10701.34 | 13442.45 | 5051.01 | 7361.01 | 8998.89 | 100271.83 | 6211.01 | 7645 | 11199.88 | 4565.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29621.04 | 268451.06 | 0 | 268451.06 | 71951.37 | 293060.11 | -24609.05 |  |  |  |  | 254958 | -13493.06
|  |  | Project Controls |  | 143591.19 |  | 143591.19 |  |  |  |  | 1520 | 2310 | 0 | 1855 | 2725 | 1615 | 3800 | 0 | 2324.03 | 0 | 0 | 0 | 16149.03 | 637.04 | 0 | 606.26 | 2613.61 | 0 | 2375.7 | 1110.15 | 0 | 4736.4 | 4373.58 | 0 | 8125.62 | 24578.36 | 4843.27 | 2359.5 | 1316 | 6086.07 | 3460.6 | 5282.04 | 5516.78 | 0 | 6235.54 |  |  | 9570 | 44669.8 | 26375 | 4756 | 3594 | 4399 | 8134 | 5663.6 |  | 6264.34 | 13442.45 | 5051.01 | 7361.01 | 8998.89 | 94039.3 | 6211.01 | 7645 | 11199.88 | 4565.15 | 0 | 0 | 0 | [5 empty] | 29621.04 | 209057.53 | 0 | 209057.53 | 65466.34 | 233666.58 | -24609.05 | -209057.53 |  |  |  | 139292.83 | -69764.7
|  |  | Perkins Coie LLP |  | 30965.88 |  | 30965.88 | 4600003709 | 72000000 | Blanket agreement |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 24.72; 2010 Total: 24.72; 2011 J: 98; 2011 M: 4377.38; 2011 A: 17756.5; 2011 M: 8984.25; 2011 J: -305.47; 2011 J: 30.5; 2011 N: 252.5; 2011 Total: 31193.66; 2012 Total: 0; 2013 Total: 0 | 31218.38 | 0 | 31218.38 | 252.5 | 31218.38 | 0 | 71968781.62 |  |  |  | 31240.85 | 22.47
|  |  | Baker & Botts LLP | [8 empty] | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 Total: 0; 2011 Total: 0; 2012 A: 4437; 2012 Total: 4437; 2013 Total: 0 | 4437 | 0 | 4437 | 4437 | 4437 | 0 | -4437 |  |  |  | 31240.85 | 26803.85
|  |  | Dewey & LeBoeuf | [8 empty] | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 Total: 0; 2011 Total: 0; 2012 F: 680.63; 2012 M: 1609.9; 2012 A: -495; 2012 Total: 1795.53; 2013 Total: 0 | 1795.53 | 0 | 1795.53 | 1795.53 | 1795.53 | 0 | -1795.53 |  |  |  | 31240.85 | 29445.32
|  |  | Volt |  | 21942.62 |  | 21942.62 |  |  | Blanket Service Agr |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 8364.42; 2010 A: 4974.19; 2010 M: 8604.01; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 21942.62; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 21942.62 | 0 | 21942.62 | 0 | 21942.62 | 0 | -21942.62 |  |  |  | 21942.62 | 0
|  | Assessments, Transfers, etc |  | 0 | 23880.32 | 0 | 23880.32 |  |  |  | 0 | 0.32 | 0 | 0 | 6.34 | -2740.06 | 21.04 | 121.64 | 208.96 | -216.69 | 730.88 | 632.73 | 1733.83 | 498.99 | 401.08 | 1342.45 | 159.43 | 4941.07 | -4385.34 | 1121.22 | 281934.18 | -278036.36 | 3204.35 | -915.4 | 3996.47 | 220.62 | 13983.77 | -185.46 | 553.66 | 150381.03 | -149679.61 | 3407.53 | -1070.45 | 177.75 | 41.05 | 884.79 | 137.27 | 1367.4 | 1245.65 | 7260.61 | 344.7 | 1318.09 | 781.34 | 1512.38 | 699.21 | -27.77 | 2367.32 | 1596.44 | 1127.28 | 787.86 | 15145.73 | 10959.93 | 36612.51 | 3797.91 | 4714.04 | 18835.06 | 8200.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35547.635 | 93903.515 | 0 | 93903.515 | 70023.195 | 96543.64 | -2640.125 |  |  |  |  | 752628.16 | 658724.645
|  |  | Outside Services - Capital Accrual |  | 4908.67 |  | 4908.67 |  |  |  | 0 | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 322.65; 2010 A: 4866.64; 2010 M: -5189.29; 2010 J: 39.9; 2010 J: 280454.1; 2010 A: -279189.62; 2010 S: 2102.98; 2010 O: -1783.54; 2010 N: 3284.85; 2010 D: 0; 2010 Total: 4908.67; 2011 M: 150000; 2011 A: -150000; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 4908.67 | 0 | 4908.67 | 0 | 4908.67 | 0 |  |  |  |  | 4908.67 | 0
|  |  | Outside Services Other Transfer - P/P/C |  | -3516 |  | -3516 |  |  |  |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: -3516; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: -3516; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | -3516 | 0 | -3516 | 0 | -3516 | 0 |  |  |  |  | -3516 | 0
|  |  | Outside Services Other Transfer - Material | [8 empty] | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 N: 0; 2009 D: 0; 2009 Total: 0; 2010 J: 0; 2010 F: 0; 2010 M: 0; 2010 A: 0; 2010 M: 0; 2010 J: 0; 2010 J: 0; 2010 A: 0; 2010 S: 0; 2010 O: 0; 2010 N: 0; 2010 D: 0; 2010 Total: 0; 2011 Total: 0; 2012 N: 10498.17; 2012 Total: 10498.17; 2013 Total: 0 | 10498.17 | 0 | 10498.17 | 10498.17 | 10498.17 | 0 |  |  |  |  | 0 | -10498.17
|  |  | Outside Services Legal - Assessment |  | 4407.8 |  | 4407.8 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 304.37 | 304.37 | 0 | 164.68 | 0 | 61.68 | 44.07 | 0 | 692.82 | 107.91 | 237.37 | 326.25 | 238.37 | 69.45 | 1942.6 | -98 | 128.8 | 86.48 | 73.95 | 3122.5 | -1292.68 |  |  | 139.78 |  |  | -3.12 | 2157.71 | [12 empty] | 0 |  | 4026.98 | 6595.78 | 6545.5417 | [8 empty] | 17168.3017 | 21572.9817 | 0 | 21572.9817 | 17165.1817 | 22882.09 | -1309.1083 |  |  |  |  | 5560.7 | -16012.2817
|  |  | Outside Services Other - Assessment |  | 10473.72 |  | 10473.72 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47.8 | 0 | 47.8 | 0 | 0 | 0.93 | 0.15 | 638.16 | 508.88 | 787.26 | 1025.28 | 303.72 | -156.03 | 323.63 | 104.27 | 3536.25 | -92.81 | 421.48 | 252.25 | 244.88 | 273.84 | 183.37 | 166.53 | 39.1 | 520.44 | 130.59 | 1363.23 | 1099.24 | 4602.14 | 344.4 | 1302.95 | 761.25 | 1512.38 | 671.6 | -27.77 | 2367.32 | 1128.63 | 1125.86 | 787.86 | 4620.85 | 10933.63 | 25528.96 | 3784.02 | 611.92 | 12032.42 | 1655.0833 | 0 | [7 empty] | 18083.4433 | 51798.5933 | 0 | 51798.5933 | 41324.8733 | 53129.61 | -1331.0167 |  |  |  |  | 738351.94 | 686553.3467
|  |  | Outside Svc-Providers Field - Assessment |  | 7606.13 |  | 7606.13 |  |  |  | 0 | 0.32 | 0 | 0 | 6.34 | 775.94 | 21.04 | 121.64 | 208.96 | -216.69 | 730.88 | 584.93 | 1429.46 | 3662.82 | 401.08 | 1177.77 | -164.15 | 12.6 | 121.72 | 572.44 | 0 | 20.07 | 560.28 | 697.92 | 149.62 | 46.9 | 3596.25 | 5.35 | 3.38 | 42.3 | 1.56 | 11.19 | 38.86 | 11.22 | 1.95 | 224.57 | 6.68 | 4.17 | 149.53 | 500.76 | 0.3 | 15.14 | 20.09 |  | 27.61 |  |  | 467.81 | 1.42 |  | 26.71 | 26.3 | 585.38 | 13.89 | 75.14 | 206.86 |  | 0 | [7 empty] | 295.89 | 8641.1 | 0 | 8641.1 | 1034.97 | 8641.1 | 0 |  |  |  |  | 7322.85 | -1318.25
| Total PSE Costs |  |  | 7258973 | 7950529.1472 | 1500000 | 9450529.1472 |  |  |  | 0 | 6667.25 | 9098.53 | 1755.26 | 5157.86 | 9282.1 | 5058.8 | 21827.46 | 17622.2 | 29833.6 | 44700.79 | 47857.98 | 83554.1 | 282415.93 | 43462.83 | 72075.6 | 69851.04 | 88402.99 | 96291.29 | 152005.45 | 450782.82 | -134735.81 | 184760.49 | 205308.098 | 190887.63 | 213425.21 | 1632517.638 | 119616.54 | 178003.46 | 383760.59 | 287911.28 | 300850.89 | 176619.7 | 183819.27 | 174448.19 | 164858.66 | 162117.26 | 181580.35 | 250373.61 | 2563959.8 | 187298.78 | 180624.19 | 214126.96 | 225514.01 | 215053.71 | 305593.01 | 107540.48 | 199595.66 | 282008.31 | 286299.15 | 181651.93 | 290541.21 | 2675847.4 | 351621.75 | 425898.09 | 518532.24 | 314438.2833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1610490.3633 | 8765231.1313 | 0 | 8765231.1313 | -685298.0159 | 10020922.6687 | -1255691.5373 |  |  |  |  | 7306348.8258 | -1458882.3056
[24 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| Commissioning |  |  | 500000 | 500000 | 0 | 500000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11441.94 | 0 | 0 | 2416.22 | 17807.6 | 67681.48 | 99347.24 | 10388.61 | 22569.77 | 20651.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53609.89 | 152957.13 | 0 | 152957.13 | -347042.87 | 375272.7273 | -222315.5973 |  |  |  |  | 500000 | 347042.87
|  |  | McMillen (Jack Snyder) | 425000 | 425000 |  | 425000 |  |  |  | 0 | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 J: 11441.94; 2012 O: 2416.22; 2012 N: 17807.6; 2012 D: 11440; 2012 Total: 43105.76; 2013 J: 10388.61; 2013 F: 19119.77; 2013 M: 20651.51; 2013 M: 0; 2013 J: 0; 2013 J: 0; 2013 Total: 50159.89 | 93265.65 | 0 | 93265.65 | -331734.35 | 315581.2473 | -222315.5973 |  |  |  |  | 5560.7 | -87704.95
|  |  | HydroInsight | [8 empty] | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 D: 56241.48; 2012 Total: 56241.48; 2013 F: 3450; 2013 Total: 3450 | 59691.48 | 0 | 59691.48 | 59691.48 | 59691.48 | 0 |  |  |  |  | 738351.94 | 678660.46
|  |  | tbd | 75000 | 75000 |  | 75000 |  |  |  |  | 2009 J: 0; 2009 F: 0; 2009 M: 0; 2009 A: 0; 2009 M: 0; 2009 J: 0; 2009 J: 0; 2009 A: 0; 2009 S: 0; 2009 O: 0; 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 0 | 0 | 0 | -75000 | 0 | 0 |  |  |  |  | 738351.94 | 738351.94
[24 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| Contingency |  |  | 4209902 | 2420210 |  | 2420210 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  | 0 |  |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | -2420210 | 956827 | -956827 |  |  |  |  | 1888244 | 1888244
[12 empty] | 2009 Total: 0; 2010 Total: 0; 2011 Total: 0; 2012 Total: 0; 2013 Total: 0 | 0 | 0 | 0 | 0 | 0 | 0 | old budget | Budget | Forecast delta
| Subtotal Project |  |  | 83106972.61 | 90239948.5791 | 4000000 | 94239948.5791 |  |  |  | 2356875.83 | 7416.7 | 26222.74 | 5934.23 | 5805.54 | 9795.36 | 12421.52 | 27521.01 | 24122.2 | 33885.41 | 47959.55 | 114655.18 | 237244.28 | 552983.72 | 52496.33 | 381905.84 | 71254.04 | 484660.55 | 143942.85 | 251182.84 | 866574.18 | 275385.24 | 294707.83 | 353291.598 | 226222.72 | 3714520.75 | 7116144.768 | -9069.29 | 4801548.79 | 7647007.43 | 2955898.89 | 2737591.8 | 1726203.7 | 1837146.05 | 1460862.11 | 1399734.82 | 1726900.83 | 1654561.49 | 5018413.92 | 32956800.54 | 2460948.39 | 2715360.87 | 3279760.62 | 4250321.36 | 3222233.09 | 4072839.4636 | 1739168.05 | 1346399.41 | 2620306.81 | 1555643.4 | 2071947.99 | 1813901.02 | 31148830.4736 | 6351257.68 | 1572890.37 | 2333944.42 | 1974807.0167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12232899.4867 | 86364534.8183 | 0 | 86364534.8183 | -7875413.7608 | 94239948.0143 | -7875413.1961 | 90239947.7051 | 94239948.5791 | 11875413.7608 |  | 96944363.2333 | 10579828.415
[24 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
|  | AFUDC |  | 5580041 | 6083947 |  | 6083947 |  |  |  | 231010.39 | 4107.21 | 6356.16 | 8947.23 | 7760.72 | 10581.69 | 10679.32 | 9112.73 | 6583.13 | 9386.15 | 11679.91 | 10937.68 | 10827.72 | 106959.65 | 18327.33 | 12850.62 | 22746.45 | 26802.44 | 24715.47 | 20947.78 | 32547.41 | 35381.43 | 38395.57 | 34948.14 | 38496.41 | 40230.48 | 346389.53 | 43890.89 | 36130.43 | 62305.65 | 117488.33 | 145320.06 | 164544.07 | 182971.77 | 198157.48 | 220228.98 | 219606.07 | 237665.53 | 258263.98 | 1886573.24 | 272222.86 | 278846.63 | 303324.02 | 318049.34 | 363663.68 | 394832.49 | 412255.14 | 422884.12 | 429853.89 | 416996.01 | 379991.79 | 387465.34 | 4380385.31 | 456928.06 | 481523.32 | 499152.4 | 432308.1 | [8 empty] | 1869911.88 | 8821230 | 0 | 8821230 | 2737283 | 11370713.1124 | -2549483.1124 |  | 4000000 |  |  | 6029981.0803 | -2791248.9197
|  |  | AFUDC - Order # 111020147, 111020148 (LGIA) | [8 empty] | 2012 F: 7.27; 2012 M: 56.09; 2012 A: 117.18; 2012 M: 150.62; 2012 J: 174.3; 2012 J: 224.76; 2012 A: 312.39; 2012 S: 366.53; 2012 O: 364; 2012 N: 561.93; 2012 D: 786.28; 2013 J: 944.63; 2013 F: 1309.19; 2013 M: 1908.19; 2013 A: 1928.7333 | 9212.0933 | 0 | 9212.0933 | 9212.0933 | 9597.84 | -385.7467
[24 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| Total Project |  |  | 88687013.61 | 96323895.5791 | 4000000 | 100323895.5791 |  |  |  | 2587886.22 | 11523.91 | 32578.9 | 14881.46 | 13566.26 | 20377.05 | 23100.84 | 36633.74 | 30705.33 | 43271.56 | 59639.46 | 125592.86 | 248072 | 659943.37 | 70823.66 | 394756.46 | 94000.49 | 511462.99 | 168658.32 | 272130.62 | 899121.59 | 310766.67 | 333103.4 | 388239.738 | 264719.13 | 3754751.23 | 7462534.298 | 34821.6 | 4837679.22 | 7709313.08 | 3073387.22 | 2882911.86 | 1890747.77 | 2020117.82 | 1659019.59 | 1619963.8 | 1946506.9 | 1892227.02 | 5276677.9 | 34843373.78 | 2733171.25 | 2994214.77 | 3583140.73 | 4568487.88 | 3586047.39 | 4467846.2536 | 2151647.95 | 1769595.92 | 3050527.23 | 1973003.41 | 2452501.71 | 2202152.64 | 35529215.7836 | 6809130.37 | 2055722.88 | 2835005.01 | 2409043.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14102811.3667 | 95194976.9116 | 0 | 95194976.9116 | -5128918.6675 | 105620258.9667 | -10425282.0551 |  | 98239948.5791 |  |  | 102974344.3136 | 7779367.402
[67 empty] | 2890852.62 | <==Orig
| Reduced 2011 numbers | [10 empty] | 2011 J: 1750265.8158; 2011 F: 3672922.06; 2011 M: 5493497.9256; 2011 A: 4354841.7446; 2011 M: 3817045.8506; 2011 J: 3071158.6784; 2011 J: 2521267.925; 2012 J: 2789650.045; 2012 F: 2789650.045; 2012 M: 2789650.045; 2012 A: 2789650.045; 2012 M: 2789650.045; 2012 J: 2789650.045; 2012 J: 2789650.045; 2012 A: 2789650.045; 2012 S: 2789650.045; 2012 O: 2789650.045; 2012 N: 1332649.045; 2012 D: 2414650.045; 2012 Total: 31643799.54; 2013 J: 655083.3333; 2013 F: 655083.3333; 2013 M: 655083.3333; 2013 A: 655083.3333; 2013 M: 655083.3333; 2013 J: 655083.3333; 2013 A: 655083.3333; 2013 S: 655083.3333; 2013 O: 655083.3333; 2013 N: 655083.3333; 2013 D: 655083.3333; 2013 Total: 7205916.6667 |  |  |  |  | 5864760.7033 | 8379279.0333 |  |  |  |  | 77453798.7227 | -17741178.1889
[43 empty] | revised 2011 | 24681000 | [6 empty] | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 642999 | 1725000
[43 empty] | delta | 8275800.54 | [6 empty] | 689650.045 | 689650.045 | 689650.045 | 689650.045 | 689650.045 | 689650.045 | 689650.045 | 689650.045 | 689650.045 | 689650.045 | 689650.045 | 689650.045
[67 empty] | 2409043.85 | <==25 of 30 days
[62 empty] | 2012 Budget | 36748561 |  |  |  | 0
[5 empty] | 90239948.1091 | 90239948.1091 | 90239948.1091 |  |  |  |  | 2012 D: Forecast variance; 2012 Total: 5599730.5264
2612678
[5 empty] | 0.47 | -86239948.1091 | 4000000.47 | [76 empty] | 88977212.8183
[24 empty] | 0.19342 | 0.34912 | 0.033649 | 0.31923 | 0.055301 | 0.1717 | 0.083397 | 0.037559 | 0.12848 | 0.13028 | 0.098922 | 0.17017 | 0.010831 | 0.048677 | -4.8395 | 0.0075247 | 0.0081477 | 0.039747 | 0.053083 | 0.095321 | 0.099596 | 0.13564 | 0.15734 | 0.12717 | 0.14364 | 0.051463 | 0.057244 | 0.11062 | 0.10269 | 0.092484 | 0.074829 | 0.11286 | 0.096943 | 0.23704 | 0.31409 | 0.16405 | 0.26805 | 0.1834 | 0.21361 | 0.14063 | 0.071943
Note on AG66: Puget Sound Energy: $349,175 accrual
Note on AH66: Puget Sound Energy: Include ($349,175) accrual reversal and $302,354 re-accrual
Note on AL66: Puget Sound Energy: Include Dec 2010 accrual
Note on AN66: Puget Sound Energy: $200K accrual reversal
Note on CC66: Puget Sound Energy:
Note on AS67: Puget Sound Energy: Include ($200,00) accrual reversal
Note on AV67: Puget Sound Energy: Include $250K are-accrual
Note on AW67: Puget Sound Energy: Accruals
Note on AX67: Puget Sound Energy: Accruals
Note on CI67: Puget Sound Energy: $403,315 to go less $250,000 accrual = $153,000 - assume billed every 6 months at $50K pm
Note on AL69: Puget Sound Energy: Include $451,458 Dec 2010 accrual
Note on AQ70: Puget Sound Energy: Include ($400,770) accrual reversal and $140,000 re-accrual
Note on AS70: Puget Sound Energy: ($76,000) accrual reversal
Note on AV70: Puget Sound Energy: Include $50K + $50K new accruals
Note on AX70: Puget Sound Energy: Construction support 8/27 - 9/30
Note on CF70: Puget Sound Energy: Saving on Jan & Feb invoices - move budget alllowance to project controls
Note on AP77: Puget Sound Energy: For work during Aug/Sept 2010
Note on CI77: Puget Sound Energy: $2,900,000 as per invoice 8/27/2011 less work during Development phase
Note on AL79: Puget Sound Energy: Include $215.04 accrual
Note on AL80: Puget Sound Energy: Include $215.04 accrual
Note on AS80: Puget Sound Energy: ($256.20) accrual reversal
Note on BB80: Puget Sound Energy: Elizabeth Hendrickson
Note on AV82: Puget Sound Energy: No info
Note on BI82: Puget Sound Energy: Locate utilities (power, comms and water)
Note on K83: Puget Sound Energy: Yep - that's right
Note on AL87: Puget Sound Energy: Include $10,000 Dec 2010 accrual
Note on AS90: Puget Sound Energy: ($10,000 accrual reversal)
Note on AV90: Puget Sound Energy: Board of consultants meeting
Note on AY90: Puget Sound Energy: Board of consultants
Note on BE90: Puget Sound Energy: BOC meeting
Note on AW92: Puget Sound Energy: Services for Project Management and Construction Documentation
Note on AX92: Puget Sound Energy: For "project management and construction documentation"
Note on AY92: Puget Sound Energy: For "project management and construction documentation"
Note on BB92: Puget Sound Energy: for Project Management and Construction Documentation
Note on BD94: Puget Sound Energy: BOC meeting printing
Note on BJ94: Puget Sound Energy: Company printing and postage services
Note on AV95: Puget Sound Energy: Fence installation
Note on AV97: Puget Sound Energy: Board of consultants meeting and travel
Note on AY97: Puget Sound Energy: BOC
Note on BC97: Puget Sound Energy: BOC meeting
Note on AX99: Puget Sound Energy: Accrual
Note on AY99: Puget Sound Energy: Over accrual on invoice due to differing exchange rates
Note on AX101: Puget Sound Energy: Water quality monitoring services from June through 12 Aug
Note on AY101: Puget Sound Energy: Water quality monitoring services from 15 Oct through 11 Nov
Note on BJ101: Puget Sound Energy: Water Quality monitoring
Note on BE104: Puget Sound Energy: Professional Services for april 2012 - "PSE Baker Hydro DAHP Level II"
Note on AV105: Puget Sound Energy: Conference call and review of comments regarding "Koncar"
Note on AY105: Puget Sound Energy: BOC meeting? - travel for Doug Aaron
Note on BA105: Puget Sound Energy: Review stacking specifications and drawings with Ryan Murphy
Note on BC105: Puget Sound Energy: no info on credit
Note on BE105: Puget Sound Energy: Conference call and schedule review with Ryan Murphy
Note on BK105: Puget Sound Energy: Generator inspection
Note on AL106: Puget Sound Energy: Include $10,000 Dec 2010 accrual
Note on AY106: Puget Sound Energy: BOC
Note on AL107: Puget Sound Energy: Include $10,000 Dec 2010 accrual
Note on AV107: Puget Sound Energy: Construction monitoring secant pile wall, slope monitoring
Note on AX107: Puget Sound Energy: "Conference call re blast monitoring and Geoengineers access road slope stabilization"
Note on AY107: Puget Sound Energy: BOC
Note on AV112: Puget Sound Energy: Honeybucket rental
Note on AX112: Puget Sound Energy: Honeybucket rental
Note on AY112: Puget Sound Energy: Honeybucket rental
Note on BG116: Puget Sound Energy: Lead hazard control plan
Note on AY120: Lenovo User: Work through end 10/2011 for "Imminent flood analysis study" - approved by Irena Netik (PSE)
Note on AX121: Puget Sound Energy: Remove and reinstall fence and hydraulic gate (for equipment to pass through)
Note on BB121: Puget Sound Energy: Repairs to gate
Note on BP121: Puget Sound Energy: Gate repair from PCL Insurance claim?
Note on AV122: Puget Sound Energy: Coordinate plant availibility and construction approach
Note on AW122: Puget Sound Energy: Review of technical specifications and Restoration Planting plan
Note on AX122: Puget Sound Energy: Construction administration: work scope and costs, coordinate construction start schedule
Note on AY122: Lenovo User: Fill restoration planting - meetings and inspections
Note on CI129: Puget Sound Energy: $42,939,000 + WST
Note on AL130: Puget Sound Energy: Include $958,002 Dec 2010 accrual
Note on AO130: Puget Sound Energy: Inlude -$958,002 accrual reversal, as well as $1,306,032 Jan 2011 + $3,002,233 Feb 2011 accruals
Note on AR130: Puget Sound Energy: Check contract value
Note on AS130: Puget Sound Energy: Include ($3,379,841) and ($1,200,079) accrual reversals and $1,200,079 and $1,000,000 accruals
Note on D148: Puget Sound Energy: Design split out from line 149 - CPR 19/CP59
Note on CB156: Puget Sound Energy: Moved $100K to Mayes Testing Engineers
Note on CI156: Puget Sound Energy: Adjusted GMP including CO's 1-3 (8/16/2011)
Note on BD161: Puget Sound Energy: Baker River Clubhouse Phase 1 - design work?
Note on BE161: Puget Sound Energy: Baker River Clubhouse Phase 1 - design work?
Note on BI167: Puget Sound Energy: Turbine cover machined per instructions
Note on BI170: Puget Sound Energy: Unload equipment at shuffleton
Note on BA171: Puget Sound Energy: Louise Popelka, 26 hrs
Note on BG171: Puget Sound Energy: Fiber consulting
Note on BA173: Puget Sound Energy: time for Dan Howell 6 hrs, Bill Steele 8 hrs, no additional detail, billed to Dennis Taylor PSE Communications
Note on AV177: Puget Sound Energy: Work by Brad Canady
Note on AW177: Puget Sound Energy: Brad Cannady
Note on AX177: Puget Sound Energy: Brad Canady
Note on AY177: Puget Sound Energy: Brad Canady
Note on BC177: Puget Sound Energy: Incorrect charges?
Note on BE177: Puget Sound Energy: Brad Canady 16 hrs
Note on BG177: Puget Sound Energy: 6/1/2012 - 6/29/2012 Brad Canady 20 hrs
Note on G183: Puget Sound Energy: As per R Bollich email 10/17/2012 - $500K "transferred" from IT department to project
Note on H183: Puget Sound Energy: As per R Bollich email 10/17/2012 - $500K "transferred" from IT department to project
Note on I183: Puget Sound Energy: As per R Bollich email 10/17/2012 - $500K "transferred" from IT department to project
Note on AY185: Puget Sound Energy: Analysis of test samples (acid wash and silica gel cleanup)
Note on BK188: Puget Sound Energy: Maintenance testing of htg
Note on AY197: Puget Sound Energy: Credit for double payment of invoice in Oct 2011
Note on CI197: Puget Sound Energy: as per invoice
Note on AY198: Puget Sound Energy: Credit for double payment of invoice in Oct 2011
Note on CI198: Puget Sound Energy: as per invoice
Note on BD202: Puget Sound Energy: Hauling gravel to LB - approved by John Jensen.
Note on BI202: Puget Sound Energy: move eco blocks
Note on AY206: Puget Sound Energy: "Sweep lower park way and road at Baker Dam"
Note on AL212: Puget Sound Energy: Include $276,250 Dec 2010 accrual
Note on AO212: Puget Sound Energy: Dec 2010 accrual reversal
Note on AS212: Puget Sound Energy: ($1,633,878) accrual reversal and $1,611,024 new accrual
Note on CI212: Puget Sound Energy: Adjusted GMP including CO's 1-3 (8/16/2011)
Note on AL213: Puget Sound Energy: Include $276,250 Dec 2010 accrual
Note on AO213: Puget Sound Energy: Dec 2010 accrual reversal
Note on AS213: Puget Sound Energy: ($1,633,878) accrual reversal and $1,611,024 new accrual
Note on BC213: Puget Sound Energy: milestone 10
Note on CD213: Puget Sound Energy: 7.8% WA state tax rate in estimate, 8.2% use tax billed
Note on CI213: Puget Sound Energy: Adjusted GMP including CO's 1-3 (8/16/2011)
Note on CI214: Puget Sound Energy: Adjusted GMP including CO's 1-3 (8/16/2011)
Note on CI215: Puget Sound Energy: Adjusted GMP including CO's 1-3 (8/16/2011)
Note on CI216: Puget Sound Energy: Adjusted GMP including CO's 1-3 (8/16/2011)
Note on CI217: Puget Sound Energy: Adjusted GMP including CO's 1-3 (8/16/2011)
Note on CI218: Puget Sound Energy: Adjusted GMP including CO's 1-3 (8/16/2011)
Note on CI219: Puget Sound Energy: Adjusted GMP including CO's 1-3 (8/16/2011)
Note on BC220: Puget Sound Energy: Supervision for Jan and Feb 2012
Note on CB220: Puget Sound Energy: Moved $100K to Mayes Testing Engineers
Note on CI220: Puget Sound Energy: Adjusted GMP including CO's 1-3 (8/16/2011)
Note on AS271: Puget Sound Energy: ($10,000) accrual reversal
Note on BE271: Puget Sound Energy: Final billing for rockslope stability monitoring
Note on BA278: Puget Sound Energy: As per pay app
Note on AX280: Puget Sound Energy: Subsurface explorations, work through 10/15/2011
Note on AY280: Puget Sound Energy: Subsurface explorations, work through 11/12/2011
Note on BA280: Puget Sound Energy: Subsurface explorations 11/13 - 12/17
Note on AX281: Puget Sound Energy: Monthly slope stability monitoring, work though 10/15/2011
Note on AY281: Lenovo User: Monthly slope stability monitoring. Forecast to complete - no money going forward?
Note on CB283: Puget Sound Energy: Actuals to date charged to internal order - John Peterman to move
Note on BE285: Puget Sound Energy: Powerhouse trail inadvertent discovery
Note on CC286: Puget Sound Energy: Moved remaining $67K to Shannon Wilson
Note on BO291: Puget Sound Energy: vs $75K forecast in Jan
Note on BO306: Puget Sound Energy: vs $71K forecast in Jan

## Treas.Grant est. Update
Lower Baker Powerhouse Treasury Grant estimate Revised for Sequestration 8.7%
% AFUDC eligible as CPI: | 80%
| Total project cost | Estimated Treasury Grant-eligible costs | Estimated % of cost deemed eligible
Total LB Powerhouse before AFUDC | 86364534.8183 | 86364534.8183 | 100%
|  | 0 | #DIV/0!
|  | 0 | #DIV/0!
|  | 0 | #DIV/0!
|  | 0 | #DIV/0!
|  | 0 | #DIV/0!
|  | 0 | #DIV/0!
|  | 0 | #DIV/0!
LB Powerhous AFUDC | 8830442.0933
Construction Period Interest |  | 7064353.6747 | 80%
Total cost estimate incl. AFUDC | 95194976.9116
Total grant-eligible costs |  | 93428888.4929
Final in-service date
| Estimated Treasury Grant amount pre-sequestration | 28028666.5479 | Pending
| Estimated Treasury Grant amount with 8.7% Sequestration | 25590172.5582

## Lead Sheet
PUGET SOUND ENERGY-ELECTRIC
Baker River Hydroelectric Project Relicensing Upgrades
RATE YEAR ENDED NOVEMBER 30, 2014
Baker River Hydroelectric Project Relicensing Upgrades
LINE
NO. | DESCRIPTION | TEST YEAR | RATE YEAR | ADJUSTMENT
1 | Baker RATEBASE (AMA)
2 | UTILITY PLANT RATEBASE
3 | PLANT BALANCE |  | 152062126.1125 | 152062126.1125
4 | ACCUM DEPRECIATION |  | -3397260.3266 | -3397260.3266
5 | DEFERRED INCOME TAX LIABILITY |  | -23946246.4897 | -23946246.4897
6 | NET Baker RATEBASE | 0 | 124718619.2963 | 124718619.2963
7
8 | Baker OPERATING EXPENSE
9 | TAXABLE DEPRECIATION EXPENSE | 0 | 2997078.4107 | 2997078.4107
10 | NON-TAXABLE DEPRECIATION EXPENSE | 0 | 335811.6663 | 335811.6663
11 | REVENUE ADJUSTMENT for FLOW-THRU TAXES | 0 | 180821.6665 | 180821.6665
12 | TOTAL DEPRECIATION EXPENSE | 0 | 3513711.7435 | 3513711.7435
13
14 | POWER COST & PRODUCTION O&M RELATED TO
15 | POWER COST - PURCHASED POWER |  |  | 0
16 | POWER COST - WHEELING * |  |  | 0
17 | PRODUCTION O&M |  |  | 0
18 | PROPERTY INSURANCE |  |  | 0
19 | PROPERTY TAXES
20 | TOTAL POWER COST AND PROD O&M | 0 | 0 | 0
21
22 | INCREASE (DECREASE ) EXPENSE | 0 | 3513711.7435 | 3513711.7435
23
24 | GRAND TOTAL OF OPERATING EXPENSES |  |  | 3513711.7435
Note on E8: Mickelson, Christopher (UTC): Per PSE's response to Staff DR 43 - Attach B

## Hydro Summary
#1 - Removed Cost Occurring after April 25, 2013
Hydro Projects
Timing & Capital | In Service | Budget
| Date | Closings
Baker
Lower Baker Powerhouse | 2013-07-24 | 95194976.9116
Lower Baker FSC | 2013-02-14 | 56867149.2009
Sub-Total |  | 152062126.1125
U4 powerhouse AFUDC Split
| Project Cost at Completion | 86364534.8183
| AFUDC | 8830442.0933
| Total | 95194976.9116
FSC AFUDC Split
| Project Cost at Completion | 53066481.8609
| AFUDC | 3800667.34
| Total | 56867149.2009

## Baker Tax Basis
Tax Basis Baker Upgrade
| (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h)
| Book |  |  | Tax Basis
| Plant Balance | AFUDC | Impact of CPI | Before | Treasury | Basis | Tax Basis | Book vs
|  |  | AFUDC* Eligible CPI% | Treasury Grant | Grant | Adjustment | Baker | Tax
80%
| (a) | (b) | (c) | (d)=(a) + ( c) | (e) =(d) x 30% | (f) =(e) x 50% | (g) =(d) - (f) | (h) =(a) - (g)
Baker
Lower Baker FSC | 56867149.2009 | 3800667.34 | -760133.468 | 56107015.7329 | n/a | n/a | 56107015.7329 | 760133.468
Lower Baker Powerhouse | 95194976.9116 | 8830442.0933 | -1766088.4187 | 93428888.4929 | 25590172.5582 | 12795086.2791 | 80633802.2138 | 14561174.6978
Sequestration 8.7%
Sub-Total | 152062126.1125 | 12631109.4333 | -2526221.8867 | 149535904.2258 | 25590172.5582 | 12795086.2791 | 136740817.9467 | 15321308.1658

## Treas.Grant est.
Lower Baker Powerhouse Treasury Grant estimate Revised for Sequestration 8.7%
% AFUDC eligible as CPI: | 80%
| Total project cost | Estimated Treasury Grant-eligible costs
Total LB Powerhouse before AFUDC | 86364534.8183 | 86364534.8183
0
0
0
0
0
0
0
AFUDC | 8830442.0933
Construction Period Interest |  | 7064353.6747
Total cost estimate incl. AFUDC | 95194976.9116
Total grant-eligible costs |  | 93428888.4929
| Estimated Treasury Grant amount pre-sequestration | 28028666.5479
| Estimated Treasury Grant amount with 8.7% Sequestration | 25590172.5582

## Book Bal
Baker Upgrade Book Balance: Sep 2013 to Nov 2014
Project Name: Baker Upgrade
Depreciation Method: Day of Service Convention, Straight-line
Lower Baker FSC
In Service Date: Feb 14th 2013
Date | Plant | Total Depreciable | Depr Exp | Accumulated
| Addtions | Plant Balance | (d )= (c) x dep rate | Depreciation
|  | (b) | 2.192%
| (a) | (c) = (a) - (b) |  | (e) = prior month - (d)
2013-09-01 |  | 56867149.2009 | 103867.6111 | -782716.6406
2013-10-01 |  | 56867149.2009 | 103867.6111 | -886584.2516
2013-11-01 |  | 56867149.2009 | 103867.6111 | -990451.8627
2013-12-01 |  | 56867149.2009 | 103867.6111 | -1094319.4738
2014-01-01 |  | 56867149.2009 | 103867.6111 | -1198187.0848
2014-02-01 |  | 56867149.2009 | 103867.6111 | -1302054.6959
2014-03-01 |  | 56867149.2009 | 103867.6111 | -1405922.307 | FSC
2014-04-01 |  | 56867149.2009 | 103867.6111 | -1509789.918
2014-05-01 |  | 56867149.2009 | 103867.6111 | -1613657.5291
2014-06-01 |  | 56867149.2009 | 103867.6111 | -1717525.1402
2014-07-01 |  | 56867149.2009 | 103867.6111 | -1821392.7512
2014-08-01 |  | 56867149.2009 | 103867.6111 | -1925260.3623
2014-09-01 |  | 56867149.2009 | 103867.6111 | -2029127.9734
2014-10-01 |  | 56867149.2009 | 103867.6111 | -2132995.5845
2014-11-01 |  | 56867149.2009 | 103867.6111 | -2236863.1955
Total - 12ME Nov 2014 |  |  | 1246411.3328
AMA - 12ME Nov 2014 |  | 56867149.2009 |  | -1613657.5291
Lower Baker Powerhouse
In Service Date: July 24th 2013
Date | Plant | Total Depreciable | Depr Exp | Accumulated
| Addtions | Plant Balance | (d )= (c) x dep rate | Depreciation
|  | (b) | 2.192%
| (a) | (c) = (a) - (b) |  | (e) = prior month - (d)
2013-09-01 |  | 95194976.9116 | 173873.2287 | -392616.968
2013-10-01 |  | 95194976.9116 | 173873.2287 | -566490.1967
2013-11-01 |  | 95194976.9116 | 173873.2287 | -740363.4254
2013-12-01 |  | 95194976.9116 | 173873.2287 | -914236.654
2014-01-01 |  | 95194976.9116 | 173873.2287 | -1088109.8827
2014-02-01 |  | 95194976.9116 | 173873.2287 | -1261983.1114
2014-03-01 |  | 95194976.9116 | 173873.2287 | -1435856.3401 | Unit 4
2014-04-01 |  | 95194976.9116 | 173873.2287 | -1609729.5688
2014-05-01 |  | 95194976.9116 | 173873.2287 | -1783602.7975
2014-06-01 |  | 95194976.9116 | 173873.2287 | -1957476.0261
2014-07-01 |  | 95194976.9116 | 173873.2287 | -2131349.2548
2014-08-01 |  | 95194976.9116 | 173873.2287 | -2305222.4835
2014-09-01 |  | 95194976.9116 | 173873.2287 | -2479095.7122
2014-10-01 |  | 95194976.9116 | 173873.2287 | -2652968.9409
2014-11-01 |  | 95194976.9116 | 173873.2287 | -2826842.1696
Total - 12ME Nov 2014 |  |  | 2086478.7442
AMA - 12ME Nov 2014 |  | 95194976.9116 |  | -1783602.7975
Open
Total Baker Upgrade
Date | Plant | Total Depreciable | Depr Exp | Accumulated
| Addtions | Plant Balance | (d )= (c) x dep rate | Depreciation
|  | (b) | 2.192%
|  | (c) = (a) - (b) |  | (e) = prior month - (d)
2013-09-01 |  |  |  | -1175333.6086
2013-10-01 | 0 | 152062126.1125 | 277740.8398 | -1453074.4483
2013-11-01 | 0 | 152062126.1125 | 277740.8398 | -1730815.2881
2013-12-01 | 0 | 152062126.1125 | 277740.8398 | -2008556.1278
2014-01-01 | 0 | 152062126.1125 | 277740.8398 | -2286296.9676
2014-02-01 | 0 | 152062126.1125 | 277740.8398 | -2564037.8073
2014-03-01 | 0 | 152062126.1125 | 277740.8398 | -2841778.6471
2014-04-01 | 0 | 152062126.1125 | 277740.8398 | -3119519.4868 | TOTAL Baker Upgrade
2014-05-01 | 0 | 152062126.1125 | 277740.8398 | -3397260.3266
2014-06-01 | 0 | 152062126.1125 | 277740.8398 | -3675001.1663
2014-07-01 | 0 | 152062126.1125 | 277740.8398 | -3952742.0061
2014-08-01 | 0 | 152062126.1125 | 277740.8398 | -4230482.8458
2014-09-01 | 0 | 152062126.1125 | 277740.8398 | -4508223.6856
2014-10-01 | 0 | 152062126.1125 | 277740.8398 | -4785964.5253
2014-11-01 | 0 | 152062126.1125 | 277740.8398 | -5063705.3651
Total - 12ME Nov 2014 |  |  | 3332890.077
AMA - 12ME Nov 2014 |  | 152062126.1125 |  | -3397260.3266

## Dep Rate
Proposed Depreciation Rate
for Baker Upgrade - FSC and Unit 4
Baker:
Lower Baker FSC estimates in service date Feb 14th 2013
Lower Baker Powerhouse estimates in service date July 24th 2013
| FSC | Unit 4
In service Date | 2013-02-14 | 2013-07-24
Net Book Value | 56867149.2009 | 95194976.9116
| Months | Months
License Life for Baker = 50 Years | 600 | 600
Months oper under lic through latest full year (2012) since Lic obtained Nov 2008 | 50 | 50
Months oper under lic in 2013 prior to On-line dates (2.14.13 FSC; 7.24.13 Unit 4) | 1 | 4
Remaining months to be depreciated and used for dep rate on NEW Plant (a) | 549 | 546
Depreciation per month | 103583.1497 | 174349.7746
Annual Depreciation | 1242997.7967 | 2092197.2948
Annual Depreciation Rate | 2.186% | 2.198% | 2.192% | Average Deprec. Rate
Annual Depreciation with effects of rounding removed | 1245390.5675 | 2094289.4921
(a) The plant's depreciable life is 50 years per FERC License that PSE obtained in Nov, 2008. The new plant is
estimated to be in service Feb 14th, 2013 (FSC) and July 24nd, 2013 (Unit 4). Therefore, the terminal retirement
date to use for purposes of calculating the depreciation rate for Baker is 549 months or 45.75 years
on the FSC, and 544 months or 45.3 years on the Powerhouse.
Note on A17: nchar: 2 months in 2008 plus 2009-2012

## DFIT IRS
PUGET SOUND ENERGY
Baker TOTAL PROJECT
DETERMINATION OF RATE YEAR DEFERRED FEDERAL INCOME TAX ARISING FROM DEPRECIATION
RATE YEAR END Ocotober 31, 2014
Total Baker Deferred FIT
DFIT arising from Depreciation Expense
|  | AMA Calculation |  |  | IRS Calculation
Accumulated
Row | Days in | Month | Deferred Tax | Deferred | # Days | Total Days | IRS | Cum IRS
| Month | Ended | Expense | Taxes | to include | in Period | Amount | Balance
| a | b | c | d = prior | e = | f = col. a row 29 | g = e ¸ f x c | h = prior
|  |  |  | month - col c | f - sum a +1 |  |  | month - col g
15
16 |  | 2013-11-01 | 3278682.2149 | -20899392.6335 |  |  |  | -20899392.6335
17 | 31 | 2013-12-01 | 3278682.2149 | -24178074.8484 | 335 | 365 | 3009201.4849 | -23908594.1184
18 | 31 | 2013-01-01 | 56541.9579 | -24234616.8063 | 304 | 365 | 47092.48 | -23955686.5984
19 | 28 | 2013-02-01 | 56541.9579 | -24291158.7642 | 276 | 365 | 42755.0147 | -23998441.6131
20 | 31 | 2014-03-01 | 56541.9579 | -24347700.722 | 245 | 365 | 37952.821 | -24036394.4342
21 | 30 | 2014-04-01 | 56541.9579 | -24404242.6799 | 215 | 365 | 33305.5368 | -24069699.971
22 | 31 | 2014-05-01 | 56541.9579 | -24460784.6378 | 184 | 365 | 28503.3432 | -24098203.3142
23 | 30 | 2014-06-01 | 56541.9579 | -24517326.5957 | 154 | 365 | 23856.0589 | -24122059.3731
24 | 31 | 2014-07-01 | 56541.9579 | -24573868.5536 | 123 | 365 | 19053.8653 | -24141113.2384
25 | 31 | 2014-08-01 | 56541.9579 | -24630410.5114 | 92 | 365 | 14251.6716 | -24155364.9099
26 | 30 | 2014-09-01 | 56541.9579 | -24686952.4693 | 62 | 365 | 9604.3874 | -24164969.2973
27 | 31 | 2014-10-01 | 56541.9579 | -24743494.4272 | 31 | 365 | 4802.1937 | -24169771.491
28 | 30 | 2014-11-01 | 56541.9579 | -24800036.3851 | 1 | 365 | 154.9095 | -24169926.4005
29 | 365 |  | 3900643.7516 |  |  |  | 3270533.7669
30
31 | Average of the Monthly Averages |  |  | -24326528.7938 |  |  |  | -23946246.4897
32
Lower Baker FSC
DFIT arising from Depreciation Expense
|  | AMA Calculation |  |  | IRS Calculation
Accumulated
Row | Days in | Month | Deferred Tax | Deferred | # Days | Total Days | IRS | Cum IRS
| Month | Ended | Expense | Taxes | to include | in Period | Amount | Balance
| a | b | c | d = prior | e = | f = col. a row 29 | g = e ¸ f x c | h = prior
|  |  |  | month - col c | f - sum a +1 |  |  | month - col g
42
43 |  | 2013-11-01 | 890216.8188 | -8918821.0629 |  |  |  | -8918821.0629
44 | 31 | 2013-12-01 | 890216.8188 | -9809037.8817 | 335 | 365 | 817048.3131 | -9735869.376
45 | 31 | 2013-01-01 | 23200.099 | -9832237.9807 | 304 | 365 | 19322.8222 | -9755192.1983
46 | 28 | 2013-02-01 | 23200.099 | -9855438.0798 | 276 | 365 | 17543.0886 | -9772735.2869
47 | 31 | 2014-03-01 | 23200.099 | -9878638.1788 | 245 | 365 | 15572.6692 | -9788307.9561
48 | 30 | 2014-04-01 | 23200.099 | -9901838.2779 | 215 | 365 | 13665.8118 | -9801973.7679
49 | 31 | 2014-05-01 | 23200.099 | -9925038.3769 | 184 | 365 | 11695.3924 | -9813669.1602
50 | 30 | 2014-06-01 | 23200.099 | -9948238.476 | 154 | 365 | 9788.5349 | -9823457.6952
51 | 31 | 2014-07-01 | 23200.099 | -9971438.575 | 123 | 365 | 7818.1156 | -9831275.8108
52 | 31 | 2014-08-01 | 23200.099 | -9994638.6741 | 92 | 365 | 5847.6962 | -9837123.507
53 | 30 | 2014-09-01 | 23200.099 | -10017838.7731 | 62 | 365 | 3940.8387 | -9841064.3457
54 | 31 | 2014-10-01 | 23200.099 | -10041038.8722 | 31 | 365 | 1970.4194 | -9843034.7651
55 | 30 | 2014-11-01 | 23200.099 | -10064238.9712 | 1 | 365 | 63.5619 | -9843098.327
56 | 365 |  | 1145417.9083 |  |  |  | 924277.2641
57
58 | Average of the Monthly Averages |  |  | -9888912.6803 |  |  |  | -9768721.9637
59
Lower Baker Powerhouse
DFIT arising from Depreciation Expense
|  | AMA Calculation |  |  | IRS Calculation
Accumulated
Row | Days in | Month | Deferred Tax | Deferred | # Days | Total Days | IRS | Cum IRS
| Month | Ended | Expense | Taxes | to include | in Period | Amount | Balance
| a | b | c | d = prior | e = | f = col. a row 29 | g = e ¸ f x c | h = prior
|  |  |  | month - col c | f - sum a +1 |  |  | month - col g
69
70 |  | 2013-11-01 | 2388465.3961 | -11980571.5706 |  |  |  | -11980571.5706
71 | 31 | 2013-12-01 | 2388465.3961 | -14369036.9667 | 335 | 365 | 2192153.1718 | -14172724.7424
72 | 31 | 2013-01-01 | 33341.8588 | -14402378.8255 | 304 | 365 | 27769.6578 | -14200494.4001
73 | 28 | 2013-02-01 | 33341.8588 | -14435720.6844 | 276 | 365 | 25211.9261 | -14225706.3263
74 | 31 | 2014-03-01 | 33341.8588 | -14469062.5432 | 245 | 365 | 22380.1518 | -14248086.4781
75 | 30 | 2014-04-01 | 33341.8588 | -14502404.402 | 215 | 365 | 19639.7251 | -14267726.2032
76 | 31 | 2014-05-01 | 33341.8588 | -14535746.2609 | 184 | 365 | 16807.9508 | -14284534.1539
77 | 30 | 2014-06-01 | 33341.8588 | -14569088.1197 | 154 | 365 | 14067.524 | -14298601.6779
78 | 31 | 2014-07-01 | 33341.8588 | -14602429.9785 | 123 | 365 | 11235.7497 | -14309837.4276
79 | 31 | 2014-08-01 | 33341.8588 | -14635771.8374 | 92 | 365 | 8403.9754 | -14318241.403
80 | 30 | 2014-09-01 | 33341.8588 | -14669113.6962 | 62 | 365 | 5663.5486 | -14323904.9516
81 | 31 | 2014-10-01 | 33341.8588 | -14702455.555 | 31 | 365 | 2831.7743 | -14326736.7259
82 | 30 | 2014-11-01 | 33341.8588 | -14735797.4139 | 1 | 365 | 91.3476 | -14326828.0735
83 | 365 |  | 2755225.8432 |  |  |  | 2346256.5028
84
85 | Average of the Monthly Averages |  |  | -14437616.1135 |  |  |  | -14177524.526
86

## #1+#2+3 Tot Baker DFIT
Baker Upgrade Book & Tax Depreciation: December 1, 2013 through November 30, 2014
Total Baker Upgrade |  | Book Basis | Tax Basis
|  | 152062126.1125 | 136740817.9467
Date | Depreciable Plant Balance |  |  | Depreciation Expense |  |  |  | Accumulated Depreciation |  |  | Net Book Value |  | NBV Diff | ADFIT | DFIT
|  |  | Book |  | 2.192% | Book Depr. |  |  |  | BOOK |  | Book
| Tax | Book | Using Tax Basis | Tax | Book | Using Tax Basis |  | Tax | Book | Permanent Difference | Tax | based on Tax Basis | Book > Tax | 35% | Expense
|  |  |  | (d) = (a) x Tax | (e) = (b) x 3.18% | (f) = (c) x 3.18% | Net Difference | [7 empty] | (o) = - curr month (n)
| (a) | (b) | (c) | Table | ¸ 12 mos. | ¸ 12 mos. | (g) = (e) x (f) | (h) = prior month - (d) | (i) = prior month - (e) | (j) = prior month - (g) | (k) = (a) + (h) | (l) = (c) + (i) +(j) | (m) = (k) - (l) | (n) = - (m) * 35% | + prior month (n)
2010-11-30 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2010-12-31 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2011-01-31 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2011-02-28 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2011-03-31 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2011-04-30 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2011-05-31 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2011-06-30 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2011-07-31 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2011-08-31 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2011-09-30 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2011-10-31 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2011-11-30 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2011-12-31 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2012-09-30
2012-10-31
2012-11-30
2012-12-31
2013-01-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2013-02-28 | 56107015.7329 | 56867149.2009 | 56107015.7329 | 2645955.8556 | 55643.3631 | 54899.5877 | 743.7753 | -2645955.8556 | -55643.3631 | 743.7753 | 53461059.8773 | 56052116.1452 | 2591056.2678 | -906869.6937 | 906869.6937
2013-03-31 | 56107015.7329 | 56867149.2009 | 56107015.7329 | 2645955.8556 | 103867.6111 | 102479.2305 | 1388.3806 | -5291911.7112 | -159510.9741 | 2132.1559 | 50815104.0217 | 55949636.9147 | 5134532.893 | -1797086.5125 | 890216.8188
2013-04-30 | 56107015.7329 | 56867149.2009 | 56107015.7329 | 2645955.8556 | 103867.6111 | 102479.2305 | 1388.3806 | -7937867.5668 | -263378.5852 | 3520.5366 | 48169148.1661 | 55847157.6842 | 7678009.5181 | -2687303.3313 | 890216.8188
2013-05-31 | 56107015.7329 | 56867149.2009 | 56107015.7329 | 2645955.8556 | 103867.6111 | 102479.2305 | 1388.3806 | -10583823.4223 | -367246.1963 | 4908.9172 | 45523192.3106 | 55744678.4538 | 10221486.1432 | -3577520.1501 | 890216.8188
2013-06-30 | 56107015.7329 | 56867149.2009 | 56107015.7329 | 2645955.8556 | 103867.6111 | 102479.2305 | 1388.3806 | -13229779.2779 | -471113.8073 | 6297.2978 | 42877236.455 | 55642199.2233 | 12764962.7684 | -4467736.9689 | 890216.8188
2013-07-31 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 9617420.0053 | 148738.1217 | 140486.2766 | 8251.8451 | -22847199.2833 | -619851.929 | 14549.1429 | 113893618.6635 | 136135515.1606 | 22241896.4971 | -7784663.774 | 3316926.8051
2013-08-31 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 9617420.0053 | 277740.8398 | 249756.5342 | 27984.3055 | -32464619.2886 | -897592.7688 | 42533.4484 | 104276198.6582 | 135885758.6263 | 31609559.9682 | -11063345.9889 | 3278682.2149
2013-09-30 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 9617420.0053 | 277740.8398 | 249756.5342 | 27984.3055 | -42082039.2939 | -1175333.6086 | 70517.7539 | 94658778.6528 | 135636002.0921 | 40977223.4393 | -14342028.2037 | 3278682.2149
2013-10-31 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 9617420.0053 | 277740.8398 | 249756.5342 | 27984.3055 | -51699459.2992 | -1453074.4483 | 98502.0595 | 85041358.6475 | 135386245.5579 | 50344886.9104 | -17620710.4186 | 3278682.2149
2013-11-30 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 9617420.0053 | 277740.8398 | 249756.5342 | 27984.3055 | -61316879.3045 | -1730815.2881 | 126486.365 | 75423938.6422 | 135136489.0237 | 59712550.3815 | -20899392.6335 | 3278682.2149
2013-12-31 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 9617420.0053 | 277740.8398 | 249756.5342 | 27984.3055 | -70934299.3099 | -2008556.1278 | 154470.6705 | 65806518.6369 | 134886732.4894 | 69080213.8526 | -24178074.8484 | 3278682.2149
2014-01-31 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 411304.9853 | 277740.8398 | 249756.5342 | 27984.3055 | -71345604.2952 | -2286296.9676 | 182454.976 | 65395213.6515 | 134636975.9552 | 69241762.3037 | -24234616.8063 | 56541.9579
2014-02-28 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 411304.9853 | 277740.8398 | 249756.5342 | 27984.3055 | -71756909.2805 | -2564037.8073 | 210439.2816 | 64983908.6662 | 134387219.421 | 69403310.7547 | -24291158.7642 | 56541.9579
2014-03-31 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 411304.9853 | 277740.8398 | 249756.5342 | 27984.3055 | -72168214.2658 | -2841778.6471 | 238423.5871 | 64572603.6809 | 134137462.8868 | 69564859.2058 | -24347700.722 | 56541.9579
2014-04-30 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 411304.9853 | 277740.8398 | 249756.5342 | 27984.3055 | -72579519.2511 | -3119519.4868 | 266407.8926 | 64161298.6956 | 133887706.3525 | 69726407.6569 | -24404242.6799 | 56541.9579
2014-05-31 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 411304.9853 | 277740.8398 | 249756.5342 | 27984.3055 | -72990824.2364 | -3397260.3266 | 294392.1981 | 63749993.7103 | 133637949.8183 | 69887956.108 | -24460784.6378 | 56541.9579
2014-06-30 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 411304.9853 | 277740.8398 | 249756.5342 | 27984.3055 | -73402129.2218 | -3675001.1663 | 322376.5037 | 63338688.725 | 133388193.2841 | 70049504.5591 | -24517326.5957 | 56541.9579
2014-07-31 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 411304.9853 | 277740.8398 | 249756.5342 | 27984.3055 | -73813434.2071 | -3952742.0061 | 350360.8092 | 62927383.7397 | 133138436.7498 | 70211053.0102 | -24573868.5536 | 56541.9579
2014-08-31 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 411304.9853 | 277740.8398 | 249756.5342 | 27984.3055 | -74224739.1924 | -4230482.8458 | 378345.1147 | 62516078.7543 | 132888680.2156 | 70372601.4613 | -24630410.5114 | 56541.9579
2014-09-30 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 411304.9853 | 277740.8398 | 249756.5342 | 27984.3055 | -74636044.1777 | -4508223.6856 | 406329.4202 | 62104773.769 | 132638923.6814 | 70534149.9124 | -24686952.4693 | 56541.9579
2014-10-31 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 411304.9853 | 277740.8398 | 249756.5342 | 27984.3055 | -75047349.163 | -4785964.5253 | 434313.7258 | 61693468.7837 | 132389167.1472 | 70695698.3635 | -24743494.4272 | 56541.9579
2014-11-30 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 411304.9853 | 277740.8398 | 249756.5342 | 27984.3055 | -75458654.1483 | -5063705.3651 | 462298.0313 | 61282163.7984 | 132139410.6129 | 70857246.8146 | -24800036.3851 | 56541.9579
2014-12-31 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 411304.9853 | 277740.8398 | 249756.5342 | 27984.3055 | -75869959.1337 | -5341446.2048 | 490282.3368 | 60870858.8131 | 131889654.0787 | 71018795.2656 | -24856578.343 | 56541.9579
12ME December 2015 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 4565092.2072 | 3332890.077 | 2997078.4107 | 335811.6663 | -80435051.3408 | -8674336.2819 | 826094.0031 | 56305766.6059 | 128892575.668 | 72586809.0621 | -25405383.1717 | 548804.8288
12ME December 2016 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 4223240.1623 | 3332890.077 | 2997078.4107 | 335811.6663 | -84658291.5031 | -12007226.3589 | 1161905.6694 | 52082526.4436 | 125895497.2573 | 73812970.8136 | -25834539.7848 | 429156.613
12ME December 2017 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 3906001.4646 | 3332890.077 | 2997078.4107 | 335811.6663 | -88564292.9677 | -15340116.4359 | 1497717.3358 | 48176524.979 | 122898418.8466 | 74721893.8676 | -26152662.8537 | 318123.0689
12ME December 2018 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 3613376.1142 | 3332890.077 | 2997078.4107 | 335811.6663 | -92177669.082 | -18673006.5129 | 1833529.0021 | 44563148.8647 | 119901340.4359 | 75338191.5711 | -26368367.0499 | 215704.1962
12ME December 2019 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 3341945.5906 | 3332890.077 | 2997078.4107 | 335811.6663 | -95519614.6726 | -22005896.59 | 2169340.6684 | 41221203.2741 | 116904262.0251 | 75683058.751 | -26489070.5629 | 120703.513
12ME December 2020 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 3091709.8938 | 3332890.077 | 2997078.4107 | 335811.6663 | -98611324.5664 | -25338786.667 | 2505152.3347 | 38129493.3804 | 113907183.6144 | 75777690.2341 | -26522191.5819 | 33121.0191
12ME December 2021 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 3050687.6484 | 3332890.077 | 2997078.4107 | 335811.6663 | -101662012.2148 | -28671676.744 | 2840964.001 | 35078805.732 | 110910105.2037 | 75831299.4717 | -26540954.8151 | 18763.2332
12ME December 2022 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 3050003.9443 | 3332890.077 | 2997078.4107 | 335811.6663 | -104712016.1591 | -32004566.8211 | 3176775.6673 | 32028801.7877 | 107913026.793 | 75884225.0053 | -26559478.7519 | 18523.9368
12ME December 2023 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 3050687.6484 | 3332890.077 | 2997078.4107 | 335811.6663 | -107762703.8075 | -35337456.8981 | 3512587.3336 | 28978114.1393 | 104915948.3823 | 75937834.243 | -26578241.9851 | 18763.2332
12ME December 2024 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 3050003.9443 | 3332890.077 | 2997078.4107 | 335811.6663 | -110812707.7518 | -38670346.9751 | 3848398.9999 | 25928110.195 | 101918869.9716 | 75990759.7766 | -26596765.9218 | 18523.9368
12ME December 2025 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 3050687.6484 | 3332890.077 | 2997078.4107 | 335811.6663 | -113863395.4001 | -42003237.0521 | 4184210.6663 | 22877422.5466 | 98921791.5608 | 76044369.0143 | -26615529.155 | 18763.2332
12ME December 2026 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 3050003.9443 | 3332890.077 | 2997078.4107 | 335811.6663 | -116913399.3445 | -45336127.1292 | 4520022.3326 | 19827418.6023 | 95924713.1501 | 76097294.5479 | -26634053.0917 | 18523.9368
12ME December 2027 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 3050687.6484 | 3332890.077 | 2997078.4107 | 335811.6663 | -119964086.9928 | -48669017.2062 | 4855833.9989 | 16776730.9539 | 92927634.7394 | 76150903.7855 | -26652816.3249 | 18763.2332
12ME December 2028 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 3050003.9443 | 3332890.077 | 2997078.4107 | 335811.6663 | -123014090.9371 | -52001907.2832 | 5191645.6652 | 13726727.0096 | 89930556.3287 | 76203829.3191 | -26671340.2617 | 18523.9368
12ME December 2029 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 3050687.6484 | 3332890.077 | 2997078.4107 | 335811.6663 | -126064778.5855 | -55334797.3602 | 5527457.3315 | 10676039.3612 | 86933477.918 | 76257438.5568 | -26690103.4949 | 18763.2332
12ME December 2030 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 3050003.9443 | 3332890.077 | 2997078.4107 | 335811.6663 | -129114782.5298 | -58667687.4373 | 5863268.9978 | 7626035.4169 | 83936399.5073 | 76310364.0904 | -26708627.4316 | 18523.9368
12ME December 2031 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 3050687.6484 | 3332890.077 | 2997078.4107 | 335811.6663 | -132165470.1782 | -62000577.5143 | 6199080.6641 | 4575347.7685 | 80939321.0966 | 76363973.3281 | -26727390.6648 | 18763.2332
12ME December 2032 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 3050003.9443 | 3332890.077 | 2997078.4107 | 335811.6663 | -135215474.1225 | -65333467.5913 | 6534892.3304 | 1525343.8242 | 77942242.6858 | 76416898.8616 | -26745914.6016 | 18523.9368
12ME December 2033 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 1525343.8242 | 3332890.077 | 2997078.4107 | 335811.6663 | -136740817.9467 | -68666357.6684 | 6870703.9968 | 0 | 74945164.2751 | 74945164.2751 | -26230807.4963 | -515107.1053
12ME December 2034 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 0 | 3332890.077 | 2997078.4107 | 335811.6663 | -136740817.9467 | -71999247.7454 | 7206515.6631 | 0 | 71948085.8644 | 71948085.8644 | -25181830.0525 | -1048977.4438
12ME December 2035 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 0 | 3332890.077 | 2997078.4107 | 335811.6663 | -136740817.9467 | -75332137.8224 | 7542327.3294 | 0 | 68951007.4537 | 68951007.4537 | -24132852.6088 | -1048977.4438
12ME December 2036 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 0 | 3332890.077 | 2997078.4107 | 335811.6663 | -136740817.9467 | -78665027.8994 | 7878138.9957 | 0 | 65953929.043 | 65953929.043 | -23083875.165 | -1048977.4438
12ME December 2037 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 0 | 3332890.077 | 2997078.4107 | 335811.6663 | -136740817.9467 | -81997917.9765 | 8213950.662 | 0 | 62956850.6323 | 62956850.6323 | -22034897.7213 | -1048977.4438
12ME December 2038 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 0 | 3332890.077 | 2997078.4107 | 335811.6663 | -136740817.9467 | -85330808.0535 | 8549762.3283 | 0 | 59959772.2215 | 59959772.2215 | -20985920.2775 | -1048977.4438
12ME December 2039 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 0 | 3332890.077 | 2997078.4107 | 335811.6663 | -136740817.9467 | -88663698.1305 | 8885573.9946 | 0 | 56962693.8108 | 56962693.8108 | -19936942.8338 | -1048977.4438
12ME December 2040 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 0 | 3332890.077 | 2997078.4107 | 335811.6663 | -136740817.9467 | -91996588.2075 | 9221385.6609 | 0 | 53965615.4001 | 53965615.4001 | -18887965.39 | -1048977.4438
12ME December 2041 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 0 | 3332890.077 | 2997078.4107 | 335811.6663 | -136740817.9467 | -95329478.2846 | 9557197.3272 | 0 | 50968536.9894 | 50968536.9894 | -17838987.9463 | -1048977.4438
12ME December 2042 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 0 | 3332890.077 | 2997078.4107 | 335811.6663 | -136740817.9467 | -98662368.3616 | 9893008.9936 | 0 | 47971458.5787 | 47971458.5787 | -16790010.5025 | -1048977.4438
12ME December 2043 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 0 | 3332890.077 | 2997078.4107 | 335811.6663 | -136740817.9467 | -101995258.4386 | 10228820.6599 | 0 | 44974380.168 | 44974380.168 | -15741033.0588 | -1048977.4438
12ME December 2044 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 0 | 3332890.077 | 2997078.4107 | 335811.6663 | -136740817.9467 | -105328148.5157 | 10564632.3262 | 0 | 41977301.7573 | 41977301.7573 | -14692055.615 | -1048977.4438
12ME December 2045 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 0 | 3332890.077 | 2997078.4107 | 335811.6663 | -136740817.9467 | -108661038.5927 | 10900443.9925 | 0 | 38980223.3465 | 38980223.3465 | -13643078.1713 | -1048977.4438
12ME December 2046 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 0 | 3332890.077 | 2997078.4107 | 335811.6663 | -136740817.9467 | -111993928.6697 | 11236255.6588 | 0 | 35983144.9358 | 35983144.9358 | -12594100.7275 | -1048977.4438
12ME December 2047 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 0 | 3332890.077 | 2997078.4107 | 335811.6663 | -136740817.9467 | -115326818.7467 | 11572067.3251 | 0 | 32986066.5251 | 32986066.5251 | -11545123.2838 | -1048977.4438
12ME December 2048 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 0 | 3332890.077 | 2997078.4107 | 335811.6663 | -136740817.9467 | -118659708.8238 | 11907878.9914 | 0 | 29988988.1144 | 29988988.1144 | -10496145.84 | -1048977.4438
12ME December 2049 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 0 | 3332890.077 | 2997078.4107 | 335811.6663 | -136740817.9467 | -121992598.9008 | 12243690.6577 | 0 | 26991909.7037 | 26991909.7037 | -9447168.3963 | -1048977.4438
12ME December 2050 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 0 | 3332890.077 | 2997078.4107 | 335811.6663 | -136740817.9467 | -125325488.9778 | 12579502.3241 | 0 | 23994831.293 | 23994831.293 | -8398190.9525 | -1048977.4438
12ME December 2051 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 0 | 3332890.077 | 2997078.4107 | 335811.6663 | -136740817.9467 | -128658379.0549 | 12915313.9904 | 0 | 20997752.8822 | 20997752.8822 | -7349213.5088 | -1048977.4438
12ME December 2052 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 0 | 3332890.077 | 2997078.4107 | 335811.6663 | -136740817.9467 | -131991269.1319 | 13251125.6567 | 0 | 18000674.4715 | 18000674.4715 | -6300236.065 | -1048977.4438
12ME December 2053 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 0 | 3332890.077 | 2997078.4107 | 335811.6663 | -136740817.9467 | -135324159.2089 | 13586937.323 | 0 | 15003596.0608 | 15003596.0608 | -5251258.6213 | -1048977.4438
12ME December 2054 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 0 | 3332890.077 | 2997078.4107 | 335811.6663 | -136740817.9467 | -138657049.2859 | 13922748.9893 | 0 | 12006517.6501 | 12006517.6501 | -4202281.1775 | -1048977.4438
12ME December 2055 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 0 | 3332890.077 | 2997078.4107 | 335811.6663 | -136740817.9467 | -141989939.363 | 14258560.6556 | 0 | 9009439.2394 | 9009439.2394 | -3153303.7338 | -1048977.4438
12ME December 2056 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 0 | 3332890.077 | 2997078.4107 | 335811.6663 | -136740817.9467 | -145322829.44 | 14594372.3219 | 0 | 6012360.8287 | 6012360.8287 | -2104326.29 | -1048977.4438
12ME December 2057 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 0 | 3332890.077 | 2997078.4107 | 335811.6663 | -136740817.9467 | -148655719.517 | 14930183.9882 | 0 | 3015282.418 | 3015282.418 | -1055348.8463 | -1048977.4438
12ME December 2058 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 0 | 3406406.5955 | 3015282.418 | 391124.1775 | -136740817.9467 | -152062126.1125 | 15321308.1658 | 0 | 0 | 0 | 0 | -1055348.8463
12ME December 2059 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 0 | 0 | 0 | 0 | -136740817.9467 | -152062126.1125 | 15321308.1658 | 0 | 0 | 0 | 0 | 0
12ME December 2060 | 136740817.9467 | 152062126.1125 | 136740817.9467 | 0 | 0 | 0 | 0 | -136740817.9467 | -152062126.1125 | 15321308.1658 | 0 | 0 | 0 | 0 | 0
12ME December 2061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12ME December 2062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total - 12ME Nov '14 |  |  |  | 14141774.8438 | 3332890.077 | 2997078.4107 | 335811.6663 | [7 empty] | 3900643.7516
AMA - 12ME Nov '14 | 136740817.9467 | 152062126.1125 | 136740817.9467 |  |  |  |  | -72607236.1106 | -3397260.3266 | 294392.1981 | 64133581.8361 | 133637949.8183 |  | -24326528.7938

## #1 DFIT- FSC
Baker Upgrade Book & Tax Depreciation: December 1, 2013 through November 30, 2014
Lower Baker FSC |  | Book Basis | Tax Basis
In service Date February 14th 2013 |  | 56867149.2009 | 56107015.7329
| OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK
20 Year MACRS Table | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027
(Half year) | 51.88% | 3.61% | 3.338% | 3.088% | 2.857% | 2.643% | 2.444% | 2.261% | 2.231% | 2.231% | 2.231% | 2.231% | 2.231% | 2.231% | 2.231%
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| OK | OK | OK | OK | OK | OK
| 2028 | 2029 | 2030 | 2031 | 2032 | 2033
| 2.231% | 2.231% | 2.231% | 2.231% | 2.231% | 1.115% | 100%
| 16 | 17 | 18 | 19 | 20 | 21 | 0%
Date | Depreciable Plant Balance |  |  | Depreciation Expense |  |  |  | Accumulated Depreciation |  |  | Net Book Value |  | NBV Diff | ADFIT | DFIT
|  |  | Book |  | 2.192% | Book Depr. |  |  |  | BOOK |  | Book
| Tax | Book | Using Tax Basis | Tax | Book | Using Tax Basis |  | Tax | Book | Permanent Difference | Tax | based on Tax Basis | Book > Tax | 35% | Expense
|  |  |  | (d) = (a) x Tax | (e) = (b) x 2.20% | (f) = (c) x 2.20% | Net Difference | [7 empty] | (o) = - curr month (n)
| (a) | (b) | (c) | Table | ¸ 12 mos. | ¸ 12 mos. | (g) = (e) x (f) | (h) = prior month - (d) | (i) = prior month - (e) | (j) = prior month - (g) | (k) = (a) + (h) | (l) = (c) + (i) +(j) | (m) = (k) - (l) | (n) = - (m) * 35% | + prior month (n)
2010-11-30 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2010-12-31 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2011-01-31 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2011-02-28 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2011-03-31 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2011-04-30 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2011-05-31 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2011-06-30 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2011-07-31 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2011-08-31 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2011-09-30 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2011-10-31 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2011-11-30 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2011-12-31 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2012-09-30
2012-10-31
2012-11-30
2012-12-31
2013-01-31
2013-02-28 | 56107015.7329 | 56867149.2009 | 56107015.7329 | 2645955.8556 | 55643.3631 | 54899.5877 | 743.7753 | -2645955.8556 | -55643.3631 | 743.7753 | 53461059.8773 | 56052116.1452 | 2591056.2678 | -906869.6937 | 906869.6937
2013-03-31 | 56107015.7329 | 56867149.2009 | 56107015.7329 | 2645955.8556 | 103867.6111 | 102479.2305 | 1388.3806 | -5291911.7112 | -159510.9741 | 2132.1559 | 50815104.0217 | 55949636.9147 | 5134532.893 | -1797086.5125 | 890216.8188
2013-04-30 | 56107015.7329 | 56867149.2009 | 56107015.7329 | 2645955.8556 | 103867.6111 | 102479.2305 | 1388.3806 | -7937867.5668 | -263378.5852 | 3520.5366 | 48169148.1661 | 55847157.6842 | 7678009.5181 | -2687303.3313 | 890216.8188
2013-05-31 | 56107015.7329 | 56867149.2009 | 56107015.7329 | 2645955.8556 | 103867.6111 | 102479.2305 | 1388.3806 | -10583823.4223 | -367246.1963 | 4908.9172 | 45523192.3106 | 55744678.4538 | 10221486.1432 | -3577520.1501 | 890216.8188
2013-06-30 | 56107015.7329 | 56867149.2009 | 56107015.7329 | 2645955.8556 | 103867.6111 | 102479.2305 | 1388.3806 | -13229779.2779 | -471113.8073 | 6297.2978 | 42877236.455 | 55642199.2233 | 12764962.7684 | -4467736.9689 | 890216.8188
2013-07-31 | 56107015.7329 | 56867149.2009 | 56107015.7329 | 2645955.8556 | 103867.6111 | 102479.2305 | 1388.3806 | -15875735.1335 | -574981.4184 | 7685.6784 | 40231280.5994 | 55539719.9929 | 15308439.3935 | -5357953.7877 | 890216.8188
2013-08-31 | 56107015.7329 | 56867149.2009 | 56107015.7329 | 2645955.8556 | 103867.6111 | 102479.2305 | 1388.3806 | -18521690.9891 | -678849.0295 | 9074.059 | 37585324.7438 | 55437240.7624 | 17851916.0186 | -6248170.6065 | 890216.8188
2013-09-30 | 56107015.7329 | 56867149.2009 | 56107015.7329 | 2645955.8556 | 103867.6111 | 102479.2305 | 1388.3806 | -21167646.8447 | -782716.6406 | 10462.4396 | 34939368.8882 | 55334761.532 | 20395392.6437 | -7138387.4253 | 890216.8188
2013-10-31 | 56107015.7329 | 56867149.2009 | 56107015.7329 | 2645955.8556 | 103867.6111 | 102479.2305 | 1388.3806 | -23813602.7003 | -886584.2516 | 11850.8202 | 32293413.0326 | 55232282.3015 | 22938869.2689 | -8028604.2441 | 890216.8188
2013-11-30 | 56107015.7329 | 56867149.2009 | 56107015.7329 | 2645955.8556 | 103867.6111 | 102479.2305 | 1388.3806 | -26459558.5559 | -990451.8627 | 13239.2008 | 29647457.177 | 55129803.071 | 25482345.894 | -8918821.0629 | 890216.8188
2013-12-31 | 56107015.7329 | 56867149.2009 | 56107015.7329 | 2645955.8556 | 103867.6111 | 102479.2305 | 1388.3806 | -29105514.4114 | -1094319.4738 | 14627.5814 | 27001501.3215 | 55027323.8406 | 28025822.5191 | -9809037.8817 | 890216.8188
2014-01-31 | 56107015.7329 | 56867149.2009 | 56107015.7329 | 168765.2277 | 103867.6111 | 102479.2305 | 1388.3806 | -29274279.6392 | -1198187.0848 | 16015.9621 | 26832736.0937 | 54924844.6101 | 28092108.5164 | -9832237.9807 | 23200.099
2014-02-28 | 56107015.7329 | 56867149.2009 | 56107015.7329 | 168765.2277 | 103867.6111 | 102479.2305 | 1388.3806 | -29443044.8669 | -1302054.6959 | 17404.3427 | 26663970.866 | 54822365.3797 | 28158394.5137 | -9855438.0798 | 23200.099
2014-03-31 | 56107015.7329 | 56867149.2009 | 56107015.7329 | 168765.2277 | 103867.6111 | 102479.2305 | 1388.3806 | -29611810.0947 | -1405922.307 | 18792.7233 | 26495205.6382 | 54719886.1492 | 28224680.511 | -9878638.1788 | 23200.099
2014-04-30 | 56107015.7329 | 56867149.2009 | 56107015.7329 | 168765.2277 | 103867.6111 | 102479.2305 | 1388.3806 | -29780575.3224 | -1509789.918 | 20181.1039 | 26326440.4105 | 54617406.9188 | 28290966.5083 | -9901838.2779 | 23200.099
2014-05-31 | 56107015.7329 | 56867149.2009 | 56107015.7329 | 168765.2277 | 103867.6111 | 102479.2305 | 1388.3806 | -29949340.5501 | -1613657.5291 | 21569.4845 | 26157675.1828 | 54514927.6883 | 28357252.5055 | -9925038.3769 | 23200.099
2014-06-30 | 56107015.7329 | 56867149.2009 | 56107015.7329 | 168765.2277 | 103867.6111 | 102479.2305 | 1388.3806 | -30118105.7779 | -1717525.1402 | 22957.8651 | 25988909.955 | 54412448.4578 | 28423538.5028 | -9948238.476 | 23200.099
2014-07-31 | 56107015.7329 | 56867149.2009 | 56107015.7329 | 168765.2277 | 103867.6111 | 102479.2305 | 1388.3806 | -30286871.0056 | -1821392.7512 | 24346.2457 | 25820144.7273 | 54309969.2274 | 28489824.5001 | -9971438.575 | 23200.099
2014-08-31 | 56107015.7329 | 56867149.2009 | 56107015.7329 | 168765.2277 | 103867.6111 | 102479.2305 | 1388.3806 | -30455636.2334 | -1925260.3623 | 25734.6263 | 25651379.4995 | 54207489.9969 | 28556110.4974 | -9994638.6741 | 23200.099
2014-09-30 | 56107015.7329 | 56867149.2009 | 56107015.7329 | 168765.2277 | 103867.6111 | 102479.2305 | 1388.3806 | -30624401.4611 | -2029127.9734 | 27123.007 | 25482614.2718 | 54105010.7665 | 28622396.4947 | -10017838.7731 | 23200.099
2014-10-31 | 56107015.7329 | 56867149.2009 | 56107015.7329 | 168765.2277 | 103867.6111 | 102479.2305 | 1388.3806 | -30793166.6888 | -2132995.5845 | 28511.3876 | 25313849.0441 | 54002531.536 | 28688682.492 | -10041038.8722 | 23200.099
2014-11-30 | 56107015.7329 | 56867149.2009 | 56107015.7329 | 168765.2277 | 103867.6111 | 102479.2305 | 1388.3806 | -30961931.9166 | -2236863.1955 | 29899.7682 | 25145083.8163 | 53900052.3056 | 28754968.4892 | -10064238.9712 | 23200.099
2014-12-31 | 56107015.7329 | 56867149.2009 | 56107015.7329 | 168765.2277 | 103867.6111 | 102479.2305 | 1388.3806 | -31130697.1443 | -2340730.8066 | 31288.1488 | 24976318.5886 | 53797573.0751 | 28821254.4865 | -10087439.0703 | 23200.099
12ME December 2015 | 56107015.7329 | 56867149.2009 | 56107015.7329 | 1873132.7202 | 1246411.3328 | 1229750.7655 | 16660.5673 | -33003829.8646 | -3587142.1394 | 47948.7161 | 23103185.8683 | 52567822.3096 | 29464636.4413 | -10312622.7544 | 225183.6842
12ME December 2016 | 56107015.7329 | 56867149.2009 | 56107015.7329 | 1732865.1809 | 1246411.3328 | 1229750.7655 | 16660.5673 | -34736695.0455 | -4833553.4722 | 64609.2835 | 21370320.6874 | 51338071.5441 | 29967750.8567 | -10488712.7998 | 176090.0454
12ME December 2017 | 56107015.7329 | 56867149.2009 | 56107015.7329 | 1602696.9044 | 1246411.3328 | 1229750.7655 | 16660.5673 | -36339391.9499 | -6079964.8051 | 81269.8508 | 19767623.783 | 50108320.7787 | 30340696.9956 | -10619243.9485 | 130531.1486
12ME December 2018 | 56107015.7329 | 56867149.2009 | 56107015.7329 | 1482627.8907 | 1246411.3328 | 1229750.7655 | 16660.5673 | -37822019.8406 | -7326376.1379 | 97930.4182 | 18284995.8923 | 48878570.0132 | 30593574.1209 | -10707750.9423 | 88506.9938
12ME December 2019 | 56107015.7329 | 56867149.2009 | 56107015.7329 | 1371255.4645 | 1246411.3328 | 1229750.7655 | 16660.5673 | -39193275.3051 | -8572787.4707 | 114590.9855 | 16913740.4278 | 47648819.2477 | 30735078.8199 | -10757277.587 | 49526.6447
12ME December 2020 | 56107015.7329 | 56867149.2009 | 56107015.7329 | 1268579.6257 | 1246411.3328 | 1229750.7655 | 16660.5673 | -40461854.9309 | -9819198.8036 | 131251.5529 | 15645160.802 | 46419068.4822 | 30773907.6802 | -10770867.6881 | 13590.1011
12ME December 2021 | 56107015.7329 | 56867149.2009 | 56107015.7329 | 1251747.521 | 1246411.3328 | 1229750.7655 | 16660.5673 | -41713602.4519 | -11065610.1364 | 147912.1202 | 14393413.281 | 45189317.7167 | 30795904.4357 | -10778566.5525 | 7698.8644
12ME December 2022 | 56107015.7329 | 56867149.2009 | 56107015.7329 | 1251466.9859 | 1246411.3328 | 1229750.7655 | 16660.5673 | -42965069.4378 | -12312021.4692 | 164572.6876 | 13141946.2951 | 43959566.9512 | 30817620.6561 | -10786167.2296 | 7600.6772
12ME December 2023 | 56107015.7329 | 56867149.2009 | 56107015.7329 | 1251747.521 | 1246411.3328 | 1229750.7655 | 16660.5673 | -44216816.9588 | -13558432.802 | 181233.2549 | 11890198.7741 | 42729816.1858 | 30839617.4116 | -10793866.0941 | 7698.8644
12ME December 2024 | 56107015.7329 | 56867149.2009 | 56107015.7329 | 1251466.9859 | 1246411.3328 | 1229750.7655 | 16660.5673 | -45468283.9447 | -14804844.1349 | 197893.8222 | 10638731.7882 | 41500065.4203 | 30861333.6321 | -10801466.7712 | 7600.6772
12ME December 2025 | 56107015.7329 | 56867149.2009 | 56107015.7329 | 1251747.521 | 1246411.3328 | 1229750.7655 | 16660.5673 | -46720031.4657 | -16051255.4677 | 214554.3896 | 9386984.2672 | 40270314.6548 | 30883330.3876 | -10809165.6357 | 7698.8644
12ME December 2026 | 56107015.7329 | 56867149.2009 | 56107015.7329 | 1251466.9859 | 1246411.3328 | 1229750.7655 | 16660.5673 | -47971498.4516 | -17297666.8005 | 231214.9569 | 8135517.2813 | 39040563.8893 | 30905046.608 | -10816766.3128 | 7600.6772
12ME December 2027 | 56107015.7329 | 56867149.2009 | 56107015.7329 | 1251747.521 | 1246411.3328 | 1229750.7655 | 16660.5673 | -49223245.9726 | -18544078.1334 | 247875.5243 | 6883769.7603 | 37810813.1238 | 30927043.3636 | -10824465.1772 | 7698.8644
12ME December 2028 | 56107015.7329 | 56867149.2009 | 56107015.7329 | 1251466.9859 | 1246411.3328 | 1229750.7655 | 16660.5673 | -50474712.9586 | -19790489.4662 | 264536.0916 | 5632302.7743 | 36581062.3583 | 30948759.584 | -10832065.8544 | 7600.6772
12ME December 2029 | 56107015.7329 | 56867149.2009 | 56107015.7329 | 1251747.521 | 1246411.3328 | 1229750.7655 | 16660.5673 | -51726460.4796 | -21036900.799 | 281196.659 | 4380555.2533 | 35351311.5929 | 30970756.3395 | -10839764.7188 | 7698.8644
12ME December 2030 | 56107015.7329 | 56867149.2009 | 56107015.7329 | 1251466.9859 | 1246411.3328 | 1229750.7655 | 16660.5673 | -52977927.4655 | -22283312.1318 | 297857.2263 | 3129088.2674 | 34121560.8274 | 30992472.56 | -10847365.396 | 7600.6772
12ME December 2031 | 56107015.7329 | 56867149.2009 | 56107015.7329 | 1251747.521 | 1246411.3328 | 1229750.7655 | 16660.5673 | -54229674.9865 | -23529723.4647 | 314517.7937 | 1877340.7464 | 32891810.0619 | 31014469.3155 | -10855064.2604 | 7698.8644
12ME December 2032 | 56107015.7329 | 56867149.2009 | 56107015.7329 | 1251466.9859 | 1246411.3328 | 1229750.7655 | 16660.5673 | -55481141.9724 | -24776134.7975 | 331178.361 | 625873.7605 | 31662059.2964 | 31036185.5359 | -10862664.9376 | 7600.6772
12ME December 2033 | 56107015.7329 | 56867149.2009 | 56107015.7329 | 625873.7605 | 1246411.3328 | 1229750.7655 | 16660.5673 | -56107015.7329 | -26022546.1303 | 347838.9283 | 0 | 30432308.5309 | 30432308.5309 | -10651307.9858 | -211356.9517
12ME December 2034 | 56107015.7329 | 56867149.2009 | 56107015.7329 |  | 1246411.3328 | 1229750.7655 | 16660.5673 | -56107015.7329 | -27268957.4631 | 364499.4957 | 0 | 29202557.7654 | 29202557.7654 | -10220895.2179 | -430412.7679
12ME December 2035 | 56107015.7329 | 56867149.2009 | 56107015.7329 |  | 1246411.3328 | 1229750.7655 | 16660.5673 | -56107015.7329 | -28515368.796 | 381160.063 | 0 | 27972807 | 27972807 | -9790482.45 | -430412.7679
12ME December 2036 | 56107015.7329 | 56867149.2009 | 56107015.7329 |  | 1246411.3328 | 1229750.7655 | 16660.5673 | -56107015.7329 | -29761780.1288 | 397820.6304 | 0 | 26743056.2345 | 26743056.2345 | -9360069.6821 | -430412.7679
12ME December 2037 | 56107015.7329 | 56867149.2009 | 56107015.7329 |  | 1246411.3328 | 1229750.7655 | 16660.5673 | -56107015.7329 | -31008191.4616 | 414481.1977 | 0 | 25513305.469 | 25513305.469 | -8929656.9141 | -430412.7679
12ME December 2038 | 56107015.7329 | 56867149.2009 | 56107015.7329 |  | 1246411.3328 | 1229750.7655 | 16660.5673 | -56107015.7329 | -32254602.7945 | 431141.7651 | 0 | 24283554.7035 | 24283554.7035 | -8499244.1462 | -430412.7679
12ME December 2039 | 56107015.7329 | 56867149.2009 | 56107015.7329 |  | 1246411.3328 | 1229750.7655 | 16660.5673 | -56107015.7329 | -33501014.1273 | 447802.3324 | 0 | 23053803.938 | 23053803.938 | -8068831.3783 | -430412.7679
12ME December 2040 | 56107015.7329 | 56867149.2009 | 56107015.7329 |  | 1246411.3328 | 1229750.7655 | 16660.5673 | -56107015.7329 | -34747425.4601 | 464462.8998 | 0 | 21824053.1725 | 21824053.1725 | -7638418.6104 | -430412.7679
12ME December 2041 | 56107015.7329 | 56867149.2009 | 56107015.7329 |  | 1246411.3328 | 1229750.7655 | 16660.5673 | -56107015.7329 | -35993836.7929 | 481123.4671 | 0 | 20594302.4071 | 20594302.4071 | -7208005.8425 | -430412.7679
12ME December 2042 | 56107015.7329 | 56867149.2009 | 56107015.7329 |  | 1246411.3328 | 1229750.7655 | 16660.5673 | -56107015.7329 | -37240248.1258 | 497784.0345 | 0 | 19364551.6416 | 19364551.6416 | -6777593.0746 | -430412.7679
12ME December 2043 | 56107015.7329 | 56867149.2009 | 56107015.7329 |  | 1246411.3328 | 1229750.7655 | 16660.5673 | -56107015.7329 | -38486659.4586 | 514444.6018 | 0 | 18134800.8761 | 18134800.8761 | -6347180.3066 | -430412.7679
12ME December 2044 | 56107015.7329 | 56867149.2009 | 56107015.7329 |  | 1246411.3328 | 1229750.7655 | 16660.5673 | -56107015.7329 | -39733070.7914 | 531105.1691 | 0 | 16905050.1106 | 16905050.1106 | -5916767.5387 | -430412.7679
12ME December 2045 | 56107015.7329 | 56867149.2009 | 56107015.7329 |  | 1246411.3328 | 1229750.7655 | 16660.5673 | -56107015.7329 | -40979482.1243 | 547765.7365 | 0 | 15675299.3451 | 15675299.3451 | -5486354.7708 | -430412.7679
12ME December 2046 | 56107015.7329 | 56867149.2009 | 56107015.7329 |  | 1246411.3328 | 1229750.7655 | 16660.5673 | -56107015.7329 | -42225893.4571 | 564426.3038 | 0 | 14445548.5796 | 14445548.5796 | -5055942.0029 | -430412.7679
12ME December 2047 | 56107015.7329 | 56867149.2009 | 56107015.7329 |  | 1246411.3328 | 1229750.7655 | 16660.5673 | -56107015.7329 | -43472304.7899 | 581086.8712 | 0 | 13215797.8142 | 13215797.8142 | -4625529.235 | -430412.7679
12ME December 2048 | 56107015.7329 | 56867149.2009 | 56107015.7329 |  | 1246411.3328 | 1229750.7655 | 16660.5673 | -56107015.7329 | -44718716.1227 | 597747.4385 | 0 | 11986047.0487 | 11986047.0487 | -4195116.467 | -430412.7679
12ME December 2049 | 56107015.7329 | 56867149.2009 | 56107015.7329 |  | 1246411.3328 | 1229750.7655 | 16660.5673 | -56107015.7329 | -45965127.4556 | 614408.0059 | 0 | 10756296.2832 | 10756296.2832 | -3764703.6991 | -430412.7679
12ME December 2050 | 56107015.7329 | 56867149.2009 | 56107015.7329 |  | 1246411.3328 | 1229750.7655 | 16660.5673 | -56107015.7329 | -47211538.7884 | 631068.5732 | 0 | 9526545.5177 | 9526545.5177 | -3334290.9312 | -430412.7679
12ME December 2051 | 56107015.7329 | 56867149.2009 | 56107015.7329 |  | 1246411.3328 | 1229750.7655 | 16660.5673 | -56107015.7329 | -48457950.1212 | 647729.1406 | 0 | 8296794.7522 | 8296794.7522 | -2903878.1633 | -430412.7679
12ME December 2052 | 56107015.7329 | 56867149.2009 | 56107015.7329 |  | 1246411.3328 | 1229750.7655 | 16660.5673 | -56107015.7329 | -49704361.454 | 664389.7079 | 0 | 7067043.9868 | 7067043.9868 | -2473465.3954 | -430412.7679
12ME December 2053 | 56107015.7329 | 56867149.2009 | 56107015.7329 |  | 1246411.3328 | 1229750.7655 | 16660.5673 | -56107015.7329 | -50950772.7869 | 681050.2752 | 0 | 5837293.2213 | 5837293.2213 | -2043052.6274 | -430412.7679
12ME December 2054 | 56107015.7329 | 56867149.2009 | 56107015.7329 |  | 1246411.3328 | 1229750.7655 | 16660.5673 | -56107015.7329 | -52197184.1197 | 697710.8426 | 0 | 4607542.4558 | 4607542.4558 | -1612639.8595 | -430412.7679
12ME December 2055 | 56107015.7329 | 56867149.2009 | 56107015.7329 |  | 1246411.3328 | 1229750.7655 | 16660.5673 | -56107015.7329 | -53443595.4525 | 714371.4099 | 0 | 3377791.6903 | 3377791.6903 | -1182227.0916 | -430412.7679
12ME December 2056 | 56107015.7329 | 56867149.2009 | 56107015.7329 |  | 1246411.3328 | 1229750.7655 | 16660.5673 | -56107015.7329 | -54690006.7854 | 731031.9773 | 0 | 2148040.9248 | 2148040.9248 | -751814.3237 | -430412.7679
12ME December 2057 | 56107015.7329 | 56867149.2009 | 56107015.7329 |  | 1246411.3328 | 1229750.7655 | 16660.5673 | -56107015.7329 | -55936418.1182 | 747692.5446 | 0 | 918290.1593 | 918290.1593 | -321401.5558 | -430412.7679
12ME December 2058 | 56107015.7329 | 56867149.2009 | 56107015.7329 |  | 930731.0827 | 918290.1593 | 12440.9234 | -56107015.7329 | -56867149.2009 | 760133.468 | 0 | 0 | 0 | 0 | -321401.5558
12ME December 2059 | 56107015.7329 | 56867149.2009 | 56107015.7329 |  | 0 | 0 | 0 | -56107015.7329 | -56867149.2009 | 760133.468 | 0 | 0 | 0 | 0 | 0
12ME December 2060 | 56107015.7329 | 56867149.2009 | 56107015.7329 |  | 0 | 0 | 0 | -56107015.7329 | -56867149.2009 | 760133.468 | 0 | 0 | 0 | 0 | 0
Total - 12ME Nov '14 |  |  |  | 4502373.3607 | 1246411.3328 | 1229750.7655 | 16660.5673 | [7 empty] | 1145417.9083
AMA - 12ME Nov '14 | 56107015.7329 | 56867149.2009 | 56107015.7329 |  |  |  |  | -29846124.274 | -1613657.5291 | 21569.4845 | 26260891.4589 | 54514927.6883 |  | -9888912.6803

## #2 DFIT- Unit 4
Baker Upgrade Book & Tax Depreciation: December 1, 2013 through November 30, 2014
Lower Baker Powerhouse |  | Book Basis | Tax Basis
In service Date June 10, 2013 |  | 95194976.9116 | 80633802.2138
| OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK
20 Year MACRS Table | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027
| 51.88% | 3.61% | 3.338% | 3.088% | 2.857% | 2.643% | 2.444% | 2.261% | 2.231% | 2.231% | 2.231% | 2.231% | 2.231% | 2.231% | 2.231%
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| OK | OK | OK | OK | OK | OK
| 2028 | 2029 | 2030 | 2031 | 2032 | 2033
| 2.231% | 2.231% | 2.231% | 2.231% | 2.231% | 1.115% | 100%
| 16 | 17 | 18 | 19 | 20 | 21 | 0%
Date | Depreciable Plant Balance |  |  | Depreciation Expense |  |  |  | Accumulated Depreciation |  |  | Net Book Value |  | NBV Diff | ADFIT | DFIT
|  |  | Book |  | 2.192% | Book Depr. |  |  |  | BOOK |  | Book
| Tax | Book | Using Tax Basis | Tax | Book | Using Tax Basis |  | Tax | Book | Permanent Difference | Tax | based on Tax Basis | Book > Tax | 35% | Expense
|  |  |  | (d) = (a) x Tax | (e) = (b) x 3.18% | (f) = (c) x 3.18% | Net Difference | [7 empty] | (o) = - curr month (n)
| (a) | (b) | (c) | Table | ¸ 12 mos. | ¸ 12 mos. | (g) = (e) x (f) | (h) = prior month - (d) | (i) = prior month - (e) | (j) = prior month - (g) | (k) = (a) + (h) | (l) = (c) + (i) +(j) | (m) = (k) - (l) | (n) = - (m) * 35% | + prior month (n)
2013-01-31 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2013-02-28 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2013-03-31 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2013-04-30 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2013-05-31 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2013-06-30 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2013-07-31 | 80633802.2138 | 95194976.9116 | 80633802.2138 | 6971464.1497 | 44870.5106 | 38007.0461 | 6863.4645 | -6971464.1497 | -44870.5106 | 6863.4645 | 73662338.0641 | 80595795.1677 | 6933457.1036 | -2426709.9863 | 2426709.9863
2013-08-31 | 80633802.2138 | 95194976.9116 | 80633802.2138 | 6971464.1497 | 173873.2287 | 147277.3038 | 26595.9249 | -13942928.2995 | -218743.7393 | 33459.3894 | 66690873.9144 | 80448517.8639 | 13757643.9496 | -4815175.3823 | 2388465.3961
2013-09-30 | 80633802.2138 | 95194976.9116 | 80633802.2138 | 6971464.1497 | 173873.2287 | 147277.3038 | 26595.9249 | -20914392.4492 | -392616.968 | 60055.3143 | 59719409.7646 | 80301240.5602 | 20581830.7955 | -7203640.7784 | 2388465.3961
2013-10-31 | 80633802.2138 | 95194976.9116 | 80633802.2138 | 6971464.1497 | 173873.2287 | 147277.3038 | 26595.9249 | -27885856.5989 | -566490.1967 | 86651.2392 | 52747945.6149 | 80153963.2564 | 27406017.6415 | -9592106.1745 | 2388465.3961
2013-11-30 | 80633802.2138 | 95194976.9116 | 80633802.2138 | 6971464.1497 | 173873.2287 | 147277.3038 | 26595.9249 | -34857320.7487 | -740363.4254 | 113247.1641 | 45776481.4651 | 80006685.9526 | 34230204.4875 | -11980571.5706 | 2388465.3961
2013-12-31 | 80633802.2138 | 95194976.9116 | 80633802.2138 | 6971464.1497 | 173873.2287 | 147277.3038 | 26595.9249 | -41828784.8984 | -914236.654 | 139843.0891 | 38805017.3154 | 79859408.6488 | 41054391.3334 | -14369036.9667 | 2388465.3961
2014-01-31 | 80633802.2138 | 95194976.9116 | 80633802.2138 | 242539.7576 | 173873.2287 | 147277.3038 | 26595.9249 | -42071324.656 | -1088109.8827 | 166439.014 | 38562477.5578 | 79712131.3451 | 41149653.7872 | -14402378.8255 | 33341.8588
2014-02-28 | 80633802.2138 | 95194976.9116 | 80633802.2138 | 242539.7576 | 173873.2287 | 147277.3038 | 26595.9249 | -42313864.4136 | -1261983.1114 | 193034.9389 | 38319937.8003 | 79564854.0413 | 41244916.2411 | -14435720.6844 | 33341.8588
2014-03-31 | 80633802.2138 | 95194976.9116 | 80633802.2138 | 242539.7576 | 173873.2287 | 147277.3038 | 26595.9249 | -42556404.1711 | -1435856.3401 | 219630.8638 | 38077398.0427 | 79417576.7375 | 41340178.6949 | -14469062.5432 | 33341.8588
2014-04-30 | 80633802.2138 | 95194976.9116 | 80633802.2138 | 242539.7576 | 173873.2287 | 147277.3038 | 26595.9249 | -42798943.9287 | -1609729.5688 | 246226.7887 | 37834858.2851 | 79270299.4338 | 41435441.1487 | -14502404.402 | 33341.8588
2014-05-31 | 80633802.2138 | 95194976.9116 | 80633802.2138 | 242539.7576 | 173873.2287 | 147277.3038 | 26595.9249 | -43041483.6863 | -1783602.7975 | 272822.7136 | 37592318.5275 | 79123022.13 | 41530703.6025 | -14535746.2609 | 33341.8588
2014-06-30 | 80633802.2138 | 95194976.9116 | 80633802.2138 | 242539.7576 | 173873.2287 | 147277.3038 | 26595.9249 | -43284023.4439 | -1957476.0261 | 299418.6385 | 37349778.7699 | 78975744.8262 | 41625966.0563 | -14569088.1197 | 33341.8588
2014-07-31 | 80633802.2138 | 95194976.9116 | 80633802.2138 | 242539.7576 | 173873.2287 | 147277.3038 | 26595.9249 | -43526563.2015 | -2131349.2548 | 326014.5635 | 37107239.0124 | 78828467.5225 | 41721228.5101 | -14602429.9785 | 33341.8588
2014-08-31 | 80633802.2138 | 95194976.9116 | 80633802.2138 | 242539.7576 | 173873.2287 | 147277.3038 | 26595.9249 | -43769102.959 | -2305222.4835 | 352610.4884 | 36864699.2548 | 78681190.2187 | 41816490.9639 | -14635771.8374 | 33341.8588
2014-09-30 | 80633802.2138 | 95194976.9116 | 80633802.2138 | 242539.7576 | 173873.2287 | 147277.3038 | 26595.9249 | -44011642.7166 | -2479095.7122 | 379206.4133 | 36622159.4972 | 78533912.9149 | 41911753.4177 | -14669113.6962 | 33341.8588
2014-10-31 | 80633802.2138 | 95194976.9116 | 80633802.2138 | 242539.7576 | 173873.2287 | 147277.3038 | 26595.9249 | -44254182.4742 | -2652968.9409 | 405802.3382 | 36379619.7396 | 78386635.6112 | 42007015.8715 | -14702455.555 | 33341.8588
2014-11-30 | 80633802.2138 | 95194976.9116 | 80633802.2138 | 242539.7576 | 173873.2287 | 147277.3038 | 26595.9249 | -44496722.2318 | -2826842.1696 | 432398.2631 | 36137079.9821 | 78239358.3074 | 42102278.3253 | -14735797.4139 | 33341.8588
2014-12-31 | 80633802.2138 | 95194976.9116 | 80633802.2138 | 242539.7576 | 173873.2287 | 147277.3038 | 26595.9249 | -44739261.9893 | -3000715.3982 | 458994.188 | 35894540.2245 | 78092081.0036 | 42197540.7791 | -14769139.2727 | 33341.8588
12ME December 2015 | 80633802.2138 | 95194976.9116 | 80633802.2138 | 2691959.4869 | 2086478.7442 | 1767327.6452 | 319151.099 | -47431221.4762 | -5087194.1424 | 778145.287 | 33202580.7376 | 76324753.3584 | 43122172.6208 | -15092760.4173 | 323621.1446
12ME December 2016 | 80633802.2138 | 95194976.9116 | 80633802.2138 | 2490374.9814 | 2086478.7442 | 1767327.6452 | 319151.099 | -49921596.4576 | -7173672.8866 | 1097296.386 | 30712205.7562 | 74557425.7131 | 43845219.9569 | -15345826.9849 | 253066.5676
12ME December 2017 | 80633802.2138 | 95194976.9116 | 80633802.2138 | 2303304.5602 | 2086478.7442 | 1767327.6452 | 319151.099 | -52224901.0179 | -9260151.6308 | 1416447.4849 | 28408901.196 | 72790098.0679 | 44381196.8719 | -15533418.9052 | 187591.9203
12ME December 2018 | 80633802.2138 | 95194976.9116 | 80633802.2138 | 2130748.2235 | 2086478.7442 | 1767327.6452 | 319151.099 | -54355649.2414 | -11346630.375 | 1735598.5839 | 26278152.9725 | 71022770.4227 | 44744617.4502 | -15660616.1076 | 127197.2024
12ME December 2019 | 80633802.2138 | 95194976.9116 | 80633802.2138 | 1970690.1261 | 2086478.7442 | 1767327.6452 | 319151.099 | -56326339.3675 | -13433109.1192 | 2054749.6829 | 24307462.8464 | 69255442.7774 | 44947979.9311 | -15731792.9759 | 71176.8683
12ME December 2020 | 80633802.2138 | 95194976.9116 | 80633802.2138 | 1823130.2681 | 2086478.7442 | 1767327.6452 | 319151.099 | -58149469.6355 | -15519587.8634 | 2373900.7818 | 22484332.5783 | 67488115.1322 | 45003782.5539 | -15751323.8939 | 19530.918
12ME December 2021 | 80633802.2138 | 95194976.9116 | 80633802.2138 | 1798940.1274 | 2086478.7442 | 1767327.6452 | 319151.099 | -59948409.7629 | -17606066.6076 | 2693051.8808 | 20685392.4509 | 65720787.487 | 45035395.0361 | -15762388.2626 | 11064.3688
12ME December 2022 | 80633802.2138 | 95194976.9116 | 80633802.2138 | 1798536.9584 | 2086478.7442 | 1767327.6452 | 319151.099 | -61746946.7213 | -19692545.3518 | 3012202.9798 | 18886855.4925 | 63953459.8418 | 45066604.3492 | -15773311.5222 | 10923.2596
12ME December 2023 | 80633802.2138 | 95194976.9116 | 80633802.2138 | 1798940.1274 | 2086478.7442 | 1767327.6452 | 319151.099 | -63545886.8487 | -21779024.096 | 3331354.0787 | 17087915.3652 | 62186132.1965 | 45098216.8314 | -15784375.891 | 11064.3688
12ME December 2024 | 80633802.2138 | 95194976.9116 | 80633802.2138 | 1798536.9584 | 2086478.7442 | 1767327.6452 | 319151.099 | -65344423.8071 | -23865502.8402 | 3650505.1777 | 15289378.4068 | 60418804.5513 | 45129426.1445 | -15795299.1506 | 10923.2596
12ME December 2025 | 80633802.2138 | 95194976.9116 | 80633802.2138 | 1798940.1274 | 2086478.7442 | 1767327.6452 | 319151.099 | -67143363.9344 | -25951981.5844 | 3969656.2767 | 13490438.2794 | 58651476.9061 | 45161038.6267 | -15806363.5193 | 11064.3688
12ME December 2026 | 80633802.2138 | 95194976.9116 | 80633802.2138 | 1798536.9584 | 2086478.7442 | 1767327.6452 | 319151.099 | -68941900.8928 | -28038460.3286 | 4288807.3756 | 11691901.321 | 56884149.2608 | 45192247.9398 | -15817286.7789 | 10923.2596
12ME December 2027 | 80633802.2138 | 95194976.9116 | 80633802.2138 | 1798940.1274 | 2086478.7442 | 1767327.6452 | 319151.099 | -70740841.0202 | -30124939.0728 | 4607958.4746 | 9892961.1936 | 55116821.6156 | 45223860.422 | -15828351.1477 | 11064.3688
12ME December 2028 | 80633802.2138 | 95194976.9116 | 80633802.2138 | 1798536.9584 | 2086478.7442 | 1767327.6452 | 319151.099 | -72539377.9786 | -32211417.817 | 4927109.5736 | 8094424.2352 | 53349493.9704 | 45255069.7351 | -15839274.4073 | 10923.2596
12ME December 2029 | 80633802.2138 | 95194976.9116 | 80633802.2138 | 1798940.1274 | 2086478.7442 | 1767327.6452 | 319151.099 | -74338318.106 | -34297896.5612 | 5246260.6725 | 6295484.1078 | 51582166.3251 | 45286682.2173 | -15850338.776 | 11064.3688
12ME December 2030 | 80633802.2138 | 95194976.9116 | 80633802.2138 | 1798536.9584 | 2086478.7442 | 1767327.6452 | 319151.099 | -76136855.0644 | -36384375.3054 | 5565411.7715 | 4496947.1495 | 49814838.6799 | 45317891.5304 | -15861262.0356 | 10923.2596
12ME December 2031 | 80633802.2138 | 95194976.9116 | 80633802.2138 | 1798940.1274 | 2086478.7442 | 1767327.6452 | 319151.099 | -77935795.1918 | -38470854.0496 | 5884562.8705 | 2698007.0221 | 48047511.0347 | 45349504.0126 | -15872326.4044 | 11064.3688
12ME December 2032 | 80633802.2138 | 95194976.9116 | 80633802.2138 | 1798536.9584 | 2086478.7442 | 1767327.6452 | 319151.099 | -79734332.1501 | -40557332.7938 | 6203713.9694 | 899470.0637 | 46280183.3894 | 45380713.3257 | -15883249.664 | 10923.2596
12ME December 2033 | 80633802.2138 | 95194976.9116 | 80633802.2138 | 899470.0637 | 2086478.7442 | 1767327.6452 | 319151.099 | -80633802.2138 | -42643811.538 | 6522865.0684 | 0 | 44512855.7442 | 44512855.7442 | -15579499.5105 | -303750.1535
12ME December 2034 | 80633802.2138 | 95194976.9116 | 80633802.2138 |  | 2086478.7442 | 1767327.6452 | 319151.099 | -80633802.2138 | -44730290.2822 | 6842016.1674 | 0 | 42745528.099 | 42745528.099 | -14960934.8346 | -618564.6758
12ME December 2035 | 80633802.2138 | 95194976.9116 | 80633802.2138 |  | 2086478.7442 | 1767327.6452 | 319151.099 | -80633802.2138 | -46816769.0264 | 7161167.2663 | 0 | 40978200.4537 | 40978200.4537 | -14342370.1588 | -618564.6758
12ME December 2036 | 80633802.2138 | 95194976.9116 | 80633802.2138 |  | 2086478.7442 | 1767327.6452 | 319151.099 | -80633802.2138 | -48903247.7706 | 7480318.3653 | 0 | 39210872.8085 | 39210872.8085 | -13723805.483 | -618564.6758
12ME December 2037 | 80633802.2138 | 95194976.9116 | 80633802.2138 |  | 2086478.7442 | 1767327.6452 | 319151.099 | -80633802.2138 | -50989726.5148 | 7799469.4643 | 0 | 37443545.1633 | 37443545.1633 | -13105240.8071 | -618564.6758
12ME December 2038 | 80633802.2138 | 95194976.9116 | 80633802.2138 |  | 2086478.7442 | 1767327.6452 | 319151.099 | -80633802.2138 | -53076205.259 | 8118620.5632 | 0 | 35676217.518 | 35676217.518 | -12486676.1313 | -618564.6758
12ME December 2039 | 80633802.2138 | 95194976.9116 | 80633802.2138 |  | 2086478.7442 | 1767327.6452 | 319151.099 | -80633802.2138 | -55162684.0032 | 8437771.6622 | 0 | 33908889.8728 | 33908889.8728 | -11868111.4555 | -618564.6758
12ME December 2040 | 80633802.2138 | 95194976.9116 | 80633802.2138 |  | 2086478.7442 | 1767327.6452 | 319151.099 | -80633802.2138 | -57249162.7474 | 8756922.7612 | 0 | 32141562.2276 | 32141562.2276 | -11249546.7796 | -618564.6758
12ME December 2041 | 80633802.2138 | 95194976.9116 | 80633802.2138 |  | 2086478.7442 | 1767327.6452 | 319151.099 | -80633802.2138 | -59335641.4916 | 9076073.8601 | 0 | 30374234.5823 | 30374234.5823 | -10630982.1038 | -618564.6758
12ME December 2042 | 80633802.2138 | 95194976.9116 | 80633802.2138 |  | 2086478.7442 | 1767327.6452 | 319151.099 | -80633802.2138 | -61422120.2358 | 9395224.9591 | 0 | 28606906.9371 | 28606906.9371 | -10012417.428 | -618564.6758
12ME December 2043 | 80633802.2138 | 95194976.9116 | 80633802.2138 |  | 2086478.7442 | 1767327.6452 | 319151.099 | -80633802.2138 | -63508598.98 | 9714376.0581 | 0 | 26839579.2919 | 26839579.2919 | -9393852.7522 | -618564.6758
12ME December 2044 | 80633802.2138 | 95194976.9116 | 80633802.2138 |  | 2086478.7442 | 1767327.6452 | 319151.099 | -80633802.2138 | -65595077.7242 | 10033527.157 | 0 | 25072251.6466 | 25072251.6466 | -8775288.0763 | -618564.6758
12ME December 2045 | 80633802.2138 | 95194976.9116 | 80633802.2138 |  | 2086478.7442 | 1767327.6452 | 319151.099 | -80633802.2138 | -67681556.4684 | 10352678.256 | 0 | 23304924.0014 | 23304924.0014 | -8156723.4005 | -618564.6758
12ME December 2046 | 80633802.2138 | 95194976.9116 | 80633802.2138 |  | 2086478.7442 | 1767327.6452 | 319151.099 | -80633802.2138 | -69768035.2126 | 10671829.355 | 0 | 21537596.3562 | 21537596.3562 | -7538158.7247 | -618564.6758
12ME December 2047 | 80633802.2138 | 95194976.9116 | 80633802.2138 |  | 2086478.7442 | 1767327.6452 | 319151.099 | -80633802.2138 | -71854513.9568 | 10990980.4539 | 0 | 19770268.7109 | 19770268.7109 | -6919594.0488 | -618564.6758
12ME December 2048 | 80633802.2138 | 95194976.9116 | 80633802.2138 |  | 2086478.7442 | 1767327.6452 | 319151.099 | -80633802.2138 | -73940992.701 | 11310131.5529 | 0 | 18002941.0657 | 18002941.0657 | -6301029.373 | -618564.6758
12ME December 2049 | 80633802.2138 | 95194976.9116 | 80633802.2138 |  | 2086478.7442 | 1767327.6452 | 319151.099 | -80633802.2138 | -76027471.4452 | 11629282.6519 | 0 | 16235613.4205 | 16235613.4205 | -5682464.6972 | -618564.6758
12ME December 2050 | 80633802.2138 | 95194976.9116 | 80633802.2138 |  | 2086478.7442 | 1767327.6452 | 319151.099 | -80633802.2138 | -78113950.1894 | 11948433.7508 | 0 | 14468285.7752 | 14468285.7752 | -5063900.0213 | -618564.6758
12ME December 2051 | 80633802.2138 | 95194976.9116 | 80633802.2138 |  | 2086478.7442 | 1767327.6452 | 319151.099 | -80633802.2138 | -80200428.9336 | 12267584.8498 | 0 | 12700958.13 | 12700958.13 | -4445335.3455 | -618564.6758
12ME December 2052 | 80633802.2138 | 95194976.9116 | 80633802.2138 |  | 2086478.7442 | 1767327.6452 | 319151.099 | -80633802.2138 | -82286907.6778 | 12586735.9488 | 0 | 10933630.4848 | 10933630.4848 | -3826770.6697 | -618564.6758
12ME December 2053 | 80633802.2138 | 95194976.9116 | 80633802.2138 |  | 2086478.7442 | 1767327.6452 | 319151.099 | -80633802.2138 | -84373386.422 | 12905887.0477 | 0 | 9166302.8395 | 9166302.8395 | -3208205.9938 | -618564.6758
12ME December 2054 | 80633802.2138 | 95194976.9116 | 80633802.2138 |  | 2086478.7442 | 1767327.6452 | 319151.099 | -80633802.2138 | -86459865.1662 | 13225038.1467 | 0 | 7398975.1943 | 7398975.1943 | -2589641.318 | -618564.6758
12ME December 2055 | 80633802.2138 | 95194976.9116 | 80633802.2138 |  | 2086478.7442 | 1767327.6452 | 319151.099 | -80633802.2138 | -88546343.9104 | 13544189.2457 | 0 | 5631647.5491 | 5631647.5491 | -1971076.6422 | -618564.6758
12ME December 2056 | 80633802.2138 | 95194976.9116 | 80633802.2138 |  | 2086478.7442 | 1767327.6452 | 319151.099 | -80633802.2138 | -90632822.6546 | 13863340.3446 | 0 | 3864319.9038 | 3864319.9038 | -1352511.9663 | -618564.6758
12ME December 2057 | 80633802.2138 | 95194976.9116 | 80633802.2138 |  | 2086478.7442 | 1767327.6452 | 319151.099 | -80633802.2138 | -92719301.3988 | 14182491.4436 | 0 | 2096992.2586 | 2096992.2586 | -733947.2905 | -618564.6758
12ME December 2058 | 80633802.2138 | 95194976.9116 | 80633802.2138 |  | 2475675.5128 | 2096992.2586 | 378683.2542 | -80633802.2138 | -95194976.9116 | 14561174.6978 | 0 | 0 | 0 | 0 | -733947.2905
12ME December 2059 | 80633802.2138 | 95194976.9116 | 80633802.2138 |  | 0 | 0 | 0 | -80633802.2138 | -95194976.9116 | 14561174.6978 | 0 | 0 | 0 | 0 | 0
12ME December 2060 | 80633802.2138 | 95194976.9116 | 80633802.2138 |  | 0 | 0 | 0 | -80633802.2138 | -95194976.9116 | 14561174.6978 | 0 | 0 | 0 | 0 | 0
Total - 12ME Nov '14 |  |  |  | 9639401.4831 | 2086478.7442 | 1767327.6452 | 319151.099 | [7 empty] | 2755225.8432
AMA - 12ME Nov '14 | 80633802.2138 | 95194976.9116 | 80633802.2138 |  |  |  |  | -42761111.8366 | -1783602.7975 | 272822.7136 | 37872690.3772 | 79123022.13 |  | -14437616.1135