## LB Powerhouse
Excerpt from PSE's Response to WUTC Staff Data Request No. 036,
Attachment D
Updated Estimate for Lower Baker Powerhouse
[8 empty] | Within last 20% of Agreement Value | Exceeds Agreement Value
| LOWER BAKER U4 POWERHOUSE S.10774.01.01.06 ($000's) |  |  | Original Budget | Budget changed Nov 2012 | Budget Change May 2013 | Current Budget | SAP Actuals | Forecast to Complete | Current Forecast at Completion | Current Budget Variance | Previous Month Forecast at Completion | Forecast Variance - Current to Previous
Over/(Under)
pre Gate 4 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
Development Costs
[8 empty] | 0 |  | 0 | 0 | 0 | 0
|  | PSE Directs |  | 173110 | 173133.56 | 0 | 173133.56 | 173133.56 | 0 | 173133.56 | 0 | 173133.56 | 0
|  | Overheads |  | 191965.61 | 191965.61 | 0 | 191965.61 | 191965.61 | 0 | 191965.61 | 0 | 191965.61 | 0
|  | Consultants |  | 595716 | 287507.45 | 0 | 287507.45 | 287507.45 | 0 | 287507.45 | 0 | 287507.45 | 0
|  | Assessments, Transfers, etc |  | 0 | 433983.29 | 0 | 433983.29 | 433983.29 | 0 | 433983.29 | 0 | 433983.29 | 0
|  | Engineering |  | 1396061 | 1283749.35 | 0 | 1283749.35 | 1283749.35 | 0 | 1283749.35 | 0 | 1283749.35 | 0
| Total Development |  |  | 2356852.61 | 2370339.26 | 0 | 2370339.26 | 2370339.26 | 0 | 2370339.26 | 0 | 2370339.26 | 0
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
Engineering
[8 empty] | 0 |  | 0 | 0 | 0 | 0
|  | Jacobs Associates |  | 1231000 | 1509940.38 | 0 | 1509940.38 | 1641683.04 | 68258 | 1709941.04 | 200000.66 | 1709941.04 | 0
|  | URS Corporation |  | 2597000 | 2775872.28 | 0 | 2775872.28 | 1860315.93 | 88973 | 1949288.93 | -826583.35 | 1949288.93 | 0
|  | URS Energy and Construction |  | 0 | 18542.04 | 0 | 18542.04 | 18542.04 | 0 | 18542.04 | 0 | 18542.04 | 0
|  | MWH Americas Inc |  | 0 | 5237.51 |  | 5237.51 | 5237.51 | 0 | 5237.51 | 0 | 5237.51 | 0
|  | Shannon & Wilson Inc |  | 1000000 | 583586.13 |  | 583586.13 | 528503.23 | 0 | 528503.23 | -55082.9 | 528503.23 | 0
|  | Consultants |  | 1174268 | 959595.51 | 0 | 959595.51 | 1388193.78 | 24834.68 | 1413028.46 | 453432.95 | 1398250.29 | 14778.17
| Total Engineering |  |  | 6002268 | 5852773.85 | 0 | 5852773.85 | 5442475.53 | 182065.68 | 5624541.21 | -228232.64 | 5609763.04 | 14778.17
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
Construction
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
|  | PCL |  | 47788377 | 47989494.493 | 2000000 | 49989494.493 | 47757542.113 | 2865344.9121 | 50622887.0251 | 633392.5321 | 50622886.6525 | 0.37262
|  | Other |  | 1300000 | 1884033.69 | 500000 | 2384033.69 | 1761568.28 | 865251.7806 | 2626820.0606 | 242786.3706 | 2627714.8306 | -894.77
|  |  | Skyler Electric Co Inc |  |  |  |  | 49098.72 | 0 | 49098.72 | 49098.72 | 49098.72 | 0
|  |  | Easi LLC |  |  |  |  | 180 | 0 | 180 | 180 | 180 | 0
|  |  | Veca Electric & Technologies |  |  |  |  | 32474.63 | 0 | 32474.63 | 32474.63 | 32474.63 | 0
| Total Construction |  |  | 49088377 | 49873528.183 | 2500000 | 52373528.183 | 49519110.393 | 3730596.6927 | 53249707.0857 | 876178.9027 | 53250601.4831 | -894.3974
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
Owner Supplied Equipment
[8 empty] | 0 |  | 0 | 0 | 0 | 0
|  | Litostroj Hydro Inc |  | 11319000 | 11685600.2035 | 0 | 11685600.2035 | 11796017.9836 | -63674.7673 | 11732343.2163 | 46743.0128 | 11732343.5163 | -0.3
|  | HTG Controls |  | 1617000 | 5599999.7333 | 0 | 5599999.7333 | 5447420.165 | 342428.7864 | 5789848.9514 | 189849.218 | 5789848.947 | 0.00436
|  | GSU Transformer - SPX Transformer Solutions |  | 754600 | 757400 |  | 757400 | 775700.49 | 0 | 775700.49 | 18300.49 | 775700.49 | 0
|  | Omega Morgan Rigging and Industrial | [5 empty] | 35389 | 0 | 35389 | 35389 | 35389 | 0
|  | O&M Tools | [5 empty] | 0 | 50000 | 50000 | 50000 | 50000 | 0
| Total Owner Supplied Equipment |  |  | 13690600 | 18042999.9369 | 0 | 18042999.9369 | 18054527.6386 | 328754.0191 | 18383281.6577 | 340281.7208 | 18383281.9533 | -0.29564
[9 empty] | 0 | 0 | 0 | 0 | 0
Slope Stability
[8 empty] | 0 |  | 0 | 0 | 0 | 0
|  | Stabilize Rock Slope - LB Powerhouse Road |  | 0 | 934082.93 | 0 | 934082.93 | 740098.342 | 0 | 740098.342 | -193984.588 | 743171.142 | -3072.8
|  | Potential Landslide Mitigation - E Slope |  | 0 | 2295485.272 | 0 | 2295485.272 | 2319990.37 | 216400 | 2536390.37 | 240905.098 | 2529768.74 | 6621.63
| Total Slope Stability |  |  | 0 | 3229568.202 | 0 | 3229568.202 | 3060088.712 | 216400 | 3276488.712 | 46920.51 | 3272939.882 | 3548.83
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
PSE Costs
[10 empty] | 0 | 0 | 0 | 0
|  | PSE Directs |  | 5669308 | 3886083.108 | 800000 | 4686083.108 | 4394175.928 | 417976.5011 | 4812152.4291 | 126069.3211 | 4843799.3894 | -31646.9603
|  | Overheads |  | 1589665 | 3844066.0292 | 700000 | 4544066.0292 | 4400510.77 | 376657.0383 | 4777167.8083 | 233101.779 | 4787519.5293 | -10351.721
|  | Consultants |  | 0 | 196499.69 | 0 | 196499.69 | 286116.09 | 26943.84 | 313059.93 | 116560.24 | 293060.11 | 19999.82
|  | Assessments, Transfers, etc |  | 0 | 23880.32 | 0 | 23880.32 | 101110.14 | 0 | 101110.14 | 77229.82 | 96543.64 | 4566.5
| Total PSE Costs |  |  | 7258973 | 7950529.1472 | 1500000 | 9450529.1472 | 9181912.928 | 821577.3794 | 10003490.3074 | 552961.1602 | 10020922.6687 | -17432.3613
| Commissioning |  |  | 500000 | 500000 | 0 | 500000 | 187528.92 | 187743.8473 | 375272.7673 | -124727.2327 | 375272.7273 | 0.04
| Contingency |  |  | 4209902 | 2420210 |  | 2420210 | 0 | 956827 | 956827 | -1463383 | 956827 | 0
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Subtotal Project |  |  | 83106972.61 | 90239948.5791 | 4000000 | 94239948.5791 | 87815983.3816 | 6423964.6184 | 94239948 | -0.57911 | 94239948.0143 | -0.01432
|  | AFUDC |  | 5580041 | 6083947 |  | 6083947 | 9471983.78 | 926150.697 | 10398134.477 | 4314187.477 | 11370713.1124 | -972578.6354
|  |  | AFUDC - Order # 111020147, 111020148 (LGIA) |  |  |  |  | 10994.23 | 0 | 10994.23 | 10994.23 | 9597.84 | 1396.39
| Total Project |  |  | 88687013.61 | 96323895.5791 | 4000000 | 100323895.5791 | 97298961.3916 | 7350115.3154 | 104649076.707 | 4325181.1279 | 105620258.9667 | -971182.2597
0.3816
| Reduced 2011 numbers | [8 empty] | #REF! |  | #REF! | #REF!
[5 empty] | 90239948.1091 | 90239948.1091 | 90239948.1091
[5 empty] | 0.47 | -86239948.1091 | 4000000.47

## Snoqualmie Proj
Excerpt from PSE's Response to WUTC Staff Data Request No. 036,
Attachment E
Updated Estimate for Snoqualmie Redevelopment Project
| Hydro Projects | Received from Michael Gibbobs 2/14/13
| Timing & Capital | In Service
|  | Date | Closings
Snoqualmie
| Plant 1 | 2013-08-15 | 120038964.75
| Plant 1 AFUDC |  | 15873838.7
| Plant 2 | 2013-04-15 | 134333992.5
| Plant 2 AFUDC |  | 15410878.5
| Diversion Dam | 2012-10-31 | 6050779.8
| Diversion Dam AFUDC |  | 894637.75
| Parks & Historical |  | 11576459
| Parks & Historical AFUDC |  | 1018224
| Sub-Total |  | 272000196.05
| AFUDC |  | 33197578.95
| Project Total |  | 305197775