| **Jurisdiction** | **Formal Application** | **Status** |
| --- | --- | --- |
| **Federal Filings** |
| Federal Communications Commission | May 7, 2010 | 5/28/10 public notice issued (starting 180 day “shot clock”)Initial comments due 7/1210Reply comments due 7/27/10 |
| Department of Justice  | Original filing May 12, 2010Refiled on June 15, 2010 | The applicable waiting period under the Hart-Scott-Rodino Act was terminated early on July 15, 2010 |
| **State filings – ILEC States** |
| Arizona | May 28, 2010 | Staff/Intervenor Testimony – 9/27/10Company Rebuttal Testimony – 10/27/10Staff/Intervenor Surrebuttal Testimony – 11/10/10Hearing – 11/15; 11/16; 11/19; 11/30/10 |
| California | May 14, 2010 (Advice Letter) | Deemed Approved 6/14/10 |
| Colorado | May 27, 2010 | Intervenor Testimony – 9/15/10Rebuttal/Cross-Answer – 10/15/10Hearing – 11/8 – 11/10, 11/12Statements of Position 11/24/10 |
| Georgia | May 25, 2010 | Cleared Regulatory Review 7/28/10 |
| Iowa | May 24, 2010 | OCA/Intervenor Testimony – 8/11/10Company Reply Testimony – 8/26/10Conference to review Non-unanimous Settlement with OCA – 9/9/10Hearing – 9/27-9/28/10Post-hearing Brief – 10/14/10Deadline to Issue Order – 11/23/10 |
| Louisiana | May 19, 2010 | Intervenor Issues/Conditions – 8/13/10CTL Responses to Issues/Conditions – 8/20/10Staff Position Filed – 8/30/10Reply Comments to Staff’s Position – 9/10/10Commission Decision – 9/15/10 |
| Minnesota | May 13, 2010 | Intervenor Direct Testimony – 8/19/10Rebuttal Testimony – 9/13/10Surrebuttal Testimony – 9/27/10Hearings – 10/5/10 to 10/7/10ALJ Report – 11/30/10  |
| Mississippi | May 25, 2010 | Commission Agenda Meeting – 9/14/10 |
| Montana | May 28, 2010 | Intervenor Testimony – 9/17/10Rebuttal Testimony – 10/15/10Hearing – 11/22-11/23/10Briefs – 12/6/10Reply Briefs – 12/13/10 |
| Nebraska | June 4, 2010  | Procedural Hearing – 8/3/10Issues List – 8/13/10Simultaneous Testimony 8/27/10Hearing – 9/21/10 |
| New Jersey | May 19, 2010 | Initial Testimony – 8/12/10Rebuttal Testimony – 9/23/10Surrebuttal Testimony – 10/14/10Hearing – 11/4/10Board Public Meeting 12/15/10 |
| Ohio | May 28, 2010 | Cleared Regulatory Review - 6/29/10 |
| Oregon  | May 21, 2010 | Intervenor Reply - 8/24/10; Staff Testimony – 9/3/10Company Rebuttal - 9/21/10; Hearing - 10/20-10/21/10  |
| Pennsylvania | May 14, 2010 | Prehearing Conference – 6/29/10;Rebuttal – 8/13/10;Surrebuttal – 8/20/10Company Rejoinder – 8/26/10;Hearing – 8/27/10Joint Petition for Settlement – 9/3/10Statements in Support – 9/20/10 |
| Utah | May 28, 2010 | Intervenor Testimony - 8/30/10Rebuttal Testimony – 9/30/10Surrebuttal Testimony – 10/14/10Hearing – 10/26-10/27/10 |
| Virginia | May 25, 2010 | Comments – 8/6/10Request for Hearing – 8/6/10Staff Report – 9/3/10Response to Staff Report – 9/17/10Statutory 180 day timeframe to rule |
| **State Filings – Non-ILEC States** |
| District of Columbia | June 4, 2010  | Cleared Regulatory Review 8/30/10 |
| Hawaii | June 3, 2010  | Cleared Regulatory Review 6/15/10 |
| Maryland | June 8, 2010  | Commission Voted to Approve – 7/7/10 |
| New York | June 4, 2010  | Commission Approved – 8/24/10 |
| West Virginia | June 4, 2010  | Commission Approved – 8/3/10 |

Note: Alaska was previously identified as a Non-ILEC state where approval of the Transaction was required. Further research has confirmed that approval is not required in Alaska. Therefore, Alaska has been removed from this schedule.