Segment D and part of Segment E. The agency chose to defer its decision on the western-most portion of the project located in Idaho in order to perform additional review of the Morley Nelson Snake River Birds of Prey Conservation Area. Specifically, the sections of Gateway West that were deferred for a later ROD include the sections of Segment E from Midpoint to Hemingway and Cedar Hill to Hemingway. A draft supplemental EIS for the deferred portions of the project and the Record of Decision is anticipated in 2016.

Gateway South (Segment F): The BLM’s Notice of Intent was published in the Federal Register in April 2011, followed by public scoping meetings throughout the project area. Comments on this project from agencies and other interested stakeholders were considered as the BLM developed the draft EIS, which was issued in February 2014. A final EIS and the Record of Decision is anticipated in 2016.

Sigurd to Red Butte (Segment G): Project construction is complete and the line was placed in service in May 2015. Sigurd to Red Butte is the third major segment of Energy Gateway to be constructed, following Mona to Oquirrh (Segment C) which was placed in service in May 2013 and Populus to Terminal (Segment B) which was placed in service in November 2010.

Boardman to Hemingway (Segment H): Energy Gateway Segment H represents a significant improvement in the connection between PacifiCorp’s east and west control areas and will help deliver more diverse resources to serve its customers in Oregon, Washington and California. Originally planned as a single circuit 500 kV line from the Hemingway substation south of Boise, Idaho, to the Captain Jack substation near Klamath Falls, Oregon, PacifiCorp has continued to pursue alternative joint-development opportunities on other proposed lines west of Hemingway. Idaho Power leads the permitting efforts on this project and PacifiCorp continues to support the permitting efforts under the conditions of the Boardman to Hemingway Transmission Project Joint Permit Funding Agreement. The Record of Decision is anticipated in 2016 followed by the Oregon Energy Facilities Siting Council’s final order on the Site Certificate.

Corrected Table 2.1 – Energy Gateway Segment In-Service Dates

| **Segment** | **2015 IRP** | **2015 IRP Update** |
| --- | --- | --- |
| Segment A: Wallula to McNary | 2017 – sponsor driven | 2017 – sponsor driven |
| Segment B: Populus to Terminal | Completed Nov 2010 | Completed Nov 2010 |
| Segment C: Mona to Oquirrh | Completed May 2013 | Completed May 2013 |
| Segment C: Oquirrh to Terminal | June 2021 | June 2021 |
| Segment D: Windstar to Populus | 2019-2024 | 2019-2024 |
| Segment E: Populus to Hemingway | 2019-2024 | 2019-2024 |
| Segment F: Aeolus to Mona | 2020-2024 | 2020-2024 |
| Segment G: Sigurd to Red Butte | Completed May 2015 | Completed May 2015 |
| Segment H: West of Hemingway | Sponsor driven | |