## Quick Reference
| Start of Permissive Dialing (7D and 10D) | Start of Mandatory Dialing (10D) | Earliest date codes from new 564 NPA can be ordered through NANPA | Earliest new 564 NPA central office code activation date | Test number effective from. |  | Next Scheduled Industry call |  | WUTC Reports from Tri-Chairs for Status of Implementation of 564 | WUTC Reports from Tri-Chairs Status of Implementation of 564
WA 360/564 NPA Overlay Implementation Dates | 2017-01-28 | 2017-07-29 | 2017-06-23 | 2017-08-28 | Test number effective from 05/31/2017 to 10/27/2017 |  | 2/16/2017 @ 10 AM PDT 866-789-8818 PIN: 2526413384# |  | 9-30-2016 Done 12-31-2016 Done | 3-31-2017 Done 6-30-2017 9-30-2017
360 NPA Code Assignment Status as of | 2016-07-20 | 2016-08-24 | 2016-09-28 | 2016-10-26 | 2016-11-22 | 2016-12-14 | 2017-01-19 | 2017-02-16 | 2017-03-16 | 2017-04-20 | 2017-05-17
NXXs Available | 21 | 20 | 17 | 17 | 17 | 17 | 17 | 15 | 14 | 14 | 14
Forecasted Exhaust | 1Q18 | 1Q18 | 1Q18 | 4Q17 | 4Q17 | 4Q17 | 4Q17 | 4Q17 | 4Q17 | 4Q17
Tri Chair information: | 2016-12-14: LOCATION; 2017-01-19: NPA; 2017-02-16: 2016.2 FCST
| Rita Schmitz | (608) 796-5600 | rita.schmitz@centurylink.com |  | CenturyLink |  |  | Year | Quarter
| Karen Riepenkroger | (913) 315-8546 | karen.s.riepenkroger@sprint.com |  | Sprint | Washington | 206 | 2024 | 1Q
| Richard Finnigan | (360) 956-7001 | rickfinn@localaccess.com |  | WITA | Washington | 253* | - | - | *Beyond 30 years
[6 empty] | Washington | 360 | 2017 | 4Q
Washington Utilities and Transportation Commission: www.utc.wa.gov | 2016-12-14: Washington; 2017-01-19: 425; 2017-02-16: 2032; 2017-03-16: 2Q
[6 empty] | Washington | 509 | 2024 | 4Q

## Customer Education Milestones
# | Customer Education | Responsibility | Target Date | Status | Comments
1 | Customer Ed Subcommittee Kick-Off Meeting | All Carriers | 2016-07-20 | Complete
2 | Develop Customer Ed milestones | All Carriers | 2016-07-20 | Complete | This is a living document and can be modified as needed.
3 | Supply verbiage for first customer notification | Tri-Chairs | 2016-08-30 | Complete | Will discuss & approve final draft at next meeting - 9/28/16. No objections or corrections to draft sent on 9/13/16 - final.
4 | Report to WUTC regarding status of implementation of 564 NPA | Tri-Chairs | 2016-09-30 | Complete | Tri-Chairs provided written status of implementation of Area Code Relief Planning
5 | Issue first customer notification | All Carriers | 2016-12-28 | Complete | Generally, should be in customers' hand 30 days prior to permissive 10-Digit Dialing
6 | Report to WUTC regarding status of implementation of 564 NPA | Tri-Chairs | 2016-12-31 | Complete | Tri-Chairs provided written status of implementation of Area Code Relief Planning
7 | Supply verbiage for permissive Press Release to committee | Tri-Chairs | 2016-11-30 | Complete | Tri-Chairs will provide to UTC staff & committee - draft provided as part of this meeting maker. Final copy will be distributed after meeting.
8 | Issue permissive Press Release | All Carriers | 2017-01-20 | Complete | Begin a week before permissive dialing.
9 | Send Special letters to Alarm and Safety, Directory, Pay Telephone & PSAPs. Also letters sent to Tribal Leaders. | Tri-Chairs | 2016-10-30 | Complete | Initial overlay notification to special organizations/associations to inform them about the local dialing changes and the new area code.
10 | Develop language for use in Directories to alert the consumers of 10-digit dialing and the new area code | All Carriers who Publish Directories | On-Going |  | Carriers to handle with each of their publish directories. As directories are due, the 360 NPA Overlay information will be updated and distributed and 10 digit dialing for NPAs 206, 253, and 425.
11 | Permissive Dialing begins | All Carriers | 2017-01-28 | Complete
12 | Supply verbiage for second customer notification | Tri-Chairs | 2017-01-25 | Complete | Tri-Chairs will supply verbiage for ALL second notifications by January meeting.
13 | Report to WUTC regarding status of implementation of 564 NPA | Tri-Chairs | 2017-03-30 | Complete | Tri-Chairs provided written status of implementation of Area Code Relief Planning
14 | Issue second customer notification | All Carriers | 2017-06-29 |  | Generally should be in customers' hands 30 days prior to mandatory.
15 | Send Special letters to Alarm and Safety, Directory, Pay Telephone & PSAPs | Tri-Chairs | 2017-03-30 | Complete | Second notification to remind and ensure necessary updates are completed prior to the mandatory dialing date.
16 | Supply verbiage for mandatory Press Release to committee | Tri-Chairs | 2017-05-24 | Complete | Tri-Chairs will provide to UTC staff & committee - 5/19/2017
17 | Report to WUTC regarding status of implementation of 564 NPA | Tri-Chairs | 2017-06-30 |  | Tri-Chairs provided written status of implementation of Area Code Relief Planning
18 | Issue mandatory Press Release | Commission & Carriers who are able | 2017-07-11 |  | Commissionn Staff advised they would like to issue Press Release the week of July 11th. Will follow up with a Media Advisory week prior to Mandatory 10-digit dialing begins.
19 | Issue Media Advisory | Commission & Carriers who are able | 2017-07-25 |  | Commission Staff will issue Media Advisory in days prior to Mandatory 10-digit dialing. Anna Gill will forward copy to tri-chairs prior to July 1 and it will be distributed to Industry Team.
20 | Mandatory Dialing begins | All Carriers | 2017-07-29
21 | First Code Activation in new 564 Area Code for the 360 NPA | All Carriers | 2017-08-28
22 | Report to WUTC regarding status of implementation of 564 NPA | Tri-Chairs | 2017-09-30 |  | Tri-Chairs provided written status of implementation of Area Code Relief Planning

## Technical Milestones
# | Technical Implementation | Responsibility | Target Date | Status | Comments
1 | Technical Subcommittee Kick-Off Meeting | All Carriers | 2016-07-20 | Complete
2 | Develop Technical Implementation Milestones | All Carriers | 2016-07-20 | Complete
3 | Obtain industry test code from NANPA and activate the test number | CenturyLink | 2017-05-31 | Complete | The industry test number: 564-564-1564. The test number will be active starting on 05/31/2017 through 10/27/2017.
4 | Open the test code (564-564) in carrier's network | All Carriers | 2017-06-28 |  | Please ensure 564-564-1564 test code is opened in your network 06/29/2017.
5 | LERG updates in BIRRDS or via AOCN. (i.e. routing changes, rehomes, change from 7 to 10 terminating digits at end office and at access tandem, etc.) | All Carriers | 2017-03-29 | Complete | Exception of paging carrier codes, all End Office Codes must be updated to reflect 10 TD-EO (Terminating Digit at End Office) and at Access Tandem in LERG as soon as possible. All NPA's: 206, 253, 360 & 425
6 | Ensure Highway boxes are programed with 10D dialing in all NPA's: 206, 253, 360 & 425 | Tri-Chairs | 2017-04-29 | Complete | There are call boxes in WA - State Patrol & Dept of Transportation - call boxes will need to be updated 206, 253, 360 & 425. Contacted Bill Legg with WA Transportation. He confirmed by email 11-1-2016 there are 193 Boxes in the Seattle area on the 2 floating bridges, but they auto dial 911 - no 7 or 10 digit numbers. No other Highway Call Boxes in WA.
7 | Network Ready for Permissive Dialing | All Carriers | 2016-12-28 | Complete
9 | Permissive Dialing begins | All Carriers | 2017-01-28 | Complete
10 | Earliest date central office codes in the new 564 area code may be ordered through NANPA | All Carriers | 2017-06-23 | Complete
11 | In 360 NPA geographic area, Establish 564 NPA Specific type of Trunks | All Carriers | 2017-07-29 |  | Operator Services trunks (0+, 0-, Directory Assistance (411)), E911 trunks, Intercepts. (If your carrier uses MF signaling, your carrier needs to establish separate trunk groups for 564 NPA calls. However, separate 564 NPA trunk groups are not required if your carrier uses SS7 signaling).
12 | Completion of 10-digit signaling transition between carriers' networks in all NPA's (206, 253, 360 & 425) | All Carriers | 2017-04-29 |  | Carriers should ensure 10-digit signaling conversion is completed in their networks. (The 10D signaling conversion refers to carriers sending 10 digits of the called to party for all calls terminating in all end offices and access tandems in the existing 206, 253, 360 & 425 NPA regions.)
13 | Send confirmation email to tri-chairs when # 12 has been completed | All Carriers | 2017-04-29
14 | Update on all speed calling, call forwarding numbers and voicemail options in embedded databases to reflect 10 digit dialing in all NPA's (206, 253, 360 & 425) | All Carriers | 2017-04-29 |  | Final check and update required for all switch programed numbers. Some voicemail systems have options like paging or wake up call notifications where numbers are stored in 7 digits. Some of 211 and 311 numbers might be translated in 7-digits and require updates.
15 | Recorded Announcements in Place and Tested in all NPA's (206, 253, 360 & 425) | All Carriers | 2017-06-29
16 | Create Industry Contact list | All Carriers | 2017-06-29 |  | Create Network Emergency Contact List for carriers.
17 | Network Ready for Mandatory Dialing | All Carriers | 2017-06-29
18 | Mandatory Dialing begins | All Carriers | 2017-07-29
19 | First Code Activation in the new 564 NPA for 360 NPA | All Carriers | 2017-08-28
| E911 Work Plan | Responsibility | Target Date | Status | Comments
| Notify CLEC Customers |  | 2017-05-29 | Complete
2 | Confirm new ESN/NPD has been established for new 564 NPA | 911 Providers | 4/29/2017 | Complete | No NPD digits in WA. All of the PSAPs are getting 10 digit ANI, which is a requirement to them going to a NG platform
3 | Notify PSAPs, PSALI customers and County Coordinators | 911 Providers | 10/30/2016 | Complete | First notification
4 | Notify PSAPs, PSALI customers and County Coordinators | 911 Providers | 2017-04-29 | Complete | Second notification
5 | Review and Submit CLEC Trunk Order Requests to local provider if needed | All Carriers | 6/29/2017 |  | Please check with local provider. New trunks should be activated by the new 564 NPA first code activation date of 08/28/2017
6 | Update PSAP equipment in all NPA's (206, 253, 360 & 425) | PSAPs | 6/29/2017 |  | All speed calling and Call Forwarding numbers should be changed to 10D.
7 | Trunk Orders Complete | 911 Providers | 6/29/2017 |  | New 564 trunk established.
8 | Build E911 Network/Tandem Translations | 911 Providers | On-going
9 | Verify if all PSAP work has been completed | PSAPs | 7/29/2017 |  | 911 Providers get confirmation from PSAPs.
10 | Activate E911 Network/Tandem Translations | 911 Providers | 8/28/2017

## 10D Signaling Completion
Following carriers notified the Technical Subcommittee co-chairs that 10-digit signaling conversion has been completed in their networks.
Date of Notification | Carrier | Notified by | Effective Date
2016-09-28 | T-Mobile | Kyeva Keith | 2016-09-28
2016-10-26 | YMAX | Amy Freund | 2016-10-26
2016-11-22 | Allstream/Electric Lightwave/Integra | Jeanne Bell | 2016-11-22
2016-11-22 | Wahkiakum West | Mark Kidd | 2016-11-22
2016-11-29 | Kalama & Tenino Telephone | Bill Cowles | 2016-11-29
2016-12-14 | Whidbey Tel | Joshua Land | 2016-12-14
2016-12-14 | XO Communications | Kelly Faul | 2016-12-14
2017-01-19 | Verizon Wireless | Dana Crandall | 2017-01-19
2017-02-16 | US Cellular | Brian Frase | 2017-02-16
2017-03-16 | Rainier Connect/Mashel Telecom | Jim Fuhrman | 2017-03-16
2017-04-27 | FairPoint Communications | Jerry Jensen | 2017-04-27
2017-06-22 | CenturyLink | Rita Schmitz | 2017-06-22
2017-06-22 | Sprint | Karen Riepenkroger | 2017-06-22
2017-06-22 | TDS | Paul Nejedlo | 2017-06-22
2017-06-22 | Comcast | Bryan Medina | 2017-06-22
2017-06-22 | Charter | Allyson Blevins | 2017-06-22

## Industry Com Contact List
COMPANY | NAME | First Name | Last Name | TELEPHONE | EMAIL ID | 2016-07-20 | 2016-08-24 | 2016-09-28 | 2016-10-26 | 2016-11-22 | 2016-12-14 | 2017-01-19 | 2017-02-16 | 2017-03-16 | 2017-04-20 | 2017-05-17 | 2017-06-22 | 2017-07-19
Sprint | Karen Riepenkroger |  |  | 913-315-8546 | karen.s.riepenkroger@sprint.com | bar: 2016-07-20 to 2017-02-16; 2017-04-20 to 2017-06-22
WITA | Richard Finnigan |  |  | 360-956-7001 | rickfinn@localaccess.com | bar: 2016-07-20 to 2016-09-28; 2016-11-22 to 2016-12-14; 2017-02-16 to 2017-06-22
CenturyLink | Rita Schmitz |  |  | 608-796-5600 | rita.schmitz@centurylink.com | bar: 2016-07-20 to 2017-06-22
365 Wireless, LLC | Donny Mckinnies |  |  | 678-916-0624 | donny@365wireless.net
Allstream | Jeanne Bell |  |  | 360-558-4159 | jeanne.bell@allstream.com | bar: 2016-07-20 to 2016-09-28; 2016-11-22 to 2017-04-20; 2017-06-22
Astound Broadband | Ernie Keller |  |  | 415-349-2910 | ekeller@wavebroadband.com | bar: 2016-07-20; 2016-12-14 to 2017-01-19; 2017-04-20
AT&T | George Guerra |  |  | 408-635-8612 | gg2395@att.com | bar: 2016-08-24 to 2016-10-26; 2016-12-14 to 2017-01-19; 2017-06-22
BackUP Telecom Consulting | Mary Lou Carey |  |  | 615-791-9969 | marylou@backuptelecom.com | bar: 2017-05-17
Bandwidth | Rob Brezina |  |  | 919-297-1072 | rbrezina@bandwidth.com
Birch Communications | Kim Campbell |  |  | 478-405-3832 | kim.campbell@birch.com
Birch Communications |  |  |  |  | network.planning@birch.com
CATT Communications | Andrew Metcalfe |  |  | 509-661-2639 | metcalfe@cattcomm.com
CenturyLink | Margaret Cox |  |  | 252-641-3384 | margaret.cox@centurylink.com | bar: 2016-07-20 to 2016-10-26; 2017-01-19 to 2017-02-16; 2017-05-17 to 2017-06-22
CenturyLink | Ryan Tyrell |  |  | 720-578-5413 | ryan.tyrell@centurylink.com | bar: 2016-09-28 to 2016-10-26; 2017-02-16
Charter Communications | Allyson Blevins |  |  | 813-302-0665 | allyson.blevins@charter.com | bar: 2016-07-20 to 2016-08-24; 2016-11-22; 2017-01-19 to 2017-03-16; 2017-05-17 to 2017-06-22
Charter Communications | Kathy | bar: 2017-04-20
Charter Communications | Stacey Hines |  |  | 314-543-2454 | stacey.hines@charter.com | bar: 2016-07-20
Comcast | Bryan Medina |  |  | 303-372-1313 | Bryan_medina@cable.comcast.com | bar: 2017-06-22
Comcast | Rhonda Weaver |  |  | 360-481-1377 | rhonda_weaver@cable.comcast.com
Comtech | Lisa Dubuque |  |  | 206-792-2632 | Lisa.Dubuque@comtechtel.com | bar: 2016-09-28; 2016-11-22 to 2017-02-16; 2017-04-20 to 2017-05-17
Comtech |  |  |  |  | NG-LECServices@telecomsys.com
Eltopia | Ed Baumgartner |  |  | 918-845-1556 | ehbaumgartner@eltopia.com
Eltopia | Will McHugh |  |  |  | wmachugh@eltopia.com
Eltopia | Aaron Seelye |  |  |  | aseelye@eltopia.com
FairPoint Communications | Nadine Fletcher |  |  | 603-656-4041 | nfletcher1@fairpoint.com | bar: 2016-07-20 to 2017-04-20; 2017-06-22
FairPoint Communications | Steve Zacharzuk |  |  | 518-392-1250 | szacharzuk@fairpoint.com
FairPoint Communications | Jerry Jensen |  |  | 509-962-0355 | jjensen@fairpoint.com | bar: 2016-07-20 to 2016-08-24; 2016-10-26; 2016-12-14 to 2017-01-19; 2017-03-16 to 2017-04-20; 2017-06-22
FairPoint Communications | Leslie Miklos |  |  |  | lmiklos@fairpoint.com | bar: 2016-08-24 to 2016-11-22; 2017-01-19 to 2017-04-20
Frontier Communications | Ellen Washbon |  |  | 585-777-1165 | ellen.washbon@ftr.com
Frontier Communications | Cathy Dahlquist |  |  | 425-261-6380 | cathy.dahlquist@ftr.com | bar: 2016-07-20
Frontier Communications | Barb Johnston |  |  | 919-941-6360 | barbara.johnston@ftr.com | bar: 2016-08-24
Frontier Communications | Kent Oliver |  |  |  | kent.oliver@ftr.com
Frontier Communications | Kris Anderson |  |  |  | kris.anderson@ftr.com | bar: 2016-07-20; 2016-09-28 to 2016-12-14; 2017-02-16; 2017-04-20
Frontier Communications | Maria | bar: 2016-07-20
Frontier Communications | Mark Spell |  |  | 425-264-6667 | Mark.Spell@ftr.com | bar: 2016-09-28 to 2016-10-26
Hood Canal Communications | John Oblizalo |  |  | 360-898-2481 X: 205 | johno@hcc.net
Hypercube | Karen Turner |  |  |  | ksturner@west.com remove - 6/23/17
Hypercube | Deanna Girard |  |  |  | deanna.girard@h3net.com
Impact Telecom | Jami Perez |  |  | 209-926-3325 | jperez@impacttelecom.com
Inland Telephone | James Brooks |  |  | 509-649-5250 | jbrooks@inlandnet.com
Inland Cellular | Randy Bennett |  |  | 509-229-3900 | g0bbler@inlandcellular.com
Inland Cellular | Kathy Hopwood |  |  | 509-229-2211 | kathy@inlandcellular.com
Inteliquent | Casey Garza |  |  |  | cgarza@inteliquent.com
Inteliquent | Nicolas Galvis |  |  |  | lgalvis@inteliquent.com | bar: 2016-08-24 to 2016-09-28; 2016-12-14 to 2017-01-19; 2017-03-16; 2017-05-17
Inteliquent | Andres Alcaraz |  |  |  | aalcaraz@inteliquent.com | bar: 2016-08-24 to 2016-09-28; 2016-12-14 to 2017-01-19; 2017-05-17
International Telecom | Mike Tyler |  |  | 206-479-6525 | miket@kall8.com
Kalama & Tenino Telcos | Bill Cowles |  |  | 360-264-2544 | bcowles@scattercreek.net | bar: 2016-07-20 to 2016-08-24; 2016-10-26; 2016-12-14 to 2017-05-17
Kalama & Tenino Telcos | Todd | bar: 2016-07-20 to 2016-08-24; 2016-10-26 to 2017-01-19; 2017-06-22
Level 3 | Kathy Michaud |  |  |  | kathy.michaud@level3.com | bar: 2016-07-20
Level 3 | Scott Seab |  |  | 720-888-3942 | scott.seab@level3.com | bar: 2016-09-28
Level 3 |  |  |  |  | DL-NumberAdminOnShore@Level3.com
Local Access | Doug Osborne |  |  | 570-709-5525 | dosborne@localaccessllc.com
Magna5 (formerly X5 Solutions) | Meaghan Perez |  |  | 206-973-5822 | mperez@x5solutions.com | bar: 2016-08-24 to 2016-09-28; 2017-04-20
Magna5 (formerly X5 Solutions) | Melinda Hough |  |  | 206-873-5826 | mhough@x5solutions.com | bar: 2016-08-24
Magna5 (formerly X5 Solutions) | Charity Mullen |  |  | 206-973-5800 | cmullen@x5solutions.com | bar: 2016-08-24
Neustar | Joe Cocke |  |  | 571-434-5690 | joe.cocke@neustar.biz | bar: 2016-07-20 to 2017-06-22
Neustar | Al Cipparone |  |  | 571-434-5789 | al.cipparone@neustar.biz | bar: 2016-10-26 to 2017-02-16; 2017-04-20 to 2017-05-17
Neustar | Heidi Wayman |  |  |  | heidi.wayman@team.neustar | bar: 2017-06-22
North County Comm | Todd Lesser |  |  |  | todd@nccom.com
Onvoy, INC | Joani O'Neill |  |  | 406-496-6522 | Joani.oneill@onvoy.com | bar: 2016-10-26
Origin Networks | Mac Kay |  |  | 541-492-1200 | mkay@infostructure.biz
Origin Networks | William Neal |  |  | 541-492-3005 | wneal@infostructure.biz | bar: 2017-01-19
Peerless Network | Patrick Phipps |  |  | 312-506-0933 | pphipps@peerlessnetwork.com | bar: 2016-09-28; 2017-02-16; 2017-05-17 to 2017-06-22
Peerless Network | Sarah | bar: 2016-07-20; 2016-11-22; 2017-01-19
Rainier Connect (Mashell) | Jim Fuhrman |  |  | 360-832-3174 | jim.fuhrman@rainierconnect.net | bar: 2016-09-28 to 2016-10-26; 2017-01-19; 2017-03-16 to 2017-04-20
RCLEC | Desiree Apodaca |  |  | 720-863-7815 | desiree.apodaca@rclec.com
Salish Networks | Tom Williams |  |  | 360-716-8040 | tomwilliams@salishnetworks.com | bar: 2016-07-20 to 2016-08-24; 2016-12-14 to 2017-01-19; 2017-03-16 to 2017-04-20
Skyline Telecom | Delinda Kluser |  |  | 541-932-4411 | dkluser@ortelco.net
Skyline Telecom | Patrick Cantrell |  |  | 541-932-4411 | patrickc@ortelco.net
Skyline Telecom | Andrea Finley |  |  |  | andreaf@ortelco.net | bar: 2016-12-14 to 2017-01-19
Sprint | Shaunna Forshee |  |  | 913-315-9108 | Shaunna.l.forshee@sprint.com | bar: 2016-07-20; 2016-09-28; 2016-11-22; 2017-03-16; 2017-05-17
T-Mobile | Kyeva Keith |  |  | 206-313-1506 | kyeva.keith2@t-mobile.com | bar: 2016-07-20 to 2016-11-22; 2017-02-16
T-Mobile | Paula Campagnoli |  |  | 925-323-3325 | paula.campagnoli@t-mobile.com
T-Mobile(Metro PCS) | Espie Creighton |  |  | 916-984-2655 | esperanza.creighton@t-mobile.com | bar: 2016-09-28 to 2016-11-22
TDS | Anne Chism |  |  | 608-833-8080 | Anne.chism@tdstelecom.com | bar: 2016-08-24; 2016-10-26; 2016-12-14; 2017-04-20
TDS | Paul Nejedlo |  |  | 608-664-4659 | Paul.nejedlo@tdstelecom.com | bar: 2016-07-20; 2016-09-28 to 2016-10-26; 2016-12-14 to 2017-01-19; 2017-03-16 to 2017-04-20; 2017-06-22
TDS | Gail Long |  |  | 541-516-8210 | gail.long@tdstelecom.com | bar: 2016-07-20; 2017-01-19; 2017-03-16; 2017-06-22
Teltrust Corp. | Alfred Nurnberger |  |  | 503-500-5000 | cto@teltrust.com
Tel West | Phil Garcia |  |  |  | pgarcia@telwestservices.com
Time Warner Cable | Maribeth Bailey |  |  | 212-364-8440 | Maribeth.bailey@twcable.com
Time Warner Cable | John Cummings |  |  | 703-962-7822 | john.cummings@twcable.com
Toledo Telco | Dale Merten |  |  | 360-864-2044 | dale@toledotel.net
TSS Digital Services | Thomas Ellis |  |  | 360-915-1104 | tom.ellis@tssdigital.com
US Celular | Brian Frase |  |  | 773-399-4249 | brian.frase@uscellular.com | bar: 2016-07-20; 2016-09-28; 2016-11-22 to 2017-06-22
US Celular | Missy Schwickerath |  |  | 608-441-4219 | melissa.schwickerath@uscellular.com
USA Mobility/Spok | Craig Wilkins |  |  | 972-801-0207 | craig.wilkins@spok.com
Verizon Business | Laura Dalton |  |  | 914-741-7018 | laura.r.dalton@verizon.com | bar: 2016-07-20; 2016-09-28 to 2017-04-20
Verizon Business | Yun Lee |  |  | 516-229-2891 | yun.j.lee@verizon.com | bar: 2016-07-20 to 2016-10-26; 2017-01-19 to 2017-06-22
Verizon Wireless | Dana Crandall |  |  | 682-831-3662 | Dana.crandall@verizonwireless.com | bar: 2016-07-20 to 2017-06-22
Vonage | Randy Rutherford |  |  | 732-444-6113 | randy.rutherford@vonage.com
Vonage | Joeffer Dulnuan |  |  | 732-266-2699 | joeffer.dulnuan@vonage.com
Washington UTC | Rebecca Beaton |  |  | 360-664-1287 | rbeaton@utc.wa.gov | bar: 2016-07-20 to 2016-12-14; 2017-02-16 to 2017-06-22
Washington UTC | John Cupp |  |  |  | jcupp@utc.wa.gov | bar: 2016-07-20 to 2016-08-24; 2016-10-26; 2016-12-14 to 2017-02-16; 2017-05-17 to 2017-06-22
Washington UTC | Tim Zawislak |  |  |  | tzawislak@utc.wa.gov | bar: 2016-08-24 to 2017-01-19; 2017-03-16 to 2017-06-22
Washington UTC | Anna Gill |  |  |  | agill@utc.wa.gov | bar: 2016-07-20; 2016-09-28 to 2016-10-26; 2017-02-16 to 2017-03-16; 2017-05-17 to 2017-06-22
Wahkiakum West County Tel | Mark Kidd |  |  | 360-465-2211 | mkidd@wwest.net | bar: 2016-07-20 to 2016-09-28; 2016-11-22; 2017-05-17 to 2017-06-22
Wahkiakum West County Tel | Carol Larson |  |  | 360-465-2211 | clarson@wwest.net
Wave Broadband | Jim McTiernan |  |  | 425-349-2943 | jmctiernan@wavebroadband.com | bar: 2016-12-14; 2017-02-16 to 2017-03-16
Whidbey/Hat Island Telcos | Wayne Jeffers |  |  | 360-321-0048 | wayne.jeffers@whidbeytel.com | bar: 2016-07-20 to 2016-10-26; 2016-12-14 to 2017-01-19; 2017-03-16 to 2017-05-17
Whidbey/Hat Island Telcos | Jacque Baldwin |  |  | 360-321-0061 | jacque.baldwin@whidbeytel.com | bar: 2016-07-20 to 2017-02-16; 2017-04-20; 2017-06-22
Whidbey/Hat Island Telcos | Joshua Land |  |  | 360-321-0035 | joshua.land@whidbeytel.com | bar: 2016-08-24 to 2017-06-22
Wide Voice | Erla Erlingsdottir |  |  | 702-913-1084 | numberadmin@widevoice.com | bar: 2017-01-19
Windstream | Nicole Winters |  |  | 501-748-6313 | nicole.winters@windstream.com
XO Communications | Ruben Galvan |  |  | 972-578-3728 | Ruben.galvan@xo.com
XO Communications | Kelly Faul |  |  | 703-547-2536 | kelly.faul@xo.com | bar: 2016-07-20 to 2017-06-22
YMAX Communications | Amy Freund |  |  | 267-424-4400 | amy.freund@ymaxcorp.com | bar: 2016-07-20 to 2016-08-24; 2016-10-26; 2016-12-14; 2017-02-16

## Emergency Contact List
Carrier | Primary Contact(s) | Telephone # | Hrs of Opr | Back Up Contact(s)/ Escalations | E-Mail Address | Telephone #(s)
365 Wireless
Allstream | NOC | 800-622-4354 | 24/7 | Gary Lang | gary.lang@integratelecom.com | 360-558-5310
American Messaging
Astound Broadband | NOC | 888-317-0488 | 24/7/365 | Ernie Keller | ekeller@wavebroadband.com | 415-349-2910
AT&T | NOC Technician | 888-910-0288 | 24/7 | George Guerra | gg2395@att.com | 408-635-8612 (O)
Bandwidth
Birch Communications
CATT Communications
CenturyLink | NOC | 800-524-5249 | 24/7
Charter Communications | NOC | 866-248-7662 | 24/7 | Allyson Blevins | Allyson.Blevins@charter.com | 314-543-5765
Comcast | NASR NOC Support | 877-245-4168 | 24/7 | Bryan Medina | Bryan_Medina@cable.comcast.com | 303-372-1313
Cox Communications
Eltopia
FairPoint Communicaitons | Jerry Jensen | 509-962-0355 | Monday - Friday 8AM to 5PM | Jerry Jensen |  | 509-925-1425
Frontier | Jerry Caldwell | 260-440-5609 |  |  | jerry.caldwell@ftr.com
Hood Canal Communications | John Oblizalo | 360-490-0107 | Monday - Friday | Mike Ablizalo | johno@hcc.net | 360-898-2481
Hypercube
Impact | NOC | 800-511-9048 | 24/7 | Eddie Archuleta | earchuleta@impacttelecom.com
Inland Telephone
Inland Cellular
International Telecom
Inteliquent
Kalama & Tenino Telecos | Central Office | 360-264-6013/360-673-4211 | Monday - Friday 8AM to 5PM | Bill Cowles | bcowles@scattercreek.net | 360-704-8377
Level 3 | Tech On Duty | 877-922-7768 |  | Scott Eversman | scott.eversman@level3.com | 847-321-9293
Local Access
Magna5
Mashell dba Rainier Connect | Central Office | 360-832-0041 | Monday - Friday 6AM to 6PM | Jim Fuhrman | jim.fuhrman@rainierconnect.net | 360-832-3174
Neutral Tandem
North Country Comm
Onvoy
Origin Networks
Peerless Network | Patrick Phipps | 312-506-0933 | pphipps@peerlessnetwork.com | Sarah Halko | shalko@peerlessnetwork.com | 312-667-4862
RCLEC
Salish Networks | NOC\Customer Service | 888-799-8079 | 24/7 | Tom Williams | Tomwilliams@salishnetworks.com | 360-716-8040
Sprint | NOC | 866-400-6040 | 24/7
Skyline Telecom | Patrick Cantrell | 541-932-4411 | Monday - Friday 8AM to 5PM | Call Center | patrickc@ortelco.com | 541-932-4900
T-mobile | East NOC | 877-710-3887, but via option 4
TDS Telecom | NOC | 888-790-1216 | 24/7 |  | telecom.network.management@tdstelecom.com
Teltrust Corp.
Tel West
Time Warner Cable
Toledo Telco
TSS Digital Services
Union Telephone
US Cellular | NOC | 800-510-6091 | 24/7 |  | noc@uscellular.com
USA Mobility / Spok
Verizon Business | National Network Mgmt Ctr | 800-937-2862 | 24/7 | Yun Lee | yun.j.lee@verizon.com | 516-832-2691(O)
Verizon Wireless | NOC | 800-852-2671 | 24/7 | Barb Jantzen Ben Fischer | barb.jantzen@vzw.com; ben fischer@vzw.com | 425-603-2134 303-873-2680
Wahkiakum West County Telephone
Whidbey / Hat Island Telcos | NOC | 360-321-8324 | 24/7 | Josh Land | joshua.land@whidbeytel.com | 360-320-8631
Wide Voice
Windstream | NOC | 800-742-9315
XO Communications | NOC | 866-966-8975 | 24/7
YMAX Comm., Corp. | NMC | 800-357-4911 | 24/7