## Plant Site Remedy Eval
| TABLE 7-6 | [6 empty] | TABLE 7-6 | [6 empty] | TABLE 7-6 | [6 empty] | TABLE 7-6
| COST ESTIMATE FOR REMEDIAL ACTION ALTERNATIVE 4 | [6 empty] | COST ESTIMATE FOR REMEDIAL ACTION ALTERNATIVE 4 | [6 empty] | COST ESTIMATE FOR REMEDIAL ACTION ALTERNATIVE 4 | [6 empty] | COST ESTIMATE FOR REMEDIAL ACTION ALTERNATIVE 4
| PLANT SITE REMEDY EVALUATION | [6 empty] | PLANT SITE REMEDY EVALUATION | [6 empty] | PLANT SITE REMEDY EVALUATION | [6 empty] | PLANT SITE REMEDY EVALUATION
| Updated 10/26/21 | [6 empty] | Updated 10/26/21 | [6 empty] | Updated 10/26/21 | [6 empty] | Updated 10/26/21
| Colstrip Steam Electric Station | [6 empty] | Colstrip Steam Electric Station | [6 empty] | Colstrip Steam Electric Station | [6 empty] | Colstrip Steam Electric Station
| Colstrip, Montana | [6 empty] | Colstrip, Montana | [6 empty] | Colstrip, Montana | [6 empty] | Colstrip, Montana
CAPITAL COSTS in 2021 | [6 empty] | ANNUAL OPERATION AND MAINTENANCE COSTS in 2021 | [6 empty] | ANNUAL OPERATION AND MAINTENANCE COSTS from 2029 to 2040 | [6 empty] | ANNUAL OPERATION AND MAINTENANCE COSTS in 2053
Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value | Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value | Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value | Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value
Design/Construct Plant Site/Units 1&2 Capture Well Treatment System | ls | 16500000 | 1 | 16500000 | Done in 2021 |  | Plant Site Groundwater Injection/Capture System Maintenance | ls | 216000 | 1 | 216000 | Done in 2021 |  | Plant Site Groundwater Injection/Capture System Maintenance | ls | 300000 | 1 | 300000 | changed to reflect O&M |  | Post-Closure Care - Units 1&2 B Pond | ls | 12000 | 1 | 12000
Design Plant Site/Units 1&2 Capture Treatment System Solids Disposal Area | ls | 300000 | 1 | 300000 | Done in 2021 |  | Plant Site Groundwater Monitoring Activities | ls | 100000 | 1 | 100000 | Done in 2021 |  | Plant Site Groundwater Monitoring Activities | ls | 100000 | 1 | 100000 |  |  | Post-Closure Care - Units 3&4 Pond Return Brine Concentrator Solids Disposal Area | ls | 15300 | 1 | 15300
Design Units 1&2 Bottom Ash Pond w/ Clearwell Closure | ls | 300000 | 1 | 300000 | Done in 2021 |  | Post-Closure Care - Former Units 1&2 A Pond | ls | 14000 | 1 | 14000 | Done in 2021 |  | Plant Site/Units 1&2 Capture System Water Treatment O&M | ls | 1450000 | 1 | 1450000 |  |  | Post-Closure Care - Additional Units 3&4 Pond Return Brine Concentrator Solids Disposal Area | ls |  | 1 | 0 | Duplicate to next line
|  |  | Total | 17100000 |  | 0 | Post-Closure Care - Units 3&4 Bottom Ash Pond with Clearwell | ls | 15000 | 1 | 15000 | Done in 2021 |  | Post-Closure Care - Former Units 1&2 A Pond | ls | 14000 | 1 | 14000 |  |  | Post-Closure Care - Plant Site/Units 1&2 Capture Treatment System Solids Disposal Area | ls | 15000 | 1 | 15000
[7 empty] | MNA Demonstration Studies | ls | 30000 | 1 | 30000 | Done in 2021 |  | Post-Closure Care - Units 3&4 Bottom Ash Pond with Clearwell | ls | 15000 | 1 | 15000 |  |  | Institutional Controls | ls | 50000 | 1 | 50000
CAPITAL COSTS in 2022 | [9 empty] | Total | 375000 |  | $ | Post-Closure Care - Units 1&2 Bottom Ash Pond with Clearwell | ls | 8000 | 1 | 8000 | [5 empty] | Total | 92300 |  | $35,844
Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value | [7 empty] | Post-Closure Care - Units 1&2 B Pond | ls | 12000 | 1 | 12000
Close Units 1&2 Bottom Ash Pond w/ Clearwell | ls | 1700000 | 1 | 1700000 | 2017 Wastewater Facility Closure Plan |  | ANNUAL OPERATION AND MAINTENANCE COSTS in 2022 | [6 empty] | Post-Closure Care - Units 3&4 Pond Return Brine Concentrator Solids Disposal Area | ls | 15300 | 1 | 15300 | [6 empty] | Total Capital $24,847,000 |  | Total Present Value Capital $19,804,461
Construct Plant Site/Units 1&2 Capture Treatment System Solids Disposal Area | ls | 0 | 1 | 0 | Moved to 2023, existing SDA has capacity |  | Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value |  |  |  | Total | 1914300 |  | $ |  |  |  |  | Total O&M $54,381,500 |  | Total Present Value O&M $36,688,381
Design/Construct Plant Site/Units 1&2 Capture Well Treatment System | ls | 2000000 | 1 | 2000000 | Added to complete Treatment System construction in 2022 |  | Plant Site Groundwater Injection/Capture System Maintenance | ls | 302000 | 1 | 302000 | changed to reflect O&M | [12 empty] | TOTAL $79,228,500 |  | TOTAL PRESENT VALUE $56,492,842
Design Units 1&2 B Pond Closure | ls | 150000 | 1 | 150000 |  |  | Plant Site Groundwater Monitoring Activities | ls | 100000 | 1 | 100000 |  |  | ANNUAL OPERATION AND MAINTENANCE COSTS from 2041 to 2048 | [6 empty] | Notes:
|  |  | Total | 3850000 |  | $3,737,864 | Plant Site/Units 1&2 Capture System Water Treatment O&M | ls | 1600000 | 1 | 1600000 |  |  | Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value | 1. Costs for project management and construction management are included.
[7 empty] | Post-Closure Care - Former Units 1&2 A Pond | ls | 14000 | 1 | 14000 |  |  | Plant Site Groundwater Injection/Capture System Maintenance | ls | 300000 | 1 | 300000 | changed to reflect O&M |  | 2. A discount factor of 3% was used to calculate the present value of the total cost per year for the range of years in 2019 dollars.
CAPITAL COSTS in 2023 | [6 empty] | Post-Closure Care - Units 3&4 Bottom Ash Pond with Clearwell | ls | 15000 | 1 | 15000 |  |  | Plant Site Groundwater Monitoring Activities | ls | 100000 | 1 | 100000
Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value | MNA Demonstration Studies | ls | 30000 | 1 | 30000 |  |  | Plant Site/Units 1&2 Capture System Water Treatment O&M | ls | 1450000 | 1 | 1450000
Close Units 1&2 B Pond | ls | 2800000 | 1 | 2800000 | [5 empty] | Total | 2061000 |  | $2,000,971 | Post-Closure Care - Former Units 1&2 A Pond | ls | 14000 | 1 | 14000
Construct Plant Site/Units 1&2 Capture Treatment System Solids Disposal Area | ls | 7700000 | 1 | 7700000 | [9 empty] | Post-Closure Care - Units 3&4 Bottom Ash Pond with Clearwell | ls | 15000 | 1 | 15000
|  |  | Total | 10500000 |  | $9,897,257 | ANNUAL OPERATION AND MAINTENANCE COSTS in 2023 | [6 empty] | Post-Closure Care - Units 1&2 Bottom Ash Pond with Clearwell | ls | 8000 | 1 | 8000
[7 empty] | Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value | Post-Closure Care - Units 1&2 B Pond | ls | 12000 | 1 | 12000
CAPITAL COSTS in 2024 | [6 empty] | Plant Site Groundwater Injection/Capture System Maintenance | ls | 300000 | 1 | 300000 | changed to reflect O&M |  | Post-Closure Care - Units 3&4 Pond Return Brine Concentrator Solids Disposal Area | ls | 15300 | 1 | 15300
Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value | Plant Site Groundwater Monitoring Activities | ls | 100000 | 1 | 100000 |  |  | Post-Closure Care - Additional Units 3&4 Pond Return Brine Concentrator Solids Disposal Area | ls |  | 1 | 0 | Not closed until 2048
Design/Build Additional Units 3&4 Pond Return Brine Concentrator Solids Disposal Area | ls | 0 | 1 | 0 | Done in 2023 |  | Plant Site/Units 1&2 Capture System Water Treatment O&M | ls | 1600000 | 1 | 1600000 | [5 empty] | Total | 1914300 |  | $
|  |  | Total | 0 |  | $ | Post-Closure Care - Former Units 1&2 A Pond | ls | 14000 | 1 | 14000
[7 empty] | Post-Closure Care - Units 3&4 Bottom Ash Pond with Clearwell | ls | 15000 | 1 | 15000 |  |  | ANNUAL OPERATION AND MAINTENANCE COSTS in 2049
CAPITAL COSTS in 2028 | [6 empty] | Post-Closure Care - Units 1&2 Bottom Ash Pond with Clearwell | ls | 8000 | 1 | 8000 |  |  | Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value
Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value | MNA Demonstration Studies | ls | 30000 | 1 | 30000 |  |  | Plant Site Groundwater Injection/Capture System Maintenance | ls | 300000 | 1 | 300000 | changed to reflect O&M
Design/Close Units 3&4 Pond Return Brine Concentrator Solids Disposal Area | ls | 3227000 | 1 | 3227000 | [5 empty] | Total | 2067000 |  | $1,948,346 | Plant Site Groundwater Monitoring Activities | ls | 100000 | 1 | 100000
|  |  | Total | 3227000 |  | $2,623,846 | [7 empty] | Plant Site/Units 1&2 Capture System Water Treatment O&M | ls | 700000 | 1 | 700000
[7 empty] | ANNUAL OPERATION AND MAINTENANCE COSTS from 2024 to 2028 | [6 empty] | Post-Closure Care - Former Units 1&2 A Pond | ls | 14000 | 1 | 14000
CAPITAL COSTS in 2040 | [6 empty] | Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value | Post-Closure Care - Units 3&4 Bottom Ash Pond with Clearwell | ls | 15000 | 1 | 15000
Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value | Plant Site Groundwater Injection/Capture System Maintenance | ls | 300000 | 1 | 300000 | changed to reflect O&M |  | Post-Closure Care - Units 1&2 Bottom Ash Pond with Clearwell | ls | 8000 | 1 | 8000
Close Units 3&4 North Plant Area Drain | ls | 220000 | 1 | 220000 |  |  | Plant Site Groundwater Monitoring Activities | ls | 100000 | 1 | 100000 |  |  | Post-Closure Care - Units 1&2 B Pond | ls | 12000 | 1 | 12000
Close Stormwater Pond 1 | ls | 700000 | 1 | 700000 |  |  | Plant Site/Units 1&2 Capture System Water Treatment O&M | ls | 1600000 | 1 | 1600000 |  |  | Post-Closure Care - Units 3&4 Pond Return Brine Concentrator Solids Disposal Area | ls | 15300 | 1 | 15300
Close Stormwater Pond 2 | ls | 520000 | 1 | 520000 |  |  | Post-Closure Care - Former Units 1&2 A Pond | ls | 14000 | 1 | 14000 |  |  | Post-Closure Care - Additional Units 3&4 Pond Return Brine Concentrator Solids Disposal Area | ls |  | 1 | 0 | Duplicate to next line
Close Units 1-4 Sediment Retention Pond | ls | 780000 | 1 | 780000 |  |  | Post-Closure Care - Units 3&4 Bottom Ash Pond with Clearwell | ls | 15000 | 1 | 15000 |  |  | Post-Closure Care - Plant Site/Units 1&2 Capture Treatment System Solids Disposal Area | ls | 15000 | 1 | 15000
Close Units 1-4 North Plant Sediment Retention Pond | ls | 50000 | 1 | 50000 |  |  | Post-Closure Care - Units 1&2 Bottom Ash Pond with Clearwell | ls | 8000 | 1 | 8000 | [5 empty] | Total | 1179300 |  | $
Design/Close Additional Units 3&4 Pond Return Brine Concentrator Solids Disposal Area | ls | 0 | 1 | 0 | Duplicate to 2048 |  | Post-Closure Care - Units 1&2 B Pond | ls | 12000 | 1 | 12000
|  |  | Total | 2270000 |  | $1,294,549 |  |  |  | Total | 2049000 |  | $8,845,150 | ANNUAL OPERATION AND MAINTENANCE COSTS from 2050 to 2052
[14 empty] | Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value
CAPITAL COSTS in 2048 | [13 empty] | Plant Site Groundwater Monitoring Activities | ls | 100000 | 1 | 100000
Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value | [7 empty] | Post-Closure Care - Units 1&2 Bottom Ash Pond with Clearwell | ls | 8000 | 1 | 8000
Design/Close Plant Site/Units 1&2 Capture Treatment System Solids Disposal Area | ls | 5000000 | 1 | 5000000 | [9 empty] | Post-Closure Care - Units 1&2 B Pond | ls | 12000 | 1 | 12000
|  |  | Total | 5000000 |  | $2,250,945 | [7 empty] | Post-Closure Care - Units 3&4 Pond Return Brine Concentrator Solids Disposal Area | ls | 15300 | 1 | 15300
[14 empty] | Post-Closure Care - Additional Units 3&4 Pond Return Brine Concentrator Solids Disposal Area | ls |  | 1 | 0 | Duplicate to next line
[14 empty] | Post-Closure Care - Plant Site/Units 1&2 Capture Treatment System Solids Disposal Area | ls | 15000 | 1 | 15000
[17 empty] | Total | 150300 |  | $

## Units 1&2 Alternative 10
Colstrip Units 1&2 Alt 10 Revision 3/2/21
CAPITAL COSTS in 2021 | [6 empty] | CAPITAL COSTS in 2026 | [6 empty] | ANNUAL OPERATION AND MAINTENANCE COSTS in 2021 | [6 empty] | ANNUAL OPERATION AND MAINTENANCE COSTS in 2031
Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value | Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value | Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value | Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value
Design/Permit/Plan/Install 8 New Vertical Capture Wells (w3-w5, w8-w11, w13) | well | 30000 | 8 | 240000 | RACER; install as scheduled to assist with dewatering for removal |  | Operate New Landfill | ls | 731000 | 1 | 731000 | Onsite Projects |  | SOEP/STEP and new landfill groundwater monitoring and reporting, and capture system maintenance | ls | 368000 | 1 | 368000 | Onsite Projects |  | SOEP/STEP and new landfill groundwater monitoring and reporting, and freshwater flushing/capture system maintenance | ls | 495000 | 1 | 495000 | Onsite Projects
Design/Permit/Plan/Install 6 New Vertical Injection Wells (IW33, IW35, IW37, IW39, IW42, IW44) | well | 30000 | 6 | 180000 | RACER; install as scheduled for Small-Scale System |  | Construct Liner for New Landfill Cell 3 | ls | 6029000 | 1 | 6029000 | Onsite Projects |  | STEP A Cell dewatering well operation | ls | 50000 | 1 | 50000 | RACER; $50,000/yr through 2049 included in Financial Assurance for STEP A Cell dewatering |  |  |  |  | Total | 495000 |  | 368000
Design/Permit/Plan/Install 1 New Vertical Injection Well (IW41) | well | 30000 | 1 | 30000 | RACER |  | Relocate Ash from SOEP to New Landfill (No backfill) | ls | 19499000 | 1 | 19499000 | Onsite Projects |  | STEP E Cell dewatering well operation | ls | 50000 | 1 | 50000 | RACER; $50,000/yr through 2051 included in Financial Assurance for STEP E Cell dewatering
Design/Permit/Plan/Install Freshwater Flushing Pilot Test and Small-Scale System | ls | 500000 | 1 | 500000 | Onsite Projects/RACER; install for IW35, IW37, IW39, IW41, IW42, IW44 |  |  |  |  | Total | 26259000 |  | $22,651,000 | STEP Old Clearwell dewatering well operation | ls | 50000 | 1 | 50000 | RACER |  | ANNUAL OPERATION AND MAINTENANCE COSTS from 2032 to 2050
Hydrogeological/Geotechnical Investigation for New Landfill | ls | 375000 | 1 | 375000 | Onsite Projects; includes new monitoring wells | [8 empty] | MNA demonstration studies | ls | 30000 | 1 | 30000 |  |  | Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value
Permit/Design New Landfill | ls | 333000 | 1 | 333000 | Onsite Projects |  | CAPITAL COSTS in 2027 | [6 empty] | PRB Feasibility Studies | ls | 30000 | 1 | 30000 |  |  | SOEP/STEP and new landfill groundwater monitoring and reporting, and freshwater flushing/capture system maintenance | ls | 495000 | 1 | 495000 | Onsite Projects
Design relocation of ash from SOEP to New LF | ls | 133000 | 1 | 133000 | Onsite Projects |  | Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value |  |  |  | Total | 578000 |  | $578,000 | Post-Closure Care for New Landfill | ls | 91000 | 1 | 91000
Design relocation of ash from STEP to New LF | ls | 133000 | 1 | 133000 | Onsite Projects |  | Operate New Landfill | ls | 731000 | 1 | 731000 | Onsite Projects | [11 empty] | Total | 586000 |  | 6246000
Prepare Facility Closure Plan for New Landfill | ls | 50000 | 1 | 50000 |  |  | Construct Liner for New Landfill Cell 4 | ls | 6029000 | 1 | 6029000 | Onsite Projects |  | ANNUAL OPERATION AND MAINTENANCE COSTS from 2022 to 2023
Revise STEP Facility Closure Plan | ls | 150000 | 1 | 150000 |  |  | Construct Stormwater Mangement Pond for New Landfill | ls | 508000 | 1 | 508000 | Onsite Projects |  | Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value | ANNUAL OPERATION AND MAINTENANCE COSTS from 2051 to 2052
|  |  | Total | 2124000 |  | $2,124,000 | Design Closure of New Landfill | ls | 300000 | 1 | 300000 | Onsite Projects |  | SOEP/STEP and new landfill groundwater monitoring and reporting, and freshwater flushing/capture system maintenance | ls | 387000 | 1 | 387000 | Onsite Projects |  | Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value
[7 empty] | Relocate Ash from STEP A to New Landfill | ls | 23034000 | 1 | 23034000 | Onsite Projects |  | STEP A Cell dewatering well operation | ls | 50000 | 1 | 50000 | RACER |  | SOEP/STEP and new landfill groundwater monitoring and reporting | ls | 225000 | 1 | 225000 | Onsite Projects
CAPITAL COSTS in 2022 | [9 empty] | Total | 30602000 |  | $25,629,000 | STEP E Cell dewatering well operation | ls | 50000 | 1 | 50000 | RACER |  | Post-Closure Care for New Landfill | ls | 91000 | 1 | 91000
Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value | [7 empty] | STEP Old Clearwell dewatering well operation | ls | 50000 | 1 | 50000 | RACER |  |  |  |  | Total | 316000 |  | 257000
Permit/Design New Landfill | ls | 333000 | 1 | 333000 | Onsite Projects |  | CAPITAL COSTS in 2028 | [6 empty] | MNA demonstration studies | ls | 30000 | 1 | 30000
Design relocation of ash from SOEP to New LF | ls | 133000 | 1 | 133000 | Onsite Projects |  | Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value | PRB Feasibility Studies | ls | 30000 | 1 | 30000 |  |  | ANNUAL OPERATION AND MAINTENANCE COSTS in 2053
Design relocation of ash from STEP to New LF | ls | 133000 | 1 | 133000 | Onsite Projects |  | Operate New Landfill | ls | 731000 | 1 | 731000 | Onsite Projects |  |  |  |  | Total | 597000 |  | 1142000 | Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value
Prepare Unit Closure Plan for New Landfill | ls | 50000 | 1 | 50000 |  |  | Relocate Ash from STEP E to New Landfill | ls | 33081000 | 1 | 33081000 | Onsite Projects | [8 empty] | SOEP/STEP and new landfill groundwater monitoring and reporting | ls | 225000 | 1 | 225000 | Onsite Projects
Decommission Units 1 & 2 Scrubber Pipeline/ North 1AD Drain Pond | ls | 100000 | 1 | 100000 | Onsite Projects; Return Pipeline may be re-purposed to convey SOEP/STEP dewatering water and New Landfill leachate |  | Relocate Ash from STEP Old Clearwell to New Landfill | ls | 3403000 | 1 | 3403000 | Onsite Projects |  | ANNUAL OPERATION AND MAINTENANCE COSTS from 2024 to 2025 | [6 empty] | Institutional Controls / Point of Use Controls | ls | 50000 | 1 | 50000
|  |  | Total | 749000 |  | $727,000 | Close New Landfill | ls | 5301000 | 1 | 5301000 | Onsite Projects |  | Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value | Post-Closure Care for New Landfill | ls | 91000 | 1 | 91000
[10 empty] | Total | 42516000 |  | $34,569,000 | SOEP/STEP and new landfill groundwater monitoring and reporting, and freshwater flushing/capture system maintenance | ls | 387000 | 1 | 387000 | Onsite Projects |  |  |  |  | Total | 366000 |  | 142000
CAPITAL COSTS in 2023 | [13 empty] | STEP A Cell dewatering well operation | ls | 50000 | 1 | 50000 | RACER
Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value | CAPITAL COSTS in 2029 | [6 empty] | STEP E Cell dewatering well operation | ls | 50000 | 1 | 50000 | RACER |  | ANNUAL OPERATION AND MAINTENANCE COSTS in 2054
Permit/Design New Landfill | ls | 333000 | 1 | 333000 | Onsite Projects |  | Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value | STEP Old Clearwell dewatering well operation | ls | 50000 | 1 | 50000 | RACER |  | Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value
Design relocation of ash from SOEP to New LF | ls | 133000 | 1 | 133000 | Onsite Projects |  | Operate New Landfill | ls | 731000 | 1 | 731000 | Onsite Projects |  |  |  |  | Total | 537000 |  | 969000 | New landfill groundwater monitoring and final remedy performance evaluation | ls | 45000 | 1 | 45000
Design relocation of ash from STEP to New LF | ls | 133000 | 1 | 133000 | Onsite Projects |  | STEP Main Dam Removal Construction | ls | 6455000 | 1 | 6455000 | Onsite Projects | [8 empty] | Post-Closure Care for New Landfill | ls | 91000 | 1 | 91000
Prepare Facility Closure Plan for New Landfill | ls | 50000 | 1 | 50000 |  |  | Relocate 230 kV Transmission Line - SOEP Main Dam | ls | 1250000 | 1 | 1250000 |  |  | ANNUAL OPERATION AND MAINTENANCE COSTS from 2026 to 2030 | [9 empty] | Total | 136000 |  | 51000
Dewater, Decommission and Remove Liner for STEP B Cell | ls | 1550000 | 1 | 1550000 | Onsite Projects; $500,000 included in Financial Assurance for converting STEP B Cell for post closure stormwater management |  | Close New Landfill | ls | 5301000 | 1 | 5301000 | Onsite Projects |  | Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value
Design Closure of STEP D Cell | ls | 300000 | 1 | 300000 | Onsite Projects |  |  |  |  | Total | 13737000 |  | $10,844,000 | SOEP/STEP and new landfill groundwater monitoring and reporting, and freshwater flushing/capture system maintenance | ls | 387000 | 1 | 387000 | Onsite Projects |  | ANNUAL OPERATION AND MAINTENANCE COSTS from 2055 to 2061
Dewater, Decommission and Remove Liner for STEP D Cell | ls | 2371000 | 1 | 2371000 | Onsite Projects | [11 empty] | Total | 387000 |  | 1575000 | Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value
|  |  | Total | 4870000 |  | $4,590,000 | CAPITAL COSTS in 2030 | [13 empty] | New landfill groundwater monitoring | ls | 25000 | 1 | 25000
[7 empty] | Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value | [7 empty] | Post-Closure Care for New Landfill | ls | 91000 | 1 | 91000
CAPITAL COSTS in 2024 | [6 empty] | Design/Permit/Plan/Install Freshwater Flushing Pilot Test and Full-Scale System | ls | 2250000 | 1 | 2250000 | Onsite Projects/RACER; install after dewatering for removal is complete | [11 empty] | Total | 116000 |  | 272000
Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value | Design/Permit/Plan/Install 25 New Vertical Injection Wells (IW1-IW11, IW16, IW24-IW27, IW29-IW32, IW34, IW36, IW38, IW40, IW43) | well | 30000 | 25 | 750000 | RACER; install after dewatering for removal is complete
Construct Liner for New Landfill Cell 1 | ls | 6029000 | 1 | 6029000 | Onsite Projects |  | Design/Permit/Plan/Install 11 New Vertical Injection Wells (IW12-IW15, IW17-IW23) | well | 30000 | 11 | 330000 | RACER; install after dewatering for removal is complete | [12 empty] | Total Capital $173,494,000 |  | Total Present Value Capital $145,459,000
|  |  | Total | 6029000 |  | $5,517,000 | Design/Permit/Plan/Install 17 New Vertical Capture Wells (w14-w18, w21-w32) | well | 30000 | 17 | 510000 | RACER | [12 empty] | Total O&M $18,356,000 |  | Total Present Value O&M $11,600,000
[7 empty] | Operate New Landfill | ls | 731000 | 1 | 731000 | Onsite Projects | [12 empty] | TOTAL $191,850,000 |  | TOTAL PRESENT VALUE $157,059,000
CAPITAL COSTS in 2025 | [6 empty] | SOEP Main Dam Removal Construction | ls | 4511000 | 1 | 4511000 | Onsite Projects | [8 empty] | Notes:
Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value | Place STEP backfill above modeled groundwater | ls | 665000 | 1 | 665000 | Onsite Projects | [8 empty] | BOLD ITALICS MDEQ provided conditional approval of the remedial actions shown in bold italics in a letter dated 8 June 2020. The conditionally approved remedy components were included in the preferred RAA (Alternative 5) identified in the Part 1 Report (Geosyntec, 2019d). Talen Montana has provided financial assurance for the conditionally approved remedy components.
Operate New Landfill | ls | 731000 | 1 | 731000 | Onsite Projects |  | Close New Landfill | ls | 5301000 | 1 | 5301000 | Onsite Projects
Construct Liner for New Landfill Cell 2 | ls | 6029000 | 1 | 6029000 | Onsite Projects |  |  |  |  | Total | 15048000 |  | $11,533,000
Relocate Ash from SOEP to New Landfill (No backfill) | ls | 19499000 | 1 | 19499000 | Onsite Projects | [15 empty] | 1. Costs for project management and construction management are included. For construction activities, construction quality assurance (CQA) is assumed to be five percent of the total construction cost, which is included in this table.
|  |  | Total | 26259000 |  | $23,331,000 | CAPITAL COSTS in 2031 | [13 empty] | 2. A discount factor of 3% was used to calculate the present value of the total cost per year for the range of years in 2021 dollars.
[7 empty] | Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value | [7 empty] | 3. RACER® Remedial Action Cost Engineering and Requirements (AECOM, October 2104).
[7 empty] | Close New Landfill | ls | 5301000 | 1 | 5301000 | Onsite Projects | [8 empty] | 4. The dewatering systems for STEP A Cell, E Cell, and Old Clearwell are planned to be installed in 2020. Capital costs for design and installation of those dewatering systems are essentially complete and therefore are not included in this cost estimate. This cost estimate presents the capital and annual operation and maintenance costs for 5 years.
[10 empty] | Total | 5301000 |  | $3,944,000

## Units 3&4 Alternative 4
| TABLE 7-5 | [7 empty] | TABLE 7-5 | [6 empty] | TABLE 7-5 | [6 empty] | TABLE 7-5
| COST ESTIMATE FOR REMEDIAL ACTION ALTERNATIVE 4 | [7 empty] | COST ESTIMATE FOR REMEDIAL ACTION ALTERNATIVE 4 | [6 empty] | COST ESTIMATE FOR REMEDIAL ACTION ALTERNATIVE 4 | [6 empty] | COST ESTIMATE FOR REMEDIAL ACTION ALTERNATIVE 4
| REVISED UNITS 3 && 4 EHP REMEDY EVALUATION | [7 empty] | REVISED UNITS 3 && 4 EHP REMEDY EVALUATION | [6 empty] | REVISED UNITS 3 && 4 EHP REMEDY EVALUATION | [6 empty] | REVISED UNITS 3 && 4 EHP REMEDY EVALUATION
| Updated 10/26/21 | [7 empty] | Updated 10/26/21 | [6 empty] | Updated 10/26/21 | [6 empty] | Updated 10/26/21
| Colstrip Steam Electric Station | [7 empty] | Colstrip Steam Electric Station | [6 empty] | Colstrip Steam Electric Station | [6 empty] | Colstrip Steam Electric Station
| Colstrip, Montana | [7 empty] | Colstrip, Montana | [6 empty] | Colstrip, Montana | [6 empty] | Colstrip, Montana
CAPITAL COSTS in 2021 | [6 empty] | CAPITAL COSTS in 2039 | [6 empty] | ANNUAL OPERATION AND MAINTENANCE COSTS from 2025 | [6 empty] | ANNUAL OPERATION AND MAINTENANCE COSTS in 2051
Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value | Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value | Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value | Item | Unit |  | Quantity | Cost Per Year | Notes | Present Value
Design closure for EHP Cells | ls | 600000 | 1 | 600000 | Done in 2021 |  | Construct EHP Capture Well Treatment System & Solids Disposal Area | ls |  | 1 | 0 | Covered in Plantsite RE |  | EHP Groundwater Monitoring/Capture System Maintenance | ls | 475000 | 1 | 475000 |  |  | EHP Groundwater Monitoring | ls | 175000 | 1 | 175000
Close EHP D/E Cells | ls | 7900000 | 1 | 7900000 | Done in 2021 |  |  |  |  | Total | 0 |  | $ | EHP Forced Evaporation System O&M | ls | 400000 | 1 | 400000 | Added to reflect system operation |  | Post Closure Care - EHP B Cell | ls | 54000 | 1 | 54000
Injection Wells | [13 empty] | In Situ Flushing System Operation and Maintenance | ls | 300000 | 1 | 300000 | RACER |  | Post Closure Care - EHP D/E Cell | ls | 39200 | 1 | 39200
Design and install two (2) vertical injection wells in clinker/McKay inside EHP cutoff wall | well | 78000 | 2 | 156000 | Done in 2021 |  | CAPITAL COSTS in 2040 | [6 empty] | Maintain horizontal injection/capture wells beneath EHP | well | 66700 | 3 | 200100 |  |  | Post Closure Care - EHP C Cell | ls | 74900 | 1 | 74900 | C Cell closed in 2025, PCC starts in 2026
Design and install two (2) vertical injection wells in shallow/middle Sub-McKay inside EHP cutoff wall | well | 176000 | 2 | 352000 | Done in 2021 |  | Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value | Post Closure Care - South Portion of EHP A Cell | ls | 23100 | 1 | 23100 |  |  | Post Closure Care - EHP J-1 Cell | ls | 57100 | 1 | 57100
Design and install two (2) vertical injection wells in middle Sub-McKay inside EHP cutoff wall | well | 220000 | 2 | 440000 | Done in 2021 |  | Design Closure for EHP G-1 Cell | ls |  | 1 | 0 | Done in 2021 |  | Post Closure Care - EHP B Cell | ls | 54000 | 1 | 54000 |  |  | Post Closure Care - EHP G-1 Cell | ls | 55000 | 1 | 55000 | G-1 Cell closed in 2041, PCC starts in 2042
Design and install twenty-nine (29) vertical injection wells in shallow Sub-McKay outside EHP cutoff wall | well | 146000 | 29 | 4234000 | Done in 2021 |  | Close North Portion of EHP A Cell for post-closure stormwater mgmt. | ls | 250000 | 1 | 250000 |  |  | Post Closure Care - EHP D/E Cell | ls | 39200 | 1 | 39200 | [5 empty] | Total | 455200 |  | $187,542
Injection System | [6 empty] | Close EHP F Cell for post-closure stormwater mgmt. | ls | 500000 | 1 | 500000 |  |  | Post Closure Care - EHP C Cell (closed in 2025) | ls |  | 1 | 0 | C Cell closed in 2025, PCC starts in 2026
Design in situ flushing system | ls | 500000 | 1 | 500000 | Done in 2021 |  | Close EHP H Cell for post-closure stormwater mgmt. | ls | 500000 | 1 | 500000 | [5 empty] | Total | 1491400 |  | $1,324,363 | ANNUAL OPERATION AND MAINTENANCE COSTS in 2052
|  |  | Total | 14182000 |  | $ | Close EHP Scrubber/Return Pipelines & Drain Pits #3 and #51 | ls | 190000 | 1 | 190000 | [9 empty] | Item | Unit |  | Quantity | Cost Per Year | Notes | Present Value
[10 empty] | Total | 1440000 |  | $820,800 | ANNUAL OPERATION AND MAINTENANCE COSTS from 2026-2028 | [6 empty] | EHP Groundwater Monitoring | ls | 175000 | 1 | 175000
CAPITAL COSTS in 2022 | [13 empty] | Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value | Post Closure Care - EHP B Cell | ls | 54000 | 1 | 54000
Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value | CAPITAL COSTS in 2041 | [6 empty] | EHP Groundwater Monitoring/Capture System Maintenance | ls | 475000 | 1 | 475000 | increased to reflect O&M costs |  | Post Closure Care - EHP C Cell | ls | 74900 | 1 | 74900 | C Cell closed in 2025, PCC starts in 2026
Close EHP B Cell | ls | 4599000 | 1 | 4599000 | Closure moved up to 2022, $1.5M of liner material purchased in 2021 |  | Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value | EHP Forced Evaporation System O&M | ls | 400000 | 1 | 400000 | Added to reflect system operation |  | Post Closure Care - EHP J-1 Cell | ls | 57100 | 1 | 57100
Injection Wells | [6 empty] | Close EHP C-1 Cell | ls |  | 1 | 0 | C-1 Cell will not be required, C Cell closed in 2025 |  | In Situ Flushing System Operation and Maintenance | ls | 300000 | 1 | 300000 |  |  | Post Closure Care - EHP G-1 Cell | ls | 55000 | 1 | 55000 | G-1 Cell closed in 2041, PCC starts in 2042
Design and install Horizontal Capture Well in Sub-McKay beneath EHP | well | 1467000 | 1 | 1467000 |  |  | Close EHP G-1 Cell | ls | 8063000 | 1 | 8063000 | Closure cost adjusted to reflect 2021 Closure Design work |  | Maintain horizontal injection/capture wells beneath EHP | well | 22300 | 3 | 66900 | decreased to reflect O&M costs |  |  |  |  | Total | 416000 |  | $166,400
Injection System | [9 empty] | Total | 8063000 |  | $4,466,902 | Post Closure Care - South Portion of EHP A Cell | ls | 23100 | 1 | 23100
Install in situ flushing system | ls | 4533000 | 1 | 4533000 | Updated to reflect work done in 2021 | [8 empty] | Post Closure Care - EHP B Cell | ls | 54000 | 1 | 54000 |  |  | ANNUAL OPERATION AND MAINTENANCE COSTS in 2053
|  |  | Total | 10599000 |  | $10,291,629 | CAPITAL COSTS in 2051 | [6 empty] | Post Closure Care - EHP D/E Cell | ls | 39200 | 1 | 39200 |  |  | Item | Unit |  | Quantity | Cost Per Year | Notes | Present Value
[7 empty] | Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value | Post Closure Care - EHP J-1 Cell (closed in 2028) | ls |  | 1 | 0 | J-1 Cell closed I 2028, PCC starts in 2029 |  | EHP Groundwater Monitoring | ls | 175000 | 1 | 175000
CAPITAL COSTS in 2023 | [6 empty] | Design EHP Capture System Treatment Solids Disposal Closure | ls |  | 1 | 0 | Covered in Plantsite RE |  | Post Closure Care - EHP C Cell | ls | 74900 | 1 | 74900 | C Cell closed in 2025, PCC starts in 2026 |  | Institutional Controls / Point of Use Controls | ls | 50000 | 1 | 50000
Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value |  |  |  | Total | 0 |  | $ |  |  |  | Total | 1433100 |  | $3,601,380 | Post Closure Care - EHP C Cell | ls | 74900 | 1 | 74900 | C Cell closed in 2025, PCC starts in 2026
Design EHP C Cell Closure | ls | 0 | 1 | 0 | Done in 2021 | [15 empty] | Post Closure Care - EHP J-1 Cell | ls | 57100 | 1 | 57100
Upgrade Liner System for EHP F Cell | ls | 0 | 1 | 0 | Moved to 2026 |  | CAPITAL COSTS in 2052 | [6 empty] | ANNUAL OPERATION AND MAINTENANCE COSTS from 2029-2039 | [6 empty] | Post Closure Care - EHP G-1 Cell | ls | 55000 | 1 | 55000 | G-1 Cell closed in 2041, PCC starts in 2042
|  |  | Total | 0 |  | $ | Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value | Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value |  |  |  | Total | 412000 |  | $159,856
[7 empty] | Close EHP Capture System Treatment Solids Disposal | ls |  | 1 | 0 | Covered in Plantsite RE |  | EHP Groundwater Monitoring/Capture System Maintenance | ls | 475000 | 1 | 475000 | increased to reflect O&M costs
CAPITAL COSTS in 2024 | [9 empty] | Total | 0 |  | $ | In Situ Flushing System Operation and Maintenance | ls | 300000 | 1 | 300000 |  |  | ANNUAL OPERATION AND MAINTENANCE COSTS in 2054
Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value | [7 empty] | Maintain horizontal injection/capture wells beneath EHP | well | 22300 | 3 | 66900 | decreased to reflect O&M costs |  | Item | Unit |  | Quantity | Cost Per Year | Notes | Present Value
Construct Partial Liner for EHP C Cell | ls |  | 1 | 0 | C Cell Closure moved to 2025 |  | ANNUAL OPERATION AND MAINTENANCE COSTS in 2020 | [6 empty] | Post Closure Care - South Portion of EHP A Cell | ls | 23100 | 1 | 23100 |  |  | Post Closure Care - EHP C Cell | ls | 74900 | 1 | 74900 | C Cell closed in 2025, PCC starts in 2026
Construct Partial Closure for EHP C Cell | ls |  | 1 | 0 | C Cell Closure moved to 2025 |  | Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value | Post Closure Care - EHP B Cell | ls | 54000 | 1 | 54000 |  |  | Post Closure Care - EHP J-1 Cell | ls | 57100 | 1 | 57100
Close EHP G Cell | ls | 5294000 | 1 | 5294000 | Closure cost adjusted to reflect 2021 Closure Design work |  | EHP Groundwater Monitoring/Capture System Maintenance | ls | 295000 | 1 | 295000 | Done in 2020 |  | Post Closure Care - EHP D/E Cell | ls | 39200 | 1 | 39200 |  |  | Post Closure Care - EHP G-1 Cell | ls | 55000 | 1 | 55000 | G-1 Cell closed in 2041, PCC starts in 2042
Construct Liner System for EHP G-1 Cell | ls | 3530000 | 1 | 3530000 | Closure cost adjusted to reflect 2021 Closure Design work |  | EHP Forced Evaporation System O&M | ls | 300000 | 1 | 300000 | Done in 2020 |  | Post Closure Care - EHP J-1 Cell | ls | 57100 | 1 | 57100 | [5 empty] | Total | 187000 |  | $70,499
Design closure for EHP J-1 Cell | ls |  | 1 | 0 | Done in 2021 |  | Post Closure Care - South Portion of EHP A Cell | ls | 23100 | 1 | 23100 | Done in 2020 |  | Post Closure Care - EHP C Cell | ls | 74900 | 1 | 74900 | C Cell closed in 2025, PCC starts in 2026
|  |  | Total | 8824000 |  | $8,073,960 |  |  |  | Total | 618100 |  | $ |  |  |  | Total | 1090200 |  | $ | ANNUAL OPERATION AND MAINTENANCE COSTS in 2055
[21 empty] | Item | Unit |  | Quantity | Cost Per Year | Notes | Present Value
CAPITAL COSTS in 2025 | [6 empty] | ANNUAL OPERATION AND MAINTENANCE COSTS in 2021 | [6 empty] | ANNUAL OPERATION AND MAINTENANCE COSTS from 2040 to 2041 | [6 empty] | Post Closure Care - EHP C Cell | ls | 74900 | 1 | 74900 | C Cell closed in 2025, PCC starts in 2026
Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value | Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value | Item | Unit |  | Quantity | Cost Per Year | Notes | Present Value | Post Closure Care - EHP J-1 Cell | ls | 57100 | 1 | 57100
Close EHP J-1 Cell | ls |  | 1 | 0 | J-1 Cell Closure moved to 2028 (expected capacity of J-1 Cell) |  | EHP Groundwater Monitoring/Capture System Maintenance | ls | 375000 | 1 | 375000 | Done in 2021 |  | EHP Groundwater Monitoring/Capture System Maintenance | ls | 475000 | 1 | 475000 |  |  | Post Closure Care - EHP G-1 Cell | ls | 55000 | 1 | 55000 | G-1 Cell closed in 2041, PCC starts in 2042
Close EHP C Cell | ls | 11644000 | 1 | 11644000 | Closure cost adjusted to reflect 2021 Closure Design work |  | EHP Forced Evaporation System O&M | ls | 300000 | 1 | 300000 | Done in 2021 |  | EHP Groundwater Capture Wastewater Treatment | ls | 1500000 | 1 | 1500000 | [5 empty] | Total | 187000 |  | $7,938,245
|  |  | Total | 11644000 |  | $10,339,872 | Maintain horizontal injection/capture wells beneath EHP | well | 66700 | 3 | 200100 | Done in 2021 |  | In Situ Flushing System Operation and Maintenance | ls | 300000 | 1 | 300000
[7 empty] | EHP F Cell Liner Repair | ls | 250000 | 1 | 250000 | Done in 2021 |  | Maintain horizontal injection/capture wells beneath EHP | well | 22300 | 3 | 66900 | decreased to reflect O&M costs |  | ANNUAL OPERATION AND MAINTENANCE COSTS from 2056 to 2058
CAPITAL COSTS in 2026 | [6 empty] | Post Closure Care - South Portion of EHP A Cell | ls | 23100 | 1 | 23100 | Done in 2021 |  | Post Closure Care - South Portion of EHP A Cell | ls | 23100 | 1 | 23100 |  |  | Item | Unit |  | Quantity | Cost Per Year | Notes | Present Value
Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value | MNA Demonstration Studies | ls | 30000 | 1 | 30000 | Done in 2021 |  | Post Closure Care - EHP B Cell | ls | 54000 | 1 | 54000 |  |  | Post Closure Care - EHP J-1 Cell | ls | 57100 | 1 | 57100
Upgrade Liner System for EHP F Cell | ls | 14454000 | 1 | 14454000 | Liner System upgrade cost adjusted based on 2021 Design work | $12,473,802 | PRB Feasibility Studies | ls | 30000 | 1 | 30000 | Done in 2021 |  | Post Closure Care - EHP D/E Cell | ls | 39200 | 1 | 39200 |  |  | Post Closure Care - EHP G-1 Cell | ls | 55000 | 1 | 55000 | G-1 Cell closed in 2041, PCC starts in 2042
|  |  | Total | 14454000 | [5 empty] | Total | 1208200 |  | $ | Post Closure Care - EHP C Cell | ls | 74900 | 1 | 74900 | C Cell closed in 2025, PCC starts in 2026 |  |  |  |  | Total | 112100 |  | $68,442
[14 empty] | Post Closure Care - EHP J-1 Cell | ls | 57100 | 1 | 57100
CAPITAL COSTS in 2028 | [6 empty] | ANNUAL OPERATION AND MAINTENANCE COSTS in 2022 | [9 empty] | Total | 2590200 |  | $2,911,385 | ANNUAL OPERATION AND MAINTENANCE COSTS from 2059 to 2071
Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value | Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value | [7 empty] | Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value
Design and install one (1) new vertical capture well in McKay inside EHP cutoff wall | well | 39000 | 1 | 39000 |  |  | EHP Groundwater Monitoring/Capture System Maintenance | ls | 475000 | 1 | 475000 | increased to reflect O&M costs |  | ANNUAL OPERATION AND MAINTENANCE COSTS from 2042 to 2047 | [6 empty] | Post Closure Care - EHP G-1 Cell | ls | 55000 | 1 | 55000 | G-1 Cell closed in 2041, PCC starts in 2042
Design and install one (1) new vertical capture well in Sub-McKay inside EHP cutoff wall | well | 88000 | 1 | 88000 |  |  | EHP Forced Evaporation System O&M | ls | 409000 | 1 | 409000 | increased to reflect O&M costs |  | Item | Unit |  | Quantity | Cost Per Year | Notes | Present Value |  |  |  | Total | 55000 |  | $195,965
Close EHP J-1 Cell | ls | 8919000 | 1 | 8919000 | Closure moved to 2028 (expected capacity of J-1 Cell). Closure cost adjusted to reflect 2021 Closure Design work |  | In Situ Flushing System Operation and Maintenance | ls | 300000 | 1 | 300000 |  |  | EHP Groundwater Monitoring/Capture System Maintenance | ls | 475000 | 1 | 475000
|  |  | Total | 9046000 |  | $7,354,398 | Maintain horizontal injection/capture wells beneath EHP | well | 22300 | 3 | 66900 | decreased to reflect O&M costs |  | EHP Groundwater Capture Wastewater Treatment | ls | 1500000 | 1 | 1500000 | [6 empty] | Total Capital $64,070,000 |  | Total Present Value Capital $53,821,363
[7 empty] | Post Closure Care - EHP D/E Cell | ls | 39200 | 1 | 39200 |  |  | In Situ Flushing System Operation and Maintenance | ls | 300000 | 1 | 300000 | [6 empty] | Total O&M $51,992,100 |  | Total Present Value O&M $31,632,140
CAPITAL COSTS in 2037 | [6 empty] | Post Closure Care - South Portion of EHP A Cell | ls | 23100 | 1 | 23100 |  |  | Maintain horizontal injection/capture wells beneath EHP | well | 22300 | 3 | 66900 | decreased to reflect O&M costs | [5 empty] | TOTAL $116,062,100 |  | TOTAL PRESENT VALUE $85,453,503
Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value | MNA Demonstration Studies | ls | 30000 | 1 | 30000 |  |  | Post Closure Care - South Portion of EHP A Cell | ls | 23100 | 1 | 23100 |  |  | Notes:
Design EHP Capture Well Treatment System & Solids Disposal Area (covered in Plantsite RE) | ls |  | 1 | 0 |  |  | PRB Feasibility Studies | ls | 30000 | 1 | 30000 |  |  | Post Closure Care - EHP B Cell | ls | 54000 | 1 | 54000 |  |  | 1. Costs for project management and construction management are included.
|  |  | Total | 0 |  | $ |  |  |  | Total | 1373200 |  | $1,333,377 | Post Closure Care - EHP D/E Cell | ls | 39200 | 1 | 39200 |  |  | 2. A discount factor of 3% was used to calculate the present value of the total cost per year for the range of years in 2019 dollars.
[14 empty] | Post Closure Care - EHP C Cell | ls | 74900 | 1 | 74900 | C Cell closed in 2025, PCC starts in 2026
[7 empty] | ANNUAL OPERATION AND MAINTENANCE COSTS in 2023 | [6 empty] | Post Closure Care - EHP J-1 Cell | ls | 57100 | 1 | 57100
[7 empty] | Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value | Post Closure Care - EHP G-1 Cell | ls | 55000 | 1 | 55000 | G-1 Cell closed in 2041, PCC starts in 2042
[7 empty] | EHP Groundwater Monitoring/Capture System Maintenance | ls | 475000 | 1 | 475000 | increased to reflect O&M costs |  |  |  |  | Total | 2645200 |  | $7,938,245
[7 empty] | EHP Forced Evaporation System O&M | ls | 400000 | 1 | 400000 | Added to reflect system operation
[7 empty] | In Situ Flushing System Operation and Maintenance | ls | 300000 | 1 | 300000 |  |  | ANNUAL OPERATION AND MAINTENANCE COSTS in 2048
[7 empty] | Maintain horizontal injection/capture wells beneath EHP | well | 22300 | 3 | 66900 | decreased to reflect O&M costs |  | Item | Unit |  | Quantity | Cost Per Year | Notes | Present Value
[7 empty] | Post Closure Care - South Portion of EHP A Cell | ls | 23100 | 1 | 23100 |  |  | EHP Groundwater Monitoring/Capture System Maintenance | ls | 475000 | 1 | 475000
[7 empty] | Post Closure Care - EHP B Cell | ls | 54000 | 1 | 54000 |  |  | EHP Groundwater Capture Wastewater Treatment | ls | 1500000 | 1 | 1500000
[7 empty] | Post Closure Care - EHP D/E Cell | ls | 39200 | 1 | 39200 |  |  | In Situ Flushing System Operation and Maintenance | ls | 300000 | 1 | 300000
[7 empty] | MNA Demonstration Studies | ls | 30000 | 1 | 30000 |  |  | Maintain horizontal injection/capture wells beneath EHP | well | 22300 | 3 | 66900 | decreased to reflect O&M costs
[7 empty] | PRB Feasibility Studies | ls | 30000 | 1 | 30000 |  |  | Post Closure Care - EHP B Cell | ls | 54000 | 1 | 54000
[10 empty] | Total | 1418200 |  | $1,337,363 | Post Closure Care - EHP D/E Cell | ls | 39200 | 1 | 39200
[14 empty] | Post Closure Care - EHP C Cell | ls | 74900 | 1 | 74900 | C Cell closed in 2025, PCC starts in 2026
[7 empty] | ANNUAL OPERATION AND MAINTENANCE COSTS in 2024 | [6 empty] | Post Closure Care - EHP J-1 Cell | ls | 57100 | 1 | 57100
[7 empty] | Item | Unit | Unit Cost | Quantity | Cost Per Year | Notes | Present Value | Post Closure Care - EHP G-1 Cell | ls | 55000 | 1 | 55000 | G-1 Cell closed in 2041, PCC starts in 2042
[7 empty] | EHP Groundwater Monitoring/Capture System Maintenance | ls | 475000 | 1 | 475000 | [5 empty] | Total | 2622100 |  | $1,179,945
[7 empty] | EHP Forced Evaporation System O&M | ls | 300000 | 1 | 300000 | Added to reflect system operation
[7 empty] | In Situ Flushing System Operation and Maintenance | ls | 300000 | 1 | 300000 |  |  | ANNUAL OPERATION AND MAINTENANCE COSTS from 2049 to 2050
[7 empty] | Maintain horizontal injection/capture wells beneath EHP | well | 66700 | 3 | 200100 |  |  | Item | Unit |  | Quantity | Cost Per Year | Notes | Present Value
[7 empty] | Post Closure Care - South Portion of EHP A Cell | ls | 23100 | 1 | 23100 |  |  | EHP Groundwater Monitoring/Capture System Maintenance | ls | 475000 | 1 | 475000
[7 empty] | Post Closure Care - EHP B Cell | ls | 54000 | 1 | 54000 |  |  | EHP Groundwater Capture Wastewater Treatment | ls | 700000 | 1 | 700000
[7 empty] | Post Closure Care - EHP D/E Cell | ls | 39200 | 1 | 39200 |  |  | In Situ Flushing System Operation and Maintenance | ls | 300000 | 1 | 300000
[10 empty] | Total | 1391400 |  | $1,273,131 | Maintain horizontal injection/capture wells beneath EHP | well | 22300 | 3 | 66900 | decreased to reflect O&M costs
[14 empty] | Post Closure Care - EHP B Cell | ls | 54000 | 1 | 54000
[14 empty] | Post Closure Care - EHP D/E Cell | ls | 39200 | 1 | 39200
[14 empty] | Post Closure Care - EHP C Cell | ls | 74900 | 1 | 74900 | C Cell closed in 2025, PCC starts in 2026
[14 empty] | Post Closure Care - EHP J-1 Cell | ls | 57100 | 1 | 57100
[14 empty] | Post Closure Care - EHP G-1 Cell | ls | 55000 | 1 | 55000 | G-1 Cell closed in 2041, PCC starts in 2042
[17 empty] | Total | 1822100 |  | $1,568,828