## PC-45 Response
WUTC v Cascade Natural Gas Corp.
Docket UG-170929
Public Counsel
UG-170929
Request No. 45
Item |  |  | (a) | (b.1) | (b.2) | (c) |  | (d.1) | (d.2)
MPP-6 Line No. | Function | Funding Project - Description | (a) Actual In-Service Date (If Applicable) | Total Actual Cost Placed Into Service | Account No. | Estimated In-Service Date (If Applicable) | Account No. | Actual Costs Incurred to Date | Estimated Remaining Costs | Comments
1 | Gas Intangible | FP-101472 - UG-PIM Installation [WO 184928] | 2016-09-30 | 1230710.83 | 303
|  | FP-101472 - UG-PIM Installation Phase 2 [WO 240286] | 2017-09-30 |  | 303 |  |  | 91507.81 |  | As-Built not created yet, costs not yet capitalized
3 | Gas Intangible | FP-101510 - UG GMS PURCHASE SOFTWARE | 2015-08-01 | 1811291.09 | 303
6 | Gas Intangible | FP-200663 - UG-GIS Enhancements [WO 193912] | 2014-12-29 | 182264.72 | 303 |  | 303 | 287058.23
|  | FP-200663 - UG-GIS Enhancements Phase 2 [WO 219443] | 2015-12-31 | 153866.46
|  | FP-200663 - UG-GIS Enhancements Phase 3 [WO230865] | 2016-09-30 | 100771.91
|  | FP-200663 - UG-GIS Enhancements Phase 4 [WO 240788] | 2017-09-30 |  |  |  |  | 95184.92 |  | As-Built not created yet, costs not yet capitalized
8 | Gas Intangible | FP-302571 - UG-CC&B Upgrade to v2.4 [WO 226343] | 2017-07-31 |  | 303 |  |  | 240437.91 |  | As-Built not created yet, costs not yet capitalized
9 | Gas Intangible | FP-302579 - Upgrade CyberSecurity Environment [WO 220001] | 2015-12-31 | 86446.06 | 303
10 | Gas Intangible | FP-302616 - UG-Taleo-Human Capital Management [WO 215308] | 2015-01-09 | 59108.33 | 303
|  | FP-302616 - UG-Taleo-Human Capital Management Phase 2 [WO 219127] | 2015-12-31 | 53466.87
12 | Gas Intangible | FP-311939 - UG-PCAD Upgrade to v6.5 [WO 235887] | 2017-05-13 | 249173.22 | 303
13 | Gas Intangible | FP-315501 - UG-JDE Corporate Consolidation [No WO created yet] |  |  |  | 2018-12-31 | 303 |  |  | No dollars in "Working" version of budget
14 | Gas Intangible | FP-315524 - UG-PowerPlan Lease Module [No WO created yet] |  |  |  | 2017-12-31 | 303 | 8638.7
16 |  | Total Intangible Plant |  | 3927099.49 |  |  |  | 722827.57 | 0
30 | Gas Distribution | FP-101191 - MAIN-REINFORCE-WASHINGTON | N/A | 171683.68 | 376 | N/A | 376 | 244517.88 | 25886 | Blanket funding projects are used for the numerous small work orders that arise on a day to day basis. As such they are ongoing and do not have an in service date. Likewise costs are accumulated and capitalized on an ongoing basis to Completed Construction Not Classified, then to Plant In Service at Year end. Cost figures listed year are current year only.
31 | Gas Distribution | FP-101192 - MAIN-RELO-REPL-WASHINGTON | N/A | 881946.39 | 376 | N/A | 376 | 1144545.65 | 255042
33 | Gas Distribution | FP-101196 - R STA-RELO-REPL-WASHINGTON | N/A | 136374.79 | 378 | N/A | 378 | 158998.25 | 85480
36 | Gas Distribution | FP-101199 - STD M&R-RELO-REPL-WASHINGTON | N/A | 566711.52 | 385 | N/A | 385 | 672425.8 | 178722
38 | Gas Distribution | FP-101201 - IND M&R-REMOVE&REPL-WASHINGTON | N/A | 135572.07 | 385 | N/A | 385 | 153059.83 | 20030
41 | Gas Distribution | FP-101275 - SERV-RELO-REPL-WASHINGTON | N/A | 710319.16 | 380 | N/A | 380 | 1160368.84 | 47208
43 | Gas Distribution | FP-200122 - RP; R-58, ABERDEEN [WO 186757] | 2016-08-17 | 441031.3 | 378
|  | FP-200122 - RP; R-58, ABERDEEN [WO 186761] | 2017-08-28 | 200309.41 | 378
53 | Gas Distribution | FP-302369 - GB - GROUNDBED WASHINGTON | N/A | 90949.56 | 376 | N/A | 376 | 120703.49 | 68868 | See blanket explanation above.
55 | Gas Distribution | FP-302588 - HILDEBRAND BLVD 6" HP MAIN [WO 211999] | 2015-04-03 | 359692.66 | 376 | 2017-12-31 | 376 | 1524374
|  | FP-302588 - HILDEBRAND BLVD 6" HP MAIN [WO 212372] | 2014-07-30 | 31417.77 | 376
|  | FP-302588 - HILDEBRAND BLVD 6" HP MAIN [WO 218037] | 2015-04-03 | 21309.94 | 376
|  | FP-302588 - HILDEBRAND BLVD 6" HP MAIN [WO 219464] | 2016-09-28 | 1436854.1 | 376
|  | FP-302588 - HILDEBRAND BLVD 6" HP MAIN [WO 228843] | 2016-02-05 | 253280.64 | 376
|  | FP-302588 - HILDEBRAND BLVD 6" HP MAIN [WO 229467] |  |  |  | 2017-12-31 | 376 | 13896.12 | 7678.88
|  | FP-302588 - HILDEBRAND BLVD 6" HP MAIN [WO 241577] | 2017-03-29 | 150358.07 | 376
|  | FP-302588 - HILDEBRAND BLVD 6" HP MAIN [WO 243931] | 2017-08-31 | 439249.21 | 376
|  | FP-302588 - HILDEBRAND BLVD 6" HP MAIN [WO 245161] |  |  |  | Unknown | 378 | 22035.15 | 110000
|  | FP-302588 - HILDEBRAND BLVD 6" HP MAIN [WO 245219] | 2017-08-31 | 436056.2 | 376
|  | FP-302588 - HILDEBRAND BLVD 6" HP MAIN [WO 246199] | 2017-08-31 | 560781.41 | 376
58 | Gas Distribution | FP-302648 - SOUTHRIDGE GATE STATION [WO 213270] | 2017-08-31 | 1562843.61 | 303
|  | FP-302648 - SOUTHRIDGE GATE STATION [WO 214539] | 2016-04-28 | 917571.7 | 378
|  | FP-302648 - SOUTHRIDGE GATE STATION [WO 242221] | 2017-08-31 | 131123.84 | 303
60 | Gas Distribution | FP-302653 - BREMERTON R-64 REPLACE/RELOCATE [WO 240957] | 2017-08-11 | 87168.328 | 376
|  |  |  | 80463.072 | 378
62 | Gas Distribution | FP-302665 - RICHLAND 4" IP CANAL/HWY CROSSING [WO 217905] | 2016-12-31 | 430905.85 | 376
75 | Gas Distribution | FP-306995 - OTHELLO REYNOLDS RD REINFORCEMENT [WO 233792] | 2016-12-17 | 244166.4036 | 376
|  |  |  | 18378.1164 | 378
77 | Gas Distribution | FP-306999 - V-13 BREMERTON REPLACEMENT [WO 246015] | 2017-09-19 | 15214.6 | 376
78 | Gas Distribution | FP-307002 - V-9 ABERDEEN REPLACEMENT [WO 229157] | 2016-11-15 | 187933.92 | 376
81 | Gas Distribution | FP-309000 - 4 in Steel IP Bore Columbia Park [WO 217904] | 2017-02-03 | 171701.04 | 376
84 | Gas Distribution | FP-311354 - DEEP WELL GB - YAKIMA [WO 237061] | 2016-11-30 | 92075.03 | 376
85 | Gas Distribution | FP-311357 - DEEP WELL GB - ANACORTES [WO 237062] | 2016-12-20 | 122490.13 | 376
86 | Gas Distribution | FP-311358 - DEEP WELL GB - WALLA WALLA [WO 237063] | 2016-11-29 | 93065.38 | 376
89 | Gas Distribution | FP-312000 - 0-2 Terrace Heights [WO 235065] | 2017-03-14 | 57435.7 | 378
90 | Gas Distribution | FP-312005 - R-29 Nooksack [WO 233264] | 2016-09-28 | 78898.58 | 378
91 | Gas Distribution | FP-312007 - R-19 Kennewick [WO 240144] |  |  |  |  | 378 |  | 50553.78 | WO not yet submitted for approval. No WO estimate.
99 | Gas Distribution | FP-313143 - V-89; Wenatchee 8" isolation valve [WO 228931] | 2017-05-04 | 56821.87 | 376
101 | Gas Distribution | FP-313621 - FAMILY METER REPLACEMENT [WO 230725] | N/A | 516457.77 | 381 | N/A | 381 | 666648.69 | 188742 | See blanket explanation above.
103 | Gas Distribution | FP-314501 - Replace 844' of steel main [WO 236984] | 2016-12-27 | 131484.98 | 376
104 | Gas Distribution | FP-314643 - 2" STL MN, RE 2 REG STATIONS - BELL [WO 234242] | 2017-02-13 | 117194.78 | 376
105 | Gas Distribution | FP-314963 - MAOP RPL 8" ANACORTES - SEG. 18191 [NO WO] |  |  |  | Cancelled |  | 0 | 0
106 | Gas Distribution | FP-314964 - MAOP RPL 8" MARCH POINT - 11C1144-1 [WO 240631] |  |  |  | 2018-09-30 | 376 | 230692.74 | 3230577.66
109 | Gas Distribution | FP-315143 - 2000' 6" Southridge Blvd Kennewick [WO 235114] | 2017-03-21 | 261246.26 | 376
111 | Gas Distribution | FP-315222 - DEEP WELL GB - WENATCHEE [WO 247544] |  |  |  | 2017-12-15 | 376 | 19436.53 | 78344.83
113 | Gas Distribution | FP-315224 - DEEP WELL GB - SHELTON [WO 247543] |  |  |  | 2017-12-15 | 376 | 24343.72 | 74474.2
116 | Gas Distribution | FP-315575 - 2" STEEL MAIN - BELLINGHAM [WO 235847] | 2016-08-25 | 56596.03 | 376
118 | Gas Distribution | FP-315607 - RF; 6" STEEL HP MAIN, KENNWICK/RICH [WO 236820] | 2017-10-05 | 4427214.5 | 376
|  | FP-315607 - RF; 6" STEEL HP MAIN, KENNWICK/RICH [WO 241318] | 2017-06-21 | 368404.44 | 378
128 | Gas Distribution | FP-315671 - INSTALL MAIN WALLA WALLA [WO 239516] | 2016-12-28 | 115425.69 | 376
129 | Gas Distribution | FP-315678 - RE/REL 4" Main IN SUNNYSIDE [WO 239752] | 2017-10-19 | 19730.52 | 376
132 | Gas Distribution | FP-315709 - RP; ZILLAH 6" TRAN [WO 240748] | 2017-05-11 | 386079.56 | 367
133 | Gas Distribution | FP-315710 - YEW ST, PIPE REPLACEMENT [WO 240514] | 2017-03-08 | 317237.01 | 376
134 | Gas Distribution | FP-315712 - DEEP WELL GB 1 - BELLINGHAM [WO 240628] | 2017-11-13 | 117427.2
135 | Gas Distribution | FP-315713 - DEEP WELL GB 5 - BELLINGHAM [WO 240629] | 2017-06-05 | 113421.44 | 376
136 | Gas Distribution | FP-315714 - INSTALL 2" ST ARO BORE SHELTON [WO 240691] | 2017-03-23 | 170964.13 | 376
140 | Gas Distribution | FP-315741 - MN RPL; 8" Kitsap HP Line [WO 241345] | 2017-08-12 | -106127.01 | 376
151 | Gas Distribution | FP-315894 - 10,700 of 6" & 800' 4" Reinforce Pasco [WO 244825] |  |  |  | 2017-11-30 | 376 | 1229859.95 | 52764.14
|  | FP-315894 - 10,700 of 6" & 800' 4" Reinforce Pasco [WO 245092] |  |  |  | 2017-11-30 | 378 | 109524.74
158 |  | Total Distribution Plant |  | 18384912.35 |  |  |  | 7385906.64 | 4474371.49
173 | Gas General | FP-101285 - GP BUILDINGS - BELLINGHAM | N/A | 76458.68 | 390 | N/A | 390 | 76458.68
174 | Gas General | FP-101288 - GP TOOLS - BELLINGHAM | N/A | 9461.78 | 394 | N/A | 394 | 9461.78
176 | Gas General | FP-101359 - GP BUILDINGS - ABERDEEN | N/A | 2201.1 | 392 | N/A | 392 | 2201.1
177 | Gas General | FP-101362 - GP TOOLS - ABERDEEN | N/A | 5780.39 | 394 | N/A | 394 | 5780.39
186 | Gas General | FP-200661 - Data Center & Network Equipment | N/A | 62472.17 | 391 | N/A | 391 | 62472.17
187 | Gas General | FP-200662 - Personal Computers & Peripherals | N/A | 143095.96 | 391 | N/A | 391 | 143095.96
189 | Gas General | FP-311969 - Sensit Portable Methane Detectors [WO 233311] | 2016-06-22 | 70485.66 | 394
|  | FP-311969 - Sensit Portable Methane Detectors [WO 240254] |  |  |  | 2017-11-30 | 394 | 473303.31
191 | Gas General | FP-315865 - UG - ThoughtSpot Implementation Prj [WO 244841] |  |  |  | 2018-11-01 | 303 | 127654.7 | 156824.81
|  | Total Distribution Plant |  | 369955.74 |  |  |  | 900428.09 | 156824.81