## PC-DR-212 Attachment A
PC-DR-212 Attachment A
Long Lake Plant Upgrade
| Project Status | Project Start Date (Actual/Planned) | Project Close Date (Actual/Planned) | Component Budget (Actual/Planned) | Design 100% Deliverable | Bid Date | Planned Construction Start | Notes
LL HED Station Service Upgrade "2" | Design | Mar. 2017 | Q3 2025 | 4462566 | Feb 2023 | Sep 2022 | Aug 2023
LL Bridge Crane Upgrade | Completed/Closed | April. 2017 | Dec 2019 | 2354027.23
LL HED - Access Road Repaving | Completed/Closed | Jan. 2018 | July 2019 | 1128035.99
LL HED - Sewer System Upgrade | Completed/Closed | Jan. 2018 | Feb 2019 | 207855.28
LL Unit Mondernization - Unit 3 | Design | Jan. 2019 | Q3 2025 | 21418000 | June 2023 | May 2021 | Aug 2023
LL Facilities Upgrade - Phase 1 | Completed/Closed | June. 2019 | July 2020 | 557640.81
Long Lake HED Fac Upgrade - "Phase 2" | Completed/Closed | July. 2019 | Dec 2020 | 181797.18
LL HED Unit Tailrace Bulkhead | Completed/Closed | April. 2020 | Mar 2022 | 1291377.15 | May 2021 |  | July 2021
Unit 75480 - LL Forklift | Completed/Closed | Oct. 2020 | Dec 2020 | 124752.09
LL Unit Mondernization - Unit 4 | Not Started | Q2 2023 | Q2 2027 | 13350000 |  | May 2021
LL Unit Modernization - Unit 2 | Not Started | Q1 2025 | Q2 2028 | 12625000 |  | May 2021
LL Unit Modernization - Unit 1 | Not Started | Q1 2026 | Q2 2029 | 11500000 |  | May 2021
Station Service 1 | Not Started | Q1 2025 | Q2 2028 | 2400000 |  | Sep 2026
LL 6.9 kV Substation | Bid | Mar 2022 | Q3 2025 | 8000000 | Aug 2023 | Apr 2022,Oct 2023 | Mar 2024
LL 6.9 kV Substation GSU2 | Bid | Mar 2022 | Q3 2027 | 4000000 | Aug 2023 | Apr 2022 | Mar 2027
LL 6.9 kV Substation Spare GSU | Bid | Mar 2022 | Q4 2024 | 2500000 | Aug 2023 | Apr 2022 | N/A
Balance of Plant | Not Started | Q1 2024 | Q2 2027