## PC-DR-212 Attachment C
PC-DR-212 Attachment C
Saddle Mountain 230/115kV Station (New) Integration Project Phase 2
Site grading & Fencing drawings | Issued 7/24/2020 for Permitting, Revised & Issued 9/24/20 for construction | Site Grading started 10/19/20 - complete
Fence Install started 1/3/21 - complete
Control Enclosure drawings | Issued 2/19/21 for construction | Control enclosure started 4/5/21 - complete
Physical drawings | Issued 6/24/21 for construction | Physical work started 7/26/21 – in progress
Electrical drawings | Issued 12/14/21 for construction | Electrical work started 1/3/22 – in progress